## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
a0738baf-8475-4cb5-b2b5-3ae53e12cadb | checklist | Columns Checklist |  | Columns Checklist
c0787df2-9fbb-4e42-854f-0f06f6d0a013 | section | Columns
1e97d17f-6e03-4915-825f-1792a9215451 | checkpoint | Area accessible & ready
bcf13b0a-33e6-43a3-882e-0f2b553ad35f | checkpoint | Drawing references entered
f3bfeca5-4c28-5c94-9d42-ab0db2c56be0 | textbox | Architectural
c32e9b5d-2b9d-552d-bda2-776a3398b717 | textbox | Structural
69d55b08-6f24-5f18-8774-ad3488f86af9 | textbox | Other
7f6c8836-7c76-5378-a7f7-e5bf28e52d18 | textbox | Column No
f5d01870-e987-44d2-9ff9-4b6b05a77c88 | checkpoint | Current plans in use / Latest drawings checked and referenced
be00bfb3-650b-4384-9ada-fcdfa82d39cc | checkpoint | Survey points given for 2 points
f51bdc0d-a1ee-4976-823f-3e06ba0bfc89 | checkpoint | Datum RL supplied by surveyor, pour height marked
214bd956-cf2c-4747-954a-5c30ac853333 | checkpoint | Blockouts, couplers, cast-in elements installed
2afb8bba-097e-4b17-8262-a243f1827541 | signoff | Inspection from site engineer
2f293e09-647e-4ddc-9208-c6f3c6b88c13 | checkpoint | Column box cleaned & oiled
6e1d874b-ac47-49c9-b15a-acce3d229a63 | checkpoint | Placement of column box over cage
815e7736-6d95-44bb-9c97-c26e78f07eac | checkpoint | Bracing props secured
cf6adf9a-9826-4deb-af80-2843fffd5297 | checkpoint | Column plumbed
99982623-57ff-4d63-8c0b-63384c1dc900 | checkpoint | Correct class of finish
7ab58358-9480-41c4-b38f-bb14d343ec27 | checklist | Core Lids Checklist |  | Core Lids Checklist
c7319361-ff72-4ea8-85da-f3937e13c3b1 | section | Phase 1
a82ba777-c4f1-46fa-9916-da377517879d | checkpoint | Area accessible & ready
1f780f0b-a79c-442e-87f0-a99f7062c93e | checkpoint | Drawing references entered
f568880e-3a88-5ac4-ab72-e399f1f03700 | textbox | Architectural
67ab2d13-5620-5d08-bd4f-da22014f5b1e | textbox | Structural
0d31a0c4-31a0-5206-aad1-b14ca8d27c52 | textbox | Other
1269518f-43b4-49e7-8622-8035c985f31f | checkpoint | Materials used complies with design documentation
724af044-7879-4393-bab2-2708258489b8 | checkpoint | Datum point used & soffit RLs checked
78facd65-c67b-4592-9cf1-84a78861716a | checkpoint | Grids marked by builder
b6d2945a-5eb4-426d-87c7-b8b54c5cb92e | checkpoint | Surveyor points given for outside of building
1466bea7-2233-4eca-8eda-0ae2bde4a9f8 | checkpoint | Fillet & drip mould installed
7456ab35-5452-4e26-a119-a86345e15dc6 | checkpoint | Check set down position & RL
afbdc69b-21fb-45b0-9915-f0fe8c1105ae | checkpoint | Check penetrations installed
936240d3-c235-4fd9-9977-8ed55151d898 | checkpoint | Column blockouts installed
7d7db929-5260-465d-97b2-19f0e1cdcfba | section | Phase 2
9a5d7399-9f99-4328-ac8c-638ced0355d6 | checkpoint | Check back propping as per design
8393d61f-1af7-49c4-9a22-fee5c1e696dc | checkpoint | Blow off deck
3ac031a2-6e26-4bb0-a98e-e13f4c978867 | signoff | Do not commence concrete till all works agreed
9fe678e3-af33-44c1-91b3-b0fca7e16f60 | checkpoint | Engage external consultant (engineer inspection)
53cbb5e7-65ea-42d1-8967-c7a194b63f95 | checkpoint | Correct Class of Finish
af1bbc49-af6f-4540-9e06-eb933c3f9719 | checkpoint | Stripping, cleaning & materials removed
f9e8fa96-8439-4f60-ae61-7eff59d9474d | checklist | Daily Pre Start |  | Daily Pre Start
c9735250-2d2a-4d5d-9602-610355d454f4 | section | Details
a8f93ba0-ebf9-4ebb-ad2a-429900dbb3dc | checkpoint | Daily pre start meeting completed
1b0a2020-0dfe-5b19-895c-2d696ab5941e | textbox | Date
eb522840-bb65-5e6a-83b5-8f3928825e42 | textbox | Time
2ff91e96-f4d3-5ed2-a0fa-f305b8e1d4a2 | textbox | Location
4d784aab-f53b-5d5c-bb73-5911052eed1a | textbox | Supervisor / meeting leader
20019a0b-99dd-548c-8b42-fc139e8648a1 | textbox | Project Manager & Construction Supervisor attending
7707739a-9523-5a2d-9be6-3ac99e758569 | dropdown | Current weather | Rain, Wind
34ff35c6-e363-5fd2-90c6-f76da8075a8f | textbox | Temp
2f186a2f-2acd-553e-bc2c-6986d288d212 | dropdown | Forecast | Rain, Wind
44851f39-efbf-5011-a887-244e3e2d4d15 | textbox | Temp
e463acb4-860e-5221-bc2f-1c7983238e6d | button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
c0a012c2-5544-58cb-bc06-b81b8017d00f | button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
6578da22-507e-5dab-a83e-0beb73fd9a94 | textbox | Any issues from the previous day
ee7ed26d-b117-5089-b031-e5fb5a16e6f3 | button | Do you need to change SWMS | Yes, No
1248ffcb-a8eb-5a40-93c5-2c8b62f0ad4e | textbox | First aiders on site today
b7159a7c-f676-50ca-92ef-1c835cb6151a | textbox | Apprentice & who are they assigned to
56b34984-8fe0-5837-b244-9b66989a9cb1 | textbox | Apprentice & who are they assigned to
2ce923f9-a5c9-56da-9279-d5b34f3ddf13 | textbox | Apprentice & who are they assigned to
e3f11968-daee-5f8a-9864-7d6923916809 | textbox | Todays tasks / jobs
5cab7b74-87be-5211-8f1f-2ee96bf51594 | dropdown | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
d1d7ad86-6f80-524a-8550-f3f901f6fce3 | button | SWMS in place for all activities | Yes, No
bf430ea4-7bc3-5696-87e9-8bffdca2c5d7 | button | Hot works | Yes, No
5bdefafb-990c-5320-ae2d-bd5b42b28d23 | button | Excavation | Yes, No
f0beaf8c-eb7d-5b78-aed2-23f1a002689d | button | Ladder | Yes, No
a991c0a2-d583-5c5e-9063-2f82ec4895f9 | button | Core | Yes, No
6c7bc44c-c7bd-5b74-be5a-648e8d8e43de | button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
81f6df60-12c6-5cb8-8fce-53e545f219e4 | textbox | If yes, list the substances
ed38aabf-6d8c-501a-ad95-d9c8a24295c8 | textbox | Attendees
65468c7d-2163-43f7-bad4-ad433b2b00c9 | checklist | Deck Handover Checklist |  | Deck Handover Checklist
4b0d13c4-ccd7-4692-a478-1592b543b3c0 | section | Deck Handover
f305c4eb-1b4f-428f-bf52-b1b4ec7eae4c | checkpoint | Communication between all trades
aa31b38c-4f8b-49d3-9236-68aebe9a1e44 | checkpoint | Signage and barricades in place
aff00038-7fd2-4dbb-8dc5-9a9700587342 | checkpoint | Deck clean and clear of materials
cf680a60-ca76-4051-b0a5-803f24c09a2e | checkpoint | Loose materials are stacked and secure
65c3d583-9cb4-4b86-b12f-a2c1e3ab8123 | checkpoint | Any backpropping required to handle loads of reo and other equipment
7123757e-5d9f-4eb9-9225-2d2e3229c4d5 | checkpoint | Designated walkways established
a4620d02-828d-4d66-a361-0b506525e3fb | checkpoint | All loose materials removed from edge
526bc134-26c7-43c3-b108-8fed3fae813a | checkpoint | Are all penetrations covered and secured
7f086acf-aba2-4dbe-96d0-b7c62905d061 | checkpoint | Rubbish bin on Deck
1f93aca0-a6ee-4b81-93bb-fbaa3455596a | checkpoint | Perimeter Screens / Edge protection installed
2720e8db-1f27-4a4e-8f8a-66663dad9365 | checkpoint | Correct spacing of frames, props and timbers
170475e5-a56c-4230-bbc0-42343e7e837a | checkpoint | Correct joist and bearer sizes
d2b4a970-ac44-43aa-8c6b-9818ed27157e | checkpoint | Acceptable jack extensions
68c0f7df-5b07-4264-ba69-5d7bb04a1551 | checkpoint | Quality of materials
150f5243-ca70-4c43-965f-163fecb90f3a | checkpoint | Adequate bracing to ensure stability
6f80e519-049c-49bc-9af5-b8f32df35895 | signoff | Deck Handover signed off
d8d69edc-88fa-4fba-bcbf-6f018d63eeaf | checklist | Hoist |  | Hoist
2e478c8f-506a-46db-9e13-97b52499c86f | section | Install
d61505c5-5aac-49f4-9344-440822fa15b5 | checkpoint | Area accessible & ready to receive hoist
54635aef-6f77-5b51-a55e-4bf064be95ca | textbox | Hoist ID. Number
f8c0a9ef-9c45-4a09-b43e-a9f6e3e09424 | checkpoint | Adequate Crane or Franna to install (heaviest lift required 4.5 tonne)
ece45a30-9d18-525e-8e03-facb45a6ea61 | button | Copy of the Certificate of service and service history onsite | Yes, No
57809fa6-7ae0-5cd3-844a-aecd7d9f2b31 | textbox | Name and Number of Rigger
4ef4cf98-99e8-48ff-9b95-099ad3b32d91 | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
5d506d62-5088-4225-b82e-5e63ec0f9e79 | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
68f0adaf-ff7f-4b0c-8be2-de4096fc3d2d | checkpoint | Scaffolder on site to assist in edge protection if required
5c4469d4-6f71-4e0d-890b-c672f3a68716 | checkpoint | Signage in place
4152e18a-e903-5941-a05c-da0c478ae00b | button | 3 Phase power accessible and adequate circuit breaker 75 start Amps at power source | Yes, No
48106ee8-5ee1-495b-b93e-6ea7a07b4600 | checkpoint | Exclusion Zone around required area
522029f9-d174-41e3-be54-f1e723741e40 | checkpoint | WMS ready and signed on to
393ab6ab-1343-4b9e-b022-e6dbe6e9c4b9 | checkpoint | Platforms cleaned and clear from rubbish
cadd7da0-b613-4020-8756-b6080875e91c | checkpoint | All loose materials removed from edge
a58ed92d-26b7-4466-a4e1-b4d43ce97487 | checkpoint | Gates installed
bc650b72-f691-4ac3-bac8-83e93cd9681d | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
41740dec-9c9d-433f-8b64-db6995707f0a | checkpoint | Log book for hoist is onsite and in good condition
992e8342-4469-5a3f-8f2e-bcf183327c3f | button | Copy of Bosform commissioning sheet on site and completed | Yes, No
bc576065-ac29-4146-9aeb-39f751ea280b | section | Hoist Jump and Dismantle
a5cdba80-55cc-4670-877b-be9a5b6d1f3e | checkpoint | Ensure exclusion zones are in place
afd7dd80-20b2-44a7-a89c-7c5c674c1696 | checkpoint | Platforms cleaned and clear from rubbish
9bfba3b9-30aa-44d1-921c-a736c1b6f43e | checkpoint | All loose materials removed from edge
a8a016e1-3993-5e24-bb68-c2752a36e8b9 | textbox | Name and Number of Rigger
cc073e98-ac4f-43c4-b475-b11519eaaa0f | checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
7e650713-be27-434c-946a-547e55be6261 | checkpoint | Scaffolder on site to assist in edge protection if required
4819c514-3e81-5977-ad37-51d21902472e | textbox | Level Number to be Jumped to
e25c5f07-2155-463f-9e3b-1a4fb4e97816 | checkpoint | Gates installed on Level/s to be exposed once lifted
2fbb6686-7d8d-49e6-bed8-bf9a1d5daa13 | signoff | Confirm concrete strength MPA 25 has been reached at supporting level
7fd94a78-7f0a-4fd2-8941-ab21909e4eb0 | checkpoint | Signage in place
7ed5fca0-66b9-5c42-8c69-f04b1250dd6f | button | Hoist Screen installed if required | Yes, No
1e59130d-c9bf-47ab-8868-0aec3c5f15fc | signoff | Copy of Engineered Bracing plan for ties back to building on site and followed
6ceedc2d-ce28-46e8-9d5c-f2f46643d67d | checkpoint | Remove exclusion zones and barricades
ad0eca08-8089-4cc0-9ad7-0e2b0ed62a69 | checklist | Injury Form |  | Injury Form
ab838d14-e412-425b-97e9-073b1ca2913a | section | Details
74e5bdfd-4417-4290-a522-b2748000d8c7 | checkpoint | Injury form completed
d86ae906-5a6f-5bfb-a614-8bcfedc5fc1a | textbox | Date of incident
6bb8aa5e-4ef2-5ba8-bbfc-636722a9a18a | textbox | Time
ff3b95a2-b80c-5329-aa7e-fce87a9e32b0 | textbox | Site location of the accident / incident
4da9fde1-a88a-5d46-b4ed-c436307756a2 | textbox | Detail of how the accident / incident happened
dc425e86-21bb-5082-ba06-47dbb54c4294 | note | Details of injured person
2d431a1a-6bf0-5e8d-a66e-2c20a1dc7322 | textbox | First name
49d313a7-8a9a-5cfd-aa33-6aba2173e3a6 | textbox | Last name
321b57ae-b297-5a70-91f1-05c3748d1975 | textbox | DOB
3746439c-3eda-54a3-87c9-68a44b30a832 | textbox | Contact No
33e6cb9a-1f67-5603-9ddb-62f71883b902 | textbox | Address
b65b1645-b9eb-5ab8-a09e-31fd799fe76a | textbox | Company
e01baf64-62d3-5480-9a44-87b64b9574f0 | textbox | Trade
8df92cea-b6b5-50b3-b593-8cc393dbe727 | textbox | Date Inducted
6b3978d8-9b50-5db0-a721-b418c3fe3dd6 | dropdown | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
c7b0894f-046b-55ba-b831-6f6d38f16b88 | dropdown | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
693f68cd-1f4c-5b9a-a38d-434977f20f6f | dropdown | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
7d09573e-7330-5cad-9d62-43cbae493948 | textbox | Initial treatment given
7cf6be4f-c5a4-5dbb-a4da-1a85aeaf3468 | textbox | Was follow up treatment provided
70d972dd-2c7e-5ed9-b576-b69699983e7b | textbox | Medical centre / Doctor / Hospital attended
4fd109df-ca9f-5997-8d36-70163b39e9e4 | textbox | Date / time attended
c87e87c0-b80d-549e-9526-fc7c3e33aac6 | button | Regulator notified | Yes, No
0084306e-bddd-5eae-ae2c-b2fe7be0276a | note | Witness details
76a7659c-3774-5c3a-8951-028db920152c | textbox | Witness name & contact details
250485c0-8d70-5618-ba94-15c386d615e4 | textbox | Witness name & contact details
64e02937-58dd-5a47-b72e-76b8336a0d7d | dropdown | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
0f766511-dde4-52ed-8fec-cdb445783305 | textbox | Other
95e3b7a0-7edd-530b-ae0a-a3681800852e | note | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
fd6bbce6-84d2-44f3-9714-02e52ca7a865 | checkpoint | Signature of injured worker
6a6f4346-a4a4-4794-bcf2-866ad7e0c3ca | checkpoint | Person completing this form
24c99f4d-cfdf-47c5-9d9d-0747bf0f30e4 | checklist | Jump System / Climb Track Checklist |  | Jump System / Climb Track Checklist
1ba0f27d-d2d0-409e-b629-09d3fe37eefa | section | Pre Lift
9aa17f8c-3425-4ba3-981d-9cd6196fcd9a | checkpoint | Confirm concrete strength MPA 15 has been reached at connection points (Builder to supply)
d8e2b378-2ffd-4ceb-a176-aa6f1fbd99e0 | checkpoint | Signage in place (Stripping in progress/Jumping in progress/ No access)
a20b0e0a-2645-4cbb-8cb9-a43cc9a9fa87 | checkpoint | Exclusion Zone in place
79eab814-1476-492a-9c2e-48950847bc3a | checkpoint | Spotters in place on slab below jump (outside exclusion zone)
b4637c3f-3b74-4430-95a3-76645f21e12d | checkpoint | All Platforms cleaned and clear from rubbish
cf2b2854-f40e-48ae-8eb7-ce4b112844dc | checkpoint | All loose materials removed from edge
f24fa9b3-1719-4eed-a442-8cebba927d0d | checkpoint | Clear communication between team leaders and Crane crew (toolbox talk)
4e4155e6-d2c8-4799-be67-431f81030b71 | checkpoint | Ladders available and secured
9f0079fe-8444-4e2b-8c6a-bc0140ad6875 | checkpoint | Flipper systems lubricated
22a273b9-31ac-4b5a-8b19-09fd200fbc3e | checkpoint | Trailing Decks clean of debris
6d932035-c2ca-437c-bc7f-edcae47f05f3 | checkpoint | Trailing decks clear of protruding ferrals in walls above
890892e1-849a-4b0e-ac56-690224a28a4e | checkpoint | Check exclusion zones in pit below are in place
1a8cbfaa-4412-486b-8c06-e0d4e7cce99c | checkpoint | Plumber to check pipes to water cooler
43844050-9431-408a-a704-d51782f35744 | checkpoint | Transfer RL heights
c0c571ca-b302-4e30-8e47-2d8f696096f3 | section | Post Lift
425994cb-a6f4-4e7e-ab8f-f692540a8ac3 | checkpoint | Confirm connection points are secure and all engaged
5a57d9e6-4b2b-4400-ab93-9b038e13f10c | checkpoint | Confirm mesh secured to doors and penetrations
ab6533c3-90a4-4079-8217-c4b4e5f24ef3 | checkpoint | Signage in place
8f10a453-4700-445a-938f-df3eeccf7269 | checkpoint | Screens and mesh infills are in place and secure
7040d1a7-40fb-496a-8ce6-d5dc547d61c7 | checkpoint | Loose materials are stacked and secure each day
614bbd87-faaf-48ef-afe5-0a13ce416010 | checkpoint | Platforms cleaned and clear from rubbish
fd29b7a4-e920-47ff-80da-e1cada993c51 | checkpoint | All loose materials removed from edge
ff0cd2fc-baec-4c2c-a779-b0c44102924a | checkpoint | Loads on platforms not exceeded
ec325575-faa9-4968-af70-580210255346 | checkpoint | Ladders available and secured
35cfcc28-600f-4870-a1b1-9421bcb26f5a | checkpoint | Access is clear and marked
a7436236-d5d6-42ea-b6f6-d41b6ad492e2 | checkpoint | Power Board connected
96de9031-a4cf-4a31-8b1e-243b07d259f9 | checkpoint | Confirm ready for lift with all involved - Team Leaders
cc6c0914-1788-432e-9683-924d48a3565d | checklist | Progress Claim Checklists |  | Progress Claim Checklists
83ed67b6-ffef-4304-a2bf-df8bca38377e | section | Details
a46ae5e8-c505-4fd4-9c19-12b146e2ef28 | checkpoint | Please add Comments / Photos
5eaa5ba3-3d09-5db4-923a-0361b21b526a | dropdown | General | Site Establishment / Prefab, Systems, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning.
e6e2c5e4-7956-5ee1-a57f-53da9e9c560e | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
250c0041-d6f2-5c05-ae56-e7afe3396f2a | textbox | General Notes
71110506-40e7-45ad-9623-8b59ddd6f55e | checkpoint | Please add Comments / Photos
afcf510d-5337-5291-8ecc-03798f17ff67 | dropdown | Level | Below SOG, Basement 2, Basement 1, Ground, Mezz, 1, 2, 3 - 23, Roof Plant Deck
3c2722fb-9811-5963-bcc5-e39d72eda88b | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
86226c53-47a8-5761-84fe-4de16cc5bb92 | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
0325013b-fcb5-51bc-a47e-01dfebfaecd6 | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
8586ab43-3c80-5f96-90e1-466ed14a77fd | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
88a81ab0-3832-5a45-b267-38cf66a526e8 | textbox | General Notes
efc92bb0-7caa-449d-a0ed-c93c0aec7056 | checkpoint | Please add Comments / Photos
bb44fc46-7510-571c-ae4b-eb23e1176070 | dropdown | Level | Below SOG, Basement 2, Basement 1, Ground, Mezz, 1, 2, 3 - 23, Roof Plant Deck
edd33d5d-7636-5b83-8b41-c8c0ee1235c4 | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
5ff3a48b-5f8b-5d81-8da7-5bb0825ee797 | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
6cdae355-78a1-580d-aa65-23b5ee3699cb | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
362e0bb8-fbdc-56df-a9d6-fbbbe1f8a98c | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
ba039758-aae2-54f8-a321-587f7f800241 | textbox | General Notes
5759315f-b292-4abe-a834-d1aa165c9814 | checkpoint | Please add Comments / Photos
533e9db2-46ab-591c-b4d1-debaa9d9b634 | dropdown | Level | Below SOG, Basement 2, Basement 1, Ground, Mezz, 1, 2, 3 - 23, Roof Plant Deck
d06d61a4-e940-51ce-8615-eefe9ec0baee | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
af2c7e88-7709-597f-8673-cc45a54c8307 | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
524806ac-13b8-585d-80bd-16df60a0cbd0 | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
a26a4388-5708-5c13-8b36-a09e3ba8cba7 | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
f2275c33-1574-5a9a-b3ed-21338c7a034c | textbox | General Notes
43a63bcf-4873-4df8-86e9-9b674acd4dc6 | checkpoint | Please add Comments / Photos
670ca547-3c6e-5451-9b96-facd55184bd8 | dropdown | Level | Below SOG, Basement 2, Basement 1, Ground, Mezz, 1, 2, 3 - 23, Roof Plant Deck
a6061405-71aa-53b5-b987-1aadf6a62d9d | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
31665501-e414-5414-b92a-b9a666a78038 | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
cbfff4e3-cb6b-5e06-afde-43e54e7f2ac2 | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
68fb93f7-a652-5779-bb5b-dff2288cc5f0 | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
16e49f71-ccbb-5840-adbd-b9f3fb5d916c | textbox | General Notes
c5f9595b-1edf-4208-bc92-32fd574cc6ad | checkpoint | Please add Comments / Photos
72f10bf4-c8ed-5c42-8ad3-7c3ad6a9da79 | dropdown | Level | Below SOG, Basement 2, Basement 1, Ground, Mezz, 1, 2, 3 - 23, Roof Plant Deck
aa82f55a-ecfa-541e-bcb9-253d40830a09 | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
5cb117ac-722d-567a-a726-925fd0da808f | dropdown | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
5916beeb-048e-542f-8a66-3c6392712326 | dropdown | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
218283a1-c2d7-5c86-b8c1-aff07eda3669 | dropdown | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
9d0efa38-ca29-58bf-b3fa-6ff9a2c45c27 | textbox | General Notes
81ae24e8-01b3-4269-8b40-e154d39bb589 | checkpoint | Please add Comments / Photos
86a7b408-41bb-56e3-becd-cedf1a4c3dab | dropdown | Level | Below SOG, Basement 2, Basement 1, Ground, Mezz, 1, 2, 3 - 23, Roof Plant Deck
4bc43f8f-efb6-5cb8-89ea-8f5d47536ec3 | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
154de168-af67-540a-97cd-c1c85dd2fed7 | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
25fec53b-fe13-5f79-9279-6064d3ce0143 | textbox | General Notes
faf8a446-90a5-4a36-983f-72270f7d926c | checkpoint | Please add Comments / Photos
8e00b4a0-3dec-5cca-b414-e0a17f42a5e7 | dropdown | Level | Below SOG, Basement 2, Basement 1, Ground, Mezz, 1, 2, 3 - 23, Roof Plant Deck
c1f62968-9c6c-566f-9487-1a739bb286cb | dropdown | Description of Works | General, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Climb Trac / Climb System , Install & Removal of Systems. Supply of Screens, Install Jumping & Removal of Screens.
ceeb46ce-7820-5beb-a328-81c0c0d341ed | dropdown | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
b53e262b-7f77-56d1-afce-a78bcd513124 | textbox | General Notes
17d91142-7214-4701-929a-9c1810a2e30c | checklist | S.O.G Checklist |  | S.O.G Checklist
73eb885c-4941-418c-bece-813ca6e92269 | section | S.O.G
9095792f-6879-4cc6-838e-5c05380b34d1 | checkpoint | Area accessible & ready
b120429f-ab84-4172-ad50-6b0969343610 | checkpoint | Drawing references entered
c9d32f7e-1333-58ca-b1e8-bf28f3987da1 | textbox | Architectural
d6404bcd-0a1e-5dd1-9177-9c6b4d893533 | textbox | Structural
3cc72b12-2a33-5edc-b401-eaa5ad77d2e2 | textbox | Other
e96f9361-27a5-4623-8178-d691bdc16506 | checkpoint | Current plans in use
6e458ef8-475c-4368-aec9-15bc8193c3c0 | checkpoint | Survey points give for grids
e27fd0e7-fb00-4bb6-881a-c4da7b93ce94 | checkpoint | Surveyors points given for edge boards
164a1d0f-946a-4593-99e7-9ab4333692c3 | checkpoint | Datum RL supplied by surveyor
68c3d733-1c9a-4a98-84cd-12cfeabacb94 | checkpoint | Edge boards plumb & straight
535c88b0-1467-426b-b28a-42d6bc4934f5 | checkpoint | Step downs secure & correct RL
4fec5101-7c7c-40c9-a704-cc034c7d264a | checkpoint | Dowels installed on pour joins
ee4fc527-0be2-4e43-acac-1177c7044ed2 | checkpoint | Column blockouts installed
563ffae7-7c70-4547-9dd2-82e716f8c7e4 | checkpoint | Correct Class of Finish
b4baad11-85d0-4f62-b3d4-c28edd170a4c | checklist | Screens |  | Screens
9dca6a5f-7970-4638-8d42-4dadac6f397c | section | Pre Lift
b7154ba2-67d7-4662-9a3a-05114ecbce71 | checkpoint | Area accessible & ready
57f0acb1-8ea9-5f66-b98a-365c04d4a8b5 | textbox | Screen number
7800dc7c-c214-4ce2-a1c1-20c48592d37c | checkpoint | Confirm concrete strength MPA 25 has been reached at supporting level
4049d039-e6ff-4bda-9776-9ce4a72398a7 | checkpoint | Signage in place
7325ea66-41d0-4f03-8db4-df178aa6224b | checkpoint | Exclusion Zone with name and number of supervisor– Ground level and Slab level
f820e2df-49d4-49a0-9c94-82a858fb96ec | checkpoint | Spotters in place
21605d1a-9fe6-4147-8d1f-e89d1f4d77f3 | checkpoint | WMS ready and signed on to
fa14d313-1814-4241-9d5e-d45eece235d5 | checkpoint | Platforms cleaned and clear from rubbish
c3ed56c6-f173-42f3-9509-02d1472c2a1b | checkpoint | All loose materials removed from edge
e2957b78-c489-47eb-b296-9ac47fc16a07 | checkpoint | Edge protection installed on Level/s to be exposed once lifted
617d943a-2dcf-47ba-85fb-b81c6317bc48 | checkpoint | Deflector shields removed
4448a409-b520-4800-a2e9-cd2377932471 | checkpoint | Radio communication woking between screen crew
dcbe4de2-235a-494a-8b7d-625404208b06 | checkpoint | Hydraulic lifting Apparatus installed correctly if using lifter
ef71c52e-2699-4f74-950f-fce8d2913828 | checkpoint | Screen Free from Debris
79b26bc9-7c8e-400a-b8d4-b85d4cfc4acd | checkpoint | All wire infills detached
6ea5dd7e-663c-4677-ad45-643538347170 | checkpoint | Confirm ready for lift with all involved - Team Leader
7d197404-d005-4d86-999d-bcdfe118e978 | checkpoint | Work at heights permit completed - attach or take photo of permit
562b6ed1-aae7-4c7a-abc3-d9864e029ace | section | Post Lift
71bddbe0-77a6-41af-ae1a-540c64595955 | checkpoint | Ensure all gaps are closed
35742309-9614-48b3-ac97-97308c48b21d | checkpoint | Mesh to be install where required
5b3e7541-905b-4257-ab01-01ecab2821a0 | checkpoint | Double check all needles are secure and double nuts in place
56f84154-dd23-445e-95b9-a68ce794ced8 | checkpoint | Clean and clear area
361abbb3-2216-4e49-ad49-8828bc88a898 | checkpoint | Remove exclusion zones and barricades
add068a7-b259-4557-ad4e-fd6027ad41ea | checkpoint | Bar caps for protruding z bars
08657f98-3a6d-40f5-9b5e-8f8ca243e23d | checklist | Site Diary |  | Site Diary
c98ba115-51b5-4424-9271-840672559637 | section | Details
35edace5-42ab-482e-a677-99bfdb867183 | checkpoint | Areas of work accessible for the day
9b6d1139-8b5b-5700-be44-d57c8d733d3a | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
8e6d897b-081e-5c3e-a0be-2e512958a5f0 | textbox | Date
457a4a31-e54e-583d-99ef-55fcb0c2cad0 | textbox | Year
ffd09254-6420-5c32-942c-0b236c6b2b6c | textbox | Number of workers on site
3d1cb1ab-a877-592b-8fd4-906d5e159c4a | textbox | HSR on site today enter name
f86f4bdf-4890-50de-b13b-562c707001ab | textbox | First Aider on site today enter name
923cd34e-3e7d-57f1-99bf-7e59a873a7fa | textbox | Injury on site today enter name
2fba2b71-d0a8-4046-92e1-8c5deeb054d9 | checkpoint-no-value | Work area 1 details entered
3e2d157a-bd78-57b7-bc44-33fbe26d90a9 | textbox | Area
ca8893d9-f0c1-55ba-9856-cdb6c88c1965 | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
f5bfa5a9-9f05-5e18-86f3-f93dc0838a47 | textbox | Comments
0dfe9920-a7c1-41f9-b491-ddcd3acc167f | checkpoint-no-value | Work area 2 details entered
ee585ed1-ce6a-561d-9679-a4d6fc0df891 | textbox | Area
5bdf2407-bccb-5170-860e-40e69fe81bd0 | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
3c6084bf-bd4e-57f3-b475-e8f4725e98e5 | textbox | Comments
5f9ac6f1-04a9-4c73-a140-c2cc83510e99 | checkpoint-no-value | Work area 3 details entered
eb4545e0-2bbc-52b9-b4fa-5510bc00c7a1 | textbox | Area
07111583-61f3-547c-b77b-b90a243f51a0 | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
e005ca77-9d30-50ba-85b8-5b8141a18813 | textbox | Comments
acdd793f-d811-4dbe-a88b-723b57aaa866 | checkpoint-no-value | Work area 4 details entered
7bb46e79-7f02-5724-9dd9-104dbbec812d | textbox | Area
be25ad5a-4ca2-525d-bbf1-4f19ae74b723 | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
b7dc4438-0819-55b2-abd3-09ca59ac28de | textbox | Comments
72b51e38-8535-4d10-8f95-87ee65f15fdb | checkpoint-no-value | Work area 5 details entered
1fec6a73-6b99-53fb-aed0-82bcfb15c0c9 | textbox | Area
ecf7af16-67d4-5810-bd87-b0a36525d33e | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
1ec45771-b0cd-58ea-a949-ece2ee9e170f | textbox | Comments
8ddfb0db-b4be-4ab6-b9f4-ce95f495f685 | checkpoint-no-value | Work area 6 details entered
0deb4935-6ba8-5d67-a027-c8c55e2c5a53 | textbox | Area
55009a01-9234-502b-817b-a5b216fdd58f | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
e474f660-6e53-544a-8b5d-4b90ed0d65ef | textbox | Comments
3965ec9c-f663-4dab-b13b-5610f0074dec | checkpoint-no-value | Work area 7 details entered
1415c1c8-2195-50b2-93ac-99dd14fe3681 | textbox | Area
e8372d2e-c0de-5db2-9eb2-cc260b9d83f7 | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
f0e7bb75-dc9c-5a31-9e03-21e469fdd832 | textbox | Other
e40c593b-c62b-4605-8eb9-cf9827624ea2 | checkpoint-no-value | Work area 8 details entered
45ee9456-28fe-50cf-8f14-19cbd84030fb | textbox | Area
4403fc30-dbff-514d-a784-0367943e3825 | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
71ec361b-2226-504b-be43-45e917b06eb0 | textbox | Comments
12842c86-5ab1-44ef-8ea6-95550ab58ff6 | checkpoint-no-value | Weather conditions entered
b27ae412-cfda-5701-a4ee-6dc7cc866a14 | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
b769d775-285e-5644-a1d3-9ad521aa28d9 | textbox | Min temp predicted
84dee054-03db-5f14-baa0-d535c1ac9ca3 | textbox | Max temp predicted
589afa16-e681-49e5-a49e-131ca6c09df2 | checkpoint-no-value | Delays from inclemency
63508f15-fad0-550e-9778-4af0ecca9ced | textbox | Total Hours of delay
a986aa31-e7d8-5b19-a0d8-4f3a76baffb6 | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
907b667a-d034-493a-8c82-ca5fa5ac4a6e | checkpoint-no-value | Delays from Builders or Others
e95a47c2-25ac-5a58-88d3-3a4cc786186c | textbox | Total Hours of delay
e8d2d9d0-5ca4-5b44-be91-75da5ea40256 | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
f5111b90-fd62-4302-9eeb-22db007011e4 | checklist | Stairs (in-situ) Checklist |  | Stairs (in-situ) Checklist
90fd2240-6895-4713-8866-d6b1d2c2d21d | section | Phase 1
37607fe0-65bb-4dc0-836e-7ad022c243fc | checkpoint | Area accessible & ready
2e4c6610-df06-4dba-9ddf-8e5fdc90859f | checkpoint | Drawing references entered
4f9580c1-6637-5421-b98e-9de4eb922699 | textbox | Architectural
4b14b656-f06f-5468-bb18-5e1619f9ed8f | textbox | Structural
9d6346c3-d14a-5822-a291-d2f42a1c939f | textbox | Other
72fb8352-8965-45a5-8f52-a5022e5b3d07 | checkpoint | Current plans in use
f71bdf68-98c1-49dd-8c7f-d5b2460e5b82 | checkpoint | Land stringers & backdrops secured
7e776520-75cf-4017-ac6c-ca2cc594a7d9 | checkpoint | Datum RL supplied by surveyor pour height marked
5f9053de-1cd9-4213-b1d8-3d3878575b49 | checkpoint | Couplers & rebate boards installed
31290b17-d71e-47ac-a3ef-35a234fb34ac | checkpoint | Base of stairs cleaned
f1ef5a8c-a6bb-4661-8ad2-f9f696027be4 | checkpoint | Riser heights confirmed
53a649c9-122b-4554-8bed-c53d36871dcf | checkpoint | Going lengths confirmed
29010f09-3444-4af0-85ef-4438c760c773 | checkpoint | Correct Class of Finish
9febfe57-6ad6-4ba7-8c07-f9409f25f8a9 | section | Phase 2
82a9a1c2-cb1e-4ada-bcc5-07f1b087c2e3 | checkpoint | Datum RL supplied by surveyor pour height marked
bef3a377-5e30-4b34-9b7d-d856f4f9d71e | checkpoint | Couplers & rebate boards installed
c0246718-58c4-48a8-9cda-74bb71b6a466 | checkpoint | Base of stairs cleaned
e0e85d87-037a-42d0-b1d8-0f86350053fd | checkpoint | Riser heights confirmed
78231e16-d8aa-42c3-a5de-ff3d3e4baf3e | checkpoint | Going lengths confirmed
175fdbf8-5609-41d1-bcdc-4441d97a1e64 | checkpoint | Correct Class of Finish
3ee9603c-2a0f-40ca-907c-627042f2bd75 | checklist | Stairs Checklist |  | Stairs Checklist
32dfc00c-2204-41c5-a6db-ea05f7aa7c50 | section | Phase 1
af6beaca-60e6-4beb-be6a-40a4757f25c4 | checkpoint | Area accessible & ready
a7534628-0ba7-4713-a248-042db56585be | checkpoint | Drawing references entered
48b5bf3e-3226-5600-82a0-f2024d2d540d | textbox | Architectural
34f8437c-cb29-5dd3-8744-e558af904bf7 | textbox | Structural
cf4b7d62-23e1-5092-9e60-bd625f2ebaea | textbox | Other
0304e7a1-f14e-48ae-a015-0c40b1e53790 | checkpoint | Current plans in use
07a1a61a-91b1-48a7-acdf-149152010ec2 | checkpoint | Land stringers & backdrops secured
75256dcc-7945-4ce3-be26-c2c9b2c4e3f8 | checkpoint | Datum RL supplied by surveyor pour height marked
58fedd49-c36e-4c8e-bb98-48b85e789463 | checkpoint | Couplers & rebate boards installed
cdba7381-dc03-4cae-bf3a-d817e09db9af | checkpoint | Base of stairs cleaned
fef85713-bf25-400e-a685-de39d1dc2343 | checkpoint | Riser heights confirmed
bcc0b8b4-c193-457d-840c-22a8aa41b14c | checkpoint | Going lengths confirmed
80732af0-d460-486c-836a-3c01c57b7ebd | checkpoint | Correct Class of Finish
2ec1bd42-28c6-421d-8ee7-96797142f361 | section | Phase 2
bf8be4b5-81ec-4812-ba99-551a424678af | checkpoint | Datum RL supplied by surveyor pour height marked
22c8cb4e-15ab-40f3-9aa5-59ef3b4028dd | checkpoint | Couplers & rebate boards installed
5855bf07-50d9-4066-abdc-6dd78fe39cfb | checkpoint | Base of stairs cleaned
8ef2b35c-2522-48aa-a81b-fec866a1ee70 | checkpoint | Riser heights confirmed
961e776e-63f1-458d-b889-382648492b11 | checkpoint | Going lengths confirmed
6e2bf517-68bd-4ef6-9e8e-36251dae9299 | checkpoint | Correct Class of Finish
4073986a-d739-44ea-8e48-a96e4d563ad7 | checklist | Suspended Slab Checklist |  | Suspended Slab Checklist
d3609d6a-364d-4309-95be-e1dec556b484 | section | Suspended Slab
260fe2d3-6738-4a8b-82aa-08a0f44ed462 | checkpoint | Area accessible & ready
016ed21e-f41d-4cf3-99a5-4202e0ad6123 | checkpoint | Drawing references entered
ab33d7c5-1ccf-4f69-a61c-b0c7a791ae51 | checkpoint | Materials used complies with design documentation
25c42580-96b2-4d8a-8a37-b41f22b9cdf5 | checkpoint | Datum point used & soffit RLs checked
0cca86b6-50ec-4eb8-9338-9596e3c9a079 | checkpoint | Grids marked by builder
8a19ffe2-0f8e-48e3-a6f9-92b7147c00fe | checkpoint | Surveyor points given for outside of building
18481696-133c-4e83-be65-af74c233bc17 | checkpoint | Fillet & drip mould installed
e0bbb5cf-9a59-4957-aca9-63aaa3770c6a | checkpoint | Check set down position & RL
adc7e88a-132f-4f54-9149-c8d6867e0cf3 | checkpoint | Check penetrations installed
7b4e4d00-2c1a-4f7e-9d04-5661a91a0d1c | checkpoint | Prop drop head wedges are secure
4a29a193-ef0d-43e2-921d-0a339280fffe | checkpoint | Column blockouts installed
ea915116-3ce8-45dc-b9db-c8b12c04b1a4 | signoff | Inspection by site engineer
db9ee149-0549-4b2f-926a-6b3524771088 | checkpoint | check back propping as per design
e221f9dd-21de-42d7-acf8-b966efa92d6c | checkpoint | Blow off deck
1dbe42b3-dd85-482d-a647-2b7d7cb72548 | signoff | Do not commence concrete till all works agreed
cbca9183-1662-4b8d-94b5-5e362f4bc65a | checkpoint | Engage external consultant (engineer inspection)
9a3f9783-5bd0-41d5-9ae9-96cea2b94df6 | checkpoint | Correct Class of Finish
8232c301-de9c-48f1-bb93-f61c22cc4610 | checkpoint | Stripping, cleaning & materials removed
658cefbc-79d3-467f-b77c-90df660fd690 | checklist | Toolbox Meeting |  | Toolbox Meeting
b0c603ef-5c6b-4864-919f-0fd99aa4dccf | section | Details
35239a35-a627-4ca8-bc5d-51277e71f3f1 | checkpoint | Toolbox signed off - Attach an forms
762204c8-c42b-574b-b53b-559ef0a942b5 | textbox | Work area
fd7f3e01-ae8b-5fea-a5be-fd8d10d95c81 | textbox | Supervisor
d0612b40-c812-588a-ba24-b5b2d0b95d72 | textbox | Date
73c8ba68-cb79-5ab1-b5da-9b593f12554c | textbox | Time am / pm
43736c63-5da0-5cb7-8b76-4ffe3c0b0354 | textbox | Actions from last meeting
f15931f4-9d68-5d29-a246-92dedfe198f5 | textbox | Injuries last week
4ff91638-6852-556b-a2e9-ed36e67cd701 | textbox | Near misses last week
c25a7015-1fd4-5960-87d3-53b07f391a3f | textbox | Safety Items discussed
54baf619-f2f9-5b08-9044-d52e717158a0 | textbox | Comments from the floor
5e12c0ff-850c-5b80-bfd7-fb6355ed80b6 | textbox | New business
46b7a14a-bff9-5d6c-8f8d-79be3daea5ff | textbox | Attendees
92fff852-2f4f-4459-9e7f-af01b1646f2c | checkpoint | Attendance verified
0f3a7929-ac78-4741-9953-5df20f0dde92 | checklist | Variation / Site Instruction |  | Variation / Site Instruction
a900863a-8f7a-4baf-bb74-f23553b67605 | section | Details
1117be45-7f4f-4774-b104-904711d1422c | checkpoint | Variation / SI Details Entered
8a534d66-2130-5281-9b21-cdd5f76e006e | note | Please take before photos
c2422c72-0e53-5ac9-93f0-1895a2a2048e | radio | Work type: | Site Instruction, Variation Work
ea35af7e-0c93-5c20-97cc-677e2609c948 | textbox | Attention:
6c3c0189-499f-5c7e-906d-54e7f404ec84 | textbox | Area/Location
0f009cec-8615-5aef-9a82-e0e27aa0ef16 | textbox | Date
d4d79d20-dc46-52c5-b650-654566422071 | textbox | Scope of work
a16c3ce3-8cc6-5322-8f94-79557001be3f | textbox | Normal Hours
789bd1c4-8b1f-515b-bc9a-5d600d4965cf | textbox | Overtime Hours
1c343282-0318-50ff-983e-523006964a82 | textbox | Material to complete task
2702f1ba-b962-474b-81cf-276dc37dbbdc | checkpoint | Reference/SI Number Entered
26944bc8-d407-5b47-b9e0-b8c4f564d1ed | textbox | Reference/SI Number
f3d6fe94-4025-4e24-9ef9-2c31ed15741f | checkpoint | Variation / SI Work Completed
b7acca71-0d90-48a2-b5e1-6cfbf8105c41 | checkpoint | Values added (Office use only)
f1725309-10b4-56a9-8e67-ec1e2866f46b | textbox | Labour Value
8c561252-2911-5007-9253-9dff7a0e2f55 | textbox | Material Value
293699ec-88a0-585c-8d22-0c78a60ce065 | textbox | Measured Items
6622c6be-ece2-58f5-88d5-55a743655232 | textbox | Total Variation Value
cbc2d47f-a74a-4d04-8e6b-ca7bf45973ad | checklist | Walls Checklist |  | Walls Checklist
5bb3abdf-37ce-4e97-a3cb-d3e518eb0b49 | section | Walls
6bd6f8d7-6437-4b4f-9fc0-18d76a4a9089 | checkpoint | Area accessible & ready
d27bd1b2-21d5-47f5-8961-81183e258fc4 | checkpoint | Drawing references entered
b1816aa0-2be0-5abc-b8dd-63ffbc42d1d7 | textbox | Architectural
9085c1f2-c3f6-5e0d-a24e-5d6ea11b1463 | textbox | Structural
f420c8d5-785e-58e1-8f65-9007165cce49 | textbox | Other
bd685335-cc87-4116-a97e-3548b0e2f4d1 | checkpoint | Current plans in use
0e247365-0126-4ba3-8c2d-f6ddcbcb2e0c | checkpoint | Survey points given for 2 points
47c8e75f-9f6a-471a-bf99-38507b587426 | checkpoint | Land shutter bracing props secured plumb shutter
0385b8b2-f159-4c94-907d-78b140b82bfa | checkpoint | Datum RL supplied by surveyor pour height marked
c7e56f68-1479-419f-9805-c89a3e04508d | checkpoint | Blockouts steps penetrations marked & installed
d13acd79-af74-460b-9534-9be97583bb10 | checkpoint | Steel tied & clear from Z bar holes
39a0705d-9c03-4e62-beb3-61b799df2b58 | checkpoint | Couplers & rebate boards installed
96e24b54-c623-4976-abfe-6808794f86d4 | checkpoint | Base of walls cleaned
570d336b-ef0a-4d39-a471-7f981796e0a4 | signoff | Inspection by site engineer
9e920925-80e9-4a66-8178-e2eddbe30536 | checkpoint | Closing shutter installed
1f85f7f5-3b15-427d-a329-0904e57e66f9 | checkpoint | Z bars secured wall straight & plumbed
3b64d2cf-44a9-4fed-9a3b-092a1a4d1c9b | checkpoint | Correct Class of Finish
a6a2e2d1-4c58-4115-84f8-08b7475691fd | checklist | Weekly Labour Hire Control |  | Weekly Labour Hire Control
50f99d5c-72ba-4f31-9f53-aa18dcf23c92 | section | Details
25a2bde4-d946-46fb-bbf6-02f0231005a5 | checkpoint | Tuesday
34fcb41d-3ea6-5a3e-a83f-8da8bc85a14c | textbox | Date
4f49ce07-8e31-5393-b985-93e40004aee6 | textbox | General Comments
72e01366-6934-4b8e-ab3b-bea737f76e6b | checkpoint | Wednesday
b99e4183-0eb2-5869-884e-6805601cbddf | textbox | Date
35cac7e3-f017-545a-bedc-606ecebe1919 | textbox | General Comments
3cd880ae-9993-4872-931f-b6e74d39043e | checkpoint | Thursday
d1a6888f-4cf1-53c0-a7ef-a47d3cb5a79c | textbox | Date
dbe5cb62-3ca2-54b9-95a0-d2cd96131306 | textbox | General Comments
2d70382b-700c-4211-b98f-c23d129ba873 | checkpoint | Friday
a9fed790-463f-54e8-aa1a-5eb4004790b8 | textbox | Date
4585861c-6c37-5525-a0ae-f3ae8e5e9484 | textbox | General Comments
b2c7f60d-46b2-42aa-a1dd-455f6a37fa85 | checkpoint | Saturday
85dd40a1-ff22-5391-86c8-a83c9e4ae8de | textbox | Date
533fc3b8-270f-5869-b9e1-53bbb1cd09a5 | textbox | General Comments
bfae5052-6405-4acb-97d4-1727a15f3fd4 | checkpoint | Monday
2cace85c-0fc6-5e65-8d93-c1aa57f97026 | textbox | Date
a135b6a6-0ab3-533e-afdf-ec3af6facf63 | textbox | General Comments
41fcf344-ca66-4e5a-917e-783db26687ac | checkpoint | Tuesday
ad22f982-64b0-5c2f-96ad-30c79d3fc41d | textbox | Date
a52fffe6-3345-5d33-91e1-e51ab01d6a04 | textbox | General Comments
a98b65f7-4b62-484c-818d-5f2fabfd6468 | checkpoint | Please Attach Time Sheet
c4821a0a-8543-4cc6-abf1-77359fbdf359 | signoff | Client Confirmation Signature