## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-1001 - Installation of Manhole - FSMH-A2 | itp |  |  |  |  | ITP-1001 - Installation of Manhole - FSMH-A2
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawing C4400-2 or aggreed with the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill / Bedding Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
label | Acceptance Criteria - As per DCC code of subdiviison 10329
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4400
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Acceptance Criteria - As per 561467-TW-04-DRW-001
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - Minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Bedding
label | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
label | Acceptance Criteria - Bedding to comply with requirements
label | Verifying Document - Photo
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.4 - MH Installation
label | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
label | Acceptance Criteria - Final levels are in accordance with the C4400 or within tolerance and agreed with the Engineer
label | Verifying Document - Photos, As-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.5 - Benching
label | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
label | ○ Benching shape to have smooth transitions at bends and junctions
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Photos
label | Frequency - During benching contruction
label | Inspection Type (Visual, other) - Visual, Test Results
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Leak Testing
label | Inspection Point: Quality Control Activity - Manholes to be water tested up to within 150mm of the concrete lid level.
label | Acceptance Criteria - The amount of water leakage from chamber under test shall not exceed 1/300 of the volume of the chamber during a 30 minute period
label | Verifying Document - Photos, test records
label | Frequency - For every manhole
label | Inspection Type (Visual, other) - Test, visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After installation of FSMH
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1002 - Installation of PVC Foul Sewer Pipes - FSMH-A2 to FSMH-A1 | itp |  |  |  |  | ITP-1002 - Installation of PVC Foul Sewer Pipes - FSMH-A2 to FSMH-A1
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Pipes shall be DN225 SN16 PVC-U rubber ring jointed
label | ○ Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket,
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawings or aggreed by the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/QE/PE/CR
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10324.
label | Acceptance Criteria - As per DCC code of subdiviison 10324
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to achieve required depth to invert as per drawing C4400
label | ○ Floor of trench to be even across width and length
label | Acceptance Criteria - Allow 100mm for bedding
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/CM
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Install Pipe
label | Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C4400
label | Acceptance Criteria - Pipe not damaged during installation
label | ○ Pipe installed to grade within tolerances specification GP 3.1.8
label | Verifying Document - Photos, Grade check sheet, Survey of position for as-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.4 - Laterals connections and installation
label | Inspection Point: Quality Control Activity - Lateral connection as per drawing C4410
label | Acceptance Criteria - – Lateral connection as per drawing C4410 and DCC standard details and project specs.
label | Verifying Document - Photos, measurement checks
label | Frequency - Every Lateral
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.5 - Embedment zone
label | Inspection Point: Quality Control Activity - Embedment material AP20 or approved by the Engineer in writing
label | ○ Where required (trenches with >5% slope) AP20 stabilised with cement hall be used (40kg cement to 1000kg aggregate)
label | Acceptance Criteria - min 100mm bedding
label | ○ 100mm overlay
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, measurement check
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | ○ Conductive signal strip to be laid at 300mm above pipe
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - CCTV
label | Inspection Point: Quality Control Activity - CCTV inspection to confirm pipeline conforms with specification
label | Acceptance Criteria - Pipeline will fail is any of the following is visible:
label | ○ Pipe misalignment or deformation more than 5% of the pipe diameter
label | ○ Dips or ponding of water inside the pipe
label | ○ Defects such as open joints, potruding laterals, cracked barrels, or similar
label | Verifying Document - Test Records, CCTV footage
label | Frequency - Every section of pipe completed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Leak testing
label | Inspection Point: Quality Control Activity - Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Test Records
label | Frequency - Every section of pipe installed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.3 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After completion of pipe section
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1003 - Installation of pipe from WCMH-3A to WCMH-2B | itp |  |  |  |  | ITP-1003 - Installation of pipe from WCMH-3A to WCMH-2B
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Pipes shall be DN475 SN16 PVC-U rubber ring jointed
label | ○ Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket,
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawings or aggreed by the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/QE/PE/CR
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10324.
label | Acceptance Criteria - As per DCC code of subdiviison 10324
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to achieve required depth to invert as per drawing C4200
label | ○ Floor of trench to be even across width and length
label | Acceptance Criteria - As per 561467-TW-04-DRW-001
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SP/QE/CM
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Install Pipe
label | Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C4200
label | Acceptance Criteria - Pipe not damaged during installation
label | ○ Pipe installed to grade within tolerances specification GP 3.1.8
label | Verifying Document - Photos, Grade check sheet, Survey of position for as-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.4 - Laterals connections and installation
label | Inspection Point: Quality Control Activity - Lateral connection as per drawing C4310
label | Acceptance Criteria - Lateral connection as per drawing C4310 and DCC standard details and project specs.
label | Verifying Document - Photos, measurement checks
label | Frequency - Every Lateral
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.5 - Embedment zone
label | Inspection Point: Quality Control Activity - Embedment material AP20 or approved by the Engineer in writing
label | ○ Where required (trenches with >5% slope) AP20 stabilised with cement hall be used (40kg cement to 1000kg aggregate)
label | Acceptance Criteria - min 100mm bedding
label | ○ 100mm overlay
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, measurement check
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | ○ Conductive signal strip to be laid at 300mm above pipe
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - CCTV
label | Inspection Point: Quality Control Activity - CCTV inspection to confirm pipeline conforms with specification
label | Acceptance Criteria - Pipeline will fail is any of the following is visible:
label | ○ Pipe misalignment or deformation more than 5% of the pipe diameter
label | ○ Dips or ponding of water inside the pipe
label | ○ Defects such as open joints, potruding laterals, cracked barrels, or similar
label | Verifying Document - Test Records, CCTV footage
label | Frequency - Every section of pipe completed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Leak testing
label | Inspection Point: Quality Control Activity - Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Test Records
label | Frequency - Every section of pipe installed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.3 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After completion of pipe section
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1004 - Installation of Manhole - WCMH-2B | itp |  |  |  |  | ITP-1004 - Installation of Manhole - WCMH-2B
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawing C4200-2 or aggreed with the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill / Bedding Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
label | Acceptance Criteria - As per DCC code of subdiviison 10329
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Acceptance Criteria - As per 561467-TW-04-DRW-001
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - Minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Bedding
label | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
label | Acceptance Criteria - Bedding to comply with requirements
label | Verifying Document - Photo
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.4 - MH Installation
label | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
label | Acceptance Criteria - Final levels are in accordance with the C4200 or within tolerance and agreed with the Engineer
label | Verifying Document - Photos, As-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.5 - Benching
label | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
label | ○ Benching shape to have smooth transitions at bends and junctions
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Photos
label | Frequency - During benching contruction
label | Inspection Type (Visual, other) - Visual, Test Results
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Leak Testing
label | Inspection Point: Quality Control Activity - Manholes to be water tested up to within 150mm of the concrete lid level.
label | Acceptance Criteria - The amount of water leakage from chamber under test shall not exceed 1/300 of the volume of the chamber during a 30 minute period
label | Verifying Document - Photos, test records
label | Frequency - For every manhole
label | Inspection Type (Visual, other) - Test, visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After installation of FSMH
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1005 - Installation of pipe from WCMH-2B to WCMH-2A | itp |  |  |  |  | ITP-1005 - Installation of pipe from WCMH-2B to WCMH-2A
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Pipes shall be DN475 SN16 PVC-U rubber ring jointed
label | ○ Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket,
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawings or aggreed by the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/QE/PE/CR
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10324.
label | Acceptance Criteria - As per DCC code of subdiviison 10324
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to achieve required depth to invert as per drawing C4200
label | ○ Floor of trench to be even across width and length
label | Acceptance Criteria - Allow 100mm for bedding
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/CM
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Install Pipe
label | Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C4200
label | Acceptance Criteria - Pipe not damaged during installation
label | ○ Pipe installed to grade within tolerances specification GP 3.1.8
label | Verifying Document - Photos, Grade check sheet, Survey of position for as-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.4 - Laterals connections and installation
label | Inspection Point: Quality Control Activity - Lateral connection as per drawing C4310
label | Acceptance Criteria - Lateral connection as per drawing C4310 and DCC standard details and project specs.
label | Verifying Document - Photos, measurement checks
label | Frequency - Every Lateral
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.5 - Embedment zone
label | Inspection Point: Quality Control Activity - Embedment material AP20 or approved by the Engineer in writing
label | ○ Where required (trenches with >5% slope) AP20 stabilised with cement hall be used (40kg cement to 1000kg aggregate)
label | Acceptance Criteria - min 100mm bedding
label | ○ 100mm overlay
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, measurement check
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | ○ Conductive signal strip to be laid at 300mm above pipe
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - CCTV
label | Inspection Point: Quality Control Activity - CCTV inspection to confirm pipeline conforms with specification
label | Acceptance Criteria - Pipeline will fail is any of the following is visible:
label | ○ Pipe misalignment or deformation more than 5% of the pipe diameter
label | ○ Dips or ponding of water inside the pipe
label | ○ Defects such as open joints, potruding laterals, cracked barrels, or similar
label | Verifying Document - Test Records, CCTV footage
label | Frequency - Every section of pipe completed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Leak testing
label | Inspection Point: Quality Control Activity - Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Test Records
label | Frequency - Every section of pipe installed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.3 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After completion of pipe section
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1006 - Installation of Manhole - WCMH-2A | itp |  |  |  |  | ITP-1006 - Installation of Manhole - WCMH-2A
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawing C4200-2 or aggreed with the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill / Bedding Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
label | Acceptance Criteria - As per DCC code of subdiviison 10329
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Acceptance Criteria - As per 561467-TW-04-DRW-001
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - Minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Bedding
label | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
label | Acceptance Criteria - Bedding to comply with requirements
label | Verifying Document - Photo
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.4 - MH Installation
label | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
label | Acceptance Criteria - Final levels are in accordance with the C4200 or within tolerance and agreed with the Engineer
label | Verifying Document - Photos, As-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.5 - Benching
label | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
label | ○ Benching shape to have smooth transitions at bends and junctions
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Photos
label | Frequency - During benching contruction
label | Inspection Type (Visual, other) - Visual, Test Results
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Leak Testing
label | Inspection Point: Quality Control Activity - Manholes to be water tested up to within 150mm of the concrete lid level.
label | Acceptance Criteria - The amount of water leakage from chamber under test shall not exceed 1/300 of the volume of the chamber during a 30 minute period
label | Verifying Document - Photos, test records
label | Frequency - For every manhole
label | Inspection Type (Visual, other) - Test, visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After installation of FSMH
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1007 - Installation of Manhole - FSMH-A1 | itp |  |  |  |  | ITP-1007 - Installation of Manhole - FSMH-A1
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawing C4400-2 or aggreed with the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill / Bedding Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
label | Acceptance Criteria - As per DCC code of subdiviison 10329
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4400
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Acceptance Criteria - As per 561467-TW-04-DRW-001
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - Minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Bedding
label | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
label | Acceptance Criteria - Bedding to comply with requirements
label | Verifying Document - Photo
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.4 - MH Installation
label | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
label | Acceptance Criteria - Final levels are in accordance with the C4400 or within tolerance and agreed with the Engineer
label | Verifying Document - Photos, As-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.5 - Benching
label | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
label | ○ Benching shape to have smooth transitions at bends and junctions
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Photos
label | Frequency - During benching contruction
label | Inspection Type (Visual, other) - Visual, Test Results
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Leak Testing
label | Inspection Point: Quality Control Activity - Manholes to be water tested up to within 150mm of the concrete lid level.
label | Acceptance Criteria - The amount of water leakage from chamber under test shall not exceed 1/300 of the volume of the chamber during a 30 minute period
label | Verifying Document - Photos, test records
label | Frequency - For every manhole
label | Inspection Type (Visual, other) - Test, visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After installation of FSMH
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1008 - Installation of pipe from WCMH-2A to WCMH-1 | itp |  |  |  |  | ITP-1008 - Installation of pipe from WCMH-2A to WCMH-1
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Pipes shall be DN475 SN16 PVC-U rubber ring jointed
label | ○ Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket,
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawings or aggreed by the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/QE/PE/CR
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10324.
label | Acceptance Criteria - As per DCC code of subdiviison 10324
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to achieve required depth to invert as per drawing C4200
label | ○ Floor of trench to be even across width and length
label | Acceptance Criteria - Allow 100mm for bedding
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/CM
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Install Pipe
label | Inspection Point: Quality Control Activity - Pipe installed to grade as per drawing C4200
label | Acceptance Criteria - Pipe not damaged during installation
label | ○ Pipe installed to grade within tolerances specification GP 3.1.8
label | Verifying Document - Photos, Grade check sheet, Survey of position for as-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.4 - Laterals connections and installation
label | Inspection Point: Quality Control Activity - Lateral connection as per drawing C4310
label | Acceptance Criteria - Lateral connection as per drawing C4310 and DCC standard details and project specs.
label | Verifying Document - Photos, measurement checks
label | Frequency - Every Lateral
label | Inspection Type (Visual, other) - Visual, Survey
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.5 - Embedment zone
label | Inspection Point: Quality Control Activity - Embedment material AP20 or approved by the Engineer in writing
label | ○ Where required (trenches with >5% slope) AP20 stabilised with cement hall be used (40kg cement to 1000kg aggregate)
label | Acceptance Criteria - min 100mm bedding
label | ○ 100mm overlay
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, measurement check
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | ○ Conductive signal strip to be laid at 300mm above pipe
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - CCTV
label | Inspection Point: Quality Control Activity - CCTV inspection to confirm pipeline conforms with specification
label | Acceptance Criteria - Pipeline will fail is any of the following is visible:
label | ○ Pipe misalignment or deformation more than 5% of the pipe diameter
label | ○ Dips or ponding of water inside the pipe
label | ○ Defects such as open joints, potruding laterals, cracked barrels, or similar
label | Verifying Document - Test Records, CCTV footage
label | Frequency - Every section of pipe completed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Leak testing
label | Inspection Point: Quality Control Activity - Tested in the presence of the Engineer or their representative testing in accordance with AS/NZS 2566.2 Section 6.4
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Test Records
label | Frequency - Every section of pipe installed
label | Inspection Type (Visual, other) - On-Site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.3 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After completion of pipe section
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT
checklist | ITP-1009 - Installation of Manhole - WCMH-1 | itp |  |  |  |  | ITP-1009 - Installation of Manhole - WCMH-1
section | SECTION 3 - RECEIVING INSPECTIONS
checkpoint | 3.1 - Material Delivery
label | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
label | Acceptance Criteria - Items are approved as per contract specification
label | ○ DCC approved
label | Verifying Document - Photos, delivery docket
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
checkpoint | 3.2 - Set out
label | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
label | Acceptance Criteria - Allignment set out matches drawing C4200-2 or aggreed with the Engineer
label | Verifying Document - Survey marks, photos
label | Frequency - Prior to commencement of works
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SV/SP/QE
holdpoint | HOLD POINT
checkpoint | 3.3 - Backfill / Bedding Material
label | Inspection Point: Quality Control Activity - Approved Material, AP20 as per DCC code of subdivision 10329.
label | Acceptance Criteria - As per DCC code of subdiviison 10329
label | Verifying Document - Delivery dockets, photos
label | Frequency - On Delivery
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE
section | SECTION 4 - IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench Excavation
label | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per C4200
label | ○ Trench width to allow for 300mm seperation between springline of the pipe and trench wall or an adjacent pipe
label | ○ Floor of Trench to be even across width and length
label | Acceptance Criteria - As per 561467-TW-04-DRW-001
label | Verifying Document - Photos, measurement checks
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - V
label | Inspection: By (Role Key) - SP/QE
checkpoint | 4.2 - Foundation
label | Inspection Point: Quality Control Activity - Scala tests on base of trench
label | Acceptance Criteria - Minimum of 2 blows per 100mm
label | Verifying Document - Test results
label | Frequency - During installation, per 20m
label | Inspection Type (Visual, other) - Visual, On site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.3 - Bedding
label | Inspection Point: Quality Control Activity - Bedding minimum 150mm compacted material
label | Acceptance Criteria - Bedding to comply with requirements
label | Verifying Document - Photo
label | Frequency - During installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.4 - MH Installation
label | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
label | Acceptance Criteria - Final levels are in accordance with the C4200 or within tolerance and agreed with the Engineer
label | Verifying Document - Photos, As-built
label | Frequency - During installation
label | Inspection Type (Visual, other) - Survey
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.5 - Benching
label | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
label | ○ Benching shape to have smooth transitions at bends and junctions
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Photos
label | Frequency - During benching contruction
label | Inspection Type (Visual, other) - Visual, Test Results
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
checkpoint | 4.6 - Backfill and Compact
label | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
label | ○ Compaction testing one test every two layers as required
label | Acceptance Criteria - 95% MDD in roads, paths, and pavements
label | Verifying Document - Photos, Compaction test results
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, On Site test
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE
holdpoint | HOLD POINT
section | SECTION 5 - FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Leak Testing
label | Inspection Point: Quality Control Activity - Manholes to be water tested up to within 150mm of the concrete lid level.
label | Acceptance Criteria - The amount of water leakage from chamber under test shall not exceed 1/300 of the volume of the chamber during a 30 minute period
label | Verifying Document - Photos, test records
label | Frequency - For every manhole
label | Inspection Type (Visual, other) - Test, visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Red pen markups
label | Inspection Point: Quality Control Activity - Complete mark up of any changes from project drawings
label | Acceptance Criteria - Signed ITP
label | Verifying Document - Red pen markup drawings
label | Frequency - After installation of FSMH
label | Inspection Type (Visual, other) - Document
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/CM
holdpoint | HOLD POINT