## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Installers Checklist (P-01 to P-12 & P-101 to P-112) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (6)
| tickbox | M20 x 96mm Brace Ferrules (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Single Ferrules (3)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 170mm Double Ferrules (2)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-13, P-113, P-16, P-116) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | T-41 Face Lifter (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 96mm Single Ferrules (10)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-14, P-114, P-17, P-117) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | T-41 Face Lifter (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 96mm Single Ferrules (11)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-15, P-115, P-18, P-118) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 96mm Single Ferrules (6)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-19, P-119) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (4)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 96mm Single Ferrules (6)
| tickbox | M20 x 170mm Double Ferrules (7)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-20, P-120, P-23, P-123, P-26, P-126, P-29, P-129, P-32, P-132) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 96mm Single Ferrules (4)
| tickbox | M20 x 170mm Double Ferrules (8)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-21, P-121, P-24, P-124, P-27, P-127, P-30, P-130, P-33, P-133) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 96mm Single Ferrules (2)
| tickbox | M20 x 170mm Double Ferrules (10)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-22, P-122, P-25, P-125, P-28, P-128, P-31, P-131) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (4)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | M20 x 96mm Single Ferrules (2)
| tickbox | M20 x 170mm Double Ferrules (7)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-34, P-134, P-35, P-135) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (4)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-36, P-136, P-37, P-137) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
| checklist | Installers Checklist (P-38, P-138, P-39, P-139) |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T Edge Lifter (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | M20 x 96mm Brace Ferrules (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | Ferrules - M20 (4)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER