## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
cd4160fa-ca9b-40c6-a0ef-aca8b3a37421 | checklist | DTM-ITP-001- Clearing and Grubbing Rev0 | itp | DTM-ITP-001- Clearing and Grubbing
978d3c0a-7747-4b99-83ca-ecbaeb8ba080 | section | 1 - Preliminary Works
f221dbc5-e143-4614-a874-4554378c07a3 | checkpoint | 1.1 - Check for correct documentation
b95c5f0c-11bb-52b8-8212-813958013045 | note | FREQUENCY: Prior to commencing any activity
7d5ddbac-fbf8-5407-951e-596fa573a7c8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
65bbcb94-b151-5b75-9c6c-e5f13f1a1dc6 | note | – using the correct and complete set of drawings & all drawings are the latest revision
e74b2e37-1e25-51eb-8460-50e28e63059f | note | – Signed onto work pack
8de91b5a-0d0d-52cf-b60c-59e914fd3a39 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ec18207d-e8a8-5b7a-b8dd-503cf9ebe8a8 | note | INSPECTION/TEST METHOD: Visual inspection
e839934b-0753-597a-8036-ef1e53ee90de | note | RECORD OF CONFORMITY: This ITP signed
4e5ae235-e8fa-513d-ac2f-3a67d50835e2 | note | HP*
3708c0ab-c870-5cf3-ba43-31c81b715047 | note | RESPONSIBILITY: Site Engineer
56cdb1c4-b025-5088-bab0-3fde9c3bfe5c | date | Date Completed:
485cf77c-9a7f-498b-a96c-1f88289e621c | checkpoint | 1.2 - Limits of work
6986b71f-10f9-54f4-ba48-75833b69e278 | note | FREQUENCY: Prior to pre commencment inspections
b0a446b7-0218-53a5-9ecd-0fe2241b93d0 | note | ACCEPTANCE CRITERIA: Clearing extents to be marked out as per drawings and ATC's/ RFI's.
741cd4f1-9d14-5a87-b4ae-440e65898768 | note | ○ Southern Outlet Highway is Road A0171, Link 5, CH 0.33 to CH 0.00.
8d59367b-1b74-58f9-aa79-4a6d517a38dd | note | ○ Davey Macquarie Couplet Main Road A1010, Link 5, CH 0.00 to CH 0.09.
dafe03b4-ea83-5376-bf7f-af0407061411 | note | ○ Davey Macquarie Couplet Main Road A1010, Link 10, CH 0.00 to CH 0.1 (approx.)
0e3b2984-c822-5138-991f-d734420bfdcb | note | REFERENCE DOCUMENTS: Cl 201.03
fd521529-655f-5dfa-9bb9-a25048f004a0 | note | INSPECTION/TEST METHOD: Visual inspection
8819e083-54f0-5acf-a92f-0622bf7eebbb | note | RECORD OF CONFORMITY: This ITP signed
9aace2a4-9a2e-5a85-a0ec-9b99f2c7034a | note | HP*
74b43e52-8f8d-5b71-a688-bd3a280e6fed | note | RESPONSIBILITY: Surveyor / Site Engineer / Foreman / Clearing Contractor
db282bd0-48fb-5114-bbd9-ef6fa91da74c | date | Date Completed:
2961961f-5fef-4f51-8943-fcb98c4d8a99 | checkpoint | 1.2 - Implementation of all measures and controls
d1b594a0-25e2-5e19-ba71-c53e42dc6be2 | note | FREQUENCY: Prior to commencing any activity
622630fc-0fa2-5d8a-ba35-eca41bf2df2a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: PSP, EMP, TMP, SWMS & WP
483316a1-2d33-5271-9e9f-601953098e53 | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, SWMS, Work Pack
ce3d923e-2652-59b7-83e0-cc1eec4f4dc0 | note | INSPECTION/TEST METHOD: Visual Inspection
b657f43c-adc2-5903-a1a4-d1832bdc43f7 | note | RECORD OF CONFORMITY: This ITP signed
a55ecc6e-2c88-5290-8f39-cc98916bc127 | note | HP*
ac66bc81-0d6e-5fa2-8a64-271cec937abf | note | RESPONSIBILITY: Site Engineer
9d26fd4d-7426-50f3-ab1f-dce4021aa70e | date | Date Completed:
4c336d60-d2ac-46e9-b845-a15843fc929f | checkpoint | 1.3 - Implementation of environmental measures and controls
87dda4f8-f8d5-57a6-bff3-eca8184cc618 | note | FREQUENCY: Prior to commencing any activity
c380380e-9686-5547-bb60-51ec3bfdf8a4 | note | ACCEPTANCE CRITERIA: Hold Point
68d7c897-9ed6-5daf-ad2d-32d51ba29215 | note | ○ EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
72481796-685e-507a-99c7-533a9209f0e7 | note | REFERENCE DOCUMENTS: Project Spec Cl160.24 EMP
f4cd4980-7ba3-5189-abba-8166853b77da | note | INSPECTION/TEST METHOD: Verify
09fdd594-e413-57a8-90df-9f6a7e57c6f1 | note | RECORD OF CONFORMITY: This ITP signed
69a8138c-3d07-5fbe-9a62-5414570075c0 | note | HP*
2e582631-845e-5355-8dd6-237fdb21550a | note | RESPONSIBILITY: Site Engineer
01112224-bd0d-5660-b162-13ddebad2ccd | date | Date Completed:
29876525-1f8e-4b96-ba43-fa34e1528849 | checkpoint | 1.4 - Flora and Fauna
6d201ff0-31ce-5bba-82b0-ac109cacfbb8 | note | FREQUENCY: Prior
768182a0-d263-515e-87a6-004ac0d8c2eb | note | ACCEPTANCE CRITERIA: Hold Point
b6baab11-a1f3-52d9-871a-64dd8471c6cf | note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits.
d56bdb8d-be0f-5e29-864f-6109f6309b50 | note | REFERENCE DOCUMENTS: EMP Cl176.I1(c)
80961749-d9ae-5a3e-904f-bb21e2424a68 | note | INSPECTION/TEST METHOD: Verify
c254e81d-846c-52f9-a90a-865e56fb2bc5 | note | RECORD OF CONFORMITY: This ITP signed, Vegetation Removal and Clearing Permit
6666e963-96af-55dc-967e-33581ec66f46 | note | HP
0c8aa277-1f1d-54cc-a94c-c144b44412d4 | note | RESPONSIBILITY: Site Engineer / QAV
6688cf9c-28c0-52ca-b77c-b311608985bb | date | Date Completed:
cc49166c-f91d-4348-b875-c39c1adb8494 | signoff | AUTHORITY HOLDPOINT
7d3152d4-3bea-43c4-933d-9bbf5896589d | checkpoint | 1.5 - Protection of Existing Vegetation
2d264ab3-fd01-5487-b6a4-7ab60d913fc0 | note | FREQUENCY: Prior to comencement of any work
4eb5b136-d200-52c3-9f6c-82b0718ba33a | note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the QAV shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
e46c452f-1e38-53fa-ba91-121421d7dda7 | note | ○ If directed by the QAV, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
a4680e63-bed2-551b-ac47-b56eeb481e31 | note | REFERENCE DOCUMENTS: EMP Cl201.10,Cl160.24, 176.I1
886d51df-c7dd-5730-90eb-0aa0d1df30ef | note | INSPECTION/TEST METHOD: Visual inspection
4ac6c785-e3b2-5ec1-b07e-a5a5e1c9d48e | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
f8e94bad-5992-5597-ba14-961f028d1835 | note | IP
29bd3e7a-66e8-5acf-a88c-56283241438d | note | RESPONSIBILITY: Site Engineer / QAV
6e0f9275-cbf8-5c84-b3d9-0f35c8cc2c37 | date | Date Completed:
632d5c5d-6ee8-424f-a136-35784a7aff7e | checkpoint | 1.6 - Cultrual Heritage
6e651572-afdc-5e9c-8573-43e023289f16 | note | FREQUENCY: Prior to removal of vegetation
4c30c36c-95fd-5c4c-b790-8e4d14cea67f | note | ACCEPTANCE CRITERIA: Hold Point
7568c301-9bc8-57e1-8548-c5e2ff08c7ef | note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
8f5da0ed-aea7-5d96-ba36-444ed2354b54 | note | REFERENCE DOCUMENTS: EMP Cl176.J1(e)
3cfd59fa-295f-58f7-824d-4588055cbb06 | note | INSPECTION/TEST METHOD: Verify
22ad1479-77ac-5bbf-9337-bec46374c948 | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
35b0fe92-ed26-5caa-95bb-c05ed4f9dd59 | note | HP
f5d0a6a8-87d1-5fcd-b233-1a85e8022573 | note | RESPONSIBILITY: Site Engineer / QAV
3a91009f-fcdf-5b63-b0b9-a92effc19bfa | date | Date Completed:
084ca863-f8ae-4ed2-984e-149419237db6 | signoff | AUTHORITY HOLDPOINT
cd370f2f-489b-453b-b982-deb672d58016 | checkpoint | 1.7 - Authorisation for works
36a3075a-7ad4-51ef-af56-03609344b910 | note | FREQUENCY: Prior to commencing works
fb3b54b8-71e3-59b4-b5d8-3679e0c7828d | note | ACCEPTANCE CRITERIA: Check that all relevant approvals (Access to 241 Davey, 326 Macquarie) have been granted including verification of the works area.
8e29ec26-dc8c-59d0-95c9-84118d80b584 | note | ○ Ensure work pack is reviewed & signed
68988739-b1ff-5959-b3b2-9dfdd09b1baa | note | REFERENCE DOCUMENTS: Work Procedure, 160.08
e2f3e977-804f-5f01-bc43-fc17b7586dfb | note | INSPECTION/TEST METHOD: Verify
14c63dc5-315f-5208-a91d-17b01abeaa6e | note | RECORD OF CONFORMITY: This ITP signed, Property Access Approval
78e054fc-418b-5d40-b724-3972ee32e47d | note | HP*
5611b064-7a63-5466-9202-4c5bd47f3072 | note | RESPONSIBILITY: Site Engineer
11105919-1f33-541c-8ac9-bbaeb6797e7d | date | Date Completed:
b263f5cf-4f17-494e-b51e-6ce510fa3e8b | checkpoint | 1.8 - Utilities
db61a8cf-77a4-544f-ab50-2b7d82468a15 | note | FREQUENCY: Prior to commencing works
b3bb7563-761e-5939-9af0-c4720ace3635 | note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
1d8c708a-7a7f-553c-aa4c-d630e5890074 | note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups, Excavation Permit
9742321b-ec0a-5d37-8374-db933beb50f6 | note | INSPECTION/TEST METHOD: Verify
f1000026-16aa-5393-8910-95be20fa72a0 | note | RECORD OF CONFORMITY: This ITP signed
a385f50f-ae0c-5b03-ac1c-1235b819d039 | note | IP
caf65a5d-d16e-593e-b1ab-5354174010bb | note | RESPONSIBILITY: Site Engineer
a53d7a95-6a9c-5403-9202-880c83cbaa06 | date | Date Completed:
35d9a4b5-99b5-427b-b648-00ba29e210b0 | checkpoint | 1.9 - Traffic Management
4f8f2031-f747-5de6-a207-0b98f72fa2b5 | note | FREQUENCY: Prior to commencing works
6e92de9e-223d-5029-adee-78d80c4a1f20 | note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS. Where localised speed reductions are required they shall be at the discretion of the QAV. TGS shall be submitted and approved by the Superintendent.
5f036104-e406-5f90-a630-7f70a5c18b8c | note | REFERENCE DOCUMENTS: TMS, TGS, TMP, 160.07
f6d0534b-ef37-5413-91a6-cc1a59a91203 | note | INSPECTION/TEST METHOD: Verify
4c1ccd6b-22e2-54c0-988e-b0845e902e23 | note | RECORD OF CONFORMITY: This ITP signed
5521c832-8b66-54b9-aa1e-28a75edd2097 | note | IP
e1a95a07-9a49-53de-a511-71512b6549fc | note | RESPONSIBILITY: Site Engineer
145d7c15-0390-5793-ad0b-874974fe4ca4 | date | Date Completed:
e75dcb2a-eff8-4502-9bd9-1c4c9c48064b | section | 2 - Clear & Grub
7b3e8eaa-2984-4daf-9625-fcb2227531df | checkpoint | 2.1 - Clear and grub trees and vegetation
50186ea9-b68d-5954-8064-716aa7df6b73 | note | FREQUENCY: Each Lot
fdd95a45-b152-5755-8866-d27b4c95f642 | note | ACCEPTANCE CRITERIA: Area within specified limits cleared of all vegetation, refuse and obstructions down to natural surface. Trees brought down in a manner so as to avoid danger to personnel and traffic as well as damage to other trees, structures and property.
4b0a80d2-f9e7-551f-a25d-4ab78b92af91 | note | REFERENCE DOCUMENTS: Cl201.04
0e71f4f6-4d4b-5d47-a6b5-2968ac2e7554 | note | INSPECTION/TEST METHOD: Visual Inspection
a07841ef-527b-566e-ad41-314a557d1877 | note | RECORD OF CONFORMITY: This ITP signed
e04997f7-5156-5e72-9217-75db12823421 | note | IP
1fb784be-af17-5b63-950d-f406fbf0df85 | note | RESPONSIBILITY: Site Engineer
8de3606e-462f-54c1-892e-a6baa3b38c59 | date | Date Completed:
0c70dc08-416c-402e-9b0d-6390a2b081be | checkpoint | 2.3 - Clear and grub trees and vegetation
9f1575bf-8394-5bc9-b565-f7413de4d6b6 | note | FREQUENCY: Each Lot
429f80ac-4467-5202-a587-ea86216e2e62 | note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
c4b0f60c-ef0f-580a-a35f-478cef69d5c4 | note | REFERENCE DOCUMENTS: Cl201.05
51a4a279-8076-5c7b-888a-6eb82301c676 | note | INSPECTION/TEST METHOD: Visual inspection
72d28079-259c-5101-924d-a4a6fafd39a7 | note | RECORD OF CONFORMITY: This ITP signed
d5d4d87e-deec-5595-ae64-8aabbd47354a | note | IP
0363a4b8-9e4c-5b08-8b9a-c22c546ed2a0 | note | RESPONSIBILITY: Site Engineer
6f2c79ce-9b79-5b84-aef1-09b9e2e5387c | date | Date Completed:
3fea4e0e-64e0-4dd8-8ebd-3243cf88c6c3 | checkpoint | 2.4 - Clear and grub trees and vegetation (embankment areas)
871b09e6-b563-5344-9466-86e9049f3f9d | note | FREQUENCY: Each Lot
4abdea04-bafc-5aeb-9d07-2d58eb933b02 | note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
1fb1d363-cd1a-5d44-a20d-410e29e6551b | note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
36fe859e-d562-5171-8842-c3ef83cffda9 | note | REFERENCE DOCUMENTS: Cl201.05
347372dd-857a-5305-a489-a82cc7a3ccf5 | note | INSPECTION/TEST METHOD: Visual inspection
36349761-d9bc-5976-9713-2f5a00dddaee | note | RECORD OF CONFORMITY: This ITP signed
d12603bf-3aef-5728-abb9-04ae5f94b3bb | note | IP
826bcc99-4c54-5121-abbb-cf208e26d95e | note | RESPONSIBILITY: Site Engineer
70aa8aa3-27d0-569d-a98f-9dd9e2f8c819 | date | Date Completed:
e4492093-5490-4bf5-859d-5865dae265ab | checkpoint | 2.5 - Clear and grub trees and vegetation at culvert sites
86a86409-02e9-5239-9587-0ef9571bdc39 | note | FREQUENCY: Each Lot
fc162fa0-733c-5544-ba01-4f443cd00570 | note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6m2 (unless otherwise shown on drawings)
5402f6e0-43c7-5089-9b94-8a0617a183d2 | note | REFERENCE DOCUMENTS: Cl201.06
c51e21a3-43a7-5bbc-a485-49d8103291f2 | note | INSPECTION/TEST METHOD: Verify
c7783ec9-28ad-56e6-bbb5-1ea14270ca92 | note | RECORD OF CONFORMITY: This ITP signed
bfff7fde-82d1-5ac1-b1c3-7979ac7f4ef2 | note | IP
fe634f17-c416-5434-8144-52aa5fe04379 | note | RESPONSIBILITY: Site Engineer
6ff5f44b-db46-5961-adc0-b0326d95bcba | date | Date Completed:
7238c519-32d0-44cb-b878-03d93b64ae75 | checkpoint | 2.6 - Backfill holes
9d70a48c-e269-59dd-8e76-c7ca935e7fb2 | note | FREQUENCY: After clearing
6c7b5e58-0a6b-5502-8c20-3d8a8eb66bca | note | ACCEPTANCE CRITERIA: Any remnants of pits shall be backfilled with similar material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
2405bb84-105d-562a-b305-3d027d77b53b | note | REFERENCE DOCUMENTS: Work Procedure Cl201.05
375985ca-7351-5e79-8975-4a65964c7456 | note | INSPECTION/TEST METHOD: Verify
a11d151d-fcb2-56d0-84cc-0e56a6b81321 | note | RECORD OF CONFORMITY: This ITP signed
6113525d-a67d-52d4-904e-72e6de7205b5 | note | TP
96d532c1-fb1d-5475-b2cd-4bdde76b94ae | note | RESPONSIBILITY: Site Engineer
3f3d4923-203c-5928-b904-059d3c47df76 | date | Date Completed:
2fb30172-3a6a-4bde-8553-4ce009c86671 | checkpoint | 2.7 - Dispose of Trees and vegetation
eed877d1-f64c-56fc-b17b-f799ab710708 | note | FREQUENCY: After clearing
a410877f-4afc-51ba-89a3-bb96c4f9ab2e | note | ACCEPTANCE CRITERIA: All vegetation within clearing limits shall be removed from site. Weeds not to be mulched and disposed of appropriately.
945b3756-20bc-5603-959c-de2aac83f47d | note | REFERENCE DOCUMENTS: Cl201.07
fe801138-cd85-503c-9c4a-7aeffc4d6f88 | note | INSPECTION/TEST METHOD: Verify
9b4cc6ec-a2b4-502f-b75b-3502b6b6f8c7 | note | RECORD OF CONFORMITY: This ITP signed
bee1236d-395f-5e33-b326-5abecacc03a3 | note | IP
7af4b583-d0e0-53bf-9b39-ba7ea70fc531 | note | RESPONSIBILITY: Site Engineer
7d2501bf-115b-543e-87c7-53cd986e7e86 | date | Date Completed:
1dac20ce-7d06-40b7-81e7-998ca642f827 | checkpoint | 2.8 - Damage to Fencing
98b70d25-b997-56df-ad11-b88d2f4f0d05 | note | FREQUENCY: During Clearing
c4093e29-5214-5216-ae3f-9f4e9d14718f | note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
c93ee17f-8c34-512e-b4e9-a2bce4dc8e4a | note | REFERENCE DOCUMENTS:
7f21f095-b9f6-5dc3-8d5c-019cc5aa86b2 | note | INSPECTION/TEST METHOD: Verify
f93c19e4-0427-5a3b-ba41-38c0c42c578f | note | RECORD OF CONFORMITY: This ITP signed
92c25d65-4cf3-574b-b562-ed02251f1281 | note | IP
757cadaa-1d83-52f2-a79d-de725a5da008 | note | RESPONSIBILITY: Site Engineer
0a1320b5-a237-523f-987d-41c97d79a9d3 | date | Date Completed:
0cc48126-9a7f-44f7-8948-9daf8e9d31f4 | checkpoint | 2.9 - Salvage of Vegetation
c4e5ae7b-9cd0-5526-b180-181c64792695 | note | FREQUENCY: During Clearing
33337043-e448-519a-a7b5-09e81fe84368 | note | ACCEPTANCE CRITERIA: Co-ordinating works with activities involving the salvage of plants and the collection of cuttings and available seed from areas of native vegetation on the site.
ea752a98-2893-54cc-ae5f-c5c1710326a2 | note | REFERENCE DOCUMENTS:
4235e68d-d813-5542-8848-aaad66ac5a34 | note | INSPECTION/TEST METHOD: Verify
96b6ca11-d379-5431-92df-fda6caca8d26 | note | RECORD OF CONFORMITY: This ITP signed
78c9f3d2-f55a-577c-a408-3e757735b698 | note | IP
d9414b16-d038-55f8-bb95-8fc25afc98b6 | note | RESPONSIBILITY: Site Engineer
7b68940d-888f-5cec-bd79-628f7fce2b6a | date | Date Completed:
4b3ff4e1-ec59-44ea-990c-1779139eb4bf | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c95c5dad-a2d5-5357-822d-56696a2a3fa9 | textbox | QAV - Print Name:
43162616-6a77-5bb5-9387-59e4242d2329 | textbox | QAV - Position:
ed646561-6cc6-52f1-86c3-8f5f8defd656 | textbox | Fulton Hogan - Print Name:
1564af1a-5ea5-5f2a-a445-60f29007d5d1 | textbox | Fulton Hogan - Position:
6b45587f-aa7b-5edf-baac-d8b136e3fbe1 | date | Work Completed On:
aa8f376b-2657-4dee-aa1b-40042ea2a8ed | signoff | Add Signature