## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-003- Earthworks Demolition | itp |  |  |  |  | DTM-ITP-003- Earthworks Demolition Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
label | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.2 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 Material Categorisation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: HOLD POINT
label | ○ Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | REFERENCE DOCUMENTS: 204.06(c)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Stripping of Topsoil
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
label | REFERENCE DOCUMENTS: 204.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 Type A Material
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | ○ HOLD POINT
label | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent.
label | REFERENCE DOCUMENTS: 204.04(b)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Type B Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Type B material shall be free of topsoil, deleterious and/or perishable matter. Type B shall have a minimum assigned CBR >5% and Assigned Percent Swell < 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
label | REFERENCE DOCUMENTS: 204.04(c)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Reports
label | IP
label | RESPONSIBILITY: Site Engineer / Superintendent
date | Date Completed:
checkpoint | 2.6 Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior construction of the regulating layer
label | ACCEPTANCE CRITERIA: HOLD POINT
label | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: 204.06(f)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 Unsuitable Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: HOLD POINT
label | ○ Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
label | REFERENCE DOCUMENTS: 204.07(d)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off, Work Procedure
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 Groundwater
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: HOLD POINT
label | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | REFERENCE DOCUMENTS: 204.06 (h)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 Trimming and Level conformity
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances:
label | – Range x = +5, -15mm
label | – Max S = 12 mm
label | ○ 80 measurements per lot (Scale A)
label | – Range x = +5, -25mm
label | – Max S = 15 mm
label | ○ 40 measurements per lot (Scale B)
label | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
label | INSPECTION/TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 Proof Rolling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173, before proceeding to subbase construction.
label | ○ The Contractor shall submit a test rolling procedure to the Superintendent including the method of preparing an area for test rolling, the extent of test rolling and a requirement to provide not less than 24 hours notice of the location and commencement time for the test rolling to the Superintendent.
label | REFERENCE DOCUMENTS: 173.03, 204.12
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP* WP
label | RESPONSIBILITY: Site Engineer/ QAV
date | Date Completed:
checkpoint | 3.2 Compaction Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD.
label | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 99% MDD.
label | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD.
label | REFERENCE DOCUMENTS: Table 204.131
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Records, Lot Register
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 Materials Property Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
label | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
label | REFERENCE DOCUMENTS: Tables 204.141, 204.142, 204.161
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
holdpoint | Add Signature