## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation | itp | CHK-001-CIV-Stormwater Drainage Pipes Installation | 8ea17dce-31d4-4a13-80ce-b333bace6f1e
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
9606f886-735c-5a77-b1cc-39eb08fcf281 | note | Document Title: CHK-001-CIV-Stormwater Drainage Pipes Installation
9085515f-c8a7-5f88-8182-6aaefc246de0 | note | ITP Description: Stormwater Drainage Pipes Installation Checklist
25d13b2b-e7dc-5f0f-ad53-a1d994db777d | note | Discipline (e.g. CIV/STR/RAIL): CIV
2c084acb-7f74-5acd-8cf7-3febc9620061 | note | Revision Number: 0
b4adb168-eba8-5e1c-8f27-5576c0a52e02 | note | Revision Date: 20/06/2023
9f9221a8-8f19-5dd1-ad90-5e22ca24428e | note | ITP created by: Kamel Alshobaki
c705680d-43f9-529e-bd52-f7ea58f1ec99 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
570725ac-0b3d-5329-9e3a-4049bbde88f0 | note | Reference - VR Section 701
| checkpoint | 1.2 - Non Dependent
6c797f0e-d8c9-54e7-a01a-137ce07388ed | note | Reference - VR Section 705
| checkpoint | 1.3 - Main ITP
131222df-4944-57f5-a6b9-3e4d709dbec9 | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
e2bfa6ec-ea00-56c3-8540-a0406d05f622 | note | Acceptance Criteria - This Checklist should be used in conjunction with ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
bb043660-7b8b-59be-b45b-428e5cfdfc73 | textbox | Enter: Main ITP Lot Number
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Bedding
75f4f975-eca2-5dfe-937c-d6438a11fa6e | note | Reference - VR Section 701
9b47376a-fe08-5d98-8ab8-bd3b3bef293a | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
72a7817a-b175-52a6-84a1-d35967def897 | note | • ATTACH: Bedding Material Delivery Docket
10689a10-dda8-58eb-9f0b-1ab77ec9b0e4 | note | Method - Document Review
1cbf99d2-38ef-59d4-bd71-095bed18b14f | note | Frequency - Each Lot
d2779326-7dba-5051-bdd6-3066a738c2e4 | note | Category - HP*
53c245ed-340a-5a18-ba8f-251cda226f29 | note | Responsible person - SE
bf8385ad-cc72-5984-957c-4344647a3be9 | note | Verifying Documents - This Checklist Signed-Off
de163a89-097a-5b49-b9dd-7023c1c75f91 | note | • Material Delivery Docket
| checkpoint | 2.2 - Backfill Material
ed7b938f-f145-57a6-97c7-6e1da5b88eba | note | Reference - VR Section 701
3b515b37-c532-592d-8838-1952620fbf33 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
5df750a7-3a3d-5e24-b259-4f40290699ef | note | • ATTACH: Backfill Material Delivery Docket
6e7be390-7d4c-52ea-ba79-798092c32ca2 | note | Method - Document Review
1e3b4d41-dab4-560c-8b55-225ec2fa3bbd | note | Frequency - Each Lot
432e4edf-52ed-5b27-8834-49810191a285 | note | Category - HP*
91a38553-84b7-5906-a1f9-60e7d4e9707a | note | Responsible person - SE
071568e4-9e91-5cd1-ac6d-bbfc2ca1b175 | note | Verifying Documents - This Checklist Signed-Off
f2421219-d8e8-5ea0-92ad-6797001d91cf | note | • Material Delivery Docket
| checkpoint | 2.3 - Stabilized Sand
9e0c1574-a3f1-58c9-a671-67bac827b197 | note | Reference - VR Section 701
d8a19c7a-94a2-541c-b895-d9e765d758a0 | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
04899235-29bc-5b5d-a85d-1b7df2799daf | note | • ATTACH: Selected Backfill Material Delivery Docket
b67cf58c-5bd1-5f77-827d-ac824aca9de3 | note | Method - Document Review
7a5d6521-9d67-562a-b2ea-14473a55cf47 | note | Frequency - Each Lot
5041558e-bca6-5b11-8b6e-1518c9b5f909 | note | Category - HP*
b0397f2b-7d09-5da6-8612-a037895ee547 | note | Responsible person - SE
bfd0e44c-d7c0-557b-9e4b-3b1cd1ef4a48 | note | Verifying Documents - This Checklist Signed-Off
85b052ee-a658-5aea-a769-460e471c360e | note | • Material Delivery Docket
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Subcontractor QA Submissions and Approved ITP
94aa007c-b6da-5ef8-8e7d-ded8ffa56bb4 | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
82b6a721-ecc4-5fcc-a681-4cc02fcfacb7 | note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
4767e7dc-c79c-59cb-bab9-9416bae6f662 | note | • ATTACH: Subcontractor Signed ITP
8d051671-df00-5680-9ff5-c26d6bd1773c | note | Method - Document Review
a2d2de44-0182-51c7-9ea7-0385a1820aaa | note | Frequency - Each Lot (in case undertaken by subcontractor)
54612012-a363-5efd-bb40-d9b1317f9e47 | note | Category - HP*
3f149ea6-abb7-53b2-9fd4-1162ce3b9c60 | note | Responsible person - SE
1c2d598c-ca00-5a23-84e9-078c4c73ebf0 | note | Verifying Documents - ConQA Hold Point Release
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Survey Set-Out
23c189ea-52f3-5cab-8155-fc171aba7c2d | note | Reference - VR Section 701.10
5d776ac9-cb07-54aa-a425-eedf4c14f4b8 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
f9828b13-a6a6-534c-a7dc-4f47dc40ef97 | note | • The culverts constructed shall be constructed true to line and level.
b56476d4-55e8-5418-bd7e-dd5911e4f545 | note | • MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
10dafc57-e13b-5a88-aa32-80e8fc1d9101 | note | Method - Survey, Measure
9916ffdc-b960-5cf2-aa31-b2d5e054f88b | note | Frequency - Each Lot
d9197a34-9591-5aea-975d-7283efc3856d | note | Category - HP*
165dde9d-318b-5344-bbbd-62fb51a4a5ff | note | Responsible person - SE
efd66298-5acb-50a8-be24-12c7457651fb | note | Verifying Documents - This Checklist Signed-Off
6e73409e-7ffa-5354-a84d-385bab2ab3eb | note | • Attach Main Lot Map
| section | 5. Construction Activities
| checkpoint | 5.1 - Trench Excavation
5b2b2eb7-86e1-548f-b84d-f35359b6dca7 | note | Reference - VR Section 701.15
c5ad33b6-322f-5ee0-9f83-c5357d50759c | note | Acceptance Criteria - For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
8fa6b910-720d-57e2-9f65-78a0e905c64b | note | • Horizontal Clearance to wall of trench
dfc8ebe7-66f7-5e10-a2eb-9eee5164da4b | note | ○ Pipe Culverts:
a5dbaf05-d04d-5653-b618-a9297c13a04f | note | • 300mm<Horizontal clearance for corrugated metal culverts<1000mm
c1299120-2fcf-5fd6-9249-6dd758235dbf | note | • 300mm<Horizontal clearance for other Pipe culverts<600mm
0df6eb03-1ca1-5bd3-88bc-a3e5a6e8cca1 | note | ○ Box Culverts:
4961334e-a762-5bc9-8c7b-ac028d716df2 | note | • 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
4b61aa72-2685-568d-a25a-edb1ff871872 | note | Method - Visual Inspection, Measure
d5b7480a-ea3e-5e7c-b034-707a34d7073e | note | Frequency - Each Lot
78f4226d-460f-5874-9d81-4de12cbdbc06 | note | Category - IP
84372a68-aebe-5fe9-82e7-79c999d6114a | note | Responsible person - SE
ea01c666-fa43-5345-a9ef-2974f063c3ff | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.2 - Trench Base
963dd88a-629d-5698-8f36-f9c465bf3c2a | note | Reference - VR Section 701.15
31bc0da9-7312-51ea-bbb8-f2ce66db1a7b | note | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant.
fbda3065-1f55-5d8e-8750-0dbf05fb5905 | note | Method - Visual
f4205396-3a5a-5e6a-9d42-25d104e44423 | note | Frequency - Each Lot
40f0cfb7-756d-55b2-92a3-05be6f241d89 | note | Category - SP
d7f54698-eea3-573a-82a7-a8fbfbc0958c | note | Responsible person - SE
9aac5b35-0df4-5111-9cac-cebab8491798 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.3 - Bedding-Placement and compaction
0914069e-a7bf-5df3-b999-7ccd58f06613 | note | Reference - VR Section 701.16, VR Section 701.20 (a)
29767ac6-022d-5c55-a2e1-7e307d4ef7c0 | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
2478666f-c7d7-5482-acbf-944f75ba648e | note | – 100 mm where D < 1500 mm
946708df-1a1f-5e8f-913b-08e5b3e6e33c | note | – 200 mm where D ≥ 1500 mm
f16371d9-2c97-585e-8d10-c65ef1ecced1 | note | • Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
00ae06f1-f24c-5d9d-bfc3-d041040cb6de | note | Method - Visual, Measure
f1cd1bd8-b5a8-5151-a6ab-92558e8b1892 | note | Frequency - Each Lot
5b5263c2-1b5c-5f6e-9bbb-9e8f70ec0cdc | note | Category - HP*
8d975cee-54e0-577c-89ce-0728ad050a4f | note | Responsible person - SE
163dddda-0e18-55dc-a7d4-12a583c13c2f | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.4 - Laying pipes-Bedding conformity
df26f6fd-e48c-5acd-bc27-cd3cffb35cc1 | note | Reference - VR Section 701.17
b1efe20c-e47f-51af-b3fb-86e666b2db0f | note | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
eb23f495-9281-54f8-8d49-3ad3953f6f8d | note | • Laying of pipes or box culverts shall commence from the downstream end.
e406d8b5-d39c-599b-a51c-7a3cb29cbb5f | note | Method - Visual
90fe179b-0765-554c-b2e7-43c6c9c113db | note | Frequency - Each Lot
ff1cd743-7e95-5ac9-8418-330b594e6c73 | note | Category - HP*
401f50d1-b66c-5314-b132-55a4e8161fbc | note | Responsible person - SE
033d5dd4-7d4a-563e-98f8-6b94391bf411 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.5 - Pipe Laying
0cf6d844-a9ef-5bb0-a6c2-35d775367940 | note | Reference - VR Section 701.16, VR Section 701.17
24fd5913-d844-5b4b-8d2b-546ed3940ba5 | note | Acceptance Criteria - Laying of pipes or box culverts shall commence from the downstream end.
72a50dc2-8871-56d0-9eb6-7bef738fe72d | note | – Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
6e492bd4-8028-5377-8c82-5c9214f458db | note | – The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
018651b0-d806-5cf8-9a97-181dfba3b2c4 | note | – The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
98cd1c37-413a-5bed-becb-00dc7bb5271f | note | – When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
140f1f68-9dde-5817-b821-f96f3c70916b | note | Method - Visual
491a255d-a322-5073-8121-44615d669c38 | note | Frequency - Each Pipe
b074fa79-b006-58d1-918d-b0c77ec955ee | note | Category - SP
da5998ce-6cff-5898-be0e-dfc1598d2e17 | note | Responsible person - SE
0a46b02e-7d06-518f-9f86-67a2d6ffeb45 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.6 - Pipe Joints and rotation
81721ed7-b94e-5f82-832f-3fbbc2ddcaa2 | note | Reference - VR Section 701.18
b93cfed2-5388-599b-be86-e642f49bb614 | note | Acceptance Criteria - All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
86ac7324-d0ed-5580-83ec-1232d385c040 | note | – Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
a849b464-4906-5afd-b005-00712dfff637 | note | Method - Visual
b9c5b291-93f6-5ad2-8923-c76e72682ff3 | note | Frequency - Each Pipe
4d76ea64-86db-50c5-84a0-31939f1acc6e | note | Category - SP
7b0d64a2-fb2b-5232-8593-5b4e39007781 | note | Responsible person - SE
67b6e2cb-d327-5a7e-9e93-e963a1493935 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.7 - Conformity with drawings
3446fb44-2f2f-5b5c-be71-70eecc37a307 | note | Reference - VR Section 701.10
6ec33e2a-70d4-5135-a457-ca85a4dc9127 | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
bba3f7cd-f3e6-5123-9686-b9bdad909a6c | note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
daa51087-6530-5676-ae0c-6b85dab098eb | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
d71d1aef-32d8-51d5-8e14-7de8fe75b7cf | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
0d522301-fd7e-5722-90f1-25aed1881242 | note | (c) invert level of pipes at pits ±50 mm
df7152d5-1758-55b2-8b3e-642760aa9ee2 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
cb27e881-f25d-5619-8d47-1411549e673d | note | • ATTACH: Survey Report
a842843e-f263-5a76-9364-ca1f5625e483 | note | Method - Measure
f9b8a8cd-0241-57ef-9df9-2427a1080082 | note | Frequency - Each Lot
594d2c7a-9346-5b74-ad7d-4aead200415f | note | Category - HP*
6557317e-9a99-5233-8fff-fbcd4c003de3 | note | Responsible person - SE
61c0e53a-c697-5759-9bce-d9958d83901a | note | Verifying Documents - This Checklist Signed-Off
17bcd92e-5064-5a55-95a5-11cb0bfd7c36 | note | • Survey Report
| checkpoint | 5.8 - Backfill-Under area to be paved
9986d4b7-b064-589c-b1b3-e2a02d3472bf | note | Reference - VR Section 701.19 (a) i
6ce9a8c0-5666-53fc-899c-5bea263f8ca4 | note | Acceptance Criteria - Culvert under area to be paved
56a37cd4-c13b-5412-b314-bc62d4cd5587 | note | – Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
3fe9e562-7344-560c-aee0-ba791184968c | note | – Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
0f25a3c8-01a3-56b0-a812-eee8283d72ad | note | Method - Visual
bd804190-8511-503d-a39b-e8990f5ac9a5 | note | Frequency - Each Lot
da4fb769-fc92-50fd-a09d-03417870346e | note | Category - SP
7c84510f-8fe2-5e8b-abab-932db9a063c4 | note | Responsible person - SE
ff35041b-9935-5445-9d2d-5ffc9a170570 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.9 - Backfill-Under area not to be paved
d3c78002-8c9a-59e7-9daa-508972f23950 | note | Reference - VR Section 701.19 (a) ii
8af641fd-1fda-597b-b813-2a5226a4e238 | note | Acceptance Criteria - The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
de84b64b-9026-5cee-992a-7b013a973b94 | note | Method - Visual
412b5cc2-0718-5eab-a377-a054207a6a76 | note | Frequency - Each Lot
a9c43f0c-daef-5277-a49d-7ec38b0946ea | note | Category - SP
7a38a625-369f-5770-b35d-20fce2c96de0 | note | Responsible person - SE
67845464-c69f-5baf-91de-be3258311d05 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.10 - Backfilling with cement stabilised sand
ba881519-3ba4-5a77-876f-0d4aedc2faea | note | Reference - VR Section 701.19 (c)
2e34911f-e716-52f4-aec4-ebfd4e84cdb0 | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height.
06f6c3f3-0f4e-5a21-8a38-fa8a144519c0 | note | Method - Visual
ba61c2f1-2137-5bd6-8787-2bc9524fa39a | note | Frequency - Each Lot
0a199f0e-677b-5b85-8231-11fb744c8bce | note | Category - SP
cd3aea3a-a12a-5cd4-8df9-066b022e8e8c | note | Responsible person - SE
31050f64-9359-5a4e-b904-f3bd9dd4c23c | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.11 - Backfill Placement
579ea0ce-44d6-558c-b890-6da5fe47bab5 | note | Reference - VR Section 701.20
86ce0d1f-82ce-5c3b-9778-b1c803d4ba67 | note | Acceptance Criteria - backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
b9d8e8be-4929-58ef-8a4f-b84a928cee0d | note | Method - Visual
3cde6f2c-2800-53a7-ac00-306bfb32190d | note | Frequency - Each Lot
a6703015-fdec-529a-b991-9d1c8e763d6f | note | Category - SP
b427c085-9b47-51fa-99fe-c93b1a2b319c | note | Responsible person - SE
2eceac5f-06d0-5160-a08a-5ac1ae050460 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.12 - Backfill Compaction
c5a32cbe-5230-5785-889f-959986f9101b | note | Reference - VR Section 701.20 (b)
13bf021e-9323-5215-9436-5a5742886f44 | note | Acceptance Criteria - 20% of all bedding/Backfill layers for each culvert shall be tested.
2c52073e-5ea2-581e-9245-de5b08e613a2 | note | – Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
7fdcb984-c725-5e7c-8345-b01f3f9c3eb8 | note | – Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fbcb7ad8-358d-59ce-9b66-cc80801e37b3 | note | Method - Test
669e4b01-823a-59c0-bb8a-6bf0a4891919 | note | Frequency - Each Lot
755a42bb-0ecd-506c-a0b4-b8e1db31f1c2 | note | Category - HP*
d5160f74-0976-5700-9c8b-3b42caab0dad | note | Responsible person - PE
4a87bbd6-2243-5d60-9f68-402626817961 | note | Verifying Documents - This Checklist Signed-Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Compaction and Moisture content tests
53daef47-5f04-5d2a-aa52-666b3f310e96 | note | Reference - VR Section 701.20
0ca32cb2-abf4-5a6b-aa53-0b1aa7cae807 | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
7abf9a95-a6b7-5bb2-8719-a12bb98bda8a | note | • ATTACH: Compaction and Moisture content test results:
e1ec9efc-d34e-5ee7-a2e9-430e62a2fde7 | note | Method - Document Review
ba29cebf-3403-5931-9785-f90a52fe53f2 | note | Frequency - Each Lot
309df2a0-9210-5e19-a306-891b9024ec45 | note | Category - IP
d73a6a6f-ec7c-57d4-b704-cc243f62f46b | note | Responsible person - SE/PE
1e6337e9-6996-53a0-8541-26e1c1738bd1 | note | Verifying Documents - This Checklist Signed-Off
a237437a-7d93-560c-8368-1a3ca7ac882c | note | • Attach Test Results
| checkpoint | 6.2 - CCTV Inspection
4204d85c-3122-5c24-9ead-455387507840 | note | Reference - VR Section 701.30
c7e55f01-5b1e-5412-bbf6-6a5199ee6609 | note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
534affc0-3c6d-5bea-8dc9-2005ae0fbbec | note | • ATTACH: CCTV Report (PDF)
931c2d3d-0e3b-5dad-8f67-e68d1fdd42f0 | note | Method - Document Review
0c6bd963-f85e-5d20-8c37-1352cc20bd08 | note | Frequency - Each Lot
00f4e48e-9af7-5c7e-9ee4-944a85eeae3b | note | Category - HP
ee58b695-f292-599b-b319-35c35833ca64 | note | Responsible person - Nominated Authority
737bc00d-6d8e-5afd-8b05-4368f350a533 | note | Verifying Documents - ConQA HP Release
ddebd2e8-da05-5192-a341-0ad54af13437 | note | • Attach CCTV Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
19e88502-33ee-55df-8d6e-62cf37895e68 | note | Reference - MRPA Quality Management Plan
f38364ae-3f30-5906-b39e-2098e27bd0c9 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
8970a0cb-f6c5-55f4-983c-7f4891888966 | note | Method - Document Review
90c95c4e-864a-50f8-8f8b-fde2664b21fb | note | Frequency - Once, prior to closure of this lot / element / Work area
d409339d-7dfa-58ce-8a68-a42352a2adbe | note | Category - HP*
1b2e97f7-2498-584d-a23a-96217de73369 | note | Responsible person - PE
f2ccecb7-ff22-51c5-8293-4c696f94d65a | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | Final Inspection
496fd5a6-ee80-5024-966f-622e9435eb5b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
07efe473-6fa8-5a4f-97eb-1e2f343ba5e0 | textbox | Name:
dfe414ca-ef6e-5840-ba07-e02dd379dd94 | textbox | Position:
b32ddedd-a1ef-5266-b966-228f8fbf2d43 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-002-CIV-Stormwater Drainage Pits Installation | itp | CHK-002-CIV-Stormwater Drainage Pits Installation | 7414c945-a4a0-4690-bc0b-05087ccd96fb
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
f59bd179-5879-5840-aee0-16ee86ef27c8 | note | Document Title: CHK-002-CIV-Stormwater Drainage Pits Installation
1412a00e-2570-5053-b894-82ef6d077511 | note | ITP Description: Stormwater Drainage Pits Installation Checklist
d5c200c7-2087-5354-874c-5f9b907a86ba | note | Discipline (e.g. CIV/STR/RAIL): CIV
d4354a69-d68e-5a38-a017-fbe34f60ab83 | note | Revision Number: 0
a34e1983-67b4-5d51-aaf1-4eb68a67447a | note | Revision Date: 20/06/2023
9fd7cd56-fb67-5782-86b8-9ea0bf4d0ecb | note | ITP created by: Kamel Alshobaki
ce015939-e704-5c36-bb9c-18dc525bea34 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
ccfaf275-1583-581a-be42-8900c0fe9a4f | note | Reference - VR Section 701
| checkpoint | 1.2 - Non Dependent
02d3b240-5119-5ab3-a32e-2824dcc9b105 | note | Reference - VR Section 705
| checkpoint | 1.3 - Main ITP
31627591-3b94-5448-b03f-11f62ff1d628 | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
76684e03-f1b8-5520-ad18-1c35637e8f2c | note | Acceptance Criteria - This Checklist should be used in conjunction with ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
159191b6-d1ad-5213-af76-a04a55a1bd1c | textbox | Enter: Main ITP Lot Number
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Bedding
8af0af7d-55ee-56ee-9a9f-6213884936c1 | note | Reference - VR Section 701
645061fd-99c8-5978-800f-b93df91f59a5 | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
31fc2a6c-c822-5d9b-aeb1-4937b1e3fdd4 | note | • ATTACH: Bedding Material Delivery Docket
1de837a3-a696-504c-8327-84630219f4d0 | note | Method - Document Review
8817ce7b-cb8c-5f71-b664-f600596f2ebb | note | Frequency - Each Lot
97715193-85a2-5900-9715-01cd53fbf96e | note | Category - HP*
8944d2d7-05d4-51ca-b16b-1b60a7cb3302 | note | Responsible person - SE
81190533-9cf0-5992-8b0f-40a3694f3ae0 | note | Verifying Documents - This Checklist Signed-Off
d7b1d269-0a88-5dfc-9963-91b23d07cece | note | • Material Delivery Docket
| checkpoint | 2.2 - Backfill Material
5bdb41a5-dd16-572e-bc79-0fa6ab563afc | note | Reference - VR Section 701
fe9e0ad2-6dbb-5993-84fa-4e868b8aff5b | note | Acceptance Criteria - Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
1779fd26-0c1c-57c7-88db-03b16bcfd546 | note | • ATTACH: Backfill Material Delivery Docket
5faf6374-7df8-5d67-9b1c-a2c460220012 | note | Method - Document Review
f42ba87a-2294-5990-9636-f3b44380cf35 | note | Frequency - Each Lot
8d8df435-e9b8-5d12-b9c5-6256ddfb2349 | note | Category - HP*
86b8a1e4-3c89-59fb-a018-deb45a4b97aa | note | Responsible person - SE
be21ab9b-d81c-5f6e-b996-4cdfdee76759 | note | Verifying Documents - This Checklist Signed-Off
f4f9158d-8b99-502e-b710-d3640eb89ea5 | note | • Material Delivery Docket
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Subcontractor QA Submissions and Approved ITP
3b726df6-22f5-5f3a-995b-22d620e2a4e7 | note | Reference - ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
9b5ead92-50ae-5e44-93cd-673042cb5471 | note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
bff24886-bf69-5c91-a605-92ff21201fb7 | note | • ATTACH: Subcontractor Signed ITP
e1aff119-ceb8-5933-b55f-0725acf408e1 | note | Method - Document Review
83d071fa-77b9-51d9-bbf5-25d8d02adf27 | note | Frequency - Each Lot (in case undertaken by subcontractor)
09172ac0-76d8-5be7-a1d7-d0f7fb4b1af3 | note | Category - HP*
1aff64e7-64b7-5b73-a14d-f6b894fb4cb4 | note | Responsible person - SE
d2df3f76-2f71-5516-9c63-4040c7cfb210 | note | Verifying Documents - ConQA Hold Point Release
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Survey Set-Out-
aebb569d-53e8-505e-b427-200b43347638 | note | Reference - VR Section 710.10
4a318685-a67f-5077-873e-055a34cfd19f | note | Acceptance Criteria - Prior to commencement of excavation the Contractor shall confirm the position of pits with the Superintendent.
1485c923-e5e7-5b15-9c3a-e9f7ef545229 | note | • PROVIDE MARK-UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
e84335c6-9251-520f-b239-8e7d55038ce0 | note | Method - Survey, Measure
1b4f81a6-9b35-509f-b098-e0f508bdf3e2 | note | Frequency - Each Lot
8f722dd7-6925-5eb8-922d-ce0a9de37f56 | note | Category - HP*
447ae7fb-24e0-534e-83d6-708d85da5d10 | note | Responsible person - SE
2b4c6f85-1f1d-533d-a6f5-3e92b046637e | note | Verifying Documents - This Checklist Signed-Off
fecda949-4d8e-5fe6-8a4e-e68ac5e58152 | note | • Attach Main Lot Map
| section | 5. Construction Activities
| checkpoint | 5.1 - Survey Set Out
96ba2c41-ade8-5b3c-872b-0449b796a064 | note | Reference - VR Section 701.10
febdb240-e17e-5935-9edd-7041d0c0f566 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
2fe0adab-90a9-559f-924f-239c05f76b2d | note | Method - Visual inspection
b11af633-30cd-5ae2-a3ae-78b21551af2e | note | Frequency - Each Lot
b4ceb6fa-4808-5e42-bd9a-08a98b262b36 | note | Category - IP
e4b3c213-1b69-5033-8535-671203ef0eb2 | note | Responsible person - SE
a0048655-15a3-57fe-825b-ea73b8190ead | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.2 - Pit Excavation
98b0e06f-21f5-51ee-b939-49717b4c60fb | note | Reference - VR Section 705.05
6b412beb-ed51-53ef-bd05-02affce60576 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
f6b19b1f-f9e9-50e6-a9c2-e59609752770 | note | Method - Visual inspection
6fd21d8b-43ee-5c39-8cca-3b00cc8543dc | note | Frequency - Each Lot
791fd2e1-acd6-5a98-9cb9-121f18084f5e | note | Category - IP
aa6a4669-0b24-5e4b-8d75-28a1925cfe1e | note | Responsible person - SE
5d3db2cf-c36a-5dd4-8b6c-14720655e9cc | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.3 - Excavation of Foundation
b25520d6-0f17-5c93-8e82-20882d0a8f24 | note | Reference - VR Section 705.05
06634074-fb4b-52a1-a0d0-9ad41bb12274 | note | Acceptance Criteria - Bedding conforming to to 710.09 shall be supplied, placed and compacted to a thickness:
70806e00-c297-5a68-aa87-376c924ec2e0 | note | • > 80mm for clay foundations
4a7ff2fd-346b-5741-b9ff-70d4679974eb | note | • > 150mm for rock foundations
e6e67fb7-c9ee-5d89-9143-f0ec7e477cc7 | note | Method - Visual inspection
4ba1992b-40e9-5224-a3c4-0a962e186b2c | note | Frequency - Each Lot
96b3a43d-4d09-57c1-97b5-3e415b5ba180 | note | Category - IP
cfd96a48-268a-540b-be33-da9a75a65135 | note | Responsible person - SE
a7dcd240-6c37-5157-a7e0-60f7f24deb46 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.4 - Placement of Pit - Conformity with drawings
c298dec4-1a1c-5e61-9e4d-c0041b4e6c3b | note | Reference - VR Section 701.10
4b272ff8-265b-55ae-a96c-d92e47f086d9 | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
44235dcb-f761-5c2b-bb52-4b37fe565597 | note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
9bbca292-c416-5ed1-839a-4b9522a17070 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
fcfdeabc-fba9-55df-9041-df9b7fb8b7bc | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
8424613f-af2a-58a9-9e33-d18c33d269d6 | note | (c) invert level of pipes at pits ±50 mm
6c9168e5-bb80-538e-a8e6-d31097ae6ca2 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
8da785b4-f829-5a97-b00e-c82f78b128d4 | note | • ATTACH: Survey Report / Data
99ab7769-496c-5cd1-a28a-0f37c2bea2a8 | note | Method - Measure
3211f42e-3460-5d5d-a20e-a7401a7aacaa | note | Frequency - Each Lot
ad18a625-2f9f-5e1e-bc17-0291f96d3d68 | note | Category - HP*
2cf144a7-e711-5181-a2b3-2df58cfece2d | note | Responsible person - SE
beef68f1-490b-5b84-b185-25a1a76850bc | note | Verifying Documents - This Checklist Signed-Off
3b3ee72b-0bfd-586e-a1af-a6d29a4e53c3 | note | • Attach Survey Report
| checkpoint | 5.5 - Jointing
777a39d3-f01b-5b9c-8e56-adb186b4d395 | note | Reference - VR Section 705.11
d895977f-67d3-5a3e-bc0b-f998f2d54895 | note | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
e8f346a1-431f-5ffa-815a-11979163496f | note | • Exposed reinforcement shall be coated with an approved epoxy treatment
1d4177da-a149-5357-b2fd-dd4bdda65685 | note | Method - Visual inspection
cc6c5b84-725c-5003-b657-89dd60b593ef | note | Frequency - Each Lot
c711b88c-a6d6-5aa9-ab0e-01a549f1ffd9 | note | Category - IP
f4fc6568-2601-5413-92a6-71f5327b678e | note | Responsible person - SE
b8fc93b5-0b6a-5974-a389-6accf67c934d | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.6 - Shaping of Floor
4cd557a1-174b-575a-9760-3b7b2e400bab | note | Reference - VR Section 705.13
15066479-78dc-5d3e-96ff-73694870bb40 | note | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
95c11416-d73b-5c34-a204-aff067fcc83f | note | Method - Visual inspection
978f5ac7-78d8-5c09-9e27-cda12c9ba702 | note | Frequency - Each Lot
aadb179c-a01e-5f8f-870e-be4ded66f567 | note | Category - IP
11715a55-911d-52ad-a4bb-00864fc4c0ac | note | Responsible person - SE
b24ad414-dfff-5cc0-97d3-aa31746afcbf | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.7 - Step Irons
1e8f1cdd-f635-577e-a3d6-20cc0a9d406b | note | Reference - VR Section 705.12
0c5830a2-6187-5c21-8a2f-573818a55348 | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
e9844158-89c7-59d2-a9a3-43d65761999c | note | Method - Visual inspection
04a502b3-603b-5c0b-bc58-7783f4ac654b | note | Frequency - Each Lot
8150cbf5-9439-52dc-9816-58e668ae2ac5 | note | Category - IP
f28c3b0c-2085-5c02-b3ad-64c606b3530a | note | Responsible person - SE
add271e7-469d-5340-bb87-75612d3cadb9 | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.8 - Fitting of Covers
79372dc2-9f96-52ec-a609-06de5902f938 | note | Reference - VR Section 705.17
102149d6-f5ec-5f35-b7e0-87767275e443 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
533066db-40c3-51fe-a89f-cd3db695888f | note | • Height shall be within 10mm of the design level.
d5152618-321c-55e8-aa79-7fe6f7809d54 | note | Method - Visual inspection
358c6a64-f9d1-5395-936c-cd7c929343d7 | note | Frequency - Each Lot
398aee41-404d-509d-8277-e6b4fdee1863 | note | Category - IP
ee6e0b20-2558-5362-9bfa-bf5db20b649a | note | Responsible person - SE
8f9ed847-56e9-599e-b2b5-c5fc7923644a | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | 5.9 - Backfilling Around Drainage Pits
2150627c-7c74-5bda-be1e-ffda710059e2 | note | Reference - VR Section 705.18
de5cb25c-0b36-5703-876e-c1bd8be09169 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal.
45a86d4a-f83b-5535-9575-4b794bd8bf76 | note | Method - Visual inspection
21f3cc3a-3755-54e5-9efa-373af3b709c2 | note | Frequency - Each Lot
b70019e6-0b70-58df-ba32-745e50b4696d | note | Category - IP
ec6fb8d3-0c7d-52e6-955e-8dfb9e4503f3 | note | Responsible person - SE
919c527f-7b59-56e6-8bd9-9579ad0db14b | note | Verifying Documents - This Checklist Signed-Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Compaction and Moisture content tests
0164e669-65cb-596b-afcd-6bd750ca1ddf | note | Reference - VR Section 701.20
e6839a1b-de1c-5aa8-bb34-2bc74576eec4 | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
1f52a655-1729-582a-a4e9-03f33b814fc7 | note | • ATTACH: Compaction and Moisture content test results:
6d043e8d-1a2a-5fea-8cca-3bd84a35208e | note | Method - Document Review
d8b7ecdd-74ac-52d6-b4c4-da1f683587a2 | note | Frequency - Each Lot
cc956f8a-48fb-5692-ad62-c0661dc079da | note | Category - IP
ed37b60f-f5e3-5ce5-a7f9-2107124d0d89 | note | Responsible person - SE/PE
f1627ae5-3bd6-596d-aa87-121bc45a888d | note | Verifying Documents - This Checklist Signed-Off
22435112-adce-53d4-b8dc-d25cfaf8a21b | note | • Attach Test Results
| checkpoint | 6.2 - CCTV Inspection
5ca32182-9538-5d03-8561-0cf7e24fd583 | note | Reference - VR Section 701.30
16822ded-fbd1-57c1-a816-d79ae699d760 | note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
2561f72f-4cb9-5bb9-8068-1fe8c992c862 | note | • ATTACH: CCTV Report (PDF)
bd69d936-d8ff-5033-b185-6e28d0c51985 | note | Method - Document Review
0e2cc413-98fa-57d6-90e0-3b064f0151cc | note | Frequency - Each Lot
61b3ea4f-e3a6-5186-babf-c6c507b93a3d | note | Category - HP
dfe97c78-9e5e-5849-a088-9c00e9326050 | note | Responsible person - Nominated Authority
244e18ef-a8d0-5db5-8fa9-522c9c201299 | note | Verifying Documents - ConQA HP Release
d0ffbe5d-1b76-55be-9935-0842fd234441 | note | • Attach CCTV Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
7bf09ad0-0f54-574e-8c14-a50a01a61315 | note | Reference - MRPA Quality Management Plan
8570bd23-cff5-59dc-956b-ac573edc46e0 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
ca6d3449-6cab-5948-b857-ccea6fd7c3a5 | note | Method - Document Review
9430d7b1-6571-58b5-82ca-f7aaab7ce1b5 | note | Frequency - Once, prior to closure of this lot / element / Work area
1477ae97-1afb-5ee9-8612-fd4a6b3eebaf | note | Category - HP*
425ed2e8-b010-544d-ba32-0b27d099bf36 | note | Responsible person - PE
e1f7cab7-f23b-5b3a-ad94-789041e6428f | note | Verifying Documents - This Checklist Signed-Off
| checkpoint | Final Inspection
44998d2a-42cd-59b8-95b5-b05e15b13e4c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5c356b69-2d02-57bf-bb59-f25ca9b69f7a | textbox | Name:
dece4c80-4120-50ff-b342-241d43b2cdc5 | textbox | Position:
7a0000ca-6c8d-5d59-a36d-75730a413790 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | itp | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | ff9eef7c-b76e-4ebb-adde-76ac9eb4fd12
| checkpoint-no-value | Referenced Documentation
ca058ea5-8c87-5e65-8a7a-c55d60fc3bb1 | note | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
ca51afac-b065-5024-b5d2-4ed023f8bf68 | note | ITP Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
6c8d57fd-4a64-5ddc-9007-a99936afaaa7 | note | Discipline (e.g. CIV/STR/RAIL): CIV
571fbc40-7f9f-5ba9-8fd5-102081e4d637 | note | Revision Number: 0
7b12ef80-3036-5b54-a129-47ead4e7e414 | note | Revision Date: 20/06/2023
f91dc7a5-1494-5490-9d1f-7f3a6b4a6779 | note | ITP created by: Kamel Alshobaki
844db0de-8120-54be-b60e-7a2a273b9915 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1 - Materials - Fabrication
2afe560e-8a8e-5d75-b1bd-e80897526766 | note | Reference / ITP Reference - IFC Drawings
f03010f3-ae40-55e9-a154-a9b9722893a0 | note | • Section 620
6f0132bf-69b0-500f-b8d9-f9d1acb54445 | note | • Section 701
f39995d6-46b1-57ab-ade8-b7697051c4c7 | note | • Section 705
2dc3073f-d70c-51c0-a62c-8eb4600387d5 | note | Acceptance Criteria - (1) Precast items manufactured in accordnace with IFC Drawings
79ee452b-5933-5e26-82a0-9a2b25162578 | textbox | Drawing Ref No.
db09458a-8dfb-51cd-8a89-5985011d413b | note | Method - Visual Inspection
7d4ec4ab-52da-5c46-8416-6cc7b90cc60c | note | Frequency - Each Lot
80566e82-963b-559d-997a-c381681e6f6d | note | Category - IP
25bafebb-935c-55d4-81d9-c500c534d519 | note | Responsibility - SE
5ee6b328-4e1a-5f23-95ac-17b8b6c1d220 | note | Verifying Documents - Material Delivery Docket
| checkpoint | 2 - Materials - Delivery
0d4b9058-4228-5584-94c0-52b51596a64f | note | Reference / ITP Reference - IFC Drawings
16f22079-b753-5259-afee-cd57e168ca34 | note | • Section 620
2bae689f-3a62-5b0b-ac05-2e8db04e5583 | note | • Section 701
d7bf7983-01bc-524a-ba29-f45637c19686 | note | • Section 705
aa362452-0cdf-51c4-8501-e5a04236261a | note | Acceptance Criteria - (1) Purchase Order and Material Description and Qtys matches
be31409f-4b88-586f-ab6a-ad76d7636717 | note | (2) Ensure precast concrete elements are as per IFC Drawings with no damages upon delivery
38ed00d5-8df2-583a-a915-c2ce93be9c43 | note | (3) Lifting and Manufacture compliance certification provided
96f410f0-4951-56bf-8391-fe27223b48bf | textbox | Purchase Order No.
c76177b2-7387-5a86-932d-86d0dd87291d | note | Method - Visual Inspection
9379ef11-fd13-5c56-9d9f-f4e19e5ea75a | note | Frequency - Each Lot
bf130132-8e63-569c-ac4b-f71c1138b79f | note | Category - IP
a4af80b5-a8b6-5bc4-98fb-2a50be6a273c | note | Responsibility - SE
e6138e48-c7f3-5862-a0a3-0fbf9cd671c7 | note | Verifying Documents - Material Delivery Docket
65bb8a6e-0f56-586d-a729-a2e8893d766b | note | • Purchase Order
| checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
687028d4-ab51-5347-906a-14413c6907f4 | note | Reference / ITP Reference - IFC Drawings
14bc78e2-a496-57db-b460-160f378eb575 | note | • Section 620
fdd00bad-aff9-5b84-afb0-fc78ff71c65b | note | • Section 701
74c1408d-1170-51d6-92ea-b8e22270b176 | note | • Section 705
22040989-7877-53b7-8f7e-ea3ea19c7330 | note | Acceptance Criteria - (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
21da3e72-7c46-562b-93bf-576934b075fd | note | Method - Visual Inspection
77022cc2-4959-5ca4-b5c5-3a93e76870af | note | Frequency - Each Lot
b6e0646d-2aa1-5d9e-8b92-206a8190fc1d | note | Category - IP
17961cf4-4f99-510f-a14f-1fc26c379fd9 | note | Responsibility - SE
91f9fc94-cafc-5e30-9719-f566af67b5cc | note | Verifying Documents - Material Delivery Docket
c5cc54cb-851b-56ed-b30c-4f1e2d4548f4 | note | • Compliance Certificate
| checkpoint | 4 - Materials - Delivery to site & Storage
5d6f12a3-fb0f-5a96-ad9d-fc99ab90fb02 | note | Reference / ITP Reference - IFC Drawings
c442ddd8-83ee-55c1-96af-100e862c20bc | note | • Section 620
9b152493-ed1d-55fe-8a9f-4ca1889f7e50 | note | • Section 701
c1041134-f97b-5980-9d8c-652c20de5260 | note | • Section 705
5570f4b0-29e1-5e29-8d91-c5839627f8ef | note | Acceptance Criteria - (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
6c79a671-baa9-5e41-833f-d3d8b84628ba | note | (2) Precast elements are unloaded and stored properly on site as per manufacturer's recommendations.
cf0d0994-1fd9-5a30-94d7-a0201069e0f8 | note | Method - Visual Inspection
3b7d96c8-4b44-50a8-b6cb-e3f471b4a248 | note | Frequency - Each Lot
cb9e7dbc-a933-5d10-8720-65bfbbcc0f3d | note | Category - IP
df384184-3a30-5ca4-84f5-b39c10b8efda | note | Responsibility - SE
4a5b82c0-1d15-5e8b-8080-19c75835b580 | note | Verifying Documents - Material Delivery Docket
| checkpoint | 5 - Materials - Others
aa74b915-0cdd-5d64-bafa-ebd15db9b9a3 | note | Reference / ITP Reference - IFC Drawings
d18f61a4-cd48-53ed-9080-df2e8f09b8a1 | note | • Section 620
09472dca-f89a-5543-83d1-0b136eb49a9d | note | • Section 701
e38c0d09-0a83-5f23-bb2c-7568685e7697 | note | • Section 705
4f1bd8ce-b26b-5fd7-8bad-6b02c75891b9 | textbox | Acceptance Criteria - Enter: Additional Comments
c3c3584f-2f97-50cb-89ec-895922371683 | note | Method - Visual Inspection
63c9bb3a-5b90-56e0-9979-a703fed467dd | note | Frequency - Each Lot
65d3f9fa-bbae-51f1-a7c2-79b738df3d5d | note | Category - IP
ce2fbc30-275d-55ac-92c0-81fdf0b90672 | note | Responsibility - SE
a7496a4a-3b20-5b7d-8910-b2af1d34e82e | note | Verifying Documents - Material Delivery Docket
| checklist | CHK-004-STR-BRUNT-RSS Walls-Fill Placement | itp | CHK-004-STR-BRUNT-RSS Walls-Fill Placement | f872f751-7a62-4676-b26e-0a51f944c2c7
| checkpoint-no-value | Referenced Documentation
278a10a6-e4ec-5bc1-8c45-c3195b9219a2 | note | Document Title: CHK-004-STR-BRUNT-RSS Walls-Fill Placement
251e01d1-ff96-54f4-8853-1edbee4feb67 | note | Check list Description: RSS Walls-Fill Placement
38e25990-2b7e-5df3-9dc5-ead2c5b33ea0 | note | Discipline (e.g. CIV/STR/RAIL): STR
22e7a8b6-ea4e-5b48-a9db-54495f4f67b0 | note | Revision Number: 0
bc86167f-ec4d-54a2-a733-64e09f8ac350 | note | Revision Date: 12/07/2023
e65347c9-9a36-5d40-afa0-be874d0cd330 | note | ITP created by: Jon De Castro
da4f64f7-c3b8-5e20-a51d-f5c1b4603a42 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1 - Soil Reinforcement-Straps
67e9ba7f-218e-5389-a589-74c96928bd44 | note | Reference - VR682.08 IFC Drawings
69000eb9-221f-5c94-82cb-e6a689e0f53b | note | Acceptance Criteria - Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
c538f65d-d0b7-5d62-a94a-964eff6c69f5 | note | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
b48b9b94-8f7f-5f56-80ea-89082aace4d6 | note | Method - Visual
6eb4f298-5507-55bd-abb3-85f668f356a5 | note | Frequency - Each strap
d293b35e-c5ec-59c0-b155-94d1ebb6b8d1 | note | Category - IP
969bf309-8d15-5ae1-a7d4-93bdfd5e70de | note | Responsibility - SE/PE
a7199577-b822-5d2a-bcda-b93c03d20776 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 2 - Soil reinforcements-Connections
5547f3db-56d4-563a-be15-5df94863d28b | note | Reference - Installation Manual
b4bf672c-3515-5e9d-a235-78d56c9f6470 | note | Acceptance Criteria - Correct number of reinforcing element shall be attached to each panel
bb0aa684-bcfa-565b-b2bd-b2364c78f8f7 | note | Method - Visual
3f4d6a11-d4cd-50da-85cc-d317e3c267cb | note | Frequency - Each panel
3c793b80-bd0c-5a98-b38f-e729d5c9be59 | note | Category - IP
88cd61fc-7908-5b70-b06d-0864aedeb8f7 | note | Responsibility - SE/PE
063b709b-190a-575a-bf28-3c016978a01f | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 3 - Soil reinforcements-Connections
f560918d-b18e-52bd-b071-689c04ba00fc | note | Reference - IFC Drawings
b03d5ce6-c2ba-590c-a33a-38b20e55fdd2 | note | Acceptance Criteria - Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
0c0380ad-98f5-517e-8361-2ccb66cd0ff8 | note | – Bolts are to be snug tight.
a5971568-3ff9-5456-a5f5-05e8e78eb440 | note | Method - Each Fill Layer
d2fb84d8-87a0-575f-b914-70da2a9629b5 | note | Frequency - IP
7877cd04-c118-56bd-9565-9b844d5478a2 | note | Category - SE/PE
31d9c2e9-fa2b-5e3a-91b0-d861e57ebb76 | note | Responsibility - This Checklist Signed-off
77d51b60-542f-581c-bb80-a75e7a82d835 | note | Verifying Documents -
| checkpoint | 4 - Soil reinforcements-Plan arrangement
bd786473-9ed7-50dc-916e-131ad2535be3 | note | Reference - IFC Drawings
eb38a1a0-c680-56b8-878b-84e33e6dec64 | note | Acceptance Criteria - Plan positions of Grid Strips are to be as per IFC Drawings.
ce1b6a6b-c9f4-5dab-960b-d7b6f08f21e6 | note | – Grid Strips shall not overlapped
4ad919c6-366f-5a2d-a0ed-5e7cdae490ec | note | Method - Visual
5835ca14-252c-5e41-8f3b-45b459539b4b | note | Frequency - Each Fill Layer
3b05dd27-72a3-5a58-920d-a9098f39db98 | note | Category - IP
98c74862-c78e-52ff-88e8-6c8217c41d73 | note | Responsibility - SE/PE
108bd89b-34c0-55c9-9629-57c914573dca | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 5 - Soil reinforcements-Plan arrangement
83d1f9af-7312-596c-8f2a-93d2c4d6d0eb | note | Reference - IFC Drawings VR682.06
f67744a7-175a-5ca5-9bf2-b2b08cbc9aa2 | note | Acceptance Criteria - Plan positions of Grid Strips are to be as IFC Drawings.
60c854c7-9bab-5282-b310-380f2b1cece9 | note | – Grid Strips are not to pass over pile cap. RSS used in conjunction with a bridge abutment shall be independent of the bridge structure.
efa76dcf-f398-5b43-a344-eda0793ddd6a | note | Method - Visual
42b5e342-8fb7-5993-ad8e-0c39b73786f6 | note | Frequency - Where applicable
dda291bb-8784-548f-9752-0ad4008876aa | note | Category - IP
719f619a-5905-58a5-9645-82af7ea52df1 | note | Responsibility - SE/PE
05b6b8d8-44ea-5718-a332-3f322f722545 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 6 - Soil reinforcements-vertical deviation
7a79652b-dbfe-5131-9510-72c110cc6b00 | note | Reference - IFC Drawings MRP-052-C-RFL-DRG-33-CBE-CSW-1702
0952434e-7a28-5212-bbf6-9c8f1a9605bf | note | Acceptance Criteria - The vertical deviation of the soil reinforcement shall be within +1% (upwards) and -0.3% (downwards) of the soil reinforcement length, relative to the connection height.
43d2c379-3b6c-59bc-8a64-1b5f0357e218 | note | ○ Avoid clash with drainage as directed in IFC Drawings.
73a1638f-9483-53b4-b43f-d1491984823d | note | Method - Measure, Survey
962f9ba3-7828-5db3-91d3-62817075c524 | note | Frequency - Each fill Layer
0e1542d1-d60d-5515-825d-b44562d1acff | note | Category - IP
1e90831a-bf16-5abd-a71f-f8b9ef898923 | note | Responsibility - Surveyor/SE
d42a7068-9935-56cd-ab8c-49c3a0d464fd | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 7 - Fill-Pacement
e0983f52-f216-5200-958a-d881ef783940 | note | Reference - VR204.10, VR682.16
9bff919a-59a5-53e5-84e8-df3ee7d962b1 | note | Acceptance Criteria - Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
bd5c90c3-aca3-5eaf-b7aa-95068b474fd9 | note | ○ All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps.
59b58a95-e337-5bfb-933e-c586fe70d2a3 | note | ○ Plant or vehicles shall not be allowed to traffic over or work on reinforcing elements until the reinforcement is protected by a minimum 150 mm layer of fill material.
8c534dbd-5a56-5e81-853f-aff9d1880641 | note | Method - Measure, Visual
abe2a3a2-7bf9-5775-a5b9-dcbeb7658761 | note | Frequency - Each fill layer
fbc7a50a-2f31-5b33-a30c-82a9e70db473 | note | Category - IP
c48acd7c-ca6d-5950-bb72-711352cc749c | note | Responsibility - PE/SE/Supervisor
5f993c76-02c6-560f-9516-65d578bb62b5 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 8 - Select backfill-moisture content
cba4dca9-a81b-5912-b394-a0a7db3afec9 | note | Reference - IFC Drawings
15b6c343-3f1f-5218-a5ba-79de08ded6e5 | note | Acceptance Criteria - Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within +0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry.
8f347cd5-8266-5e76-8584-0c8f31e1405e | textbox | Attach Test Reults
1c88671b-42fc-5342-85d4-79e92c6c0793 | note | Method - Document review
48811520-3203-5b3f-abb3-225a913330fb | note | Frequency - Each Fill Layer
153ec488-1a32-50fb-b4dc-4b3882b6f564 | note | Category - IP
08f7265c-eb4c-5b5a-8890-be9f432b2f81 | note | Responsibility - PE/SE
ff00a782-bc03-5f04-96f5-a98e9abd7741 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 9 - Select backfil - placement
d0ac4e7a-1007-5cfe-a283-f452f06aede1 | note | Reference - IFC Drawings
7eb6a73e-c6d9-521a-b549-3c0b57a6b77e | note | Acceptance Criteria - Select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
4897bc10-63a2-5f50-816e-d119477c3746 | note | ○ Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with Temporary works design.
c25bcd2a-bd3e-5385-b722-d593d0ed5f68 | note | Method - Measure, Visual
3d853783-3e39-5b4c-865a-12a60abe864b | note | Frequency - Each fill layer
7ab3f82c-081b-5ac2-9738-851f29b6a864 | note | Category - IP
559d83d3-08e6-5a06-8009-d629e7889b59 | note | Responsibility - PE/SE/Supervisor
42c7ace5-7a06-5a25-8625-05ed2d479cf1 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 10 - Test Roll / Proof Roll
f6852064-f06e-5776-866b-6a4f3adf06b5 | note | Reference - Section 173.03, Section 204.12
e29e958c-6b20-5117-b145-58b80b6ec74a | note | Acceptance Criteria - All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
c626d566-a2be-560d-9d86-8ce40d8a0096 | note | Method - Visual Inspection
96731eb8-2d9b-5e60-b86a-f4433969c3aa | note | Frequency - Each fill layer
07269b66-70b7-5789-a478-61f200799769 | note | Category - HP
bce736af-6120-5586-9be2-4ce5758b985d | note | Responsibility - Nominated Authority
509ee4a4-3db0-5258-8d66-8333935261d0 | note | Verifying Documents - This Checklist Signed-off, ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 11 - Compaction and Moisture Content Testing Frequency & Acceptance
a4215ff2-5e72-5bf1-af2c-782f68984a3e | note | Reference - IFC Drawings VR 204.14 Table 204.131 VR 682.16
20a11e53-7338-598c-8a48-662ae7ba88e9 | note | Acceptance Criteria - Testing frequency shall be in accordance with Vicroad Specification section 204.14 (Scale A)
804ffa05-ba30-58c0-a80b-3f3508a72cba | note | ○ The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
f4885eaf-5f4d-50e3-88fa-48c4e7531f3c | note | Compaction Requirement to be Scale A:
a1f439bf-2d66-5325-94cd-84ad87d33188 | note | ○ Characteristic Density Ratio 99%. (6 tests per lot)
c5119e78-7a91-5adf-a5c9-a1f54f2aa19e | note | Lot size:
52b19582-af59-51bc-bcaf-5b678be36df3 | note | ○ Type A Material - the lesser of one day's production or 5000sqm
515a13f9-2bdc-584f-be54-a8a5caf3ff99 | note | Attach: Compaction & Moisture Content Test Results
b793f44b-36e5-5616-a5f4-18ed322b8565 | note | Method - Review Document, Measure
4803c4bf-0173-5b97-8bed-8e0e715c60b2 | note | Frequency - Each Fill Layer
33bf608d-5659-5b2c-833c-1e56b77e61d8 | note | Category - IP
f75e31a4-4286-573f-96ea-e8b09bbbde9f | note | Responsibility - SE/PE/SPE
486ed48d-2dff-55d4-87a5-8bb84e5ec59b | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 12 - Post Compaction Material Property Testing
e05624fc-7403-5bdf-8eb8-8edb15965d5b | note | Reference - IFC Drawings
10daa4a3-10a7-5de2-8130-de627dc4f359 | note | Acceptance Criteria - Material Properties Testing (Scale A)
96258462-e88c-5450-bbba-dd719143d5c1 | note | ○ CBR ≥ 8% and Swell ≤ 1.5%
ec13f130-deab-5b67-a174-82159ad1f643 | note | ○ LL ≤ 30%
abee187a-ae68-5dc7-9a78-d56b6fa7527a | note | ○ PI ≤ 12%
fa4fe2bd-7b05-5d86-8540-bc8dacf0e697 | note | Grading:
1a6e715f-9cb0-50db-bda8-05756563b1c7 | note | ○ 150mm 100%
f88e939b-196b-53e7-916c-35d2e03ac0b8 | note | ○ 37.5mm 60-100%
fd1b4035-9192-5baa-b7b4-5d7eaa152a3d | note | ○ 9.5mm 25-100%
9726b05d-5c82-56d4-8bf2-c04cfede9095 | note | ○ 2.36mm 15-100%
5922e582-0c0c-5f2b-ba58-7e704908c37b | note | ○ 0.60mm 10-100%
c6ec6076-4fdd-5479-83b4-d72145e751d4 | note | ○ 0.075mm 0-15%
d6a1a30a-f658-5a7d-94df-5dbbd9758642 | note | Select backfill must meet the minimum requirements of VR Section 204 for Type A Filling.
6ae70c3d-7d67-5c69-ad06-273fe3f5372b | note | Attach: Post Compaction Material Property Test Results
cad55619-e2d5-5481-b12b-8f1910c2fedd | note | Method - Review Document, Measure
46048de7-5c78-5baf-a748-32acc0fa5af3 | note | Frequency - Each Fill Layer
ff815915-355e-5f5c-a313-d08023d20d76 | note | Category - IP
f35aece5-721c-5ec2-b00e-fc0e572df9d8 | note | Responsibility - SE/PE/SPE
7be02c3c-51a9-5076-9579-09fa6b52af49 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 13 - As-built Conformance Survey
a3c16ce5-1996-585f-be86-eec6490cbdf8 | note | Reference - MRPA Quality Management Plan
33edd09d-c301-505a-afba-6db4606bf5b6 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
892f799b-c2d9-598d-9a13-eb25a22f5f6b | note | Attach: Survey As-built / Survey Report
90c890fa-597b-57f3-af79-ed0778c1e28e | note | Method - Document Review
f6c9e511-edf9-5558-9498-e33f4debd5a7 | note | Frequency - Each Fill Layer
032ef670-f6d9-5fd4-bde1-6bae72fca271 | note | Category - IP
de7f778c-1d9a-5003-89eb-58fd4ab59723 | note | Responsibility - Surveyor, SE/PE/SPE
384a82d7-3bdc-5e6a-bd36-e905da8e9a70 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | Final Inspection
27f532be-ec5d-5cc7-ae85-8b99d2b3d2b2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
be95bcc2-5df1-5798-8dd2-7dfd02e5c872 | textbox | Name:
14f912b9-97e5-53a1-9a29-fe07eb239d5c | textbox | Position:
bf51b4c8-4ea8-540b-94b9-43bdfbc75138 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation | itp | CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation | 8ca584e0-141a-4ded-88f9-dfdc8f44c439
| checkpoint-no-value | Referenced Documentation
260f0fba-d7c4-50d4-a0cf-0073f02d0976 | note | Document Title: CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation
a4e9ee7d-0256-5482-9b16-ed2fd49ab071 | note | ITP Description: RSS Walls-Precast Panel Installation
a72e9f1f-7780-5ae7-9a86-1feba72d0fc8 | note | Discipline (e.g. CIV/STR/RAIL): STR
6ac80a43-d2da-5c6b-bab6-ba8c483a7459 | note | Revision Number: 0
10666bdc-99d3-5f67-98ce-7de3fd1a4be3 | note | Revision Date: 12/07/2023
b586f668-f413-59df-9461-1061f7746610 | note | ITP created by: Thilan Rathnayake
595b09c3-b4c0-5d73-9f65-68ae1159a50c | note | ITP approved for use by: Jon De Castro
| checkpoint | 1 - Panels-survey set out-Tolerance
5211a526-f2ec-5326-a9b4-20500dd095da | note | Reference - IFC Drawings VR 682.20
c8985b56-712e-5605-9771-fbf65a38eb03 | note | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
ff685a1a-6a7d-5721-8a54-a48696f6540b | note | ○ Above must be checked with surveyor prior to backfill
a2f9944b-5829-59fd-9490-9986437c5e48 | note | Method - Measure
7cb77c33-5f14-52b1-b0f3-58a164678abb | note | Frequency - Base course panels
5410afd1-baaa-576e-bca8-c8fc5bdc3074 | note | Category - IP
a39acee5-7b15-5902-ab33-51cfee216a3e | note | Responsibility - Surveyor/PE
4d4f6e7d-dc41-523e-97ab-d761d3e34c9b | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 2 - Mark-up panel for construction team
f1eafa38-bda0-5ae5-ba4f-9924f2b357d7 | note | Reference - Construction Manual
260c1114-5524-5bb2-aa0d-38d739b60a3c | note | Acceptance Criteria - Mark number of strips per row on the back of each panel.
a652d824-9b8f-5141-b95c-7b0b46c02657 | note | – Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
cedfd48b-27f0-5658-b289-ef85f8ec32e9 | note | Method - Visual
0340fe16-eb92-5222-8da3-734ba6f714a6 | note | Frequency - Each panel
a443ce58-3689-585d-88b8-4d48f1a5e237 | note | Category - IP
274d007c-3438-57b2-b33d-af625b58ea34 | note | Responsibility - SE/Supervisor
53242dbf-bf95-5e05-ade3-45558efd3dd5 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 3 - Panel installation
6f8ab849-a297-5885-a742-33b8ce377e53 | note | Reference - IFC Drawings
3816b97f-704d-50a5-a4ff-5fcedf3385ad | note | Acceptance Criteria - RSS Panels are to be installed as per IFC Drawings and specified schedule.
5f568e9e-5c4d-5e21-bdc7-44f60a32975e | note | – Check for correct architectural pattern
745cea8b-b508-56e1-b0ac-ee2c2498a780 | note | – Check for Weephole Locations
d7cc33a1-a2a1-501d-9c2e-afa9af383ab0 | note | – Check the 19mm nominal gap to be maintained between panels
1f24a168-8444-59c9-8319-b4d4a93af74e | note | – Check the min 1:40 slope to be maintained (RSS Panels must lean backwards to this slope)
6289cb6b-54c0-5060-a3d6-f80e2e6bd7d8 | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
e2a991e2-427d-5bb7-86d3-4b03ce36ea8e | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
07ecdae9-bc51-5c8d-b124-1b25aa2cc933 | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
510cde3d-b18a-54cd-afec-d96a787776fd | note | – the wall level shall not deviate from the specified level by more than ±20mm
f3b299fe-256c-540e-b053-cd5a61c0aadb | note | – the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
1963ac44-5a5f-56e4-ad5b-3016a769924c | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
9f5e8b44-5220-58b9-a761-96b5f81a1e0d | note | Above must be checked with Surveyor prior to backfill
2135dca0-4d53-5b5b-a1cb-acbb6685e16e | note | Method - Visual, Measure
55e78b70-782a-5a45-a507-3f24a488af4e | note | Frequency - Each panel
bd0966c6-fa63-5173-b842-607107cdf891 | note | Category - IP
4a51c2bb-a384-556b-ac77-fe99b9cc3ac8 | note | Responsibility - SE/Supervisor
a806dbde-8253-5921-8010-9896ebe004eb | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 4 - Panel installation- Corner Panels and Panels interfacing Abutment
09fbab31-763c-5104-9133-9a23580a005e | note | Reference - IFC Drawings
67a27126-7b97-5639-948e-ac6f1880cffc | note | Acceptance Criteria - 20mm nominal gap between panels and Abutment wall is to be mainatined
203813e0-838b-56fb-b2c3-c8079925d24e | note | – 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings.
0cfd6a62-f425-5d0f-a83c-e3c1810f1db5 | note | – 600mm wide BITAC tape installed
8b5010e2-2a4d-57f3-87f0-81a50c422d8c | note | ○ Folded plates must be installed installed at coner panels and panels adjecent to abutments
780ed63b-e87b-57fd-9ca5-cf9e3e03321f | note | ○ Above must be checked with Surveyor prior to backfill
1db0e448-4425-5a82-94c6-af433fa48bd7 | note | Method - Measure
b2c6f4ec-f7eb-55cf-affd-e902842dc86a | note | Frequency - Where applicable
0e432d82-64c1-50f7-b4ba-ffd3f9aed7c7 | note | Category - IP
8bb244c9-c2da-5f3c-9afa-063b53850950 | note | Responsibility - SE/PE
314acf63-1de4-52ec-9426-2ce3d01dc930 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 5 - Install Rubber Bearing Pads
6206b36f-0cdf-5150-8f7e-23b1013937b5 | note | Reference - IFC Drawings
a1a71677-1403-5053-88f5-481e9a68c70f | note | Acceptance Criteria - 3X19mm bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
df3890e9-4f77-513d-a83e-b77ad72d1d3e | note | ○ Above must be checked with Surveyor prior to backfill
e5232162-9939-51e8-9ee7-d3586acc3ff0 | note | Method - Visual, Measure
b32a0d15-36a7-5fa4-9344-8a0de58469e5 | note | Frequency - Each panel
1a6356f5-b8c9-50fd-b9b2-c1c8ca36ec0e | note | Category - IP
2acffb47-e1fa-58f4-8ebe-37b20cc15cd6 | note | Responsibility - SE/Supervisor
853ea9e0-dde1-5afe-9d0b-8674945724a8 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 6 - Filter fabric -Installation
a1c97ea3-2aac-5681-840b-370fdf2a49d7 | note | Reference - IFC Drawings VR 682.11
12a06542-6df4-5cad-83b1-106c9a53b4fa | note | Acceptance Criteria - Install Filter Fabric against all vertical and horizontal joints
8ec9c040-3be8-520b-9f29-ab2cd1ca8827 | note | Method - Visual
9c075862-dc5c-580f-ba0f-fc9d5b3b3929 | note | Frequency - Each course of panel installation
9e728eec-58e1-5e08-97ed-848c6aa11614 | note | Category - IP
24f49fc8-66e8-59d7-880b-cd9ca21798a0 | note | Responsibility - SE/Supervisor
1fb55feb-de04-512f-998a-e91ec9646cb3 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 7 - Drainage-Vertical Strip Drain
461c7572-009d-5445-9809-4aa4cd087343 | note | Reference - IFC Drawings VR 682.11
6e616bbc-aea6-5a94-ad26-dd28eb9dd981 | note | Acceptance Criteria - Install 300mm wide vertical strip drain as per IFC Drawings and in accordance with VR 682.11 at every vertical joint between panels in RSS wall.
fb6f2659-002c-5770-a23c-c8f76df45c44 | note | ○ Ensure no gap is formed between strip drain and RSS panels
35bdbb48-a5fe-5254-902f-1591699697af | note | Method - Visual, Measure
7e6caa25-f16a-504a-ab53-37a828013245 | note | Frequency - Each course of panel installation
c49de9c3-9d97-533c-bbab-98e684b7418d | note | Category - IP
7cb17193-4b68-5f14-9ff2-dc128269eccf | note | Responsibility - SE/Supervisor
59614ab5-7889-5fc0-942e-30e3e401880d | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 8 - Panel installation-Survey reference points
75e6faef-9aec-5896-802a-9d367e55e0d8 | note | Reference - VR 682.21
dbeac78f-e490-57a3-b1c2-54ab92a1b423 | note | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
a9af1f1d-d58c-556b-a3de-f858288b1df4 | note | Method - Visual
cc155fd1-c6f2-5bf6-b522-4906608a04c8 | note | Frequency - Each course of panel installation
c9f0183c-2017-5a5e-b661-65f9e8a556b5 | note | Category - IP
1cc4ddec-d556-5029-8fec-d3c8908ce4e8 | note | Responsibility - Surveyor/SE
e6082d36-1c18-5338-946d-bf399eb62f00 | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 9 - Traceability of precast units and records
eac59d6f-d222-5753-90c0-84722b566603 | note | Reference - VR 620.09
a6bd0a62-69d2-5d0c-81c5-6024c738a13b | note | Acceptance Criteria - Unique ID of precast panel is recorded.
ba9072b4-4d0f-5aa7-b9ad-4d5a09769340 | note | ATTACH: marked-up elevation drawings or installation record with reference to panel ID
3b444bea-4ec2-5855-81f2-e5ab5b676c9b | note | Method - Visual
921c7325-11ea-5856-9d12-316a89b238cb | note | Frequency - Each panel
4ef7a121-da06-535d-81db-ea6fae89cb19 | note | Category - IP
82617d76-ccbc-5c40-b604-e3da7b7cba09 | note | Responsibility - SE/PE
3f942fa6-1469-5e7c-b2e5-51032e1540bf | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 10 - Panels installation - As-built Conformance Survey
a2c95f36-e6be-547d-9424-2ffdf3131462 | note | Reference - IFC Drawings VR 682.06 VR 682.17 VR 682.20
1d4908d7-702b-53e0-bb8e-4fd5cdd4809e | note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
0a212629-632a-5ff2-9833-0faedb1b42d4 | note | The Contractor shall record the results of this checking together with details of any non–conformances and the associated corrective actions
c9b3f4e2-92bd-59bc-aa88-2faa1bf8f10c | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
24b7db75-ab0c-556e-bbf2-dce672761ef0 | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
0644ce95-67d0-5560-adb1-a03e117a9ba2 | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
0fbbad67-4588-50c3-931b-b0698a432444 | note | – the wall level shall not deviate from the specified level by more than ±20mm
68764baa-da2f-5e05-b9b2-af2dac847600 | note | – the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
90309008-0936-58b4-84e4-3aba1917ffa0 | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
18b44a79-1e97-5298-b685-11171d8cad34 | note | ○ Above must be checked with Surveyor prior to backfill
36bd4f20-b63a-54c8-b14c-61a81be556a3 | note | Attach: Conformance Survey Report
ca0a6014-a2d4-5843-aa20-ce6e479e6536 | note | Method - Survey, Measure
dce3d991-e3fb-5cd2-94e1-85132d4d3ebe | note | Frequency - Each course of panel installation
28d05d87-ce06-5a52-94ca-2307c90e714a | note | Category - HP*
9d534e6e-5be0-5412-9b79-b06110215945 | note | Responsibility - Surveyor/PE
f5324639-d3f0-5d75-9a9a-b1aa2bc7bf6c | note | Verifying Documents - This Checklist Signed-off
| checkpoint | 11 - Non-conformance Report (NCR) Closure
33b38d94-d4ac-5e30-8969-1839e7d54d89 | note | Reference - MRPA Quality Management Plan
2a1d7a4b-0ef7-5bdc-8d98-2f639f66913f | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
e248cc40-31b1-5aa5-ad73-e8eefb70e47d | note | Method - Document Review
a4450f20-9deb-587f-bfb8-c3c954affe13 | note | Frequency - Once, prior to closure of this lot / element / Work area
937eed05-ca5c-5fff-939c-66db6d9015b1 | note | Category - HP*
9a78233f-7e2f-53e7-8028-3e635fa86f8b | note | Responsibility - SE/PE/SPE
16913ad9-f7c3-5ae9-89db-1554c832500e | note | Verifying Documents - This Checklist Signed-off
| checkpoint | Final Inspection
65d538a0-d8eb-5911-bb2f-3c383e02e213 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6e95c2b9-6526-547d-b632-d5973152598f | textbox | Name:
12a1b0ed-0157-548d-92ac-bfd2c22d0191 | textbox | Position:
8ecc9d66-479f-50f6-8f1c-d9656c351341 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-006-STR-BRUNT-RSS Walls-Precast Panel Material Inspection | itp | CHK-006-STR-BRUNT-RSS Walls-Precast Panel Material Inspection | 0570cf38-85a1-4f4a-857c-b96b36099f0e
| checkpoint-no-value | Referenced Documentation
f76d3b5b-40a7-5895-acfd-4b6d4d03c0d7 | note | Document Title: CHK-006-STR-BRUNT-RSS Walls-Precast Panel Material Inspection
7ba44276-6325-5718-b49a-cdb9d6f54fd0 | note | ITP list Description: RSS Walls-Precast Panel Material Inspection
7853928e-05ff-557b-85e5-c77d205e15c7 | note | Discipline (e.g. CIV/STR/RAIL): STR
67f6a71b-16ba-520a-8446-baa459aead6e | note | Revision Number: 0
adab1fe0-7049-54cc-b9c5-a364e3b55169 | note | Revision Date: 12/07/2023
dfc6c1ce-366d-5b9a-ac30-21fafceed120 | note | ITP created by: Jon De Castro
efd970af-29e2-55a2-9468-34cef7f63524 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1 - Delivery Details
67684e17-790e-5dce-9c4e-d88d18d1e256 | note | Reference - Delivery Dockets/Packing List
57711259-9986-5dbf-bb9d-666ba5ac08d0 | note | Acceptance Criteria -
fcdb7893-48af-5c9b-a905-344c28ec7ab2 | textbox | Enter: Delivery Docket Number:
aaa2e3ef-8a82-5d86-8a62-960392850429 | textbox | Enter: Delivery Date:
8865130b-6aaf-5893-9a0d-4038a232c3d8 | textbox | Enter: Element ID / Birth Certificate:
57c6c277-a777-5f58-8a09-3fd572545493 | note | Attach: Delivery Docket and packaging Slip
f0709ed0-5e5c-50c7-aedc-e7803becb1d2 | note | Method - Document Review, Visual
f77c573f-a77d-5861-8199-2ea19ffcb2df | note | Frequency - Each Delivery
ad845f22-16c7-52b6-a3fa-1a7f68bf2646 | note | Category - IP
9ededeee-3931-5d1e-8c6f-e11595a317f6 | note | Responsibility - PE/SE
70786740-20a4-59e3-834b-b18108ad1aca | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 2 - Packaging Inspection-Quantity
c21385cc-ee7e-5ee3-90a6-68f940b7542a | note | Reference - Delivery Dockets/Packing List
fe6305eb-3a7c-5250-8551-216279e00ded | note | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
fbfae4a0-233a-5ef0-80a7-b31b5752f56e | note | Method - Visual
2bd46567-0b11-5bc8-9379-054e8600c994 | note | Frequency - Each Delivery
bb8f5707-1791-54a7-b849-6b456b7fc3f4 | note | Category - IP
4b034bf2-cf28-51c6-850f-c468c0ddf395 | note | Responsibility - PE/SE
f225fc9d-c4df-5555-b506-222a4884573b | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 3 - Packaging Inspection-Delivery Contents
30f278a9-96ec-51e2-985c-cef8317078c8 | note | Reference - Delivery Dockets/Packing List
53a4f871-9f9f-5ff3-bd18-afbc5bf3650e | note | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
8ffd8ae0-5652-5f0d-aafd-b7d81b25b608 | note | Method - Document Review, Visual
cea3d946-6e04-544e-8426-983bbc80dfea | note | Frequency - Each Delivery
e1e2056c-0655-5666-a365-ad6bc9461791 | note | Category - IP
8e02e31b-8048-5212-b241-33b1d53289f2 | note | Responsibility - PE/SE
0a73a7eb-09bf-521a-b430-7991b6781a99 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 4 - Packaging Inspection-Birth Certificate
06408d55-ae92-5f9d-b660-b584fdd71bdc | note | Reference - Delivery Dockets / Packing List / Panel IDs
dfdbff38-d7c4-5c9a-b034-805ad34bc787 | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
eb3fbd12-a48e-587c-9271-9628ebb4f77d | note | ○ Precast components are to be marked on the birth certificate.
842ccd02-96bc-51ca-bd96-8ae203b1cbd7 | note | ○ Cast date and lot are to be marked on the birth certificate.
834dd60b-cc91-5215-ba53-042d5fc91dbb | note | Method - Document Review
c265b807-5c96-569c-84bc-d0b7098f1df9 | note | Frequency - Each Precast item
82bec59b-5014-5fbf-b4df-350b97969ee9 | note | Category - IP
2d804f78-4c79-5932-ae57-f7a6ab1d5e08 | note | Responsibility - PE/SE
021b1965-4dbd-5410-9814-429e389c85ea | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 5 - Packaging Inspection-Transport
48aedba6-a89f-55be-a4b6-3eb096952077 | note | Reference - Delivery Dockets/Packing List
be635ddf-7b22-5fb3-a716-e4ebc971b856 | note | Acceptance Criteria - Is the condition of packaging acceptable.
21e4b16f-3cfc-5a2f-b7f1-0b949a110147 | note | ○ Precast items are protected from damage during the transport
525d36ad-ab91-5e69-a964-240697c6fdf0 | note | Method - Visual
a100e94c-d7c3-5270-b5fd-16dfe37fda0f | note | Frequency - Each Precast item
2cd1bc00-36bf-5dbc-b189-f89f54bfc833 | note | Category - IP
fa7f7be2-9e61-5c56-98b5-0d7c422139b2 | note | Responsibility - PE/SE
76bbd453-9f78-5010-80a1-2f13c41dbcca | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 6 - Fault IDs:
625d4810-d891-59ee-9e03-c7faac2871fa | note | Reference - Delivery Dockets / Packing List / IFC Drawings
99c21b11-f961-5848-b458-28e935c2b255 | note | Acceptance Criteria - For each precast type delivered, check for the following:
0d5943f9-4dc6-5c05-b98d-8c4aad9457ec | note | 1 - Identification markings match the panel type
7c5f0c9f-71de-5557-acbe-d1d0320d46e3 | note | 2 - Panels fabricated as per drawings
62c908e7-0acd-560f-8e14-41ac2bb41aa3 | note | 3 - Cracks
df42b422-cb7d-5d7d-8eaf-425c2699e180 | note | 4 - Spalling/Damage to concrete surface
351d7721-80ca-5cc0-ad25-fc9a582e6b47 | note | 5 - Exposed Reinforcement
e54bb0da-2384-5a64-9ebe-10c41948f7a5 | note | 6 - Damage to Anti - Graffiti coating
8f61a6c7-6b71-51e9-9ba6-c0d7a67b9cc2 | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
51704519-9ad9-52e7-917f-e9c13bd6beea | note | Method - Visual, Measure
179c755e-965e-5051-aa0f-6f1a576b4f79 | note | Frequency - Each precast type delivered
4be6185d-26ae-532a-96c0-487f89e89755 | note | Category - IP
2c064b14-fe39-5865-81f7-23f4455b8ae0 | note | Responsibility - PE/SE
269fa554-b88e-5037-8ed4-ef4f650fa2ba | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 7 - Check for Faults - 1
daf60bf3-2c9c-5322-8942-0604a27cff53 | note | Reference - Item 6 on this Checklist
75308634-364d-5515-8d77-a68f5667951f | note | Acceptance Criteria - For Each Precast type delivered:
d329ee29-9a7f-5e5b-ac34-d2e9feb9f8cc | textbox | Enter: Panel Identification:
7e565a57-8d8e-56a9-a8eb-e60e2d1b1b84 | textbox | Enter: Quantity:
d7686cf8-8b45-5a94-bac7-2b41083d658b | textbox | Enter: Fault ID if any:
ca17df41-500f-5ca1-a9d6-8a9047c5dc9a | note | Method - Visual, Measure
abe37b4d-f370-536f-877e-94e58677678e | note | Frequency - Each precast type delivered
bbe12d15-4b63-5b3e-aef8-fcf7faba8b7e | note | Category - IP
ef9f5de3-9bb6-5fbd-ae1e-f90a9039c6b8 | note | Responsibility - PE/SE
ebfc6fce-5c50-510e-833f-75d1296c3a92 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 8 - Check for Faults - 2
da2257ce-b761-581d-95d2-fa1d25e33a26 | note | Reference - Item 6 on this Checklist
06638b27-969a-5bce-96a9-d26ce942bea6 | note | Acceptance Criteria - For Each Precast type delivered:
b0092f04-9a21-5833-b5bc-d76a51e15bb0 | textbox | Enter: Panel Identification:
24e71767-831f-59ba-8bc1-0075988c1482 | textbox | Enter: Quantity:
9a1b4445-945a-55f6-823a-a7b9913e8ba1 | textbox | Enter: Fault ID if any:
0376b34b-4440-502a-91d8-1499e322c65a | note | Method - Visual, Measure
e3a90f0d-b8b9-5dfd-95f7-25b7a5421495 | note | Frequency - Each precast type delivered
b3816b61-7b09-5598-add2-5a2495c710d9 | note | Category - IP
de40d8b0-76ba-5c7b-9dc8-cbb059981da4 | note | Responsibility - PE/SE
e44bd527-2285-58a5-bf5d-e80a2d6f6a46 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 9 - Check for Faults - 3
a6e29f72-37aa-585f-bda5-16b4d701ae77 | note | Reference - Item 6 on this Checklist
74062a46-8b54-5389-b131-1b8e8423f6f6 | note | Acceptance Criteria - For Each Precast type delivered:
0f545e45-511f-5d70-944e-e0c304ea5d3f | textbox | Enter: Panel Identification:
dc96e25f-f2b5-5857-921b-a9e555a830f1 | textbox | Enter: Quantity:
6c9c1e55-25a3-5eea-b9df-ad957dab756b | textbox | Enter: Fault ID if any:
dfbc998c-fdbf-5592-a6df-5ffa82552069 | note | Method - Visual, Measure
c5326041-0a86-5348-879e-91974c776d7a | note | Frequency - Each precast type delivered
5a8efc0f-c171-53a2-8bc1-5a8950bbf3d3 | note | Category - IP
19fd7bab-2d06-5ed4-9a6e-cadabfa32b78 | note | Responsibility - PE/SE
c98d5534-d25a-5c7c-8d8f-0836974e88cb | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 10 - Check for Faults - 4
22f00228-2d0f-5e0b-92c8-ede78a0d611c | note | Reference - Item 6 on this Checklist
91a13008-45a7-5c9a-97ba-3e6ef51ebaef | note | Acceptance Criteria - For Each Precast type delivered:
91459e97-c13e-51f3-8c9f-3b3dfaa12545 | textbox | Enter: Panel Identification:
8eafea4c-9814-5f23-9ef4-8c55e7fcb697 | textbox | Enter: Quantity:
a9ca65bf-6ed3-5061-9396-c675cb76447b | textbox | Enter: Fault ID if any:
4ed98112-8fb0-5fe5-a715-68cf4f376f95 | note | Method - Visual, Measure
8d40dd2a-5978-560d-adb6-055480afef73 | note | Frequency - Each precast type delivered
4e38fce0-af45-53b5-a6bd-65a27d84b141 | note | Category - IP
d4b7c6ba-0844-54a2-a34b-1d0c35827460 | note | Responsibility - PE/SE
0f5e99ea-99b0-5a84-906e-868c46bb576b | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 11 - Check for Faults - 5
a3f6907e-615f-5dd8-a770-19b0f5742d13 | note | Reference - Item 6 on this Checklist
7069babf-20d9-5616-ab6f-0b5b8f2c5a66 | note | Acceptance Criteria - For Each Precast type delivered:
0c60416b-9c6c-5ff7-89f7-4873b2019bde | textbox | Enter: Panel Identification:
59751eba-8baa-5873-ad24-909288a970aa | textbox | Enter: Quantity:
24821fc7-ef10-55aa-a7be-2df10f7ce476 | textbox | Enter: Fault ID if any:
3a1dffd3-fedf-5cc9-8976-d40b5245b881 | note | Method - Visual, Measure
0bf8aecc-63ec-5357-9555-5daf938f80fe | note | Frequency - Each precast type delivered
994ebeb6-8665-50a9-9982-22bd3f8376a7 | note | Category - IP
902d27db-5987-5659-b680-137d31304515 | note | Responsibility - PE/SE
27f476f5-0836-5999-8768-9753b6ab7309 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | Final Inspection
a074f32a-2fec-5ef4-9539-062677340f75 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ac7d0f22-54b5-5d24-93ce-5017066638cf | textbox | Name:
b73b81e7-5360-596e-b5ba-45169034f23b | textbox | Position:
498a10d7-22cc-5e2f-94fe-2fed2c5b0738 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | CHK-007-STR-Bridge Beams-Material Inspection-Precast Beams | itp | CHK-007-STR-Bridge Beams-Material Inspection-Precast Beams | bc1c8904-f06d-4106-9dfc-eb49adbb5d6e
| checkpoint-no-value | Referenced Documentation
dfd7adae-34c4-5135-83ea-3a54676b7312 | note | Document Title: CHK-007-STR-Bridge Beams-Material Inspection-Precast Beams
a322883d-0692-529f-a06f-86484421316e | note | ITP list Description: Precast Beams Material Inspection
3048e99d-e33b-5085-8f40-ffbd0c0ac2d7 | note | Discipline (e.g. CIV/STR/RAIL): STR
9f9e6d36-3b7f-5d54-8a03-4acf990204a5 | note | Revision Number: 0
2b735b03-3f0d-5468-8808-ac2f0f170c86 | note | Revision Date: 13/11/2023
897e4c2d-afa7-57b0-a165-b628b95b240a | note | ITP created by: Jon De Castro
e72f6f2e-a18c-5351-85aa-5b31ed2a5f81 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1 - Delivery Details
f3111d15-4001-54b0-8602-5f5d96b5ceb8 | note | Reference - Delivery Dockets/Packing List
d27afd39-1af5-5598-a27e-8301884c9d95 | note | Acceptance Criteria -
7461541a-87ac-5878-993f-06297b1102cb | textbox | Enter: Delivery Docket Number:
a2b92781-f9d3-5472-ba03-f0516b18119d | textbox | Enter: Delivery Date:
7ff08965-4522-5063-a6e6-533049c8644e | textbox | Enter: Element ID / Birth Certificate:
d5615bd0-3d8d-531a-97a6-eb2b3300c24b | textbox | Attach: Delivery Docket and packaging Slip
c788bf7b-f857-51bc-9959-63193e5bde65 | note | Method - Document Review Visual
22763074-cf40-57d8-b34a-ef2d1c25ca32 | note | Frequency - Each Delivery
1c9fa12b-66bc-5932-8d16-098e61a4dfbc | note | Category - IP
48decff2-16e5-544f-8491-8dcc84b5b448 | note | Responsibility - PE/SE
c20daa56-b88f-5caf-afa8-d49d8caac84a | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 2 - Packaging Inspection-Quantity
ff13bd9e-aaef-5e7c-9481-c30d3b5c2c36 | note | Reference - Delivery Dockets/Packing List
1458c8bd-69f2-5d1b-8036-679a7d4aee0a | note | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
f154150a-9a70-5d16-856d-5f335048745f | note | Method - Document Review Visual
900e55d0-4468-5f4e-8834-ede234fac5a4 | note | Frequency - Each Delivery
5bd04159-5d66-5745-b814-64b25749749c | note | Category - IP
f2f66dc8-d968-5f18-985d-1eebf33eaf3d | note | Responsibility - PE/SE
0ad7f272-5154-55e3-ab89-2d9d987ce843 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 3 - Packaging Inspection-Delivery Contents
1707845d-356c-5b2a-881f-0313abf9c305 | note | Reference - Delivery Dockets/Packing List
b1665b0a-713f-5b2a-9bc6-10ca7ac644e0 | note | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
82674218-b1be-57e8-aa76-d4c51c6b548a | note | Method - Document Review Visual
a82e21ea-437a-548b-a366-e60b2ca3ab8e | note | Frequency - Each Delivery
3bfabf91-cd4f-53b8-971e-07f777fc8e3b | note | Category - IP
455db3d1-7108-5f31-8e55-276ca384a370 | note | Responsibility - PE/SE
e67242fe-beb2-5d26-9783-8de288c5d6bf | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 4 - Packaging Inspection-Birth Certificate
ab910067-7f64-5395-b470-24c60b47714f | note | Reference - Delivery Dockets/Packing List / Panel IDs
b715b6cf-9bed-5a45-92f1-abbfe587a5d5 | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
c326dd3a-fa15-59e5-b943-74f13d292e04 | note | ○ Precast components are to be marked on the birth certificate.
e4cf6d30-3aa8-5259-8347-41994a99e9fe | note | ○ Cast date and lot are to be marked on the birth certificate.
706ac485-4b18-5e8d-b0b8-0e692f2bb7d0 | note | Method - Document Review Visual
cdc6623b-ffa4-5f83-85ef-d4b63c44c10c | note | Frequency - Each Precast item
7fb1e315-167b-5c7b-a9f9-377c036f9ae9 | note | Category - IP
8a0d938a-cbe9-52a7-a12a-2b9076113602 | note | Responsibility - PE/SE
5dbe302d-fbe2-5491-861c-e3a2bd8308c5 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 5 - Packaging Inspection-Transport
1b026506-5471-5849-9711-e56299c72a24 | note | Reference - Delivery Dockets/Packing List
9456ed7d-dc58-5418-96df-1b0b8d39ec9e | note | Acceptance Criteria - Is the condition of packaging acceptable. Precast items are protected from damage during the transport
d973b4dd-f12a-5425-a04c-8660cee38afc | note | Method - Visual
063f9657-a735-5348-8a22-667a754c1cc2 | note | Frequency - Each Precast item
2399dfe4-7230-55f4-a6ee-5d4536b46b80 | note | Category - IP
476cd1e8-e3af-557f-992d-07cb35d0076a | note | Responsibility - PE/SE
2761bd04-3301-50e9-baa4-5b6e4aa05d4b | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 6 - Fault IDs:
06c8b759-f1c7-5fd1-b97e-716e3f6f0090 | note | Reference - Delivery Dockets/Packing List/IFC Drawings
7a7022ff-82bb-53bc-a1af-fad788d6009a | note | Acceptance Criteria - For each precast element delivered, check for the following:
5d398be3-76ec-5ada-87a4-168e8e1b89b7 | note | 1-Identification markings match the panel type
a2147ec4-72bf-51fc-8aa6-4a315b473269 | note | 2-Panels fabricated as per drawings
743426ab-8c19-55f8-b9a8-ca97a070afbf | note | 3-Cracks
7a9c3245-69c9-5365-a4ef-d042e5b98509 | note | 4-Spalling/Damage to concrete surface
6a452974-944b-5bc7-bbfa-a26f5251d3a9 | note | 5-Exposed Reinforcement
cdee9705-758b-5ce0-b956-072c1013a3a2 | note | 6-Damage to Anti-Graffiti coating (where applicable)
bbb51746-e809-5ee0-87dc-56da1c43d52e | note | 7-Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
bc0778ea-d8a9-5d82-827a-14b82e45a8ca | note | 8- Others
a307e74f-fb62-52da-89db-165ff3666174 | note | Method - Document Review Visual Measure
5d849687-cdff-5399-b5d8-6fc730cf811f | note | Frequency - Each precast type delivered
f0309cb3-3cd2-583e-9011-518a5945d6f3 | note | Category - IP
745a2fb5-eb4f-545c-abc4-e52a7ae45579 | note | Responsibility - PE/SE
53f8b58f-f19e-5ed7-9905-27ae7dcf7780 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 7 - Check for Faults - 1
4f8cdf0d-2e68-5297-b5d1-35f766bc264c | note | Reference - Item 1 on this Checklist
e2606ad4-f76d-510d-bf77-71c07a73e975 | note | Acceptance Criteria - For Each Precast type delivered:
0a159632-e9a4-5ac4-a82d-e51c4a11e2dd | textbox | Enter: Panel Identification:
58a6954f-153f-5fab-b168-ae1a8e066178 | textbox | Enter: Quantity:
9ba07b58-67c4-53cb-b4bf-ac07005d080d | textbox | Enter: Fault ID if any:
dbd24d70-f072-5922-b780-0725a079d05b | note | Method - Document Review Visual Measure
8ec42a1b-849f-5d2c-93dc-f938cc59d078 | note | Frequency - Each precast type delivered
46d99e8c-d4c3-5ef3-a422-4bb226d3f2c2 | note | Category - IP
c29d30c8-fbeb-563b-9534-0b129c3592dc | note | Responsibility - PE/SE
5b157eb8-2829-5f3e-886d-afe913ba60ee | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 8 - Check for Faults - 2
dc3ca2fc-dbe9-5963-8913-7f308751bc50 | note | Reference - Item 2 on this Checklist
a34aa432-0a97-50a5-8b79-08a5968e1947 | note | Acceptance Criteria - For Each Precast type delivered:
70018a08-4c69-5936-9eae-28953cdd583d | textbox | Enter: Panel Identification:
e64b7c38-2cba-50f4-a49b-63367bd48ce8 | textbox | Enter: Quantity:
318ede5a-953a-55b0-af59-091357795dd3 | textbox | Enter: Fault ID if any:
a2676782-c623-5109-b162-512ae82968e6 | note | Method - Document Review Visual Measure
1b1fe310-6627-5cf6-8f94-5170f85a824a | note | Frequency - Each precast type delivered
346b6716-ece0-52e7-a913-c834c1ed2bc2 | note | Category - IP
b1d85036-8955-5378-a1e5-5d06c79add53 | note | Responsibility - PE/SE
eb76352f-214a-594f-a77c-80d03481e168 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 9 - Check for Faults - 3
8ca1bd22-d380-5616-bf4f-8b9bbc43652c | note | Reference - Item 3 on this Checklist
4ff5aa10-51ae-539a-9c26-6e57d89c361e | note | Acceptance Criteria - For Each Precast type delivered:
2e6badf1-5f05-55df-9a2a-fa4684eb4b8f | textbox | Enter: Panel Identification:
979201ad-46a7-58fa-aa3b-a821583099c0 | textbox | Enter: Quantity:
5a578121-3bb0-59e9-99b1-2b938f92186e | textbox | Enter: Fault ID if any:
58445ffe-6fee-5e14-a72b-5e1ab24da6ae | note | Method - Document Review Visual Measure
05a3238e-2110-5de7-98ba-4a7ecbda1757 | note | Frequency - Each precast type delivered
379c7738-4283-5bb5-9bd4-130aa6dc2448 | note | Category - IP
5a6cc3aa-6d30-51d9-acb0-14cc457c3abe | note | Responsibility - PE/SE
582098b9-d79d-5860-a82e-d8c503286854 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 10 - Check for Faults - 4
79198f46-02a9-5449-b23d-8767ea0e260e | note | Reference - Item 4 on this Checklist
496ac4de-e59b-5bf0-af55-1da136c332e0 | note | Acceptance Criteria - For Each Precast type delivered:
eeef025b-2f51-51c1-ad01-31ae928906e6 | textbox | Enter: Panel Identification:
b5d4dfc1-6bc3-5399-9d3a-6295feb2925f | textbox | Enter: Quantity:
767efd9c-7d2e-51af-9253-ca466b21a0f0 | textbox | Enter: Fault ID if any:
9b2d8be4-0e78-5fdf-a814-d86a4e730ed8 | note | Method - Document Review Visual Measure
20002d20-8f76-5b40-8489-46fda9abf58c | note | Frequency - Each precast type delivered
fed5061b-7ee8-51ff-b8b1-3396c719fe17 | note | Category - IP
e0aac3ff-654f-517e-bf3b-495b708ad2df | note | Responsibility - PE/SE
1c5f9478-c748-5363-8ac1-f9d94e5ce18e | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 11 - Check for Faults - 5
9ed9c2e2-9057-57a8-90ad-ee1ef901946d | note | Reference - Item 5 on this Checklist
a0b87573-e45e-5eff-9803-6de1d6d5dfaf | note | Acceptance Criteria - For Each Precast type delivered:
7034beeb-a01e-5d78-80cc-a4dd0adea398 | textbox | Enter: Panel Identification:
ff4a71cc-d957-5ade-a86b-055f8180fb80 | textbox | Enter: Quantity:
138e6dba-23f3-50db-b210-0986fbdeb4c8 | textbox | Enter: Fault ID if any:
01e6fe5e-2191-56f9-9eba-a06759dde311 | note | Method - Document Review Visual Measure
e867b9d2-cd8c-57d8-989d-cae260c68bc7 | note | Frequency - Each precast type delivered
a8135d85-16ff-5f5d-9cac-55d4656a59b7 | note | Category - IP
26d53a33-ead8-5346-99eb-b1e1ad35b4fd | note | Responsibility - PE/SE
f6029b54-9c50-5d6d-a4d9-8226c924a850 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 12 - Check for Faults - 6
15291040-212d-5a9f-928f-db7f82b60c8e | note | Reference - Item 6 on this Checklist
f64e45fb-50ca-52c3-84c1-cf65344a629a | note | Acceptance Criteria - For Each Precast type delivered:
b274a41e-3c4a-5b0f-a038-14ab36e83e18 | textbox | Enter: Panel Identification:
52d5b905-2a08-500a-9bee-f1347f723da4 | textbox | Enter: Quantity:
7aaa5d02-edef-58f0-9dec-371a52edff98 | textbox | Enter: Fault ID if any:
429ff7ff-0e72-568c-bf90-63bf99c8f06c | note | Method - Document Review Visual Measure
3689eca7-2ef7-5f67-bf35-1b87181df5f3 | note | Frequency - Each precast type delivered
9328afa5-78b8-564d-9ae9-7c25e447a278 | note | Category - IP
1e6a61c8-02a0-5563-88eb-95b1c6b3d0ae | note | Responsibility - PE/SE
c53b2037-e7cd-5227-a843-58fadd1be5f4 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 13 - Check for Faults - 7
9e5ec316-56f3-570b-90a7-e8a3cf40f034 | note | Reference - Item 7 on this Checklist
efe42cf2-d900-57c6-a2bb-1ae0391b37b2 | note | Acceptance Criteria - For Each Precast type delivered:
d275719e-a988-5bb7-b320-3083685f3769 | textbox | Enter: Panel Identification:
3439f314-3b5f-5cb1-9a33-9e349d5f696f | textbox | Enter: Quantity:
8b079fae-503a-530c-b642-3803a2f18946 | textbox | Enter: Fault ID if any:
7d03adee-e3b0-5ec2-ae37-f7be5a5a6324 | note | Method - Document Review Visual Measure
e65dc822-d855-5e0d-9994-38cf2727525b | note | Frequency - Each precast type delivered
919cdc66-1ab8-585a-b311-bbed8cad893b | note | Category - IP
01bc5ade-940f-54a2-8db3-d0cf989542f2 | note | Responsibility - PE/SE
05ebb967-a2e8-5471-ab1c-23b00f5512e0 | note | Verifying Documents - This Checklist Signed Off
| checkpoint | 14 - Check for Faults - 8
90a15ae6-09be-598a-ba3e-e0d333a31bce | note | Reference - Item 8 on this Checklist
58cd2323-ba46-557c-8775-f6aba4ddc1a2 | note | Acceptance Criteria - For Each Precast type delivered:
2edb034c-f9e1-5c00-a27c-6ae7f1dbba8b | textbox | Enter: Panel Identification:
98e21db7-1c1b-5dad-896a-34d42821cc9b | textbox | Enter: Quantity:
4bc0d747-04f3-5940-9572-b3d4baf045c1 | textbox | Enter: Fault ID if any:
71215d95-0289-5d12-b7de-1ea0b4c963cc | note | Method - Document Review Visual Measure
b883b51b-9e85-5b04-94ac-ca7264590e0a | note | Frequency - Each precast type delivered
cc8090c7-e3f6-54c3-8dbe-d60d6728285c | note | Category - IP
135377e9-42ba-50e8-8558-5ab465c29b22 | note | Responsibility - PE/SE
e446a539-12d8-5fcb-b4ad-56c52220ce9c | note | Verifying Documents - This Checklist Signed Off
| checkpoint | Final Inspection
84d9e4dd-80cc-5c58-bcf0-66ad55dd1dcc | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
525cfcb3-a25e-5d33-b1a0-1af2cc6c7be7 | textbox | Name:
b01aa05d-8665-5a74-a4e7-1b8f0712e0e1 | textbox | Position:
472f7a9c-5c83-5722-b45e-be0395df9121 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-016-STR - OHW Structures Piling |  | ITP-016-STR - OHW Structures Pilling | eef7af09-66b8-47db-9512-9d23c3787642
| section | 1. Referenced Documentation
| checkpoint | 1. Referenced Documentation
6d75905b-07b8-5e13-b390-d11b52066b1b | note | Document Title: ITP-016-STR-Brunt - Overhead Wiring Structures Piles
25fc532b-3682-55cf-8499-c43ab2276bec | note | ITP Description: OHW Structures Piling
25f42d5f-087c-5edb-9bdc-6e244c2dab6c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
6e5019be-b9b4-5917-8341-bac778d9966b | note | Discipline (e.g. CIV/STR/RAIL): STR
e611855a-68fa-5e12-85cc-9cbfe4ed46cf | note | Revision Number: 0
d703875b-2d08-5fb5-a938-e288c1f8f377 | note | Revision Date: 21/12/2022
ae7103d2-f4e4-5eed-925a-8e91636519df | note | ITP created by: Casey Knowles
ef2f780b-b06e-5605-b8c6-12f6ef21e186 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
d75bbc7f-4a0b-506c-a2a7-14e5386b2ce0 | note | Reference - VicRoads Section 606 July 2017
| checkpoint | 1.2 - Non Dependent
ae8bff4a-42a3-580a-8c4e-5d2db5b84c2a | note | Reference - VicRoads Section 610 Feb 2020
| checkpoint | 1.3 - Non Dependent
a02fdeab-9f5b-5d5d-81ea-26c0aab6147d | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
66967e35-84fb-5140-aaa3-5236e5c02ecf | note | Reference - AS2159-2009
| checkpoint | 1.5 - Non Dependent
b0041dd5-f7b8-5f68-9993-f16305955c57 | note | Reference - AS3810.1 2018
| checkpoint | 1.6 - Non Dependent
aec856d6-1d8c-5b81-a21e-f95b5607e407 | note | Reference - AS5100.3-2017
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
b3844d19-3c04-5d51-9153-9eaef57490d0 | note | Reference - 610.07 Table 610.071
3b58881b-b880-57e0-bc65-93161972d7cd | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
7bc36f21-1387-53c1-a6c9-3cd8381e56b8 | textbox | Enter: Teambinder Material Approval number
cae957aa-ec28-5707-830c-951a66807c95 | note | Method - Document Review
54867dfb-1bf6-527a-aebb-ffb609a51ff2 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
a35ac1d4-8c4f-5505-a7d0-f5cf5226c96a | note | Category - HP
ff9f2d3e-3042-5355-8299-2eba33557146 | note | Responsibility - Nominated Authority
f91e9f3a-4fc7-5b99-add8-129ec4899d03 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
3951fa93-0e36-5cc5-9512-c64256ec59b9 | note | Reference - 611.05 (a)
4e563028-aa74-57d0-8cf5-1d231baddb84 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
e5c17641-b10e-56e7-a3fd-6babac3f47d7 | textbox | Enter: Teambinder Material Approval number
b059eb69-2ee5-5787-92b5-46c6011ae554 | note | Method - Document Review
26edb014-e6ac-53ee-9b53-c99cb3c01737 | note | Frequency - Once for each supplier, 14 days of award of contract
7a2e238a-171b-5ea2-baae-e816551a3309 | note | Category - HP
c036e448-4623-53ae-89d8-07d2ab9e7964 | note | Responsibility - Nominated Authority
7a70db95-6141-56f8-b2e9-cfa8a58ce0bc | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
ad53c4fe-946f-5c1a-b009-4c481f63bb47 | note | Reference - 610.26 (a)
3fcb2cf7-c4b8-5ae1-b71f-2f30139c1499 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require testing to demostrate suitablity to prevent excessive deformation under loads.
3931cec5-fc17-5887-ab73-836a16ace267 | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
10967ddb-2832-50ee-a39b-b07e8bd085d8 | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority
ae0bf16a-90a3-5cd4-b427-23e5c8240b7a | textbox | Enter: Teambinder Material Approval number
135a68e9-98ef-5a64-b577-debc40a2a9a0 | note | Method - Document Review
769fa397-44e1-5937-a464-3faea5466b1b | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
23c2a5a6-4060-5441-bf79-d731328abc4e | note | Category - HP
21cad5ab-4012-5ff6-b2ae-cdafaded3557 | note | Responsibility - Nominated Authority
4780be35-f84f-5694-af4b-8701c5c86e5c | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Cast-in Bolts, nuts washers
c684f3a8-fec4-5cb2-8a12-6a45b83e5f4c | note | Reference - IFC Drawings
a3bd4659-a516-5a1f-bf12-88b97f9801eb | note | Acceptance Criteria - Unless the drawings note otherwise all bolts, nuts and washers shall be 8.8/TB galvanised components to AS 4291.1 & AS/NZS 4291.2
c2156da2-3fa6-524a-b245-fb0863d8bd40 | note | • Washers installed under bolt head and nut. Tapered washers used as required.
775b07cd-813e-5473-830a-a149338c7acc | note | • Slotted holes and required hardened or plate washers in accordance with AS4100 and AS 5100.6
ff967c5e-9397-5f05-899b-f04438a746a9 | note | • If HDG, a certificate is required. HDG thickness should be as per designs.
f86c57ba-2cde-5b7a-af58-17c27aea07f2 | textbox | Enter: Teambinder Material Approval number
abcfa52e-971d-5bf4-b437-6c794dc1d448 | note | Method - Document Review
1f449ea9-8364-5da1-b0ad-3ba5e62e44d2 | note | Frequency - Once for each supplier, 14 days prior to placement of hold-down bolts
f9744f86-c2a3-501a-8ce0-0725d178ce20 | note | Category - HP
b58ca47c-a231-5933-81c4-992cd3695315 | note | Responsibility - Nominated Authority
629212cd-3668-5ba2-8ec7-68ddcb24faaa | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Working Platform Certification
c4064d7c-2e71-5411-8642-78fc796483cd | note | Reference - Temp Works Design
6ce5a0bb-569a-59ea-9819-9989a30a30dc | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement
7b3570a1-1fbd-5a1b-9364-e51fa70d9262 | note | Method - Document Review
cfed4fe6-be1b-524d-895b-246dc3213c98 | note | Frequency - 14 days Prior to works commencing & after rain event which there is >10mm in a 24hr period.
c490ab29-b37c-5e48-92fa-e8b5de83b2f9 | note | Category - HP
805ea187-20c6-59c8-a2d9-3a33d90b0fec | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
71baafbc-37a1-53a8-afd1-44758c98ad85 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Piling Operations Work Procedure
899849f2-25ee-50d8-a354-a8ee8889b31e | note | Reference - 606.03 (a)
f257c195-c370-5c2e-b34b-41d590265d40 | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
c28edede-10ee-5512-8edc-e591c5bef884 | textbox | Enter: Teambinder Approval number
03456f31-ed63-52f3-9558-76c0fa815b73 | note | Method - Document Review
c285a223-ebeb-5151-bc96-d30db01b34c7 | note | Frequency - Once, 4 weeks prior to the commencement of piling
581df56f-0f4e-5ec0-8ae1-cc72ecadcb10 | note | Category - HP
421cd6fe-c986-5e61-af82-6b18e6aa4753 | note | Responsibility - Nominated Authority
7f4d58be-55c4-5431-bb22-ccd17fe71925 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Temporary Steel Casings
85cf63ea-e7c9-5586-a215-683eacb69e5c | note | Reference - 606.03 (b)
7e6626e3-ab70-5b34-ae6d-d9fe0ca70913 | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
2debd97c-9da6-5b97-8307-f72ccacffa55 | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
9eb06191-6953-5f1c-a939-acf85c70eab4 | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
eda654c3-765d-595d-a894-9e43d18575a9 | textbox | Enter: Teambinder Approval number
9ebb7cf7-8a0b-59bc-8057-a74d862ad8ee | note | Method - Document Review
1f8c3bb8-af4b-552c-97f7-92a231d51977 | note | Frequency - Where applicable, once, 14 days prior to use
25cb5f79-e074-574c-829a-4bb8806e081a | note | Category - HP
29071cf4-1fe0-5357-b0be-0dfcc1bd84ca | note | Responsibility - Nominated Authority
85640938-bbe4-508a-a6ba-87a8af35948d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Casting Under Water Procedure
3201180a-6520-54ab-a780-637d1e424d7e | note | Reference - 606.06 (a)
e49f44f0-04e1-5744-9dad-0b6ea366841e | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
11622133-9d38-5390-b84d-a5715104f124 | textbox | Enter: Teambinder Approval number
87ab2ae2-a7f8-5438-8cfb-f6d4528f7717 | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
0bb2389b-1a8a-51fd-a81a-c56ec9872faf | note | Method - Document Review
120d7443-5ab7-5cce-8ae8-7b7ee9277d1b | note | Frequency - Once, 4 weeks prior to the commencement of piling
0d69acdb-a7ad-5300-90f0-59f3b8c06600 | note | Category - HP
c882b95f-bc90-5b94-93e6-b327d283e917 | note | Responsibility - Nominated Authority
0b44b29e-2c32-51d5-aa19-b2a8fb952358 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Pre-qualified Pile Testing Consultant
fdb83e28-2359-51cc-bd96-2a3ce3c182a4 | note | Reference - 606.07
1336b521-30ea-56af-b331-545c22e78345 | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor. Details of the consultant to be submitted for review to the Nominated Authority.
a4803dc4-d65d-5b6f-b611-36d9f119897e | textbox | Enter: Teambinder Approval number
0811d0ee-d3c8-5f41-9370-c4d0cc2669d0 | note | Method - Document Review
3cf03bd7-cab2-5308-92cc-aee931bf8263 | note | Frequency - Once, 14 days prior to testing
ea707cef-b7fe-5e08-9916-4f254a234819 | note | Category - HP
e23afe74-40f1-5b00-aeb1-2380996c06e6 | note | Responsibility - Nominated Authority
991154f0-018b-5415-9274-cd96571b979e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Reinforcement Welding Specifications & Qualifications
8bc9a2d9-9d1f-5671-883b-2864748d40a4 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
ebee1b98-a2b2-566b-9369-3adc4d003f85 | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
6b8ec349-504d-5461-bcf5-02b3d44cd551 | textbox | Enter: Teambinder Approval number
733ab2c4-db40-5dcb-b282-4b781d4de24a | note | Method - Document Review
fb18b20d-53d4-5b60-b52b-62e1c0102f32 | note | Frequency - Where applicable, once, 14 days prior to welding
e7aff11d-54cf-5aca-b57d-f436276f239b | note | Category - HP
e4d650e4-39e1-558f-be34-931bad456c88 | note | Responsibility - Nominated Authority
34e85cf0-9271-5388-ab2c-9c4abfc43633 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
02f3487e-7a44-5424-8e38-d74e3e8313b5 | note | Reference - MRPA Quality Management Plan
0a629ace-e87f-5fc8-b3d2-68c52e938bfe | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
941e827c-cd78-5245-898e-cae5ab99b132 | note | Method - Document Review
3d501d55-b55f-58b0-9492-7fa6b0efb21a | note | Frequency - Prior to starting Works and at regular intervals
758d6763-d52a-5e4b-89dc-04d464c1afde | note | Category - HP*
aa7e50b0-57e7-5a63-b4b6-e9cf8b2c6868 | note | Responsibility - All
9ab37582-6ea2-5aa9-98aa-e0f9e9795cb8 | note | Verifying Documents - This ITP
| checkpoint | 4.2 - Survey Set-out
d75d8d83-18ce-5693-9344-6be325f6961f | note | Reference - IFC Drawings 606.08 (a - c)
e7d3c85a-7672-5923-b247-c8494da69ad7 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
bb08dd98-a3a4-5e63-aa7c-83643a1ef33a | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
5f3528af-4814-5c2a-8638-4f11ce160e45 | note | Method - Measure, Visual
2f44c78e-02bc-5775-8d92-f3063a517a34 | note | Frequency - Each pile
42d40f5c-42e7-528e-becc-51f0ec451ac3 | note | Category - IP
93b0be93-870f-5a4e-8544-21fc926f0349 | note | Responsibility - Surveyor, SE
df6e2c84-d97f-548f-9ac0-bc37b4afafa7 | note | Verifying Documents - This ITP
| checkpoint | 4.3 - Protection of Adjacent Piles
abd54425-9406-5a42-a953-3924b8e438a5 | note | Reference - 606.04
1d19da5b-1b73-534c-a18f-210420cb3043 | note | Acceptance Criteria - Pile construction shall not:
d2490933-b71e-597b-8fcb-490e03f172ca | note | i. result in damage to adjacent newly cast piles due to ground vibration.
fbde29f1-74de-558f-8cd6-17df3d05d12d | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
abbd86ef-025a-5629-afcc-a9cfd422f10e | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
8d4a5a21-76e4-58ba-810a-b6756e323ccd | note | Method - Measure, Visual
244d8aa1-c040-58c9-a9ef-b5551f49ea73 | note | Frequency - Each pile
4ef0a8d5-b531-51be-adbd-7b8b468841fb | note | Category - HP*
cb3cf172-ac68-5f41-b241-c5015604748f | note | Responsibility - SPE/PE
3a04e6ef-9101-5320-ac20-e85f58def130 | note | Verifying Documents - This ITP
| section | 5. Construction Activities
| checkpoint | 5.1 - Boring Operations
9d323a10-3a5a-53c9-ba03-f41014c974d0 | note | Reference - IFC Drawings 606.03 (a)
e8093f8f-5c19-5a4f-947c-b195c43f4ad0 | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
a432f664-3f0f-562c-9f59-56d4e2ca9c40 | note | Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
2f181057-df10-5ded-a93f-7e28aceffdba | note | • Excavation clean and de-watered (where applicable) for inspection.
c0422aa1-6ce3-5879-8175-945b728980be | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in
84c0a7de-a014-5375-9ddd-1662a6b61a0a | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
190aab8b-5eaa-5f47-8dac-5f49e25fcc7b | note | Method - Measure, Visual
e5236c84-fc04-5bdc-8736-45e8b32a3b7e | note | Frequency - Each pile
8d5b9a0c-36e7-5776-baa9-1a087f8cee4d | note | Category - IP
dae80ee6-e578-540b-a41d-2edc80a8c25b | note | Responsibility - Surveyor, SE/PE/SPE
e34454f5-4f8e-5df0-9be9-11ebac9e0f2b | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Formwork Extension
875a628e-5a1e-53a1-9942-3a04759c6257 | note | Reference - IFC Drawings
ac323ac1-7687-57e1-bc5e-fee02fbc206c | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
e5376c2e-9526-554e-943b-fb55b5df2369 | note | Method - Measure, Visual
dcc693e7-8e22-5609-950d-5249981a1ad4 | note | Frequency - Where applicable, each pile
19695304-e827-59fd-a075-7d1d9681af1a | note | Category - IP
33b240ce-1d50-5d3d-9fe6-2545a9e25fba | note | Responsibility - Surveyor, SE/PE/SPE
72c26afa-720b-5fc8-a3ba-81ae7bcd8eca | note | Verifying Documents - This ITP
| checkpoint | 5.3 - Inspection of Pile Excavation
348c85ce-7360-527b-9027-7bb67662fe33 | note | Reference - 606.05
714bd385-a796-5af4-bed8-4682ad0f6ebe | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
0abfcaf2-8de2-5986-a637-5e6b7066e70d | note | Attach: Geotechnical Field Sheet or Report
7fc4ff6d-2403-56a0-a692-f1a436298d64 | note | Method - Measure, Visual
b763f9af-c7ef-5e6b-80db-4be7c25a3192 | note | Frequency - Each pile
3037953b-d049-58f3-b9e2-bf72be317719 | note | Category - HP
70ae129b-1a9e-5516-b3e1-3c9801f18a4f | note | Responsibility - Geotechnical Engineer
6442a920-9395-588d-8d07-03a56b9624d6 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Reinforcement - Placement
f88b1a63-7d7a-52cc-a50a-a2ed50b6fd60 | note | Reference - IFC Drawings
1819c9e6-8dca-5276-89de-490a0736cf13 | note | • 611.06
7544be1a-279d-5785-9b51-3d858c951f52 | note | • 611.09
d8aa8e11-57f9-5748-938d-37d2e9503e0d | note | • 611.10
88303a6d-db42-55b6-9d64-e05478c9333e | note | • 611.11
6f3d244f-daf9-5af4-a06f-3e4ed6e0a105 | note | • 611.12
3ee40575-40a0-55e9-b0a0-82211e0fab27 | note | • 606.06 (a)
d1eda92b-8019-5905-a66c-e43e1a5be4e9 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
b5b9f8ff-3bef-5641-a8cd-7fb9801b0a24 | note | • Projecting reinforcement is the correct length and location.
616d71b3-2a58-522d-852f-4abba2bc4422 | note | • Splice lengths achieve the minimum length and are in contact for this length.
1a0395f2-4e3b-52fb-85ba-4a6152994467 | note | • The reinforcement surface condition is free from dirt, debris and damage.
16966cc7-9cd2-5706-af1b-da789b709c37 | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
a882721d-021b-5416-aa80-5087a64ba74c | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
a607965b-8cf4-50d1-8606-1d668e6f1031 | note | Method - Measure, Visual
cb5731fc-954a-5d35-b139-167fa92f05c0 | note | Frequency - Each pile
f89f649c-f448-5874-b463-a9669978e2e6 | note | Category - IP
cc31fdb1-4e56-5a55-a323-b39b3e461b08 | note | Responsibility - Foreman, SE/PE/SPE
cc8dbe71-4ae9-54a3-b24d-d5c71f4cb1d1 | note | Verifying Documents - This ITP
| checkpoint | 5.5 - Reinforcement - Electrical Continuity and HD Bolts - Electrical Continuity
d7aea5b4-1acc-533d-bf5d-141e29bad945 | note | Reference - IFC Drawings 610.29 (d) 610.43
fb81158d-d34a-5e7e-b9d1-403910d2f7be | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
1fe75c70-b5fc-55a1-95a7-911eef639bc3 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
7a3c8c13-3203-587e-ad37-23e2b6f8cf45 | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
8b2e60c2-552d-5a5f-bdab-5455458e126b | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
b7c72e5d-de73-5988-a73d-3f023663b28d | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
fa59a9ba-c09f-503c-8aaf-0ece013df7c7 | note | • Overhead wiring structures shall be fully earthed, by bonding the hold-down bolts to the pile reinforcement
9f75330e-6cd9-560e-860e-c3f3c224fc0b | note | • A minimum of 2 No. hold down bolts shall be electrically continuous with the pile reinforcement. This is achieved by tack welding 70mm of stranded copper cable between the hold-down bolts and reinforcement
7145aeaf-06e8-54c0-9495-cee4309264ce | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
36a95d80-8873-5d7b-8ba2-41a6bf6ec52d | note | Method - Measure, Visual
47836e7a-91c6-518a-9124-e442c2a566ee | note | Frequency - Where applicable, each pile
88b7ce34-9dc5-5e75-aae8-a8cddd6316dc | note | Category - IP
8f6db2a9-310a-5c8f-955c-496429e55481 | note | Responsibility - SE/PE/SPE
91fdca11-0f2e-5eb5-9317-215b61877a7b | note | Verifying Documents - This ITP
| checkpoint | 5.6 - Cast-in Items
f2f36ab1-eca6-5435-bad9-15d15492f738 | note | Reference - IFC Drawings
9a9fc0e0-57d7-5c13-af40-4216bdde1d4a | note | • 610.46 (a), Table 610.462
1c4cf6c4-6536-5a00-9219-79879354cedb | note | • 610.47 (a), Table 610.472
c7611c31-f9af-5fd1-ad3e-569f026d9b62 | note | • AS3810.1 Table 3.3.6.2
e6e1f715-a33f-545a-9853-03dd459aa402 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
91b91468-db96-5700-bf96-d73678aff904 | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
df51edab-53df-5f50-8fab-da8c7b427099 | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
67ecea6e-cb66-5639-8b11-4b23b0620991 | note | • Grout tubes shall be fastened at regular intervals to prevent kinking
e847a825-7a49-562a-95e4-572b0ede217c | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
998c7056-79de-526b-a966-0f1ef0bff36a | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
bf21ee75-d55e-5b47-839f-aab01f20dacd | note | ii. Running dimensions of a group of the above = ±6mm
17d7717e-e3e2-5af1-b7c6-e2888406613c | note | iii. Ducts and conduit location = ±12mm
2d3191c4-1ad5-5d52-97fc-510d1a26b010 | note | iv. Diameter of ducts and conduits = ±3mm
d3170435-fdc0-5d81-a759-308469170f8c | note | Method - Measure, Visual
f49e993d-e73e-5ef5-ac89-a0ff4319633c | note | Frequency - Where applicable, each pile
e1b537f7-d1a8-5f91-99b1-938f35cedb25 | note | Category - IP
b4223b7b-5928-5722-960a-cd0a4d372e63 | note | Responsibility - Foreman, SE/PE/SPE
6abd5362-2740-549c-8303-c31854820961 | note | Verifying Documents - This ITP
| checkpoint | 5.7 - Pre-pour Inspection
137d834d-a665-5ab4-8470-9ed4ac30cd78 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
3cbdd7eb-c3ee-5fb5-981e-569cc1f184d0 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority. All foreign material has been completely removed from the excavation.
2ca92fd8-40a9-5a19-829e-641b47c47d86 | note | Attach: Pre-pour inspection checklist
816b67fd-31e8-504b-b5a8-032c45453d4f | note | Method - Measure, Visual
faf2c412-8fef-5fbc-ab6c-162774ddc711 | note | Frequency - Each pile
61341418-e4f5-524a-a69c-a34ca557e9ef | note | Category - HP
8debcfe5-76bd-5dae-abba-9dd3a797887f | note | Responsibility - Nominated Authority
175bde89-2df4-57c9-9f26-4696e12df01a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Weather Conditions & Evaporation Limits
b67a3327-8d53-5a02-bebf-88184b02a99b | note | Reference - Hot and/or Cold Weather Concreting Procedure
67536b1c-effb-5a8d-8c5b-7833569225e3 | note | 610.17, 610.17 (a) & (e), Table 610.171
c02b52dd-8c4e-5a45-8284-5844b15401f5 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
aca97baf-8ddb-507e-b708-662356f93c8c | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C
e0ea8c11-bf39-5378-b477-b2123212d6a4 | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
ea6a937c-d5ab-596c-b0d8-e028356913ca | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
1c7c438f-9d8a-5267-9de1-6390ee5119b2 | note | • Record: Required information on the Concrete Pour Record.
512ea921-7582-5312-af91-cae3b8d666db | note | Method - Measure, Visual
6989e803-a179-54fd-b747-9326d69f5ce7 | note | Frequency - Each pile
1fc0add7-3b95-5fa4-8bb2-f461c666a648 | note | Category - IP
2f362302-5f70-55dc-8501-a576aa74a1c3 | note | Responsibility - Foreman, SE/PE/SPE
0fac5482-23eb-543a-bc59-6939953044bd | note | Verifying Documents - This ITP
| checkpoint | 5.9 - Concrete Testing - Sampling Frequency
ab3ed66b-7893-5d53-99c7-13ccc1da5895 | note | Reference - Site Sampling & Testing Procedure 610.16 (b), Table 610.161
86de89b9-623c-5610-8d25-3117da8db987 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
14afaead-2658-574b-8615-ac1d50f5a6f1 | note | • 0m³ to 10m³ = 1 sample
c2752f8a-2bf1-5f79-9367-19445320eb6d | note | • 10m³ to 25m³ = 2 samples
79424a81-1823-5ae9-9ef0-c74b3f3c458d | note | • 25m³ to 50m³ = 3 samples
701077a5-9472-58a9-b7ca-7bbdff7d8933 | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
6d86ec8e-233c-5107-b10a-c0af4a6ce163 | note | • For each additional 50m³ and additional sample shall be taken.
f93d6fb7-d291-50b3-ab4c-e408862e0f3e | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete.
3dcc49af-bfd9-5801-992c-3318e8654f28 | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
ec7643b5-13ae-5c13-b5dd-b3709844a09d | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
a910de4c-9586-5bc7-926d-bcc27e2d388b | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
6813406c-29f4-5b72-80fb-a54cebca6303 | note | • Record: Required information on the Concrete Pour Record.
e6e965a6-8013-59f1-bdc5-f9b5d90ed064 | note | Method - Test
9f14260a-5e32-50e8-8885-11475cb78d66 | note | Frequency - Each pile
7fc91ca3-d95b-57a3-aea7-aa80ec882734 | note | Category - IP
24182c06-55c9-53b6-ac77-0a9e04f79024 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
b7f12ee4-6d53-56ca-9eac-88875f061d9a | note | Verifying Documents - This ITP
| checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
c0820e52-8f07-5bb4-8efb-da4f81042e8d | note | Reference - 610.13 (b)
4d5914eb-698f-5ee8-9728-a49776abf191 | note | Acceptance Criteria - Spread range = 550mm to 750mm
3c5634cb-f14b-5104-90fe-c02b51877d0d | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
344eb366-30a7-51f6-9742-c955676ac6b7 | note | • Passability = ≤10mm (aggregate height differential)
1e9c33c2-fa5f-5873-82dc-151cbbc1b410 | note | • Record: Required information on the Concrete Pour Record.
fe7242f6-15c8-516a-b416-dce52bb00621 | note | Method - Test
d69d7829-ea92-5468-aee4-3cca324cb0f5 | note | Frequency - Each sample of Self-compacting Concrete
237d73de-38b8-5794-bac2-8aa5ff6f4b36 | note | Category - IP
8685bc1c-1fbe-5068-98d6-8a3553f0385e | note | Responsibility - Concrete Tester
75fac9f1-ecc5-5aa1-8a05-f405a14f6215 | note | Verifying Documents - This ITP
| checkpoint | 5.11 - Concrete Testing - Slump Test
01d8e568-829f-5ffc-9cdb-51af66cbf73a | note | Reference - 610.16 (c), Table 610.162
776771bf-cc00-5e6f-900f-3543181b2474 | note | Acceptance Criteria - Consistency of concrete to be determined by a slump test in accordance with AS 1012.3.1
fa95401f-2425-5489-9358-6152a2a1c83e | note | • Slump to be within limits as per Table 610.162
33f48bef-67fc-5110-8861-e6faa7e837d7 | note | Method - Test
efdb63ca-be0a-5f52-b469-df0b8c173498 | note | Frequency - Each sample
7cb8d994-f047-57f9-b743-d49db740425c | note | Category - IP
aa18e3a9-dac1-5566-8d4d-d4b6cdc4961c | note | Responsibility - Concrete Tester
00ebd30f-c79c-5f8c-ada5-41a65c0dede4 | note | Verifying Documents - This ITP
| checkpoint | 5.12 - Concrete Testing - Compressive Strength Cylinders
d3bee8f9-b06a-5f82-9b96-74be1853ceb5 | note | Reference - Site Sampling & Testing Procedure 610.16
ed25b051-1609-5758-8b44-4374b7bb68a7 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
a4b98818-ec65-54f4-b44c-6e5c73eceb2e | note | • Record: Required information on the Concrete Pour Record.
f011b391-536f-5567-8cde-9c00d26ff0e8 | note | Method - Test
7c0b35a2-1298-5541-8658-3fe5884cb524 | note | Frequency - Each sample
423ec98e-9dbf-5c75-9b66-145d736f42eb | note | Category - IP
c66928a2-f69b-560c-a6a9-486577c8318f | note | Responsibility - Concrete Tester
c8fc1277-1bed-5e15-970a-38fff0a65b06 | note | Verifying Documents - This ITP
| checkpoint | 5.13 - Placement & Compaction (Dry or Wet Excavation Conditions)
bcbaeb3e-e5b2-5a89-abbc-70d1f1d03572 | note | Reference - Piling Quality Procedure 610.18 (a) & (b) 610.18 (d) (i) 606.06 (a & b)
0e9e4dcc-bc7e-5764-aa4e-49fd90c63f30 | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm. All concrete batches are traceable.
4af505f3-82ad-5a40-b360-b84b4488de6f | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m. The initial discharge is pumped to waste until a consistent workable mix is discharged. the ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
45fe1315-e631-58e1-bf91-ade20de5448a | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
b3b87ce8-0417-5c63-8c50-d1b9136964b5 | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
231b56f2-3f89-545f-84ba-27d045c43bd3 | note | • Record: Required information on the Concrete Pour Record.
3a44e041-e683-548e-9c9a-acaf4af683fd | note | • Attach: Concrete Pour Record
aad7249d-696b-521b-82c6-9a6060495344 | note | • Attach: Concrete Dockets
c37b7bce-ac5b-5e6d-99c0-10c50a710028 | note | Method - Visual
30d1915d-1d91-55fd-a2dd-29000774d4e5 | note | Frequency - Each load
75fb5568-49d2-5054-b2eb-b8bd47b25f20 | note | Category - SP
e136336a-2bde-5bd2-80c4-f769656a5580 | note | Responsibility - Foreman SE/PE/SPE
e937cfe1-ee26-5711-a848-3de79d707a25 | note | Verifying Documents - This ITP
| checkpoint | 5.14 - Surface Finishes
c3d71bdc-9f3a-5110-b496-7af8f1554b32 | note | Reference - IFC Drawings 610.31 610.20
8f0a57b5-d3e2-55a4-94d2-2a9cd606b7bd | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
9f269fdd-7eaa-59b6-868a-5950241ccd3f | note | Method - Visual
44833f4f-fab0-5487-8ce8-88f38b822494 | note | Frequency - Each pile
b5706f54-8f38-5178-b8ee-271decddd291 | note | Category - IP
050f1f8e-8c26-5c7f-b4bd-c0b20deb3b71 | note | Responsibility - Foreman SE/PE/SPE
20169090-0151-52db-ad2a-9dd92e3cd2f8 | note | Verifying Documents - This ITP
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Compressive Strength Test Results
fff6907e-65f4-5467-90d2-000792791833 | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
3b63ece6-4fd0-515d-b5d8-31611fe40551 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
9111bc53-0485-55d8-8a1e-5c7c1bfd19f6 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
ea454378-a0b2-57d8-b59f-a6bf5764b7d2 | note | Attach: Compressive Strength Test Results
a0faf426-f004-503f-90d6-e864ca69fad7 | note | Method - Document Review
819d2039-1659-5c7f-9be5-8165651d8e25 | note | Frequency - Each cylinder
ac23d88d-5eaa-537b-a87f-c588464dc3d8 | note | Category - IP
172a32dc-6840-5766-a4a4-160f9b5fca7a | note | Responsibility - SE/PE/SPE
081151e7-be56-5a12-9318-7dd10c4ccb94 | note | Verifying Documents - This ITP
| checkpoint | 6.2 - Pile Integrity Testing
07334617-8c27-547b-9e4c-bb8f0f8280fa | note | Reference - 606.07 (a, d & e) AS2159 Clause 8.8
03da2f59-2869-57d1-92f6-f757d1adaf86 | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
65e0dc03-50bc-5578-ad66-ed589936c74d | note | Cross-sectional area = ≥95%
d8cf11df-b173-5180-bd41-e4cf9f0744d4 | note | If any test fails, all piles shall be tested.
7369a072-e54b-5cd0-8a1a-7ffa777f8f42 | note | Attach: Pile Integrity Test Report
2e7342eb-53f1-52e3-8886-3183ed1e38ec | note | Method - Document Review
dea1839d-1e4e-5160-98be-e277138df491 | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
ba7f953e-c3d5-5e6b-a4cb-14622ec8748c | note | Category - IP
f5e00654-e023-5591-917d-b5384cd032d9 | note | Responsibility - Testing Consultant SE/PE/SPE
f89b5c1d-4689-594a-b259-177bb4ced69d | note | Verifying Documents - This ITP
| checkpoint | 6.3 - As-built Survey
bb940145-3d41-5699-ba97-cc48ecaa917b | note | Reference - IFC Drawings 606.08 (a - c) AS2159 Clause 7.2.2
1c5b3fa2-64ca-5735-9230-c6e74c2b0b35 | note | Acceptance Criteria - The following tolerances apply to piles:
51832e71-c061-57d4-816f-ce24c0bccd5e | note | i. Pile head plan location = ±75mm
1b55898b-28f8-599f-a994-15d284860969 | note | ii. Variance from vertical or rake = 1:100
4eec18ec-da58-599f-ab18-fd08d9c51e68 | note | iii. Irregularities in straightness = 1:100
96914fad-f377-5bea-8598-1f69579b16d6 | note | iv. RL = ±25mm
23f6dcd2-b3a6-5c84-85b8-d73d94dceead | note | Attach: Survey As-builts / Survey Report
42ba2410-7130-5096-b6b5-30e4c376e862 | note | Method - Document Review
eaa52dc3-1c01-5f10-8a75-e13c8ae0961a | note | Frequency - Each pile
5b23bf33-058e-5fdd-b8c9-79159dd44c96 | note | Category - IP
a5b41953-8ca7-500b-9bcd-0d9d35ca946b | note | Responsibility - Surveyor SE/PE/SPE
858c0a12-778b-54ae-b7ba-109382579f71 | note | Verifying Documents - This ITP
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
6cb72887-727e-55f4-89db-ddeddc523b32 | note | Reference - MRPA Quality Management Plan
afda1f76-7681-5667-bd1c-30baf67e19ef | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f42c1f86-158e-50cf-bd91-c94117e750c1 | note | Method - Document Review
33529240-cd58-5aab-a8dd-402445ca3537 | note | Frequency - Once, prior to closure of this lot / element / Work area
018ceca3-b319-5537-870e-13c45754ab86 | note | Category - HP*
c5683397-2598-5130-8668-2ba6e420a9a0 | note | Responsibility - SE/PE/SPE
b6b096a4-7642-506e-9524-485e9d8a0a97 | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
ce008633-ee3a-5091-b887-644bdc24eac6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
890a42a3-707e-5439-a264-feba315b06ed | textbox | Name:
f3ca944c-8e2e-5d1e-8a1d-d2f84bfbe1c9 | textbox | Position:
78f38e3a-ad91-5c2c-8ced-09c089ae69a5 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-018-CIV - Rail Delineation Temporary Fencing |  | ITP-018-CIV - Rail Delineation Temporary Fencing | d5893295-6f23-44df-9977-9016088197db
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
49a60d57-6123-55aa-b7be-8a3ac319df20 | note | ITP-018-CIV-Brunt - Rail Delineation Temporary Fencing
004e7bf7-04cc-5797-a0c8-f77b5bfeb28a | note | Rail Delineation Temporary Fencing
05937d5e-05eb-503f-8173-a4a5afb41186 | note | CIV
39b8aecc-a924-52bd-a916-1d3d6d511c72 | note | B
26157d17-12a8-5451-88c0-67dabf0e4bf4 | note | 12/01/2023
f5e170dd-c3cd-5fc0-97c5-ad2808e9b949 | note | Casey Knowles
71fbd623-fa48-56fa-b525-8b5ecacdeccf | note | Jon De Castro
42a58549-c3ab-5734-92f9-4aca1ffce1dd | note | ITP for Brunt Rd only
| checkpoint | 1.1 - Non Dependent
2a8dffb2-68f4-56ab-8267-6b79039a65a2 | note | Reference - IFC Drawings L1-CHE-STD-005 L1-CHE-STD-025
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
47a88c6d-99ce-56d9-b81c-4296f94a7690 | note | Reference - IFC Drawings
1f8f3773-4552-5da2-8fca-4e45f9ea0688 | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings. Attach concrete delivery docket.
fad838b6-117d-5c25-8bfa-8f3fec182da1 | note | Method - Document Review
465f6575-e2da-5ee4-b4a4-17b91c139182 | note | Frequency - Each Mix
c65899e4-f70a-5dd7-b994-f192d1f1d8e2 | note | Category - HP
37647053-5974-590b-86c9-32fcf9a52e62 | note | Responsibility - SE/Site Supervisor
f50fafae-c8a3-53d1-9a60-d87721ed1afe | note | Verifying Documents - Supplier Certificate of Compliance Deivery Docket
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Steel components
43f5e242-67a4-53d0-9f15-d42f95ea2531 | note | Reference - IFC Drawings AS41000 AS1163
aad9508b-99cd-5949-a2a6-c0879564fce3 | note | Acceptance Criteria - All Steel must comply with Australian Standards. All dimensions relevant to setting out and site work are to be checked on site by the project engineer prior to works commencing. Erection and fabrication tolerances for structural steelwork as per AS4100. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250.
68e38571-4c53-55f4-9706-1b5e67fee084 | note | Method - Document review Visual and Measure Order Acceptance Checklist
7e5e872f-74be-5056-b114-360a394a55a1 | note | Frequency - All elements
d9013d35-bae3-5ab0-ae7d-18c7c680d90c | note | Category - IP
8b909d21-7bfa-5c6b-81bc-ec20c9e003c0 | note | Responsibility - SE/Site Supervisor
31969b90-b953-5ff5-9610-ddd905d0d0c7 | note | Verifying Documents - Supplier Certificate of Compliance
| section | 3. Preliminaries - Documentation
| checkpoint | 3.1 - Excavation works
746f05a8-9cb3-5aef-99a8-97e1b6741361 | note | Reference - IFC Drawings L1-CHE-STD-005
0b971038-b61c-5974-ac75-f8b8416c5882 | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements. Follow asset owners guidelines for work around their service. Where posts are within 1m of an underground service, or whereelse nominated, post footing installation shall be via Non Destructive Digging. Direct driven installation method to be used for all other posts.
13dbafa5-7241-5964-8836-36c8a07348c5 | note | Method - Document Review Visual
13176b84-2181-5f95-9bdd-4dd04ea67f58 | note | Frequency - Each Post
3a345071-3c5c-55e4-bcd9-dbaf004afc52 | note | Category - IP
f7b83b8e-1327-527a-bef4-e217b1ff5d9c | note | Responsibility - SE/Site Supervisor
51ec3f16-acc9-5089-886e-3423c124400f | note | Verifying Documents - This ITP
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-out
4354b5ad-148a-5feb-b0c5-a4fd6827327a | note | Reference - IFC Drawings
8b11fcad-069d-5452-bb6f-51152ab69e64 | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays, gate locations, tie in points. Offset checked against the running edge prior to installation of posts. Up track & Down track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
e3a55277-3c60-5aaf-a95f-8d2993c5c464 | note | Method - Measure Visual inspect
85f06c05-df5a-5869-8e77-1177888cb636 | note | Frequency - Each element
6e26e5a2-dc02-59e2-b5f4-1ccb78c62dd3 | note | Category - IP
ed5ece6c-530e-5cab-ab49-ddfa30530145 | note | Responsibility - Surveyor SE/PE/SPE
2c880b13-ccda-526d-aa13-f4f4dad1ba24 | note | Verifying Documents - This ITP
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Ground Conditions
23486828-33da-5083-a2c5-d4e1dd7d80b7 | note | Reference - IFC Drawings
ef49b2f3-119a-56ef-908e-0324f4e85a7b | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
a78e4402-7058-5d25-bec6-1baae39cad42 | note | Method - Visual
89f204c9-bd12-5f35-9504-48cc4fa9f1f6 | note | Frequency - Each post
2bb05fad-3eba-56be-9338-60100d6af1de | note | Category - IP
71baf2cf-e7a8-59f9-b6ec-ab5cb7e8f375 | note | Responsibility - SE/Site Supervisor
8fafa8f8-3cff-5286-9bd5-177d8174624f | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Post Foundation
1f6c1322-3b7f-5fa6-b463-6c4ae1a99851 | note | Reference - IFC Drawings
4ca189e9-92c6-5c08-b722-e6f4381ff4c3 | note | Acceptance Criteria - Post into 101.6x4 CHS Sleeve - 300mm Dia - 1300mm Depth - 2700mm Typical Spacing
8b83fb41-283f-5030-91bb-70f89dea38be | note | Concrete Footing (for Steel & Timber Posts) - 300mm Dia - 700mm Depth - 2700mm Typical Spacing - 600mm Post Embedment
f7bc3401-a5dd-51de-8928-fce8d4965834 | note | Direct Driven 88.9x4CHS Posts - 300mm Dia - 1500mm Depth - 2700mm Typical Spacing
cfffcb64-04df-5ccf-867a-040ac64c6489 | note | Gates - 350mm Dia - 1100mm Depth - 1000mm embedment depth - 1350mm end span spacing
e6d1c2f2-e6b6-56d2-a2b0-0abf480a0fd9 | note | Where post is installed through a slope/embankment, increase the depth of embedment by 600mm from the above requirements.
1a67751d-98eb-50a0-8524-78039394ee95 | note | Section 610.161 Concrete testing at frequency as per 610.161. Minimum of 2 samples per truck.
4e960bab-f889-5d87-b090-e541877b7d70 | note | Method - Measure
d604e622-e325-54e6-a093-1541c34e78d7 | note | Method for Section 610.161 - Concrete Testing
9636d6a0-6913-5b7a-9dd4-fad18142c44e | note | Frequency - Each footing
4ea90bdb-d70d-5df3-9851-505be07bc053 | note | Frequency as per 610.161
7fc7ce7b-7c2c-5c96-9090-179e3b6b6ad9 | note | Category - IP
b10326f6-3ce3-56ea-a6e0-828a4a18dff1 | note | Responsibility - SE/Site Supervisor
4bfec945-e638-560f-aff6-14088bd969b9 | note | Responsibility for Section 610.161 - Testing Report
3e3fcdb0-146f-5c53-83d8-2ff6f1c3708e | note | Verifying Documents - This ITP
| checkpoint | 5.3 - Post Installation
cf971ca5-ad2c-5529-83ad-b513cef13a2f | note | Reference - IFC Drawings L1-CHE-STD-005
e532c69b-3dc0-5a93-8961-159cacc277ab | note | Acceptance Criteria - Up track & Down track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
f001543d-2005-514a-a4c0-fef2cc86b2fc | note | Maximum post spacing to be 3.1m to avoid clashes (localised only).
5afe9b53-8275-5ada-aa78-904369e93aa3 | note | Two spans at 1350CTRS at the end and at Refuge bays.
c548d363-c92a-5aa4-a9ac-d5ef9d0e6305 | note | Max. post height 1800mm above ground level.
5dd8fac0-9455-5edc-9a6b-afad0faab199 | note | Vertical Tolerance: ±20mm from the design line.
6fe7376b-c944-59b7-976c-93b69f877b12 | note | Timber Post to be installed directly either side of OHLE footings (existing and future).
d784857a-6fd5-5f4f-a8fc-545c410ebfbb | note | Method - Measure
211b8e04-a859-5287-a305-6f5bd032cce1 | note | Frequency - Each post
8796a8d0-5340-57fa-8672-12aae4ddd175 | note | Category - IP
2794f13c-ae4f-52fd-8c38-df1ad9f798e9 | note | Responsibility - SE/Site Supervisor
edb3e090-070e-50b1-b86c-78253cbe27c3 | note | Verifying Documents - This ITP
| checkpoint | 5.4 - Chain Wire Mesh Installation
6d38b241-4e87-5069-9878-e5af856b25ba | note | Reference - IFC Drawings
5678344b-dcfa-5ad0-8707-fed1bd27e053 | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wires.
9193df3b-210d-5e64-8eac-5f52ef496631 | note | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tie wire or approved clips.
9688de5d-4bfa-59b4-b9fd-a422901f0a09 | note | PVC coated mesh and tie wire to be installed for 2m extent either side of OHLE footings (existing and future).
49f21903-d3f4-55cd-88b1-b229b0fb1df7 | note | Distance between ground and bottom of chain mesh and ground to be 50mm.
e22a3857-59eb-5150-bc72-631cb139a45c | note | Method - Visual
77ba1fda-0dc5-51e4-9d45-38feaa67d47b | note | Frequency - Each element
81b8af1d-342e-5835-bfd0-ae5a1c4fdfb8 | note | Category - IP
fc72415e-c29a-54dd-816b-e6ff69a3ba6b | note | Responsibility - SE/Site Supervisor
c2ba6288-f9ae-5341-98a2-22d7d7800fd6 | note | Verifying Documents - This ITP
| checkpoint | 5.5 - Bracing
e285804e-4544-5d5d-9831-6d345a5e4c1c | note | Reference - IFC Drawings
04aeb4a0-044a-558f-8cda-8daa90cd63ff | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
0d2055fc-371a-5e89-bb13-10119de679cd | note | Bracing to be installed on both sides of the fence at the fence corners
ab353d7a-98ba-5b9b-86ea-ac8498c7c7b0 | note | LVL Brace to be used between timber and steel posts either side of OHLE footings (existing and future).
5cbedd33-eb2c-5564-8040-45785cec9eeb | note | Method - Visual
a0a30cc2-6f4e-5294-8f21-6e6c3505d6cb | note | Frequency - Each element
9ff30c8b-b87c-55d9-8b2c-3478781e9e00 | note | Category - IP
8de83fba-2a21-5502-9f27-e4ef089e1801 | note | Responsibility - SE/Site Supervisor
f3669e03-cf21-560f-baee-b0825ee65f31 | note | Verifying Documents - This ITP
| checkpoint | 5.6 - Refuge Installation
0be0407d-2057-54df-8164-da8777a31d32 | note | Reference - IFC Drawings
9826e0e2-62f2-5c02-9232-b5e98c6c7ceb | note | Acceptance Criteria - Refuge Access to only open from track side.
e580def4-c676-566f-8ebc-71c06b91e480 | note | No chain wire mesh to be installed at refuge access.
91b6cf41-f7ca-552f-b589-bea179eb35be | note | Refuges at southern fence shall be staggered in relation to the northern fence refuges. Refuges to be at maximum 20m c/c spacing.
777a0624-bc31-5ba4-a541-f578a8a342ca | note | 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
c488423c-2815-5386-801c-0060493cb192 | note | Method - Visual
54cc27cf-531c-5349-a92a-9e14bb54ed2e | note | Frequency - Each element
e7e5bf24-af5f-5779-8b11-f1dd7253171c | note | Category - IP
37f5601d-984d-5029-bda6-1c8cd3d1c816 | note | Responsibility - SE/Site Supervisor
abb6bb21-04d9-5cb3-a619-bde27e5129ba | note | Verifying Documents - This ITP
| checkpoint | 5.7 - Refuge Signage
5e62ca1f-ed75-5861-a660-b11a7afcd564 | note | Reference - IFC Drawings
5784ab9b-c4db-5195-bd3a-ad8942d3b413 | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
64208897-0291-5a5d-8c81-2d79384a80c6 | note | Method - Visual
fd13c10c-5c46-52a1-a655-937897db63e6 | note | Frequency - Each element
9b3d222e-7fb4-5487-8885-8df0da101902 | note | Category - IP
77f57202-29f3-53f1-a6b0-e60ba98262ea | note | Responsibility - SE/Site Supervisor
8005ca26-59e4-5a78-ba8a-52c61864b319 | note | Verifying Documents - This ITP
| checkpoint | 5.8 - Fence Tie In
8c9bc60a-c6d7-5afa-b50e-8540dfc89cd2 | note | Reference - IFC Drawings
0ab05ce6-09ba-5ee1-8652-3c775917ee7c | note | Acceptance Criteria - 200mm Air Gap to be provided to existing fence to provide electrical discontinuity.
797b4484-ed2f-5765-a4ba-9a5eb07215e2 | note | Method - Measurement
b7636286-e696-5a1b-9e0a-6f0080041231 | note | Frequency - Each Tie In
d92fa36a-aa5e-5b74-9cbd-fb024a05789a | note | Category - IP
d0aaf000-801e-5163-9aff-3bba0499ee90 | note | Responsibility - SE
223e1f94-4634-57b0-b2fb-e12555c90ac9 | note | Verifying Documents - This ITP
| checkpoint | 5.9 - Gates
9aeb0f06-0da3-5114-bf79-80593abcdda9 | note | Reference - IFC Drawings
e4f35f63-2865-52b8-8731-cd212c8841ee | note | Acceptance Criteria - Gates to be installed as per IFC drawings. Location may be moved nominally to avoid service clashes.
0fcf76bb-bc05-5aaf-9ee6-864ebcecef9f | note | Method - Inspection
704048f5-3aca-50f1-9c3e-b34dda0158ec | note | Frequency - Each element
9d4a3491-a19e-55cf-b7b9-170ef9dc1653 | note | Category - IP
7b2c7f3a-5328-572e-9cc1-5f116b2da8fd | note | Responsibility - SE
7bcfc6b9-7795-5569-a402-6fadf7936430 | note | Verifying Documents - This ITP
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Fence Height and Track Clearance
cf442c4e-c33d-5cef-aa37-a000215ef6de | note | Reference - IFC Drawings
d7dbecd1-e4f7-551a-b5a5-d85ea510f3f0 | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. Attach as-built survey.
ba894dc1-d999-57d8-b7b2-7dc7c4b0b016 | note | Method - Survey / Measure
391efbbc-fb16-56c4-8b1c-a71ed9d76952 | note | Frequency - Each lot
f0d79ab1-2a5b-535b-ab43-c9b09e3ce516 | note | Category - IP
5b6ca6e8-8518-5231-91b6-1d5f62f87ebd | note | Responsibility - Surveyor SE/Site Supervisor
ade9378e-84ef-564f-ab93-88b1339d7aa7 | note | Verifying Documents - As-built survey
| checkpoint | 6.2 - Compressive Strength Test Results
c9093542-6ed3-54b3-aa62-17ef9dab268a | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
6874aee7-3030-527f-9c9a-3bede66730bb | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
1468fd3c-5f67-5ee6-8ace-40cb9bb08173 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength
d972ca36-b0d2-53e5-8fc7-1805498efb8d | note | Attach: Compressive Strength Test Results
0a9644b9-5a87-5eb6-aaf8-422b17750f14 | note | Method - Document Review
f8217460-d5e0-5c0e-9508-cba33f895b43 | note | Frequency - Each cylinder
62c960da-f1b9-5e61-b25f-56bc1abe4abf | note | Category - IP
eaf7232a-fb89-5a48-825a-b5e7976d0b08 | note | Responsibility - SE/PE/SPE
20fe5757-37dd-59f0-b6a8-a9fe0c090f7a | note | Verifying Documents - This ITP
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
f0af6660-3bba-5898-b888-8be70ed9bc64 | note | Reference - MRPA Quality Management Plan
73d8010c-9604-53b0-aeb0-feb9c5b536cd | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
295d5bf7-383b-5205-bb6c-ca4fa06fa177 | note | Method - Document Review
59e3d294-acfa-5f1e-97cf-ef9315d54327 | note | Frequency - Once, prior to closure of this lot / element / Work area
8f32cf8f-7c6d-5da9-a4d4-44447eaf85a5 | note | Category - HP*
3a82e2e4-cfdd-59ac-840b-591962fba7b9 | note | Responsibility - SE/PE/SPE
55c1dbc2-4996-5ab3-8198-4ea381913302 | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
f8699205-a213-5aa7-a73a-06b8836c5969 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
aed79ae8-abf3-5f0e-bc61-ab0724ab1db6 | textbox | Name:
6a91607d-f6d8-5917-8f37-c45d98e89380 | textbox | Position:
09b6037e-8554-5bf4-80df-69f833451586 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-019-CIV - Conduits & Pits - Rail (Supply and Install) | itp | ITP-019-CIV - Conduit & Pits - Rail (Supply and Install) | 10482046-fbfb-4ebb-93c9-6e3092ba1ab9
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
f5f2e605-ff9c-584e-8af5-7e105d3e9ed7 | note | ITP-019-CIV-Brunt-Conduit & Pits-Rail (Supply & Install)
f0c9db2b-f6bc-5d22-9dd1-ae628970b8dd | note | Conduit & Pits - Rail (Supply and Install)
afc16df7-5ab8-5198-8002-4f59cf4c9793 | note | CIV
3e7dbcb5-8836-5dd3-aa82-50aff6ba3407 | note | 0
f52cd485-d011-5213-b0d3-d775f181853e | note | 13/01/2023
9fe5cd5f-a9b1-58f0-bf27-c56f3d61f756 | note | Shubham Bajaj (Sammy)
5ca1fb1d-3644-589e-8a7a-60567332f935 | note | Jon De Castro
66f93ac0-90cb-5f8b-818f-7cc762e4f33a | note | This ITP is to be used in Brunt Rd only.
| checkpoint | 1.1 - Non Dependent
7000b2a5-bc0b-5dae-bf94-1a50fe67650d | note | Reference - IFC Drawings L1-CHE-STD-043 (VRIOGS 012.2.1) L1-CHE-SPE-070 Australian Standards MRPA Standards
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Conduits
1a2e5641-4981-55cc-95d8-bc200ee6d9ed | note | Reference - HV Conduit: AS 2053 - HV Conduit (boring): AS 4130 - Comms Conduit: AS/ACIF S008:2006 - LV Conduit: AS/ NZS 3000 - 2000. - L1-CHE-STD-043 - L1-CHE-SPE-070-
c3d31b76-c761-5345-b989-1782e338d2c3 | note | Acceptance Criteria - LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness LV & COMMS CONDUITS TO HAVE A MIN 600mm BENDING RADIUS Inspect materials upon delivery and attached delivery dockets.
54d92a46-d7e3-5eb9-9039-59f8c16a520e | note | Method - Visual Document Review
68014b69-0e72-5ca5-b207-573c74db7ee6 | note | Frequency - Each Material Type, Each Delivery
23932b10-fbad-5efb-a718-483460d0852a | note | Category - IP
e3997368-ffcd-521a-9481-1722e2f3a753 | note | Responsibility - SE/PE
11fb24a2-bfef-56be-a396-0518a4e98791 | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| checkpoint | 2.2 - Pits and Pit Lids
3e25cad9-a5a5-540a-b3bc-169967ed69e8 | note | Reference - IFC Drawings -VRIOGS -012.2.1 Section -6.15-16 - VRIOGS 012.2.1 Section 6.9 - VRIOGS 012.2.1 Cl. - 6.7 (c) - L1-CHE-SPE-070 Cl. -10 -AS1289-
ae0286d0-bfa8-52c3-b81b-d34f38a74fa4 | note | Acceptance Criteria - Pits: -Pits located within 1.5m of nearest rail, pit to be 300LA Railway loading - Pits 900x900mm or greater, multipart pits lids to be used. -Pit Lids: Pit Covers shall comply with AS3996-2006 - Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C. - LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6) -Inspect materials upon delivery and attached delivery dockets.-
6f680932-7548-51b9-8592-1b43c44ac4ce | note | Method - Visual Document Review
3fd0dfdc-c724-53bb-9d01-9ef21ebadbf5 | note | Frequency - Each Material Type, Each Delivery
10f7d7b4-8b90-56ae-85d6-c42f7334aff9 | note | Category - IP
3db869ea-2788-541a-90c6-abbb10af596a | note | Responsibility - SE/PE
1ce80539-56e1-5d21-8c31-2ddb03ddef03 | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| checkpoint | 2.3 - Warning/Marker Tape
19b8d005-9b23-575f-ad8a-ec7bd8cf25bb | note | Reference - IFC Drawings AS/NZ 2648.1 TS-SP-013 L1-CHE-STD-043 6.4
5d829ec8-65ac-541c-8a45-2a85037768b6 | note | Acceptance Criteria - Warning/Marker Tape: Above LV: 150mm minimum wide orange coloured PVC ‘DANGER RAILWAY SIGNALLING CONDUITS’
9436ed88-be1b-5186-adc4-acf6a5e58844 | note | Above Comms: 75mm minimum wide white coloured PVC ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire to be laid directly above trenched VicTrack assets
d5235150-3157-515e-99a4-3f24dd0aee4d | note | Above HV: 300mm minium width orange coloured PVC 'Danger - Electrical Cable Below'
0d5cf6cb-aeb5-50db-b8cb-6b06bcb86af6 | note | Inspect materials upon delivery and attached delivery dockets.
95970bf9-eb68-54b8-9f13-327dc13025bb | note | Method - Visual Document Review
aecdd65e-1b37-59c4-ba7f-7f10e9aeb314 | note | Frequency - Each Material Type, Each Delivery
4702353a-b047-5b10-aad3-458147742f9d | note | Category - IP
c8f17d97-c376-5fc4-be9b-1e94ceb95668 | note | Responsibility - SE/PE
e89f21bd-5d8a-54c1-918d-7d7a8fc28fdc | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| checkpoint | 2.4 - Protection Barriers
8a37118a-3924-587e-9d51-45abc496b36b | note | Reference - IFC Drawings L1-CHE-STD-070 10.3.3 AS4702
3120690f-430e-5e26-85a8-28c6eba85fd8 | note | Acceptance Criteria - Protection barriers shall be polymeric cable protection covers complying with AS4702 OR a min. 40mm thick concrete barriers (pavers) not less than 15MPa at 28 days Inspect materials upon delivery and attached delivery dockets.
62f63b42-6498-5138-bdd6-2b68dc7223c2 | note | Method - Visual Document Review
1ba15ade-ffe0-52ae-908e-e7300d019009 | note | Frequency - Each Material Type, Each Delivery
845efd91-d37e-546a-8834-ceb2e6ac1b08 | note | Category - IP
5b24d959-e81f-5a69-93fb-dcb02eeec2c9 | note | Responsibility - SE/PE
0813e889-c9db-59e8-a322-ece83e6afc78 | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| checkpoint | 2.5 - Backfill Material (stabilised sand)
fc849307-a4b8-5fbe-b51f-dc89f84a10fb | note | Reference - IFC Drawings L1-CHE-STD-043 Section 2 Table 1
b41d9d70-017a-585f-8ed3-289ee2a0aaee | note | Acceptance Criteria - Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits. Inspect backfill material. Attached delivery dockets (if applicable).
ac059ad7-e386-50fd-8eb8-a22e4860a703 | note | Method - Visual Document Review
26ff958e-9fe5-5fb6-9e2a-59480aa1c5d7 | note | Frequency - Each Material Type, Each Delivery
716dd006-8d38-5f23-a5ec-ded1f6edd0ed | note | Category - IP
b6d4af4d-2f94-5fd9-86b3-2745c04fe548 | note | Responsibility - SE/PE
14094ae7-514e-5061-8ec9-0741b90906b0 | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| checkpoint | 2.6 - Bedding Sand
51d353cf-3d5b-58f7-8b2e-801c52de9767 | note | Reference - IFC Drawings AS2758.1
d1ea6e61-fa75-5bf5-b068-271597493481 | note | Acceptance Criteria - Bedding Sand shall be a clean sand that is an uncrushed fine aggregate to AS2758.1 and shall have a thermal resistivity ≤ 1.2 °Cm/W at 5% moisture content.
4cabd3b2-444e-5c86-b36d-a2f87bae9cdb | note | Method - Visual Document Review
cc9d9b7a-f81e-516e-aa3d-3b6cbce30f9f | note | Frequency - Each Material Type, Each Delivery
8e497d93-d921-52ad-b9de-462b06835397 | note | Category - IP
d821f960-9a70-5aea-b5b8-941981a8112b | note | Responsibility - SE/PE
49c522d3-32af-5770-b482-8f74b7cd6b93 | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| checkpoint | 2.7 - Draw Wires
a21e2381-b3d6-5832-86fb-a784bfe99c26 | note | Reference - TS-SP-013 AS 4142
0b4ce6d4-b3fe-59fd-a676-66e6b87785ea | note | Acceptance Criteria - 6 mm diameter polypropylene blue/yellow
f21dc47a-2e1c-580e-8c32-8854cf5a1993 | note | Method - Document Review
b654a229-62e4-5c0c-9672-68155b9951cc | note | Frequency - Each Material Type, Each Delivery
5a700b49-8951-529e-885f-07db9bc61451 | note | Category - IP
b82b10fd-92cf-5c55-91d8-49b047feee63 | note | Responsibility - SE/PE
360f9dff-4221-53fc-b4d4-8fd22ff186fa | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| checkpoint | 2.8 - Concrete Mix - Trench
2486c569-a575-5c8c-8361-42253ea4e5d3 | note | Reference - L1-CHE-STD-043
5ac4b019-c799-5d47-8df3-e989f6157aaa | note | Acceptance Criteria - Concrete strength at 28 days shall be not less than 25MPa. Chemical admixtures or fly ash shall not be used
ade23e7d-b422-5e50-a3be-9029fcef81f6 | note | Method - Document Review
3ee93585-2698-571e-9ae7-a42078825a96 | note | Frequency - Each Material Type, Each Delivery
38021260-8f68-5365-86ed-8f3e22321111 | note | Category - IP
8e854544-7261-5fa5-ae92-e8b580c1c1b8 | note | Responsibility - SE/PE
61f5a9f6-b3ad-57e0-b62c-e537cf55d778 | note | Verifying Documents - Attach Material Conformnace Certs Attach delivery dockets
| section | 3. Prelimnaries - Procedures & Documentation
| checkpoint | 3.1 - Services
4f73390a-8ec7-53eb-8615-d8048612bf66 | note | Reference - Services CAD file
c09a53c8-0b92-526f-b220-c5fad1f72f2b | note | Acceptance Criteria - All services within 5m of Excavation location have been identified and appropriate control in place (refer to MRPA Excavation Permit). Survey to mark out existing services.
c393a1cd-e412-5246-8075-87b442734d00 | note | Method - Visual
0826e828-aba0-52b6-af9b-90fb81c34d1c | note | Frequency - Prior to commencement of works
d8d5aa4a-63f6-52b0-9d6a-92d162a7c422 | note | Category - IP
8c0e5a58-f118-5d28-b448-b2f09b7dae34 | note | Responsibility - SE/Site Supervisor
0909aeb7-c15d-5225-9927-f18967cc6645 | note | Verifying Documents - This ITP
| checkpoint | 3.2 - CSR Works Procedure
8319042b-97b4-5cdb-b6e8-cd9b41899a81 | note | Reference - WAP_BRU_201
7daf1245-ba81-5550-86f4-61233f160119 | note | Acceptance Criteria - WAP to be reviewed and signed by all relevant stakeholders along with Rail Safety highlighting works proedure with in the Rail Corridor
a3bd840e-d56d-5867-b484-1b5696fe3676 | note | Method - Document Review
96afa029-bc3e-577b-820a-aed15b8e1eba | note | Frequency - Prior to commencement of works
ccb15b3c-7f02-5c38-8ae6-388c4ca1f523 | note | Category - HP*
b12b12c5-e50f-537b-966b-a67c4c38058e | note | Responsibility - SE/Site Supervisor
d477e924-b384-5633-aa9f-415cfaafa7d9 | note | Verifying Documents - This ITP
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set-out
f6aeb431-97df-5c58-bb61-dc9a0b8b5e77 | note | Reference - IFC Drawings
f7897f00-4768-56e1-8432-2bb08cd26ee9 | note | Acceptance Criteria - Survey to set out trench alignment and pits, and establish construction control (alignment and level).
f4edd5ff-826c-51e4-ae2c-3f4df49d42bf | note | Method - Measure Visual
9c72ceb0-cc50-5349-9a1a-e7c19cd92c03 | note | Frequency - Each element
f31f08b2-fe81-57a8-8c23-788ba4595e82 | note | Category - IP
1e809443-e7fd-5a69-976d-13ed6d43af32 | note | Responsibility - Surveyor SE/Site Supervisor
8da1f169-a897-50d7-b3e0-2bffb7c13808 | note | Verifying Documents - This ITP
| checkpoint | 4.2 - IFC Drawings
c8553c6f-7ddb-59e9-88a3-b0437d52b970 | note | Reference - IFC Drawings
7f3eba87-8ebf-5d9d-971e-f088c39da223 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
c6ed01ca-d710-504c-b0c9-5332568ac2f1 | note | Method - Document Review
16802713-3117-5e2d-9748-4e371b0b2e82 | note | Frequency - Prior to commencement of works and at regualr intervals
e01a3a4f-6a54-58ac-8a42-5f8690c55db3 | note | Category - IP
97af38ec-7cbd-596d-bfb2-9e1272409415 | note | Responsibility - SE/Site Supervisor
6891a9b3-b37e-5cd8-a15d-ec70b3dfe123 | note | Verifying Documents - This ITP
| section | 5. Construction Activities
| checkpoint | 5.1 - Trench Excavation
31e168b2-9b16-574a-9a51-148afc20d816 | note | Reference - IFC Drawings L1-CHE-SPE-070 7.3 Table 2 L1-CHE-STD-043 L1-CHE-STD-070 7.1c
2f9938d0-2e44-5cc7-881e-de3d6d132396 | note | Acceptance Criteria - Trench profile and depth as per IFC drawings. Edge of trenching to be a min. 2m from strucutres/pile foundation (unless it is mounting the structure) and a min. 4m from the rail for HV and 3m from the rail for LV & Comms The bottom of the cable trench shall be level across its width and free from any protrusions and rubble that could cause damage to the conduits. The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
7a311320-809c-5cda-99c1-a58ad60e15df | note | Method - Measure, Visual
cd04608c-d208-5eef-8240-b4698fd1a48a | note | Frequency - Each lot
778f455a-959c-5590-8031-ef84bf5c9add | note | Category - IP
6277b753-4ad2-5b12-a03f-c15a18415412 | note | Responsibility - SE/Site Supervisor
573388ad-968d-54b3-b39f-68ac3df1a654 | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Trench Stability
0ee562ce-980e-5d98-a929-fb2516f7ad67 | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings MRPA Standards
9b31f2f2-f67a-5dc7-b6d8-49f17f2ed42d | note | Acceptance Criteria - Trench stability check: - Shoring, - benching - geotech signoff Attached Geotech Report
f752b05d-52c0-5310-b989-53e8db433feb | note | Method - Visual, Document Review
818f1ecb-2a23-5c7c-9321-534fbd702df8 | note | Frequency - Each lot
3922c741-b48d-5a37-902b-30ef7ba69a6d | note | Category - IP
3fac6657-ca7c-5acf-b904-358b78739879 | note | Responsibility - SE/Site Supervisor
0ec11a44-ddf6-5098-829b-d7734e37c8b9 | note | Verifying Documents - This ITP
| checkpoint | 5.3 - Placement of Bedding Sand for Conduits
983ca552-ff7a-5bc6-a7b7-00717df3ec87 | note | Reference - IFC Drawings L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070
11382dbc-f616-5d2b-8114-852ca946134d | note | Acceptance Criteria - 100mm of bedding sand/crusher dust to be places at the base of trench.
48470d92-f1a2-5c0b-ba79-7a3e8fda940f | note | Method - Measure, Visual
f485fae3-901e-565d-8d75-66450f1cc5d4 | note | Frequency - Each lot
f01b30b1-e20d-5242-a146-d007e3b1de9e | note | Category - IP
c31b5283-1499-52dc-abf3-eb7f3f39373d | note | Responsibility - SE/Site Supervisor
07751179-7e43-50e8-879c-f3c1223e2ef6 | note | Verifying Documents - This ITP
| checkpoint | 5.4 - Conduit Placement & Configuration
a6c6b201-e994-5a4b-8b9b-87613f485936 | note | Reference - IFC Drawings L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 L1-CHE-STD-077
6de8075a-c26c-5171-9ce8-56f63142f8c8 | note | Acceptance Criteria - Conduits are configured in accordance with IFC drawings and meet cable separation requirements. Min Cover - HV: 1000mm - VicTrack: 650mm - Signalling: 800mm - LV: 800mm - Electrolysis: 800mm - SCADA: 800mm - MTM Comms: 600mm - 800mm below water coarses (stab sand encasement) - 1200mm Under VicRoads Roads & top of Rail - 900mm below council roads
52109e8f-9d0e-589f-8091-e91f4fc75f29 | note | Method - Measure, Visual
97cb5454-4ebc-54df-abcf-d5e494d0084f | note | Frequency - Each lot
e9b3c849-24ff-5da9-926a-8406ada3e9db | note | Category - IP
748bfda5-fef7-5f7c-a2fe-4a11dea5395d | note | Responsibility - SE/Site Supervisor
9c7f27fb-4453-52c9-8360-78a13731a27d | note | Verifying Documents - This ITP
| checkpoint | 5.5 - Separation of Services
bf75eb71-d0c9-5f1c-8061-5fbc9cedbc2f | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 L1-CHE-STD-077 IFC Drawings
47d107ae-3f46-54c1-a688-c821d3de20e3 | note | Acceptance Criteria - Separation of services - HV: Min. seperation distance between HV conduits at least 50mm - VicTrack: fiber 300mm from HV - Utility: 300mm to utilities - Rail: When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
9271bbb6-803d-5e26-bdc2-3a021bb59326 | note | Method - Measure, Visual
b820c892-0aab-589d-a39f-3cb44fd00e65 | note | Frequency - Each lot
ad4a7b47-e6ab-5b59-bc84-3cdf7ec1b622 | note | Category - IP
b4749dd0-3fc0-5b99-9d94-f408dff65d72 | note | Responsibility - SE/Site Supervisor
5eb73bd7-ca90-5d00-8875-d513ba020e2e | note | Verifying Documents - This ITP
| checkpoint | 5.6 - Joints
be6757fb-0a1f-5b38-81c1-de267131a034 | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
ab06d936-00cd-5449-9514-8c47754b54dd | note | Acceptance Criteria - All conduit joints shall be made by utilising the spigot and socket ends. Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer. The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer. Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
9e99e3dd-4735-531d-ba78-3354093d1c2e | note | Method - Visual
5ab51977-7faf-5117-825d-0c58294707c5 | note | Frequency - Each Joint in each trench
1bb473e9-4570-53a2-866f-a867909b3e28 | note | Category - IP
a99fb1e4-d449-5582-918f-6ae36fcd2d7c | note | Responsibility - SE/Site Supervisor
8b4e2294-bed6-57b4-b92a-58b401ca99a9 | note | Verifying Documents - This ITP
| checkpoint | 5.7 - Conduit Inspection
ced848d7-c95c-57d6-a01b-af82f8c1deed | note | Reference - L1-CHE-STD-070 16
8cfdbd39-e3a6-5921-af8a-c517ce021eb9 | note | Acceptance Criteria - Provision shall be made for inspection of cable routes by NA, MTM/VicTrack representatives prior to backfilling.
1ba591ac-2b8c-5e28-b8b4-522b06af1aa9 | note | Method - Visual
68d52625-82e0-572e-968b-cbd969d7a9ce | note | Frequency - Each lot
1daccdff-ce36-51a2-82d4-821f5796a3a1 | note | Category - HP*
1b796cec-32f5-5db6-9ce7-a0fe75e55267 | note | Responsibility - SE/PE MTM / VicTrack Rep.
196fd312-0ab9-5d12-a924-b8e6ab16735d | note | Verifying Documents - This Itp
| checkpoint | 5.8 - Bedding Sand Installation
6439821d-3b0a-539e-a5bd-a29205128f05 | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 CL13.1 IFC Drawings
72a7b0e5-1a18-5401-b9ab-1f968be75fcc | note | Acceptance Criteria - Bedding sand/crusher dust extends 50mm past edge of conduits. Bedding sand/crusher dust extends 100mm above conduits. Attach Delivery Dockets
661712aa-8df0-5490-818b-e209e90f1993 | note | Method - Visual
eecd0b27-272b-5097-9354-1ed3696afb05 | note | Frequency - Each lot
a4985578-d821-5d17-b35e-f3ce1478f9e4 | note | Category - IP
daac82f3-f1fb-5e29-b525-218b85b0082f | note | Responsibility - SE/Site Supervisor
5abb78f0-df4a-5bb6-9158-a11045bf9abb | note | Verifying Documents - This ITP
| checkpoint | 5.9 - Marker Tape
2ee9f90e-4145-5378-a563-2f07150328eb | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-SPE-070 Cl10.3.3
ea796636-5a11-508f-bc19-296cc487ec72 | note | Acceptance Criteria - Warning Tape installed a min. 300mm above top conduit or a min. 300mm above HV protection barrers. Tape to be one continuous length. VicTrack to inspect the Marker Tape placement..
75fcfd03-06b3-5a50-bbaf-7f81adb1f4e8 | note | Method - Visual
6ca8df7e-7644-5467-bccd-bc1d15389b7c | note | Frequency - Each lot
6ec070f3-d5b1-5108-970a-408932a29d3a | note | Category - HP*
c52de600-d7ed-5fcf-bb40-0c1b9eb6736b | note | Responsibility - SE/PE MTM / VicTrack Rep
c9e61785-68a2-541a-8140-f35aa48d2b15 | note | Verifying Documents - This ITP
| checkpoint | 5.1 - Backfill Installation for Conduits
1215f506-abf1-5139-9ca9-ede5e01cf9be | note | Reference - IFC Drawings L1-CHE-STD-043 clauses 6.15 and 6.16
edc87b66-8158-5c51-bc1f-d5d8c7bd32d3 | note | Acceptance Criteria - Backfill per trench profile - 150mm layers of 3% stabe sand - conduits under water ways to have 800mm cover from base of water way and backfilled with 3% stab sand
2f4d802d-425e-5859-a56e-297e22e71eb5 | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement
e9f9cb0a-8098-509d-8a1d-82263a9db34b | note | Trenches under road pavement - backfill to be same material as the road formation material.
8451879b-4f26-5339-9b7f-c910670d5e39 | note | Trenches immediately adjacent to footing shall be 3% stab sand. To be thoroughly placed to fill all voids without placing undue strain on or cause displacement of conduits
3f000d7c-733d-58b8-b372-7630f7aa04ac | note | When conduits are within 2.1m of edge of sleeper they must be encased in stab sand or cover is to be increase to 1.2m
54fab800-c369-5e22-89c9-fe84dd44a732 | note | VicTrack to be notified and witness the first layer of backfilling.
9a1821d5-508f-5050-a919-8bfaa59c1665 | note | Attached Delivery Dockets
45f12870-344a-54de-a597-8347f0d98f16 | note | Method - Visual
7f6780f7-4556-57aa-a027-dcfe4158bfbb | note | Frequency - Each lot
e054a422-473a-57dc-a243-abe0613a5c31 | note | Category - HP*
4f7acf9a-7389-58b8-98cd-17c679e45b16 | note | Responsibility - SE/PE MTM / VicTrack Rep
5160af98-1cdf-5927-8ca9-e8874b0522d9 | note | Verifying Documents - This ITP
| checkpoint | 5.11 - Signalling Pits LV Pits Electrolysis Pits SCADA Pits MTM Comms Pits
6bec5f74-c885-5f3d-aef2-e757cee5278a | note | Reference - L1-CHE-STD-043 Cl7.14.o, Cl7.14.g
1d8a676b-ac6e-5a5b-a758-fda8f59c4dd3 | note | Acceptance Criteria - - intervals no greater than 400m (electrolysis 190m) - 3m from rail - Access Roads, Class D lids - Footpaths and non traffiacl areas, Class C Lids
ca60609a-f573-574a-a8b1-e26df6cd0dd8 | note | Method - Visual, Measure
19aea829-8f98-5e76-b018-1988f0372fa2 | note | Frequency - Each Pit
ee60dfc8-7418-50a8-9648-c5076a7b8666 | note | Category - IP
a44e682f-ab1a-5488-a3f1-6c8450159698 | note | Responsibility - SE/Site Supervisor
215f8f04-4b82-5607-a92e-f2a0b83aa21b | note | Verifying Documents - This ITP
| checkpoint | 5.12 - Additional Considerations
21d3f3c6-1ed6-5144-b0ba-f8a1d3d68635 | note | Reference - IFC Drawings
ef0651f6-25f8-569f-b27e-c92a1eae2f6b | note | Acceptance Criteria - Access tracks to pits Safe access and egress (i.e. lid doesn't open up with workers back to the rail) Hand rail & retaining wall installed as required
6bfe9811-c054-5aae-a9a0-6371e1d481a8 | note | Method - Viual
3ca3f387-87ee-5d3a-8b58-96f53179df75 | note | Frequency - Each Pit
45dea665-6bcd-56d4-bd84-7466e81e0a53 | note | Category - IP
2064a6ac-9ee8-59bb-906f-188136bbb6d8 | note | Responsibility - SE/Site Supervisor
e285c370-3a67-5266-8817-540bf5059bf1 | note | Verifying Documents - This ITP
| checkpoint | 5.13 - Bedding for Pit Installation
1d1acdf6-c1f3-5b02-abc9-9a446c743353 | note | Reference - L1-CHE-STD-070 Cl 7.21.u L1-CHE-STD-043
82b8bb32-922b-5bbc-88d2-78360c8b0c88 | note | Acceptance Criteria - 150mm of crushed rock under pit extending 500mm past the pit Drainage arrangements shall be provided at the base of each pit. Attach Delivery Dockets
b456a94d-3797-5db3-af27-601c479058aa | note | Method - Viual, Measure
2f97c633-239a-50c2-9837-9ca78c3d262f | note | Frequency - Each Pit
5812cc8f-bc37-57b2-a63d-3ba306b406e2 | note | Category - IP
dfac8c14-7629-5348-af3d-be469b668120 | note | Responsibility - SE/Site Supervisor
d6594ec0-47f7-52c2-b28c-e671c275430f | note | Verifying Documents - This ITP
| checkpoint | 5.14 - Pit Orientation
d21be06d-2f50-5a3c-96cd-1744f3e3b54a | note | Reference - IFC Drawings
5dbffe02-ed8c-5dab-afa0-9e70abbb177a | note | Acceptance Criteria - Pit to be parallel to track and parallel to conduit route.
c53d0e23-54b9-5807-88f7-a62027ffd390 | note | Method - Viual
623b01cb-b4be-50a1-8531-9a3d84396ccf | note | Frequency - Each Pit
7612ded7-bb59-51c0-960b-c314d06053af | note | Category - IP
2b960379-9c78-5540-8fe2-3df45f6b04fe | note | Responsibility - SE/Site Supervisor
a46448a1-6778-5d6d-9404-d45a2483a7d3 | note | Verifying Documents - This ITP
| checkpoint | 5.15 - Pit Installation
31e183c5-69bf-5835-9bb1-23dc245d9fbf | note | Reference - IFC Drawings
7cf89215-7515-5610-930e-4054b39d807c | note | Acceptance Criteria - Pit installed to design specifications Pit chamber floor to be 100mm lower than the underside of the lowest conduit.
15dd1e46-b3fd-50cf-8881-0493526c6c5e | note | Method - Viual
d83f4381-0d7a-5b64-9c97-cc3fa783f34e | note | Frequency - Each Pit
578f0d3b-e5ba-50f4-8103-9dc9021b71e3 | note | Category - IP
b8b56d36-719f-5a65-bcf0-b81c14c1854e | note | Responsibility - SE/Site Supervisor
73f98bc9-2259-5b5c-b0a9-54fc79838d1b | note | Verifying Documents - This ITP
| checkpoint | 5.16 - Conduit Entry onto Pits
01c846da-35b1-5346-9efa-76909fbe342e | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
75a71957-ec19-5c32-86dc-6b1715adbcf9 | note | Acceptance Criteria - Lowest conduit 100mm from the pit chamber floor.
f4f05fb6-29b3-5e3d-b7c3-42e4a26eb8e1 | note | Method - Visual, Measure
2c1ab7d3-10b2-5373-b4b2-cc9f308ba35e | note | Frequency - Each Pit
e9039d61-8f84-5fb3-b948-5c6194ea4d63 | note | Category - IP
c55852c7-d1f6-5156-af38-34425ce3e753 | note | Responsibility - SE/Site Supervisor
e9e5cbe1-12f3-5a39-9176-8eb00ccca1df | note | Verifying Documents - This ITP
| checkpoint | 5.17 - Tracer Wire
b6d86eda-a4aa-5ff2-80a3-c9911c34d790 | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
148a025a-d9c4-51c1-a8c7-e4eb959ed6a9 | note | Acceptance Criteria - Warrning tracer wire for Vic Track routes to be drilled into pits and crimped off. If tracer wire broken needs to Crimped
d9c50d8a-4e2e-50fd-b41d-8102437f9dcf | note | Method - Visual
0bb1ed8d-8bf8-5c0b-a8d5-cf8c76951063 | note | Frequency - Each VicTrack Pit
a2f69fb4-9fb3-5a72-820e-1e3bc3219a2c | note | Category - HP*
8bed12df-4265-5e8c-958f-47230c7d80d8 | note | Responsibility - SE/PE, MTM / Vic Track Rep
2d564c82-26ea-591b-93ce-a5a56d34cbc6 | note | Verifying Documents - This ITP
| checkpoint | 5.18 - Spigots and Bell Mouths
3a5ed17b-1292-5ac2-8c83-1874ac823b70 | note | Reference - L1-CHE-SPE-070_9.3.4
67b40699-8e04-5c49-af5c-b199ecd02ee4 | note | Acceptance Criteria - All conduit ends in pits are to be correctly fitted with spigots to ensure that there are no sharp edges on the conduit; they are to be mounted flush with the pit wall and not touching any other spigots. HV Conduit entering the pit shall extend a minimum of 150mm beyond the edge of the excavation and be fitted with Bell Mouths.
5075ed70-a410-58a4-bd81-dd465bc9ed00 | note | Method - Visual, Measure
f95af92d-d40a-5e40-9ac9-f4e8e6093ffb | note | Frequency - Each Pit
cf326f79-269a-57ea-af0d-ffcf1b042d13 | note | Category - IP
019d64f4-e77f-5b39-a911-33f5d28a6330 | note | Responsibility - SE/Site Supervisor
7a71d65f-2062-5643-ac67-256b9393309b | note | Verifying Documents - This ITP
| checkpoint | 5.19 - Draw Ropes
4fddd25a-2e50-5faa-8dac-60f5122ab73f | note | Reference - VRIOGS 012.2.1
ae2a31d0-adb9-5f0f-b602-bd1484ba3aef | note | Acceptance Criteria - The draw wire shall be continuous for the complete length of the conduit run. The draw wire shall have a minimum of 2 metres of slack within every pit.
f0295b7f-2df6-5b71-b42e-a608abd1f9c5 | note | Method - Visual
bb04d2e8-e4f3-50f1-89a5-e65002b50f04 | note | Frequency - Each Pit
b6ddd768-834b-55d9-92af-1c61bff578fd | note | Category - IP
fbeb27cc-01b2-58a7-97ed-2e158416fb60 | note | Responsibility - SE/Site Supervisor
385a5488-fb42-52ac-9085-d01bcd3ee125 | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Backfill and Compaction Testing (if applicable) arouns Pits
f34712a4-4629-51ca-951a-4ef63e31ab8d | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
b43e99b3-7e22-5bec-9f96-045452c9fe68 | note | Acceptance Criteria - Backfill used around pit & pit lid to achieve 95% standard compaction in layers no more than 150mm layers
86d7362b-9e72-5c52-8af6-60da91022eb0 | note | Sand within sand pits to be compacted in layers no more than 250mm layers
25af188a-d434-5389-a3cf-8b1598a754af | note | Backfill shall be compacted and level with the collar and surrounds for Trafficable Pits.
4dd85bb9-4962-5a69-b7e0-5e19baedd459 | note | Attach Test Report
84aadcfa-8cab-5d77-ab61-9ff66d6cd181 | note | Method - Document Review, Visual
c17f066a-ccce-592b-8623-bee914e7a491 | note | Frequency - Each Pit
157733a2-96ba-5c65-835d-a04bd0d385fd | note | Category - IP
c689da68-6299-5651-a09e-df7799513497 | note | Responsibility - SE/Site Supervisor
adfc0dee-98df-51e0-ae47-9033a21f1a3c | note | Verifying Documents - This ITP
| checkpoint | 5.21 - Spare Conduits
6aa8e623-4824-5e92-b800-03b855ff89db | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
d1b025a1-af11-529b-aac2-f516bab063ab | note | Acceptance Criteria - Spare conduits to be sealed and to be included on survey report.
f760e199-67d3-509c-bff5-2dc9c4feab0d | note | Method - Visual
8e47d88a-0574-5c79-a413-4ebd4fed19da | note | Frequency - Each Pit
572a128a-e120-52e5-aba6-88b37b930a43 | note | Category - IP
e9aad2e9-9405-5ba8-8e26-5704716c8a71 | note | Responsibility - SE/Site Supervisor
3332dde4-4bb0-58df-a2be-a883cc5ca7cb | note | Verifying Documents - This ITP
| checkpoint | 5.22 - Pit Lables
fcaeb923-984d-59cc-a6f5-2bf1352b80de | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
1886d953-0a8c-573b-ad19-bdff48bad2f1 | note | Acceptance Criteria - Pit labels Brass Label (30mm x 150mm) - HV: DANGER - Railway High Voltage - VicTrack: Victrack Comms - Signalling: Rail Sign Comms - LV Pits: Electrical - Electrolysis: Electrolysis - SCADA: Rail Sign Comms - MTM Comms: Rail Sign Comms
be068c4a-fdbc-5cb7-b4b5-83353c698c47 | note | Method - Visual
c6b04755-352c-5fd0-8725-f6ac82c7dad4 | note | Frequency - Each Pit Lid
cb3e1c0d-4ea6-5bf5-bdbe-beb4d532712f | note | Category - IP
62faa399-ecc6-5637-80af-9a98d828830c | note | Responsibility - SE/Site Supervisor
78a35a19-dfe2-5eb3-b383-49434e56f93e | note | Verifying Documents - This ITP
| checkpoint | 5.23 - Pit Numbers
00f40897-f49f-506b-ac7c-dceaf55700e1 | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
1850fa58-26b6-5e26-931f-b212a4505035 | note | Acceptance Criteria - Pit Number Brass Label (30mm x 150mm) - HV (22kVV Feeders): ###HV - DC (HV Feeders for OHLE): ###DC - VicTrack: ###C - Signalling LV: ###SL - Signalling HV (2.2 or 3.3kv): ###SH - LV Pits: ###L - Electrolysis: ###E - SCADA: ###MS - MTM Comms: ###M
4136458b-7750-5dda-859e-4a4feafd0a35 | note | Method - Visual
f5e0ea52-3a68-5ff6-86f6-bff2fa17e015 | note | Frequency - Each Pit Lid
3c18a722-73be-53f3-baff-d282f401efad | note | Category - IP
2e4d0544-f8ae-5adc-a066-ce6e313da7fe | note | Responsibility - SE/Site Supervisor
922a44a0-bac8-5c84-9bd9-befc1fc18d32 | note | Verifying Documents - This ITP
| checkpoint | 5.24 - Cable Route Markers
76144e2c-9d32-56bb-b798-72a0c14e63e9 | note | Reference - L1-CHE-SPE-070_13.2 STD_E0169 and STD_E0170 AS 4799 STD G0003 and STD G0004
851593a3-d4bf-529e-9865-4432b44abf58 | note | Acceptance Criteria - Cable Route Markers - points entering & leaving the rail corridor - no greater than 100m spacing - Change of direction (more than 5 degrees) - White posts with marker plates for conduit runs
a2c4cced-3ec8-5cdb-a5df-2593006d3056 | note | Method - Visual
dde5e227-af25-5233-8a21-81ea915d0507 | note | Frequency - Per Cable Route
77140785-815c-5d0a-a7c5-1abfc2b839ae | note | Category - IP
2ec1825a-3131-5a94-92a6-13b1318521ea | note | Responsibility - SE/Site Supervisor
92464743-752e-5dd0-9a9f-2083d2d62077 | note | Verifying Documents - This ITP
| checkpoint | 5.25 - Cable Pulling
1494b263-e790-5ad5-a651-456fc0af211e | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
c9535c07-e04b-581e-8634-9d1d88708e1c | note | Acceptance Criteria - Cable pulling to be witnessed by MTM/Vic Track and to be signed off.
bbdeacc4-7dd7-56e5-9eb7-000f6bd60a5b | note | Method - Visual
ce0a57de-9675-5e21-9b32-15812b6505eb | note | Frequency - Per Cable
dba4d3f2-a7ce-5cd6-9626-8be6b9aa0999 | note | Category - HP*
474ee7e6-7362-5d2c-b506-07fe3c4b24c1 | note | Responsibility - PE, MTM/VicTrack Rep
bd760feb-58ca-5224-99e0-eb3055eeca9f | note | Verifying Documents - This ITP
| checkpoint | 5.26 - Cable Labels
9ef4c9a8-fa9f-5704-9850-6bf884198749 | note | Reference - L1-CHE-SPE-070 Section 13.3
efad579a-3661-5e1f-b9d1-144f6e4286bb | note | Acceptance Criteria - All installed High Voltage Cables shall be legibly and indelibly marked with an appropriate identifying label at each end of the cable, and at any cable joints. The label shall state the destination points of the cable and the name of the cable relevant to appropriate drawings
db7184c0-91c8-523c-8a5e-1b918cde877d | note | Method - Visual
bf02e5a2-0b10-58bf-9b89-39a34dcdfc08 | note | Frequency - Per Cable
accb6718-bf60-554a-be21-ca1362f3fe60 | note | Category - HP*
74044936-4613-5e6d-902a-ac8db4105c17 | note | Responsibility - PE, MTM/VicTrack Rep
9b40c73c-5ec2-5c4c-a5c6-86fe8b7bf6a4 | note | Verifying Documents - This ITP
| checkpoint | 5.27 - Cable Joints
47dcd337-e290-5aba-a232-d5866aaa4a1b | note | Reference - L1-CHE-SPE-070 L1-CHE-STD-043 L1-CHE-STD-070 IFC Drawings
f4979caf-7a3d-578f-9e9b-c4f8f47ec52a | note | Acceptance Criteria - Cable joints are installed correctly, with sufficient fault loops lengths & supported correctly in pits.
28ce7dd7-acdc-5a80-bebb-da227bb23e0a | note | Method - Visual
6b0e7a25-6a73-5a31-8e4c-b58b98dc4f48 | note | Frequency - Per Joint / Termination
fdc4d8a5-c058-5414-bb21-5d1981be273c | note | Category - HP*
82a72261-7740-52f9-91fc-33b9d728b414 | note | Responsibility - PE, MTM/VicTrack Rep
d8d9b669-8174-5dc3-9e64-fcfd35b05734 | note | Verifying Documents - This ITP
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
02106fe5-d566-5b85-98cd-a1dcc18d12dc | note | Reference - IFC Drwings L1-CHE-SPE-070 Section 13.1
d7ae121c-bd83-5853-a896-8374bb78c956 | note | Acceptance Criteria - Survey report to include but not limited to: - Cable joint locations. - Cable pit locations (Corners) - Pit dimensions & pit lid type - Under line crossings - Under road crossings - Changes of direction - Spare Conduits - Conduits labelled as per trench profile - every 10m - Other significant points of the cable route Attached Survey Report
94afee7e-64b6-5e7a-ba07-69b0937eda7f | note | Method - Document Review
b59d4a09-0d06-5844-9d5f-19485cfeb6e3 | note | Frequency - Each Lot
9dd4d079-ae23-5898-9c6e-353133039da1 | note | Category - IP
f80025b6-b905-5028-8249-9419356af0af | note | Responsibility - SE/PE
4a7d1749-f277-5aee-9c95-df47d4bf8421 | note | Verifying Documents - This ITP
| checkpoint | 6.2 - Handover Check
36959fc4-1351-5557-b4ac-8b7bd36e550b | note | Reference - IFC Drawings
a256166c-16b0-57a8-9d36-2959eeeb1411 | note | Acceptance Criteria - Handover check completed for Testing and Commisioning. Attach MTM/Vic Track Check Sheet (Signed-off)
4ea092cb-cee5-5635-b6f3-8a4413911cf4 | note | Method - Document Review
91226f36-24e5-5000-bddc-573f2454c21c | note | Frequency - Each Lot
9f42d629-13b9-58ae-a16f-cc418daa4139 | note | Category - HP*
243e7650-8bb6-54a2-b774-b0d45203c161 | note | Responsibility - PE, MTM/VicTrack Rep
341268b9-7221-56d7-afdb-66a4f3420b38 | note | Verifying Documents - This ITP
| checkpoint | 6.3 - Testing and Commissioning
4761b513-130e-54c7-be0c-2eac06929c23 | note | Reference - IFC Drawings
2bc7534d-a4bd-50e4-8d0e-e0e47e35e524 | note | Acceptance Criteria - Testing and Comminsiong to be completed Attach Testing and Comminsiong Report
9e155767-af8b-5295-b8d7-eceb90ee37af | note | Method - Document Review
b0867c87-652a-5a61-80c5-246fd20e093d | note | Frequency - Each Lot
8c71499c-15cb-59a8-9382-08808b0e21a1 | note | Category - HP*
bde653dd-1100-54ed-a88d-9175c9f8c3e9 | note | Responsibility - PE, MTM/VicTrack Rep
05f4da77-ea4c-5ef3-9f5d-635e089da9c7 | note | Verifying Documents - This ITP
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
1eb887ad-d2c9-5b90-8429-d24b8886d8e2 | note | Reference - MRPA Quality Management Plan
a0d218be-7278-5693-ae27-4f9a72d8e886 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
5f2b5974-f034-5c87-a837-8b055c750b1e | note | Method - Document Review
43d06d31-b21e-5d03-bf0b-3e9f529fc409 | note | Frequency - Once, prior to closure of this lot / element / Work area
02360c91-5c9a-518f-8db9-1f6e878a5bf0 | note | Category - HP*
79a480a4-be4e-5faa-bee5-924856dbef33 | note | Responsibility - SE/PE/SPE
3e71145f-3e36-5b89-aa40-a0a52e143f42 | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
3d519fc7-4d88-525b-b612-f6f6a689afdd | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f7ac4b8f-c17d-5d54-90cb-f484b7552b0f | textbox | Name:
39d9ba1c-8668-5096-b3be-284178b5df4e | textbox | Position:
e1aaeb98-a9ec-5db1-a282-6eec7ced6bbd | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-022-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS | itp | ITP-022-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS | 8b3c83f4-9492-4b34-974e-01c36b4b52b5
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
bb58bdfa-4120-5ad2-9c3c-ea12decbd2c2 | note | Document Title: ITP-CIV-BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS
508d739b-0428-5786-b6a2-2324fdf08065 | note | ITP Description: BRUNT-SUBGRADE PREPARATION-GROUND IMPROVEMENT WORKS
b5d53ed2-76de-5868-a604-34ba51eed229 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
af41fadf-b378-5b72-a6b3-d74b37e4a522 | note | Discipline (e.g. CIV/STR/RAIL): CIV
593917a4-bd96-5872-b49e-e55615ac2fb7 | note | Revision Number: 0
12864ece-51e4-531d-af25-dea021f6cec7 | note | Revision Date: 28/02/2023
3112fbd5-2352-524a-94fa-fa07363b3ef5 | note | ITP created by: Jason Lee
6a158d1b-553a-5d68-9e18-fa57deb033c2 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
3d626682-501e-5091-b26a-f911b15d9d6a | note | Reference - VicRoads Section 204
| checkpoint | 1.2 - Non Dependent
b6c9a89a-d9e2-5fce-87b6-3e9b8b4ce26a | note | Reference - VicRoads Section 173
| checkpoint | 1.3 - Non Dependent
c3f1a1c5-fdc2-51ad-8238-48311eade7dd | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Non Dependent
a7738ac7-d205-596c-96cf-be00246c449c | note | Reference - N/A
2b875782-377d-5ece-9af8-5ea21e0ec665 | note | Acceptance Criteria - N/A
7ea0bdeb-5398-55fb-9a93-3bbe5ffdb8cf | note | Method - N/A
fb5210b6-82a1-5837-8eef-3c8bb4b0c1b0 | note | Frequency - N/A
9faa04f5-ce46-5a4f-a43b-932195a47531 | note | Category - N/A
deef606b-1d3a-599b-b842-17cf36010848 | note | Responsibility - N/A
36478e73-3df7-5da8-81b5-90b82a60fb48 | note | Verifying Documents - N/A
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Non Dependent
226b6ad5-c3d5-55f9-9b5d-0b8ecc0ff33d | note | Reference - N/A
f1dba21b-817a-538c-b918-11d3af342ead | note | Acceptance Criteria - N/A
1db13ed2-e1e4-5a6b-beec-d0661d29ffdb | note | Method - N/A
6f232d0a-cc0c-5858-96b0-2d33c4b26ceb | note | Frequency - N/A
53730b95-bb82-5365-ba16-f1fd2e1dddcc | note | Category - N/A
8dd23b29-48ea-584d-b3b8-6bc292b82369 | note | Responsibility - N/A
b454a5f6-bd6c-58c3-9ef8-e5407d586335 | note | Verifying Documents - N/A
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Survey Set-Out
018e5cc8-29a6-5f1d-9e0f-acd0d655ba97 | note | Reference - IFC Drawings
a55e3b75-c1d1-5062-b183-47c5367293a1 | note | Acceptance Criteria - The Area of Excavation has been set out in accordance with the drawings.
621a270d-f986-56c8-8c7a-f4dd7c4409de | note | ○ IFC Drawings with work lots marked-up attachment required
5c346335-e18c-527c-a008-b713b518bab8 | note | Method - Verify
cc42a24e-630e-5a47-897d-61bde68a2e06 | note | Frequency - Prior to Commencement of Excavation
0abd0a1e-5de1-5772-b643-e84f9eb53569 | note | Category - IP
3c1c2e6e-5869-509b-8129-0117e8a1097d | note | Responsibility - SE/Surveyor
66be2e1f-4be7-5514-bb08-1611b690e9e3 | note | Verifying Documents - This ITP
| checkpoint | 4.2 - Material Classified as Silt
bfea54f4-2e2c-5b2e-8a32-c0dd4f9c854b | note | Reference - Section 204.04 (b) - Table 204.041
169a9f7c-a3de-5fd1-ac7d-c159df3b2294 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
92d28415-883f-5f38-9b97-325360126453 | note | ○ Type A Material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
93819912-66fa-5767-aa18-4f90c0bb46f5 | note | ○ Superintendent satisfied with stabilisation
ff91152b-af6c-555f-af68-110d95eec4db | note | ○ Attach: TeamBinder Material Approval Ref No.
31fc819c-6119-57ce-9277-e34836ccb198 | note | Method - Document Review
906bb5c9-ebc9-5f33-87b4-bf9854484eb0 | note | Frequency - Prior to Commencing
7f4f2d70-a8d5-5425-9193-6af766f21d83 | note | Category - HP
dddf4b23-986e-5a8f-8021-141969ec1b73 | note | Responsibility - Nominated Authority
2a302808-5e46-524e-b371-0dfa0ca6495b | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction Activities
| checkpoint | 5.1 - Subgrade Material Properties Inspection
38d53059-0d3c-5ceb-81ed-fe01858e15a2 | note | Reference - IFC Drawings
caf337eb-314d-527b-bb51-5f9b41e79ed4 | note | ○ Section 204.06 (c)
cbb97342-52a6-527c-9ed3-5ec5266c2f3a | note | ○ Section 204.06 (e)
452a6488-adee-53b5-846c-dd10e6662501 | note | Acceptance Criteria - Section 204.06 (c)
df98b1b1-fc91-5461-9667-1d8db9b9b69b | note | • Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04 and Table 204.041
1ba5b4ff-1574-5cc4-8e6f-a5f2b50eb04a | note | ○ Section 204.06 (e)
7e15d369-7f79-5238-a8eb-9cecfce0b782 | note | • In situ material within 400mm of cut floor level to be consistent with IFC Drawings
96eda9c3-e9f9-5b83-adb4-e86ec0695a0f | note | • Assigned CBR not less than Type A material and shall have swell less than 2.5%.
81cf8b92-ee12-5903-8bc1-7d78684ec20b | note | • If parameters are met, rip and re-compact to a depth of 150mm.
fbca6f52-1ed7-5f9f-81e1-843c862839be | note | • If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
0f901ee5-1773-5f9c-bf1e-ce694967d78f | note | ○ Attach: Laboratory testing Verification
a72ee641-a577-52fe-a643-d3d9578d7c9d | textbox | Type A fill Lot Number:
4b9201b6-36fb-5e5a-a028-8bc4d78bcb18 | note | Method - Verify - Document Review
ec28dde2-7951-5d6a-b88c-bbd6eb179f88 | note | Frequency - Each Lot
8095a172-4686-5ed0-91fc-f1070b6b5eb4 | note | Category - HP
003adcd5-59e8-53d9-9c13-838b275237d4 | note | Responsibility - Nominated Authority
39df3f2e-d91c-5bd3-ab63-bfe593ff9381 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Acceptance of Rock Subgrade (where applicable)
6a0a4cb7-ed15-5f7f-a7ed-f3782f3df3f9 | note | Reference - Section 204.06 (f)
32c27b42-5910-5dbc-aa8e-d16fa43a8b05 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
bd7faa9e-9b02-59dc-ad6b-55edaac511e7 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
430ad468-549a-541b-b591-73867db082c9 | note | Method - Site Inspection/Document Review
1c0c28d3-17c7-520a-a958-d9096327cef7 | note | Frequency - Prior Construction of the regulating layer
814a6aa6-f9ec-5740-b5f0-4f98c11cc1fd | note | Category - HP
26026df9-c2ec-54c7-93e1-5f32e7c22ed9 | note | Responsibility - Nominated Authority
835727b7-4b5b-58a8-9e7d-992e98687822 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Unsuitable Material
f4f939a8-f393-5b4a-87ce-3f91f2a81625 | note | Reference - Section 204.07 (d)
9e4c172b-77e8-5ebb-b943-db064194afb8 | note | Acceptance Criteria - Where unsuitable material is encountered, proposed in-situ treatment or extent of excavation must be submitted to the Superintendent for review.
1d38bc96-e3ff-576d-8874-d7cbdd9915b0 | note | Method - Visual Inspection
25e7240b-78bf-577a-8391-cab566c7e3f3 | note | Frequency - Each Lot
0f4f5aff-c9fa-5975-b1ef-4f0c0a23f6b7 | note | Category - HP
92b89906-ea5f-5c60-8190-4d26fd00f105 | note | Responsibility - PE/Nominated Authority
819efa65-3d19-57f1-9b4d-ea5bbc86b83f | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Groundwater
5f49dc32-5c38-53de-b78d-686e4249d762 | note | Reference - Section 204.06 (h)
2689c2cf-2c26-5fed-b881-9d5414ac1e95 | note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
068b5009-657d-51c7-841c-3490dee3a522 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
038e5479-ebe9-5d18-a38b-ce3e77e13873 | note | Method - Visual Inspection
111315cf-6439-5d73-aa4e-764b23decb2a | note | Frequency - Each Lot
ecc354eb-2a66-5887-8502-0a8439342048 | note | Category - HP
e23c5ebd-b4ad-521b-8b59-3c36178b8794 | note | Responsibility - SE/Nominated Authority
c00642c7-1e3a-563a-8027-bb5e1ca6f8b4 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Fill Construction
1f03cb93-5d27-583e-a28a-bf97b50b5c9d | note | Reference - IFC Drawings
104fe3d6-9103-5002-a637-f5fabee7bc99 | note | ○ Section 204.10 (b)
4a078569-e599-5359-8ced-eadc2f6b59b0 | note | ○ Section 204.11 (b)
b42272fe-cc6b-5252-a227-e59fa3c585e1 | note | Acceptance Criteria - No Fill to be commenced on prepared areas until area has been reviewed by the Superintendent.
3a692930-f7eb-51b7-a611-ccb8612d6c9f | note | ○ As per the notes in the IFC drawings, excavation is required until natural clay is exposed with a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement.
5917022e-0d86-5ecb-90d5-2373144b605f | note | ○ No Fill placed against or within 3m of a structure until the foundation for fill has been reviewed by the Superintendent.
0f9ed091-ec96-55c9-aaee-20e5f2587a6a | note | Method - Site Inspection
8e763716-9b72-5435-a6bc-4fac98f23801 | note | Frequency - Each Lot
ae9397c4-998b-5cb1-b503-7ca9cf83b026 | note | Category - HP
267df310-71a2-512a-830b-7f7cbf76bcfc | note | Responsibility - SE/Nominated Authority
92fa1a6c-5b73-506e-abf5-8737007b68e8 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Proof Roll
b7b3de7f-c4da-52c1-9382-a52720fe4077 | note | Reference - Section 173
1e261148-f865-57d2-8ba8-58c7659216ff | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
0724e991-95f6-54fd-b0b1-2adeca5f7775 | note | Method - Visual inspection
67f8df28-1dbc-50cf-9e74-7fe44e12a1cf | note | Frequency - Each lot
83f94572-fff0-57d8-8d11-c9fc4db9eff6 | note | Category - HP
eee07f6d-a388-5f5e-ab47-a2b5a361a1dd | note | Responsibility - SE/Nominated Authority
1c09f2a6-db38-533e-9e33-e2c68b2b6d2d | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 - Compaction Testing
df5b77a0-205c-535f-86ad-583915132b87 | note | Reference - Table 204.131 IFC Drawings
08c687c5-7744-5cdc-a8a4-b7dbd2c614b4 | note | Acceptance Criteria - As per IFC Drawings Notes:
ad4074fb-fe91-5507-b9d0-72a5e9dabf6c | note | 7. SCALE A MAY BE ASSUMED FOR THE PURPOSES OF ALL MATERIAL TESTING EXCEPT WHERE APPROVED BY THE DESIGNER
e86e0963-9c8a-5214-af39-37e9209bd344 | note | ○ Attach: Compaction Test Result:
be38ab00-07a4-53be-9616-1b7927119e5f | note | Method - Document Review
0434e82f-77bd-57dd-b7f6-e9c069b0a3c8 | note | Frequency - Each lot
8ac35dab-ad09-5e52-a380-6555a87447a8 | note | Category - IP
0a55771f-1676-563a-bf78-25a84d15a4ad | note | Responsibility - PE/SE
15dc585b-8005-57d7-b1de-c76f930f1091 | note | Verifying Documents - Test Records, Lot Register
| checkpoint | 5.8 - Post Compaction Material Property Testing
6dd0a750-e3de-50ed-b116-0b0fd3c96aa2 | note | Reference - Table 204,041
b6ed6fb1-6867-5088-bdd3-d4d4df254f36 | note | ○ Table 204.141
9626f4f7-1268-548e-a519-55828be10a97 | note | ○ Section 204.14 a) or b)
5c0132a3-d6f5-530c-9242-3fe96527f86e | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
7a8e1914-3e5a-504c-bf87-233f1722b1af | note | • CBR ≥ 8% and Swell ≤ 1%
79db980d-e003-55a7-8dc0-da11e82bafe2 | note | • Max Permeability = N/A
60d2f918-b20b-5cc4-b53c-9fc3e09fdbd9 | note | ○ Grading: 75.0mm 100%
acf7aea1-2dfd-584f-b7e0-f53fbc519a21 | note | • 37.5mm 50-100%
0bece197-1cf1-5cf6-90e5-330598b3fa17 | note | • 4.75mm 25-65%
d16f8f35-5d1a-52c7-8084-f66adf833546 | note | • 0.425mm 10-25%
439bc086-27ac-5be3-91f8-14af50b65ee5 | note | • 0.075mm <20%
1013d625-6deb-55eb-8574-239aba8df32d | note | • Max. PI x%Passing 0.425mm = 1000 , PI = <25
675286be-728e-5a6f-a529-189818654323 | note | ○ Scale A:
1b382757-34c3-585b-a3b0-442b32f3be6c | note | • CBR & Swell
1537e2df-ac62-55fe-b395-92bc2312f4df | note | Initial - 1 Lot Test to determine Assigned CBR and swell
b22a1f59-ff3f-549a-b53b-4eaf8926d2d3 | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
7e69a118-7821-5611-b49b-13cd4ccc8dc5 | note | • Max Permeability
7bc57646-1cea-52bf-b515-372f8371246a | note | Initial - 1 test per 2 lots
6daed1e1-351d-5fce-abd7-f2147ce0d7ba | note | Reduced - 1 test per 4 lots
2ee2489a-bee7-506f-a772-8685461cbe6b | note | • Grading:
3ef0f00a-5fec-50c2-9cdf-cd843030d934 | note | Initial - 1 test for each lot tested for compaction
a1025dc4-c69e-5479-b88c-ce212e5f3034 | note | Reduced - 1 test for every second lot tested for compaction
767436af-f0f5-5e18-b753-55a079ded349 | note | • Max. PI x%Passing 0.425mm & PI
aa203ed5-4213-515c-b840-7422511ae6d4 | note | Initial - 1 test per 2 lots
306aaa67-cef6-5af5-b2e8-578ccb8c8f2d | note | Reduced - 1 test per 4 lots
decadef9-4e0a-5a54-92fd-db2b75219a60 | note | ○ Scale B:
c5aef63b-4ddf-5276-af1f-c3362f7b4ec4 | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
c4f6a6fa-9f95-5a0c-a619-b84c35420bb1 | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
e2572cf0-3ed5-55ff-85bf-7d57df2c1241 | note | • Attach: Post compaction test results:
a7c9f43e-2ea4-5d44-ab5d-ed2736781de4 | note | Method - Review Document
52cf5482-7497-555c-bfd7-14ba9f84815f | note | Frequency - Refer to Section 204
01ae599e-c39d-5846-8724-b10d10c69097 | note | Category - IP
8bd04083-d02e-5cf6-98c3-1bce2c4c94dc | note | Responsibility - PE/SE
8d7ed096-5e5a-5783-90dc-684dfe99188b | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Survey Conformance
639b8b28-543c-5a27-b002-755cd2e8ecf5 | note | Reference - VicRoads 204.03 (f,g,h) Section 173.05
e5ff157e-2237-5b44-8390-35c8b81b1e44 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
f3d5ef07-7f2c-5bf8-b769-cde02820b7c4 | note | ○ Level tolerances (Scale A):
0884ddd0-741c-5694-812b-ac8f70444503 | note | • Range x = +5, -15mm
faadcbf9-43dc-5357-8437-46ab6ab892ae | note | • Max S = 12 mm
0c013f8b-feef-5679-9b0e-990f0b37fd17 | note | • 80 measurements per lot
40481a8b-e1e5-5a6a-9407-000f04948d79 | note | ○ Level tolerances (Scale B):
2feb8781-f69b-5180-932c-62ab1238c583 | note | • Range x = +5, -25mm
511be02c-b280-58c4-b46b-6acfee0a60ac | note | • Max S = 15 mm
dfb56a20-886a-53d6-a065-56a0621217bb | note | • 40 measurements per lot
64afcb48-f94d-5085-809c-19548db004b5 | note | ○ Level tolerances (Scale C):
73152944-e379-5e04-9380-41f83374d79a | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
b74359e9-e0eb-5556-b2c6-73bde0dd0ccf | note | Method - Review Document
0d7e4661-e80b-5ef1-8fef-aec9c991cbfd | note | Frequency - Each lot
2109a2b5-f4ba-59bb-b382-72552342dd15 | note | Category - SP
2609fa1c-81f7-5c11-b3d2-0f941e22ac35 | note | Responsibility - SE/Surveyor
f2e96422-a2be-5d03-992f-bfd98a94b8fc | note | Verifying Documents - Sign ITP, Attach Survey Report
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
fe91746c-aeb1-5262-b60c-88bf03bb401a | note | Reference - MRPA Quality Management Plan
bddcdcc2-d079-590b-b2da-96a3d38d68a0 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
aa6969ef-d785-5257-8608-95abac88d2d6 | note | Method - Document Review
2a33830a-62a8-50be-afac-8e1c994ac66d | note | Frequency - Once, prior to closure of this lot / element / Work area
a7de5295-c614-5b98-98ad-52aa5c30a428 | note | Category - HP*
67ce426b-ee5a-562b-838f-efd0828c8661 | note | Responsibility - SE/PE/SPE
a8651c65-cf7c-5725-b89c-5be35921a7b5 | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
5babc2b5-1b08-5d59-8e3f-4f2e2b2a3c5c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
830072d9-d6c7-5c42-a146-4234f092c816 | textbox | Name:
fc6d4cc6-0dd8-556d-92e0-651de3ef3960 | textbox | Position:
dc8ce6b4-b90f-5251-9bed-bd1cf6a71329 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-023-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS | itp | ITP-023-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS | 5135b347-e346-4d44-9786-99f7d9d757f4
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
608bc9b8-4d24-5d38-8891-0f38e64678cd | note | Document Title: ITP-CIV-BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS
ca96d36b-f70b-5d75-9dfc-0c053d3f6941 | note | ITP Description: BRUNT-TYPE A FILL -GROUND IMPROVEMENT WORKS
d5d90515-c32b-5b54-9eac-ae6999e7faff | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
1d058632-9d65-5d46-a8c0-ed7806381eb3 | note | Discipline (e.g. CIV/STR/RAIL): CIV
630b59b7-9ecc-5f2a-9596-bfe06562b01d | note | Revision Number: 0
16c94da3-ada3-5aa7-abac-e2ce93bc7022 | note | Revision Date: 28/02/2023
ada22881-16bb-5602-a5e6-d113b0220b9d | note | ITP created by: Jason Lee
c3c6a086-f2c2-54d0-bbe1-2d6db8bbe43d | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
f1eefa63-acc0-50ff-865e-5c16f1e0f582 | note | Reference - IFC Drawings
| checkpoint | 1.2 - Non Dependent
612f1174-30b4-5612-aeb7-d81e60576044 | note | Reference - VicRoads Section 173
| checkpoint | 1.3 - Non Dependent
524ad304-c04b-52be-a39a-14b9a87c27a5 | note | Reference - VicRoads Section 204
| checkpoint | 1.4 - Non Dependent
0af22688-0632-5ee9-8f07-ef2266c62230 | note | Reference - VicRoads Section 176
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
662aa7f2-7db1-5c30-892d-96a85fb0034f | note | Reference - Section 204.04 (b) Table 204.041
cb99b706-879c-5c38-92ed-049b18b487af | note | ○ IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848)
26292d2e-7cbe-5478-a8eb-9c4094f79088 | note | Acceptance Criteria - REPLACEMENT MATERIAL (Type A) TO MEET THE REQUIREMENTS IN TABLE Note 1 of IFC Drawing MRP-089-C-ACD-DRG-30-BFD-CBR-2848, AND OTHERWISE CONFORMING TO TYPE A FILL REQUIREMENTS IN ACCORDANCE WITH VICROADS STANDARD SPECIFICATION SECTION 204 and Table 204.041
77c9bd14-7c78-51fa-9999-3b3c0af52742 | note | ○ Table Note 1:
27763cf5-0239-54d4-82e2-893a6461fe7b | note | • Assigned CBR ≥ 8%
0833a489-aaa4-51ee-9719-7422165a6f2e | note | • Swell ≤ 1%
206a15ec-5238-5e3e-b046-9dc59d60c892 | note | ○ Grading:
40c3a798-a840-5651-bfcc-79340b36d7bd | note | • 75.0mm 100%
c7a19fc2-a40f-5f96-bbed-5ff9987ba560 | note | • 37.5mm 50-100%
b124536f-61a2-5f88-bde7-b29121257bd0 | note | • 4.75mm 25-65%
81338221-8a3e-50be-ac7a-f9513d04b1c7 | note | • 0.425mm 10-25%
9f51db48-6030-5079-99d6-981b3d45d887 | note | • 0.075mm <20%
2f6a3436-f7b3-5f46-a98b-62c2bea26721 | note | ○ Reference: Material approval in Teambinder
79dc5baf-6f17-5cbb-9b0c-4c00e4d8589e | note | Method - Document Review
a5159c8f-a6e0-5748-ac21-e1d17b5ee363 | note | Frequency - Once, for each material type
5a8fbc55-df51-5374-9124-06cfd6f2060e | note | Category - HP
a867cd67-abc0-542b-9c15-21eee7eddc1a | note | Responsibility - Nominated Authority
f569e136-de27-580c-b2d5-47d59bf1ccee | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - Pre-Commencement of Fill Works
20672cf2-b148-554d-9e41-b9d550ebfcd4 | note | Reference - Section 204.10 (b)
dfa63c4f-ec8a-50a4-b62f-2c3364993950 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
b869729f-5b23-57ca-a047-140552a47fbb | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
dec48db6-93a2-5fc1-bf08-c9f6997f9dae | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
78bd0182-29f5-5de2-a93a-fa176e139873 | note | ○ Reference: Subgrade Preparation Lot Number:
dc342577-ef9e-5a77-8724-2aed4bb852f6 | note | Method - Visual Inspection
a27a788f-bca9-5b39-bcbb-1cdfd15fb96c | note | Frequency - Prior to commencement of fill works
a293dc7a-0b23-517c-ac83-a1436db4899f | note | Category - HP
84d6b0c6-4420-51f3-9862-e3b5207c93d8 | note | Responsibility - Nominated Authority
e26964b3-5403-5470-88cf-092561b90469 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
aadb9fc0-f978-5096-b1a4-0975bed76e28 | note | Reference - IFC Drawings
5518dc15-e984-56ff-8278-1a49be38e302 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
2670b42c-d8d1-568d-afb2-69fb0d3ed441 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
83d41b36-e4cf-55cf-bbde-d22f0155c1f7 | note | Method - Visual Inspection
414b1747-20d9-5ae3-9d09-53d8015196a3 | note | Frequency - Each lot prior to commencement
bd350683-72de-59c0-bab1-afcba2bb3205 | note | Category - HP*
aa3b30c8-db19-517d-9fc2-cefa69f9569e | note | Responsibility - PE
9fe2964f-8c4a-54b5-97d1-b40b4a07d019 | note | Verifying Documents - This ITP
| checkpoint | 4.2 - Flora and Fauna
a8cbc41c-34bc-5d4b-913c-5874be114e1b | note | Reference - Section 176.I1 IFC Drawings
e6236db1-71e8-58a1-91fb-56df9e82eb8b | note | Acceptance Criteria - Prior to removing any vegetation, an on site inspection with the Superintendent and other relevant authorities to confirm, identify and mark trees, vegetation to be removed. Any removal shall be consistent with the IFC drawings and any relevant permits.
37ae1caf-20a7-5d59-8c20-e87747467047 | note | Method - Visual Inspection
3aa48337-2aa5-5050-b5c0-fa98dcd83301 | note | Frequency - Each lot prior to commencement
0364bfd1-ffb5-5acc-b75a-d6336a4406be | note | Category - HP*
e2945eda-97b0-553e-a092-504d712fdbc6 | note | Responsibility - PE
6ae818f6-c701-5f88-a3a5-954277965355 | note | Verifying Documents - This ITP
| section | 5. Type A Fill Activities
| checkpoint | 5.1 - Placing of Fill
c4a41537-a4d4-56d2-bc76-09bc427f8526 | note | Reference - Section 204.10 (d)
45f3d688-a979-5346-a288-fb0e37531436 | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
72ea836b-7949-52f2-98ac-7ae92a6b3c92 | note | Method - Visual Inspection
e5bcb441-730f-544e-ba12-55bec2a5c4d2 | note | Frequency - Each Lot
1dc3e577-b107-53a5-b80e-20b2f5a3c1d0 | note | Category - WP
e3cd2c60-f327-51b0-a657-92d2f89d585d | note | Responsibility - SE/Site Supervisor
f00c1138-0099-5cef-abb2-672acd8b7ab0 | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Fill at Structures
7f451446-f853-5a70-9fe8-417ac45973cc | note | Reference - Section 204.11 (b)
7361b002-7efc-5143-a005-b7df9573fab6 | note | Acceptance Criteria - No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
ce6570a7-085f-54c8-a1d9-24a5f3bb2558 | note | ○ In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
9e164658-5500-5c01-ab2c-14fa5c228ed0 | note | Method - Site Inspection
1a9b36fe-b4b7-5a25-a95a-9ca926688bcc | note | Frequency - Each Lot
875cf3bc-4045-5cb3-bf6a-1bf63d4d044e | note | Category - HP*
bfe5a610-ff57-5c15-84c9-537560c11aa7 | note | Responsibility - SE/Site Supervisor
16f6e1c4-3e7e-5bd1-b9c6-5e67268b223b | note | Verifying Documents - This ITP
| checkpoint | 5.3 - Test Roll
620bd7a1-e9bb-5e3a-8c73-c17586ef12df | note | Reference - Section 173.03, Section 204.12
2004b4de-5424-57c5-b0e9-12cb750bdba2 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
9bd95ebb-cf3e-5fa1-a3f4-fb95bc37d23f | note | ○ Superintendent to be present during all test rolling
6538ee20-03f9-52b3-81e2-eb7ccbb92091 | note | ○ Attach: Test/Proof Roll Checklist
53ea0f67-0b8a-58f7-abb9-3823e4677085 | note | Method - Visual Inspection
52ab74ff-f352-5348-844e-c4f07ec22c19 | note | Frequency - Each Lot/Layer
be77fb0f-18dd-56d0-b114-3b9671f717c4 | note | Category - HP
7666143b-ae7d-5d54-a9a6-7f5eb6f48052 | note | Responsibility - SE/Nominated Authority
ff195926-3b1e-5ba6-8357-2464e52c23b6 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Compaction Testing
faeb565e-f6ae-5af8-a557-e441ccc4deb2 | note | Reference - Table 204.131
25e4b16b-0a6a-5f78-b75d-b21c319d33ba | note | ○ Section 204.14 (c)
9cdfec8c-ca86-5e76-837f-59e15ffb51c1 | note | ○ Table 204.142
e152780f-3fc2-5164-a8b2-6002fb7c3d4a | note | Acceptance Criteria - Testing as per 204.13. Ensure testing is tracked and reports available.
ad898289-eb07-5c69-8a7d-4319064a2cfe | note | ○ Standard Compactive Effort
44d13e18-b539-5208-a1d4-3901a44a773c | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
f4b99e6f-6c17-518a-91a5-9d6475318bdf | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
fc734cb6-0011-51c3-b471-57850b9310ff | note | ○ Compaction and Moisture content
875662f0-242f-595c-9163-8d48162061c3 | note | • Scale A: Characteristic Density Ratio 99%.
2391f43f-c06c-5893-a738-7410071492f4 | note | • Scale B: Characteristic Density Ratio 98%.
f820ce71-ad7b-54e1-8794-bee85e69e046 | note | • Scale C: Mean Value of Density Ratio: 100%
fa31c371-2b6d-554a-a82e-f78d9f28d22d | note | ○ Lot size - the leser of one day's production or 4000sqm
792aba6b-4829-53f3-94b4-1e8a1d0674c0 | note | ○ ATTACH: COMPACTION TEST RESULTS
d2fb14fd-b45c-50d0-80a2-9150638b4530 | note | Method - Review Document
d6d94bd4-83b0-5d86-b81a-5cecb1615005 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work, subject to Superintendent satisfaction
9c2a2d56-1b91-5db3-9466-163ade3570b9 | note | Category - HP*
fba1206e-653e-5566-956f-cc16a83c2433 | note | Responsibility - SE/Site Supervisor
e009323b-d14b-5a75-91d8-e0b86c0650df | note | Verifying Documents - This ITP
| checkpoint | 5.5 - Preparation of final surface
251716ad-556a-5604-80a3-41477a4e9e79 | note | Reference - Section 204.15
1fd21efb-aeb7-5911-9327-9517d7058eb8 | note | ○ Section 204.03 (g)
f0f0eb05-e18a-56a5-a959-a7e6eeb83058 | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water.
3403c884-f1ad-55ae-b0ee-96a6c7f320ca | note | Method - Measure
1c1623ec-5542-5be9-8b8e-3b2b64ff7d5a | note | Frequency - Top layer
eea9d068-5397-55a8-b48a-5ef964dfe62b | note | Category - IP
738ed636-a84e-545b-9ef2-8317aeb69139 | note | Responsibility - SE/Site Supervisor
40827042-8ed6-59dc-bd94-7e8e0e7e5833 | note | Verifying Documents - This ITP
| checkpoint | 5.6 - Post Compaction Material Property Testing
35d2043e-68f2-5d1f-9b80-8d3d76031471 | note | Reference - Table 204,041
07dfe39a-22e7-50cf-b5ea-2437feaea6c8 | note | ○ Table 204.141
ba5e4bc7-792b-55ca-9c95-e3fb734af997 | note | ○ Section 204.14 (a) or b)
900215c1-b1db-5386-9dde-75b281d00add | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
59e29ec4-3f6e-56e1-92e6-accf71e35fed | note | • CBR ≥ 8% and Swell ≤ 1%
7e913156-e812-5f6a-a648-aa3a0b636ee5 | note | • Max Permeability = N/A
cc1fb4d7-aa21-581a-904c-8ccd15458439 | note | • Grading: 75.0mm 100%
7976b4cb-f2d8-502a-9e16-937c44e234e4 | note | • 4.75mm 25-65%
cdef815b-ea7a-5d8b-ae1b-d261b43537b6 | note | • 0.075mm <20%
3de0bba3-1ea4-54c6-9e05-696be575488b | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
f76847da-0b81-57d2-bd8e-49d2e4491dd9 | note | ○ Scale A:
1a13a0f1-f904-5a85-8a65-a0a2a038ad9b | note | ○ CBR & Swell
3c21d6ca-bf9e-5d90-a121-e9ca10878a3c | note | • Initial - 1 Lot Test to determine Assigned CBR and swell
cd2e2fe7-7ccd-5e60-9d0c-00cc8cf66c08 | note | • Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
481135cc-60dd-5872-9e01-f954e32d6f56 | note | ○ Max Permeability
1f09b526-4420-5dec-80aa-3f78af5e72e4 | note | • Initial - 1 test per 2 lots
fd8d4ee3-01f7-50b8-ac65-8ad0c068d91b | note | • Reduced - 1 test per 4 lots
3ac60a97-4d57-5e1a-a8d7-6de229565c19 | note | ○ Grading:
c9d24a67-22af-5689-8e82-d974d897248a | note | • Initial - 1 test for each lot tested for compaction
84060d02-40e7-51ee-94d4-1f437af69935 | note | • Reduced - 1 test for every second lot tested for compaction
34965bc1-9a79-5e6c-bf2b-fa9dc07b8646 | note | • Max. PI x%Passing 0.425mm & PI
08d235df-ca38-509f-a09b-166eb1562d48 | note | • Initial - 1 test per 2 lots
88914396-0a83-5f35-95b1-3966815ac428 | note | • Reduced - 1 test per 4 lots
de950fa9-b5cb-5c76-b503-e95af9d5b5a1 | note | ○ Scale B:
11e71d21-719e-508a-b779-156f8a9188e1 | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
4122729a-c9c3-5d67-859d-bc5cdca6175b | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
5d99cb0a-b9f4-50ae-91de-69075112b4ea | note | ○ Attach: Post compaction test results:
da2c7bb3-7cc8-50fa-992e-6707c51c2dec | note | Method - Review Document
61470146-bada-577d-9046-65b6a00aa958 | note | Frequency - Refer to Section 204
f0ab3b5e-405a-5881-adc7-418257da8073 | note | Category - IP
3ef2fea3-2692-5e20-b1df-addb2a5ff1c5 | note | Responsibility - SE/Site Supervisor
15009d7d-cb2a-586c-a6e4-14d883edf419 | note | Verifying Documents - This ITP
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Survey Conformance - Asbuilt
e082acaa-6cd9-5345-a688-6de9434d74c6 | note | Reference - VicRoads Section 204.03 (f), (g) and (h)
30b209ef-9006-5dc1-aa09-7e71570bcc8a | note | ○ Table 204.031
cd9819cc-87f4-5388-931d-2823de73c69f | note | ○ Section 173.05
eaddbce7-087a-55f7-811c-95312be9e158 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
442b513f-9ed4-52ad-b5d5-c5a0c3b4aa59 | note | ○ Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173. The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
b00063e8-451a-5905-9e77-c542244140d1 | note | ○ Level tolerances Scale A:
0ab770e6-5875-5f7c-a230-bfc3830076fb | note | • Range x = +5, -15mm
95db91dd-c242-59a4-ad07-29cd781c0265 | note | • Max S = 12 mm
239d3a92-883a-5fff-9bbe-5f3233620493 | note | • 80 measurements per lot
fab6e7fd-b117-5a68-9c31-883c29054caf | note | ○ Level tolerances Scale B:
5e4e9774-2bb7-5f4a-93d9-9164ee44059b | note | • Range x = +5, -25mm
05802788-4ac1-5687-86a8-8a268b0b205f | note | • Max S = 15 mm
9a7630e3-2be6-5c2e-a43e-549a3c49f2cd | note | • 40 measurements per lot
9a23cfa8-58c8-57f1-8d6c-4e1aab48f6b0 | note | ○ Level tolerances Scale C:
bd4da008-c09a-58aa-ba96-74c1795c1445 | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
7915a4a1-9956-560f-b72e-b76ae43bdbb3 | note | ○ Attach: As-built conformance report/data
6024c497-8ee1-550c-9a18-824f7b1af4a1 | note | Method - Document Review
0f19a731-9c97-5d5d-b2c4-5722d2bf2d2c | note | Frequency - Top of Type A
b8b8e46d-4941-5b4e-9a34-3ca779fa529e | note | Category - HP*
c4e1f084-99be-5d52-968f-fde6c98b4cd6 | note | Responsibility - Surveyor, SE/PE/SPE
689c4a8f-2b51-5c9c-889e-cc11a2861cdd | note | Verifying Documents - This ITP
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
fe93b47b-7914-53da-8b48-f6a3d7b2761b | note | Reference - MRPA Quality Management Plan
8dabd54d-cbb4-5b83-b3f7-ff5aefa39ada | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
12db578d-b9be-5d13-bfa2-6983cea9d369 | note | Method - Document Review
5a0776d9-7ff8-58de-ada5-b823c8839c33 | note | Frequency - Once, prior to closure of this lot / element / Work area
2fefecb6-294c-568a-aec2-dc808131db6e | note | Category - HP*
8db3229c-58b3-5cf0-b61b-834d9802fb6e | note | Responsibility - SE/PE/SPE
8a8a1eea-b439-5085-998e-62e51e7e815c | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
f565b218-b6c5-5f08-881d-d5be63756a37 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
37664645-15e0-5c92-bbc3-ab90d8a0574f | textbox | Name:
3bc3f19b-1517-572f-9011-7adfcae3fd19 | textbox | Position:
c5477d9c-bde2-5e04-97c4-414e76f970e6 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-024-CIV-Brunt-Footpaths & Shared Use Paths |  | ITP-024-CIV-Brunt-Footpaths & Shared Use Paths | c67bdbe9-c439-46db-a9ae-14ceeee91984
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
1bfe8e83-fcaa-521c-a0f6-03748aed1f1d | note | Document Title: ITP-024-CIV-Brunt-Footpaths & Shared Use Paths
83f1348c-d3bf-5d37-b50e-9ae469c2011b | note | ITP Description: Footpaths & Shared Use Paths
99a77119-57fd-5991-82ca-002bf3a0db99 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
d18f0a10-c2fa-5f87-82a9-7ae8aa57b661 | note | Discipline (e.g. CIV/STR/RAIL): CIV
46e3c69c-9bc0-5fcf-87eb-7884fc71f0ee | note | Revision Number: 0
dd57b9f5-60a5-562b-8f89-c9253d53348d | note | Revision Date: 28/02/2023
85bea7e8-52ad-522a-b754-b1984c88e218 | note | ITP created by: Jason Lee
0ca26cee-2e75-57be-84ae-9dc54b060efe | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
b4185d05-6796-54fe-9536-ef7a84fd8319 | note | Reference - VicRoads Section 304 August 2013
| checkpoint | 1.2 - Non Dependent
f56cb33c-e1ab-589a-8598-833742baa360 | note | Reference - VicRoads Section 703 August 2021
| checkpoint | 1.3 - Non Dependent
3d2bd5b3-8546-54fd-a1c5-819732001739 | note | Reference - Council EDCM 401
| checkpoint | 1.4 - Non Dependent
fc13dd62-317f-59d5-aae6-87308671a8c9 | note | Reference - AS4586
| checkpoint | 1.5 - Non Dependent
20b5ac4b-144b-546a-a83f-0f756eb7a6ee | note | Reference - VicRoads Section 812 July 2016
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Bedding Material Placement & Compaction
3c9e193d-a994-59d1-b8d8-9b897d457d17 | note | Reference - IFC Drawings
403c7dc7-d5cc-5257-9d92-67136deedfc7 | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
53530aa6-4907-5f50-9ce2-90cbadef0314 | note | ○ Section 812.04
a3a05144-2137-502e-8f32-ee1f80e5c1e6 | note | ○ Secton 703.21
ac7ac269-562d-5302-a825-be2fca2cf8a3 | note | Acceptance Criteria - Footpaths: 20mm CLASS 3 CRUSHED ROCK
659e10b9-31f9-5eee-b0fa-ab3654a1e572 | note | ○ SUP: 20mm CLASS 3 CRUSHED ROCK
50a1284c-9d55-506f-a789-e5a0dc499f7f | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
c08ead8c-a7e8-541a-87c5-e563bf69ab46 | textbox | Enter: Teambinder Material Approval number
508be8a8-48d8-560a-be5c-22e85bbd111a | note | Method - Document Review
52cdaf99-f78b-57a5-a7c1-42c892b8073c | note | Frequency - Each Lot
db7dd89e-9240-577b-b06d-edc27fa5ac99 | note | Category - HP
d2175564-5c0d-5ee8-87fe-6971950be314 | note | Responsibility - Nominated Authority
163ee965-c4a6-5754-ab2d-3322637b231f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete Mix
e65580d6-41cc-50ab-9ad7-e58f3ae5d00f | note | Reference - IFC Drawings
cb02efa8-27d7-58ed-a6ed-8b92925d4646 | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
0738f9ca-1707-5da2-a523-afa4e07ca7dd | note | ○ Section 703.05 (a)
c7d13439-98ab-590d-9aee-ac8b383011ef | note | ○ Section 703.07
c43cf9ab-2392-56e8-9326-45a08afafb2e | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
eee8797b-b11e-5017-ab69-7e8842a72e42 | note | ○ Footpaths: 25MPa CONCRETE WITH eMESH FIBRES APPLIED AT 5.6kg/m AT 100mm SLUMP
09d6f886-f50e-59ba-93aa-bff4081b9f89 | note | ○ SUP: 32MPa CONCRETE WITH eMESH FIBRES APPLIED AT 5.6kg/m AT 100mm SLUMP
7813cedd-ecfa-5cbe-bbab-d722c687367d | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
27ba6be8-0b83-59de-a612-8ef04a123fbe | textbox | Enter: Teambinder Material Approval number
74e03b57-1fc3-59b8-9232-171f684a2ec8 | note | Method - Document Review
f3da797f-1ee9-5c5f-bc6d-7a4876084555 | note | Frequency - Each Lot
19118bdf-a36e-5749-b4c2-37e45418dadd | note | Category - HP
b807dffa-2ce0-55ba-bd77-e2458b188ad4 | note | Responsibility - Nominated Authority
9816e9f2-966d-5559-a80f-084d1cedeeb3 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Reinforcement
d782bd31-762e-58f1-a2a0-b6faccd893e3 | note | Reference - IFC Drawings
1740775c-4ee6-5799-91b0-c738da4a78d8 | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
43cd447d-c08e-59dc-9f9c-1eb9f03afd86 | note | ○ Section 703.16
1d43267b-789d-5772-934d-dccf3d562865 | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
6906fbd4-e7cd-5072-92cd-0e6d38694193 | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings:
4107958f-b97c-5972-bcbc-0fa6869aa752 | note | – Footpaths, Residential driveways and Median islands infills: SL72
71ffbd86-aa42-5725-858a-d01ffc1d563d | note | – Industrial Crossovers: SL82
93e4efb9-4243-557b-86f4-b06cfd4f3bb0 | note | – Traffic Islands: SL82
9c80e0e0-b24a-5a63-8584-a3ff67e7927d | note | – SUP: SL92
cc48533f-7bd3-5c72-8f7d-81c6e26a2e73 | note | ○ Refer to drawing MRP-089-C-ACD-DRG-14-BFD-CPT-2221 - Pavement Composition. PT04 Footpath and PT05 SUP - it states the use of 25MPa & 32MPa Concrete with EMesh Fibres - can you please double check if you're going to use the conventional SL72 and SL82?
90d751b7-3a7a-5fcf-a8c4-adb56a189e0b | textbox | Enter: Teambinder Material Approval number
1422087c-62bf-5f72-a685-bc7e067d16c3 | note | Method - Document Review
14b219da-ed59-5682-b007-d8500fad6c16 | note | Frequency - Each Lot
61af9c47-93fc-587e-8e81-012eebafdd7b | note | Category - HP
82b90322-96de-5ea2-a3a8-59845319a923 | note | Responsibility - Nominated Authority
b10cf40b-4248-5d42-9318-533d1bd48272 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant (if required)
a4a77a56-c136-56a4-a542-7d08a33cfb7c | note | Reference - Section 703.09
91d7748d-c3a4-5da6-bbe3-c5326f80749c | note | ○ Section 610.17 (f)
3f70f723-5987-521c-bca8-453e03280194 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
b7e40042-3c88-567e-9614-0f3a9ade65b3 | textbox | Enter: Teambinder Material Approval number
199ba761-65d4-5d3c-85b4-27a6636f1af5 | note | Method - Document Review
5ffa9297-23bd-58c9-8296-2aa568405b4f | note | Frequency - Once, for each product, prior to placement of concrete
94dec77e-775b-51d0-8e34-bcddc79f378e | note | Category - HP
c14b8f9e-39fc-5ede-9eb8-95ed09ee67c6 | note | Responsibility - Nominated Authority
2c0b4624-e945-5c1a-bb03-abe76a28b0a3 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound (if required)
02cf34bc-ff92-5e3e-9c2a-51f1ee2586c5 | note | Reference - Section 703.10 (a)
7993bcd0-d512-5d64-b21f-d06336e700f2 | note | ○ Section 610.23 (d)
8d0ab502-91f4-5224-8a8c-b182bfd2aea4 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
6100d778-5a1f-5a4e-9a93-a8d0b4fae32c | textbox | Enter: Teambinder Material Approval number
f842ee45-2268-5e56-abfe-4bf6ce1f9e86 | note | Method - Document Review
ef194e5a-4761-53bb-897e-ad1055018a9e | note | Frequency - Once, for each product, prior to placement of concrete
a572726d-3431-5025-98fb-b55e66e22296 | note | Category - HP
6ece0f71-a980-5f9b-a89e-421dfb630925 | note | Responsibility - Nominated Authority
858d3b39-0120-597e-9be2-380fb25c030d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Survey Set-out
23552379-9db0-55be-be99-f329fe36964a | note | Reference - IFC Drawings Section 703.17
6e6e4c00-9d5a-58cc-970a-e694f76a4dd6 | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
e097952b-8963-5f3e-86ff-d25035a43226 | note | ○ The Nominated Authority will review and confirm the set out.
ed91dd9b-5218-5050-8b0f-85d28b3899b7 | note | ○ Attach: Survey Report
d3c4acec-0094-5caf-9819-8cc38459af23 | note | Method - Document Review, Measure, Visual
37c11418-aa49-553e-9227-59f3bf09d9f8 | note | Frequency - Each lot
b82bb3a0-f0a2-50cc-8f9a-a672c165f0f8 | note | Category - HP*
c6d8090a-6ca9-5612-9f41-9a9e58a920be | note | Responsibility - SE/PE, Surveyor
16c77218-742f-5b1f-87f2-8e48792d2506 | note | Verifying Documents - This ITP
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Site Clearing & Grubbing
dce0c0dc-2a60-50a5-b079-3befeceb55ea | note | Reference - IFC Drawings
766b58c8-140a-5c40-ad42-e7868acfd475 | note | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed.
8bf14aee-cf44-5650-b6c8-15e825cf6e00 | note | Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
d3e5ff87-2687-544d-b5d3-4082268f051b | note | Method - Visual
432d4b2b-bed4-57a1-abcc-ed0d59abb340 | note | Frequency - Each Area
91f8a77e-42f8-5c1b-9240-77f2e5fdd3a2 | note | Category - IP
eb78ef41-a85b-5e38-b3fa-dc282687e5c6 | note | Responsibility - SE/PE/SPE
bc5c0b70-c43e-51aa-a3c3-0bc5e919c448 | note | Verifying Documents - This ITP
| checkpoint | 4.2 - IFC Drawings
334d439a-674e-5856-9177-51462443ec23 | note | Reference - MRPA Quality Management Plan
40158f54-70d5-5e54-bf3f-21fb8531a7de | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
266016d6-e78c-5713-ab43-0c450d6ad7f8 | note | – Using the correct and complete set of drawings
f027216b-538b-5e9d-b2e5-3d45b5f8c2f1 | note | Method - Document Review
1906192d-eab2-57d0-a83f-a3f981406535 | note | Frequency - Prior to starting Works and at regular intervals
f2df83b9-df0f-5595-80a1-63295fc61438 | note | Category - HP*
e96420a0-52c7-5caf-b0d9-4f1846a8db32 | note | Responsibility - SE/PE/SPE
57105e39-4000-57ff-9706-45985c3ee694 | note | Verifying Documents - This ITP
| section | 5. Construction Activities
| checkpoint | 5.1 - Excavation
23d74e3f-b76c-5b86-a3db-c9a7429c28af | note | Reference - Section 703.20 IFC Drawings
a04bb207-3e3e-5783-ac15-725670e2f9dd | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
136535c1-bd65-53b4-9c79-b6ed827ba2fb | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
d0507c72-f1b9-5824-b1af-345eb0e3fb9c | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
15d21de3-318b-5012-b7ce-ff3986fb00cb | note | Method - Visual, Measure
5bfd6748-c576-56c7-b417-eb172d8dad6c | note | Frequency - Each lot
0de846aa-ad28-5242-9b7e-c778c655e2f8 | note | Category - IP
b8f42c38-22ad-5dc8-8439-b9994531d4c8 | note | Responsibility - SE/PE/SPE
52a6c132-cfb7-5e28-a83c-a95fe6eae0e6 | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Excavation-Pavement Thickness Increases for Crossings
5f665620-c20a-5199-907a-9da0fdb9a3c5 | note | Reference - IFC Drawings
db0a0375-db2e-571b-8606-0e6c2cd2cbb9 | note | ○ MRP-089-C-ACD-DRG-14-BFD-CPT-2211 and MRP-089-C-ACD-DRG-14-BFD-CPT-2221
0216784c-272a-5f62-a408-dbac354c582a | note | ○ Relevant Council drawings
a8d5867c-ef3c-5b8b-9787-254a229719ec | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
fde0df83-aa37-5390-8ed1-fd42253e1b59 | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
795c3bd2-74df-5b5c-97a7-1c04053cb3a4 | note | Method - Visual, Measure
be6b6283-dc83-50b8-b2dd-af0a78d4be68 | note | Frequency - Each lot
3dbdcac0-bd2c-5c5a-a0d6-2ab010a1124a | note | Category - IP
5df83bd9-2f6a-53c7-97e4-9464bbaf6507 | note | Responsibility - SE/PE/SPE
93d7b90a-4092-5592-bc17-20f86b0cb110 | note | Verifying Documents - This ITP
| checkpoint | 5.3 - Bedding Material Placement & Compaction
1dd74886-62e1-529c-88d5-96ccb23c06df | note | Reference - Section 703.21 IFC Drawings
7850a8a5-542d-59ae-b5a8-f8dd0be7314e | note | ○ Relevant Council drawings: EDCM 401
daecca66-1383-5374-934f-3e6350e83a63 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings :
05425642-21ed-513a-a853-f78f108be84a | note | ○ Footpath: Bedding shall be 100mm as per drawings
6a933b88-c5bf-5a08-84bd-7edfe0601ccb | note | ○ SUP: Bedding shall be 150mm as per drawings
5b356e25-506a-5111-a85c-a8866a89d722 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
dc1c7186-dd99-5d09-9e65-88e86b632db2 | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
cde5f769-d200-521f-91df-b29d2a7110fc | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
4197b55f-4a49-53a5-8f11-1935ff5fca60 | note | ○ Attach: Bedding Material Delivery Dockets
7c78d2f2-5376-506f-b38f-176a34269f75 | note | Method - Visual, Measure
100158ef-d415-5ffe-96cf-0645bfcb1b5e | note | Frequency - Each lot
cb8b95d7-9ff5-527e-aab4-f07fee289393 | note | Category - IP
5a714991-7256-5bf9-aaf2-968ceab5371f | note | Responsibility - SE/PE/SPE
41f9b44f-14b7-587a-9dd8-92d64891d458 | note | Verifying Documents - This ITP
| checkpoint | 5.4 - Shared User Path - Compaction Testing
a7bf7dd6-dfb0-5ac2-b7a9-fd63b0ecc28b | note | Reference - Section 703.21
d0426a53-8729-5854-93b2-2486b8b5d3a3 | note | ○ Section 304.08 (a), (b)
024c4105-7f39-5463-8aa2-77148b857bb4 | note | ○ Section 304.11 (a)
acf8a5b1-f7c6-5de9-804e-74ff15621eca | note | Acceptance Criteria - Compaction shall meet the following requirements:
729256dc-189c-543f-93e9-ae2673f0d404 | note | ○ Scale of Surface Level Measurement = Scale C
94bd9e4f-10e7-550e-870c-d2a64656932b | note | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
79dd5e38-a695-5f26-b0e1-bd7498c433b9 | note | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
85c875a1-74c6-505f-9688-fa5d096e6883 | note | ○ Attach: Moisture Content Test Results
2753deb8-1053-5260-ae4b-1c1859d498ca | note | ○ Attach: Mean Value of Density Ratio
3936d40e-25c8-5e2b-865b-f90f225c28a0 | note | Method - Document Review, Visual
487c656e-9b07-5ea7-b524-dc8569d1a889 | note | Frequency - Where applicable, each lot
2bbe7e98-a9d2-5748-9e8a-3e9a444f73ee | note | Category - HP*
18ddea85-f0d4-53f7-ba38-dae84f5bef83 | note | Responsibility - SE/PE/SPE
4f67672e-2722-5e3e-b4e7-1ec5de0d49c4 | note | Verifying Documents - This ITP
| checkpoint | 5.5 - Shared User Path - Proof-rolling
790608ff-ba4c-579d-8b0f-2afca76bb14f | note | Reference - 703.21 304.08 (b)
50c979e4-be68-5c77-bf63-b7250d41033a | note | Acceptance Criteria - Bedding material to be compacted and proof rolled before any construction. Withstands Test rolling without visible deformation or springing.
dd79b33c-d7ba-5894-aa2b-eb0d3ae324cd | note | Method - Visual
c57607fc-5b14-5e6c-ae65-cc0823a19f6d | note | Frequency - Where applicable, each lot
1ed96d8a-7519-502f-a713-6304f788979a | note | Category - HP
b5613905-df2f-5604-b0f5-69b784ed94ec | note | Responsibility - Nominated Authority
94586081-5033-57b8-995e-57c23d86630d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Formwork Construction & Placement
bf029538-5b4c-5e0b-b44b-04edeba50558 | note | Reference - IFC Drawings Section 703.12
0506b54f-3891-53bd-9c56-8f615223dca2 | note | Acceptance Criteria - Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
6442ee48-118d-5a56-8913-c2ce5650e2e3 | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
f622b089-1910-5827-95f6-7f63317e1dc6 | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
ae3a2a0b-e04c-5cd5-904c-a29be156f3ae | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
a8f91009-0137-5f10-aa20-8979dc868d5f | note | Method - Visual, Measure
46b35e7c-562c-5a32-af61-bd2b5af038e8 | note | Frequency - Each lot
9491556f-4e5d-5e2d-9017-0bf95c17d7fa | note | Category - IP
d1adcb82-f191-5d97-9f05-62bcca1af07f | note | Responsibility - SE/PE/SPE
7a5d53f6-ae28-5808-a325-40464a11d73f | note | Verifying Documents - This ITP
| checkpoint | 5.7 - Construction Joints & Matching Existing Surfaces
624ceb25-de14-534a-a00d-b5d713062ee0 | note | Reference - IFC Drawings Section 703.24
9777f599-61de-555a-a16f-c57f0feee942 | note | ○ Relevant Council Standard Drawings
35c8d37a-0d83-5eaf-b61e-a2d2a1d8f23a | note | ○ Relevant Council drawings: EDCM 401
7b6c0a9a-6192-538f-ab71-33193d1895b0 | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
f3d8e0e6-eede-5f29-ab12-73ea2e2a3359 | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
5fe2b618-676b-567c-b9f5-d6b86013e12a | note | i. Concrete cutting of a shear-key
9ce650cc-c4ee-5cd1-96e5-4f8ba971087e | note | ii. Surface roughening
c875bae8-3cb5-5039-aa1d-062de08cc364 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
5d769cb2-4c6a-5729-a4f4-c21a87509ea6 | note | iv. Cutting a groove for sealant
26208c2c-3759-5ab2-85a5-5333de722cc1 | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
a5ee7ee5-0a58-557c-9c01-14527dd38b1d | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
7948fa8c-325f-5c33-9d54-cc6df501aacb | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
e2bb95d0-b191-5706-959b-d417f23e6117 | note | Method - Visual, Measure
5e29ec3c-5974-5cc4-b9fe-5a36302ae52d | note | Frequency - Where applicable, each lot
f75cb5de-5e3f-556f-996a-3efae6ea392e | note | Category - IP
b48c94d0-74b6-5f5a-a250-68e3e7491df3 | note | Responsibility - SE/PE/SPE
14f17ab1-734c-5625-a6fd-c0b8a77a7984 | note | Verifying Documents - This ITP
| checkpoint | 5.8 - Isolation Joints
ebd1aa27-a2ad-5a01-8a8e-fb65cf624428 | note | Reference - IFC Drawings Section 703.26 (c)
3b4fb2fc-0170-5895-aaa0-7ee86a6917a5 | note | ○ Relevant Council Standard Drawings EDCM 401
dad58fa9-124e-597f-a291-c4ed33f09882 | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
ccdd4c11-0847-5f31-87b0-749ed4a30712 | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
c785baf1-4d0e-5bd5-b465-d84477a0b6cf | note | ii. at any location marked on the drawings
050b2b3b-046e-50d3-91d4-ba3d7da384ec | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
63adb08f-a1b1-5b7c-8c91-e2e7c349b6fc | note | Method - Visual, Measure
42f21996-dbb3-5702-a310-b33f6a3f8a58 | note | Frequency - Where applicable, each lot
c3bf70ac-4b90-5f5f-9a36-99a382320509 | note | Category - IP
1875394d-7b9d-57b3-97cb-4cbc83ae9e7a | note | Responsibility - SE/PE/SPE
be496ad5-1185-5290-af09-79b8e17364d7 | note | Verifying Documents - This ITP
| checkpoint | 5.9 - Expansion Joints
88853a16-0cf8-500e-a057-e0bf53de4e79 | note | Reference - IFC Drawings Section 703.26 (a) (ii) & (b) (i)
2d489bfe-2267-5fee-b557-837a5dae730e | note | ○ Relevant Council Standard Drawings EDCM 401
04d54f34-6f7b-5427-96cd-2b0eeaf0f94a | note | Acceptance Criteria - Where applicable, expansion joints shall be placed:
60486ae0-2d31-5aaa-a68f-e57122fbaf25 | note | i. on either side of vehicle crossings
6da1226d-6a1f-5594-821a-657400544723 | note | ii. at junctions with existing footpaths and shared use paths
d7700fb9-d85f-5013-9a74-4b69a368bbb1 | note | iii. at junctions with bridges
e737b7f2-4fe9-5a19-a4cb-4290bf65d5c6 | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
5ab1f4af-a725-55d5-abdb-5d3665a7e30b | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
539178e8-7b09-52e2-9912-46e04930dce5 | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
c3d3d4a2-8cd1-5eba-afad-7301c6a65517 | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
c477e726-fa74-5b5b-9978-e156465e52f7 | note | Method - Visual, Measure
73c3e26c-1029-510d-b30a-3c05a47c77c2 | note | Frequency - Where applicable, each lot
c7d867fe-dff4-5eec-8f97-fab40d41a54b | note | Category - IP
7c73570b-107c-503b-96fa-8eb88ae3ccee | note | Responsibility - SE/PE/SPE
274cd5f4-551a-5784-b87b-2a2555e867ae | note | Verifying Documents - This ITP
| checkpoint | 5.10 - Reinforcement Placement
2932a363-30fa-5b94-bbdf-178714eb018e | note | Reference - IFC Drawings Section 703.13
cabf76ee-dfeb-5c08-8350-19d6e22f0227 | note | ○ EDCM 401
90b1acfc-88fc-5448-aa28-da43673418a9 | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
8e9583ea-ebf9-5564-9621-0d87f209e6ed | note | – Footpaths & SUP: SL72
c054a8e6-c127-5cea-8997-9f5fc1f75e5a | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
3704b4e4-c65c-5e59-b072-eb6747121d96 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
6fb30326-9231-5d90-8eaf-a134ea16e382 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
97663c1f-e59f-5681-bd1d-a4b2cb11aa4b | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
165d7fe5-1012-58fd-a458-63bcccead258 | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
b38cc4d7-cb82-505c-b493-e220a20020fe | note | Method - Measure, Visual
47afba04-a44b-5523-af51-06a886aabf44 | note | Frequency - Each element
169b1163-9d4b-5683-aa20-e857398cc8c7 | note | Category - IP
fc95cb4e-d905-593b-9c10-2ba78a2ef1f8 | note | Responsibility - Supervisor, SE/PE/SPE
64949b2a-95d0-5fa3-b98a-f34624691701 | note | Verifying Documents - This ITP
| checkpoint | 5.11 - Pre-pour Survey
9737515c-d48c-5a4f-820d-b335501cfdc4 | note | Reference - IFC Drawings Section 703.15
68b88916-88b3-5107-9a41-5680182e3fb8 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
640e6ae4-d9bf-50e0-8a81-621f95c0cbaf | note | ○ Erected formwork and base layer within the tolerances below:
8db6129e-314f-50ba-9bf3-bf1ab071cb80 | note | ○ Departure from RL = ±10mm
3592b375-7a20-54f1-94bc-d6ef6b8b2db6 | note | ○ Departure from alignment = ±10mm
c99dc229-6edf-5ed3-9e4b-90680b95159e | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
8399daf9-38ea-5075-96a5-9a4f18b69137 | note | ○ Irregularities in alignment = 5mm in 3m
7b5e026d-4379-57a6-a58e-bbb7ae8a930a | note | ○ Section dimensions = ±5mm
822e81be-2097-5466-839f-cb7e14b93608 | note | ○ Section dimensions (less than 25mm) = ±3mm
c6ae5b7a-eec3-5354-a6d4-483969b953eb | note | ○ Width of pavement = -5mm, +15mm
80ca98a6-1a0e-5f17-a1c2-cc89068811b9 | note | Method - Measure, Visual
f1c48168-ba15-5a08-afd5-15e895d1c7ab | note | Frequency - Each lot
d9ce8ffe-1c28-55a1-936a-9eb2a5726876 | note | Category - HP*
5854c554-cf42-5102-b6b1-2c17f157ed7b | note | Responsibility - Surveyor, SE/PE/SPE
fabf2964-f5fe-5f7b-997d-69c52a69135e | note | Verifying Documents - This ITP
| checkpoint | 5.12 - Pre-pour Inspection
73b8e100-caf3-5daf-abc4-9295d2248f91 | note | Reference - Section 703.09
28014ba8-efdb-58e3-89c3-df4fc4489cf2 | note | ○ Section 703.21
0855f46d-e713-5658-a762-71cc73de0adb | note | ○ Section 610.17a), b) & c)
6f4a1a99-f4c6-537f-81f9-2db82ef3e2ae | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
1d7268c8-9b66-5543-988b-31af62a853e3 | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
7e96e282-61f5-5e3a-a915-d5ed31a4303e | note | ○ Attach prepour inspection sheet
b1950bba-89ee-52ee-8e0e-91feb45645c2 | note | Method - Measure, Visual
6fd3c247-0667-5089-b69f-4463d0933212 | note | Frequency - Each lot
a14dc190-6154-511e-94ed-59d6bc233710 | note | Category - HP*
ae7a85e2-1df1-5f44-9a30-9371ac29f6d7 | note | Responsibility - SE/PE/SPE
e5fd0350-7bc3-520b-9bce-7ce159271cc0 | note | Verifying Documents - This ITP
| checkpoint | 5.13 - Weather Conditions & Evaporation Limits
dedc2506-f32d-5686-be19-8901492cb05c | note | Reference - 703.09 610.17 (a - f) Table 610.171
6411a4e8-5435-57ec-8fff-62fa2a8c8ca0 | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
b84c4aa1-c02a-5b48-83cf-294080328760 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
8aa98db9-593e-5b29-942b-d37ee282dee2 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
8f33b661-0006-5122-9458-0d7c51cd6f4f | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
56b1a495-0331-5b56-87f9-9fc6fa2525f6 | note | ○ Record: Required information on the Concrete Pour Record.
1fa0424b-a999-5a78-b6cc-8ca03f9e88e5 | note | Method - Measure, Visual
3c026aa1-2d77-5299-bd7a-c588b43735c7 | note | Frequency - Each lot
8739f88a-da74-5e13-96f8-8d43c5747051 | note | Category - IP
96c35f67-4fa6-5a0e-b116-50f26d976b1a | note | Responsibility - Foreman, SE/PE/SPE
f5e24c58-660f-52d9-bbee-c1d8e305a69c | note | Verifying Documents - This ITP
| checkpoint | 5.14 - Concrete Testing - Sampling Frequencies-Footpath
acec883f-cbdc-5605-b2cb-83aa8a0d89af | note | Reference - 703.11 AS 1379-2007 Cluse 6.2
43072fc8-1f70-5b99-be6a-bb035e005489 | note | Acceptance Criteria - The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
d9fed927-3461-58ca-8a17-7bd4b642234f | note | ○ Correct quantity of cylinders manufactured per sample.
7c34f844-ccbd-5185-829e-deb22424a2bb | note | ○ Record: Required information on the Concrete Pour Record.
326c6148-bf27-53aa-a9e2-776b483a535a | note | Method - Test
4a75e29f-9efd-526d-ae1a-7ecf637b485a | note | Frequency - Each lot
99b1f650-7836-546a-9996-8166ef536252 | note | Category - IP
793ac5bd-f846-5814-ab8a-ee14a578116b | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
19ef0d23-2da3-52d2-b8de-0b94a5c9f624 | note | Verifying Documents - This ITP
| checkpoint | 5.15 - Concrete Testing - Sampling Frequencies - SUP
660c318a-5879-5323-894f-b18fc767f434 | note | Reference - 703.11 610.16 (b)
bd2d8a31-9dfa-5999-afc4-e934d430e501 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
6d9ee38a-e887-5a8c-aefb-6c9f7fe253ad | note | ○ Shared User Path:
99ffaede-984f-5afb-bc44-c53e920b2778 | note | • 0m³ to 10m³ = 1 sample
99fa58de-9b29-5f6c-8f78-6a2c55c2fb39 | note | • 10m³ to 25m³ = 2 samples
61328106-662a-58f1-a19c-f360b3211416 | note | • 25m³ to 50m³ = 3 samples
720558e9-e151-5c9b-a13b-390cb91dd355 | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
c411f79e-0828-5573-a80a-aa1cbf8de176 | note | • For each additional 50m³ and additional sample shall be taken.
b920758e-9219-5e7f-b7b5-bf25dadd919b | note | • Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
74d4bd2e-a162-588f-b942-23ce79b89f98 | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
fdfa37ec-e54a-5107-9a28-c9c8ded649f9 | note | ○ Footpaths:
ca4f1aad-6c5f-5f1d-b9cd-33a9b54369cb | note | • 0m³ to 50m³ = 1 sample
f14b9756-ae2e-5763-91f7-1a60b5e7fab3 | note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
5acfbe51-f4de-57b4-ad1b-f31290553f61 | note | • Compressive strength cylinders = 2 no. 28 day strength.
71f06185-4f2b-5b9c-9e07-854563474bc3 | note | • Correct quantity of cylinders manufactured per sample.
b170fd60-7ee8-5f7a-9654-0eccf69318f2 | note | ○ Record: Required information on the Concrete Pour Record.
7d9cb691-9b37-5fa2-bb01-839a1988d989 | note | Method - Test
274d136f-b46f-5f83-b1f6-ab0d3c9dade4 | note | Frequency - Each lot
6807d940-131d-505a-aacd-d117bd60744d | note | Category - IP
87db886a-c66a-55a5-af0a-4d72fc2fb4fe | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
a1ea0eb5-1d59-5eb8-87f6-1c47eebae1c7 | note | Verifying Documents - This ITP
| checkpoint | 5.16 - Concrete Testing - Slump
3b6eed49-a15d-5228-a5f4-8e2329a7625c | note | Reference - 703.11 610.16 (c)
e81392c2-392b-5b1c-8f3b-5dc5899c1e11 | note | Acceptance Criteria - Slump testing tolerances =
aefea509-04b2-5849-9003-bd364ed9d901 | note | • <60mm = ±10mm
1df6be63-2589-59d6-867e-b6a7666cd4b0 | note | • ≥60mm to ≤80mm = ±15mm
36846dca-331c-5e6a-bf44-367ac6329535 | note | • >80mm to ≤110mm = ±20mm
da910f43-2c05-5d82-811e-26164d45dafd | note | • >110mm to ≤150mm = ±30mm
6ba2c7fe-2f35-58f1-8d58-de404bc048e5 | note | • >150mm = ±40mm
56899129-a9a0-5965-9cd5-1affae27133d | note | ○ Record: Required information on the Concrete Pour Record.
964cba56-bfcf-5a93-b3b1-59dcd7790e3e | note | Method - Test
44e5451d-4479-517c-a81a-90c96bb5f8a2 | note | Frequency - Each sample
8bf99059-3aed-5569-a6f9-968629dd0028 | note | Category - IP
f8a351d5-3477-5815-8b42-f1ebbc3bd7c1 | note | Responsibility - Concrete Tester
67b50d1d-8418-54e9-bf2e-aa648b5a79a1 | note | Verifying Documents - This ITP
| checkpoint | 5.17 - Placement & Compaction
959ebf63-8c16-59b1-9788-01c1124656a6 | note | Reference - 703.08
c46ac046-54c4-54fc-a8c9-06719d566fb2 | note | Acceptance Criteria - All concrete batches are traceable.
27f9e586-eec0-524c-8e6e-862b7404bf44 | note | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
3745f32d-9019-5a1c-af53-e7e9c6a674c5 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
487641fa-1063-5abd-9664-ff9cfd64e29b | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
aec2ce2c-bc12-55c4-a073-32334d3005b3 | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
dd23c0cb-f618-57b8-9393-27230fd4d225 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
3a132827-bc66-5e8d-ba8b-5680e40d95c4 | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
b6d21852-a419-506b-b115-59c5943d180f | note | ○ Record: Required information on the Concrete Pour Record.
dc89a6a0-d62f-5dd2-ac7f-95c26374d400 | note | ○ Attach: Concrete Pour Record
66f5a412-28d2-5031-bd77-37c2e02cd069 | note | ○ Attach: Concrete Dockets
03be6649-e3d8-5e5f-8ba9-3875a04091b1 | note | Method - Visual
84005c09-2179-55a4-b986-def392f59412 | note | Frequency - Each load
6b4a7bfb-c423-5b3d-9e13-8d9c66cb1385 | note | Category - IP
006320f1-aacb-584a-bf0b-12b7c2e7ae89 | note | Responsibility - Foreman, SE/PE/SPE
5d7da57e-ef4e-55b8-abe9-27ea757bc22f | note | Verifying Documents - This ITP
| checkpoint | 5.18 - Surface Finishes
200ab523-38a7-5dc0-8428-da72317f83dd | note | Reference - IFC Drawings
a055cb51-73d4-5784-b1f3-0227c6cd0645 | note | ○ Relevant Council Drawings 703.25
a110c910-fb72-5b23-a43c-0611f9162556 | note | Acceptance Criteria - Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
ebe0a5e5-3d9f-5b81-857d-3c55a7587c34 | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
5bbc0fcf-10c5-5b87-a734-c7086ef5dd75 | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
4fd6b4e5-96bb-545a-8d63-b23781ae80f4 | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
f4137f06-2325-59f9-91ab-c8b3c73f3a87 | note | Method - Visual
d31135e6-cc60-5ade-80d6-7d7c91c61063 | note | Frequency - Each lot
e2229baa-1019-5e79-b39a-ed01e953e665 | note | Category - IP
090a0be2-f9cc-5883-8a86-9aa7a974536a | note | Responsibility - Foreman, SE/PE/SPE
456b4490-bbb1-5ca9-a7b9-94e9f9c7305a | note | Verifying Documents - This ITP
| checkpoint | 5.19 - Footpaths - Crack-control Joints / Weaken Plane Joints
fc900d1b-995f-5399-b66a-89e700e6fb5a | note | Reference - IFC Drawings
15091f6c-44f3-5f33-90d7-bf86a0c2f40a | note | ○ Relevant Council Drawings Section 703.26 (b) (ii)
d8ff3e2b-ccde-5875-b291-e8dc6fe18f2d | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
747d76da-2482-54c4-826c-2c232f90e8c7 | note | Method - Visual
04be7279-008e-5566-bd16-4c3efbf121d9 | note | Frequency - Where applicable, each lot
e5a5065a-21a9-5028-9ac7-35129e4fd7e7 | note | Category - IP
3cef4468-a3fb-5396-999f-bcda193081d7 | note | Responsibility - Foreman, SE/PE/SPE
04082cea-d009-5cef-9b10-426c62f930e0 | note | Verifying Documents - This ITP
| checkpoint | 5.20 - Curing
1d28e45d-0301-53cc-ba49-a1b0c7425f47 | note | Reference - Section 703.10
613bbd23-93ea-564d-90b8-a1df53ff97d7 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
2746efe2-c129-56f1-9c43-bb30cb8a197c | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
243c2fc6-533d-5477-a031-a53616f42d70 | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
73f68001-4dd7-581f-92e2-df34d1c256ab | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
1ff83b1a-3775-58c8-98cd-5713dc02ebf2 | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
fbc386ce-16d7-5331-848b-af97704d2c80 | note | Method - Visual
5dec4180-01bf-5a72-b207-0fd9439613a5 | note | Frequency - Each lot
2f2d4c7e-403a-538c-b398-58d48f68f285 | note | Category - IP
d1ce4522-2c47-531d-a6d1-77c98d36b1f5 | note | Responsibility - Foreman, SE/PE/SPE
e276d436-c975-5eac-a698-929d2aa4f74e | note | Verifying Documents - This ITP
| checkpoint | 5.21 - Hardstand Grade
b8303995-a1e4-591a-9d6a-2357ae9890dd | note | Reference - STD S0075
7466a273-6379-5a67-a2aa-166fbfa4fa48 | note | Acceptance Criteria - Hardstand that are connected to the Bus stop must have a grade between 1% to 2.5%
f8ffd8b5-8dd6-58b6-87d0-d44c811b663e | note | ○ Attach: Survey As-built
5eaa3d41-f591-5117-b29e-c8676f882ca5 | note | Method - Visual
a4ce2971-1e48-52d3-a391-acb77806bee6 | note | Frequency - Each lot
bf53f6a6-7657-5335-aab6-bb3e6f2f6e82 | note | Category - HP*
aa5c27cf-30c7-5670-837d-95973a7d4525 | note | Responsibility - Foreman, Surveyor, SE/PE/SPE
425f24ca-5d40-52f6-bcc1-4f55050b28c9 | note | Verifying Documents - This ITP
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Shared User Paths - Crack-control Joints / Weaken Plane Joints
c01b8d6a-e215-5041-9d14-b19a8911d6a4 | note | Reference - IFC Drawings
28169128-4cf2-5cd8-b3b5-9be9fb0e94cd | note | ○ Relevant Council Drawings Section 703.26 (b) (ii)
fae4453f-7aa3-5196-9f4e-46429a811608 | note | Acceptance Criteria - Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
279e59e8-9b2d-5b0a-9791-c0c31dc6a7a1 | note | • <20°C = within 24 hours of finishing operations
98519f4a-9190-5788-a5fe-7004859cf885 | note | • ≥20°C - 35°C = within 4 hours of finishing operations
e88c45ac-57ae-5fc2-b819-8a779f3ede81 | note | Method - Visual
128b9809-909c-5bff-84fc-c2357ef4a074 | note | Frequency - Where applicable, each lot
bc2efbd7-0089-51d0-a473-22212b5a80b6 | note | Category - IP
6111eab7-de5c-5ef4-afd9-cb71739a456f | note | Responsibility - Foreman, SE/PE/SPE
3e78f426-15c6-5e52-8d54-c219bf337ea3 | note | Verifying Documents - This ITP
| checkpoint | 6.2 - Protection of Newly Poured Concrete
a3a27ce1-1ded-598a-9809-0f818a1272fc | note | Reference - Section 703.27
f19246c9-4296-5e1d-ab6b-3ccd7dacf7a2 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
f9190d4c-adbb-5c55-8001-7bf24d2fbd48 | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
726e025c-9409-5019-bef9-2b54622c7d41 | note | Method - Visual
df390c42-10f3-5d13-a8a2-a78e69200257 | note | Frequency - Where applicable, each lot
1e601bf5-e30c-5757-8987-df87fb89cbb9 | note | Category - IP
a09d244d-d04a-54dc-8747-f8b464fe3d0f | note | Responsibility - Foreman, SE/PE/SPE
a0aa58db-ed4b-53e3-a763-067d51413c95 | note | Verifying Documents - This ITP
| checkpoint | 6.3 - Stripping Formwork
2d5ef642-ead3-58fb-88ba-387ffddb3080 | note | Reference - Section 703.12 AS3610 Table C2
ec0c5c2f-942d-53d8-a236-0e8e365da5a7 | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
58032c71-5c8f-5c18-852d-92f310535d15 | note | i. 2 days for vertical formwork on external surfaces; and
70470727-1cd0-5800-a898-a20908665029 | note | ii. 1 day for vertical forms on permanently hidden surfaces
e01a005c-4fff-5dc5-b0d8-0515a584fa53 | note | Method - Visual
12b7c2a8-4e03-549b-b7f1-46541af4a1e4 | note | Frequency - Each lot
7bdc520a-95c5-579c-a3bc-9b90ac6cce3f | note | Category - IP
6329c288-92d3-5c07-beb1-83b62778dc9c | note | Responsibility - Foreman, SE/PE/SPE
6778ffb5-7b4c-57c1-ae72-6810fe09daa4 | note | Verifying Documents - This ITP
| checkpoint | 6.4 - Backfilling & Pavement Restoration
f2f5d9f0-a031-5133-8c6e-9fd1ed59eb00 | note | Reference - Section 703.29
646a108a-dd82-5d9c-abf6-c5738a315b76 | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
c0b4ee79-e6dc-5daf-8cee-0b4d237cee87 | note | Method - Visual, Measure
fb16859c-aac3-598a-b8d2-50c5c9d0e7cc | note | Frequency - Each lot
94dec536-2e23-5ca4-9658-d0d7d584fcca | note | Category - IP
e2714db8-a359-54fb-872e-5a5c7e04bd13 | note | Responsibility - Foreman, SE/PE/SPE
b8f8b1ee-2fb0-55cf-b0fe-832da324e92a | note | Verifying Documents - This ITP
| checkpoint | 6.5 - Surface Inspection - Cracks
6c4c5e96-a3bc-54a5-85d9-7777964c4730 | note | Reference - Section 703.3
bb67248d-0d40-5211-8604-7add019c5945 | note | Acceptance Criteria - No cracks greater than 0.2mm. If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
618f8dfb-a791-5ff0-8652-665563da8763 | note | Method - Visual, Measure
ff4fdae0-b01b-5ec6-83fb-5587aeffb66b | note | Frequency - Where applicable, each lot
f6de8df7-4f68-5de4-a496-465715bda13d | note | Category - IP
71b05d15-390c-50c1-8e91-a7a5588507dd | note | Responsibility - SE/PE/SPE
05da6a71-cd84-5963-b488-0ebda3b456cc | note | Verifying Documents - This ITP
| checkpoint | 6.6 - Surface Inspection - Surface Finish
685e4933-e28f-51be-9960-1da29d3e80b8 | note | Reference - IFC Drawings
c8fac977-dee3-512b-97fc-75bb0ee6088f | note | ○ Relevant Council Drawings
b275786f-6158-538a-afef-90f5f28ce7f1 | note | ○ Section 703.25
6cd1ff9f-d9ff-5997-ae4a-d6ec8bb58330 | note | ○ Section 703.10 (a)
9e21130b-ee36-579f-b0f3-2b8d791dbb90 | note | ○ AS4586
dc8df539-d676-5bb6-b552-9b8ab4788059 | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
3a0369a0-a701-5b4d-8077-eec9aca7f468 | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
ba9829bb-afc0-5060-b706-bc3af8f23b2e | note | ○ All Finished Surfaces to comply with AS 4586 Slip Resistant Classification of New Pedestrian Surface Material
d1421787-d530-531a-9f8b-5919d91823eb | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
92dfeaa8-53e9-5f9d-899e-8ea81a70a351 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
070d58cc-6aa5-58b4-8cf1-ddc4a7154cf8 | note | Method - Visual
56f93c12-5891-5938-ab4f-99a8d7456af3 | note | Frequency - Each lot
8f604336-58f3-573f-94e5-66e9f010e22d | note | Category - IP
c07d6a91-37ca-58e8-bc1b-7dd0c04d83ee | note | Responsibility - SE/PE/SPE
c01809ef-6e0e-5966-9ffe-5d6dedd8e137 | note | Verifying Documents - This ITP
| checkpoint | 6.7 - Compressive Strength Test Results
5bf53eaf-e73e-5827-bd19-02c81d210770 | note | Reference - IFC Drawings
25a100cd-0277-5886-8a2f-c312a5b012e2 | note | ○ Relevant Council Drawings
47ac36d8-a978-5303-b371-d683cff276f0 | note | ○ Section 703.11
e0f5a26c-43e7-5fa1-bb49-aa5c23b92b4a | note | ○ Table 703.111
b31b683f-9394-5895-b4d8-4ddf4dab38f4 | note | ○ Table 610.05.051
65940027-13e4-5089-aae2-fe5fab242b24 | note | ○ Section 610.16 (g)
e1c70621-8803-52d1-ba3c-c36f49aa2090 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
7d2a54fa-1132-5c46-8f31-dceae759106e | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
9c93fa42-a7a8-5165-953d-d51a78549bfa | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
4e37af95-7b72-54a4-89d4-58a29e588322 | note | ○ Attach: Compressive Strength Test Results
c84cde45-b574-5725-bddf-9be287c6a38f | note | Method - Document Review
80c3c37f-fa89-5565-8b77-3dbf3594eda1 | note | Frequency - Each cylinder
68043d6e-60ff-5096-a0fe-736d768bdab2 | note | Category - IP
60d55850-211b-5cc3-a2cd-d99bd070a380 | note | Responsibility - SE/PE/SPE
ec8c2d00-4d4e-5c8a-91ec-37c352351ac3 | note | Verifying Documents - This ITP
| checkpoint | 6.8 - As-built Survey
66811eaf-ec3b-53de-a401-78064624bed1 | note | Reference - IFC Drawings Section 703.15
2195c9df-4a7c-5652-8c83-e956fbc88043 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
e9d912eb-8b23-54a7-851e-eef08ee70964 | note | ○ Departure from RL = ±10mm
64f713d0-e2bb-541a-bfac-757c0d00b08a | note | ○ Departure from alignment = ±10mm
15463c75-64a7-57b0-ab9e-187ac75c23ae | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
c17ffaf0-04de-5d66-a340-9002e2fc95f6 | note | ○ Irregularities in alignment = 5mm in 3m
50e5ea19-d89f-5bc4-8237-f250b5150eb4 | note | ○ Section dimensions = ±5mm
547c84f7-b7aa-5914-ad10-1f17c5655dc1 | note | ○ Section dimensions (less than 25mm) = ±3mm
6ee551dd-33c8-5a43-a583-bd9da615e97d | note | ○ Width of pavement = -5mm, +15mm
bc16c36c-b4b3-5b5e-a226-0f30d9674a6c | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
8a8ee913-fc89-5471-a26e-3dea275f291c | note | ○ Attach: Survey As-builts / Survey Report
f4ea1b28-4fab-5bfd-9bd0-58f383f4dfbc | note | Method - Document Review
9331e090-49de-5d5d-9c9c-4f44710dd867 | note | Frequency - Each lot
d036f617-47f3-5206-bfde-ae8c2c7acd41 | note | Category - IP
7a541f26-757a-540e-88a6-470875a95e73 | note | Responsibility - Surveyor, SE/PE/SPE
a972e9b2-d9e7-5891-ada3-c38a6d9a9e19 | note | Verifying Documents - This ITP
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
1c5fe5cd-88de-567b-994d-a26b4050fa89 | note | Reference - MRPA Quality Management Plan
659a8b6d-28ae-559b-9732-adbac5909987 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
6c25391f-7cc0-55b4-8130-020bb18fe9a0 | note | Method - Document Review
7d04c6ce-42c9-5beb-b9ea-d65ad6485c15 | note | Frequency - Once, prior to closure of this lot / element / Work area
054abc32-5b4f-5193-be72-2d28be2b6760 | note | Category - HP*
316242c0-8958-520c-9f6d-b386c33ee6a0 | note | Responsibility - SE/PE/SPE
d6250411-1f6a-5291-8cdb-ac2bdb6c5abe | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
5153d69d-b63d-54b7-8149-1d64ce4aeab5 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
92e136a6-3aca-5bc4-a9cc-66592e8a79d1 | textbox | Name:
3c962548-ed6f-5443-97f7-9593a73f63cb | textbox | Position:
7de713f1-a553-56be-8290-a2fd0656dd84 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-025-CIV-Brunt-Kerb & Channel (Supply and Install) |  | ITP-025-CIV-Brunt-Kerb & Channel (Supply and Install) | 8fc93039-3f87-4784-a7a7-dc13bd43a9cc
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
6b9720fd-7c54-5cf8-83b5-464feaa8ed6e | note | Document Title: ITP-CIV-Brunt-Kerb and Channel (Supply and Install)
0e6587bf-f846-5421-80a0-baa41fcc578a | note | ITP Description: Brunt-Kerb and Channel (Supply and Install)
c0cd8cbd-1654-548d-972a-a5adcdcc076b | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
155c011c-e213-55f1-bc6d-8285ae2f5a7a | note | Discipline (e.g. CIV/STR/RAIL): CIV
6e06a300-6840-55bb-a8d6-9c8089ea14ed | note | Revision Number: 0
6db6d066-fdaf-520a-aec1-17f0af044566 | note | Revision Date: 28/02/2023
a89e24cb-4456-5db4-b9d9-eb494cbe8408 | note | ITP created by: Jason Lee
3916dd72-2ab0-547b-bc3e-cb7775ca8d4e | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
6c8075d5-ea12-5e1a-9e79-550a7e944716 | note | Reference - VicRoads Section 703 (August 2021)
c475052b-a0f9-5e66-ae25-7a671d3b24d1 | note | VR SD2001
18db27d2-f917-5068-bfe3-43b91b47943f | note | VR SD2102
f355ee05-bd4e-573f-87c6-52c77c66161d | note | AS 2876
b5bb447e-3292-529a-9deb-efd6f8224243 | note | AS1379
| section | 2. Preliminary - Materials
| checkpoint | 2.1 - Mix design
af5dd723-16cf-5e62-ae6b-0f6ce6c2f02f | note | Reference - SD2001 AS1379
d3edf9c4-cd78-5a54-811a-0bff1da73bd7 | note | ○ Section 703.05, 703.06, 703.07
7c5d059b-f2cb-516f-8d9b-3f130990f9fb | note | Acceptance Criteria - Approved VR mix design to be used.
c58ee228-b282-518c-9576-d8fb2c20fb84 | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
fdf3945e-5cfe-5c79-9737-e1e436c9270f | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
e59bc8b5-c96b-51e2-b16b-4226b571ab3e | note | ○ Attach: TeamBinder Material Approval Ref No.
1fae6b38-55f6-58af-b1d1-edd124d72e84 | note | Method - Verify, Document Review
7c3bbe00-7308-5622-8594-91bd7279e957 | note | Frequency - Prior to commencing any activity
1ade6834-1d61-5e19-b039-4249962c160e | note | Category - HP
afebfdec-685f-5d94-a848-d40dba43b376 | note | Responsibility - Nominated Authority
130fc6f8-d4d4-57f8-be5b-f5c30f6378bb | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Bedding Material
05f9e601-2f17-507b-a49c-02dbf4b5d43c | note | Reference - Section 703.21 IFC Drawings
57be8a0e-b490-5b5c-b724-56b92d93412d | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
0366bb4d-fde1-573a-975e-fba83ea93aa0 | note | ○ Attach: TeamBinder Material Approval Ref No.
b4d4092b-9061-5068-9373-09928b763e2c | note | Method - Verify, Document Review
52470324-1bb1-5c80-8165-effb7fb0379e | note | Frequency - Prior to commencing any activity
8f45bf6b-336f-55f6-a2e0-e9c126aa4007 | note | Category - HP
bbfca76e-ef3e-52cb-90a6-59c47ca91211 | note | Responsibility - Nominated Authority
1ec7da20-a739-50d5-8e00-db593a62666d | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Curing Compound
e490f7e7-8245-5a91-ba2c-944e0149e45a | note | Reference - Section 703.10
14f15093-1e14-52cc-89bc-7c490305ef6d | note | Acceptance Criteria - Curing compound shall comply with AS3799
9249160f-5008-5b13-bb07-df126a394131 | note | ○ Attach: TeamBinder Material Approval Ref No.
52ca43d2-042a-5b0f-afc8-c064ee68420b | note | Method - Verify
258e3006-017b-56fa-9f62-3443442f6641 | note | Frequency - Prior to commencing any activity
873555ee-c52f-578f-8290-8feaa4f82eb1 | note | Category - HP
fad85ce0-dbe9-519d-a1ff-73594efafef0 | note | Responsibility - Nominated Authority
ab43aa48-62bf-5a36-884b-aa6fa78ff91e | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminary - Documentation
| checkpoint | 3.1 - Check for correct documentation
021ba59a-a9fd-56d5-987c-591c9d347ca6 | note | Reference - IFC Drawings
10280ead-9431-599c-81b4-0043d9a45b4c | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
45a172bd-7165-5125-ba17-777a46f5c67d | note | – Using the correct and complete set of drawings
65913086-8170-5273-9b4f-a88ac1aabc59 | note | – All drawings are the latest version
fdfc4b06-15b7-5e1c-8359-4f084e9fab7a | note | Method - Visual inspection
1d61fac2-9d46-5cee-83f0-5ab550e2a9d0 | note | Frequency - Prior to commencing any activity
80ec6a66-a9cb-5140-949f-049a2cebafb6 | note | Category - HP*
339fd17f-24b3-5cc4-97aa-ffb38e2c576c | note | Responsibility - SE/Site Supervisor
abc6f78c-8477-56fe-9b83-8d8cb8b240ce | note | Verifying Documents - ITP Signed
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Setting out
a16289eb-b911-5576-b5f4-97ab64853d2e | note | Reference - Section 703.17 IFC Drawings
163cf5fe-2cee-50fe-8ac6-a9f2357ee805 | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
318f09fd-1dbc-5304-b643-29a200a1d09a | note | ○ The superintendent will review and confirm set out.
5cff4dbb-db92-584b-b7db-baadd3b93c4f | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
b90ae5f1-9223-5f33-9394-843291c46aa0 | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
96557c43-533c-5adf-bbf1-290da2e7ec92 | note | Method - Verify
c95a16dc-18b6-55da-a01e-69cbb7b2376b | note | Frequency - Prior to start
db982897-f4d9-58f1-9d0f-51972e5a4e13 | note | Category - HP
70b9bb77-7bec-54f6-b44c-089f578ab7b5 | note | Responsibility - Surveyor/Nominated Authority
c68f5a4e-717d-5735-b6f1-5b1e16ec61e5 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Temporary drainage provisions
e3db48db-005b-5112-9fef-68db22f8c28d | note | Reference - Section 703.18 CEMP
883813aa-aa9e-5112-abd1-87d00aee34a0 | note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
a9423001-6490-58fa-9635-b31af6f4bf4e | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
26a276b8-ca94-5c0b-abb7-05bebe9d566c | note | ○ Attach: relevant written approval from relevant stakeholder.
e84aa963-a2ce-5a52-85f7-1e2a4cd17492 | note | Method - Visual inspection, Document Review
84a6249b-53d6-54d2-85ff-43ab75497cd1 | note | Frequency - Prior to start (where required)
201831f5-5fce-58a2-8b0d-d81df58a5d82 | note | Category - HP*
f73cdbc9-7822-57a5-89bd-49351af30360 | note | Responsibility - SE/PE/Site Supervisor
5445c107-3686-54e5-ad7e-b9b8c175ec1e | note | Verifying Documents - ITP Signed
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Bedding
d33f54e9-ca24-54eb-8d17-67f50f53ad6e | note | Reference - Section 703.21
a3850de6-27ea-56bd-8325-f3d0757d7b33 | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
be93843e-19ae-5001-94c8-b0af77e51825 | note | Method - Visual inspection
c774239a-caa8-57d0-be9f-a446ebaf28d2 | note | Frequency - Each lot
137c745f-6de6-5a97-883f-00048936622f | note | Category - WP
bf02cbfe-592e-50f3-8b4f-46eec034330d | note | Responsibility - SE/Site Supervisor
93bb4ebb-a596-5cae-a687-dcde82574aeb | note | Verifying Documents - ITP Signed
| checkpoint | 5.2 - Formwork
6b899e08-2249-5a8c-9be7-f6de9651379c | note | Reference - Section 703.12 AS3610
a5ed3721-86eb-54b2-a77a-47e14accd765 | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
47ed9196-a856-5a7d-9819-d408cd01a922 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
c925cada-b3cd-5a2e-b634-d4b9a5e65e84 | note | Method - Visual inspection
4ad2d805-bd9c-522a-8c1e-c39739b52ddf | note | Frequency - Each lot
b46fb4d1-33c2-5cd2-b1e4-24525bd27401 | note | Category - WP
45e4fa9c-fd67-5580-9870-6de32a7e3827 | note | Responsibility - SE/Site Supervisor
2030e67b-3ac4-50b6-aa12-d9e169f8cee0 | note | Verifying Documents - ITP Signed
| checkpoint | 5.3 - Pre Pour Check
b07207af-c798-552b-b88a-ecd4486890f8 | note | Reference - Section 703.09
c559e05c-fa9f-5976-8a4d-5865485b5fc1 | note | ○ Section 703.2
52a0c6f0-3b03-57dd-9269-aa0d404eaea4 | note | ○ Section 610.17 (a,b,c)
28926b95-32f4-5386-bf1e-bc963d960e1b | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface.
75949ddf-e97d-54d0-9ddc-5d1dd0755144 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
ecdbf081-7f57-5809-99d1-6ad38d7c8221 | note | ○ Attach: Pre-pour Inspection Record
bd9b9228-6841-5843-8a03-fff4ee2587cb | note | Method - Verify
45e82ca2-3cb2-5081-ba37-f01b680f20b2 | note | Frequency - Each lot
cd348c05-4398-54d9-9637-b99e41a83599 | note | Category - HP*
e831c4bc-a3d5-5a26-9a4d-8bdfa433dc1b | note | Responsibility - SE/Nominated Authority
61944123-9a5d-5287-809a-ca141e84a5f2 | note | Verifying Documents - ITP Signed
| checkpoint | 5.4 - Concrete placement
c18ed478-280d-5ca5-ba6b-90bbe6afbd76 | note | Reference - Section 703.08
746fbf47-aca2-5616-8b66-5c2d5becb861 | note | ○ Section 703.23
82891dc7-8a75-58a5-b7d2-3f8d0c9a02d7 | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
a23e5753-4753-524e-a70a-128183a1c077 | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
12df94d1-ba31-597c-af7d-95a03c25583e | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
e3e891a6-398e-5f34-a8d7-32956094ab3a | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
e3f5f4de-5daa-52a9-b77c-d9fbe7bf1d1d | note | ○ Attach: Concrete Pour Records
06aca65e-b1be-5d8a-9f16-a97bb2144a94 | note | Method - Site inspection
7d32eb90-eecd-569c-9d17-50d9a67103ff | note | Frequency - Each lot
43c60e2d-e654-5b2a-ac5b-13f668cad2b0 | note | Category - IP
0d715546-0588-5581-aa95-a17703c06449 | note | Responsibility - SE
425ee9d5-51fa-5554-877a-ead7513cfd24 | note | Verifying Documents - ITP Signed
| checkpoint | 5.5 - Transitions
74710bbd-79c4-534f-85f4-d5af53e4e955 | note | Reference - Section 703.24
cafe4aec-8191-524d-8a43-b4e95c2fac65 | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
b305fc0c-53b3-5f32-81c3-1edf46d2eda0 | note | Method - Site inspection
5c79c742-c283-59de-8b77-b07aac651bf8 | note | Frequency - Each lot
e765d43e-147d-5545-b419-321e198decee | note | Category - IP
e33bb3a8-1608-5056-9d6f-3f7b7833792f | note | Responsibility - SE
c62b3c98-18fa-5519-a1a6-d2358ceede85 | note | Verifying Documents - ITP Signed
| checkpoint | 5.6 - Surface Finish
8c4ece4a-7a68-5462-928e-4c8e336719d5 | note | Reference - Section 703.25
b9873d0a-957b-50fd-9011-967da43e742d | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
2a790de8-bdb6-5a20-9636-c2db00f0cff4 | note | ○ Renderings shall be applied within 30 minutes of extrusion.
bb8be37c-f451-5be2-a7f8-c99311bbcecd | note | ○ Concrete to have a neat appearance and uniform colour.
711b7d8e-8bc0-589e-ae54-99d9ed953e4c | note | ○ Class 3 finish required for external surfaces.
2a3302ef-a81b-51f0-8b31-54111b93a6e4 | note | ○ Class 4 finish required for permanently hidden surfaces.
19196b76-0f10-547a-a57a-793dcff16523 | note | Method - Visual inspection
f40cde76-09e9-5f91-b2f2-c4900654519b | note | Frequency - Each lot
5c5cb985-469c-543c-bd81-43f365d0b94e | note | Category - IP
370f11ef-b472-53a0-80c4-79d7b1ff0b44 | note | Responsibility - SE/Site Supervisor
47835453-5089-539a-adf6-67f86166eff4 | note | Verifying Documents - ITP Signed
| checkpoint | 5.7 - Formwork Stripping
c13892db-3821-5cf0-8394-4cc7e24e33f3 | note | Reference - Section 703.12 AS3610
adaefd91-8d45-5845-94c7-52f213adf185 | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
9c58dda6-5cc7-5071-8cf1-b5613dcf0dd4 | note | – External faces 2 days
172f0c76-8027-54be-9e43-8055421d5966 | note | – Permanently hidden faces 1 day
75201602-c629-5aac-9aed-562f0fc51ab0 | note | Method - Visual inspection
2cbe73db-08d8-5c37-9449-d0f2809be82e | note | Frequency - Each lot
54608081-a238-5289-bc13-dc356ea17919 | note | Category - HP*
0a676042-e1b5-5b05-a1d3-9c87590a8b6a | note | Responsibility - SE/Site Supervisor
99d6866c-f9ea-53a6-9dbc-aa4b5eac9a98 | note | Verifying Documents - ITP Signed
| checkpoint | 5.8 - Tolerance
f9da69dc-4a2f-5e22-ac86-a264fc97add6 | note | Reference - Section 703.15
313cfe39-2a69-5084-8944-a8808c8f5025 | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
19d13dd4-9508-569d-a170-b3ba81d4e4a0 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
ec146257-a2d6-559e-ac99-02d5a57b154e | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
1d786647-6e24-575e-83dd-af9cfd67714c | note | ○ Attach: Post-pour Inspection Records
e3a31006-2992-5bd3-9ee2-9bfe0ffd0cd0 | note | Method - Verify
ab0deb0a-927e-5e4f-b819-4fc0419a22db | note | Frequency - Each lot
524ecabe-ef33-5a82-90c6-a53cb78a57bd | note | Category - IP
75d4ee7f-df08-55f5-9836-24481554391c | note | Responsibility - SE/Surveyor
020d7643-23a4-568e-8902-41694cbfd16a | note | Verifying Documents - ITP Signed
| checkpoint | 5.9 - Curing
e95ae1e9-7d58-58ef-8412-459cbb679961 | note | Reference - Section 703.10
d5e7fcdf-3082-5428-a67a-13bef639cf58 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
fa88f4ff-d9e1-59ae-a193-3d6ad488a8f0 | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
2f2d1947-c68a-5627-ad3f-31dff96ef14c | note | Method - Visual inspection
bf5a4477-b469-5418-9c69-6afaf1a9652e | note | Frequency - Each lot
00b3cfa8-dc43-574c-a99b-86e3b38b2e3e | note | Category - IP
c66f8918-c2c7-5749-9365-a5c1bfad44d8 | note | Responsibility - SE/Site Supervisor
e748b495-8b0d-5748-ac16-f42c7de73b41 | note | Verifying Documents - ITP Signed
| checkpoint | 5.10 - Joints
a779896f-6899-5b0b-a16d-75fdedcc2424 | note | Reference - Section 703.26
80c5b5e2-4dc0-5228-9e4d-6eb7570cb3de | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
92ac0610-2d6e-5e8b-84bb-8b8fb76364f6 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
358da6d6-6b6d-5b82-8de5-2424eef44aa0 | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
9ee4f16e-0cdc-5b46-8fa0-151f075ed77e | note | Method - Verify
6fa3aceb-1d56-5ea1-a757-87db0a9a617e | note | Frequency - Each joint
b7f5f983-5f27-5ea2-8851-fe9eb21e6387 | note | Category - IP
f96b1b58-ee0c-563c-a8dd-df87e2aa0d2c | note | Responsibility - SE / Site Supervisor
cef9a541-6501-5fed-87cc-b16ee5d91b61 | note | Verifying Documents - ITP Signed
| checkpoint | 5.11 - Protection of Concrete
cbdb2031-8efe-5e6b-bc52-6174c1a15bd7 | note | Reference - Section 703.27
59522271-cc56-5128-b3dc-ce6977ed1620 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
3aa7ded0-b8db-58a7-a209-25268905e03b | note | Method - Visual inspection
dac70034-3a05-5663-a2a5-92ea895aa3e0 | note | Frequency - Each lot
6b6211e9-97fe-5e94-b659-cc54b5cd217f | note | Category - IP
d68c4a23-dc36-5670-9b7e-cbe94e67442e | note | Responsibility - SE
663475ed-44f6-5f6d-869b-197d6888c915 | note | Verifying Documents - ITP Signed
| checkpoint | 5.12 - Bus Stop Kerb Height
9d5cf70f-8ab8-5026-86d4-46eb9f0c31c2 | note | Reference - DoT Handover Process
a6eeae5d-4b98-51fc-b63d-66f0f294a588 | note | Acceptance Criteria - Height of the Bus Stop Barrier Kerb to be between 150mm and 180mm.
bedd2986-6812-5f5a-9563-75345dc3df84 | note | ○ Note: Capture this in pre-pour checks i.e. formwork and post-pour checks
1263cc7e-18a8-54b4-9a95-361c699414b9 | note | Method - Visual Inspection
dfd2da32-317d-5d3c-a645-05d1f5afbd27 | note | Frequency - Each lot
75a9d908-535b-52da-a507-20f3004162f1 | note | Category - HP*
a8f252f3-91e4-5dee-a2fa-d8508b1894fc | note | Responsibility - SE
1fe5290b-1871-581b-8703-c5548a6bb2af | note | Verifying Documents - ITP Signed
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Backfilling
b53a095f-d246-51aa-b082-fa1667060f13 | note | Reference - Section 703.29
2f2595ad-bda7-5f53-b802-56149cd55fb2 | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
6f13a1d2-052c-5999-9fdc-da59caeb91bf | note | Method - Verify
5f50916e-2e10-527a-92dc-7e9b825acac5 | note | Frequency - Each lot
90529844-08a4-5186-a013-97adc13b6c11 | note | Category - IP
48163269-4f49-5333-8d97-c7431153a201 | note | Responsibility - SE
d4304b2b-66fd-5a51-b531-2cefd9a446ff | note | Verifying Documents - ITP Signed
| checkpoint | 6.2 - Cracking of Concrete
6532b6b1-cdd8-5d96-9633-323b28aed103 | note | Reference - Section 703.30
9ee5caf9-429b-52ad-a2fd-e5fbe3c38c6c | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
9b6c0d10-c759-578d-bddf-2c4d89c74dcc | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
9c6ea6b3-2429-5293-a530-0b401d77f5c1 | note | ○ Attach: Pot-pour Inspection Record
cf748b34-40af-5488-820b-28ba86a53986 | note | Method - Visual inspection
608e97c3-88ab-5916-a1b4-0ca02e0c3410 | note | Frequency - Each lot
5cc82f4f-ec72-5858-b19e-5863be1b2b9f | note | Category - IP
976a12d1-72d1-5a9a-aa7c-562eabe003f8 | note | Responsibility - SE
654837d4-0bd8-5d3e-b4b2-12b2804e4ce4 | note | Verifying Documents - ITP Signed
| checkpoint | 6.3 - Survey Conformance
faf20553-d8b0-51d1-896a-11e959a693ef | note | Reference - Section 703.15
3f8f4fda-5f51-5dea-a591-5c00ebf1c477 | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
b40b1afa-7d83-5424-b680-ee268c0b5f7f | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
5fd732f4-152a-5cce-9896-376d353cd52f | note | Method - Document Review
5793e36b-b360-5651-be76-27cda0844adf | note | Frequency - Completion of each lot
ce84a221-4ebb-5ce0-8e39-4c8cde130f10 | note | Category - WP
9e81b46a-917e-540c-9d22-f4bc9905cdad | note | Responsibility - Project Engineer/ Surveyor
31e95b2e-e34f-5228-b2a5-97b7b354a406 | note | Verifying Documents - As-built survey records
| checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
8f3dd12a-ec56-5da9-8788-7d0b5101f828 | note | Reference - MRPA Quality Management Plan
d11a228e-8117-5a4d-a3a6-d9cf1cf5fa79 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
093ead3d-53f8-565d-9578-7161d9dc6c52 | note | Method - Document Review
dad69e78-a114-5212-b553-d791ce7a3ee3 | note | Frequency - Once, prior to closure of this lot / element / Work area
577b29ef-7a28-5160-807f-e4ace71b2f39 | note | Category - HP*
40da50e2-ad7e-5d50-90e6-82ba3f8790e4 | note | Responsibility - SE/PE/SPE
e8799b54-b047-5cc2-943c-0ca609aab3b2 | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
e42d15d7-cb37-5c1d-9154-ff1c1a6636ae | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a6870f92-e3ae-5500-8f3f-1defed728f9d | textbox | Name:
57ddebda-7818-52a3-a53b-027cbc5a9598 | textbox | Position:
48bbf3cb-ac40-5ef5-b208-56f7de9559d7 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-026-CIV-Brunt-Subsurface Drainage (Supply and Install) |  | ITP-026-CIV-Brunt-Subsurface Drainage (Supply and Install) | 9e1d4f1f-3efd-4ca3-b032-7fdf366f8f87
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
b3395565-3a0b-5911-a9e3-5463ac5c62b6 | note | Document Title: ITP-CIV-Brunt-Bus Stop-Subsurface Drainage (Supply and Install)
f474b4e6-6883-5a4c-ac86-89dc729be028 | note | ITP Description: Brunt-Bus Stop-Subsurface Drainage (Supply and Install)
e9db8c05-8c92-5ebf-bad2-060132f07712 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
d8205acd-1d62-5c0b-80f6-5fcc03993ca7 | note | Discipline (e.g. CIV/STR/RAIL): CIV
2c1a8b98-56bc-5776-9ad8-ea305f307eac | note | Revision Number: 0
8ce9b793-bb01-56dc-bf07-c6a4fccfd7b4 | note | Revision Date: 28/02/2023
1949e694-0142-5d3b-b7fe-eab4674b0e49 | note | ITP created by: Jason Lee
8a7cad72-a57e-5fd9-b6df-349ef0c2875a | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
2400a9f6-05f1-549a-9fe8-3dc749147088 | note | Reference - VicRoads Section 702 (May 2019)
| checkpoint | 1.2 - Non Dependent
c29098b3-51f9-5447-ab53-fa7b04206d50 | note | Reference - VicRoads Section 204 (Dec 2015)
| checkpoint | 1.3 - Non Dependent
8033d78b-3768-5675-895c-8cdda97777f7 | note | Reference - VicRoads SD1611
| checkpoint | 1.4 - Non Dependent
4545ab06-1079-5596-9028-f9c0c525ad33 | note | Reference - VicRoads SD1051
| checkpoint | 1.5 - Non Dependent
0f76ee56-4c4c-5bec-ae17-d13fbd88fcc9 | note | Reference - VicRoads SD1631
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Drainage Pipes
04b0f4ee-072f-5267-8071-8773c006eb03 | note | Reference - IFC Drawings Section 702.04
e1c8f5b4-8f95-5575-87c8-badc56584bfd | note | Acceptance Criteria - Subsurface drainage pipes:
3704b23a-8c79-52d1-b54c-9fd85fb02795 | note | ○ Category 1, 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
bfd78149-374f-5553-9603-df9f7e5182dc | note | ○ Attach: Material Approval Ref Nos
0f1e3c36-0bbd-5e35-8c9c-477090b75b89 | note | Method - Verify, Document Review
bb4c30ae-77c3-5f42-9b00-963ee71c2996 | note | Frequency - Each Lot prior to work start
e12c95c9-27c1-56f3-816e-9b8b8b3439a0 | note | Category - HP
54d26d63-98e1-547b-9594-1fb763b6337c | note | Responsibility - Nominated Authority
735604ed-8094-5e1a-8d75-85647e05acbd | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Granular Filter Material
633f1e8c-7381-5606-8218-c47efb980413 | note | Reference - IFC Drawings Section 702.05 Table 702.051
d64cd33c-890d-5d77-80c1-3716aedaba49 | note | Acceptance Criteria - Granular filter material:
e6d241a5-0698-5b3d-9c53-0550e76ea3c2 | note | ○ Filter sand to be as per IFC drawings and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
e71474ff-cbb5-5258-81f9-1b6336791c67 | note | ○ Attach: Material Approval Ref Nos
0e206454-c20f-5f21-9d53-8dddd5d17eff | note | Method - Verify, Document Review
f1e078d5-94b4-5b21-a9f1-53d2f1ac4dbd | note | Frequency - Each Lot prior to work start
cf7fecfb-c43f-5e67-bc18-f0b9498343bf | note | Category - HP
b70c9767-bb45-5fa0-ad6d-ee9411c81967 | note | Responsibility - Nominated Authority
00252c3e-25f0-56f4-ab5a-5ef755433199 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - No Fines Concrete
8960fe11-dcf6-59da-8182-1e1e3374e5dc | note | Reference - IFC Drawings Section 702.05
7215b38c-473b-506c-a33a-c6f5ffd6aa41 | note | Acceptance Criteria - No Fines Concrete:
eba097b4-5988-5213-8ec0-ae3abe5fcfe0 | note | ○ Shall comply with 702.05 (e)
8d82463a-e1c8-5fb6-95ba-4661d2567a19 | note | ○ Attach: Material Approval Ref Nos
ebec0b73-4d6f-5f10-84bd-a45584111603 | note | Method - Verify, Document Review
f154c029-3188-5c3c-bcc6-b2e07169cc17 | note | Frequency - Each Lot prior to work start
e2bc0348-3a15-5a4a-b0ea-f61a671910f2 | note | Category - HP
dd64800e-c706-5471-b78a-3cdde818b8e0 | note | Responsibility - Nominated Authority
2de116d6-d7c3-50b4-9270-77f96ce079a0 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Geotextile Filter
dacd7574-fcf8-5603-bc1c-f9c3892819a7 | note | Reference - IFC Drawings Section 702.06 Table 702.061
4751d3d1-f4a2-5cca-8aae-dbc22bdab569 | note | Acceptance Criteria - Geotextiles:
0a4bdc81-db90-5f23-99f2-35639cbc4764 | note | ○ Shall comply with 702.06
f595cbef-7b94-54d8-8dbf-d9a54df14539 | note | ○ Attach: Material Approval Ref Nos
0669068d-736e-5fe4-914e-430829da2d65 | note | Method - Verify, Document Review
d25939c8-a39d-5b6f-b1fe-992c28f5ff13 | note | Frequency - Each Lot prior to work start
d9102875-d8e7-5288-9ad6-831ebba392c8 | note | Category - HP
2aa41455-3ae6-57c2-ab3b-97bbd3979162 | note | Responsibility - Nominated Authority
e10ad554-3a80-5489-9347-bf38e24c7ee5 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
959f8a2c-0edc-57e9-9a62-75f9d4ad250e | note | Reference - IFC Drawings
8e3015b5-a62a-5332-8f61-056382e5816d | note | ○ SD-1051
f755239e-d27c-51d0-be53-194a6d72ce8e | note | ○ SD-1611
796e55ad-96e2-5680-8b44-deb8c26b8f7c | note | ○ SD-1631
a4df8900-3c6a-53b9-8304-b2ef5c5464cf | note | Acceptance Criteria - Subsurface drain pits: shall be Type S1 (as per SD 1611).
2dfaafab-2b45-56b0-9c83-c04e3b5560a6 | note | ○ Pit Lids shall be: Type M3 circular lid (as per SD 1051) for Type S1 pit.
370484e0-bc3b-52f4-8c11-0658028fd51f | note | ○ Flushout risers: As per SD 1631
a5603778-f5d7-5b8d-b757-c92cf82bbf26 | note | ○ Attach: Material Approval Ref Nos
1ce29ec8-b67d-51cb-a5d5-88109b838e96 | note | Method - Verify, Document Review
e99d77b9-bb2c-5dbd-8a64-675b307095e9 | note | Frequency - Each Lot prior to work start
73a2e2c4-430c-5971-915e-6b2bcb82afa8 | note | Category - HP
df8d4cff-1247-5f11-a093-279ac368ad1a | note | Responsibility - Nominated Authority
878afe15-c3d9-5547-b3e6-dc0a60ecf269 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documentations
| checkpoint | 3.1 - Check for correct documentation
4394027f-5cb7-5eff-bcaa-525563181bed | note | Reference - IFC Drawings
e3165533-413b-586b-8e02-eafa3bd47138 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
416f5b1f-508f-5f83-a29e-0842dd5fc66f | note | – using the correct and complete set of drawings
49dbbb7b-aa81-5eee-923e-5742c4f988cd | note | – all drawings are the latest revision
dd9a92bb-22db-5dd9-be1f-ada5f924de40 | note | Method - Visual inspection
ce5887c7-cabb-5e67-bff8-b82987cca048 | note | Frequency - Prior to commencing any activity
21cab3ba-a4ce-5539-ace4-8860721ac7ac | note | Category - WP
4e595c86-6e51-5921-9db5-525de900ad8e | note | Responsibility - SE/Site Supervisor
b2bc93f9-91d3-54af-a03c-2bf2a553aede | note | Verifying Documents - This ITP Signed-off
| checkpoint | 3.2 - Methodology for compaction of Granular Filter Material as Backfill (where applicable)
1d7bd6e7-8da0-5dd8-b3b2-1f4ef5a33296 | note | Reference - WAP-252
b5db7353-790e-57e4-92c2-95abe6ed9acf | note | Acceptance Criteria - Ensure that all workers/subcontractors understand the correct method for the compaction of the granular filter material.
a667863b-b5df-5145-b28e-adcc7ec480ab | note | Method - Verify, Document Review
f8d68acf-bd0f-5c7b-a2b2-3b41a0ad37bc | note | Frequency - Prior to commencing any activity
f870b312-7292-5aa6-b047-72cc5d4bfb1b | note | Category - HP
290afb04-a008-56a3-938b-0b2e01909f06 | note | Responsibility - Nominated Authority
e442cce2-9424-5798-ac4c-5ef39da35403 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Methodology for placemnt of No-Fines concrete as Backfill (where applicable)
7b135730-aead-5c07-92f2-ef33378d9f6c | note | Reference - WAP-252
874e59f2-34f8-58c1-8cd6-a4744e368513 | note | Acceptance Criteria - Ensure that all workders/subcontractors understand the correct method for placing no-fines concrete to prevent segregation and slurry formation at concrete surface that may block water passage into filter material.
0de0f051-cca1-5596-96c5-221f466ba865 | note | Method - Verify, Document Review
2aa14198-f017-5f56-940b-0e398b676c84 | note | Frequency - Prior to commencing any activity
2bd6c79a-e5c8-5600-924a-376166450bf7 | note | Category - HP
0a1e9426-34d3-5f80-9926-b945ae66e593 | note | Responsibility - Nominated Authority
0c72b873-bea1-5c9b-a3dd-57979a9cbd47 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
7bf0abe4-9d9d-5810-b1cf-06221f9c9aa9 | note | Reference - IFC Drawings Section 702.03
02f7fa51-6554-5d05-bbe8-b7648994b96a | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
535943b5-cbba-5f70-88ea-94861f682599 | note | Method - Visual inspection
c9e7bbbd-e725-5501-a1ea-d5af04c080b5 | note | Frequency - Each Lot
e4a85799-1a52-5455-9b57-23331ac7a6f5 | note | Category - IP
0f5759ce-8fb8-5680-a7fe-f9e8bf7cc5c5 | note | Responsibility - SE/Site Supervisor Surveyor
79b9b1ca-5431-50ba-8647-5c5338691dbe | note | Verifying Documents - This ITP Signed-off
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Trench Excavation
021723f2-237d-52e8-b07d-84016718cade | note | Reference - Section 702.08
f7115049-5ace-5548-a512-cb4c44b77d65 | note | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
ca22ed6b-818d-5b23-ab3b-82f9757b1df2 | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
7aea9e49-ae94-56a3-a636-29e9813404af | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
c70e20e2-5dd3-5c48-90d2-1af9596ff686 | note | ○ The base of the trench shall be inspected by a superintendent to verify compliance with 702.08 prior to placing beding in completed excavations.
56d60bef-3f99-5d96-898d-1019a40e49dc | note | Method - Visual Inspection
b2c47000-caaf-5134-895f-28d28b835e8c | note | Frequency - Each lot
f76b9329-1dd2-5512-9347-5571f0372e4b | note | Category - HP
72f437ad-938f-566f-955a-84275adde39d | note | Responsibility - SE, NA (Nominated Authority)
d6c37153-40f3-53bb-8e9c-b74292d2c5d7 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Placement of bedding
4ed05d57-0dcb-5d93-bbfc-8d9278cde37d | note | Reference - Section 702.09 c)
5c8de953-8862-51b2-b848-6fa1e9393e64 | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level.
a9ad2c87-3844-50bd-98e0-023e8cb42257 | note | ○ Attach bedding material delivery dockets
f6771e2a-4100-5df4-a5b9-3b15665c6a49 | note | Method - Visual inspection
e7128135-a4fb-542d-b41b-84f5131a80fb | note | Frequency - Each lot
5ac40b52-4ebb-5411-9007-3ccc92ced2e2 | note | Category - IP
323b117a-20a3-58a9-95a3-7311c0627e2d | note | Responsibility - SE/Site Supervisor
5565e797-0161-56ad-9b2d-15e75789a656 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.3 - Pipe and Geotextile Installation (if required)
b4d9fca6-72ad-5a07-a3cf-9fcf2a87e036 | note | Reference - Section 702.03 Section 702.09
0b9d3de2-86fd-5797-ba25-ce2ac2621dcb | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding and held firmly in place. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped in accordance with specified requirements.
91c6a304-c9aa-566b-b6c8-001710c3d38b | note | ○ Attach Suburface pipe and geotextile delievery dockets (if applicable)
86c3b1c1-77b6-5278-82cf-05f87fd98734 | note | Method - Visual inspection
96f42b24-de96-52b2-9af2-00937d531614 | note | Frequency - Each lot
1ed7cd32-1e83-51b4-b989-843ee8106312 | note | Category - IP
17f65d6c-ec78-5fa8-b467-3a495406f903 | note | Responsibility - SE/Site Supervisor
f41aedfc-f159-542f-bc11-13af9b64a879 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.4 - Backfill Installation (Granular Filter Material)
215f28a9-8aa1-5116-ac68-d6a8532a6570 | note | Reference - Section 702.09 (g)
ff9a1bdd-23ab-533c-8c7a-1380c8834165 | note | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
0cc74d39-f944-5b2a-9eea-d5d5e1c4ebf5 | note | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
3162047d-8353-535b-9b9c-4d9ad3cbe610 | note | ○ Attach Backfill Delivery Dockets
43fa7c4a-db78-54e0-a411-25f406317606 | note | Method - Visual
8f402814-4f8f-5f5d-a584-47efca6ed81b | note | Frequency - Each lot
65a0f132-6ffb-554b-b126-d736e2921120 | note | Category - HP*
53fe7a00-9ce3-5c62-95f5-5e9c3e5a658c | note | Responsibility - SE, NA
602c2602-1bb2-5b1f-a054-79eed78c5776 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.5 - Backfill Installation (No Fines)
3df65192-1619-5dce-a460-3d88ce4af660 | note | Reference - Section 702.09 (g)
d4c88d80-3611-5aa9-8700-8ab94534cf04 | note | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing.
ff27146d-1111-59a9-a0b8-5fa96862b78e | note | ○ Attach Backfill Delivery Dockets
9407dd1f-76d7-56e7-b52c-31e0618ddf2a | note | Method - Visual
5f3237ff-8b90-515a-9d8e-9c2b5f84a69a | note | Frequency - Each lot
4982544e-0de7-5d8e-b98e-0a85ed98e0df | note | Category - HP*
681c7c21-d3e2-5f1a-a5be-64d14bb79ae1 | note | Responsibility - SE, NA
67e674e8-529a-53ee-bf7f-c2a87ce5b820 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.6 - Install Pits and Flushouts
85a8e825-e267-5d14-bc27-6cfd6ac53734 | note | Reference - Section 702.10
95908e9f-3939-5d31-b8ed-08f3eb26f577 | note | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run.
47c658b6-49fb-5d42-b3af-7be761791416 | note | ○ Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings.
8f0ac1b6-9e5c-5918-a1d4-0627bcc9e8c1 | note | ○ Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
1077798d-908f-58e1-9ac5-b7e3d21af43b | note | ○ Attach Pit and Flushout Delivery Dockets
d6d94ab4-bda0-5e14-a200-5a063ab5d8d2 | note | Method - Visual
90cfe745-16ca-5419-af29-75dbafcf93c5 | note | Frequency - Each lot
23824176-d99b-59d8-ad54-530df8b0dfb1 | note | Category - WP
e1af612d-d5e5-52ff-9a69-316ffce0459f | note | Responsibility - SE/Site Supervisor
7ef9892c-5cfd-5e18-ad6e-66a5f0cba26d | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.7 - Marker Points
aff4db2e-8870-594a-bec2-2779c4e5d6da | note | Reference - Section 702.11
e0a83e99-a752-5b02-9cc7-994a63b8be5b | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
e9c6528d-ee2e-5968-bddc-e00d174c99b4 | note | ○ Attach Marker Post Delivery Dockets
2af24377-9e06-56ee-8e5f-1d688b684f3f | note | Method - Visual
3146938d-0f4c-5e75-87dc-b5b35aef08ef | note | Frequency - Each outlet
7d69c59d-0e25-5afb-ab50-540215c69aa4 | note | Category - IP
da54708b-a4b5-5ac0-9019-85f769b34816 | note | Responsibility - Supervisor
4db1bf5a-691c-514a-b035-090dd28affd1 | note | Verifying Documents - This ITP Signed-off
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As Built Information
4fe74e23-00f4-5f26-87cb-9c7c60d83a97 | note | Reference - Section 702.03
dc7df969-9d9d-5b5d-a90d-2b9bc9466768 | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
8d1a693e-6cad-5e08-be1e-ff7a8bdd7150 | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length.
15987b07-0456-57d8-8802-e248495faf41 | note | ○ Attach Survey Conformance Report
36afaf3a-bd12-5acd-8c52-c9e863e53083 | note | Method - Document Review
cc018ce2-60bb-56a3-aafd-7bb35bdd7bbe | note | Frequency - Each lot
c8ff3d80-e905-58c8-b525-7fbb7a416d44 | note | Category - IP
bfd13f01-3592-5caf-a2eb-2908bc18280b | note | Responsibility - Surveyor, SE/PE/SPE
d05d0c39-a5a7-5552-8487-ade48b18290a | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.2 - Flushing
43fbfa24-c70b-537a-8108-eb7042d41e1b | note | Reference - Section 702.09 (h)
5bae2049-4aea-5700-995f-9d0bc57ee7bf | note | Acceptance Criteria - Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
9759caea-6ca6-5835-adc9-bd3457e14cda | note | ○ Attach Flushing Tests Records
f04646e8-086f-580b-a24a-9b01118575d4 | note | Method - Document Review
b55ade86-34be-54ec-b69a-864c3d879820 | note | Frequency - Each lot
53a8451b-55ad-577d-b9fa-6c9ce060b801 | note | Category - HP
864b7fb1-77c8-5414-b316-d74146969ae9 | note | Responsibility - SE, NA
c337baf6-510a-5830-8ed3-7f8e69f994e3 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Inspection of Subsurface Drainage - CCTV
391b1bba-9b7a-5b60-a823-644a0b6f2660 | note | Reference - Section 702.09 (i)
f71d4619-8c45-5006-abdf-5a2f6caa3ba2 | note | Acceptance Criteria - All subsurface drainage lines shall be inspected, after the flushing test as per clause 702.09(h), and prior to placement of asphalt by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is free from obstruction and to check for visible signs of defects.
0afd8870-bae6-558b-9aa4-27419dbd8c27 | note | ○ Attach CCTV Inspection Record
5dc9be2b-ad70-5bd0-baa8-638a379d46bb | note | Method - Document Review
ab0121d1-0039-519d-9d44-265722e5826e | note | Frequency - Each lot
7683439a-10df-5bca-831b-9eb82c453d3f | note | Category - HP
2b4b2c5a-6217-576f-9dfa-3bf2894d9b33 | note | Responsibility - SE, NA
af8e374f-627a-51fc-ba3a-ec0c6fc1782c | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
64f3495d-e591-592a-9618-e621541cb5e2 | note | Reference - MRPA Quality Management Plan
828fc54c-f2ec-5a8c-9670-8070921e6cdb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed in CAMs.
62ed4e9c-54d8-5ee8-a10d-f292a9a739f3 | note | Method - Document Review
d914075e-6666-5eea-be30-9dd549f257d7 | note | Frequency - Once, prior to closure of this lot / element / Work area
6719151b-73ec-5c47-af9c-64457f350a68 | note | Category - HP*
312e563e-d80f-5648-80aa-5e7ebebf6146 | note | Responsibility - SE/PE/SPE
14639952-de68-5044-bbb6-10f933df6824 | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
393652fa-f944-5342-9df3-8a6a486083e0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
b2fe1be0-83ee-5221-8eea-1706ab485015 | textbox | Name:
7b4eae08-0075-5469-b3c3-ffe5c078fcee | textbox | Position:
9071c45f-3936-57b0-a08f-2fdb6371fb58 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-027-CIV-Brunt-Signage (Supply and Install) |  | ITP-027-CIV-Brunt-Signage (Supply and Install) | cbe034e6-3d34-47dd-939a-093ede516809
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
bfeef2f0-bca8-51d4-89a0-0c41fd27baca | note | Document Title: ITP-CIV-Brunt-Signage (Supply and Install)
c1621b2b-7c66-571d-ac26-e9eee2c231fa | note | ITP Description: Brunt-Signage (Supply and Install)
076c1bc3-5618-5b2c-a5e4-d57a8425a33a | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
dc099d8b-36a0-5323-a1b5-1917f513b7ec | note | Discipline (e.g. CIV/STR/RAIL): CIV
7f71c04d-b0dd-5417-84af-53202e7780c1 | note | Revision Number: 0
355e4ddb-bea2-5b61-b7c4-5760da31dce2 | note | Revision Date: 28/02/2023
655a326f-582e-525a-96f5-db3230626464 | note | ITP created by: Jason Lee
fb918bda-1e6d-5c7b-87e2-42f41c6013b6 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
b74c2cf6-e90a-52c1-9664-963d716ecb13 | note | Reference - VicRoads Section 860 (Feb 2023)
| checkpoint | 1.2 - Non Dependent
aa063e7e-0d66-5124-803b-59e1075e63b1 | note | Reference - VicRoads Section 714 (Feb 2023)
| checkpoint | 1.3 - Non Dependent
df42a309-3bed-52a0-a30d-4dbb28142daa | note | Reference - VicRoads Section 703 (Aug 2021)
| checkpoint | 1.4 - Non Dependent
b705eb3e-c163-553d-bf70-3e8a2eba60ce | note | Reference - IFC Drawings
| checkpoint | 1.5 - Non Dependent
85bdbd9f-6220-5a99-86d0-3e66852ac8a8 | note | Reference - AS 1742.2:2009
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Manufacture & Supply of Signages and Posts
7cec4bbb-ef4a-50c1-b13d-d28f5d3289bc | note | Reference - Section 860
a67fe110-11b4-51a7-b260-0026b76c034b | note | ○ Section 860.06
fafaaf18-fb39-5958-88d6-e21ce810e582 | note | ○ Section 860.07
69ee7ff5-b238-5ae4-9cf7-5806d00a2307 | note | ○ Table 860.071
e847a3fe-32e8-5baf-93b9-2fcedc47dec0 | note | ○ Section 714.03
fda09eb7-f78f-53ff-be39-fab14d65e5cc | note | ○ Section 714.06
88810b92-45ce-567d-8afe-c7c7db6324b5 | note | ○ IFC Drawings
20c49c9c-e780-5aeb-a991-7a9bb03fce2f | note | Acceptance Criteria - Signs are to be manufactured in accordance with Section 860 and IFC Drawings
20d23df5-7400-5cdb-896b-76f8ac559289 | note | ○ Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071.
a6b87b97-487b-5749-b42b-8c4852842e67 | note | ○ Packaging and Storage of Sign to be in accordance with Specification 860.06.
9cceac4f-40f5-571b-b980-2a3dd57f41c1 | note | ○ Signs and components shall be handled and transported so as to prevent damage.
c119eab5-6b59-55ef-a8b7-54571a8852e7 | note | ○ Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer.
9bbe5a09-b455-583d-ab27-729e9bb9de9f | note | ○ Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either:
94f62c2f-4657-5908-9a9e-1d58cbd9f7c9 | note | – Hot dipped galvanised; or
04f0d2f6-b4fe-5706-9925-962235cb6d4c | note | – Pre-galvanised prior to forming
71e2e54b-5241-5987-81ed-69743fee6186 | note | ○ Attach: TeamBinder Material Approval Ref No
48a56d57-3694-57ab-a323-90b734d53b10 | note | Method - Document Review
c4e44512-d428-5466-8adb-dbc697274271 | note | Frequency - Prior to works start
b635fe1c-e337-5929-b550-97a033431668 | note | Category - HP
e55c9c93-97b4-50a4-9b43-16087623ca7c | note | Responsibility - Nominated Authority
e4a3dc92-c560-54d3-beb8-4bef2a0ae355 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documentation
| checkpoint | 3.1 - Check for correct documentation
7f47e098-3ea7-56be-97df-c02df4bba0c9 | note | Reference - IFC Drawings
368b94ef-3188-571e-8875-0289577d3810 | note | Acceptance Criteria - Ensure that all employees and sub contractors are:
747f9daa-7fb6-5ba6-9a17-1fd8bf521a2d | note | – Using the correct and complete set of drawings
b944ee0e-1499-543d-b1cb-084f5656fd96 | note | – All drawings are the latest version
3344164b-9516-5ce0-b7cc-bd03ec34796b | note | Method - Visual inspection
cfed2639-5142-525a-bb5a-475396e193f5 | note | Frequency - Prior to commencing any activity
3f02c1c5-f604-5c36-90b1-c17099fc635a | note | Category - HP*
8c9c732a-7d74-538c-81cb-269d710b2196 | note | Responsibility - SE/Site Supervisor
c4fe3b8a-56a0-5791-9da8-9765f6a2fe84 | note | Verifying Documents - This ITP Signed-off
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Setting Out - Position of Posts and Signs
427eb93c-6bb1-5a54-b44a-c3c017b1e27a | note | Reference - Section 714.06 IFC Drawings
7784acbe-af4b-5ce2-b371-a98e540c66f0 | note | Acceptance Criteria - Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Superintendent before the erection of posts
ac42b444-e9b7-5529-8e7c-da15058dc25b | note | Method - Verify
344c7924-14db-554c-ad6a-d907152071cc | note | Frequency - Prior to start
fe1f8cd0-13dd-5c14-adb0-9267db537d2b | note | Category - HP*
42e44d2f-549e-5c6c-9526-765401335920 | note | Responsibility - Surveyor, SE/PE, Nominated Authority
7389a70d-22da-5b4e-87ac-8bf3116c3c84 | note | Verifying Documents - This ITP Signed-off
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Foundation
5dd9840e-45da-5bd9-92c8-6cf35b665479 | note | Reference - Section 714.06 (c) Section 703
96a19468-e452-59a0-a76b-3ae6c5db53a7 | note | Acceptance Criteria - All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below:
88e3e050-277a-57be-93c6-8f19af2feb9e | note | ○ Post sizes 32mm and 50mm nominal bore steel = 225mm diameter
c4a77849-0ac7-5534-a3d2-15f9e1eb49da | note | ○ Post sizes 80mm to 150mm nominal bore steel = 300mm diameter
422545f7-fd93-50f3-9ae2-73431d2fc52a | note | ○ Frangible hardwood posts 180mm x 100mm = 300mm diameter
843bfbf5-8bd6-579d-a208-7e842757f96c | note | ○ Concrete shall be 20MPa and complying with requirements in Section 703.
c98abbf2-b88c-507c-9e54-3425d18aca4e | note | ○ Attach: Concrete Delivery Docket
11e5f0a0-0a3a-5547-b81b-53983548a6ac | note | Method - Measure, Visual
68dce87b-5685-5e1d-880a-f35068389a4e | note | Frequency - Per Lot
43548a84-58aa-5c37-88b0-5b8b64745a86 | note | Category - HP*
5678d170-60fe-578f-9a08-3cab5d12e47b | note | Responsibility - SE/PE, Nominated Authority
ee70e2ea-f524-525c-80df-5a592b981723 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.2 - Post Installation in Sockets
9dede390-23ff-5810-b0b7-3b40344becc6 | note | Reference - Section 714.06 (d) Table 22 of AS 1742.2:2009
157aa50a-739b-51e1-80dc-c34b7fddce65 | note | Acceptance Criteria - For Post Size 32mm Socket size to be 50mm Nominal Bore Tube
cd81a36b-ee34-5f02-9186-df9831b10854 | note | ○ For Post Size 50mm Socket size to be 65mm Nominal Bore Tube
a54ad967-7dee-5db8-9b7a-52c15417d6f0 | note | ○ The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface.
08b6ab0d-e432-5b36-a6ce-bb1d32aea5db | note | ○ The sign post must penetrate a minimum 450 mm into the socket.
50ef56b5-bbcf-5ee2-a65b-6524c9ad2630 | note | ○ Depth of the socket should be as per Table 22 of AS 1742.2:2009.
e9a149dd-035d-5487-a815-c84172b0fd88 | note | ○ The sign post should be securely fixed into the socket by an approved vandal-proof method.
35b4a040-775d-5707-956d-6da6ce082610 | note | Method - Measure, Visual
a772a573-2735-5d72-b69c-e21dd848bfff | note | Frequency - Per Lot
0c189354-6885-5c58-a855-c0f0fd56b405 | note | Category - IP
a83cb3c9-7140-55d7-ad55-e85a0245379c | note | Responsibility - SE/PE
2c4e8b1b-f2c5-56fc-9221-30ff7a2dcd8d | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.3 - Backfilling of Post Holes
1f517259-97eb-5509-97d8-ff01fc86291f | note | Reference - Section 714.06 e
1fdacb4a-f599-583e-942f-12683cf42946 | note | Acceptance Criteria - 32 and 50 mm Nominal Bore Steel Posts
538af8f3-4022-5d1f-aaaf-0d7a5e01e027 | note | ○ Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa.
4f92b166-46e9-5ad5-b0cb-74dc5aebcf04 | note | ○ 180 mm x 100 mm Frangible Hardwood Timber Posts
2151b9c7-37ab-5bff-9372-63ed3d44db30 | note | – frangible Hardwood Posts shall be erected in accordance with the drawings;
5aaaa807-a337-5a90-bcd1-56df8962ec20 | note | – post-holes for frangible hardwood posts shall be filled with a mixture of gravel and cement (4% by weight)
906b72c1-d70e-550d-8847-114a6528357e | note | ○ Attach: Delivery Dockets
4c9f7dc3-611b-5eb7-bcd9-ea320139420f | note | Method - Verify
e100148b-64d8-56d1-9d74-cf48a884b7e9 | note | Frequency - Per Lot
5fab3570-9edb-5fe5-aae4-a1f991baa42e | note | Category - IP
24ffe9b8-91ae-5ef9-a7c4-5bd1fc15bf58 | note | Responsibility - SE/PE
fe160453-4165-5837-b3db-9c688da327b9 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.4 - Sign Fitting
ecd41049-35e2-5906-8cd1-3721cd81721c | note | Reference - Section 714.07
fd9d8c3e-0039-5e0b-b329-3fb249a036ad | note | Acceptance Criteria - Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows:
7e4b02c7-9bd8-5822-a158-4b85a39e3325 | note | – Signs up to 200mm in depth – one fitting per post
a6477a7d-d139-557e-9c79-5e06114844bd | note | – Signs 201 to 900mm in depth – two fittings per post
4cbe527c-e325-5c1c-bf16-d54450d0b96c | note | – Signs 901 to 1200mm in depth – three fittings per post
dd78d408-e5bc-572a-bc6c-5c02af48f32a | note | ○ One extra fitting provided per post for each 400mm increment or part thereof above 1200mm.
6ffc6e10-c657-50d4-a116-ab95f8c89041 | note | Method - Measure, Visual
6f990118-da00-5cd6-b015-ac5abc01546e | note | Frequency - Per Lot
ee0a9e94-99f1-54d6-8edf-a0afd1a0953f | note | Category - IP
4b9cae86-fb96-5a25-ba85-bff30d349095 | note | Responsibility - SE/PE
a3324cba-db44-5f38-ac65-5aa901478073 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.5 - Mounting of Signs
7f09b195-a1b5-544a-9055-8fba4ff32ef0 | note | Reference - Section 714.07 (d,e,i) IFC Drawings
a2e2afbf-654b-5cf3-8f93-ec2a8c949c1f | note | Acceptance Criteria - Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground
5f411997-cfe3-5cbc-86d2-0a31e78dff5c | note | ○ Signs shall be positioned in accordance with the following tolerances:
983672af-ab36-51a8-8208-d90c56a89677 | note | (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign;
ba2f2b13-fcae-587f-9b7c-a864b5565eab | note | (ii) +/-100 mm of the pegged sign location or specified location.
13591091-99f7-5c2c-931b-cc2fa8d716bf | note | ○ When a sign is to be mounted on frangible posts on a cut batter having a slope steeper than or equal to 2:1, the mounting height at the shorter post may be reduced providing that:
6913b740-f478-5c09-990d-df5ba8e9c09b | note | (i) the uphill corner of the sign is a minimum of 800 mm above the ground;
73de89ae-d70e-5a39-a419-06fe9441ce63 | note | (ii) the sign at the longer post is 2200 mm minimum above the ground.
95a5ddc3-00ad-5451-ad3e-b505e62a85bb | note | ○ Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰)
17fee63b-08bb-5bc9-90ea-e0f47e44991f | note | ○ After erection of each sign, all stiffening bars are to be removed.
3c018456-e3da-5181-a0e6-d44ff5571c2f | note | Method - Measure, Visual
22f8fe07-c7e0-5707-85aa-9a66a7f72eab | note | Frequency - Per Lot
887670af-c03d-505f-b2b6-d5720d662eb7 | note | Category - IP
10e9052e-8ed6-576c-af9c-b2bf3be1e7f6 | note | Responsibility - SE/PE
6a3a994e-6e4e-5a3f-b993-3830d8c90339 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.6 - Masking of Signs
b6d183cf-4718-5bda-b294-33b4954e4877 | note | Reference - Section 714.08
2f3beb93-7fe8-59af-bd4f-75bbbdb203f8 | note | Acceptance Criteria - Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign.
e12a82c0-d3aa-58eb-8dde-e2b7d29b643f | note | ○ Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard.
fbcd658d-0d93-527f-b308-bb6f93915840 | note | Method - Measure, Visual
2b786447-a02f-5842-bc3e-19da575c58c7 | note | Frequency - Per Lot
b6503b80-b926-5bca-a194-f6d062cc66d1 | note | Category - IP
bb0a577c-8f1f-5829-befa-0b15d87efc68 | note | Responsibility - SE/PE
2266c127-d4d2-5750-929f-021bb3aaaf9b | note | Verifying Documents - This ITP Signed-off
| section | 5. Post-construction / Post-installation Activities
| checkpoint | 5.1 - As-built Survey
49ee943e-d0c4-5be6-b68c-a4794d74f353 | note | Reference - Section 714.05, IFC Drawings
d84640b6-965e-5f7d-9955-adbe16d453b8 | note | Acceptance Criteria - Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714.
b94c3bd2-2d19-5b83-b187-bfe7a36eefa1 | note | ○ Attach: Survey Conformance Data/Report
36add929-d674-5969-8494-4c3a30b613f0 | note | Method - Document Review
b93a3999-5c78-584f-89fd-c16c6e12deec | note | Frequency - Per Lot
a8869624-b472-5afc-8a62-8ae9d7a8659b | note | Category - IP
fbb72c22-4a11-53e8-9624-b170f3cd4712 | note | Responsibility - Surveyor, SE/PE/SPE
a8943292-22a5-55b3-9529-8cf3017ae918 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.2 - Non-conformance Report (NCR) Closure
f5361328-afa5-575c-9b8b-bf39a6a879d2 | note | Reference - MRPA Quality Management Plan
067cab8e-c8e7-5893-aea9-5c066a1be848 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
0f349fd4-e496-51eb-bf72-eeef3e23e635 | note | Method - Document Review
edac4b90-5f86-5818-a66e-b70f55a3b44d | note | Frequency - Once, prior to closure of this lot / element / Work area
b5fa9945-7b73-598f-aee3-badb44939395 | note | Category - HP*
be999e6a-08ff-58ac-b276-7a913ab73c2c | note | Responsibility - SE/PE/SPE
9f3b2427-9b18-57f2-bbf0-77480454e22b | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
70502c38-226e-5b91-85b0-4a649945ae17 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d0b3ebed-1144-5550-82cc-5f10be65d9a0 | textbox | Name:
f8ab2061-aec1-5209-83c6-46b0ea2611ef | textbox | Position:
5ba1a661-9098-5438-9ea0-624ba5ec1313 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-028-CIV-Brunt-Tactile Indicators (Supply and Install) |  | ITP-028-CIV-Brunt-Tactile Indicators (Supply and Install) | f3b842f6-7be3-46d2-af4f-93c74f0ea49e
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
8e75e9ca-efe9-5bb5-8f8d-802257850201 | note | Document Title: ITP-CIV-Brunt-Tactile Indicator (Supply and Install)
54427697-c1bc-58c6-ac84-cc4b4bd8dc75 | note | ITP Description: Brunt-Tactile Indicator (Supply and Install)
25beff45-fd7c-504b-b9d2-5b68817b91b4 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
e9165758-7893-5402-bede-d10f343a3d07 | note | Discipline (e.g. CIV/STR/RAIL): CIV
01dc2020-46c7-5280-9dd7-4364fa703a74 | note | Revision Number: 0
12bc21bb-7fec-5d0b-ab1b-e70edae47f90 | note | Revision Date: 28/02/2023
b6d168fe-17ee-5e12-9146-cb47de98611d | note | ITP created by: Jason Lee
277e75e1-7250-50df-ae5c-b771df7eef66 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
3e905e4c-c773-5792-ba87-f3bdb388e5df | note | Reference - AS1428.4.1
| checkpoint | 1.2 - Non Dependent
14580d31-dc6a-5206-b020-51da7449352b | note | Reference - VicRoads Section 160.A9
| checkpoint | 1.3 - Non Dependent
17ae885f-25d3-5c78-aff7-7bce3f68902b | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Material Conformance
422e4587-b563-5f79-945b-31c2b214af81 | note | Reference - AS1428.4.1 Section 2.2 & 2.3.1
bee8700c-08c1-5eaa-a1a7-6254966ab456 | note | Acceptance Criteria - Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1
952e1e67-3be0-5c45-bf59-829280f7250c | note | ○ Attach: TeamBinder Material Approval Ref No
077ee115-69ca-5c84-9bdc-427b95f7214b | note | Method - Document Review
7a266cc6-4d6f-596a-b271-99f683de9d9a | note | Frequency - Prior to works start
5c2109f9-51ed-5dfa-a870-531b6cb82dc5 | note | Category - HP
8aed34b8-fe8c-53f3-8622-5ae77a6a17b0 | note | Responsibility - Nominated Authority
2c6f99ad-a50a-59e2-83d3-98e50eddab26 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documentations
| checkpoint | 3.1 - Documentation Conformance
84ce62df-b73f-51b9-b822-8f5160177037 | note | Reference - DoT Handover Process
b809b874-c2c4-5014-928b-5cc6001fec45 | note | Acceptance Criteria - Tactile to be yellow in colour, VicRoads approved as per design note RDN 06-05 and DDA Compliant
8ad9db83-4cb6-54c0-8132-fd02ca1b9589 | note | Method - Visual & Document Review
25e053d0-5322-5a22-90b2-83ca6e82f892 | note | Frequency - Prior to works start
42543203-f0e4-54ad-93f3-531cb98a0b1e | note | Category - HP*
92589faa-d232-5f8d-bbc8-668b33c6b4b2 | note | Responsibility - SE/PE
8389de24-ece6-581b-b653-a9b23e58a387 | note | Verifying Documents - This ITP Signed-off
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-out
a956e336-312b-5045-b682-53c84330268d | note | Reference - IFC Drawings
faa830ae-ee8d-5925-b980-74d7b62b4030 | note | Acceptance Criteria - The required positions of the tactiles are clearly set out by a surveyor as per IFC Drawings.
206faacb-2b4b-5e70-a867-2c22a7482a63 | note | Method - Measure, Visual
218d02c6-f235-5918-990e-0d677624a9d2 | note | Frequency - Per Lot
42197c27-a548-5de7-bd46-a7cf8669e420 | note | Category - IP
b6fa9b8b-1568-5947-b3cd-b956cc46005d | note | Responsibility - Surveyor, SE/PE/Site Supervisor
48b670ca-bb08-5ae1-a268-89f39180b58b | note | Verifying Documents - This ITP Signed-off
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Installation
254a156e-4abd-553d-87fc-60fbcebab0f0 | note | Reference - AS1428.4.1 Section 2.3.3
f5a81d6d-f514-5a94-ae96-7f71cc0bba32 | note | Acceptance Criteria - Notify Nominated Authority prior to installation.
98b48cb3-ce32-51b4-8d61-5f7d45964f4a | note | ○ Warning indicators shall be installed as follows:
79c9b47f-231a-5d59-adb0-dba5c06bbafb | note | (a) For the full width of the path of travel
0321adbe-6056-51b2-80ac-7ac29cae5277 | note | (b) Perpendicular to the direction of travel when approaching the hazard.
1750f37c-d785-5b78-a2af-f88af9ee20f2 | note | (c) Set back 300 +/-10 mm from the edge of the hazard except at railway platforms and wharves.
665804cb-a091-53ef-9b35-2a2630753a6a | note | (d) Where integrated warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below, over a minimum depth of 600 mm to 800 mm from the direction of approach.
4f47a977-6ea8-5321-87db-1b43c6e04f40 | note | (e) Where discrete warning TGSIs are used over a depth of 300 mm to 400 mm, the arrangement shall be as shown in Figure 2.1 below with a minimum of 6 discrete truncated cones in the direction of travel.
b909090d-f514-5606-ba57-aa5a3f1005dd | note | (f) Where discrete warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below with a minimum of 12 discrete truncated cones in the direction of travel.
de774656-4288-5bfc-89c2-c8739d815bdb | note | ○ Where required on a path of travel, warning indicators shall be located at both the top and bottom of stairways, ramps, escalators and moving walks
9e4fd6af-0504-57fc-afba-7fac1c011641 | note | Method - Visual/Site Inspection & Document Review
2d67d4f8-1d97-5f7d-a5ef-596355a3084a | note | Frequency - Per Lot
51fc4391-1e19-54b0-bc73-769873a5d2cf | note | Category - HP
1cddd39e-cba8-56e5-ae37-1c696638696f | note | Responsibility - Nominated Authority
91e7cec2-6acf-5834-a3e2-d55921ebb301 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Laboratory and On-site measurement of luminance contrast
ce5e4a5f-e365-5e98-9e81-2f35b79b0659 | note | Reference - AS1428.4.1 Appendix E
0ec367ae-35fb-5e76-a56b-baa1a247600e | note | Acceptance Criteria - Submit Test report to AS1428.4.1 E5.4: The following shall be reported:
f961abfb-d90a-5b7c-a595-c4c65da89ca3 | note | (a) Full description of the surfaces tested with product details where known.
e503b15e-cdf3-51e2-90f0-5211233a89b2 | note | (b) The instrument being a luminance meter with a 1° measurement area corrected to approximate the CIE 1931 Standard Observer.
a3aae981-8a2a-5e9c-af5e-fa94f9f3a214 | note | (c) The location of the sample, if on-site.
56fb0b7c-56fc-5ee3-ad29-f671b3d71e1b | note | (d) The location of the sample of the measurements on the TGSI.
cb6117c1-6c73-5a53-8c50-d12d15c89b61 | note | (e) A description of the light source(s) illuminating the sample, including type, [e.g. fluorescent tube, incandescent, high pressure sodium discharge, metal halide, and colour (in general terms)].
5cf4ec8d-ad3a-5224-82b2-3dca8b991923 | note | (f) The mean luminous reflectance of the adjacent surrounds to the tactile indicator under the conditions set out in Paragraph E5.3
1bd7cc91-1f5f-5a97-a25b-d206d0a0be1d | note | (g) The mean luminous reflectance of the tactile indicator under the conditions set out in Paragraph E5.3
da8d0eb2-bd23-53ef-bb09-025910403cbb | note | (h) The luminance contrast with the surrounds on both sides of the tactile indicator.
a074fe00-e422-51c1-9a5c-2d96fd473e6f | note | (i) A reference to this test method, i.e., AS/NZS 1428.4, Paragraph E5, Appendix E.
556c14a7-d7d6-5ce9-9b62-92b67063133c | note | ○ Attach: Laboratory Test report
3a639eaa-5be8-5eb8-8915-bc0a5b20c485 | note | Method - Visual/Site Inspection & Document Review
19122103-fe3e-57b1-b301-b5aa83167887 | note | Frequency - Per Lot
db8463b5-bcec-5fc5-8db1-459e28f4418e | note | Category - IP
33ea5f3c-70c1-5042-9bd7-ef55c3a49c62 | note | Responsibility - SE/PE
b9b32ae1-779b-5818-9ab7-ad0fb215ef16 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.3 - Distance between tactiles and sleeve
90ebdf45-ce6a-5489-8169-8891b7b31d4e | note | Reference - DoT Handover Process
2760a26f-8d34-5f6e-b575-b726141c9912 | note | Acceptance Criteria - Distance between tactile and sleeve to be a minimum of 300mm as per note 1 of the Handover Process
9563b40a-243d-549f-b430-285807d06138 | note | Method - Visual Inspection, Measure
71180c9b-3be8-5794-b0f0-e310c15e28bf | note | Frequency - Per Lot
c355c0ac-0ac1-5af8-9f49-c2ca732c801c | note | Category - HP*
dd870336-3def-57ba-918c-60e599385bf3 | note | Responsibility - SE/PE
2f5f8b3b-b833-5763-ab03-76fcd2ec351d | note | Verifying Documents - This ITP Signed-off
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
a35c44f4-e897-5bc8-95fd-cc746b8afd30 | note | Reference - IFC Drawings VR 160.A9
f84482eb-4780-5d50-b159-786478071bac | note | Acceptance Criteria - As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format Attach: Survey As-built / Survey Report
ad833244-84bb-570c-b20e-6e0cc318bbf4 | note | ○ Attach: Survey Conformance Data/Report
46a9343c-6b88-5f74-90f0-022711c637aa | note | Method - Document Review
98b1afdb-a5b2-5d68-92e8-4b55195a294b | note | Frequency - Per Lot
48c0cf0d-7d66-56ee-9222-9e0bce3fae79 | note | Category - IP
4d34d05f-f664-5186-8f4c-4fd28e4831fb | note | Responsibility - Nominated Authority
38ebcac8-443e-5006-9ed4-24cbc885b2b1 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
127e9ecd-2f88-5ef5-b610-755bccbeb13a | note | Reference - MRPA Quality Management Plan
829e9b3a-80a8-53fb-bad5-9e0446be97b4 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
123f22a3-eab2-52fb-9a31-296a1e5f83a9 | note | Method - Document Review
45d0357f-a6cb-596c-b466-7454d16bd990 | note | Frequency - Once, prior to closure of this lot / element / Work area
1a8c7f04-e476-51c9-b5a3-9bdbaea5de2a | note | Category - HP*
91b0c3e1-4394-5569-a1a1-0041bf8e0bf0 | note | Responsibility - SE/PE/SPE
6535e693-5604-5003-b500-f9e2750a689c | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
54c2951f-c042-52f0-a3a4-8ae6cafa98e3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
13f5a694-8eb3-5a6e-a92c-caf0fb02f51c | textbox | Name:
a7b5cff4-7576-50df-acfd-f7aa6cab62f6 | textbox | Position:
10097da9-3731-5196-9a6c-22b2302d5ce9 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-029-CIV-Brunt-Concrete Bus Bay |  | ITP-029-CIV-Brunt-Concrete Bus Bay | 7b04372d-fcd1-47de-9e8e-92dedac0ea69
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
caf9db12-2018-5750-8479-565821ebf315 | note | Document Title: ITP-CIV-BRUNT-Concrete Bus Bay
411b6ec1-f607-5295-8af6-0851cff9b0d6 | note | ITP Description: BRUNT-Concrete Bus Bay
3c9d0224-2f34-582a-87b6-abd5ea9a23c7 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
1bf9a3f1-2282-58a5-bc5a-aebe52a4467e | note | Discipline (e.g. CIV/STR/RAIL): CIV
1e71785d-f8fb-5629-894c-0c48ba86d218 | note | Revision Number: 0
922a279d-b268-5e01-9fb8-fa540481b9bb | note | Revision Date: 28/02/2023
386e9fbd-ec37-5fc6-a3d2-75cf56ff5e0c | note | ITP created by: Jason Lee
38a9b04b-acc2-54ae-b888-2a7f753671e8 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
edef361b-85f5-5412-a5ff-d11c0b85ed1b | note | Reference - VicRoads Section 204 (Dec 2015)
| checkpoint | 1.2 - Non Dependent
fe81b397-87f4-5da9-924a-6375168e4fc9 | note | Reference - VicRoads Section 173 (Oct 2008)
| checkpoint | 1.3 - Non Dependent
cc6d33fb-9970-5873-93a4-c4e463c4da87 | note | Reference - VicRoads Section 306 (Feb 2023)
| checkpoint | 1.4 - Non Dependent
1400856e-20b4-5f43-8a07-b546c5816211 | note | Reference - VicRoads Section 610 (Feb 2020)
| checkpoint | 1.5 - Non Dependent
60e60bc0-dcc6-5f1b-95e8-254f6311ab98 | note | Reference - VicRoads Section 611 (Nov 2018)
| checkpoint | 1.6 - Non Dependent
7bfff9c1-5727-5208-ae94-b3c82af0e5c3 | note | Reference - IFC Drawings
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance - Subbase
4c956041-cee8-513d-b408-7d36227e36d9 | note | Reference - Section 306.04
0f08c28d-58a8-547a-bad6-56c1f636d241 | note | ○ Section 815.04
bf82a309-4200-5ef6-9165-fba6a5885c4d | note | ○ IFC Drawings
f760ddf3-1c3d-515b-bc54-a3d11bbd1756 | note | Acceptance Criteria - Cementitious Treated material shall comply with the requirements of Section 815.
a7c5505c-22ed-5751-b436-a4243d6867b4 | note | ○ CTCR mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02
65b68e7c-7cba-5000-8974-e3625612abc8 | textbox | Enter: Teambinder Material Approval number
bfbbcd95-4894-55cf-b1c4-7c4d07745642 | note | Method - Document Review
05387843-24af-5e06-9723-e8e97d5f6f12 | note | Frequency - Once, for each material type prior to start of works
ad41da11-c5e4-5ca8-939a-23473c30ec0e | note | Category - HP
7bf5ce3e-e748-5edb-975f-648c4e743c32 | note | Responsibility - Nominated Authority
10f6ea35-b18f-5180-b57f-ee0362f98a65 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete Mix
7148111b-7121-5f9c-9728-798d48484e5d | note | Reference - Section 610.07
85709d76-7734-50ef-ba6b-a6e68750138d | note | ○ Table 610.071
f9ed9eed-11a3-59e9-9a48-d290829e0a64 | note | ○ IFC Drawings
a6018a0e-7a05-5d16-84e2-9ba760b24582 | note | Acceptance Criteria - Contractor shall submit to Superintendent the concrete mix design for approval 4 weeks prior to placement of concrete.
98e8edb3-ca08-50ff-9740-b780980fe580 | note | ○ Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
04d6f6af-3cd7-5285-b7e4-c863e2c7f857 | textbox | Enter: Teambinder Material Approval number
8b17784f-37f1-5514-a9ba-ac4ec3508425 | note | Method - Document Review
e0919b8b-98cf-5e1c-b337-7372b2d21103 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
83242421-05f7-5ef0-bbc3-93b52548dd60 | note | Category - HP
78902225-1448-5e36-9fda-959b26fe6f3e | note | Responsibility - Nominated Authority
6352b70a-d392-5763-8df5-90cdc1a96d80 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - ACRS Certification (for Reinforcement)
a0a5d962-3baf-5384-8cea-dcf691937be1 | note | Reference - Section 611.05 (a) IFC Drawings
2565475e-2548-5a2d-90f3-6aa80b05b4a0 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
d303cfb0-2ead-5249-8cde-36f3323a4523 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
199e9db4-5548-5100-8424-04c70947a048 | textbox | Enter: Teambinder Material Approval number
8e81a99f-5d1e-5c7f-bc8a-9a944c65a7d1 | note | Method - Document Review
43c16cdf-63b7-508a-8bef-23d4b304e651 | note | Frequency - Once for each supplier, 14 days of award of contract
a4863fab-0d63-58fa-a272-03044bef21dc | note | Category - HP
137ae5b5-0b54-5496-8424-5b583c43961b | note | Responsibility - Nominated Authority
e1c217ce-f7f5-5726-bc62-6417e5e63601 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Curing Compound (where required)
80e514bf-917b-5167-9ba3-adcbeb6a5589 | note | Reference - Section 610.23 (d) IFC Drawings
b2c576be-7abf-52e8-b7bc-4dcebc1fd07d | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
46dfec42-3e3e-53dd-92ce-617cb5ddda2c | textbox | Enter: Teambinder Material Approval number
f32b40e3-8f95-5b97-9f04-dfa8fe68d1ba | note | Method - Document Review
a85fafbe-8ab9-5bc6-aae6-ea706bc873d3 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
a40a9a01-7171-52bc-b45f-bc640144a5fa | note | Category - HP
c0282d51-27ff-5dfe-9461-2077eaebb229 | note | Responsibility - Nominated Authority
afdb636f-d818-5963-8ef5-5a8e40dca864 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - IFC Drawings
b3681098-cd40-5c21-8c29-de690581d7c9 | note | Reference - MRPA Quality Management Plan
f56ab2cf-4c6b-5e62-90ed-7b04cf043e23 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
bac24401-a4dc-5fba-9727-8e74d231aa4e | note | Method - Document Review
dee57f30-a1a4-5ab5-a192-ea585f7771b3 | note | Frequency - Prior to starting Works and at regular intervals
013b3700-fe0c-563e-8411-7c884d94c709 | note | Category - HP*
644a8ddb-8567-5d5f-94b0-226b34a1d8fb | note | Responsibility - All
3df17921-7b28-5c2a-99e8-12b5f7c01269 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 3.2 - Curing Method
4e4e63d8-4631-58af-9a9b-f522e5cc79b4 | note | Reference - Work Activity Pack / Works Procedure
efc22851-143f-5de0-ae68-44337ea97463 | note | Acceptance Criteria - Contractor shall submit to the Superintendent for review full details of the proposed methods of curing, as part of the concrete mix design submission, not less than four weeks prior to placement of concrete.
711e7e2c-0046-5566-8d6f-66f6c8fa77d9 | note | ○ The Contractor shall not proceed with the placement of concrete until the curing method(s) has been reviewed and approved by the Superintendent.
25fa41d4-8928-5509-b02b-6560729233aa | textbox | Enter: Teambinder Hold Point Ref No.
11a9aaca-a2ae-5fa1-900f-b68c02f6b469 | note | Method - Document Review
7da243b7-ab19-5df1-9167-365b88169386 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
ffa80ee6-9685-5835-9cde-257d315ebddd | note | Category - HP
8d86ae73-e02b-5d01-a89c-146968149ba9 | note | Responsibility - Nominated Authority
fa25f054-4fe8-5b71-94f0-ce56d7ff1a95 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-Out
109bcee5-6efe-5f2a-a199-1bd2e7309e5d | note | Reference - IFC Drawings
2dc038bd-7f87-5ac2-935d-9b6fb4dac946 | note | Acceptance Criteria - Area has been set out in accordance with the IFC Drawings.
f28904ba-0011-5989-9cd5-c260621dbe15 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
a2d00555-3449-562b-a01a-38f7942d0372 | note | Method - Verify
562dfa34-d3c6-5a84-87d9-8e26a20030fa | note | Frequency - Prior to commencement of excavation
299ef434-dcb4-5871-83fe-9511be3d3f1b | note | Category - HP*
983744d8-aec4-5c3d-b86d-3756c3340879 | note | Responsibility - SE/Surveyor
f66086fb-07d8-58c9-b8f7-3ae1ac2157b3 | note | Verifying Documents - This ITP Signed-off
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Inspection of Subgrade Material Subgrade Material Properties
27256ddf-bec6-52ea-a642-31d42309f2b7 | note | Reference - Section 204.06 (c)
04f75cce-81d2-568f-9fba-3948a2a0b0bb | note | ○ Section 204.06 (e)
f48079be-11ab-5b4d-82e7-afcf404c2950 | note | ○ IFC Drawings
f83e3305-5ac7-5290-9cd2-2d1b3761edda | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
dd207e00-4ff8-5d81-9150-e1d31fa6aa67 | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
1543ff6d-0b32-5939-ae35-eba76677c165 | note | ○ Assigned CBR ≥ 2.5%
a4979506-9bf4-59ad-a7ff-8ac72858b93b | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
0785c31b-e7f2-5931-b85e-c0e1e1fd75d9 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
6263951a-93c5-56cf-98ca-e3dfb320fc80 | note | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
8ee6880f-3e91-56b1-a24a-f01336628f7e | note | ○ Attach: Laboratory testing Verification:
cc0adc2f-1f24-576a-8655-e7d4203e43f4 | textbox | Enter: Type A fill Lot Number:
e8b1cc2f-3bf8-5e48-9388-3abf340d7451 | note | Method - Verify-Document Review
3ec8fee5-4fe3-5702-82c7-fc87e8b6d6ef | note | Frequency - Each lot
03a0c186-6618-5134-b0ca-238c4ffbfafb | note | Category - HP
8ff8e024-d050-5f91-a39c-545d43933496 | note | Responsibility - PE/Nominated Authority
956dd7e5-7171-523d-8a9c-71ae2d9161ae | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Material classified as Silt - Subgrade
54c3241d-8dfc-50fc-bdce-eecfb1958fa4 | note | Reference - Section 204.04 b)
f2c82231-b2dd-5462-8869-ac54430cf833 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
f403cc26-f4fe-5030-b4f4-1631dc9f6d3a | note | Method - Document Review
40cd4aea-a43a-50fb-b835-29363bbdb6e1 | note | Frequency - Prior to commencing
cd0cfa96-a511-5fde-9b05-5172ec553c72 | note | Category - HP
c6110036-9414-5e87-b955-5648f087cbbc | note | Responsibility - SE/Nominated Authority
86fc36ba-78ba-5ecc-9feb-94bb14b57ea2 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable) Subgrade
0f90d9a1-07e8-5379-ba21-45391290ef7d | note | Reference - Section 204.06 (f)
2555fc5b-985d-5d68-b42a-1cf37ed755fa | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
a9529f2b-6872-5f1a-a035-f9c1159fdaf0 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
fb1fec35-270f-5bfa-99e1-8c1f0ed424dd | note | Method - Site Inspection/ Document Review
85df7d4a-3de7-5810-a2e7-248a6916cb2d | note | Frequency - Prior construction of the regulating layer
072ae39e-4519-57bd-96ad-df56098af0e2 | note | Category - HP
a97d530f-3275-5a13-8c90-e9891a698c5f | note | Responsibility - SE/Nominated Authority
8cde1718-6e4d-5825-91f6-3e337ac5f5a7 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Unsuitable Material - Subgrade
6c27cee8-abf5-5d59-83cf-4cc059fa44cf | note | Reference - Section 204.07 (d)
0f074b48-917b-5f9f-ad50-aa000b675010 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
c8864228-5773-511d-99e0-119f61d75f9d | note | Method - Visual inspection
11b746b7-bca5-5e63-ae80-f2417c860002 | note | Frequency - Each lot
8e779b8b-4fd2-5200-b13b-aea80d32bdcf | note | Category - HP
8712d6d5-69cc-5bf2-a528-c4da247f9288 | note | Responsibility - SE/Nominated Authority
c166706f-cbcf-5bb2-81a2-b4d6f0a3b3fd | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Groundwater - Subgrade
60d4a694-a9ea-5103-90cc-ea66e6cc8a9f | note | Reference - Section 204.06 (h)
9250ec9a-7607-5b96-9192-5d737c3ddf9d | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
fdd53b23-05ef-5b40-aae0-04dd7bbdc3cc | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
0f6fd019-09b0-57ac-a27e-a0dce53e672d | note | Method - Visual inspection
e73fa3f7-02ce-5f87-9ff1-b8cc3482ceff | note | Frequency - Each lot
0d597a40-20af-5a07-a395-9fa8c7da113d | note | Category - HP
c07c6b72-548a-5e75-8e75-350a558733a4 | note | Responsibility - SE/Nominated Authority
c8315728-fd9d-5aa4-864e-ce81a56bc2b5 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Cut to Fill Zones - Subgrade
3f2b269c-a77b-5ab2-af59-0a8100b4fd28 | note | Reference - Section 204.06 (g)
a832284e-e20f-5c84-bf32-43481992de01 | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
d39978ee-ec1d-5942-9df8-c034e8b33610 | note | Method - Site Inspection
6a0e7c76-7881-5b13-92db-7f79d30dda23 | note | Frequency - Each lot
2045e013-f45f-595b-93cb-42f3b79d561b | note | Category - IP
694798ad-9ca7-5c8d-8414-36a8d1ae656d | note | Responsibility - SE/Site Supervisor
8fd40f2b-b1e0-5393-bfe8-cbf268d3bbb8 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.7 - Proof Roll - Subgrade
85522c6c-7845-555a-9045-d64149ff6e30 | note | Reference - Section 173
cb28fb58-ae76-519e-9ed8-35fa86fd4853 | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification.
2c951033-e2d5-5dfb-a166-25c543e5c264 | note | ○ Attach: Proof Roll Inspection Checklist
795bc2c6-9970-5753-aa70-a29d60868fb2 | note | Method - Visual inspection
a7f62046-d4bb-530c-8a05-c4879e28d01d | note | Frequency - Each lot
15fce067-ef0b-5c94-b7c2-6a7c27041053 | note | Category - HP
6b589ef1-b238-59ed-987c-65a4b004b517 | note | Responsibility - SE/Nominated Authority
73b6f83f-e7ae-52b1-99b0-6defd25008fe | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Compaction Testing - Subgrade
830b47c4-7f47-500b-a251-6928e61623aa | note | Reference - Section 204.13 Table 204.131
bb9e27ce-858d-5c6e-ba36-d66d8a452f47 | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
c45275dd-997a-5e63-9b24-713f4bd31e92 | note | ○ Ripped and re-compacted material below Cut Floor Level
d6e8bcd2-8051-53a6-9f6b-4fde0d45dbea | note | ○ Scale A: Characteristic Density Ratio 99%.
f88ed07e-3770-525b-a915-8d1db189520f | note | ○ Scale B: Characteristic Density Ratio 98%.
2d94a38b-76a6-5725-9f2f-72465ab6dc2b | note | ○ Scale C: Mean Value of Density Ratio: 100%
e9278444-6cb5-5505-8d12-dfe5d46a40e5 | note | ○ Attach: Compaction Test Result
8d9edd84-4c0c-534b-b5fd-fc7a39486b7a | note | Method - Document Review
9d3a94f5-5590-5d3d-814c-960c4633a1c1 | note | Frequency - Each lot
ae2b712e-50c6-5315-93ee-40e6c333b4bf | note | Category - HP*
1f6f7520-889b-5982-91f7-a441bccb3586 | note | Responsibility - PE/SE
9b13259e-795c-513b-b154-5e1171dde4ca | note | Verifying Documents - ConQA Hold Point Release
| checkpoint | 5.9 - Post Compaction Material Property Testing Subgrade
39844e27-d52c-5000-b4ef-a7d14c358aef | note | Reference - Table 204,041
3e6dec71-2932-5fd9-be21-9e73a81c244e | note | ○ Table 204.141
3f274020-2f88-5c8b-8c1d-b8f347922054 | note | ○ Section 204.14 a) or b)
6bb06da9-2b6d-5c2b-a0c3-9cfd02d5cd01 | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
9c80d35a-a637-5985-bfe8-53120f1a9e17 | note | • CBR ≥ 3% and Swell ≤ 1.5%
ed26261e-90c3-5d1a-8344-7e848baddbf8 | note | • Max Permeability = 5X10-9 m/s
8395085c-0b4f-5758-bf94-957d309d8ce3 | note | • Grading: 75.0mm 100%
dda184db-ff6f-5392-9b38-043bb985b25c | note | • 4.75mm 40-80%
a2f4030c-2507-5716-be3d-d774a8f34f05 | note | • 0.075mm 10-40%
1e45dc2b-87a2-5066-bed8-c0ff92454f21 | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
95176f6a-9ff7-5714-a678-07762256d646 | note | ○ Scale A:
ac4e0572-cd9c-5c49-a5a7-7a05dadbbb30 | note | • CBR & Swell
8b1e2deb-db78-564a-b766-b7117c155e9f | note | • Initial - 1 Lot Test to determine Assigned CBR and swell
fc04549e-3617-563e-b481-2628a4a61b04 | note | • Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
d9c94ed4-a23d-5771-9a5d-3089b4020cd8 | note | • Max Permeability
4cd69abe-32fe-544a-865b-ff53b1b6d1c2 | note | • Initial - 1 test per 2 lots
6efef97f-d05c-55eb-b87c-39c4e135289f | note | • Reduced - 1 test per 4 lots
b9399688-349e-5bf7-8325-79a238d42706 | note | • Grading:
77591a59-8032-5f6d-ae13-68965d4513a6 | note | • Initial - 1 test for each lot tested for compaction
ca6ba866-1df1-5ac0-808b-117176caf46b | note | • Reduced - 1 test for every second lot tested for compaction
b4de1358-a734-5c04-9fa0-fc02d1b77401 | note | • Max. PI x%Passing 0.425mm & PI
99e06d6b-8586-5fe7-979f-e3c7987b0348 | note | • Initial - 1 test per 2 lots
f6bb2e15-da14-59a6-8c95-09786cf7ecd7 | note | • Reduced - 1 test per 4 lots
1d883054-2e45-5408-a9c2-8392141506c4 | note | ○ Scale B:
dcdb0b38-0e38-5258-9e83-85a1c0d387bd | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
d98f0934-39a1-5992-a3b1-fd50f3bb70e3 | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
fff2839b-a7cc-5388-beb5-7df599d3201f | note | ○ Attach: Post compaction test results / Attach Material Property Test Report
91370acf-7647-54c8-8cca-233ce8137c85 | note | Method - Review Document
2d715851-4804-5634-a6c4-700b1d6f6a9f | note | Frequency - Refer to Section 204
10b93fca-1290-531e-91ae-a3fa4292ac9b | note | Category - IP
f4380798-678f-577e-9480-98732a7a912b | note | Responsibility - PE/SE
ce59f910-41fb-51e5-91c9-68874f73d936 | note | Verifying Documents - Sign ITP
| checkpoint | 5.10 - Test Roll - Subbase
967d7bab-a5e0-5b9b-9f8a-5d57c19afa8a | note | Reference - Section 306.10
c765a610-9dff-5c5b-8151-823c2e6597a6 | note | ○ Table 306.091
e038db28-54ba-5661-9c15-db53f68097f9 | note | Acceptance Criteria - Shall be test rolled in accordance with Section 173 within maximum allowable working time for the relevant binder and time of year as specified in Table 306.091
d3e20825-9212-5bcf-8938-fab2e53d10b7 | note | ○ Table 306.091
2200545e-9bd9-5446-ac16-813db23f9302 | note | • Type GP - 2 hrs (Oct to Apr), 3 hrs (May to Sep)
61ae5483-d56e-5877-80bd-9326c23de667 | note | • Type GB - 3 hrs (Oct to Apr), 5 hrs (May to Sep)
8f0acf05-2794-58a0-beaa-afc77380d7c6 | note | • Slag/Lime Blend - 8 hrs (Oct to Apr), 12 hrs (May to Sep)
b4308e16-25fb-5bb0-b2d2-1fcd2b752f33 | note | Method - Testing
ebefb6b0-529c-581a-869d-c187cc9e15a7 | note | Frequency - Each Lot/Layer
17ac3fc0-cdb6-5a90-9083-afe2a0973836 | note | Category - HP
52f7b98a-e40f-5c1c-ab1a-a48f5681e8ca | note | Responsibility - Nominated Authority
21a1552a-0350-5b49-8dbc-c4b779ce7df5 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.11 - Compaction Testing - Subbase
dc832e6b-3808-5066-9119-03344780e903 | note | Reference - Section 306.09
799519d2-c3e7-51c9-90e4-ba3dbcbb446e | note | ○ Table 306.091
762f6072-3d63-550e-8b47-58aa7f9c19e1 | note | Acceptance Criteria - If the Contractor proposes to use an alternative cementitous binder to those included in Table 306.091, laboratory test results shall be produced to the Superintendent showing that the binder satisfies the required working time determined in accordance with the VicRoads Test Method. In addition, the cementitious treated material using the alternative binder shall meet specified strength requirements.
ff55c439-a399-5ac4-bce3-6d69aa1c6e89 | note | ○ Characteristic Value of Density Ratio
8438a92a-a17f-5fc3-821a-9093819aa850 | note | • Scale A - Not less than 96%
2cbd5e9f-ad52-5340-942e-9d1e9694eb8d | note | ○ Mean Density Ratio
afeb0a1b-7f9b-5dac-8338-822516cc85b9 | note | • Scale B - Not Less than 96%
65b9f80a-6b35-5f6a-a3dc-eaa25b133127 | note | ○ Attach Compaction Test Report
fc7f2520-5f8f-5b00-bb15-f8261fe1161b | note | Method - Review Document
c5d0d187-6557-5af1-8fca-c647e6fbb577 | note | Frequency - Scale A - 6 per lot, Scale B - 3 per Lot
737b80a3-6463-59d4-a3a1-b7adfb9dfcdf | note | Category - HP
ec6ec993-ab55-5f08-a3fb-7116baedec3e | note | Responsibility - SE/Site Supervisor, Superintendent
a7bcae4a-ead5-56b8-8a01-55f5682eeac4 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.12 - Reinforcement Placement - Base
ecf9502f-1157-598a-9aa4-69e5ab79c417 | note | Reference - IFC Drawings
84556406-ebbc-52d3-8abf-481b2ab01288 | note | ○ VicRoads SD 2071
962d5ec9-169a-5134-be0f-5b3ecc9c81ae | note | ○ Section 611.06
ea8e669e-ea90-5606-96fb-40a2e9318a4e | note | ○ Section 611.09
24959be5-92f7-5787-a201-703ec9ecc55b | note | ○ Section 611.10
8718ae74-4180-5727-a35f-f868ab56d627 | note | ○ Section 611.11
9e116de5-4aa5-5bd8-be92-b4e234052e47 | note | ○ Section 611.12
7efc634b-d302-59df-ab4a-bab94738a5c0 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the drawings.
472b9b59-8d02-51d8-9ae8-4eb5c995abf3 | note | ○ Projecting reinforcement is the correct length and location.
9d1c05d1-e0c8-5108-940d-4e70dff47c59 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
6f4cf99a-b077-549c-8c7f-5d16001b9b90 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
ae21b4d9-5080-5541-b612-56cad5e2ede4 | note | ○ Minimum cover as shown on the drawings for each face has been achieved (including tie wire locations).
c37f20fc-9c5c-51aa-8e14-d2e572a1420a | note | Method - Measure, Visual
e8e50829-c6c8-59f2-8422-128e8ac57e52 | note | Frequency - Each element
6ab8dcdf-4926-5b4b-b3f7-f4f2ea32d129 | note | Category - IP
64b78505-86a5-5ae9-bf23-33dbe9e1ceec | note | Responsibility - Foreman, SE/PE/SPE
dc22e4c8-6fb7-5089-815b-683a9c854403 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.13 - Pre-pour Inspection - Base
a32e2e7e-595b-5c94-a5fa-2f130e15afd8 | note | Reference - IFC Drawings
741c118c-f557-50ad-b177-7e27d4ab262b | note | ○ Section 610.18 (a) (ii) & (iii)
f0fb1b98-6f9d-5ce4-89f7-88bf46836472 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
3a1c623a-5a22-5a9e-a770-4a60df6f64ad | note | ○ All foreign material has been completely removed from the forms.
b1df940f-a69a-57f0-99f1-dcd4c275f5f1 | note | Method - Measure, Visual
6c6c658e-7c90-5934-bb50-b2ddb8b204f7 | note | Frequency - Each element
3db5a9db-ce3b-56cc-b2b7-2a76c11b4479 | note | Category - HP*
07014d9f-5f05-5a19-9821-c8f30045caac | note | Responsibility - SE/Site Supervisor, Superintendent
5bb883be-bc7e-5af8-bff6-e8261221aee4 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.14 - Weather Conditions & Evaporation Limits - Base
592c33ff-ec10-5e44-bb3e-4acf40032e8b | note | Reference - Section 610.17
4e5409d0-49b0-570f-a619-6099548d9ef9 | note | ○ Section 610.17 (a) & (e)
80938f8c-60de-567c-a068-e5120dbf521d | note | ○ Table 610.171
9ca51774-01b1-5b29-b5c4-69d69b78609c | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
f0d3547d-992a-5df2-a655-fc7374040754 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
76b278ac-77ca-57f6-b7e6-5b8c9e8d2d1d | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
960125e4-ca19-5cb4-a17d-69f4804762de | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
ca9d5847-9ce1-576b-9212-34058f01e8fd | note | ○ Record: Required information on the Concrete Pour Record.
b866aace-d854-545b-8797-12e3b04da5d2 | note | Method - Measure, Visual
f06753fa-b011-553e-8463-90e41070013c | note | Frequency - Each element
9c8f4b28-183b-5725-b216-c220927c8654 | note | Category - IP
d275f000-83b5-5fbe-959b-032ca3c3b8c1 | note | Responsibility - Foreman, SE/PE/SPE
534bf274-303f-5a20-8a63-b068cdfb88d5 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.15 - Concrete Testing - Sampling Frequency - Base
e6d72e43-77d5-5f54-a143-1be4fc44458a | note | Reference - Section 610.16 (b)
9628b2c4-a514-58b4-ba06-fbac01a2a454 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
b428e355-2fab-5b4d-ad8e-38e715ee7993 | note | • 0m³ to 10m³ = 1 sample
e6e5eaf0-f86b-5e5f-9f04-1743375c070c | note | • 10m³ to 25m³ = 2 samples
9cfa3145-34a6-5255-aad0-f57764a7eb5a | note | • 25m³ to 50m³ = 3 samples
545f7875-4675-55b5-88b4-a08abdc595e2 | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
248a7a5b-3985-504b-a03e-55daf3f4ccde | note | • For each additional 50m³ and additional sample shall be taken.
58cb67ee-18f4-5a86-a6f6-c8fc9f89d8b4 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
3b415adc-2af1-5473-9e5b-25cef850f5e8 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
da28969b-91bf-5a52-b6a6-07633e328405 | note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
23f57939-3df3-5aba-b610-60934d05110d | note | ○ Record: Required information on the Concrete Pour Record. Qty of samples taken
2f92ee87-cd85-5830-be10-f3230c944d86 | note | Method - Testing
a1e77885-7df8-5568-9d45-ee5a88b163ba | note | Frequency - Each element
b53f36a0-57cc-5572-ae39-cefe066e7720 | note | Category - HP*
88e69a7b-5dca-5774-8453-ff4933810c0d | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
34d5593e-01fc-5d5a-850c-fdcad9d9cb72 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.16 - Concrete Testing - Slump - Base
29a8ce74-cd4f-5b48-a043-de1b59ec33f9 | note | Reference - Section 610.16 (c)
385241b8-9e7c-59f7-b126-4a18e66bf73b | note | Acceptance Criteria - Slump testing tolerances =
7d069a5e-3fd4-5dd5-9bc2-8fe0022e8bbc | note | • <60mm = ±10mm
7078828c-f1c5-5a9d-8ace-5986bfc76d84 | note | • ≥60mm to ≤80mm = ±15mm
ec1921a5-77d8-5434-a2e0-06c3d7fb1fcf | note | • >80mm to ≤110mm = ±20mm
fcfa5596-25fd-5d4e-abd7-d7678ef76305 | note | • >110mm to ≤150mm = ±30mm
b7edc4d9-38b1-5cee-8133-238f6d67e740 | note | • >150mm = ±40mm
cb8da4cd-4414-5b97-9d44-ff7f39f93728 | note | ○ Record: Required information on the Concrete Pour Record.
c8055676-30b2-5cb4-b4fa-7d1ba5501c1f | note | Method - Testing
c6f45d40-df2d-59d2-8e20-7b98690425c2 | note | Frequency - Each sample of Standard or Superplasticised Concrete
dd4da5ef-358c-5450-ab8c-0da343525b4d | note | Category - IP
e5a0733b-7be5-5c16-92a2-ee935bdd492b | note | Responsibility - Concrete Tester/SE
ff01d2cd-3c71-5f11-8cba-5ddf88a26d0c | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.17 - Concrete Testing - Spread, Passability & Viscosity - Base
89d6d38c-f829-5154-84af-d7102e269707 | note | Reference - Section 610.13 (b)
fda8f12b-b951-5f93-8b85-13e72236b885 | note | Acceptance Criteria - Spread range = 550mm to 750mm
d617ef23-011a-55a8-86a7-d9e82753e868 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
153b5924-c167-5526-afbd-6fee9f45130f | note | ○ Passability = ≤10mm (aggregate height differential)
d06f332d-2eee-54ce-b61d-21f63f8dc3ef | note | ○ Record: Required information on the Concrete Pour Record.
657d6fb6-ed82-5b06-92f8-e6cd46bf032a | note | Method - Testing
b75e22fd-9243-558b-9d19-7dde7427dd99 | note | Frequency - Each sample of Self-compacting Concrete
32d5ba1c-a139-508b-91b5-fbc4bb41590e | note | Category - IP
34eb1525-cff8-5b36-bcb9-b64687658787 | note | Responsibility - Concrete Tester
cc230a73-5be8-545c-95a5-0cacfa1cef4e | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.18 - Concrete Testing - Compressive Strength Cylinders - Base
84585246-2beb-5517-ac11-8933ba3f9684 | note | Reference - Site Sampling & Testing Procedure
7d73eb57-fb64-5159-88df-80d323f22cb0 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
506370cb-f8c9-5893-8cda-63ad276d4051 | note | ○ Record: Required information on the Concrete Pour Record.
263d4651-89cc-5ce7-8a8a-a75911d8ed76 | note | Method - Testing
c05ecc31-ffac-592a-ad8e-f7c58137ffe2 | note | Frequency - Each sample
f3833984-7026-5642-9b30-a984a2b99b57 | note | Category - IP
fdfd1b4b-8c3f-576b-b160-577824fb79e6 | note | Responsibility - Concrete Tester/SE
21929ddd-f350-50f2-8e1e-75e9bc6fac2c | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.19 - Supply & Discharge Rates - Base
7765e00d-f314-5fa4-ac98-3d03f74cd3fe | note | Reference - Section 610.13 (a) & (f)
a6d7580c-c703-5f14-87e8-ac7ed1005a4d | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
e51207c7-b770-5016-b411-edf750097df7 | note | ○ No water is to be added once discharge commences.
208be9fd-d1e6-5699-99fd-457fd79d139b | note | ○ Maximum time between batching trucks is 25 minutes.
e1a307b1-4197-5f81-967b-90e43f26442a | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
ea7346e5-468a-54e1-b001-015278744176 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
efbacd5d-83bc-56d9-823b-be1e245e22f5 | note | ○ Record required information on the Concrete Pour Record.
c1661ea2-9a18-5267-ba43-25b15c69a323 | note | Method - Measure, Visual
a35586b3-9c8f-5416-b1d5-e2b6bc1be65f | note | Frequency - Each load
857e62b9-b881-53a2-9b05-28fab3f06319 | note | Category - IP
12652a5c-b679-5271-a595-e87e8b4b841b | note | Responsibility - Foreman, SE/PE/SPE
567e8383-ccb3-575a-8124-7b5913249f5a | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.20 - Placement & Compaction - Base
dda55b0a-5ac0-51ee-8013-0813cc3bb7a0 | note | Reference - Section 610.18 (a) & (b)
fd909993-80f6-5b78-baf7-392240928ee6 | note | ○ Section 610.18 (d) (i)
5483a4a4-4196-5b57-99a9-8d3235c66e3b | note | Acceptance Criteria - All concrete batches are traceable.
a2e66e68-48b3-521e-8af3-8cb2ccd8c38b | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
86b1c074-3e6f-5ab5-964d-13028369cb27 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
f537f6ce-0f02-5045-a81e-74a4c2173f43 | note | ○ Concrete is not moved horizontally by use of vibrators.
72338c08-67ef-54ed-9ae4-417fa8765436 | note | ○ Adequate compaction is ensured
fa67ce1a-a5ae-5a8b-9819-2bbd99666268 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
60023424-591b-5939-a95f-2d996c9b98ca | note | ○ Concrete layers are not more than 350mm
54fc84e0-4d78-502b-8721-cf680e495487 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
3ffe9ea3-b656-5760-8561-75586a70f707 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
afc9dc01-ef3a-5b27-926a-0aef966611df | note | ○ Record: Required information on the Concrete Pour Record.
1c92950b-9583-5bab-b398-1364a9e0bf2d | note | ○ Attach: Concrete Pour Record
7f405dbb-cfad-5ec2-ab60-bbaff8b3b2d8 | note | ○ Attach: Concrete Dockets
60a1b87f-aed2-56fa-890d-dced2573ae43 | note | Method - Visual
4cf5b9a3-0cf9-5699-86ce-636e86136f8c | note | Frequency - Each load
48d22fba-aac1-5a04-9145-9a908dfdd1cb | note | Category - IP
a2f50d53-cf88-5313-9813-c354ccb57691 | note | Responsibility - Foreman, SE/PE/SPE
6864a1a7-3682-5d40-a852-f89d5f4dd3a9 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.21 - Surface Finishes - Base
a528f7ce-cc44-5e54-810d-0f2cd6a262dd | note | Reference - IFC Drawings
ca4c567b-790b-594e-8528-57df1dd33c4e | note | ○ Section 610.31
f923951d-8f97-5d03-bd35-161cdfd132de | note | ○ Section 610.20
12173215-14c2-5b52-91db-2b496e30b8f3 | note | Acceptance Criteria - Surface finish as per IFC drawings.
3bba3c90-7a8d-5b65-8ab2-99fe8859840d | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
117dc360-4e00-50fc-b497-3ac67f1927ee | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
49ea6395-d9bf-5fec-90a3-7e077844382b | note | Method - Visual
92433ff8-5ad9-5938-97d1-ed26ec0ff1cc | note | Frequency - Each element
5bd1c430-498e-5fa3-9f8f-1e8e562e1966 | note | Category - IP
93c7c50b-78a5-546e-a305-317bb9a07d69 | note | Responsibility - Foreman, SE/PE/SPE
fb31029b-a91c-5ab9-9552-781613cdceb0 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.22 - Curing - Base
d9b58ab2-1ff9-5a9b-ae77-ceb4c09f5ea4 | note | Reference - Curing Methodology
b881c6fc-f625-558d-9c64-49848e88a668 | note | ○ Section 610.23
e0d69eb6-0ab2-5ef3-9b40-ad4ba8431e9a | note | ○ Table 610.231
1dd114fd-ef70-507f-94b0-96f6132c806a | note | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
325a795a-587a-5a9f-9aa0-0aa08a6c6014 | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
8054a731-b4fc-5d64-8409-ffca3a34aadb | note | Method - Visual
78aa4486-169e-5c15-ad2b-a3ec9d7f41a9 | note | Frequency - Each element
49c18bbb-e24b-5804-80dc-0bf8f6821543 | note | Category - IP
0b419ffe-ab4d-508c-83dc-8d2fb7f8f6fb | note | Responsibility - Foreman, SE/PE/SPE
1c49a50c-998d-5b58-8b81-e09c87e7df0a | note | Verifying Documents - This ITP Signed-off
| section | 6. Post Construction Activities
| checkpoint | 6.1 - Survey Conformance - Subgrade Prep
1f460ff3-fb91-5148-909c-8d8cb239b346 | note | Reference - VicRoads Section 204.03f,g and h
16f6a8aa-8f2d-512d-92b8-be397795cd77 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
7d8fcab7-c159-539f-9a2c-74d71ac23674 | note | ○ Level tolerances (Scale A):
8c8a52af-a907-5bcc-bed4-75ceaf6c43f3 | note | • Range x = +5, -15mm
068a6e8c-c6f1-5c61-87f3-8913068dc448 | note | • Max S = 12 mm
cec24779-165b-58d7-91a3-8341f52753ed | note | • 80 measurements per lot
cef49d7d-94e7-59ce-a5fa-f33c69e8e286 | note | ○ Level tolerances (Scale B):
7cc7d0b3-90f4-5619-b330-6dd25f1c24ed | note | • Range x = +5, -25mm
384b398d-6c4c-5126-b64c-45052411f263 | note | • Max S = 15 mm
5d704266-42cb-5f1e-ab98-3b0220ea8db7 | note | • 40 measurements per lot
593a1a25-dcf3-533c-a84d-352f722c0a5e | note | ○ Level tolerances (Scale C):
397ca26d-2aca-5cfc-91a4-cdd7a87bc4da | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
b62dacb7-ee24-5812-9202-cf40b043cdfb | note | ○ Attach: Survey Conformance Report/Data
ad44e58b-eb36-573d-9b81-4641ec4bb8f5 | note | Method - Review Document
63549c1d-b0eb-5193-abf9-a7ff02c1a7ca | note | Frequency - Each lot
b7d97d94-3311-557d-8e8e-893f8f10793e | note | Category - HP*
34d68fd9-2d85-5d19-8439-eec3fa19b984 | note | Responsibility - SE/Surveyor
e344b488-6059-54e4-9d80-e074f9224975 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.2 - Survey Conformance - Subbase
5c61ebdc-a250-5e86-b9d7-14b37b9b783c | note | Reference - VicRoads Section 306.03
7171dba5-a434-5b3d-8d4d-80968e373e40 | note | Acceptance Criteria - Level tolerances Scale A:
e7f864ed-a8d9-5643-9f62-773bc8794b9d | note | • Range x = +4, -8mm
19b09fc7-3435-5535-814e-24c8979c2e27 | note | • Max S = 8 mm
a938fad8-accd-5dd7-b9e0-affac9b8699e | note | • 80 measurements per lot
4bbb25f7-f1a3-517e-8980-8f61dd2bdd4d | note | ○ Level tolerances Scale B:
b577c215-124a-579a-81e6-83cfbc8cc91d | note | • Range x = +6, -12mm
71ccbfc4-23cf-532d-aed0-e8f0fc2e3af4 | note | • Max S = 13 mm
abca4921-df1c-5efd-a38a-4970ed6f0277 | note | • 40 measurements per lot
3a9349d4-0def-5947-be63-65586ef63a55 | note | ○ Level tolerances Scale C:
7d8dd630-9429-51f5-a71e-e76504c79bc7 | note | • No point on the subbase surface shall be more than 10 mm above or 25 mm below the specified level.
88214201-e46e-57b3-91b7-782afda4f87e | note | ○ Attach: Survey Conformance Report/Data
551fd600-8c00-553d-973f-35d0a43d969e | note | Method - Document Review
8bd32c52-f438-51fc-bb80-3503fb3cb734 | note | Frequency - Each lot
25bfe88d-0778-5982-adad-4310e4916dc5 | note | Category - HP*
3dc77001-95eb-5700-87f9-c9557129ba0c | note | Responsibility - SE/Surveyor
6f5a577c-4dc3-5da1-9c38-e0bd3100b7d6 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
883d7109-fd3c-5a9d-91cf-317127f4eb20 | note | Reference - MRPA Quality Management Plan
d75d29e3-a7b9-5761-b983-959b5e0aabae | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
027c7a79-ff4e-51a9-b03e-b19b42eb53b1 | note | Method - Document Review
16eb7c17-efe1-5ad0-82dd-0136a4761b54 | note | Frequency - Once, prior to closure of this lot / element / Work area
92c21fce-1dc3-5a1b-8cad-9f6310b494e8 | note | Category - HP*
0e4aee27-fcaa-5250-8953-b747772b0696 | note | Responsibility - SE/PE/SPE
87ae1cfd-fbf5-5834-9983-21fa91459970 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.4 - Surface Inspection - Cracks (Concrete Base)
8700f7dd-2292-5250-b75d-cd68c1ac7f27 | note | Reference - Section 610.24
a8d92ecd-12f6-5049-a18a-412af24cc16f | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
5881ddfa-e240-50f1-9206-02634702de2e | note | Method - Visual, Measure
9285caf2-2da1-5537-95d9-e1a694d44852 | note | Frequency - Each element
2d2eca1b-8b8d-54c9-9975-201e2f4f13f3 | note | Category - IP
9bdd13a1-418b-5fff-93e2-d6c6aa8bff5e | note | Responsibility - SE/PE/SPE
eed839b6-3f87-5a8a-8568-37cae59db177 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.5 - Surface Inspection - Surface Finish
f67f9754-e07f-5754-ba79-4dbd7bbd1bb2 | note | Reference - IFC Drawings
545c572e-3dae-565d-bb56-68f186604278 | note | ○ Section 610.31 (a) - (n)
d050bd7a-9656-5132-b975-f58eefea106c | note | ○ Section 610.32
e4cd17ca-7de9-5c8b-bf09-72f7dd93fbba | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
37266cf6-ec08-5381-aa4a-31065ad026e6 | note | Method - Visual
4f3168ff-fc06-55eb-b9a9-07b521585533 | note | Frequency - Each element
7669a9c3-9384-5d5b-bb24-6313785edf4c | note | Category - IP
04cab9a1-9de3-5655-bc91-2845423f5a90 | note | Responsibility - SE/PE/SPE
60c3db65-63a2-597c-bc07-6bcfe359ed95 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.6 - Measurement of Concrete Cover
227cfd5d-0687-591f-9f71-6feeb9751113 | note | Reference - Section 610.34
1e84bd84-ba49-5035-97ca-d63b7ca06fe9 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
8a3adc6d-b2e3-591e-8949-f5985b57ed72 | note | ○ Minimum 10 no. measurements recorded in each area.
d55f8a5d-8029-581a-9885-60ea84930fd9 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
94ea4c2c-7be9-548b-873a-b3abea6a32f8 | note | ○ Attach: Covermeter Check Record
f69ddaac-ac96-57d3-83df-af9c0cf80517 | note | Method - Measure
da5d7cda-9165-5812-899b-843a83a58c30 | note | Frequency - Each element
982a9050-650a-51cc-9c58-6a946276218f | note | Category - IP
7f988c66-b9a0-5738-b5b2-c88b458363e9 | note | Responsibility - SE/PE/SPE
8754e88e-8506-5c0d-8773-870f4aa805b9 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.7 - Compressive Strength & VPV Test Results
8315ab84-c22c-5d15-88bd-c924f68a8631 | note | Reference - IFC Drawings
7a4cbe18-3d68-5cdb-be1e-030b03ec22f5 | note | ○ Table 610.051
2eba627b-25d4-56b8-b12e-f5fafdc3a1cc | note | ○ Table 610.061
baad0e74-2451-5e77-a20f-befeef22b795 | note | ○ Section 610.16 (g)
848338a5-a889-59ce-b563-5d7b2a521a46 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
5fed2ad6-ce71-5a96-b514-a5536c608974 | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength and VPV results comply with table 610.061.
d9476344-2d41-5895-96dd-320a713d844f | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
31759d6d-b6ed-56ae-b2b0-a9940ef2b8b2 | note | Attach: Compressive Strength Test Results
f00bca8a-9865-5fa6-83b6-51462bd46a0d | note | Method - Document Review
5477df40-c573-5a1b-a574-8891195d80ca | note | Frequency - Each cylinder
13267daf-d60d-5adc-a6da-39490483c9e0 | note | Category - HP*
cdf1be92-c65d-5616-8f6b-5f385b4315b1 | note | Responsibility - SE/PE/SPE
691c8a71-a32d-52f5-9ff9-ad33a0df1c21 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.8 - As-built Survey
10422342-97d2-56d5-a144-1ae200e531c4 | note | Reference - IFC Drawings
01165553-f8a9-55dd-83e0-1eee042564dc | note | ○ Section 610.46
0026d87a-6fa2-5ee2-b113-93296788b249 | note | ○ Table 610.462
90b788ed-8c8e-55dc-b3ae-aacb73dea5fa | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
b598a992-672c-5769-855c-0782c2d5fcb7 | note | ○ Attach: Survey As-builts / Survey Report
7ca5d50d-b32d-564d-ab9c-eb3ac2ded0b3 | note | Method - Document Review
0e8f30dd-f993-5486-a2d2-dbb8564b2dc6 | note | Frequency - Each element
c96a8c36-19b8-561d-a8f1-2c6f8988b2a9 | note | Category - HP*
a16a9d03-44fe-521a-a7ab-e5dc238affc9 | note | Responsibility - Surveyor, SE/PE/SPE
b0ae07c6-3e97-5582-b066-db57532df8e9 | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
f4fc45bc-2812-51c7-aeef-4d330c90b5d9 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
193573d6-f80f-5f79-9510-ca8d1fbd4cd2 | textbox | Name:
fb762a41-ef5c-5468-9d65-ba5c3ce1aae9 | textbox | Position:
026b5584-561c-5a57-9665-32cf20b67fad | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-030-CIV-Brunt-Clearing and Grubbing |  | ITP-030-CIV-Brunt-Clearing and Grubbing | ba5f7183-5cb7-4850-8f9e-16a2b3e2d0de
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
8e159dce-c0fc-5a2f-99cf-3f63a72657cf | note | Document Title: ITP-CIV-Brunt-Site Clearing and Grubbing
a88f30c3-1c99-5145-bf25-935e107a813c | note | ITP Description: Brunt-Site Clearing and Grubbing
8aaf5de8-344d-5041-b605-e15f7d3e74a5 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
e27646ab-89b8-53d1-a6d6-29edd40984ae | note | Discipline (e.g. CIV/STR/RAIL): CIV
920ca111-04bd-54e4-90da-30818ef50777 | note | Revision Number: 0
532cc76d-d04e-57e1-a6ea-f45a16479ab1 | note | Revision Date: 28/02/2023
82e97086-0839-5ddb-b3fb-7b539c347600 | note | ITP created by: Jason Lee
59706888-a445-5ece-bec2-9fb019c0a56b | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
41274045-7e03-5cfc-bfe9-519c34f415db | note | Reference - VicRoads Section 201 (Feb 2023)
| checkpoint | 1.2 - Non Dependent
bd9820d7-64f4-532d-8fee-fa48fbb1f7b0 | note | Reference - VicRoads Section 204 (Dec 2015)
| checkpoint | 1.3 - Non Dependent
ff055742-db8b-5e13-9cfd-f637d6ead5a2 | note | Reference - IFC Drawings
| section | 3. Preliminaries - Documentations
| checkpoint | 3.1 - Environmental Controls
f96b350f-03ea-545f-864a-b38eb5881247 | note | Reference - MRPA Environmental Management Plan
af3fc118-cf64-5be5-99c9-ba02ba6f89f0 | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified.
6dbbfc26-8422-55e1-affa-048b5ef04591 | note | Method - Visual
cda550b9-7fe3-5102-91de-7bc7888505a8 | note | Frequency - Where applicable, prior to starting Works
bcedc756-769f-5605-ab22-005225a0a0b0 | note | Category - WP
56a46289-ed66-5e8a-90a2-ddfcf63bad92 | note | Responsibility - Supervisor, SE/PE/SPE
5e538427-cb74-57a6-8a11-a991ccf2655a | note | Verifying Documents - This ITP Signed-off
| checkpoint | 3.2 - Vegetation Removal Permit
9ac1f8ab-382c-56d7-bdf2-a6a62e73b6a1 | note | Reference - MRPA Environmental Management Plan
0db262ae-7bf8-5837-80aa-6630a51c9ca4 | note | Acceptance Criteria - Prior to removing any vegetation or habitat:
cbd48a4a-b007-5686-8470-97831c088414 | note | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
bf7cecb2-352e-50d4-9efd-35dae4f666cc | note | ○ A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
41fd6293-8d9e-54b2-8a78-3147950d66fc | note | ii. fence and sign all sites nominated as No-Go Zones.
06ad73c1-e049-5a6f-a7d9-bf5706f9abdc | note | ○ Attach: Vegetation Removal Permit
6154d21a-0e38-585e-9761-c6e8e3d87ac7 | note | ○ Attach: Ecologist's Report
b1e4490d-b2eb-5217-bc2e-cc3742bfb6a7 | note | Method - Document Review, Visual
4d492a62-16a9-5588-af10-9405b8518f6e | note | Frequency - Where applicable, prior to starting Works
a9796e06-dcb1-587f-9ed6-8548d229a497 | note | Category - HP*
e3369c96-49a0-5435-8ac7-21428db73f04 | note | Responsibility - Supervisor, SE/PE/SPE
1a3fbe70-7c5d-51de-8dec-da1ca3a57604 | note | Verifying Documents - This ITP Signed-off
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set-out / Limits of Work
7033a169-8831-5f24-97a6-c236517ea004 | note | Reference - IFC Drawings Section 201.03
8537a109-996f-587a-8a85-2b37f9bf097c | note | Acceptance Criteria - The limits of clearing and grubbing shall be:
8a8dfa2b-fc13-5b6e-8042-1fc9299951a9 | note | a. the limits defined on the IFC drawings
a05ff1a4-0d08-5019-85b1-ca32ad2a75b5 | note | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
e2ba3099-74e1-5dd8-b68d-ec21ff8b0c07 | note | c. no more than the width required for completion of the Work under the Contract.
15fba5b9-eccb-5e77-8b1e-f35d7dd9283b | note | Method - Measure, Visual
2e69f213-391a-5e11-bf2b-5d037f0da46c | note | Frequency - Once, prior to starting Works
2c6f3110-4df5-5948-932c-184ec1c58a77 | note | Category - IP
c728fe2f-29ec-5b6e-acee-5dc637679bdf | note | Responsibility - Surveyor, SE/PE/SPE
ef0a2d88-5065-5813-9079-0feb05cd53d8 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.2 - Cultural Heritage and Areas of Significance
01235c33-bb64-5172-a9e0-4e097adc940e | note | Reference - MRPA Environmental Management Plan Section 201.10
bfb6425d-21bc-516b-8e81-4e2a4d14282f | note | Acceptance Criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
c1720823-2141-5b0d-a8c1-5e881087a3f9 | note | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
e5eb9ee8-59fa-5b38-a9fe-440bad117d04 | note | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
e0cba92b-b4c0-5b00-b9de-64c0afda7fd4 | note | ○ Attach: Cultural Heritage Report
73fe8de0-13fb-5600-b67e-b0a5a76614d5 | note | Method - Document Review, Visual
e08f5c86-2a8b-5b0b-bdd1-2e5dcd6213ff | note | Frequency - Where applicable, prior to starting Works
456c2ead-ba45-51e7-b0e7-7854231b1b03 | note | Category - HP*
cf49de65-7951-56fb-8dc0-14998e7e2fe1 | note | Responsibility - Surveyor, SE/PE/SPE
f82c6fb5-98c5-526e-b6fc-e066f807f40b | note | Verifying Documents - This ITP Signed-off
| section | 5. Construction Activities
| checkpoint | 5.1 - Stripping of Topsoil
940aa0bb-8a1b-5f02-bf75-7f530cbbb63a | note | Reference - IFC Drawings Section 204.05
2baf29db-b6e8-55cc-8eb0-3ccdf1360e2b | note | Acceptance Criteria - Topsoil shall be stripped for the full width of the formation.
e3b65fa1-d8c7-5c4f-9974-499305deae73 | note | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
6903c3bf-7231-5e09-9912-7a512f32e506 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
eab16182-d4bb-509f-ab26-89c45189cc4a | note | Method - Visual
62a58451-9947-5141-a966-224431207035 | note | Frequency - Each Site
37fc8206-75c8-5787-929f-8c027933db69 | note | Category - IP
a45ac57f-cdc0-55ca-9b42-cbb403be9a0a | note | Responsibility - Supervisor, SE/PE/SPE
c6e72ae6-4f2e-554d-8ef7-1c0774f1888d | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.2 - Stockpiling
b661b657-c5f7-5782-bec4-54e5f0c8ab0a | note | Reference - MRPA Environmental Management Plan Section 204.05
081fa4de-7415-5bfc-b7db-ccd28d0d30a0 | note | Acceptance Criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
db375597-8e73-5ce8-8808-e72e87dd760f | note | ○ If this clearance is not possible,additional protection shall be provided.
f3c0f298-03b4-5e3b-b1a3-5a8556e111b9 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
271dcf4b-62b2-55f7-b78c-b683e81ed91e | note | ○ Topsoil shall be re-spread as soon as practicable.
c5d68771-e5be-5c94-9855-212452342383 | note | Method - Visual
7d8c706c-0aca-59f6-87b9-3246decde5ea | note | Frequency - Where applicable, each Site
0b9e2cc3-3ac9-57fb-84fc-b7a16e81e2f5 | note | Category - IP
c0550552-c38a-5d41-9907-bc0f5224933b | note | Responsibility - Supervisor, SE/PE/SPE
cc9218f7-a511-5c3a-af0c-7843ac923cef | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.3 - Abandoned Services
ae39f2e0-e89b-5aa3-ae50-a9ec03a179f8 | note | Reference - IFC Drawings
6c26e770-2873-56e8-ae4c-60dd370f20df | note | ○ Excavation Permit Section 201.05
34a64120-1ebb-5b90-bc23-51ce4f37f07c | note | Acceptance Criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
6ba6291e-d66a-59a2-8db2-e0dfa48132dd | note | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
fd996bba-5400-5f03-aa9c-6dee2d5d5623 | note | ○ Decommissioned services to be disposed of in a suitable manner.
0e0275b4-7eab-5239-b65e-38fa022bb502 | note | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
23950f11-c3a0-5908-b3b8-77dee2632d4e | note | Method - Visual
27965389-0054-5019-934f-e50c32c1e0e1 | note | Frequency - Where applicable, each Site
5ca8853f-122a-5188-b5e6-b75c41b9c0b5 | note | Category - IP
6c76dd7b-7d4e-57b0-bf27-99c258c9413b | note | Responsibility - Supervisor, SE/PE/SPE
ebd33d17-7447-51f5-b7b4-1fe5f554afbb | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.4 - Clearing of Trees and Vegetation
7b3d7c5c-d918-5f57-9e5a-0cd3f7e8e4d3 | note | Reference - IFC Drawings Section 201.04
fd3faa39-c3ce-59b5-84b2-f655485e413d | note | Acceptance Criteria - Clearing work shall not be undertaken outside of the specified limits of work.
38a15f72-6519-5920-b85a-ecbdec9b76e1 | note | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
09e4c152-87a4-5be0-9535-4e8b2f6a0eeb | note | Method - Visual
52bc273a-82e6-5491-b15e-31030df188f6 | note | Frequency - Where applicable, each Site
8084b753-1945-5149-888b-d9d8b0c93398 | note | Category - IP
b12484da-fc0c-5506-9109-d8e11a14924c | note | Responsibility - Supervisor, SE/PE/SPE
012c3e38-2b70-579e-a478-5586ea5adfaa | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.5 - Grubbing of Vegetation
0b28bc1c-dfe9-57da-bf01-ac77c1004816 | note | Reference - IFC Drawings
596b9fa2-9fed-5afb-addb-1c05a03a3f85 | note | ○ Section 201.05
b88e69dd-988a-5091-9e7e-6435abeb4a3a | note | ○ Section 201.06
ce4a36f0-5e1d-5ca0-ac66-6816148dbe0c | note | Acceptance Criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
19edc6d4-7c89-59e8-b85f-83ebddf2d349 | note | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
30081dc4-c9d1-5b17-a466-b273981ca391 | note | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
fe4211e4-e3b1-59d5-9420-be89cea4db7c | note | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
eefc6cd6-1740-565c-b23d-4f8a63bade8a | note | Method - Visual
b15fe6d7-2385-59a7-9292-b45542e3adbd | note | Frequency - Where applicable, each Site
f7421ccd-c37a-5d30-a1ae-3b2c0249b7a2 | note | Category - IP
65f09293-0563-5db4-8098-29ab822c2d07 | note | Responsibility - Supervisor, SE/PE/SPE
d5d225c9-52ab-5c43-9d62-d587899aefe9 | note | Verifying Documents - This ITP Signed-off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Disposal of Materials & Vegetation
0af8ef14-2062-53c9-a8e0-47277ac9636b | note | Reference - Section 201.07
7e7fc2b5-3739-5c64-ad6d-ed6b7ab38d48 | note | Acceptance Criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
f882d4cf-9eda-5112-9f43-ba707575596d | note | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
669ece55-b78f-5055-9032-9ad6d2132985 | note | ○ Tree trunks and large branches shall be removed from the site.
9fde0a91-fec6-528c-9c45-113e89062d93 | note | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
cedd56a7-ccbd-5362-8e90-13e001535037 | note | ○ Attach: Delivery Dockets (for Items sent off Site)
0f07b41a-5f5b-593f-82da-24db428dbac2 | note | Method - Visual
d6e4dcec-b5b4-5954-b853-60381a53828c | note | Frequency - Where applicable, each Site
ba120b6a-8953-5045-81c0-19efd39162a0 | note | Category - IP
d7f6fa1e-19fb-525c-a844-9bdb7fe4d1ec | note | Responsibility - Supervisor, SE/PE/SPE
f978476b-5824-53a0-8ba3-3dec9af342b7 | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
481bc89d-e15c-5e38-9fc0-31567aadafd5 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
69aa806c-5b45-5302-adda-fbeb74558e23 | textbox | Name:
e8eadce0-323e-557d-b656-35c9b1ea2954 | textbox | Position:
f18bfb61-9d5b-5479-a614-7395a4212482 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-035-STR-Brunt-CFA Piling | itp | ITP-035-STR-Brunt-CFA Piling | b61f8fec-a5d5-4184-a4ff-0bbf1c503723
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
0aa960c2-e638-5872-aa47-dbadda66f16d | note | Document Title: ITP-035-STR-Brunt-CFA Piling
f9c2bf03-6063-5f79-b7ae-cb49968bc48b | note | ITP Description: CFA Piling
91b5e611-c235-5c96-a7c8-8ed00acd3ca8 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
d0d4aed7-b66d-5dec-be2a-1c85ce0314ff | note | Discipline (e.g. CIV/STR/RAIL): STR
5fd47d5f-b1b0-5a64-a1df-b4c862bfc5ed | note | Revision Number: 0
081f5b39-e865-58f7-8e44-6d5c50f75a46 | note | Revision Date: 5/05/2023
ae9751c9-bf32-5399-a1dc-b670b7814f7c | note | ITP created by: Yasna Naicker
bc737d5c-fa2c-5651-a507-b41c1d4fea6a | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
c1e55f20-2d9f-57b7-8203-0c51e766d5b2 | note | Reference - VicRoads Section 607 March 2015
| checkpoint | 1.2 - Non Dependent
22a5fd19-e18c-545f-9695-927bbb11be8f | note | Reference - VicRoads Section 610 June 2019
| checkpoint | 1.3 - Non Dependent
cfba98d1-6992-53fc-a685-eac8b646be78 | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
b5bc179c-f0bb-5513-80bf-e85ac73d5c53 | note | Reference - AS2159-2009
| checkpoint | 1.5 - Non Dependent
c1ae77b6-4ffb-586d-8197-7432ebf42623 | note | Reference - AS3810.1-2015
| checkpoint | 1.6 - Non Dependent
01ec5812-6224-54cd-986e-4d8e78bc4be7 | note | Reference - AS5100.3-2017
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
61fff819-1753-5ec3-8359-99ecbd4f84be | note | Reference - 610.07, Table 610.071
5675c286-19c8-560f-9362-c68423319d7e | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
c60d1012-9917-58fc-81dc-ba8beeaa8ad1 | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
04fae702-0112-5fe1-a8b2-105487c0adeb | textbox | Enter: Teambinder Material Approval number
43e9672b-aab9-53e6-af0c-e0db817db98d | note | Method - Document Review
f0411c03-a63b-5476-9b40-fd3c3e9d3438 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
7c034814-067e-50c5-93a7-8d94f9e6c325 | note | Category - HP
a4d62623-2ef5-580b-971f-67241c2893a4 | note | Responsibility - Nominated Authority
7166a5e4-2ddb-57f5-8469-136b586aa805 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
fd46d9de-df7a-54fa-80a0-0220f5568809 | note | Reference - 611.05 (a)
197357fe-355a-5da7-8385-dcf3c2832123 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
42f31bfc-b7cd-53b8-ac3c-d7302de1a2b9 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
739bfb7b-368e-5160-9d1a-56d91111df41 | textbox | Enter: Teambinder Material Approval number
576478af-b335-5f54-9f5d-df81f59da018 | note | Method - Document Review
99991d44-c451-5c21-bad1-e01183cde786 | note | Frequency - Once for each supplier, 14 days of award of contract
045e11f0-27f5-52d9-a43c-8b55bbaf3711 | note | Category - HP
153f2f98-e6f0-5444-a1b7-e859ae6896a1 | note | Responsibility - Nominated Authority
e9af8e13-551b-5556-b048-b65de482af4f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
2ec36ef9-6f09-5f32-8d83-dd4b69215502 | note | Reference - 610.26 (a)
872de1c1-522e-5102-ac60-257cda23adc0 | note | Acceptance Criteria - Wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads.
2eef4d22-1a56-516c-9528-6e8c6a67dcfb | textbox | Enter: Teambinder Material Approval number
b4f2ea8a-f740-51d8-9815-987481080ce8 | note | Method - Document Review
9dff2b56-8480-5113-854f-1dd599bb558e | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
a13589ed-c3b8-511c-b28a-2261bb3df2c6 | note | Category - HP
b90cc05b-20fa-5ce4-b2dc-31ccb076450e | note | Responsibility - Nominated Authority
fd976820-a9b8-5744-be65-16db7f905b6e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Working Platform certification
18193ce2-9108-593c-94fa-dfd9787bfee9 | note | Reference - Piling platform design
ac073311-34c9-5ea0-9de1-a902cda543bd | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement.
e015bbaf-e19a-52b6-a1c0-178db552aef9 | note | ATTACH: Piiling Platform Certificate
6262479f-4570-5533-9920-712e3b797ae3 | note | Method - Document Review
849f7800-378e-5603-a5b6-6eefe00491b6 | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
cbe10d9c-c85b-58f8-81f8-91ce069577ae | note | Category - HP
83a1d080-0c0e-5f85-a919-f93fcfd49baa | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
e4868708-efc7-5e7a-b7d6-7d0c8cd2f8c1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete CFA Pile Design
4ad5053f-6e67-5b6e-ae2a-b072afb4c33a | note | Reference - 607.01, IFC Drawings
09240cbe-a7c8-52a5-a69d-116b94f6fc43 | note | Acceptance Criteria - Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
28301354-041f-5079-b2b8-e4daf0ce03de | textbox | Enter: Teambinder Approval number
8472fd42-c3ea-5a06-9f5f-49f422ca6c6e | note | Method - Document Review
f5f374b7-11bd-5401-8917-2e6f53ec78b6 | note | Frequency - Where applicable, once, 4 weeks prior to the commencement of piling
45f9a7eb-eee9-51eb-90d1-433f4871c9c3 | note | Category - HP
9aa99a41-f1e7-55bc-b3bb-9cde323bd8c0 | note | Responsibility - Nominated Authority
58536aee-4be6-5d73-863b-ad06357aa892 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Piling Operations Work Procedure
2e4ecb90-dfe8-5db6-b9f1-3c9306d34c91 | note | Reference - 606.03 (a)
69a93ec0-f990-561f-9f52-3b1180a35ea6 | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
e8210c62-2a73-5a27-9d59-7a010b01ab58 | textbox | Enter: Teambinder Approval number
07fc85fb-c6ed-5529-82b2-cb87b23df484 | note | Method - Document Review
d7c4dec6-34ae-5846-9407-6e25f893ec59 | note | Frequency - Once, 4 weeks prior to the commencement of piling
9ab2cfb6-2588-5ace-ab3e-203c540dbd24 | note | Category - HP
ad532b41-6b9f-5cd8-bfe3-ac39efceeb46 | note | Responsibility - Nominated Authority
4f0df4e5-82f7-5c62-a0ca-e0d7ab5cc820 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Casting Under Water Procedure
9cf1162d-79f2-59b3-92c0-95f0d04ea05c | note | Reference - 607.04
2c1b9b44-fbfb-56c0-a50f-d71784221a7f | note | Acceptance Criteria - Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
5f833e8d-158a-56d8-a275-536e6b481685 | textbox | Enter: Teambinder Approval number
d80ceae5-889a-514b-a9f5-f31b458a8c9b | note | Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
8ed89d73-7b82-593f-877e-631e684ce762 | note | Method - Document Review
899879f7-78ef-52df-a02e-ec7117e4e516 | note | Frequency - Where applicable, once, prior to placement of concrete
364025c4-ab98-5fcb-8c65-f5364aceef31 | note | Category - HP
7b7e50da-f9c8-5cee-aad0-a84d6ee52d25 | note | Responsibility - Nominated Authority
f65a4fa4-35b1-5c3a-9cdc-b7045ffa40b0 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Dynamic Pile Testing Procedure
edd3aab1-cefd-5ad1-b5d8-078f886809cb | note | Reference - 607.07
8ee3bf09-700e-5c14-9435-6836952ec79b | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
7c1c8737-5710-5cc8-9b88-7cc0702cc60c | textbox | Enter: Teambinder Approval number
a8f8ec6f-66c2-511d-a9ca-6940dc3d4ac2 | note | Note: Attach Superintendent Dispensation/Approval if not undertaking this test.
a93b50aa-5240-5769-88cc-2eb29db6f48d | note | Method - Document Review
580c6004-3a3c-59ac-a22e-53f241eba7c2 | note | Frequency - Once, prior to testing
7d66b00c-996a-5ad3-b6ba-781d21ea5e02 | note | Category - HP
c62b6032-8e1d-5927-8287-5ac3bc13fbe8 | note | Responsibility - Nominated Authority
ad2f7672-6a79-5692-8cc9-8ba3c99b3e5b | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Pre-qualified Pile Testing Consultant
256f5573-bbc4-5975-b7d7-a1726f2a7890 | note | Reference - 607.07
0c2c3d9b-afac-588f-85cf-87e9b92b7439 | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
9bc73370-b743-5cad-b350-a8093ad28baa | note | Details of the consultant to be submitted for review to the Nominated Authority.
7ec44a5e-0c90-5871-9acc-d854515d4d8b | textbox | Enter: Teambinder Approval number
59e4b968-2d58-5bad-9d7e-d62d84e62b46 | note | Method - Document Review
31f3a859-ffd0-5c98-b236-654f3c5e4a83 | note | Frequency - Once, 2 weeks prior to testing
7b54256c-7621-5ad1-b355-fd8835ee392d | note | Category - HP
f1ebb6f2-bb55-51d5-9c7f-476a06c70165 | note | Responsibility - Nominated Authority
c59ff1a3-3625-51ed-a149-1d006670df32 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Reinforcement Welding Specifications & Qualifications
76c7b424-3d19-5010-a0d5-ae88821db508 | note | Reference - 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
93426112-fc27-51e6-8cfd-3f81f30ac2b7 | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
9566ec70-5a53-508b-a502-a94f87402045 | textbox | Enter: Teambinder Approval number
960110e8-e88a-5365-9219-42500a6a9d71 | note | Method - Document Review
acd0683a-6c15-5fe1-834c-6883989c5310 | note | Frequency - Where applicable, once, prior to welding
68add482-d74b-5335-a288-839ce03790ca | note | Category - HP
a96a6cfc-cb35-51c3-9859-ca2b4ef63fe1 | note | Responsibility - Nominated Authority
881a921f-fce2-599b-8e91-285cc2f73dbc | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
ec6a2c09-fb6e-5c29-816e-d7ae28548d9c | note | Reference - MRPA Quality Management Plan
7cc34870-5907-5e61-99c2-86aa5581708a | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
2aa6c8ef-e2ab-5f01-9b5d-295b41e54f2c | note | Method - Document Review
e972c1c8-d7f9-54ba-908d-b152cd45e114 | note | Frequency - Prior to starting Works and at regular intervals
a24f43fb-22ef-5424-acf9-1fac12da10a4 | note | Category - HP*
3fd06e54-517c-50a7-a0c9-6572b88571f5 | note | Responsibility - All
976cfc1d-a942-5563-b53b-85ff4c54e429 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out / Set-out of Piles
8750bee5-7c62-57fa-a162-b25902d5d749 | note | Reference - IFC Drawings 607.06 (a)
2c41c2b8-3de5-5869-82d7-a5d56dbbc58e | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
089ca947-5d55-5c57-91c8-22bb0f33da04 | note | • Ensure Pile Set-out is correct and working area is clear.
c3749257-33cb-5940-b876-ff51b69090dd | note | Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
84e3b278-29a2-5164-b7f1-85255f094a58 | note | Method - Measure, Visual
d747b0ce-56bc-5c92-841a-f72f957ec76c | note | Frequency - Each pile
567f59cf-2b69-5a36-98a0-d3d091f4280f | note | Category - IP
c4eb5a53-aab8-5d3f-87a4-99ef1860077b | note | Responsibility - Surveyor, SE/PE/SPE
5299ebf9-5242-5c97-a59c-4cf5b1b728fb | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Protection of Adjacent Piles
5a1b9bb3-b292-577e-a9cf-31b2a82b4420 | note | Reference - 607.05
7b54e630-577f-5b7b-b92a-66aab5290895 | note | Acceptance Criteria - Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
fe5b7f0b-4859-50b3-bbcb-c140e936b6bb | note | • Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 MPa.
ade4e829-b6a7-5402-99aa-9633bab87384 | note | Attach: concrete compressive strength test results, and Lot maps to show pile strength, locations and sequence of piling works to ensure pile protection requirements are met in accordance with VR 607.05
a993aa98-891e-5c9d-b837-145a2e07af8f | note | Method - Measure, Visual
06d00eb7-34e7-5ad6-a88c-abf4efd706a4 | note | Frequency - Each pile
363ea986-3b17-5f78-b651-752a1e459589 | note | Category - HP*
5ca95659-bb17-565a-844e-b93ee0454818 | note | Responsibility - SPE/PE
f67e3490-89ab-507c-921b-c7a8f62bc38b | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Reinforcement - Inspection
90b5255e-370f-5e44-93e9-cfc61c225570 | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
9c1882bf-8111-5b2b-a59d-a92272dfec67 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
2c2802f5-1a33-5aa6-b8c4-06ecf369a943 | note | • Projecting reinforcement is the correct length and location.
5924312e-76a6-5159-82f5-026018370a1f | note | • Splice lengths achieve the minimum length and are in contact for this length.
836b6004-482f-58d3-8c69-5aa0e130a5bb | note | • The reinforcement surface condition is free from dirt, debris and damage.
3d35cb49-b438-5dd9-b626-b4accdb2184d | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
2ab7b32b-4ed5-5e6a-a3e7-9ddc7e047d19 | note | • The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
4c18b7c6-ed74-516f-9307-58a6344ef842 | note | Attach: Prepour Inspection Checklist
ae51b4c0-55a2-516f-a508-39729517802f | note | Attach: Steel delivery dockets, checked if correct to steel / cage design, fabrication checked as acceptable, cage/splice lengths matches design.
8958a577-eb89-55ec-be46-63d15cc806b2 | note | Method - Measure, Visual, Document Review
b4cf6b91-ae5e-5492-955d-3eb47c7ba0c6 | note | Frequency - Each pile
b87b2c1b-ea7c-5c34-9d29-7619c4aa200a | note | Category - IP
17565e47-428c-521a-a5dd-1e71eacd0f92 | note | Responsibility - Foreman, SE/PE/SPE
39f49942-27c6-5b54-8e76-524906a75095 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Reinforcement - Electrical Continuity
5c5dafec-aef9-5b7e-ad7d-336bbdca139b | note | Reference - IFC Drawings 610.29 (d), 610.43
07196ca3-8053-5e94-806a-3bdeb853f188 | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
0d15d2b2-575e-517a-800c-607c4be36f4e | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
f75fe682-6b9c-52b0-a1ec-341aa8ad56ec | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
64c35a9e-f4f9-5673-9916-86f1283bf120 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
45ee079f-c0ac-5206-a4e1-cbb67ced3b7e | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
3dba28f4-9e48-5bf6-857f-d9ee1337797c | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage, and Prepour Inspection Checklist.
a2b7bbca-e01b-50a5-8c20-2b26d688cc35 | note | Method - Measure, Visual
20e7dc73-e228-5910-980d-33abde5b1737 | note | Frequency - Where applicable, each pile
9396d32c-d342-5a27-b9ee-696925eaa128 | note | Category - IP
fa676bf3-c194-5bff-85f0-43662fbbbafa | note | Responsibility - Earthing Engineer, SE/PE/SPE
02cce1d1-3f7a-5eef-b9bc-9933318573f9 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Augering Operations
c589cdde-24bd-5fe6-b9d4-201c71ad3d41 | note | Reference - IFC Drawings 607.04
4d3a9fab-e126-5e3e-a1fe-a88e73db204c | note | Acceptance Criteria - Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
702e52bb-4b95-5677-93e8-95db835138dc | note | • The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
2a0102c2-5c14-57f9-83f4-ad396a10673f | note | • Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
37cf969a-8d00-5ad5-b69a-16618446d6da | note | Method - Measure, Visual
d5eab16d-a068-546f-99cb-c197764b0fee | note | Frequency - Each pile
7387cf89-db8e-5d14-9a98-5bec8e8f928d | note | Category - IP
22664e86-f9ee-5575-9f3c-22794e7e66dd | note | Responsibility - Surveyor, SE/PE/SPE
2fc65949-4740-5e7a-a3a6-bd636f94ce07 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Inspection of Excavated Material
6176eb11-0554-56e0-85b4-363a58b1ad45 | note | Reference - 607.04
02bf8312-a1b0-5862-b08b-b57d4ef13197 | note | Acceptance Criteria - Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
c1fbd861-5733-510d-b602-662b110b1138 | note | Attach: Geotechnical Field Sheet or Report
151c352a-bdc3-5c30-986a-7298d24254fc | note | Method - Measure, Visual
f24f4c37-8ab7-507c-bccc-93c70f7d194a | note | Frequency - Each pile
44174ff0-f1a2-55f1-bd12-298f00babea2 | note | Category - HP
8de12356-fa73-5965-b741-eecc42823bde | note | Responsibility - Geotechnical Engineer
a01ca903-644c-5541-a42e-add00cb8bee8 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Increase in Depth Beyond Design
de499ebc-bb00-5382-8c98-2d03c1f9fd15 | note | Reference - 607.04 (a - d), Piling Operations Work Procedure
8efd0d88-778b-5e71-a081-92ca0d5f6542 | note | Acceptance Criteria - Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
459ec03a-9a80-5909-a38d-e11cae305d11 | note | • A full account of the changes shall be submitted for approval to the Nominated Authority:
bcd6b1c4-0bf3-56ef-ab4e-c078d6af71a4 | note | Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
f0139d5c-4716-5e91-a22d-0ea098e6dcc4 | note | Method - Measure, Document Review
5ae8bef4-3e81-5941-8067-8228b211037c | note | Frequency - Where applicable
cc5940fc-4ebb-5459-a51c-0d2feb56556d | note | Category - HP
31ced675-4ad3-5413-9cf6-da94b0afd3da | note | Responsibility - Geotechnical Engineer
ec990ccd-e27f-5843-82a0-fdb97180b16f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Weather Conditions & Evaporation Limits
0cd12fbf-eae6-5dff-b250-d4bdeba79fb1 | note | Reference - Hot and/or Cold Weather Concreting Procedure, 610.17, 610.17 (a) & (e), Table 610.171
313a061c-2adb-55f5-8191-a9285c321e59 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
f4e127ba-4532-545a-9d3b-e90ca9d9742c | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
13f8d3a4-f782-5965-8d5b-78f433f2bb7b | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
94c3b8a9-b6c5-5005-8dbf-826e8e8a2bd6 | note | Record: Required information on the Concrete Pour Record.
acf3e947-0d25-5f6a-9980-8ec5fdc55763 | note | Method - Measure, Visual
777c2318-8b33-5d8e-b1a8-a7339715a2e7 | note | Frequency - Each pile
02389c6d-783c-50ad-95ff-c04d9920636a | note | Category - IP
6355464b-9ae6-5c42-9d9f-a5d054ac00e4 | note | Responsibility - Foreman, SE/PE/SPE
d1712511-2c20-5ecb-baec-70a15e761c02 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Concrete Testing - Sampling Frequency
724a044f-36e5-5a17-afec-f10dac0fac86 | note | Reference - Site Sampling & Testing Procedure 610.16 (b), Table 610.161
8c0a9c8e-0bca-5473-9eca-c372cee673c8 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
ff87ea71-f0c1-5e97-9a62-c846cefd80c6 | note | • 0m³ to 10m³ = 1 sample
3605c8ff-e29c-5890-ba22-9182d16b803b | note | • 10m³ to 25m³ = 2 samples
e5339f0e-23fc-5ad6-ac31-bc5e8758141e | note | • 25m³ to 50m³ = 3 samples
d1b4ff75-108d-5bec-8923-d31d879c1e14 | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
7b47c896-72a9-567d-bf35-b7841254d1f8 | note | • For each additional 50m³ and additional sample shall be taken.
06d686ac-0ba3-53d7-ae76-4259a549ff97 | note | • where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
d116f5fc-831e-5055-b6d5-618f6be2fc74 | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
a2215a73-bd5b-5994-85e2-b5da16ce9aba | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
e6b25e08-8cc9-54c0-83c3-aab586782b19 | note | Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
1207547b-e641-5c0a-a2fc-c490d8b2e5c0 | note | Attach: Concrete Pour Record
df804b9b-05bc-52c4-975d-714a9ef5e85c | note | Attach: Concrete Dockets
ed41d273-5244-537a-a2f9-156a859f93df | note | Method - Test
1840d52a-1ce6-5488-b441-b36463f010a1 | note | Frequency - Each pile
d299b58b-f6ad-53f4-a887-e4b0acf55265 | note | Category - IP
2f8f2bef-e4a4-5d53-a11f-331c0ab7ddc0 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
e4129f3b-cbc0-512b-bfa3-4389ef7313bf | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Concrete Testing - Spread, Passability & Viscosity
f6e478a6-d64f-5712-889f-7d54a59f9f8e | note | Reference - 610.13 (b)
4f146275-01ae-5fe4-94b0-934a96e9e130 | note | Acceptance Criteria - Spread range = 550mm to 750mm
0e76f407-c748-5bde-ade7-584a25a8d4a3 | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
67ae64be-6584-5845-a4cb-f34345fe6be2 | note | • Passability = ≤10mm (aggregate height differential)
dbc2d120-5a09-5891-806e-40700db67d90 | note | Attach: Concrete Pour Record
49e214af-1886-51c9-b2b6-b4505f0a0f29 | note | Attach: Concrete Dockets
245a54d7-79f1-59e5-abba-aea25eda9685 | note | Method - Test
87f9bf45-3f4b-5a43-9c84-cf1d537c450a | note | Frequency - Each sample of Self-compacting Concrete
e53b91dd-a183-5e6b-bdbb-0527b7c0a761 | note | Category - IP
01c68b91-57b5-59b5-9afe-a366712db270 | note | Responsibility - Concrete Tester
a8532648-89e8-55c5-8043-3eaedabb39f2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Concrete Testing - Compressive Strength Cylinders
c62af0cd-d7ea-5e2a-b93b-a606c039874a | note | Reference - Site Sampling & Testing Procedure 610.16
1a4d2db6-ef58-5b38-ac16-d4327427e8fb | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample in accordance with VR 610.16.
21eead5b-08a0-5089-8c7e-eabca07e3211 | note | Attach: Concrete Pour Record
bae6ae17-979f-5f4f-a1fb-704267d5bac9 | note | Attach: Concrete Dockets
264accb4-469c-544d-908b-13b9b227a5d0 | note | Method - Test
2dfcf173-d627-5d28-a1f4-ebf3bcc3e47e | note | Frequency - Each sample
44a966bb-78ea-57fe-b3dc-6779a357f72a | note | Category - IP
66915a1a-73ce-5a45-b7b7-5ba351418534 | note | Responsibility - Concrete Tester
1f94d9c7-26c1-5c5e-bd2b-420f7c5eb505 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Concrete Placement & Compaction
775fd08b-d4bf-5487-b529-f02ed40c3679 | note | Reference - Piling Operations Work Procedure 610.18 (a) & (b), 610.18 (d) (i), 607.04
b54271a3-1c36-5a6d-998c-e4714c27b0bc | note | Acceptance Criteria - All concrete batches are traceable.
680e06a8-c42e-5d09-aaa9-304f22e23290 | note | • The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
10e67b12-d505-5fe1-98b6-7ba4c79fb93c | note | • The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
3f0cd7ba-d47e-5752-90fe-014320e63802 | note | • Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
fe86878a-89b1-5d50-81b3-8e7db06b0668 | note | • Concrete shall not be dropped freely from a height exceeding two metres
c7db1aaa-5354-5703-8112-1f1ad90b4c02 | note | Record: Required information on the Concrete Pour Record.
332191ee-7a22-5428-8f4e-fe636040bc43 | note | Attach: Concrete Pour Record
e5d829c2-d1be-5a17-89ac-0704121c4b9b | note | Attach: Concrete Dockets
8cd48764-ccd3-59db-be1d-2916c2528418 | note | Method - Visual
1b60ac25-8c66-5800-9f0f-b2e963d48025 | note | Frequency - Each load
c9bc8f04-340f-5263-a6bd-6003b34fdfdd | note | Category - SP
b8443c96-e362-57d3-a7f6-41632bdf465c | note | Responsibility - Foreman, SE/PE/SPE
a06d9733-e8a5-5876-8f21-5dba858bbecb | note | Verifying Documents - Foreman, SE/PE/SPE
| checkpoint | 5.11 - Reinforcement - Placement
d5b50a5b-63e9-5fd3-9583-93bdca1389a7 | note | Reference - IFC Drawings 607.04
af90d0b3-80c8-5f33-ab3c-325aad1153a7 | note | Acceptance Criteria - The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
84b70667-a4c5-5b1b-b79e-e5dbac27c41e | note | Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
9beac68c-b274-5868-bc9b-7a8cef9c7811 | note | • If the cage cannot be positioned into its final level, the pile shall be rejected.
a25a40b8-7667-5cdc-a74c-ae9d51065d0a | note | Method - Measure, Visual
a12fae45-dc95-5ddc-9aef-22ee3b6c7fb5 | note | Frequency - Each pile
8cfc98f4-ac2b-5067-bfac-142187e9419e | note | Category - IP
ef5b02e3-d19c-55ce-b7c8-78579864161f | note | Responsibility - Foreman, SE/PE/SPE
fef82a69-eb18-5d8c-858a-9bac81cf49f3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.12 - Cast-in Items
2a6283e8-4c17-5f34-a76e-ae0ca78d1080 | note | Reference - IFC Drawings
efae13c5-2ef6-55f6-a2e1-e9f60876d972 | note | • 610.46 (a), Table 610.462 (November 2018)
61e6f95d-86b5-57d9-b657-a11ff2446326 | note | • 610.47 (a), Table 610.472 (March/June 2019)
d763eebd-2d11-5e52-85af-734f751f51e1 | note | • AS3810.1 Table 3.3.6.2
730e9f1e-c900-55d0-95a8-3d03f9bce244 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
ae2512a8-52cd-5b95-8299-af6acbfb2889 | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
4ad0bf9b-d4cd-5f67-b5fc-b2dfcf10d472 | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
8780252b-bdfa-5874-9916-7d83892e94db | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
d331e6ee-fedf-5bf5-bf7e-b2e0deeb2106 | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
3a6a10b0-37a2-5a76-9938-5ad2a3506c2b | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
43964141-8381-55fd-b651-56cb4f8c27e4 | note | ii. Running dimensions of a group of the above = ±6mm
501fdcad-b4a9-51fe-9245-6ea9a4bff4ad | note | iii. Ducts and conduit location = ±12mm
8f0e2b56-e4d7-5f26-9d7e-433e93b33074 | note | iv. Diameter of ducts and conduits = ±3mm
6acc8164-a0e2-56ff-9df9-263c53bf103f | note | Method - Measure, Visual
71f1e1a8-ce48-583c-ad09-bdfd06198734 | note | Frequency - Where applicable, each pile
73b67de9-f086-57fb-924e-3b63112597dc | note | Category - IP
cc41d956-7d8d-507b-b64e-47b24e650f73 | note | Responsibility - Foreman, SE/PE/SPE
423480be-3135-552a-95c3-bfed6fcf59c1 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Pile Trimming
651659f6-4071-509a-a028-9a4e481fa681 | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 607.04
0874bf55-bc8b-5c31-ab05-bbe4db9468fc | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
3db87bc7-e555-5827-82fe-850f89e4007c | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
902b6ffa-ec9e-5b75-a814-18a9d855528c | note | • Any weak or damaged concrete shall be removed back to sound concrete.
d7ae451a-50f3-599d-9065-53eb762526e2 | note | Method - Measure, Visual
c237e938-dc11-541b-93c8-cecab930a8cc | note | Frequency - Where applicable, each pile
d69090fb-b133-5b2f-ac8b-492cbf2e076e | note | Category - IP
e49dfbb7-3857-590a-bc9f-c185292e6976 | note | Responsibility - SE/PE/SPE
4494a7f3-c2d2-5d7e-9972-bd1899d12f4d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Compressive Strength Test Results
d15ad762-e826-56d7-a4bf-a7e19f634473 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
43df1580-ce2e-5ba6-a441-daeab583cf61 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
e8fc75c0-45dc-5320-bf3b-e8c822702886 | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
d4512cad-9c34-5f36-b9c1-25bbdad12017 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
70203cdb-d772-50eb-a688-58617aa2beb0 | note | Attach: Compressive Strength Test Results
4502c68e-81bb-5c66-904f-8e506031a7ac | note | Method - Document Review
e9fe83bc-da66-5a92-b316-8ce3577ce6ec | note | Frequency - Each cylinder
58755d29-43e9-5b9e-8b68-70ed83b17291 | note | Category - IP
bce13450-e9ae-58df-8e97-0c9afe6190c7 | note | Responsibility - SE/PE/SPE
7442624b-4735-52e9-b984-fed1c804d24a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Pile Integrity Testing
7ff63f61-dd13-5093-b954-2e13eadc80ac | note | Reference - 607.07, AS2159 Clause 8.8
4467728d-acca-5b6e-a384-87473cb6d451 | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
618e7e64-e609-5f6b-8af6-aaba1d5789d8 | note | • Cross-sectional area = ≥90%
280ac7bb-131b-52ab-884b-42b412bb6424 | note | Note: To help ensure the Pile Integrity Testing is done properly, proper planning on site activities are to be considered, i.e. plan for PIT to be undertaken with minimal works around the area to avoid induced vibrations that may affect testing results.
311ce2f6-05ed-5f40-b7ed-93b57310b465 | note | Attach: Pile Integrity Test Report
fed01780-15ad-57cf-99b3-50bba918e984 | note | Method - Document Review
cb280dbf-4298-50a9-880b-694f017f495b | note | Frequency - Each pile
3694a9aa-2969-5817-b65e-3db6929c2475 | note | Category - IP
8bc3219d-c1f5-5bde-92dd-35213ba03277 | note | Responsibility - Testing Consultant, SE/PE/SPE
a10e8c15-83c3-5a37-a85e-90e9d4ba38d3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Dynamic Pile Testing
661d8995-283f-5577-8ec8-b69649d04a49 | note | Reference - 607.07 (b), AS2159 Clause 8.7
a6aa5a3a-720b-5daa-9d34-4ff05ec4bfc4 | note | Acceptance Criteria - Where applicable, Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
da1c4900-9fa8-548e-955d-496df4df7d55 | note | • Measured Ultimate capacity = ≥ values on IFC drawings
1c12ca18-d35d-59d8-987f-e852843442fe | note | Attach: Dynamic Pile Test Report
13132dd3-84ec-5c9d-b5da-f242e8799927 | note | Method - Document Review
8c04da0a-b056-56ce-bc58-74d7efeea9e9 | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
86bf9df6-d816-5de1-a6ae-d4bf06c2e3ed | note | Category - IP
363c927c-a311-5ab5-9b58-17c4ad6d0ca9 | note | Responsibility - Testing Consultant, SE/PE/SPE
943c1f47-79aa-5f4b-ae06-5922e21ca7d7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - As-built Survey
4fb1dcc6-5e95-547a-adf6-507977be6322 | note | Reference - IFC Drawings 607.06 (a & b), AS2159 Clause 7.2.2
82e7e41f-5d07-52dd-9d83-474b2055004a | note | Acceptance Criteria - The following tolerances apply to piles:
82fe87a6-38d1-5b06-86d0-a9fee5fc13de | note | i. Centre of pile head plan location = ±75mm
b233b546-0509-5538-b39a-ba639c894892 | note | ii. Variance from vertical or rake = 1:50
3262c4ba-6308-53cf-b3b5-f3520f209171 | note | iii. Irregularities in straightness = 1:100
887184cf-a4c0-5ffb-ae67-69271fb7b04a | note | iv. RL = ±25mm
67fc6ad7-37d7-5b95-ab25-50cae1996b2a | note | Attach: Survey As-builts / Survey Report
180fa052-dcfd-5945-914d-c5929eae4fa5 | note | Method - Document Review
242073dd-f787-52d9-96fc-0144684fc018 | note | Frequency - Each pile
9e3c0d01-a976-5b4c-b50d-8d034b304169 | note | Category - IP
4c2474d9-9e83-541b-b490-aa45af04e81f | note | Responsibility - Surveyor, SE/PE/SPE
94ad3d89-653c-56c1-9394-c87b943c784a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Non-conformance Report (NCR) Closure
2aa97275-b16c-53cb-8fd6-7d1f821cb847 | note | Reference - MRPA Quality Management Plan
004a505e-d85f-517e-a609-4d027731ddd6 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
1afc7120-8fdd-5853-b286-048a0b17d13d | note | Method - Document Review
af22082b-9447-53f3-8c35-71136a90d8b6 | note | Frequency - Once, prior to closure of this lot / element / Work area
680b5883-f204-53a0-b50d-0289f37263ec | note | Category - HP*
b6b9e98a-d2e0-5e6b-94aa-138dc0091736 | note | Responsibility - SE/PE/SPE
713af050-3b7c-512b-997f-fbfb92820536 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
28c9c095-1d3a-530a-8e77-2815ee15e916 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d986f432-74a5-56e9-964d-36757bb156a9 | textbox | Name:
5281f24e-9b97-59c0-86c8-b6bc9512399a | textbox | Position:
1ee3060a-fcad-5108-8e53-eaf8f9cf1bac | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-036-STR-Brunt-Pile Caps |  | ITP-036-STR-Brunt-Pile Caps | b4ffdd33-2c24-49db-b77e-bd3ab0e19a58
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
098f8cbb-b16f-5ba5-a8c5-0e5a8d868e20 | note | Reference - 610.07 Table 610.071 IFC Drawings
440d584f-7572-595a-97e9-b83a5b05a947 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
f8d85f64-1ee3-537a-a109-5047e709ffae | textbox | Enter: Teambinder Material Approval number
f712a817-1f1c-5b4a-a2ad-a3ed366995f1 | note | Method - Document Review
f3295a30-cb1c-5c8a-8f5e-2319fd53674f | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
018b73a2-4f89-5fe6-93a1-239bb3ee38fc | note | Category - HP
812f2c64-f726-57dc-833b-ed35a7a29248 | note | Responsibility - Nominated Authority
cca3fdbe-c2c6-5402-bb3c-9b7832e76791 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
9a5b8ae8-c176-5aca-9db8-87b7ac923590 | note | Reference - 611.05 (a)
e3baaa8c-50d9-50c4-91b8-7b87f3b485a1 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
4ba8642b-ac29-59a8-a6ab-467c0a25f67d | textbox | Enter: Teambinder Hold Point Ref Number
bbe1050b-ec9a-5f44-a700-6c8b688d325f | note | Method - Document Review
abcc6bdf-65c5-50cc-8c51-83a6cc015630 | note | Frequency - Once for each supplier, 14 days of award of contract
56da5718-0146-56f8-8335-f5855f68a6f4 | note | Category - HP
542b40b0-a3a8-5f1c-a021-bf8c439dbe37 | note | Responsibility - Nominated Authority
25fe6ad3-2176-55be-ac2c-45ed6a703636 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
f5182306-a9ca-5b9f-8f5e-0ac52757a04a | note | Reference - 610.26 (a)
ffd3b82b-7c1f-5593-a9ea-c5ba4469c020 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12%. Bar chairs and spacers made of wood, metal, plastic coated metal and site made concrete shall not be used. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
47585ae9-b0ee-5416-a604-c69472db9b43 | textbox | Enter: Teambinder Hold Point Ref Number
23bab01d-7137-5ee9-885c-1185ee2cc45d | note | Method - Document Review
53482a8b-5f0f-5456-a4f2-a1e19dd7fa1c | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
86e9b33c-3476-59f8-943b-211d8d4b60b1 | note | Category - HP
d8f08528-5738-5b7d-a954-ed0c0766dbe0 | note | Responsibility - Nominated Authority
772708e2-4bc4-52d5-907c-17967d4c46e6 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
aa1b76ec-f6bc-5e63-86ff-a2870dc469e4 | note | Reference - 610.17 (f)
7dc00732-e762-5209-9cca-d6f9bacdcf55 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
6227f7f6-86c6-5e45-8397-3c17c1bb10ff | textbox | Enter: Teambinder Hold Point Ref Number
dfd4bd8e-e9fe-5d3c-a67e-e75bebd406a3 | note | Method - Document Review
a7664b82-b560-52e5-b646-ad326e356aca | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
69133545-15b9-560d-9019-c64cbbed397d | note | Category - HP
9995aa5a-bed7-5a10-8f0d-866cec3f2cbc | note | Responsibility - Nominated Authority
7d0f841e-ae40-5c3b-aa87-246669504914 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
df343d77-5a91-5b13-95f8-c2fe8c58aa45 | note | Reference - 610.23 (d)
2c88a27b-4e5b-5fca-8627-710b811e524c | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
838e7672-9cce-576f-87f2-1f141ac3bd0c | textbox | Enter: Teambinder Hold Point Ref Number
f7831b20-bf6b-5497-93d4-b4f46577bda0 | note | Method - Document Review
191471df-abeb-5335-865c-86930d6d0e76 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
7452cfdb-26c8-523c-95d8-444f871ab536 | note | Category - HP
3d05fec2-a235-570d-bbbf-68bd0b026389 | note | Responsibility - Nominated Authority
688004cb-3a0d-5662-aea0-3d1df8296440 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
02553d14-aca3-5cb0-9494-a9736db49898 | note | Reference - 610.18 (a) (i)
d6049262-2162-527d-8b49-604bee995860 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
a7cc3dd7-7a23-5494-b7f3-d30eeb9233b5 | textbox | Enter: Teambinder Hold Point Ref Number
412f0b13-ab6f-5c17-b327-d8357d75cc0c | note | Method - Document Review
f616ea0e-6475-5512-879d-73ccf3846a89 | note | Frequency - Once, 4 weeks prior to placement of concrete
5806d0c6-fdd4-53fc-81cd-0c2f85598d27 | note | Category - HP
8a3965d8-0e9f-561b-9f71-9de3563c6c18 | note | Responsibility - Nominated Authority
99710cd4-4a3d-532f-a718-36fe0a5c12fd | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
11e93264-5ea7-5b67-91bc-1be690858dde | note | Reference - 610.18 (a) (v)
7cfe810e-fa8e-5e0b-9e4b-11de6b945037 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
12ee03ca-8ccb-5ecc-a49b-565390d39d9d | textbox | Enter: Teambinder Hold Point Ref Number
39c93cd6-f5f5-53fe-bfc5-c61861bd22b4 | note | Method - Document Review
a4d29fb3-ee9a-5cda-9919-1d079f6e5901 | note | Frequency - Once, 4 weeks prior to placement of concrete
83db0f00-1350-5e74-8a88-88ba3da9a1ec | note | Category - HP
355b3673-881f-52d5-b0e2-0de81210f696 | note | Responsibility - Nominated Authority
04380f09-0e8e-586d-8591-d123269dff00 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
51fd7a40-6c56-5aa8-a4e1-5b7b7120741c | note | Reference - 610.18 (a) (iv)
f1caeba5-c0e3-53f4-a2eb-54f4d556cdde | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority.
6edb911d-be2d-5fa6-93b8-9c27ca6f5b17 | textbox | Enter: Teambinder Hold Point Ref Number
f14b4117-34d6-54b2-980e-f766cfa389f4 | note | Method - Document Review
9e3d0734-9472-52ef-8dbc-b68333b2376d | note | Frequency - Once, 1 week prior to placement of concrete
af1aed21-bbeb-513c-80e4-f68e01ad4922 | note | Category - HP
7662a40d-3c79-5789-9b86-daaf5597fded | note | Responsibility - Nominated Authority
10d3c5f0-f85d-50ff-b073-6419bc94b89e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
a44284f2-d9f7-505d-9119-2446530b58ad | note | Reference - 610.17 (a)
bd78e9e5-92cb-52cb-a848-ba5928132145 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
34b66f28-d37e-55f3-865b-470702efdbb0 | textbox | Enter: Teambinder Hold Point Ref Number
c16a2413-0475-5677-9160-d50a63e06da9 | note | Method - Document Review
5767eb76-8d4e-5918-9f94-2d99c7d8129f | note | Frequency - Once, 2 weeks prior to placement of concrete
b0e1274d-2c7b-5a85-80ff-f81d67e7cbdd | note | Category - HP
ea74d491-7d10-5bb8-be26-85e062d1a404 | note | Responsibility - Nominated Authority
d6fcaa57-97b1-5a85-8e64-664ce099f9bc | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
85014965-373a-57f7-84a4-265b306c89fd | note | Reference - 610.23 (a)
243fcd1c-dfcd-59f6-9314-5a1af354cb71 | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
3a78b946-4ae4-56b3-9cfd-fcd0668f9d37 | textbox | Enter: Teambinder Hold Point Ref Number
4531e6be-1ce7-55d9-86f7-0047868056d1 | note | Method - Document Review
ce397625-3a26-5014-94e5-f7926460cc6b | note | Frequency - Once, 4 weeks prior to placement of concrete
ccdd4086-9409-5d30-a79f-ae31eb840d65 | note | Category - HP
a080db56-cb10-54b7-9824-73251cd09552 | note | Responsibility - Nominated Authority
1fa566ca-ff79-5bea-a51b-c12b104ce2a7 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Concrete Drilling Procedure
d02111c9-3663-5578-8608-f9d3ae273b4e | note | Reference - 610.46
f4b068aa-2fbf-549c-8a11-359a5d71f800 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
51f971b6-34d5-5d26-98cb-3a6e9f3a8f01 | textbox | Enter: Teambinder Hold Point Ref Number
f1c7e833-e86d-54e2-aa3a-0dd508d7545e | note | Method - Document Review
6bc4e780-2ec1-5d14-bea6-94e16d881333 | note | Frequency - Where applicable, once, 2 days prior to drilling
3ce4a568-d872-56be-867b-5cf24b920bbf | note | Category - HP
be6bee66-a562-5651-bd79-596652f10e89 | note | Responsibility - Nominated Authority
7d111ff8-9331-58aa-8ba6-7e92560dd2cc | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Temprature difference measuring-Calibration
a0454849-f6dd-5880-b529-5a866b601461 | note | Reference - MRPA Quality Management Plan
0df6f689-124b-5494-954f-8f27ebdae715 | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date. Attach: Calibration certificate
77e08991-58ff-56f6-a6c9-297e709d3590 | note | Method - Document review
61c897b8-4d76-5955-b7cd-18358574c9bd | note | Frequency - Where applicable
8696ea57-93a3-5729-be50-acf2129a9355 | note | Category - HP*
539d1f40-283d-5d07-8dac-0e639cd8eff3 | note | Responsibility - PE
3b17d02e-81ec-54f4-b07f-4b1f76a4a277 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
3209893c-c0cf-5f8d-84a9-2f97032316d5 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
d14f2fcf-3297-5b7c-99a4-7f13f087bd96 | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
d4f66754-849b-5b28-b0af-9a914436e9d9 | note | Method - Document Review
d0252a74-d461-5a2a-b342-ad52c2ec3c61 | note | Frequency - Where applicable, once, prior to welding
b6bc1b00-4974-508f-9bcc-de90da54004e | note | Category - HP
48e9b073-eb69-5d6c-9ffc-382c55c0a56d | note | Responsibility - Nominated Authority
4a32f467-83b1-5176-ba3d-dc1335617445 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
e388ce43-9895-510f-a339-aa447144bc7b | note | Reference - MRPA Quality Management Plan
a9dc8304-d5ea-58e3-94a6-ae026935d1d8 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
5ca144d6-20b3-5461-87b4-56eecaec5d0b | note | Method - Document Review
f2b50cce-7042-5016-8e03-4617c7f4ecd6 | note | Frequency - Prior to starting Works and at regular intervals
21805050-d3e5-5d0b-a67e-84f4d3411997 | note | Category - HP*
cdf5209f-15e6-58e1-a23c-a2b5bea1346d | note | Responsibility - All
09642fee-c2fa-541d-a206-6529bad3a30b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out
ce15e68b-50ea-5c65-8508-11a7105c71d5 | note | Reference - IFC Drawings 610.47 (a) Table 610.472
cf484311-050b-5b76-8297-13304e5422ac | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element. Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
f3665e28-0538-53be-9e2b-0164b26c77c4 | note | Method - Measure Visual
f000f582-cd35-59f7-ad04-b6609b40fbbf | note | Frequency - Each element
e98a011a-199f-588e-adc2-2b54a63c4ce8 | note | Category - IP
916b6110-d987-582b-a435-887e27ccddc9 | note | Responsibility - Surveyor SE/PE
8bd8aab1-dfe7-5f87-bb3e-d09bd793c183 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Piles - Completed Prior to Construction of Pile Caps
c61bb648-eb1d-505f-9817-a9e10720d44c | note | Reference - IFC Drawing
c57d8280-e42b-51c3-a6fd-509758e4c329 | note | Acceptance Criteria - Related piling Lots are closed. - Pile design strength is achieved - Integrity and Dynamic tests performed and interpreted (if applicable) - Pile is broken back to the design level - As-Built Survey performed - Related piling NCMs are closed
5e6cfee2-ba05-5a8a-bee4-733674f62998 | textbox | Enter: Relevant Piling Lot Numbers:
c456396b-2b4f-5787-b834-a83ffc4ab3f5 | note | Method - Doument Check
54267abf-b229-5597-b058-4a688f307b14 | note | Frequency - Each Element
419d6b2d-4f47-506f-9a60-5f837e41f514 | note | Category - HP*
e95aa341-c3e4-5444-bd6e-3f98b1a701a3 | note | Responsibility - PE
c9386a57-73ba-5f80-acda-1e02622a1c7b | note | Verifying Documents - This ITP Signed Off Piling Lots Closed-Out
| checkpoint | 4.4 - Excavation support
4ea0c2c0-769f-565d-8442-5b5ce579f9f5 | note | Reference - 602.02
58d25467-8960-526f-b4c6-ea4d4d30addb | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal. Where applicable, a PTDT approved for use.
44eef87f-4d1b-5160-964d-b36e7f13aa90 | textbox | Enter: PTDT Ref No.
485751f4-4486-50ff-9493-4281e361347c | note | Method - Document Review
7edb9410-5a16-57e8-be9b-ab1fe8f55c38 | note | Frequency - Where applicable, not less than 10 business days prior to excavation
bcfd5a4e-16fd-5f5c-9744-8c9202278145 | note | Category - WP
b912b57c-58ed-5c75-96cc-30c2502005df | note | Responsibility - SE/PE/SPE
dddb85e6-c706-5f9a-a591-b5fb0f24d1bc | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.5 - Excavation Inspection
7a998f3c-a6b4-50ea-a8ec-b9b8f0cd26c5 | note | Reference - 602.03
e2b1a4df-5e84-550a-ab32-9566289ad1f0 | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
4db0caa9-82ef-5bd8-a39b-00d7f5ffa12a | note | Method - Visual
82f60e4b-cd65-5567-864d-6baaafa60506 | note | Frequency - Where applicable, prior to placing blinding concrete
9c85cb4c-db68-5cbe-ae52-822617255102 | note | Category - HP
3245ec29-4f9b-5c0b-9e99-b5f2239b840b | note | Responsibility - Nominated Authority
75f39ccf-44be-588a-adb6-90021ebdd9ab | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
a4839947-0c63-5e62-acf3-c5aec3417913 | note | Reference - IFC Drawings 614.04 614.05 614.06
d761bcee-ca5d-508d-b3da-b038cea48dea | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
dde44b48-b786-5b73-a1f8-72fc75482562 | note | Method - Document Review Visual Measure
345d8b74-72b1-50ad-a8ff-7e3e4b4794e9 | note | Frequency - Each type of element
a8ecfc0d-0698-574c-8fc6-34f6127695cf | note | Category - IP
f31825ed-3262-5942-8adb-6ee7b529cba7 | note | Responsibility - Temporary Works Designer Proof Engineer SE/PE/SPE
6f6f4e75-40fa-5392-98ad-e900c66b1d49 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
25ea7377-8e9b-5f64-8930-a90f52c9dc94 | note | Reference - 614.08
4aa95979-26b0-5687-841b-8a8e5ac59a8d | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Pile caps with heights greater than 2.0 metres Any member for which self-compacting concrete is proposed. Attach: Attachment A Attach: Attachment B
abdab0c3-ee7d-5653-b58a-07c260e22436 | note | Method - Document Review Visual Measure
5e1d66f9-07d3-5413-9cdf-0b75f90bc163 | note | Frequency - Each element (where greater than 2m)
9056429c-a03b-5ec1-9c50-5e93296dbd28 | note | Category - HP
2a809e8d-d10b-5692-89af-9df1e9994827 | note | Responsibility - Temporary Works Designer Proof Engineer
ed93240b-c595-5089-ba26-0cc5f50d070e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
b969eda7-182d-5517-9ed6-7dd5395dd4de | note | Reference - 614.08
4429d295-0d32-5954-b55c-7c6a1d1ea8ca | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Pile caps,with heights less than 2.0 metres Attach: Attachment C
29e85043-0873-520c-9e0b-ae284f2ca9b1 | note | Method - Document Review Visual Measure
82ef2331-da67-5c8e-bb4e-67823690c818 | note | Frequency - Each element (where 2m or less)
3880e2ee-6beb-51ca-a094-3921ba29b5ec | note | Category - HP
4d87cdb7-2b58-5408-b11e-4d6e893c136b | note | Responsibility - Temporary Works Designer Proof Engineer
52d4b6c6-297a-5807-a010-c0f1135bbc6c | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
a756eefa-5fc4-532f-970e-24f60fcda23e | note | Reference - 610.47 (a) Table 610.472
4c3c6924-b846-56e5-b2ed-1d3804e9a136 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
892170e0-eec9-5d2f-9513-6a01433abcfc | note | Method - Measure Visual
533bae3b-893b-5c55-bc12-b1aa09ea202e | note | Frequency - Each element
58ab9f30-d3dc-54ae-b1d7-27c1dfde181f | note | Category - HP*
f92249e5-0f58-52e2-b8cf-eec1b1443ffc | note | Responsibility - Surveyor SE/PE/SPE
e67159f0-57e6-5836-9bfe-4fd93f33027e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Reinforcement Placement
e8cf548b-4a76-5604-88f6-5af7249f61ac | note | Reference - IFC Drawings 611.06 611.09 611.10 611.11 611.12
f935207c-3926-5ada-a018-1191b97e86d0 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
5f959ebb-bb8e-58a3-8928-0871cadf5fa4 | note | Method - Measure Visual
999ca954-48a7-544d-80ef-e06447150c6a | note | Frequency - Each element
6bcefbad-0866-53f7-ac92-660412f1b9db | note | Category - IP
f31eccae-8815-51a4-9690-d6d0274d2484 | note | Responsibility - Foreman SE/PE/SPE
b8d6d75c-fd2b-552a-b848-3b25009e5389 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Cast-in Items
74032e67-0a68-5ac5-a62e-4430d341fa43 | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
19eff7aa-b5e2-5175-be09-119875dd996c | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm
07bae29a-ab97-53a6-95e5-079116261330 | note | Method - Measure Visual
10c99e81-0598-5305-87a4-0dcb25b72bf5 | note | Frequency - Where applicable, each element
5b5cd102-82be-51da-af46-d500cebfe5f5 | note | Category - IP
b7b13819-5351-59e5-a634-0b06a207bfb0 | note | Responsibility - Foreman SE/PE/SPE
518f4944-6da8-5e27-a327-b032fc5156cc | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Thermal Differential Monitoring
b3dbe9ee-97a3-52e0-bbc4-562e6ebe8f33 | note | Reference - 610.22
43b37f9d-ed19-5286-99c7-dde0352682ac | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints
1824cc2e-619b-5fa8-a9a6-ef7ae0205b30 | note | Method - Measure
10e6ae45-50fc-5fc2-9f9c-944d23e2eb1b | note | Frequency - Where applicable, each element
92ee9284-1a01-5f1e-bb32-1c50ae9dbd00 | note | Category - IP
68505c5a-4573-58f6-a9f8-4ee5407859f2 | note | Responsibility - Foreman SE/PE/SPE
59066a98-70c4-5c2f-b3da-91094bf775bb | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Pre-pour Inspection
a8418297-a8db-5adc-b9f4-834705652d17 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
2a670680-9925-5b26-9f6b-efc981610529 | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms.
f6442cdc-a37a-5464-922b-e3725801d92f | note | Method - Measure Visual
0d033ef3-9c0a-5e3e-be91-4bf4e8aee380 | note | Frequency - Each element
2e66489e-4e71-5094-8a1e-0bde763030d4 | note | Category - HP
a9a01ec2-6180-5e0a-8767-d59429059993 | note | Responsibility - Nominated Authority
1935b835-6d91-54e1-8d02-bbcf732855de | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Weather Conditions & Evaporation Limits
52d2349c-307e-551d-b120-6f5dc3623c04 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
e019b690-805f-5104-9f29-7d5012ef03c7 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
861237e2-651c-56c4-a4d1-2de5a89ce4f0 | note | Method - Measure Visual
f5f08055-dd6d-5b1e-88a4-c1a3be708423 | note | Frequency - Each element
feee0e70-eef7-5d1e-ad70-9b4a8ad524cc | note | Category - IP
95b32c73-613c-53a0-bfd7-279a58006522 | note | Responsibility - Foreman SE/PE/SPE
a2c513c3-6ac8-5ca7-a982-987f97e867f1 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.1 - Concrete Testing - Sampling Frequency
49628ef9-9b11-569f-83f5-aa2141365d2d | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
cbd55bc6-cbf6-5cb5-bc04-6343ada4578c | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record.
c36f7e20-5697-545d-80f2-d8acd21fbb80 | note | Method - Test
894c0213-360e-51c8-a157-99bdfa938bca | note | Frequency - Each element
88b84979-b791-5889-ab83-7add31bef937 | note | Category - IP
4757910e-e230-5800-88ef-1215b8b323bc | note | Responsibility - Concrete Tester Foreman SE/PE/SPE
dce900ae-6e0e-56a6-8fb6-31e3cbb8e82e | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.11 - Concrete Testing - Slump
adbe7890-fdbf-5c2c-a067-2eecdd318fdf | note | Reference - 610.16 (c)
7c757053-1731-5391-b78d-86b406c6ce79 | note | Acceptance Criteria - Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record.
d3cb471a-9cba-557b-8543-a98346f2488d | note | Method - Test
19d2de68-c9ef-5c6e-852c-fca524efb403 | note | Frequency - Each sample of Standard or Superplasticised Concrete
a52de42d-dc1e-5a4e-8166-15cd8b4f9fbf | note | Category - IP
894fe283-17cf-5666-a2e5-9f8296973af7 | note | Responsibility - Concrete Tester
6d31fab1-8b11-5f40-96d3-45035d9229a8 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
059938be-7222-59d3-84dd-d4e3101c0eb1 | note | Reference - 610.13 (b)
21c16234-0814-5e54-8d5d-bcee18e0aba4 | note | Acceptance Criteria - Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
07ddf00c-2422-599b-9e61-5871eef2e8f7 | note | Method - Test
470a573c-84e7-5aee-8440-524fdbaac5e9 | note | Frequency - Each sample of Self-compacting Concrete
f7dfdddf-4c64-5a28-93e6-96ab498d3240 | note | Category - IP
72a4aeb1-a877-5339-8bbf-dc11f48586a8 | note | Responsibility - Concrete Tester
8d393093-43a0-5420-b944-23209e44acfa | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
784217b2-cd71-5d98-92a4-9561a48f4bbc | note | Reference - Site Sampling & Testing Procedure
b71cc5db-dc01-5ff2-b149-32174bed1bf3 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
65b49233-8e98-55cb-a313-6f0a9a2aae36 | note | Method - Test
2ebfe147-c255-5ec0-a115-0ce9b7c7edbf | note | Frequency - Each sample
ca4113c2-b1cd-5294-9817-90339ff156fc | note | Category - IP
3355880a-5d21-5d36-a0de-257c41e22b77 | note | Responsibility - Concrete Tester
36e91db3-a563-5f66-a905-1c57eb6d4fbd | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.14 - Supply & Discharge Rates
d6d41efa-8e54-5e3e-99b2-640a36825c0d | note | Reference - 610.13 (a) & (f)
9304e8a3-f9f8-5b1b-aba7-43c2988c7693 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record.
a7eb4195-110b-5d2a-965c-2dc8a174cb51 | note | Method - Measure Visual
ece1186d-ae13-5ed7-b0e8-94f8223ca23c | note | Frequency - Each load
6af35a40-7fee-5573-8e89-566a34f6666e | note | Category - IP
31700686-168a-5811-9808-c26a924f8c36 | note | Responsibility - Foreman SE/PE/SPE
5a191b49-e06d-5c11-bdbb-b4f83cb5d3fe | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.15 - Placement & Compaction
1d9cefca-7f2c-5239-9b40-1dfcd720f1b0 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b) 610.18 (d) (i)
6d4ae2b9-5fde-57a1-9a6d-0776ac97d12c | note | Acceptance Criteria - All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets
f936e992-53fe-5bb0-b51a-45f88403bd62 | note | Method - Visual
20ac63c1-21d2-5c9d-8220-12cbe0173a65 | note | Frequency - Each load
e797608e-9e37-5d61-82c6-42a8b0f9205b | note | Category - SP
2097c9bc-d0ae-5b1c-9532-cf1c3639b103 | note | Responsibility - Foreman SE/PE/SPE
3be2b370-367f-5f39-87f8-b2d44f2ee641 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.16 - Surface Finishes
d24d3199-f298-5213-9ec1-7d7931425e70 | note | Reference - IFC Drawings 610.31 610.20
86002295-ed83-516b-8aa8-41d5c81b937d | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
22bf0399-bfe3-5bdb-862f-7a4c2cb3cfd4 | note | Method - Visual
d77dd1df-4f54-5d4c-ae84-71b48acf2c22 | note | Frequency - Each element
2ef4dbee-e43f-5e4b-adcd-955980b26c22 | note | Category - IP
bfa48b61-403e-51aa-8931-e9851827efda | note | Responsibility - Foreman SE/PE/SPE
cce04cbd-e8be-50f9-8b5b-8e143e927bb5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.17 - Curing-Top Surface
21106287-c6c9-5dfd-923b-f8c69a96c9f6 | note | Reference - IFC Drawings
db24251e-7158-56ae-b5e3-79ab765ffd06 | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
a8c3717c-33f1-557f-8205-e8f6042a6bf2 | note | Method - Visual
dd81ecf0-79c0-5369-8945-a416b99ee15f | note | Frequency - Each element
c19d6163-e362-561b-a4ea-290694eb23a5 | note | Category - IP
6949eefa-03e7-57b6-a949-6ea8057f1a69 | note | Responsibility - Foreman SE/PE/SPE
a3ced9e4-0561-510e-b599-778f6ac3a749 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.18 - Curing after formwork removal
1177183c-8c8a-537f-8c4a-8ca7b9cda6e2 | note | Reference - IFC Drawings
bfd61cc5-7b35-5ab3-9798-5f3b6996b73e | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
6916ef18-d578-50fa-afd5-25751c66017b | note | Method - Visual
5a946f86-3d4c-5bb0-b88f-35e1c0b5acb2 | note | Frequency - Each element
c2ae9517-a300-5f31-aaf1-20c5dfa786da | note | Category - IP
fe1a2b81-8fe3-5a42-b718-ef536ec1efa5 | note | Responsibility - SE
d739062c-1955-519d-9660-76e375af4ef8 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
180f3af9-db14-5361-97f9-552ab465d6eb | note | Reference - 610.22
e9c16f31-2d63-5c0b-b033-440ca8d6aa36 | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints. Attach: Thermal Monitoring Report
397aee8b-0cca-5789-b7d5-3b89e2722d9e | note | Method - Document Review
d69cb643-31fd-52a1-9fa9-7429ea02ad73 | note | Frequency - Where applicable, each element
d56c6635-96ee-5d35-bcc8-f72c250f09ef | note | Category - IP
6337281c-953e-51a5-88b8-74e9182e22bd | note | Responsibility - Foreman SE/PE/SPE
3bc3103d-8daf-59c4-aa40-062bf039f9e8 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
d7d92cdf-7538-5a99-887f-4263b9077cb0 | note | Reference - IFC Drawings
e0a02ec8-5468-5aaf-b12d-61e9561d7a1e | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
c5134ead-afd7-511c-9428-a6f68cc2f97d | note | Method - Document Review
9f503083-889b-53c1-a38a-06928eaced2b | note | Frequency - Where applicable, each element
7da1fb81-ed75-5f83-b5da-ba43b4386943 | note | Category - IP
7b0d1eb5-d8ed-5458-a188-98a50acac138 | note | Responsibility - Foreman SE/PE/SPE
6f276df5-bd3c-5f6d-a5b3-80fde98c3bb1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Surface Inspection - Cracks
8135bdb3-3f5b-5c02-a5a1-611791b02ca3 | note | Reference - 610.24
671c3703-6228-51cd-9f4d-42a4b89ca8ba | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1) If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
e56636d0-b71e-5196-a56a-6427c4da5d50 | note | Method - Visual Measure
a8a83e94-bdd5-5fcf-8885-9772f90403b4 | note | Frequency - Each element
2f4e73ad-7a09-553c-bd73-fa04d8dddf5e | note | Category - IP
58a84b2a-4317-51ee-b803-6d827c9d0530 | note | Responsibility - SE/PE/SPE
017c7c26-b0d4-571d-bf49-4e416de2ea74 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Surface Inspection - Surface Finish
e338adb1-c2c6-5f21-b13a-93617fb156f5 | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
2732711f-abb4-5929-8d78-d0159f97b4ac | note | Acceptance Criteria - Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
0a2c0c57-2c8e-5690-aacf-2c26294f50d0 | note | Method - Visual
505f59db-423d-58d6-9a00-b9436aa219dc | note | Frequency - Each element
50cb94fc-5c3a-5fb0-a6dc-9a2f7a9f41bf | note | Category - IP
b6f07abc-b362-5c19-a91e-4d8f549561ed | note | Responsibility - SE/PE/SPE
18d89ee0-1eff-5033-b9e7-328ea8894424 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Measurement of Concrete Cover
9c04e3e0-47ec-5c78-9d7a-88683570dddb | note | Reference - 610.34
274c1769-1da8-5123-8448-d801b4d0c376 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record
9cd3f90b-1132-5e50-82b7-3584757cdbaa | note | Method - Measure
565212a3-3f9a-52f9-8ff0-f96d0b8030c1 | note | Frequency - Each element
79e6f8f0-dc6f-5e30-bce2-6eed0e444c52 | note | Category - IP
fbeb93bc-13e8-582c-a824-a7a8c0be6448 | note | Responsibility - SE/PE/SPE
6d441370-0c64-59fb-b1a6-285300ed16f6 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
3ae1967f-7536-58e9-831d-6cb6f3bec996 | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
ce716b6b-c005-5d03-aa7b-174c644cd372 | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour. Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure. Attach: Concrete Test Results or Maturity Test Results
2a478ee0-8c9d-5937-aa30-c976ef70df12 | note | Method - Document Review
5024904e-fd6c-54c2-ac7a-88083c407e4c | note | Frequency - Where applicable, each substructure element
76141904-b90b-5645-b555-d1149325e74a | note | Category - SP
79ac799c-26fe-535c-8569-b8e41383db16 | note | Responsibility - Foreman SE/PE/SPE
5dc8cd0c-6c6d-5a80-910e-ae04c0bba17b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Compressive Strength Test Results
49b05607-c868-5f9e-a4ff-b2f17444e919 | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
7019dc92-4d64-58eb-9b20-96f1ecedee0f | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
91f9378e-7d6b-5b3f-8de3-054ef2f4151e | note | Method - Document Review
e7447507-9e95-5994-803b-99ee192cefe3 | note | Frequency - Each cylinder
5a063d64-0095-59d9-b590-642d3a3fc8f2 | note | Category - IP
f78635f8-b362-5bca-8cd3-867093b9298c | note | Responsibility - SE/PE/SPE
aabdd767-7979-5168-8e07-12f403eaf0fa | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.8 - As-built Survey
4e787d84-d422-57b9-87fa-a4574e74bf81 | note | Reference - IFC Drawings 610.47 Table 610.472
962cdbb0-781c-54a2-beeb-94d0a523b697 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report
5b975817-1518-573c-8f41-0a7016b9d07d | note | Method - Document Review
765bb70a-b6e9-570e-9716-13a64ea836a0 | note | Frequency - Each element
d5c19e56-f3e0-57a1-b37b-605b35871e84 | note | Category - IP
92612b34-43ab-5aa7-8161-a063acf24b74 | note | Responsibility - Surveyor SE/PE/SPE
6b39aee2-7915-5ae9-b374-bbaeb333ac89 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
6a4afbfe-1b73-575f-b113-932a5654c0f9 | note | Reference - MRPA Quality Management Plan
4522cd81-a806-539f-8fcf-188d6c7462d8 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f016c3da-ccb4-5fb0-a86d-104b8bac0380 | note | Method - Document Review
d9f9b507-14f0-5884-b597-9ad21ce95c55 | note | Frequency - Once, prior to closure of this lot / element / Work area
d0b4a905-4103-575e-aaf7-f7a5c4f2f428 | note | Category - HP*
102165b4-8eb2-51ad-acf8-cfef477a884a | note | Responsibility - SE/PE/SPE
6001f37b-89fd-56e1-8d62-e505adc23557 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
e68c1839-171a-5fc5-9e3f-fc66ae4fb0e3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
817ce759-d9f5-5c9e-8bf7-b580ad3cad02 | textbox | Name:
afe8fcbe-1e68-5e0e-ade5-7f30bd2dcda5 | textbox | Position:
a41be08b-b9c0-58f5-a862-f0a70144a852 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-037-RAIL-Brunt & Camms-OHLE Structure Installation | itp | ITP-037-RAIL-Brunt & Camms-OHLE Structure Installation | 5924be4e-f723-4d5c-b99f-73d0a69f9920
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
6d72ed3f-6d78-5b8d-a5a0-64d3ae2aaaa2 | note | Document Title: ITP-037-RAIL-OHLE Structure Installation
59e4878e-a961-5ccc-bf4d-73dccbc16053 | note | ITP Description: OHLE Structure Installation
abb7d608-347e-568d-b7aa-2d87bbc66e4a | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
258625e6-11ec-5610-a204-efcd1f2f80db | note | Discipline (e.g. CIV/STR/RAIL): RAIL
9154e766-75b6-5c7c-8cd9-9f835e2a3b0c | note | Revision Number: 1
e7c49f81-0b7b-5dc6-970d-b9ac8428af14 | note | Revision Date: 16/05/2023
cabb008b-e37c-5696-8912-8240a303a35d | note | ITP created by: Nikhil Siram
9517ee58-787c-5976-9a46-7d886a63afa3 | note | ITP approved for use by: MRPA Quality Team
| checkpoint | 1.1 - Overhead Line Electrification
f4fb4320-5d00-52f4-a870-43194e472fe4 | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
| checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
c267b0e3-3f3a-5c05-a2bd-9f64e6b6976c | note | Reference - VRIOGS 001 AS 4100
| checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
29c058d4-1776-550e-ad3a-9d6d865ce53a | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
| checkpoint | 1.4 - Fabrication of Steelwork
2f0eeead-3395-533f-841c-d3f06f067d4f | note | Reference - VicRoads Section 630 January 2023
| checkpoint | 1.5 - Structural Steel Work - Fabrication and Erection
a6f9eb5b-b3db-5b7b-9a18-8a64e59c90bf | note | Reference - AS 5131:2016
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Structural Steel Components and Fasteners
df164392-ce09-5e95-a929-0efa7df8c7a6 | note | Reference - IFC Drawings
c6d1648b-4187-5fb5-9a83-de9bc00864cf | note | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
34cc1264-a6f9-5ed3-8a2b-3a7210f16442 | note | • Typically this consists of but not limited to:
1f95a117-5b39-59e8-9e36-9fd36c3c35bf | note | i. Completed fabrication ITP
945a0c42-6763-56d3-bcaa-450ef31544e4 | note | ii. Weld Procedure Specifications
c825d6e4-a776-583d-89d1-ef4080f720af | note | iii. Weld Procedure Qualifications
453e1423-81f8-5b71-a54f-188f54128727 | note | iv. Welder Qualifications
1a59b914-1059-5567-98d0-9fc13e00ee19 | note | v. Material Certificates
8dd7fcd4-eb1a-5f8d-9502-22a7c50de144 | note | vi. Coating certificate(s)
b928ca54-1466-5e10-9553-046624c917fb | note | vii. Non-destructive Testing (NDT) Reports (if any)
d1be8dc9-e075-55fb-a2d3-8843bf721568 | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
bbff11ec-8bcb-53c3-9be1-acb06e9e9304 | note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
089341a6-7e48-5916-a38f-44dfee34a0c3 | note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
e05eea70-0d93-5e96-919c-63901617cdd3 | note | • All bolts nuts and washers are hot-dipped galvanized.
8d83087e-b15f-58cd-a571-32c971918049 | note | Collate: Structural Steel Quality Assurance Documentation.
013c0453-109f-545d-9ac1-b1b41853bd94 | note | Attach: Collated QA documents in ConQA
f2c47931-6fe2-5230-8f33-303bba3301d0 | note | Method - Document Review
9791c0f6-8a97-5ddb-8219-994c8984b831 | note | Frequency - Where applicable/ Each element
cfe977da-c8d3-512a-859a-41d5355eb5a4 | note | Category - HP
dda9e098-76fa-5581-bb9b-9542a7cc0c79 | note | Responsible person - PE
989fc628-2412-5a10-88b3-2b34fa6e32d9 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Bolted Connections Using Direct Tension Indicators (DTIs)
52963a3b-5499-5d8e-823c-134f23016277 | note | Reference - AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
0cc4aa85-9077-5b24-9600-3bc41398158c | note | Acceptance Criteria - Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
43af5010-9b5d-5546-9b44-5951011cb367 | note | i. technical data sheet or information on the product
03b83642-131e-5c25-8fde-37e80f3cfaac | note | Method - Document Review
947519a7-b478-5a15-9b24-89914d2bec0e | note | Frequency - Where applicable, once
d2a8e7d2-0ce9-5873-90d4-0e90ff84db43 | note | Category - HP
39e213a9-be5b-50c1-aea7-6dea51634da6 | note | Responsible person - Nominated Authority
6a2c4d7f-1873-5157-8474-fae0d0b2343d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Overhead Wiring Small Parts Steel and conductor wires
92f6067f-dba4-59ec-8a1b-e2f2bfbe46db | note | Reference - Relevant MTM Standard Drawings
6fbc421c-f570-5377-923b-2d51992ae560 | note | Acceptance Criteria - Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
e5bbef1d-01f8-5e79-8a11-2b30a1c9af1a | note | • Deliveries are to be inspected to match the purchase order
09468182-8b6f-5bef-ae99-658391765fc1 | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
3fe302fb-200b-5b03-8196-220e7b645c22 | note | Method - Visual inspection and measurement
68e78db9-111d-57ee-afdb-ff1a64702a20 | note | Frequency - Upon delivery
6ca8959d-5d0b-5cc9-add4-007e70183bb6 | note | Category - IP
cc4a804b-5286-51aa-8ffd-58430212e1dd | note | Responsible person - PE
b129078b-efdb-550b-83f8-26c22d771b00 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 2.4 - Grout
7957dfa1-65af-5562-8bed-69e36e7ccfba | note | Reference - IFC Drawings
538f6a6e-206a-51e8-84f5-5869980d1c90 | note | Acceptance Criteria - All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
8bdefdc1-ef5f-56e3-bc52-3b46dac67c55 | textbox | Enter: Teambinder Material Approval number
6fc8816a-e807-52ec-8434-2e214f212dfc | note | Method - Document review
5661ecbb-a853-5d09-8ee2-ee220c02523a | note | Frequency - Where applicable
6d85827f-6c60-577c-974f-b99b98bc973f | note | Category - HP
89d95a06-69c8-51af-a3a1-101d82558115 | note | Responsible person - PE
5f34245f-48cc-5a5e-accf-1fbbd6b6f85d | note | Verifying Documents - This ITP / Material Approval
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Installation Methodology & Works Method Statement
171068ba-a4df-5a56-9869-0db14d2c2bc1 | note | Reference - AS5131 Clause 11.2.3
0f41121b-531f-596d-9728-d61d547046c0 | note | Acceptance Criteria - Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
df7bea13-9b96-5bf0-82dd-e6c07b6d0203 | note | – Transported to site;
ff206edd-2257-5314-a69c-01cf2843a185 | note | – Handled on site;
64e5f9c8-aa48-5b83-bc70-33044b389a13 | note | – Installation Procedure (subcontracor ITP's);
e9b4571c-ba79-534e-86b7-a5d711e80861 | note | Submission of Work Package Plan and MRPA approval and acceptance.
1cebfb9e-38a8-5744-90bb-f06245352b5b | textbox | Enter: WAP number
6923c8a0-e9c3-58b0-83c6-35f149fe6399 | note | Method - Document Review
962b5dfc-5cf6-57f8-b4e0-ea073e74d6be | note | Frequency - Prior to Works Start
bcd02dec-2ac2-59ef-8b00-b4778fd46716 | note | Category - HP
503721d8-4b51-514e-a4c3-a03fb4a484fc | note | Responsible person - MRPA/CAT5 Engineer
97763b85-77d0-5541-ab1e-55ae313cdf7e | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
ce937adb-b587-55d4-82c5-607b201c3cbe | note | Reference - Contractor Design Management procedure
920555af-3e5d-5e75-a074-62b6ef43a715 | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
70a4ccc3-8f70-5249-816f-c91bf5ea7df7 | note | Method - Document/Drawings Review
e2446ba0-1fc0-5058-8512-a4d63c846da6 | note | Frequency - Prior to Works and at regular intervals.
c2a7d4b4-7af3-525b-9786-46049fd3186d | note | Category - HP*
0266a824-cd43-55bd-a5da-48568928301c | note | Responsible person - MRPA/CAT5 Engineer
fdbdb367-020c-5aa5-9e10-ace6145bd88c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Cantilever assembled.
86f53223-997b-52e3-b72b-c37b60ce98fc | note | Reference - Cantilever assembled as per IFC design.
c40c001a-4cd6-503c-8529-487185ca41cb | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
43e36e3e-3276-5d9e-88d5-cd05885e8d06 | note | Attach: Signed off Cantilever fabrication Checkshit
163bae1b-5bcd-5ea3-ac83-8592a89159db | note | Method - Visual, Document Review
4642be35-681a-5c8c-9739-ed4c23e56525 | note | Frequency - Each Task prior to works start.
ae0cdaad-e69d-5b6d-94ff-6397a19ba158 | note | Category - IP
d65eb044-a10e-5075-b907-a7229203959f | note | Responsible person - MRPA/CAT5 Engineer
4b1c0d7a-aa0e-5afd-ab9c-0fe3d6e90f37 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Mast istallation
aa625822-7699-5987-9c55-d5e0ba29b0e9 | note | Reference - IFC Drawings:
2d27763c-a5b2-5441-a0aa-5615d1e709ee | note | Acceptance Criteria - Mast installed as per IFC. Mast rake is as specified in the drawings
e61034af-13ea-5efe-87d9-733be438919f | note | Method - Measure
9541ea85-8426-5f5f-8650-5e7e382c479a | note | Frequency - Where applicable
e0cd6d96-a66a-5e4a-b7d6-e1c7fa028fd2 | note | Category - IP
0787673a-b315-5afd-9233-1f7bc152c541 | note | Responsible person - PE
a322d063-ad54-5fee-8cfb-193124de5c59 | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Cantilever installed.
675eacb7-dfc2-5bce-b57a-b3f7c96b8f56 | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
7a850a9c-672b-5a9e-97d8-d8bf202f2059 | note | Acceptance Criteria - Work instructions in accordance to IFC design
7262ac23-beb4-5218-a064-8f9144ee4844 | note | Method - Measure, Visual
cfa4a9d8-4e98-502d-9c18-4dc8241b1bcb | note | Frequency - Each OHLE Structure
f8060119-cf00-5903-8f47-59c904bfb3ed | note | Category - IP
64dde716-2f5a-594b-8d90-86fea4d0508b | note | Responsible person - MRPA/CAT5 Engineer
82d3e066-3d51-59d1-80f3-d2a59dfd8453 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Bearing type Joints TB Friction type joints TF
08266f98-d97c-5583-a99b-00a0fa5cdf59 | note | Reference - IFC Drawings
bd864333-0f6f-5768-b6e8-6f3a11589b1f | note | Acceptance Criteria - BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
bb408d39-17a3-589b-bd7a-08f8e086142f | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
c4f21ee7-bcc8-5803-ac31-16a1f33210f7 | note | – DTI squirts are to be visible for inspection
674ab1e9-fa91-5b90-a0c7-4b8ef6eb3316 | note | Method - Visual
f9e90c6b-5182-5469-bb41-d2d8a590b8ca | note | Frequency - Where applicable
a5cbe38b-fded-52eb-944b-0eb5394fe12e | note | Category - IP
ea5fc9e6-d5c0-5e9f-9f3e-b4d02df97074 | note | Responsible person - PE
5e77b6ed-bf7d-58bf-8e61-bcb961a6d6ee | note | Verifying Documents - This ITP Signed Off/Visible marks
| checkpoint | 5.4 - Install SPS to correct height / position relative to track
8c54d2c7-6aa7-514b-8485-ea94711db8c9 | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
da7b225a-37c5-5d8d-a176-6c58ee8e170a | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
63ae7235-d0aa-5ac4-9446-bbff52779674 | note | Method - Measure, Visual
83061b83-0149-589d-86fa-776afa364b99 | note | Frequency - Each OHLE Structure
0ce7cbd5-1542-5885-9a7d-ae356578f6d2 | note | Category - IP
3023e226-ccf6-52ff-8d56-cb72f4cf09fa | note | Responsible person - MRPA/CAT5 Engineer
e1c88c2d-9902-502e-93f1-f5a4d371889f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Cantilever checked once installed.
cf2aa39e-e3ce-5c8b-88da-76cc12c8a3ae | note | Reference - Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
5998ba3d-9481-5012-85de-152168705311 | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
4b089b71-7891-5f97-a4fe-baf8435d31c3 | note | Method - Measure, Visual
06e4fd63-e646-5837-afd6-dd04ee5488c2 | note | Frequency - Each OHLE Structure
c28bc4e4-4f59-51e1-a416-22921a0ea4b8 | note | Category - IP
dfadfe65-7855-5d33-8a01-ed0e8aaa45e3 | note | Responsible person - MRPA/CAT5 Engineer
646d5145-5742-532f-966c-de0ece4f73b2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Base Plate Grout
db701ec4-3e19-55c6-847b-bbc27cb9d85e | note | Reference - IFC Drawings
8b2d2df2-2d78-597c-81cb-4760a40d972d | note | Acceptance Criteria - Grout to be mixed as per manufacturer TDS.
8398b1b5-40cb-5438-bf29-e0d5bac67466 | note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
37a1d5bd-ca01-5343-ad86-7ce432a252f7 | note | Method - Visual
254b4394-104b-52c0-9735-180d1519cc84 | note | Frequency - Where applicable
f0d369d4-e850-53a1-9e65-23582cb60068 | note | Category - IP
8b162e61-a4a5-5905-be16-dbaa0eb9bc84 | note | Responsible person - PE
c5b7a329-34f1-5f54-ba80-5dfa98f8cd33 | note | Verifying Documents - This ITP
| checkpoint | 5.7 - Installation of wire supports at the correct height and stagger.
3415b506-0075-527d-ad4e-b58eae2e67f5 | note | Reference - Install as per design drawings.
4d14147c-17bb-5c30-86b7-f918c8fef1db | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
79923a8b-7553-5982-899e-a9676fc48113 | note | Method - Visual
6917ac62-ed8f-5f7f-94f1-40cdc8c81ae7 | note | Frequency - Each OHLE BWA structure
bb2d4409-cebc-5571-838d-83baef9ad15e | note | Category - IP
45687855-7fdb-5878-b0fe-634de4dba562 | note | Responsible person - MRPA/CAT5 Engineer
505e2e25-6118-54d1-9fa3-3549991ae5b8 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Install to correct tension
678e34a8-b471-5343-b559-c0412014d858 | note | Reference - Install as per design, use span/ambient temp. tension charts.
8d007b74-a143-50a8-85eb-8ad72d905a0c | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
3bee82f4-cab0-509b-964b-b0d03a913063 | note | Method - Measure, Visual
d39d8272-a5fc-5dc3-90c5-3f9440deff17 | note | Frequency - Prior termination
3aeec4fb-fa07-5f69-9553-5b74cf5861a2 | note | Category - IP
8b1fc78d-3a30-511f-b9ae-8f8a12c57107 | note | Responsible person - MRPA/CAT5 Engineer
3160ff55-a201-51a2-9734-f6f025949028 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Defects/Temporary Works
98726157-e411-5c79-a6d1-580d1ba80c9b | note | Reference - IFC wiring layouts, cross sections and design drawings.
1f2d7746-0ce3-5195-80e5-7eb6d7c9590f | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
85f4c472-614a-5af7-b974-c337b1f1b0f1 | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
7dd89858-318e-58a4-bed2-118ccc24c7e1 | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
e1c32b6d-7820-5439-a2c8-270bc6bd7e43 | note | Method - Document Review, Visual
15bd0cf7-dce7-5526-aee8-6db048cca231 | note | Frequency - Each OHLE Structure
2002e2a1-8292-5c9b-9197-7de1ad08c035 | note | Category - IP
a7739776-7f37-5d25-b0cf-0b22d4ea6a1a | note | Responsible person - MRPA/CAT5 Engineer
39d754e3-29af-5b2e-b82f-5f84364afa14 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
0cbf5164-d6f6-52f3-91c2-fefe15c89356 | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
6c76a7b2-a17f-5b84-93cd-ff46b1e225c8 | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
02205503-8a04-5215-8026-debc2173555c | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
0d7bf166-dbf9-5b8d-9f70-bfa5462b8db7 | note | Method - Document Review, Visual
c786a896-18a5-540b-aa33-b68e777e1ee8 | note | Frequency - Each OHLE Structure
78d813d0-d474-56c8-9120-31917c2cf689 | note | Category - IP
07b9e0d5-2b0e-5e79-b170-c44416f16319 | note | Responsible person - MRPA/CAT5 Engineer
f01d40e0-8d53-5a75-94f5-285ea2cd0bcb | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
322bdee2-14d6-595a-9b73-171650de7002 | note | Reference - MTM Quality Management Plan
237ac672-3945-548d-8c16-0699f1e6bc91 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
edcbd8e9-5613-52e3-9e6c-6ac20b7841d4 | note | Method - Document Review
36dc12e7-e4a7-593b-9fd7-63243004f81b | note | Frequency - Once, prior to closure of this lot / element / Work area
a998f83e-3fc0-5454-a7cb-33e80899e0e6 | note | Category - HP
994db6da-e9eb-50cc-aede-d0eaf2175eea | note | Responsible person - MRPA/CAT5 Engineer
4243a3df-73a7-596b-b293-ec2b2b9cc738 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
afb82533-6ecb-5bfc-b31a-3e89684cf43b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0f67c1a0-b28b-5083-b647-75d95802f573 | textbox | Name:
256973fd-337a-52af-8065-80e68f251fa9 | textbox | Position:
c7a75a95-8242-5957-83e0-216b787b1111 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-038-RAIL-Brunt-OHLE Wire Regrading | itp | ITP-038-RAIL-Brunt-OHLE Wire Regrading | 7cc87bbd-e73b-4f28-ac06-a447742d9afb
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
0de47312-507d-5ed3-9788-ea6c5c2d4da6 | note | Document Title: ITP-038-RAIL-Brunt-OHLE Wire Regrading
3c7f90e2-8980-5d9c-8a18-eac590d0cc42 | note | ITP Description: OHLE Wire Regrading
2b58d7d9-d139-5b10-9f2e-01d5073c77eb | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
be489d5b-9540-5aef-b609-28ea07e93919 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
faf86eaf-fe46-591f-92f3-4a2f2b64d99a | note | Revision Number: 0
51491dca-fd5f-5100-b381-bb3662bf3c31 | note | Revision Date: 16/05/2023
d0f4a1df-8361-59ef-ad1e-e96a10b4b016 | note | ITP created by: Nikhil Siram
64753031-4ba2-5cd2-911d-306a0ac3ff60 | note | ITP approved for use by: Kevin Liang
| checkpoint | 1.1 - Overhead Line Electrification
7c6cc7eb-3837-53a2-b9d5-3b2a0edaaeda | note | Reference - L1-CHE-STD-011(1) MEST 000002-02(1)
| checkpoint | 1.2 - Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
753988f1-ce1f-5c9e-8693-5628f562c419 | note | Reference - VRIOGS 001 AS 4100
| checkpoint | 1.3 - Electrical Networks Standard Electrical Networks Principles and Performance
07e93314-1f55-537c-9203-4e1cdc8cffe2 | note | Reference - L1-CHE-STD-015(1) MEST 000002-06(1
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Procurement Materials delivered/collected to stores/Site.
7202f173-3c3e-5f40-9fd4-ea93d8d97c0a | note | Reference - Contractor - Site Material Control procedure.
4a173b72-4131-5292-9e42-5c3eb3e5190f | note | • Cat5 Material received - Brunt and Camms Tracking sheet
e0ff0d10-b6c0-5fce-99f0-817725aeb9c4 | note | Acceptance Criteria - Ensure materials are delivered/collected as required.
39059d4e-8f70-56a3-a692-4e9bbaf2cc56 | note | • Certificates of Conformity provided by MRPA
91e03e61-97b7-5301-b561-3840a860025f | note | Method - Document Review
c723753d-62cd-5cf2-9876-9080f8c9595c | note | Frequency - Once for each supplier, prior to works start
da2927b8-8963-53ac-ae64-193b21e36b22 | note | Category - IP
2a0f34f3-498b-5b47-be95-d19b2aaf1036 | note | Responsible person - MRPA Engineer
c171e223-f382-5675-9318-242641a742da | note | Verifying Documents - This ITP Signed Off
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Produce Work Package Plan
00271e6d-79b3-5ec3-b207-80d8aca140a0 | note | Reference - Work Package Plan WAP_BR_184
1abde248-d5dd-5ad6-8657-6ed508d50247 | note | Acceptance Criteria - Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
e8972752-28fa-59d0-b3b9-3aef27665867 | note | Method - Document Review
52216cc2-83e1-5ad5-b939-ba7458623be6 | note | Frequency - Prior to Works Start, TBC in accordance with MTM Standards
ba4a677b-35db-5a0b-93da-dc32b19ac5a5 | note | Category - HP
326247ea-3f1b-51f5-9b28-7cf381de16c9 | note | Responsible person - MRPA/CAT5 Engineer
f7e6f9a1-b9e5-59ae-be39-e884a5cbb825 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
1a8a870a-6829-55b1-88c9-ce0abb0c294d | note | Reference - Contractor Design Management procedure. MRP-DPK-089-00-ETN
553366c3-d6dc-526f-bc81-0c0b65a5fd96 | note | Acceptance Criteria - Ensure correct and most recent revision of IFC design drawings are used for construction.
25da1b89-68a1-54d1-8dec-fe01c23aee36 | note | Method - Document/Drawings Review
bc730528-aac9-5e7d-9d84-c041356744d1 | note | Frequency - Prior to Works and at regular intervals. TBC in accordance with MTM Standards
8b34c9bd-300f-55eb-afed-5335b4dea4cd | note | Category - HP
75689d22-5b58-5f53-9330-5630ed16ed44 | note | Responsible person - MRPA/CAT5 Engineer
63143b2c-551e-5a8f-acfb-867939ed19c7 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Task Specific Permits
55d44a38-c9c9-51ae-95b7-c26482a6f80c | note | Reference - Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS
1c38b6f5-8cda-5b58-bded-cdf9c833bb85 | note | Acceptance Criteria - Ensure all task and activities have relevant permits issued and received.
7f32e4be-b37d-57e5-aa09-ea49131d87e5 | note | • Task Permits to be generated and signed off by appointed person.
c246c46d-b4c7-5ef3-82cd-849c5eb85e47 | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
dda9e8f7-77a1-533d-9426-f750b3f74376 | note | Method - Visual, Document Review
5c819c1b-59dc-5541-b719-79eb0d580c05 | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
48245370-9101-59c9-981e-3389d89b2f60 | note | Category - IP
a72b1b45-6bf8-5b3b-a3d7-b72494200c6d | note | Responsible person - MRPA/CAT5 Engineer
db7308f4-05a9-5ea8-9eda-4674270e0f70 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Cantilever assembled.
ca84a1fb-4cb0-5a70-bd0b-9d3ca5fe8d69 | note | Reference - Cantilever assembled as per IFC design.
7d50ef61-5de5-5a63-9987-c8dccbfe1c60 | note | Acceptance Criteria - Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
2ab2fc8f-4a1a-5644-b249-a6364fd1ba4b | note | Method - Visual, Document Review
46cefae2-86c4-5d23-8cef-a68edcb7ff10 | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
4abb2602-439c-51d6-92bf-0b6ad6c1c7f6 | note | Category - IP
2394a8a7-b0cc-5aa7-8035-d1b77d5b3d54 | note | Responsible person - MRPA/CAT5 Engineer
8b081b4e-c8bd-5c93-8562-7912579e0233 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.4 - Pre-Installation check
12eeca52-3c46-5e61-a93d-053ef20e3b20 | note | Reference - IFC wiring layouts, IFC cross sections and BOQ. Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
fe0e7c5d-f09d-5969-9e7f-380b0225d9f8 | note | Acceptance Criteria - Ensure that locations matches most relevant IFC drawings
ae467d31-12c4-5d17-9ecf-c2da1632fcf9 | note | Method - Visual, Document Review
75043ee9-219c-57c0-be3b-084c3a3f9132 | note | Frequency - Each Task prior to works start. TBC in accordance with MTM Standards
05f3b3dc-0dda-55a3-a1e8-4612895fbe93 | note | Category - IP
e26f5e7c-6a17-57d4-9249-d79c3e3add7d | note | Responsible person - MRPA/CAT5 Engineer
b1553a9a-e57e-5ca1-8361-914884546dd6 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Cantilever installed.
bf11e6e1-2a73-51d7-a588-f38d5dea66fe | note | Reference - Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
5df2179e-76df-5461-89f7-8651140ed22a | note | Acceptance Criteria - Work instructions in accordance to IFC design
1e1c9b1d-0363-5ac1-afe2-eb8ffa961d06 | note | Method - Measure, Visual
2c76d2c3-2c64-5761-bc7e-2e20b90fddb8 | note | Frequency - Each OHLE Structure
c7b167bb-a6b0-5bc1-9266-304216a1307d | note | Category - IP
9ee53310-b1a1-5093-a742-b028ff09b54a | note | Responsible person - MRPA/CAT5 Engineer
3b119a73-4366-5f35-b77a-463c906d951f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Install SPS to correct height / position relative to track
246b499c-5e2d-50cb-a1bf-afc5232d08ce | note | Reference - Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
991d03a2-f3f7-5a47-9796-03ee4863e3eb | note | Acceptance Criteria - Ensure SPS is installed as per IFC design drawings/MTM design range.
4c15efab-a234-50cb-a4a2-3acd0ebb81d4 | note | • Supervision / checking to ensure that equipment is installed correctly.
74cc6f13-761c-55eb-a717-3f16a4f07281 | note | Method - Measure, Visual
b20b7925-b652-5fa6-a351-155c08f3e6a0 | note | Frequency - Each OHLE Structure
d3205a6c-17cf-556e-8a2e-04700037e9d2 | note | Category - IP
7a593682-05dd-5f7b-b797-c660527ab432 | note | Responsible person - MRPA/CAT5 Engineer
0cc332cf-11e0-516c-beec-136636aff87d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Cantilever checked once installed.
c0025b36-90bb-5128-a5b5-400f28c437aa | note | Reference - Cantilever checked as per IFC design drawings/MTM design range.
a4dba3e0-d66e-5267-94d2-5d48fa47dc9d | note | • Completed check sheet. CAT5/OHLE/CHK002
5413d3fc-ebf3-518b-978f-d18d511b73df | note | Acceptance Criteria - Supervision checking to ensure that equipment is installed correctly.
397b9682-7eb3-547a-8c86-70aaf6100dc9 | note | Method - Measure, Visual
72c7db37-a5c4-552d-8458-261cd5895049 | note | Frequency - Each OHLE Structure
65822c87-5b92-5efb-9a96-8937c724ad26 | note | Category - IP
2ba2ee78-5265-51ee-ab3b-50a55d22261f | note | Responsible person - MRPA/CAT5 Engineer
bb448425-d995-56c1-8983-7e79023abbc7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Installation of wire supports at the correct height and stagger.
746443a0-cbe7-58dd-bd6f-cc74b4c36b28 | note | Reference - Install as per design drawings.
71c05836-df10-562d-94d2-cd9b689e8bfd | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
1848125a-9ab8-56c7-8105-d38210155edf | note | Method - Visual
d980bbf6-b711-5924-af9d-1a8f0791646e | note | Frequency - Each OHLE BWA structure
ed9cf684-cedc-503f-a6ba-bff2f2459f8a | note | Category - IP
238da381-7d45-5f94-ac26-486af50135bf | note | Responsible person - MRPA/CAT5 Engineer
9e596ae9-4ef8-52e2-9aaf-a707d53d4026 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Installation of small parts
205ef441-5a5c-5b3e-91e4-0e604289dc0a | note | Reference - Install as per design, use span/ambient temp. tension charts.
4423e5f5-8380-514a-8cc6-227db2359a4a | note | Acceptance Criteria - Engineer checking to ensure that equipment is installed correctly.
efb9ba0e-1894-5da3-a6d6-51fdfe220796 | note | Method - Measure, Visual
ebfc7377-d480-5ceb-bacb-5da4f937d487 | note | Frequency - Prior termination
08dd5aff-c8ed-5b95-b7fc-28c787705f49 | note | Category - IP
f9064340-2834-5865-94a7-b9582e1e2d2e | note | Responsible person - MRPA/CAT5 Engineer
5dd56a71-8fd5-5a96-8fcd-24a75d588a8e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Complete Clearance Checks
fb56f735-2b38-5790-94de-e61ec67a13e1 | note | Reference - Install as per design, use span/ambient temp. tension charts.
d0d1c656-650c-5dfb-b95a-cfa8d2ab3fc3 | note | Acceptance Criteria - Visual inspection for clearance and wire staging from Hirail EWP
05e10a61-aa61-58b3-b2a1-d6f6780d020a | note | Method - Measure, Visual
7c6ca83c-c794-5ed6-bfa1-c7c355f4cb08 | note | Frequency - Prior termination
86aaa4a7-6ff3-5bdd-bf11-b856526617f5 | note | Category - IP
674fc628-7c15-5e3e-b13b-cea98914339e | note | Responsible person - MRPA/CAT5 Engineer
5e65eef1-27f2-57c3-a42c-2664de6bee22 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Complete Pan Run Test
3f1362f1-9c04-5417-ba2a-bf94b9a0d940 | note | Reference - Install as per design, use span/ambient temp. tension charts.
58aed145-9fe7-5ccc-b0a2-b0c237649e59 | note | Acceptance Criteria - Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
a5872029-2871-5e8a-85ad-6e15dc885a3c | note | Method - Measure, Visual
b4a51d72-ba11-5ccc-8845-cf7e4cd1171a | note | Frequency - Prior termination
01c8c2be-b28f-5165-a986-b305946de7e9 | note | Category - IP
4e2ec300-1568-581f-a41e-32223be3140a | note | Responsible person - MRPA/CAT5 Engineer
90124b4d-280b-5977-9f0c-e7df9ed6b4f9 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Defects/Temporary Works
f170923b-d7e2-5e37-a98b-6ea0740a4dbf | note | Reference - IFC wiring layouts, cross sections and design drawings.
31f97a90-5ef4-58be-8f4d-7137ce337568 | note | Acceptance Criteria - Ensure all Defects/Temporary works are capture and closed out correctly.
89365b30-6360-50da-8d95-8840cc80dc84 | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
76dc76b5-c250-5f64-9d12-859e0616f063 | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
b42e09e0-e2ce-5624-83d7-7d597ab32e1b | note | Method - Document Review, Visual
052a8f92-e608-5a16-890b-5d5c28735a25 | note | Frequency - Each OHLE Structure
3902bf27-2db6-5f2d-a04c-7a1c0afed6c0 | note | Category - IP
6f19a318-59ce-5127-8a6f-3d684451f970 | note | Responsible person - MRPA/CAT5 Engineer
5cb0a103-b4b7-5774-ab38-8d23f39de1a7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Relevant documentation readily available. (As-built Survey)
7c5dcc2f-54bf-5ff1-bf81-59f0bd483c57 | note | Reference - As built drawings and check sheets to accordance to MTM Design spec.
29b7b095-278e-533f-b458-ab70e5cb492e | note | Acceptance Criteria - Ensure delivery of relevant documentation to client.
11b4fc20-41f1-53bb-b500-7a5988c8a93a | note | • As built drawings and check sheets.CAT5/OHLE/CHK/002 check sheets.
4b83be60-75c0-5b13-be31-8806f75a0b8c | note | Method - Document Review, Visual
da08ec12-ac2e-5b0d-9c67-6fcf8afcc3f3 | note | Frequency - Each OHLE Structure
c236780e-771e-5ff2-b976-4b335614688c | note | Category - IP
2ac64e0a-adb2-5593-909d-3512b0bde8b2 | note | Responsible person - MRPA/CAT5 Engineer
f84011ea-74bc-5d32-a6c1-d9c08b980ea1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
2c36b3e8-bb8f-59f5-89ad-e93da7181fab | note | Reference - MTM Quality Management Plan
2f949301-71ac-51a1-94b5-f293a1307a6a | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
dd435533-64db-59d0-9272-2f2df24a2b61 | note | Method - Document Review
6e6573be-d8a8-5d3f-8507-bd262580f250 | note | Frequency - Once, prior to closure of this lot / element / Work area
f1b535c4-ac93-596b-998f-6c939863ee89 | note | Category - HP
c02290c6-9c2c-58e8-9a8c-0ee822470a49 | note | Responsible person - MRPA/CAT5 Engineer
1ebf1882-4eb5-5ac2-95c4-db5bd4562cd1 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
445b13e1-680a-520a-92d3-5f677bdf993f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2dde5716-4b43-58d4-a576-b43028bba46e | textbox | Name:
8b6b65cf-5e02-594d-b1af-c3e4d1626d6a | textbox | Position:
8dbd467d-7286-580f-9210-5a96cea5ceb7 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-039-STR-Brunt-Abutment & Pier Walls | itp | ITP-039-STR-Brunt-Abutment & Pier Walls | 79c4b4f2-508c-4833-88c8-fb27cbc79373
| section | 1. Referenced Documentation
| checkpoint | 1.1 - Non Dependent
4cccd459-ced3-573a-9143-d209910aa770 | note | Reference - VicRoads Section 602 October 2007
d0f04660-49ee-5faa-a2d9-b03494d550ca | note | Acceptance Criteria - N/A
655a1364-55dd-5a44-91ac-49147e5c82cb | note | Method - N/A
b39e0f69-1115-538b-95c4-eec539ed358a | note | Frequency - N/A
d8508f09-bc82-5ead-ad85-c1aa94524492 | note | Category - N/A
8ebe5b89-7c9a-5293-8006-f40b2fd9abe3 | note | Responsibility - N/A
1b873118-8536-5718-a439-1e298e09b6f4 | note | Verifying Documents - N/A
| checkpoint | 1.2 - Non Dependent
4e7c8ba1-02b8-574c-9c0f-db4e5e304bd5 | note | Reference - VicRoads Section 610 February 2020
d8a92e7f-4160-5aa1-9f88-b783a7b5bd68 | note | Acceptance Criteria - N/A
43921d0f-1977-5979-9a22-fdd4e9caf589 | note | Method - N/A
58cdf3fc-d7d3-5f5c-b23d-e482b2729b05 | note | Frequency - N/A
e7bc0d0d-9695-53e2-baa9-8995f0e5a00f | note | Category - N/A
85d0ce92-23e5-574d-a8a2-df06569f2167 | note | Responsibility - N/A
112a1923-797c-54a0-a1f6-942665e8f5c1 | note | Verifying Documents - N/A
| checkpoint | 1.3 - Non Dependent
ec799ef9-552c-5ff7-b880-df6bd5fb602c | note | Reference - VicRoads Section 611 November 2018
40dba7b2-cee3-5b9e-9642-e603224a79fe | note | Acceptance Criteria - N/A
c34f86a3-303f-55e5-9f6c-c196813b3df6 | note | Method - N/A
6d48088a-141c-5fc7-a5dd-7725d04c6d2b | note | Frequency - N/A
b78d9171-ebf4-5409-9078-d9ceca5524d4 | note | Category - N/A
3729502b-66db-5109-94da-51bbc9c872fc | note | Responsibility - N/A
5f8eecca-98fe-5e5c-a0b5-492fe3774075 | note | Verifying Documents - N/A
| checkpoint | 1.4 - Non Dependent
25b93da6-a106-575e-8a0b-7a72986375e8 | note | Reference - VicRoads Section 614 June 2017
f1e4cc31-bbe4-5dac-b8d6-1871c3b7e73a | note | Acceptance Criteria - N/A
574323d4-9226-5f2d-8d00-74fa8ae321f0 | note | Method - N/A
0ef77b72-645e-58dd-a7ee-a61b08c648c9 | note | Frequency - N/A
7ec60cd2-76f4-5b3f-8a5c-9ba0beabb2ea | note | Category - N/A
3347fc0f-6a7e-5dad-aac7-74293e2ba061 | note | Responsibility - N/A
6802dcf8-1ada-5a67-a808-c3807ba05c7c | note | Verifying Documents - N/A
| checkpoint | 1.5 - Non Dependent
c68f3e83-0179-5ebb-9bbd-9d7ea2f5d75e | note | Reference - AS3810.1 2018
ab92a0e9-07ea-5121-8284-090cf522f5cd | note | Acceptance Criteria - N/A
bd03dac7-d156-5b68-ab66-f2683924336f | note | Method - N/A
e84ed2db-5793-59a6-b0b6-b23666479e44 | note | Frequency - N/A
ce54ab53-b965-5a25-95c7-967262fc22fc | note | Category - N/A
495a46de-23e6-5320-9f8e-7a8378792e57 | note | Responsibility - N/A
60737339-2703-5e03-ac14-be4e84f36d66 | note | Verifying Documents - N/A
| checkpoint | 1.6 - Non Dependent
cde843e5-264a-5a20-bfc5-110f2df1e343 | note | Reference - IFC Drawings
3a5c7b19-c433-55b1-91d7-c0685696de23 | note | Acceptance Criteria - N/A
90d20625-fea4-530c-8e6d-780b05d714c0 | note | Method - N/A
b262fe62-fbfc-5adf-abde-be5779071ede | note | Frequency - N/A
ea7edfb8-b0f9-5510-aefa-3bfa21954834 | note | Category - N/A
494e2593-42fc-545a-aa21-f8c8a24b81f8 | note | Responsibility - N/A
2586d5f9-a990-532e-83cd-21d9f58366c5 | note | Verifying Documents - N/A
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
5c9899c3-5ab9-5827-a282-e1e1fe250889 | note | Reference - 610.07 Table 610.071 IFC Drawings
8beafd62-c37e-5b37-b124-ef3022efd2c4 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box]
ebe9e65c-bc91-5078-9512-141d977e5876 | note | Method - Document Review
7416527f-f177-56e7-bb60-0821d44a0fdf | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
308e8a11-c2f1-565a-ada9-de63f1758b3e | note | Category - HP
f1279922-6211-5b32-b418-cd62bb810ee1 | note | Responsibility - Nominated Authority
b8fa37c9-09fc-5cd0-875b-8783297ccb0b | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
4b963a42-68d3-5c2a-8169-5d2cb92cb05c | note | Reference - 611.05 (a)
70ce63ae-1c53-5669-82db-fa918e4eb8d4 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box]
19c62f7b-3796-5c6c-acff-55950f8e8c5f | note | Method - Document Review
60327a72-b1db-5eac-9667-27a30d87d942 | note | Frequency - Once for each supplier, 14 days of award of contract
6d4d2db3-a16e-5d81-b797-4f1b0982081f | note | Category - HP
67a9ba7d-3945-5077-9c57-cc659a6a52e9 | note | Responsibility - Nominated Authority
b1690cfe-089c-5a82-be2e-d8d18bba5f45 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
be656ef0-156f-5f83-811d-5e1d05bfabf9 | note | Reference - 610.26 (a)
7b5b57de-1ae1-56fd-9924-eedc74f21703 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
e8800d34-ae29-59dd-b834-9ebd6c2a971d | note | Method - Document Review
94518050-ece1-5d5e-920f-beb71936485d | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
be94ac9b-ea0e-5bd9-a49a-01190aee7587 | note | Category - HP
4a2963c9-4030-5abb-a520-0e6442bcbb4b | note | Responsibility - Nominated Authority
8f47ddb0-e77c-516e-9859-df9d3551ef51 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
0b0e5a35-0113-5521-a8da-1f47a61efdb6 | note | Reference - 610.17 (f)
a48e8ab0-21de-5463-b2f6-f76d94d3f4be | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
c4d35dba-d8b1-5723-b61a-ae396d66e393 | note | Method - Document Review
4f470773-a016-54f9-8fd3-2de1b90eb6fb | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
cc22510f-044d-55cd-86f4-6632e33899ef | note | Category - HP
dcf6d01b-8a48-57c2-b7aa-5e623f893a01 | note | Responsibility - Nominated Authority
9d4a3266-3526-5760-936a-5acf47c1e77f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
383504b6-d72c-523d-956c-dfe687cbb9fd | note | Reference - 610.23 (d)
76501349-083f-529c-af68-fe546f5f16ab | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
04057559-edf6-57f5-8f7a-92c6fb241ed6 | note | Method - Document Review
eb184a1a-d1b7-53d5-b525-ded07fc01244 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
29c6b85d-c4cf-5e5d-8034-912eae992c10 | note | Category - HP
936053de-5434-5ee8-abd6-fdab35825996 | note | Responsibility - Nominated Authority
abbcc674-3f39-55fe-b16b-a0d9b1904465 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
64494500-181c-57ba-934e-0f006fe6f5a4 | note | Reference - 610.18 (a) (i)
81188805-9441-56b4-83b0-0f19935f4bc2 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
7ca36c4d-cff6-517f-89bc-a407a436d215 | note | Method - Document Review
0247bbad-3b33-564b-ab8f-0839acd965e7 | note | Frequency - Once, 4 weeks prior to placement of concrete
78eeefdd-dd7c-5ba1-ae60-85c6e9602bb3 | note | Category - HP
862685b9-fba2-565a-9bb9-6c23072561bd | note | Responsibility - Nominated Authority
d8f37535-59f0-5a36-8232-17e4d253268e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
f012a11b-42bc-53cf-a8e7-f934390242ad | note | Reference - 610.18 (a) (v)
1aa48cde-8b63-5489-9841-3a3535652da0 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
01f0e493-751e-5404-96fc-98463e6c33b9 | note | Method - Document Review
343fd5ba-10b0-5846-bf37-47c5b9d3ad76 | note | Frequency - Once, 4 weeks prior to placement of concrete
f1f45fa1-91fc-5c60-a50a-8dc23cd109db | note | Category - HP
6adb57c4-c448-5715-a352-5814bffcf505 | note | Responsibility - Nominated Authority
d37c12b4-9b3f-51d4-baad-f201db5f58a1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
b227db33-a623-5000-b426-ea4b7190ab25 | note | Reference - 610.18 (a) (iv)
cd136bc8-9abe-587a-8839-b7e5fbdc3d85 | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
33f45caa-eab6-5a09-a69a-bf146e820e82 | note | Method - Document Review
5f4baef1-6299-5569-8294-76b1cbc16ecb | note | Frequency - Once, 1 week prior to placement of concrete
18c488aa-65de-5059-98cb-1c2035d95308 | note | Category - HP
ee05f8be-cf5f-5870-9089-0530227de196 | note | Responsibility - Nominated Authority
9fbcdcc8-0ac2-5a0e-84c2-679a2a87bf9a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
8982e95c-928b-54c0-9d60-a4877ca2d5e4 | note | Reference - 610.17 (a)
3954bebc-631a-5892-a716-11e077f7b176 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
52f49082-1b48-5d44-97d8-667c1c03c0b6 | note | Method - Document Review
69f128ef-ca46-5fb8-8eff-6ca934c76822 | note | Frequency - Once, 2 weeks prior to placement of concrete
418e7d50-2367-572b-9439-018f8de248cb | note | Category - HP
8726db37-538d-5a9e-80f8-02da9da4f6ff | note | Responsibility - Nominated Authority
ad87a9df-26ba-55c0-8f24-3c910818cea4 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
8dd025e0-6711-53f1-9d86-35c7c858f7d7 | note | Reference - 610.23 (a)
cbff9b0d-7a96-5cd6-961a-5b2da0fcc19f | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
8ddf1181-db23-52aa-bdab-e79a875dacbc | note | Method - Document Review
88cbf9ff-da61-5771-a97c-8976f0db91f9 | note | Frequency - Once, 4 weeks prior to placement of concrete
2e3faab8-8e9c-5a0c-974d-a2f5a8acb866 | note | Category - HP
1b0675c1-5b6a-5c54-9108-c719257d552b | note | Responsibility - Nominated Authority
0d760fbc-802c-5cc4-8e6f-3eafc9b18b07 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Concrete Drilling Procedure
14436427-156e-5d6f-9db3-c936285a016b | note | Reference - 610.46
fba3c4ac-80aa-50f4-a953-51377e5394e9 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. The planned locations and drilling procedure shall be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
08f996c8-9a68-5e9f-bc02-4dd6d0716d8b | note | Method - Document Review
a4f16b3b-fa99-5399-8f0c-df40dac14c04 | note | Frequency - Where applicable, once, 2 days prior to drilling
b66a3910-e0b7-5ed4-b2b8-58403055ead4 | note | Category - HP
b3e17dcc-3f8d-5f78-95a1-2d8850ba6485 | note | Responsibility - Nominated Authority
65b60b2f-7a38-5911-8597-100fddb17310 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Temprature difference measuring-Calibration
58251653-b470-5847-bce0-bba9ce25f8a2 | note | Reference - MRPA Quality Management Plan
88ba2adc-a8e5-595d-8f2b-740e4f45b7e2 | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date. Attach: Calibration certificate
de0817a7-040a-5a34-b618-fe59a4e43da1 | note | Method - Document review
433a4966-696d-5d26-933b-592c9d68bec7 | note | Frequency - Where applicable
4ef059b9-87c1-5269-870e-7b661fd6b6cb | note | Category - HP*
e097fee4-6360-57fa-a8fb-4f3b49e1460c | note | Responsibility - PE
48e99013-5342-57d2-9802-81cdd8fb7275 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
344b821b-f7bb-58c5-9f1e-2b6f7cd3b613 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
568e8ab7-ba0d-51b1-a339-ff59e9d0ca77 | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
5d8b6331-54fd-5668-83f4-28535ceaf5ec | note | Method - Document Review
705ea27e-f6af-554f-9846-266edc2c6142 | note | Frequency - Where applicable, once, prior to welding
2914cf11-6112-595a-8db5-b7eaefad1f21 | note | Category - HP
bc21b9d0-e5ff-5847-8f8e-fa7c8500842e | note | Responsibility - Nominated Authority
f03e65f4-4851-5cde-b623-403ef1f947e9 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
8cdf502f-6c51-5cb1-bec7-5c21b05d9f5c | note | Reference - MRPA Quality Management Plan
928b859a-2f90-5ded-a030-d5287153094e | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
fc810e3e-d6a0-5614-a7a8-42d36a6d5ad7 | note | Method - Document Review
51bac255-a183-591c-874b-5607339f29a1 | note | Frequency - Prior to starting Works and at regular intervals
7b2589e6-4f8a-5ac6-8b10-0263d6f47f00 | note | Category - HP*
ccd8d590-8003-5534-a538-cfba4c6c994a | note | Responsibility - All
e97ad841-4116-5fe4-8bdb-c0d4d377d5ed | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out
853e92cd-9757-5e5a-87c6-b9bea52cb472 | note | Reference - IFC Drawings 610.47 (a) Table 610.472
aa8de62d-4016-50c8-9258-f2d9c1eee94e | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element. Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
a0bd1962-5d96-5dec-98e3-9dc0f36e7646 | note | Method - Measure Visual
ab0768de-a12f-5cf6-96b4-709a86cfa290 | note | Frequency - Each element
e7b711ee-2797-571a-af6c-d5f243629307 | note | Category - IP
ca7c20a0-ff54-58d7-a596-31ed8712f1a1 | note | Responsibility - Surveyor SE/PE
ca2639fa-9aeb-5551-b6e7-67864f1701df | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Pile Cap Work Lots
2a621d4f-ffd5-5114-b93d-d51352b18f56 | note | Reference - TeamBinder Work Lots
bd2a34b6-6508-5ab4-b46d-8eb68c61cd3e | note | Acceptance Criteria - Related pile cap work lots are closed. - Pile cap design strength is achieved - As-Built Survey performed - Related pile cap NCMs are closed. Enter: Pile Cap Lot numbers: [FREE TEXT]
71162c70-465c-5cb7-9b46-227026dd57e8 | note | Method - Doument Check
3290a5cf-98ee-567e-9254-59bc63e91c8f | note | Frequency - Each Element
a371902b-e4fc-5bef-ab7f-d13f2b6efe87 | note | Category - HP*
ad8b5344-ea3e-531d-9547-ecf78ef11a57 | note | Responsibility - PE
7c33f0e3-d5f3-555a-abcb-f199aec84c81 | note | Verifying Documents - This ITP Signed Off Pile Cap Lots Closed-Out
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
b6059d7c-d858-55c3-9534-5442f9d1b94a | note | Reference - IFC Drawings 614.04 614.05 614.06
77b6e89a-80cb-5a72-843c-12638adfa537 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
68456cc0-2d5a-5e81-9eb4-9906afb596db | note | Method - Document Review Visual Measure
e0bd3f63-a5c4-50b2-bff0-f9baa9989dd3 | note | Frequency - Each type of element
403344f6-3fb4-522a-9fac-e798c8497da0 | note | Category - IP
3e1ab3af-3395-532a-874e-3e86cf004bdb | note | Responsibility - Temporary Works Designer Proof Engineer SE/PE/SPE
d33ee62f-09dc-5c0b-8311-0d51154f28a0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
a56bf123-8571-5b3b-a92e-bf40597ba434 | note | Reference - 614.08
334358ee-c450-5401-882b-0c57a7bf7350 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Abutment / Pier Walls with heights greater than 2.0 metres Any member for which self-compacting concrete is proposed. Attach: Attachment A Attach: Attachment B
16ca4080-497d-58f3-8ae7-6e81d3f04f24 | note | Method - Document Review Visual Measure
32396dba-8cd9-5807-9be7-bbcefeed4623 | note | Frequency - Each element (where greater than 2m)
65a546f3-691c-5340-aaa3-56f6bce25282 | note | Category - HP
7b6983c4-521d-52bb-b2e0-ce496db7f60d | note | Responsibility - Temporary Works Designer Proof Engineer
cd9585a6-7a9e-59c1-8e38-8930d079245b | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
138079ea-c694-5e1c-97e8-6535f81e292e | note | Reference - 614.08
872b02dc-1110-5576-94b3-ec9d3d28756f | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Abutment / Pier Walls with heights less than 2.0 metres Attach: Attachment C
e3ad572f-18ae-53ff-92ab-f1c42c36eb58 | note | Method - Document Review Visual Measure
fa3e65ef-b526-5918-8344-92efa3c3e32f | note | Frequency - Each element (where 2m or less)
e6bfe1c9-f6f8-5bb8-abe5-99ad94075902 | note | Category - HP
1b707faa-90e4-560a-9020-8bbb4e3e72ee | note | Responsibility - Temporary Works Designer Proof Engineer
5a52374f-ba16-5eef-897c-04402119b9da | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
d2de03df-1cc4-5d09-947d-26e6b44bb951 | note | Reference - 610.47 (a) Table 610.472
a436d230-1fb2-53c1-8092-5a24a1202177 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
f6f92731-0b0a-5c80-a476-2fbb3a3f1af6 | note | Method - Measure Visual
aee89be1-aa59-53a3-a9cd-27f34715e38e | note | Frequency - Each element
df04ef6b-1ed2-5728-bcc4-867097dff138 | note | Category - HP*
cdd10722-ea56-5f57-8a55-c49b44ff7302 | note | Responsibility - Surveyor SE/PE/SPE
ce3c9849-84cc-59e9-af58-c809668bffe3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Reinforcement Placement
444f12aa-7064-5ff3-869b-eb08ea22002d | note | Reference - IFC Drawings 611.06 611.09 611.10 611.11 611.12
831d8b62-d820-51de-a7d9-e9a93e6208a4 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
b0ef2ed9-b676-5f59-b5ef-a90d7a72755b | note | Method - Measure Visual
dc3990d1-5490-59d1-9d79-7d009a0182d0 | note | Frequency - Each element
395dd28a-5e01-523c-bd95-93d65706b853 | note | Category - IP
b2ee29d8-a0e5-53c1-8cff-007938dbce82 | note | Responsibility - Foreman SE/PE/SPE
79b6db57-e501-531e-b5f5-509e9405905e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Cast-in Items
42fd93b9-38ca-59d5-8ff8-d2aa4810da63 | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
1fea725a-d447-51bd-abcd-883b94bf9102 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm
573dba7c-bf2a-5031-8598-e756db730f8b | note | Method - Measure Visual
fc2b96f7-3c7d-5eda-a1bd-ba00df613750 | note | Frequency - Where applicable, each element
ab9dc972-c801-540f-a0f8-7e4992e140ac | note | Category - IP
7b5a70fc-4999-5793-9919-c429b7c23a0d | note | Responsibility - Foreman SE/PE/SPE
252d89d7-8579-5676-bd81-e9f26b3c5aa2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Thermal Differential Monitoring
0d7bf27e-8818-5871-b35c-9b1104b82717 | note | Reference - 610.22
ed2b2d8b-c29d-5034-a74f-95d0d8d4c1f0 | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints
cc61d434-7fef-560b-8c6b-dbcd58d8d054 | note | Method - Measure
f4a9015c-8fa4-584e-9eef-505beabc51b7 | note | Frequency - Where applicable, each element
99465483-aae4-54e2-a170-0b47adf2fb00 | note | Category - IP
4617a105-da28-5d0d-9768-2d131af3d36b | note | Responsibility - Foreman SE/PE/SPE
0be51540-bee3-50f5-b24a-a8620bfe8b18 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Pre-pour Inspection
f93cc9ef-31da-5e43-b0d9-99e8690e628a | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
1ad31d6f-ea60-5971-9886-e447ddc150d7 | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms. ATTACH: Pre-Pour Checklist
08cb289a-b6ea-50e1-945f-187ce2afeaad | note | Method - Measure Visual
941461d9-d076-50b4-bd17-b9f6b66a978d | note | Frequency - Each element
03f0622b-af69-5822-8d96-82b909c9f3ff | note | Category - HP
e5fa2ab6-262b-59ba-ba9a-b99f4f8d09c4 | note | Responsibility - Nominated Authority
1fde2979-7fe1-53c1-bdca-4b49fe0710d3 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Weather Conditions & Evaporation Limits
e180ac65-be8f-5927-953b-2b780e7c7e22 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
b8d76bee-d41c-5c23-8313-ecfc41499d20 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
93723221-91c6-523d-8adc-3742ee0618c5 | note | Method - Measure Visual
92fde4d0-7811-5ce1-a552-f7187cc77429 | note | Frequency - Each element
3c8fe2df-36d4-5d5e-9ad6-2e808a51dcff | note | Category - IP
9f443025-0fb5-5f19-b5f4-3cb390d3f37f | note | Responsibility - Foreman SE/PE/SPE
511bee15-07c6-56ae-afc5-c9c39705b8ac | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.1 - Concrete Testing - Sampling Frequency
35a59115-02b3-5652-b477-739fd1208678 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
bc055292-1f5d-5550-98f4-dc757bf48107 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record.
28002b3d-c2fb-5683-9a13-ca8b2dcf0bee | note | Method - Test
cddec7dd-58a7-595b-88d8-3c0d9aada2a6 | note | Frequency - Each element
e4a0b2f8-10ae-5bcd-b2ed-a23afbcdeb35 | note | Category - IP
326db85e-4e3e-5a3f-8588-30530a4aab71 | note | Responsibility - Concrete Tester Foreman SE/PE/SPE
c7ecfdbd-d629-5188-afea-3837575bbc4b | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.11 - Concrete Testing - Slump
b2e17938-46a9-59ab-be6b-e1d6a00e6b7b | note | Reference - 610.16 (c)
f78167b5-57d8-530c-88c1-de8cac321803 | note | Acceptance Criteria - Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record.
a2816b0f-4128-50a5-928e-283eac3e7cc8 | note | Method - Test
efae318a-d39a-537e-a46b-a661abed720e | note | Frequency - Each sample of Standard or Superplasticised Concrete
f1b4d18f-7840-5838-9f03-e355aa3ae870 | note | Category - IP
2546f268-5ae1-51f6-857e-d1acb1c51837 | note | Responsibility - Concrete Tester
d77c0756-9cfd-5876-9d30-3e90d8b27282 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
efc93f8c-2a96-5555-91b6-2ee3b695a0f1 | note | Reference - 610.13 (b)
dff9c5d5-102a-5ae6-bffe-fddba54934ab | note | Acceptance Criteria - Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
1802fa85-a773-5710-ae8c-ea50230a748e | note | Method - Test
cd3aff2f-67a4-54e1-aed9-361174a7c50f | note | Frequency - Each sample of Self-compacting Concrete
06fbfd36-4f64-58e6-bff8-6324235f72d5 | note | Category - IP
3a032d56-3003-53e3-933f-1aa68623301d | note | Responsibility - Concrete Tester
83fd8cd3-3ac2-59a0-9a0a-5408aba81104 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
d6746860-aac2-5042-9ab3-ddfe3f347119 | note | Reference - Site Sampling & Testing Procedure
a92d35ed-376a-5dba-b32f-8d8629889733 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
ad5a9486-d291-53bd-89b3-f917a911ad5e | note | Method - Test
d8f7ea2c-3986-529f-ba6e-8b487fa48fb6 | note | Frequency - Each sample
bff41ff6-047e-584a-832a-25280d1de8e1 | note | Category - IP
6090c487-5d58-5da1-b6db-f5da0af7fd95 | note | Responsibility - Concrete Tester
baa4f4f6-d4be-509e-b5ec-51bf3c435f6a | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.14 - Supply & Discharge Rates
8b5e38ed-2da2-597c-ba52-a5e35fac89a8 | note | Reference - 610.13 (a) & (f)
093dacfd-01b4-59c0-9dcd-e64022c29a59 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record.
fa353945-b089-56f4-a35f-7c25c0b02172 | note | Method - Measure Visual
89528c71-89aa-5f3b-9a92-6b51410c2dac | note | Frequency - Each load
6c3ee74e-967e-58be-8a0f-8f8384b9ec49 | note | Category - IP
1985b5f8-6cb1-5f35-b052-32e113f4e545 | note | Responsibility - Foreman SE/PE/SPE
a687c782-bf45-53f6-9cf1-57769eaeff2e | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.15 - Placement & Compaction
18824c5d-c9bb-5e4e-8539-a5258a0a720a | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b) 610.18 (d) (i)
69264839-d8e7-5731-a475-ba57b8cfe5af | note | Acceptance Criteria - All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets
d34ccef8-e3ee-5323-bcba-498be7340bdd | note | Method - Visual
cdc23c14-1040-50f9-9d84-6c1c442e9487 | note | Frequency - Each load
22da6b92-946c-5476-bb7e-0fae94a67070 | note | Category - SP
7c889f7f-fbc2-5120-b776-9dcd3711165e | note | Responsibility - Foreman SE/PE/SPE
4d472eec-585c-5d5c-952c-505113d3e2c0 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.16 - Surface Finishes
2740b497-342d-5e7c-b15a-b4f846a20e30 | note | Reference - IFC Drawings 610.31 610.20
9d0b7f35-f20c-5c3f-b188-4f1b9a9a0aaf | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
eba391f0-7d3b-5f96-90cd-ecb5c5dc71d8 | note | Method - Visual
f87ee014-fbfa-56d5-a811-935dc76c84fe | note | Frequency - Each element
dfc51f71-acb8-5f6b-a616-948527845b16 | note | Category - IP
b3863d0e-a95c-5ede-9f4c-002e96a1b1b6 | note | Responsibility - Foreman SE/PE/SPE
a1ee18b8-5c32-5e6d-884b-fc8cb5bb466a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.17 - Curing-Top Surface
58b36654-fe31-59f7-a324-174f781a9f33 | note | Reference - IFC Drawings
85f47480-edb4-55bc-89d8-d3106269ab1f | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
0542af66-032c-55f6-8990-eba9effba401 | note | Method - Visual
ec665b74-00bb-58c8-a624-3e59031227e9 | note | Frequency - Each element
37bea3b9-282b-557d-964e-27811e917ae3 | note | Category - IP
09a0e070-8eb7-54a4-8129-3c1aa11f67cb | note | Responsibility - Foreman SE/PE/SPE
8c2a29fe-9be1-59a4-a7ce-660baf74da85 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.18 - Curing after formwork removal
aef21db6-5e75-5288-8032-e9fe9a1df97c | note | Reference - IFC Drawings
87fed6eb-895f-56bb-baeb-df091c19f381 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
f94a5208-0924-5b12-80d7-7760a2f35d53 | note | Method - Visual
2966387e-ed10-5b51-81fe-439c91a19618 | note | Frequency - Each element
65a39e87-4e78-5adb-ba28-19d402c2d3a7 | note | Category - IP
97df17e5-e619-5740-b7b2-f6fab8a51755 | note | Responsibility - SE
3bb580dd-1937-5150-b195-b6863138ccc5 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
10c56024-3e2d-56a8-9264-bf951dd9e175 | note | Reference - 610.22
f354c98a-0861-58d1-bf27-f63d57c8b0d4 | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints. Attach: Thermal Monitoring Report
5789d657-d010-5e56-8624-16f786619708 | note | Method - Document Review
7d4c31f2-c837-5afd-9d10-b7ec8adfd6a1 | note | Frequency - Where applicable, each element
af02e5d4-b22c-5301-9dac-b90f382eb5c4 | note | Category - IP
5895347f-ce7a-526e-a2da-1426d7930fb2 | note | Responsibility - Foreman SE/PE/SPE
bb27bb5f-8372-5a0d-a70e-a1c81ff015ce | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
73e8ec76-980e-5c07-94da-ee220a835c56 | note | Reference - IFC Drawings
7d28667a-ead0-5708-8ae0-0d9bf286ff15 | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
9164f8ea-7361-5daa-81ea-919af1980ab8 | note | Method - Document Review
02316d14-06c1-564a-a951-dba0ea5c5c16 | note | Frequency - Where applicable, each element
13719a54-2220-5786-9a1f-b093e3dfe6cf | note | Category - IP
13980211-aabf-5c97-abd3-deed0294a19b | note | Responsibility - Foreman SE/PE/SPE
568745ef-39f7-557e-8616-f2a529639fb6 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Surface Inspection - Cracks
fe5ec126-bacd-55bc-a97a-5233f04130cb | note | Reference - 610.24
3b657d28-8625-5c44-b6fb-b6cefc1c808f | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1) If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair. Attach: Post-pour Checklist
ade551e2-608c-5a69-8b8f-2d02fe369949 | note | Method - Visual Measure
f86da82b-bb4a-5ddb-ae4f-953d8e036ba6 | note | Frequency - Each element
815874de-dc30-5858-aa34-3e07b1b4b3cc | note | Category - IP
f800e79f-5e67-5f95-b26f-897ec5de8728 | note | Responsibility - SE/PE/SPE
8ab0d78e-a4f6-53c5-b931-c45c0d5e5361 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Surface Inspection - Surface Finish
2ebdccea-19d9-55b5-b1d2-40a4a97b8cdf | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
25424a33-a334-5c33-bc2d-89381f8ee200 | note | Acceptance Criteria - Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair. Attach: Post-pour Checklist
43377be1-5fbb-54a6-b8c4-40d11d0c0a0b | note | Method - Visual
8efb1338-d924-58d8-9732-1365943f0036 | note | Frequency - Each element
856bda69-aa42-5ba5-9f3a-8e7dc18747c5 | note | Category - IP
c49d4421-4389-5412-ac80-94558ddf1511 | note | Responsibility - SE/PE/SPE
e3d5b81f-b312-5476-af1e-7888feb60120 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Measurement of Concrete Cover
669507af-275b-5c36-8fdc-1cba47c20fbf | note | Reference - 610.34
7064b917-02df-586a-bc36-df09734b2c7a | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record
ff911b46-d8fa-53c7-9e6c-87d7a4e25b1e | note | Method - Measure
5b2822ff-1754-5674-bf6e-17f729cf353a | note | Frequency - Each element
fa219d24-2cad-58b0-8f3b-f1c1a847063a | note | Category - IP
46412833-1ca2-5d8e-b1f6-714e2bc1e33c | note | Responsibility - SE/PE/SPE
71faffb7-ae5f-54b5-9f13-f9f1656de7c2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
37a5317b-da01-5f29-8315-74e43d878764 | note | Reference - Placement of Fill Material Against Concrete 610.35
b598f4ff-841c-5be1-ba1b-7176fb8d1f57 | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour. Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements as per VR610.16(l) or maturity testing requirements as per VR610.16(m). Attach: Concrete Test Results or Maturity Test Results
36cc2882-23a6-5745-8029-50a564c3daf9 | note | Method - Document Review
4b33a6a2-8a6d-5d96-b1c7-66a1a3092641 | note | Frequency - Where applicable, each substructure element
31fe6c82-0d5f-5240-a564-67f795cc8891 | note | Category - SP
ff3fba5e-556e-5ada-88c8-3c0c2b4ec50c | note | Responsibility - Foreman SE/PE/SPE
35d365ba-f707-5882-808b-04984df130f2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Compressive Strength Test Results
751caeac-6bd4-5b1f-9182-be1575ab072a | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
9c431492-7d3f-55d1-81c4-4a6e598d4379 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
37371031-ea59-5ee6-aedb-8a95af2d9817 | note | Method - Document Review
e331b9cc-3427-585b-b74c-beadbe289fa9 | note | Frequency - Each cylinder
83f94358-0df1-596e-b4df-ab4695db92e9 | note | Category - IP
aa76bdb3-1f65-57ed-967a-3397d54c892a | note | Responsibility - SE/PE/SPE
e28bd86c-0a9d-5b0c-94a9-ac5e3dd099ef | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.8 - As-built Survey
be5e5621-44db-540a-8d66-4e7771f6428b | note | Reference - IFC Drawings 610.47 Table 610.472
9c44c529-de07-5c25-a8b0-4d65d9ab7481 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report
81ed64f3-7bf5-5de6-9e10-62057627d3f5 | note | Method - Document Review
46c3e00f-210a-5b68-ba6e-565de02248db | note | Frequency - Each element
439667f9-bd8e-54e2-bfe7-4fa8bf531df2 | note | Category - IP
94cb8565-a0d4-5dea-816f-088d3cde89eb | note | Responsibility - Surveyor SE/PE/SPE
3735b127-6757-5cd5-ae3e-49455d426593 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
8f780748-2b7f-54b9-8ed7-11d4f3c81d59 | note | Reference - MRPA Quality Management Plan
4dcee724-5247-5abb-a82d-bc843105d0ce | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
6ae15404-8b4a-53e8-8cad-87888fd5cf06 | note | Method - Document Review
4429dd24-6f70-58f3-b683-0cd66acc088e | note | Frequency - Once, prior to closure of this lot / element / Work area
83188ce6-da23-5d7d-86a9-8f356d50aec8 | note | Category - HP*
062fdf13-150d-5dfd-b79d-fd15e9cfaadc | note | Responsibility - SE/PE/SPE
bfac8609-f59f-5ecb-b168-24dd00f2141a | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
b93b4bf0-ba64-59d3-904c-8682a7fc8f08 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5869039b-5b46-5e16-ba36-92bca989c4f6 | textbox | Print Name:
736ff85c-25b3-5b69-a890-bc69071408dc | textbox | Position:
236e24a3-75c5-53a1-9d3c-e75f83ac52a2 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-040-STR-Brunt-Crossheads | itp | ITP-040-STR-Brunt-Crossheads | 0df3df74-7b1a-46ac-9670-03a76ca36598
| section | 1. Referenced Documentation
| checkpoint | 1.1 - Non Dependent
b27e02bd-a3bd-55c4-adbb-7ae2ea5d5f55 | note | Reference - VicRoads Section 602 October 2007
ffae9433-8834-5ea4-96f5-8d3c4af86b6a | note | Acceptance Criteria - N/A
dcfd8a5c-5404-5cfa-963c-68fc312a8820 | note | Method - N/A
a3d5a28c-9a4f-5675-b78b-75b86f359daa | note | Frequency - N/A
95d17df0-aa69-521a-97a9-2b5c0248e7b7 | note | Category - N/A
ff4e7392-46ad-5c34-92d9-0131d5c4d832 | note | Responsibility - N/A
286caf76-0051-57f9-b4c5-7a41fd4a8df6 | note | Verifying Documents - N/A
| checkpoint | 1.2 - Non Dependent
1e6805a4-02ec-570e-bcd5-08ee451ab745 | note | Reference - VicRoads Section 610 February 2020
8643fd40-2c93-5175-86cc-34a1645e1e90 | note | Acceptance Criteria - N/A
ec12a90f-cca4-5fe9-837a-35ccc67e3768 | note | Method - N/A
e5bbd377-ed40-59a1-a2b3-20fa3b14ca6a | note | Frequency - N/A
dba2365c-95e4-58d8-a6d3-addc8e397a57 | note | Category - N/A
1c58e7d1-d1c7-5f99-94a3-33cdb4b4cfa4 | note | Responsibility - N/A
00cde830-cd5f-5f34-9fb5-9125eb5acd1f | note | Verifying Documents - N/A
| checkpoint | 1.3 - Non Dependent
1927c941-cbc6-5019-8660-5254e525166d | note | Reference - VicRoads Section 611 November 2018
787de003-e96a-5b9a-a448-44aec24ceabf | note | Acceptance Criteria - N/A
9d86c5a4-ff5e-584d-b2b8-e7ef8a68fa55 | note | Method - N/A
f7fd4255-6313-5dd0-ac0d-241f1deddc01 | note | Frequency - N/A
23a2c1d3-067b-5086-be81-c7278a62cea8 | note | Category - N/A
c76851d1-43f1-5cd0-9bd4-bb9ac83d3748 | note | Responsibility - N/A
577fec26-ce59-5921-9f9d-f46b69883893 | note | Verifying Documents - N/A
| checkpoint | 1.4 - Non Dependent
7be9747c-bc23-54be-9233-c50d9594172e | note | Reference - VicRoads Section 614 June 2017
67c8e5e5-d33c-5df2-8216-3922f89d57cb | note | Acceptance Criteria - N/A
d17fd006-d929-5c32-a4d8-90e6a3584bad | note | Method - N/A
297bfd2a-4dee-592c-9d02-4dfe6c3f16f8 | note | Frequency - N/A
5fc10871-3891-54ca-8e39-3006d7e5bd74 | note | Category - N/A
cdf16ebc-fb2f-536d-9fea-5456ed1c920f | note | Responsibility - N/A
591ba7c4-ee1a-529d-a8c5-92438e0cb0b3 | note | Verifying Documents - N/A
| checkpoint | 1.5 - Non Dependent
b6f7f1ac-8d06-5997-b9a8-2b88180f267b | note | Reference - AS3810.1 2018
35b1594d-b99a-50a9-8eca-7d376d4f4195 | note | Acceptance Criteria - N/A
7d44adca-7e50-5e3f-a012-1693227b8082 | note | Method - N/A
b7ba4732-568f-5382-aac7-0f8e38d69069 | note | Frequency - N/A
e4b8c650-06fa-57b7-85ba-2a4f05fc4b1c | note | Category - N/A
86d3a37b-015b-5082-833d-3290a58e44b3 | note | Responsibility - N/A
4d339497-ea86-5b50-913d-016e3bebb42e | note | Verifying Documents - N/A
| checkpoint | 1.6 - Non Dependent
4285755e-655d-5616-83e8-c0e9984faa05 | note | Reference - IFC Drawings
61e4615c-d2a0-5d12-811d-044a405b75b8 | note | Acceptance Criteria - N/A
56b6850e-9c12-575f-8842-a35b86042806 | note | Method - N/A
d0b3c59d-3af3-572f-8e78-556dafe45df5 | note | Frequency - N/A
8c3ff816-4a40-5a90-aa52-4dbbdba42cb1 | note | Category - N/A
ae0eaf4a-6b06-54ba-802a-a7934b44d817 | note | Responsibility - N/A
d7782900-0a60-5799-8567-6a136881e208 | note | Verifying Documents - N/A
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
918edcb4-81e1-530e-9d1a-b8b4c572f762 | note | Reference - 610.07 Table 610.071 IFC Drawings
e1a92914-15f3-5ccc-bc48-4115f886e5ae | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box]
31caf27d-b691-53c6-befa-2e4aa2e077c7 | note | Method - Document Review
e28ef35e-e155-57e3-8f6e-b340de18209f | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
2b77ec8e-894f-5486-93c9-3ddf48eb4673 | note | Category - HP
d0a54058-3f28-5500-9a0a-e61fab8a10bf | note | Responsibility - Nominated Authority
78cf7dd5-1895-5220-b6d0-61e098bf7619 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
421ad706-39d3-5088-917f-6b4ddf84599a | note | Reference - 611.05 (a)
48d3f568-5c01-520d-99b2-2eb40253a41d | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box]
23930ca5-ee26-5567-a66a-a1e560bd0a05 | note | Method - Document Review
0cfc3e95-fed7-567f-a1b3-be30d4d118a0 | note | Frequency - Once for each supplier, 14 days of award of contract
b3d56112-e4af-5979-bdb6-83d43eac8934 | note | Category - HP
6f7dec3e-d645-5192-815e-87d815f55c45 | note | Responsibility - Nominated Authority
d6f94f03-ef28-551e-a7f9-652daee5aab5 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
1cef25d7-6f85-5a72-8268-5fadc5db4da2 | note | Reference - 610.26 (a)
6220aef8-62e7-5d50-b1b5-226bdd856dde | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
20dcbb55-3013-5ee2-a64a-dfa343b20f87 | note | Method - Document Review
e88c864e-633c-5755-b68e-3c48a0d04705 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
60441de4-35d9-5924-a163-98da58bf71c2 | note | Category - HP
802db343-794f-5f36-8d51-7dd80a2f09ce | note | Responsibility - Nominated Authority
89f2a046-9e76-5c17-b46a-d3f65f5b21b0 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
a2947c71-87fa-5491-bb49-b253a633fcc5 | note | Reference - 610.17 (f)
fd859f12-b12d-53dd-813b-f12c14f3a319 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
753a7a2c-c676-53a3-821c-b5411cf6f4e8 | note | Method - Document Review
e565407e-f510-5cc2-9bb8-19a2b81f1485 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
cba30253-fd5e-5370-8b67-a3e1d038fa53 | note | Category - HP
63f32dfb-2eee-5b95-ad71-620d958754e6 | note | Responsibility - Nominated Authority
6a407cba-ec3c-50ee-9195-b1f0e7c0b3c2 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
98f01bcd-2515-52cb-b5f6-8f5b2ec0588d | note | Reference - 610.23 (d)
b94e7cf7-a7c4-5cd1-be5c-91af20b02043 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box]
c4ba51c4-6c22-542b-962c-33cef24de85f | note | Method - Document Review
6d7d1877-bfe4-5585-86c7-d033dd367c6a | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
ff5f208e-7e1e-53d4-81ac-95000c4aa81c | note | Category - HP
9e00c9ce-6f11-530e-89bf-d47f4ff1ea53 | note | Responsibility - Nominated Authority
5bcc536f-c24b-5388-bc1e-5eb72270baf4 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
f160812d-e3ff-5f99-92ff-de4b6e4b17f7 | note | Reference - 610.18 (a) (i)
c3227d0f-b5c4-51df-8693-f6ac4e0d917d | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
b2767d9a-302a-5232-9456-2343092653b0 | note | Method - Document Review
5e461b58-e190-5154-8173-496a6de513c1 | note | Frequency - Once, 4 weeks prior to placement of concrete
3e2d2090-4049-56e0-82eb-4c1651685388 | note | Category - HP
883d92ea-14a6-5881-8d14-774bef18d609 | note | Responsibility - Nominated Authority
22f669da-9e51-5dc9-8df2-aa3b00af6745 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
98101f73-23a2-5a6a-b9df-cc4d7d867547 | note | Reference - 610.18 (a) (v)
3ba7dd65-438f-58b5-bce9-441dcbdfdc71 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
3d742dc4-89d7-5f3b-8b4c-7853963fccb6 | note | Method - Document Review
1db625e1-dc4f-5e98-ac07-7cf4453fe201 | note | Frequency - Once, 4 weeks prior to placement of concrete
bd67564a-e828-50ce-baa0-423c89cf6743 | note | Category - HP
22e3591f-efde-5779-b2f4-5a273036ef58 | note | Responsibility - Nominated Authority
4ec0d086-ccb1-52fd-9153-aa5b7d1475d7 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
6dc4edc5-1c92-54d7-8fb4-fc38ba7a685c | note | Reference - 610.18 (a) (iv)
9b3f6f8f-6c86-5b4e-8715-3e8a7143d2f7 | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements. Minutes of this meeting to be submitted to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
3946dfe2-252b-5480-8289-83754a1f1b3d | note | Method - Document Review
3213ba14-256d-557a-9f77-706546399329 | note | Frequency - Once, 1 week prior to placement of concrete
dd1935fc-1457-5ac0-8614-78e8b18800a9 | note | Category - HP
9efa6ca0-c0f9-56c7-a1ea-395c6d55ef91 | note | Responsibility - Nominated Authority
1e8c5879-02da-538b-a8dc-9564a88153d6 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
5ea6b2fd-58a0-5d19-b444-46a1e6452d91 | note | Reference - 610.17 (a)
1c0fc2ff-02af-504c-8355-70ffc433dd4f | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
afe5d178-8293-5baf-826e-7b5e082a7099 | note | Method - Document Review
7364801b-789c-577a-95fc-98a2426d7756 | note | Frequency - Once, 2 weeks prior to placement of concrete
10b0f276-fc2f-58aa-8efb-b22c5c6535af | note | Category - HP
b275b502-d78e-5a64-a999-da14e716fd9d | note | Responsibility - Nominated Authority
a68b835c-45c9-51dc-b9d3-9a9ca3147a65 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
3aae0f2f-f22b-5c4e-a851-e7bf6b38ca7b | note | Reference - 610.23 (a)
642e9225-2876-5d24-95fd-e0ba0d2afd0c | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
ac470752-fb9e-5b86-85ae-9ae771ddd6b3 | note | Method - Document Review
159fb69e-44d1-5608-a0a4-391556830f69 | note | Frequency - Once, 4 weeks prior to placement of concrete
ef8152c7-02e8-55c3-83c4-1ee60d199b70 | note | Category - HP
533e00ac-98e3-5a46-93e6-5b31cf4d3cd2 | note | Responsibility - Nominated Authority
b8a29ee7-7153-55ca-9074-e7d4ccf3cc6a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Concrete Drilling Procedure
16ab8fa8-bd83-5447-9f52-06027e275e31 | note | Reference - 610.46
6e061024-196d-564d-bf69-f9479d316ca4 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. The planned locations and drilling procedure shall be submitted for review to the Nominated Authority. Enter: Teambinder Hold Point Ref Number [free text box]
81a73c3d-c5d9-5b4a-89f8-b20c7c24d87a | note | Method - Document Review
7227a096-842b-5d0f-a920-96ad0a3f5fcb | note | Frequency - Where applicable, once, 2 days prior to drilling
f8b627a6-e501-552c-ae5d-e2745127063f | note | Category - HP
f2f1d1d5-868b-5a6a-a3ae-a005419d053b | note | Responsibility - Nominated Authority
430af4b0-37f5-5485-a1a1-e7a6a09210c3 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Temprature difference measuring-Calibration
12f6306e-7351-5020-b9c6-459486d8e395 | note | Reference - MRPA Quality Management Plan
5cef6a4c-1b8a-5861-b124-57254ae4edde | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date. Attach: Calibration certificate
9a0c08cf-9b46-56bd-afdd-d44dc6a5b1ef | note | Method - Document review
85e1c8a3-832e-5a0b-972c-ab9b7c0c4389 | note | Frequency - Where applicable
3bd3d113-faa8-5cc9-bd20-61b613722dee | note | Category - HP*
57b4f106-11ff-5c81-8d33-a034ed70af0c | note | Responsibility - PE
6b96458e-ce5d-5d88-9af0-9762ecb8330e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
43526566-3504-5165-88fe-fbb5ca2897a8 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3 611.14 (b)
1de32447-6063-5cc2-b2b5-64d7bd771623 | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
adcf6ce9-cf15-5c3f-a698-572fa7498e85 | note | Method - Document Review
7cb6c8f8-1109-52a5-83e1-4d378540d159 | note | Frequency - Where applicable, once, prior to welding
99c32091-8bea-5619-99cc-435504dabd62 | note | Category - HP
a5b6a8cb-42ea-5d0f-8489-cffdab4d6d8c | note | Responsibility - Nominated Authority
72084f31-b242-580d-adc9-43041bc3ec71 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
4a22cc0a-8cca-5946-b69e-e6eac22c1791 | note | Reference - MRPA Quality Management Plan
684e6bb2-c252-501d-9656-cc5034f030d6 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
98d9944f-67b7-5ad4-a164-fae860024707 | note | Method - Document Review
6a85a2f4-b48d-5f0f-8904-ef45d6993d7c | note | Frequency - Prior to starting Works and at regular intervals
40f28076-0f78-5248-ba90-0cec46ff06ee | note | Category - HP*
18b35bed-8178-5f76-8c83-1968f2ee5d56 | note | Responsibility - All
c05ca8f3-267b-569a-b38d-4f6adc906f9c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out
b818dde3-7602-518f-b1c2-3844f2ab74fa | note | Reference - IFC Drawings 610.47 (a) Table 610.472
556dc52b-43ba-59b6-823a-375507e402d3 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element. Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
7b072249-790d-533f-8557-88f2d0586d7b | note | Method - Measure Visual
57aaac33-640d-5585-a77e-03a062db17a7 | note | Frequency - Each element
8c22ecdc-550e-55d1-af90-9283076249ba | note | Category - IP
7528832c-c774-5583-b0de-d7050d70fea0 | note | Responsibility - Surveyor SE/PE
28c234a6-b109-51bb-82b7-9b78a88703fe | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Abutment / Pier Wall Work Lots
c379fa4a-636b-598b-96d2-37af22101559 | note | Reference - TeamBinder Work Lots
fb99a79d-9833-54a1-af4b-481f00029de5 | note | Acceptance Criteria - Related abutment / pier wall work lots are closed. - abutment / pier wall design strength is achieved - As-Built Survey performed - Related abutment / pier walls NCMs are closed. Enter: Abutment / Pier Wall Lot numbers: [FREE TEXT]
4ea2f308-352c-5fec-9a11-2e2c3220bd40 | note | Method - Doument Check
f2050a72-874c-5c82-8645-b0f2ee58d2d2 | note | Frequency - Each Element
53c98460-2528-54fc-8fd5-083bb2623d8c | note | Category - HP*
085e5e0b-3bad-5495-a489-1cad26af26ef | note | Responsibility - PE
d692abb4-5579-5f4c-a6b7-b09e4c6ba091 | note | Verifying Documents - This ITP Signed Off Pile Cap Lots Closed-Out
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
a05c905b-7151-5f79-a2a9-c4b61bf2dc15 | note | Reference - IFC Drawings 614.04 614.05 614.06
350af9a0-008d-5e60-820f-f07be33bd51c | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
4c7a085a-3d3c-5304-9f00-2e10f5fecc45 | note | Method - Document Review Visual Measure
6284c549-5770-5bc1-93af-c7ddb75c50e0 | note | Frequency - Each type of element
fddc320f-0913-5986-b20b-b16d667489d1 | note | Category - IP
49f47fc5-8c82-50d2-9a81-a1b627596a9c | note | Responsibility - Temporary Works Designer Proof Engineer SE/PE/SPE
58a220be-4d06-59e9-8a7d-948c3dc4e236 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
48559d8e-5b1d-5cfd-bc12-3821ec1ff0db | note | Reference - 614.08
efa73ba2-e7c0-54dc-98b1-e5aed8f028ed | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Crossheads with heights greater than 2.0 metres Any member for which self-compacting concrete is proposed. Attach: Attachment A Attach: Attachment B
cb4142e9-45f0-5061-8e39-137a27bf550c | note | Method - Document Review Visual Measure
857539d4-fa76-5fdf-bad6-f4e13d02a380 | note | Frequency - Each element (where greater than 2m)
5e762c19-15d7-5a63-9855-f18807d607a2 | note | Category - HP
ab4f7337-6efd-53ba-8275-efb8ea27021c | note | Responsibility - Temporary Works Designer Proof Engineer
6bd5bcc0-1c7a-55c5-ae9e-096166be64c1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
dbca33b8-c2ed-5c54-a7b1-39aa6387475c | note | Reference - 614.08
d9ada07f-bc81-5db2-95eb-fc6b13f4820e | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Crossheads with heights less than 2.0 metres Attach: Attachment C
17b618c5-09c2-50c7-a729-1b7c960f67a3 | note | Method - Document Review Visual Measure
c398905c-8b48-5d13-86c8-e9414e4434a3 | note | Frequency - Each element (where 2m or less)
e1fc8d57-15a0-51fd-89f3-9104faa30e95 | note | Category - HP
eecc1478-245c-5625-9d54-b112ae7ac22f | note | Responsibility - Temporary Works Designer Proof Engineer
30e04448-3425-5dec-b4f1-2b395d70bc94 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
8375b679-f42a-5468-bdb0-5b326e6a6ee9 | note | Reference - 610.47 (a) Table 610.472
ac065a9b-3f12-5b14-9b78-41dfbdf9ce18 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
5693bb02-4db0-54d9-b0d9-cc1311ec0596 | note | Method - Measure Visual
ddddac92-d684-51bf-97fb-e922bd36c737 | note | Frequency - Each element
9e62f2b9-b698-5f75-8ae1-f8eadb2d067b | note | Category - HP*
af422d34-5fec-5e5d-bf70-934cdccb1824 | note | Responsibility - Surveyor SE/PE/SPE
9517f1e2-2def-586e-a7ae-e968f0ce0596 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Reinforcement Placement
9a04260f-72ed-5537-806a-ff1dd1348b5e | note | Reference - IFC Drawings 611.06 611.09 611.10 611.11 611.12
9d6bf065-dc53-5da0-bd20-f2cc60eccaea | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Projecting reinforcement is the correct length and location. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
e6c96f7e-c7dc-526d-9418-92ab16012672 | note | Method - Measure Visual
6cda1915-d726-5b89-8181-52242ee00407 | note | Frequency - Each element
84d2f6a3-fef7-536d-9e5e-4c9e73ca665d | note | Category - IP
1cd00d7e-2ea4-5693-9c46-099d13a2df48 | note | Responsibility - Foreman SE/PE/SPE
570072b6-00af-5322-9650-7e8cdec0df09 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Cast-in Items
c61b20b8-bf6b-5510-9adb-79fba456db7f | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
c369328c-5ace-5575-8161-b74a8735af2f | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement. Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress. Tack welding of any cast-in items shall be performed by someone pre-qualified to do so. Grout tubes shall be fastened at regular intervals to prevent kinking. Placement tolerances to comply with the IFC drawings, if not specified, use the following: i. Bolts, ferrules, projecting bars & couplers = ±3mm ii. Running dimensions of a group of the above = ±6mm iii. Ducts and conduit location = ±12mm iv. Diameter of ducts and conduits = ±3mm
085b72f5-9646-58a5-b431-91a62fe6322b | note | Method - Measure Visual
8a8a4c45-5df1-5b6f-9ae6-f3340ae9f3ab | note | Frequency - Where applicable, each element
1b04e21d-0952-5d86-8c26-eada22ce12f9 | note | Category - IP
c447ac9e-9b30-5f85-b914-47d8d52eba8f | note | Responsibility - Foreman SE/PE/SPE
0f084027-0412-50f7-9f76-6305a952ecc4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Thermal Differential Monitoring
070eaade-8423-56af-9527-ec48caca95cc | note | Reference - 610.22
09761e02-987a-5788-89ee-572df79f82f9 | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints
dfca3876-cd23-521c-a131-bdf6f88bb51d | note | Method - Measure
499c51ac-eb3e-513e-9163-1355f57a510f | note | Frequency - Where applicable, each element
9238e603-d9cf-5700-9b25-efe31d49b092 | note | Category - IP
00cf57c7-41d9-5991-92c2-b554d437b3c3 | note | Responsibility - Foreman SE/PE/SPE
1c570081-7c75-5691-85b8-bee49b1f5d7f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Pre-pour Inspection
d554e54b-b30f-509f-a3d8-1dcb577c1446 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
e4ee19e2-9cb6-57f8-8cc9-272c17425930 | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority All foreign material has been completely removed from the forms. ATTACH: Pre-Pour Checklist
e88c3d50-2280-52d7-9647-dbb1267d16c5 | note | Method - Measure Visual
4bbd4333-6c8a-5254-aec9-6556ed860891 | note | Frequency - Each element
dd0acafe-034b-5e99-9257-dbf24ae4e0eb | note | Category - HP
3f87274f-b955-59f6-8c0c-ccce086e1703 | note | Responsibility - Nominated Authority
800d902e-2236-5079-8962-424ae6acad82 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Weather Conditions & Evaporation Limits
655bef1d-965f-5b01-ba40-ddd154cde961 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17 610.17 (a) & (e) Table 610.171
efa039c9-e681-529b-b9c7-3210d7ca83bc | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete. When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS. Record: Required information on the Concrete Pour Record.
fbc58ff0-a45b-5a3a-951a-de99d1aeb309 | note | Method - Measure Visual
48d4782a-4c78-5541-a251-96c4c2b77e7b | note | Frequency - Each element
7ab5c6a3-027f-5dea-804b-c400bfbae4e2 | note | Category - IP
39214867-76e6-5336-8078-6b2fd220c52c | note | Responsibility - Foreman SE/PE/SPE
9b2688b2-2632-5939-9c4b-49e74bfc455d | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.1 - Concrete Testing - Sampling Frequency
56916cde-7a10-533e-8364-4acaa213e5b8 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
969b00ca-003d-5169-ba31-ad1cb1b27831 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing). Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork. Record: Required information on the Concrete Pour Record.
81480667-cf08-58df-9b45-e4dcfea06500 | note | Method - Test
3eebebc6-5572-545f-a0ec-639b82203d3a | note | Frequency - Each element
a0f272b3-ccbf-53c4-b91f-ca6aa7ebba4d | note | Category - IP
e2c5ffbb-243c-5d28-b29f-ea9b9287d26e | note | Responsibility - Concrete Tester Foreman SE/PE/SPE
73bd296d-f903-5a55-85d6-4a85b1ae4ca4 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.11 - Concrete Testing - Slump
1660eb06-4a81-55d4-8b70-c92e207d0d3c | note | Reference - 610.16 (c)
960d6af4-1945-5f81-a355-389e26a78684 | note | Acceptance Criteria - Slump testing tolerances = <60mm = ±10mm ≥60mm to ≤80mm = ±15mm >80mm to ≤110mm = ±20mm >110mm to ≤150mm = ±30mm >150mm = ±40mm Record: Required information on the Concrete Pour Record.
37f86e25-f7c5-594e-9a60-37171106a012 | note | Method - Test
bcc116a7-e941-5804-8e12-d5279d75b0a4 | note | Frequency - Each sample of Standard or Superplasticised Concrete
eb31cbcf-de15-592c-882c-1b87a3ac9236 | note | Category - IP
9873cede-cf33-5f77-aacf-6d1a92dc3738 | note | Responsibility - Concrete Tester
49fc3606-5232-564e-b5d1-0a1d6fdf0ecf | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
98c0aa97-37b6-5622-86b3-58e2667c3e59 | note | Reference - 610.13 (b)
6f010b1a-0cf4-59ae-a08c-1c463a1cfd28 | note | Acceptance Criteria - Spread range = 550mm to 750mm T500 = 2 seconds to 5 seconds (to reach a spread of 500mm) Passability = ≤10mm (aggregate height differential) Record: Required information on the Concrete Pour Record.
e94ac6be-3fc8-59ce-89e2-0e3fbf9c9421 | note | Method - Test
2bf65978-a881-5051-8904-9a8c431e87d5 | note | Frequency - Each sample of Self-compacting Concrete
c404afe3-852a-55f5-a5a9-2ed95962fc19 | note | Category - IP
e3e83cf2-2578-565b-94ff-13c246522302 | note | Responsibility - Concrete Tester
38fbf372-81ce-5ce8-b01a-29fbcd0b3e54 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
ff419925-61e1-5016-9ee2-418ff5ec0ec5 | note | Reference - Site Sampling & Testing Procedure
e3d312d9-042c-563d-a8c4-eecab742bc12 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample. Record: Required information on the Concrete Pour Record.
ffddce52-8b2d-557b-b028-3203f0f35dee | note | Method - Test
d9ddbaaa-7268-551b-a258-6d4b5c293be8 | note | Frequency - Each sample
6ee1ccf3-6fe3-5283-8faf-0771f987bff6 | note | Category - IP
3c33a3f7-fb7e-5d44-b5c2-8ca9aff4ea52 | note | Responsibility - Concrete Tester
a2145eda-d740-5205-b386-9bd0d503f5ce | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.14 - Supply & Discharge Rates
f9f4dc53-dbda-5fac-b131-95451aa92e41 | note | Reference - 610.13 (a) & (f)
c5558aad-49c1-50e1-9a38-4ff3773b2caa | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed. No water is to be added once discharge commences. Maximum time between batching trucks is 25 minutes. Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants. Concrete that stiffens or is showing signs of stiffening shall not be used. Record: Required information on the Concrete Pour Record.
9cb29739-ca5d-5c3a-9404-22d6fa96de20 | note | Method - Measure Visual
ee13608e-74f2-5896-a9ec-a72510e5dbf6 | note | Frequency - Each load
9fd3268e-32df-54c8-9456-ea8f7fde7358 | note | Category - IP
cef3e338-786c-5334-9946-78167c58e28b | note | Responsibility - Foreman SE/PE/SPE
397306ee-3475-5fa0-a449-bd6e7808ff34 | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.15 - Placement & Compaction
2e4940f0-2109-5e70-8891-0449c8b0b1a4 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b) 610.18 (d) (i)
9d188a50-ae2d-5344-ba61-df14a2317a76 | note | Acceptance Criteria - All concrete batches are traceable. Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged. Concrete is not dropped freely from a height exceeding 2m. Concrete is not moved horizontally by use of vibrators. Adequate compaction is ensured Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments. Concrete layers are not more than 350mm Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence. Vibration continued at each point until air bubbles cease to emerge from the concrete. Record: Required information on the Concrete Pour Record. Attach: Concrete Pour Record Attach: Concrete Dockets
5b3051c0-7105-50df-8354-5a7e6c65b280 | note | Method - Visual
24975b6a-5b8d-554f-b9b8-4f18531ab0ef | note | Frequency - Each load
ac224157-12c9-5fa4-8e9b-fa782d4d7d33 | note | Category - SP
a13f59ae-e425-5fdb-bbfd-c8ae18f6ac02 | note | Responsibility - Foreman SE/PE/SPE
a520eb1d-ef99-5808-a542-4a50c14d559b | note | Verifying Documents - This ITP Signed Off Concrete Pour Record
| checkpoint | 5.16 - Surface Finishes
671404c4-d7aa-546e-87a8-ab9999d925a3 | note | Reference - IFC Drawings 610.31 610.20
f9390968-dc06-58a7-b18e-aa3634732ca1 | note | Acceptance Criteria - Surface finish as per IFC drawings. Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31. Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
8157bfe9-e5b5-5383-b160-bf60eff6c54f | note | Method - Visual
517d2803-3a2c-5b9f-88b4-9a870467c7ea | note | Frequency - Each element
51b5cb06-bc34-5cb4-99c7-07e1d80a8fcc | note | Category - IP
8c7b7bd8-27c4-5c92-a7b6-e36c77d9472c | note | Responsibility - Foreman SE/PE/SPE
b26db7e3-42f9-5473-8c13-81733c2ecf4b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.17 - Curing-Top Surface
57fc6b60-402c-5a8d-b2a9-bb55e3d7b2d6 | note | Reference - IFC Drawings
df315db6-4ba4-5534-b7c3-e7c6b03d4eb4 | note | Acceptance Criteria - Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
22e849c5-e151-5532-9c4e-f8c197f94eb9 | note | Method - Visual
e12659ad-4824-5511-9ab8-4167dbb3d7b0 | note | Frequency - Each element
7fcff00b-565e-5730-a434-c009221669ad | note | Category - IP
515014a5-212f-5400-98e2-af1e67ff5acd | note | Responsibility - Foreman SE/PE/SPE
f27411f6-cfbe-59dc-bab9-7c8c89924f38 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.18 - Curing after formwork removal
ba8119b7-25c8-5a43-984e-6b823da6a8a9 | note | Reference - IFC Drawings
799cafa6-3f75-55be-aa51-4a898d7461cb | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
2610e6ce-1fd2-580f-a3f3-4f57c9bae9f1 | note | Method - Visual
11a047be-5506-52ca-9fbd-940fb4aa9973 | note | Frequency - Each element
0440a80e-cac6-5fdc-84cf-759a68644a89 | note | Category - IP
bb990bb9-496d-543e-b900-534de4abce16 | note | Responsibility - SE
6a3585b1-9c18-5045-8cc7-f5d40738d1a6 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
98f468ca-9ba7-58c7-890a-c0fafb9df112 | note | Reference - 610.22
f9ffc736-205e-5c3d-a375-ff997d2f20c5 | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C. Only applicable if the element has: i. the smallest sectional dimension exceeding 500mm ii. one or more faces being restrained by previously hardened concrete or other external constraints. Attach: Thermal Monitoring Report
237ab443-f0ca-50e6-9389-26398358d58b | note | Method - Document Review
0cd841d1-7ff4-5f55-9173-808df6a05be4 | note | Frequency - Where applicable, each element
b42786bb-18f9-596e-9d6a-3dfc37b00f74 | note | Category - IP
144dbf8d-8963-5a64-8b51-42d68c08765b | note | Responsibility - Foreman SE/PE/SPE
06f865aa-824b-53dd-9eec-3b26bff028c0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
4e03f94f-be01-5211-aa1c-6c60fc5173a5 | note | Reference - IFC Drawings
23cb961a-ddcf-5371-8740-e4eaf2a6d42d | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
43e1b657-c423-5cb8-a935-eeffd19ff604 | note | Method - Document Review
ba82acc7-fde8-5903-9f31-4d4f07de2965 | note | Frequency - Where applicable, each element
0012e05d-28dc-5dc8-b227-8f1a0c0b79a8 | note | Category - IP
4eea8a01-a114-505e-ba53-612db767b395 | note | Responsibility - Foreman SE/PE/SPE
f6e85855-2e8f-5a81-b4a7-54eb87fa715a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Surface Inspection - Cracks
89620f70-ec61-545c-bbde-e8557db56b6b | note | Reference - 610.24
2758516c-6d18-5ed6-9196-1f1e44edce36 | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1) If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair. Attach: Post-pour Checklist
30f970bb-7b06-5486-9fab-8deca58dc9df | note | Method - Visual Measure
ab96af6d-fc82-56fd-8ccb-ecfe009aecfb | note | Frequency - Each element
9aad0867-be7a-52fe-afb8-d6e5aef78cc9 | note | Category - IP
20851d8b-e99d-50fa-a081-59d44a965dee | note | Responsibility - SE/PE/SPE
06f2703d-1497-55eb-b86a-0b3a7067cf18 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Surface Inspection - Surface Finish
ac3e2410-75df-5173-a744-c0558f8efd45 | note | Reference - IFC Drawings 610.31 (a) - (n) 610.32
aa49abe4-0182-57a2-83b1-86d19f45f614 | note | Acceptance Criteria - Comply with the IFC drawings and specifications. Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair. Attach: Post-pour Checklist
53829b38-606f-590a-a1d7-ced8a5ce90bd | note | Method - Visual
6c11cf1f-3845-5d1e-bf19-203db4a3015d | note | Frequency - Each element
057af62e-4e54-559f-88d8-39ed8bd5c279 | note | Category - IP
640e3f1f-982e-5100-82a2-573688064af1 | note | Responsibility - SE/PE/SPE
e04f75ff-22ba-58cb-96e3-443d0e9587c7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Measurement of Concrete Cover
51191e84-7760-5e5f-b89d-4c26b6c49679 | note | Reference - 610.34
fb0b1cac-310f-5292-a28d-366134e796a7 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area. Minimum 10 no. measurements recorded in each area. Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority. Attach: Covermeter Check Record
e96ba2f2-e62a-5721-882f-3a11c5b56ab1 | note | Method - Measure
52f8268e-14dc-5a5d-b82d-0ab90e6c3ede | note | Frequency - Each element
401f8ed4-12bf-50b5-98e3-61ac695d3a09 | note | Category - IP
e9515fe0-b57e-5a8e-9c1c-20a9193a7707 | note | Responsibility - SE/PE/SPE
b7bcd815-a450-5da7-b391-bc37d1b9179a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
93f0aec6-e247-5319-8f3b-6048c41b7cea | note | Reference - Placement of Fill Material Against Concrete 610.35
7ff6682c-3d4f-5c45-a355-d6b5ea52a950 | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour. Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements as per VR610.16(l) or maturity testing requirements as per VR610.16(m). Attach: Concrete Test Results or Maturity Test Results
670f36f0-f640-57d9-aacb-cafc21273890 | note | Method - Document Review
0d783648-7291-5191-afea-7d5a5b03e8dd | note | Frequency - Where applicable, each substructure element
65025062-941e-5a82-a8ca-f11961f91d53 | note | Category - SP
eb16fc23-bceb-5abd-9df4-828793069435 | note | Responsibility - Foreman SE/PE/SPE
218a70fe-3d5c-5226-86cd-d1828fe87ee3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Compressive Strength Test Results
000593ad-5c2e-5439-893c-25e3755e5c7d | note | Reference - IFC Drawings Table 610.05.051 610.16 (g)
3202c9fa-8dda-54f6-a2fd-db2f496e2bd6 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Attach: Compressive Strength Test Results
425c742a-30ef-5603-a32a-34114c6faee3 | note | Method - Document Review
1144a892-0394-579a-80f5-0dff0087a9c8 | note | Frequency - Each cylinder
520e280e-3993-5464-a7df-5aa461981720 | note | Category - IP
0bad5ad8-31d6-57c0-bb14-9c73c7de9f25 | note | Responsibility - SE/PE/SPE
1296c5f0-6067-54ee-b52d-a7cc533e224d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.8 - As-built Survey
bfb193a9-24d3-55a6-8786-7ab287c647a0 | note | Reference - IFC Drawings 610.47 Table 610.472
5b72b0db-c4aa-541f-a2da-16abedc334a3 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element. Attach: Survey As-builts / Survey Report
4e0744ab-e0d8-5863-ae68-8bea3d70d182 | note | Method - Document Review
03c62e78-25e5-5e94-8248-ab8b19602479 | note | Frequency - Each element
51611656-e8c2-5e23-b7a4-1f53ea64ddfa | note | Category - IP
5a2e9cd2-943b-5d40-93a8-6acd1f73d144 | note | Responsibility - Surveyor SE/PE/SPE
98e67c7c-2b22-5fc0-9b24-d481576eace5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
cf0bd29a-5c5b-58a6-a5f7-604ed039ade4 | note | Reference - MRPA Quality Management Plan
1d7e2348-4c6a-5b56-aa94-3a429e9db1b1 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
be18b9c3-41e8-559e-808f-1d0ddfeda1de | note | Method - Document Review
7cbe5143-69e0-5c6e-90cf-5d013f75684e | note | Frequency - Once, prior to closure of this lot / element / Work area
86fd1693-d25a-5824-ae8d-70916a1dcdcf | note | Category - HP*
2af0cf3a-7018-5fb1-9e9c-29bc1065127a | note | Responsibility - SE/PE/SPE
7cb2bddd-415c-529d-b921-1ba53f42843a | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
274fa4f1-8cc6-5c73-a542-6611f151d5bd | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6986390d-871c-5db7-ae1c-44740ef89e15 | textbox | Print Name:
61b07c1f-a48d-5637-9471-f83ecee6941c | textbox | Position:
c32a73a9-08ac-555b-8d15-e7c1c1b44270 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation | itp | ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation | 41e0c697-a58c-4e2c-a5aa-26507684652e
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
8efa6ac7-1af9-566e-ad45-6c8092f1aa3b | note | Document Title: ITP-041-CIV-Brunt-Stormwater Drainage Supply & Installation
db3736db-7a5b-5aa2-aac4-469ed7495b1d | note | ITP Description: Stormwater Drainage Supply & Installation
2040fe3b-04ea-59a3-a0ab-bb016f32c9ef | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
72211ba2-e5c1-5ddd-8d5c-a661487da60f | note | Discipline (e.g. CIV/STR/RAIL): CIV
0508fab6-a678-54d6-8ef0-8dd1dbb96404 | note | Revision Number: 0
feca692b-ea2e-547b-a65e-682bdeafeeb8 | note | Revision Date: 15/06/2023
f0f06b29-7376-5966-b9d4-30854fc26287 | note | ITP created by: Kamel Alshobaki
f98f0887-e7c6-5797-9b79-83e914c58d0b | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
b19d3ec8-6437-5778-88d2-d888367a8c01 | note | Reference - VicRoads Section 701 (May 2020)
| checkpoint | 1.2 - Non Dependent
1cfa6932-1c82-513c-ba0f-55bc1a6e56c2 | note | Reference - VicRoads Section 705 (June 2021)
| checkpoint | 1.3 - Non Dependent
7061884d-9d02-5b78-9dbb-ddedb5553253 | note | Reference - IFC Drawings
| checkpoint | 1.4 - Non Dependent
a19f1b1c-9b49-537b-b5ab-944cdd7a8ed4 | note | Reference - CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
| checkpoint | 1.5 - Non Dependent
17aa524a-ddea-59d4-8a55-44a82dd335ef | note | Reference - CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
| checkpoint | 1.6 - Non Dependent
509ccfc7-c0e9-5eb0-9ff0-17ecba712120 | note | Reference - CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
beafd793-64c9-5261-b53d-ef61c4274144 | note | Reference - VR Section 701.04, VR Section 701.05, VR Section 701.09
992d77ce-7504-5d6b-9bff-d8d9364f9763 | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and VR Sections 701.05 & 701.09
552c4f00-2ba0-5f1c-a110-bbcf118317fc | note | • Precast reinforced concrete box culverts shall comply with the requirements of VR Section 701.04
3836f5f4-f4fa-53c0-af57-a05602ed61fa | note | • Rubber ring joints shall comply with the requirements of AS 1646
10abda73-fd7b-5f4b-8c05-c7cd0f0ba145 | textbox | Enter: Teambinder Material Approval number
b8d17af5-f190-584e-9b71-662323a7bb2f | note | Method - Document Review
4c7a6422-475e-54b7-a645-a3ef9f8e173c | note | Frequency - Each lot
36806afa-3f72-59ac-8519-03d2543f5b71 | note | Category - HP
3a0d5bed-0645-54a7-a26c-7e3c9e9435de | note | Responsible person - Nominated Authority
f1350160-a5a9-5cf6-a319-eef155ad97f0 | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Precast Drainage Pit
54719274-398f-5209-84c6-f52d3d62dcf6 | note | Reference - VR Section 705.07, VR Section 705.04, VR Section 705.09
82c92b6d-8d2c-5849-985b-d83e0a193511 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705.07 & 705.09
6df2cbea-d001-51dc-b5d5-d3970a406fae | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04. Concrete grades shall comply with Table 705.041
269c96fa-be97-5a74-bc3b-b5c4f2a1205f | textbox | Enter: Teambinder Material Approval number
39eb13e5-b872-52b9-a615-965cc0cbfdc2 | note | Method - Document Review
bdd5fe2c-2a19-58cc-90c5-b6575ac4d9fe | note | Frequency - Each lot
60c30fae-6fb3-5a50-9c1d-22e463d777b0 | note | Category - HP
2fcc6cef-8ede-5339-9e85-101366e6e0c5 | note | Responsible person - Nominated Authority
f35ab8ef-0350-5f68-adb7-f3de64da22ff | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Cast in Place Drainage Pit
4b87532c-9284-5bcb-9bb9-caf2b07a9f45 | note | Reference - VR Section 705.06 IFC Drawings
88325314-2481-5650-bbc7-cd6141946096 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of VR Section 705.06 and at the locations and to the dimensions shown on the drawings.
e4fd580a-ba63-556e-8f4e-118446246cb2 | note | Method - Document Review
4e43e2c5-0480-573c-b045-a6f9ba662a33 | note | Frequency - Each lot
929c4ada-6198-5192-9bfe-e6f14ea2029f | note | Category - HP
e885cb91-cc36-5a3d-8f8c-78f306db5192 | note | Responsible person - Nominated Authority
ff00914a-9b1b-555b-9c03-a21b32f57bdc | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Drainage Pit - Step Irons
29367844-bdd6-5b08-a63b-4e1d2e80ed58 | note | Reference - VR Section 705.04, VR Section 705.12
dd001160-c1ed-5d4b-9027-df26165ffa47 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
bb6a9eae-8a99-5220-a6ce-25ff98015832 | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705.12
93168828-d157-5c14-bed2-c25d9cf94129 | textbox | Enter: Teambinder Material Approval number
18c170e3-5f87-543c-8a42-dc5cc815aafc | note | Method - Document Review
58b99ac5-7b1a-5c56-b995-68d4f815df66 | note | Frequency - Each lot
ee9aed34-3e70-5783-9639-d8155a9d9ac8 | note | Category - HP
f346954f-6415-5cb1-8b58-0d8ffe2f4a7f | note | Responsible person - Nominated Authority
c6a40ef2-237b-570e-a448-eda1abfa6f3b | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Drainage Bedding Material
a54cc0ee-11be-51a7-8435-fad9afa0dffb | note | Reference - VR Section 701.09
42926976-e375-5e1b-8bd1-c008e6494045 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
19403b49-59ed-56eb-af78-79bc58c5633f | textbox | Enter: Teambinder Material Approval number
09ae3c2d-3135-5a0b-837f-985263614209 | note | Method - Document Review
9f5690fe-56f7-5785-a33f-c3eee114bbd1 | note | Frequency - Each lot
e92f6911-d171-5b46-bcc7-aaf6aefa212c | note | Category - HP
aad5bd5a-85aa-5672-b297-106851194110 | note | Responsible person - Nominated Authority
8ba688c2-f867-53bc-9477-9dd7d213b224 | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Drainage Backfill Material
a6ea9783-3a9d-5af8-bbf3-72cc0a6deec3 | note | Reference - VR Section 701.09, VR Section 701.19
60fb09a7-24f4-5171-a950-da79861302c7 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
36707ec3-bc28-551a-bd67-eca140c5fc7b | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
57f4e67d-e3e7-53b4-bdcd-10ad37cae90a | textbox | Enter: Teambinder Material Approval number
b1350551-c72a-590e-b6f8-00f9153c5c9c | note | Method - Document Review
f3d9b4ba-c10c-551b-a940-96b561a3f375 | note | Frequency - Each lot
260805b1-7965-57cd-ad0a-5c1258755f8f | note | Category - HP
ecfb820f-58ea-5c24-8eef-82290673155c | note | Responsible person - Nominated Authority
315ff527-3c40-52b8-84ea-e07668ed62ae | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documents
| checkpoint | 3.1 - Subcontractor ITP (where required)
b346fefd-3197-5a15-b26c-a97b51205f5b | note | Reference - Subcontractor ITP
2ee65426-7ce7-5160-8388-cbb2da243536 | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
66607613-f10a-5938-ab63-a991a0309555 | note | • Attach: Approved Subcontractor ITP
49cc36c3-8d83-5b0e-9a87-cb6ded23d1a1 | note | Method - Document Review
fb069165-6154-54c5-a167-1eeb304fb8ed | note | Frequency - Each Lot
52267484-5a92-58d4-ab18-8c2f7ed600db | note | Category - HP
965b0c6a-89fc-5977-adf4-30949f6e87a1 | note | Responsible person - Nominated Authority
5c551a93-1fab-5d22-92db-42770603e4d5 | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set Out - Pits & Pipes
f61cd40a-bdbe-5d7c-9e0a-f56fa589abf4 | note | Reference - IFC Drawings VR Section 701.10
f94fabb0-6d3d-5610-b5ea-650d5251aa7c | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
8e08840d-0a9a-5fdc-b49b-9563dccf3e3e | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
0656b119-b153-52c2-9b8d-61a0b61b21c4 | note | Method - Survey
71bf9684-02f8-5b3c-906c-3d14d4969c08 | note | Frequency - Each Lot
00b1750f-2f31-5f0b-9cd0-1164909833a8 | note | Category - HP*
c750e803-594f-5cf2-9b01-b021666573e8 | note | Responsible person - PE
65cec57b-2b6a-50ff-b308-756d9074a31f | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
6843d0dc-7083-5f73-8d3e-f151e7e62b26 | note | • CHK-002-CIV-Stormwater Drainage Pits Installation
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Pits - Excavation
d9fb2314-20f2-5689-a4c9-f6485ecdd73c | note | Reference - IFC Drawings VR Section 705.05
94b1f337-96f6-5d84-b99c-5125e02105ea | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
1e5bca5b-d1ef-58d5-84b4-598124beb473 | note | Method - Visual inspection, Measure
3c04a529-bbb0-58fb-a985-aaf5fec2ff89 | note | Frequency - Each Lot
e51d549d-7f68-5070-ab55-b68eddb3fcd8 | note | Category - IP
1b0863bb-666d-5f22-bd09-b59a2531d2e0 | note | Responsible person - SE
7c74fd68-1741-54fb-b409-c0a0d002ac64 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.2 - Pits - Placement of Bedding Material
6ee9bf49-2002-5fbe-87d6-dd9c1be7d977 | note | Reference - IFC Drawings VR Section 705.05
14f40619-e8e1-5e89-860b-849acbbb6d76 | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
f855a180-923b-5827-941a-318fa267845e | note | • > 80mm for clay foundations
f3ad8be9-b490-51b8-ab02-fe849c810de6 | note | • > 150mm for rock foundations
df8e9e65-6856-51f2-97fb-e1bd94bfbfec | note | Method - Visual inspection, Measure
23f885ee-b7bb-5b6f-be95-eedc9aefc8dd | note | Frequency - Each Lot
5acd2abe-eb02-5162-b567-da9b3bc095df | note | Category - IP
cbb1461a-82ed-5e4f-ac19-b4d2171d9da1 | note | Responsible person - SE
225a9c35-7a2b-5051-8495-8440a0dba373 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.3 - Pits - Bedding Testing
bfc5e01b-4739-573f-b816-923d7d9aeb3b | note | Reference - IFC Drawings VR Section 701.20
d8a22b2d-ea11-5923-afad-b51653bec59a | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
ee2993d5-5a3e-5ecd-b8d3-8a392a27b4d7 | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
21c866e7-1e40-5d55-b0ac-418f4fc47783 | note | Method - Compaction Test
5ae29770-8ab3-518f-90a1-2745cd1dc23e | note | Frequency - Each Lot
2fe55d11-4eb2-55af-a716-3fed30f92d9c | note | Category - IP
c22d38b7-9cff-5778-8d9c-f9cebe99e8c7 | note | Responsible person - SE
af057cfc-ec6f-53d2-9992-2a1e3b26aca5 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
ecf83090-6dbe-5963-be21-6c51c607d4ab | note | Reference - IFC Drawings VR Section 701.10
8625197f-c2cc-5904-a6bd-eaa43e0784e9 | note | Acceptance Criteria - Survey pick-up to verify:
6fb5ef44-7053-59d4-9ecc-2f7cac035abd | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
51bd31d4-61e9-5363-88c6-6bf0269d1109 | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
39eed91f-f0e0-5708-b952-b7aa9d0250da | note | Method - Visual inspection, Measure
e5b0f36e-c299-5ce2-9187-3a099ca506a9 | note | Frequency - Each Lot
0b62b24f-4051-5790-b95e-52211e106190 | note | Category - IP
90a7743b-91e7-5976-8a7c-274a7f277364 | note | Responsible person - SE
18a49315-88f7-5018-9952-16d55710db6a | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
625cb1a6-4ff5-5c28-8363-cdab3903fe7e | note | Reference - IFC Drawings
22cac150-d5cf-598c-a60a-eb11f5dbb822 | note | • VR Section 705.06
c62a181b-8057-5b08-b10f-9556ee4a3daf | note | • VR Section 610
df9b5087-1613-5833-8e12-418fe2b97e4c | note | • VR Section 611
6e62b6fd-90c2-58ec-af9f-3e5e039ddd10 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of VR Section 610 and 611.
964fbd77-6b0e-5eb1-a25c-1bd41114b90d | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
5829fe93-e143-5228-8eb2-616ecf83a1b6 | note | Method - Survey, Measure
c1095af3-60bc-5d5e-bbff-8ec9f5f17d81 | note | Frequency - Each Lot
6168af60-98df-516b-b9a1-385cf2add5bb | note | Category - IP
44ac9791-2ac0-51fa-87f7-a7b73985a09b | note | Responsible person - SE
df641de4-c3c5-55cf-8037-6b3662e3d1d0 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.6 - Pits - Jointing & Drainage Connections
b1eea6a1-fe41-57f0-b075-0a3d9558e338 | note | Reference - VR Section 705.11
b3604eae-3d9c-5eac-92ef-7631eb8d14b7 | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with VR Section 705.11.
551f82b1-a90b-5f6a-82d1-96b966322d76 | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
730c888f-c15e-5a0a-b62a-dc346cfc4204 | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
8d07d1f1-9c6f-5cb1-937a-59d758857bb0 | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
680a1612-7203-5085-812c-1e00303aa38f | note | Method - Visual inspection, Measure
8ef94bed-86c1-52d3-81ad-819cc2edc002 | note | Frequency - Each Lot
150117f8-a458-52a3-b075-d73af00352bb | note | Category - IP
80584a05-702a-5fc3-acbc-dd68dcb36434 | note | Responsible person - SE
07b5b70f-f3cf-51f4-bd7f-0c5092fed2e1 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.7 - Pits - Shaping of Floor
85d4f19e-1d7d-55f7-981a-ff8ca8a017bd | note | Reference - VR Section 705.13
d5c3a9ca-72b8-5502-83d9-b2004128de77 | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Section 705.13.
8b8277da-e178-54bf-ac2d-8a2e40d3b978 | note | Method - Visual inspection, Measure
7e2be60a-2345-5d9d-84d6-1aeeeffa3adb | note | Frequency - Each Lot
06ab661a-b9c4-5a41-80df-75fdb304660b | note | Category - IP
5ea84f62-e7b3-5336-8927-b219bf0142e3 | note | Responsible person - SE
76fb2369-7366-52e3-bcc7-aa0084a26281 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.8 - Pits - Step Irons
d1a86954-7e66-5f0d-827b-f8cbf31ff305 | note | Reference - IFC Drawings VR Section 705.12
19350d53-7c1b-58d7-adb4-a3dba078f255 | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
5fc0a94e-1cb8-590f-ba30-b0eb8d4a475a | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
e4a605f5-98b2-511b-9c91-da7a3f1fe11f | note | Method - Visual inspection, Measure
8da764ec-56de-5b0d-82b7-8e7625b00919 | note | Frequency - Each Lot
f1754124-a620-5682-938d-2ae32036a0d7 | note | Category - IP
2436f2d5-a965-5ef5-9e16-617e511b1375 | note | Responsible person - SE
3019903d-908b-5f0f-913b-22f41f3b80c6 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.9 - Pits - Fitting of Covers
733ca8bc-6d1c-5085-9c42-627dc07dac56 | note | Reference - IFC Drawings VR Section 705.17
2947ffe6-90a4-5789-aaf5-dc38cdb24c49 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
d9457adb-7435-5c3d-ac64-ce3a32ca4376 | note | • Height shall be within 10mm of the design level.
6e52d8a2-39ff-5475-88ad-b4c248065b1a | note | Method - Visual inspection, Measure
e4ff1cf7-6322-5e08-b6f7-cad58be68b02 | note | Frequency - Each Lot
1ea4532b-b7e0-53fe-bff8-7a59dc193afe | note | Category - IP
fc48d455-6845-5616-867c-52e79a321e82 | note | Responsible person - SE
b95b421d-6206-5218-aa42-782cfd26aa07 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.10 - Pits - Pit Lids
81a5466b-3566-5a49-8229-3cef73a42a4d | note | Reference - IFC Drawings
ae3bcbf9-d601-5910-a70c-1ce447ea68e1 | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
acb492cc-5885-5c2f-8ce9-0b86db4a33e5 | note | Method - Visual inspection
4d1a2c2e-381c-5cd6-b6a5-4ed42ae0b1ed | note | Frequency - Each Lot
031aeff2-57bf-568c-8900-96fd27a47b37 | note | Category - IP
d994d795-7c96-5026-b86d-a50db01dfbb0 | note | Responsible person - SE
7aea9fd3-cecb-5904-bc3c-a388f3397a09 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
d567fcef-f7ba-5f0a-b906-43164ad4ab5b | note | Reference - VR Section 705.18
c848f6bd-7913-5ea7-a2c9-e9ae5a5df2c3 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
276cc002-85cf-504d-8a33-f9bb40e52bf9 | note | Method - Visual inspection, Measure
34f64ea1-8e1a-53f6-b921-77129dd0e7ef | note | Frequency - Each Lot
e7e92a5c-aa38-590b-a916-461c8ca74933 | note | Category - IP
ef0355ae-4569-58a7-be2f-b5bf61da5c43 | note | Responsible person - SE
c100aa6f-692b-57a9-ac24-7b63bf005d2b | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
| checkpoint | 5.12 - Pipes - Trench Excavation
4804863b-00ac-57e7-8fe7-43c06ca70dba | note | Reference - IFC Drawings VR Section 701.15
c106b9d3-6811-56e2-b667-b83e53a4e76c | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
174510a6-410f-57c3-94dc-be49136c747c | note | • > 300mm, < 600mm for RCP
7b11c222-6cab-5e5a-b2bd-2f2b21c3f444 | note | • > 150mm for Flexible Pipe
582487af-ab21-5826-a997-6208bd87ab88 | note | • The base of the trench shall be compacted to refusal using mechanical plant.
09c5b94e-e486-5219-82c7-1ad5a247818d | note | Method - Visual inspection, Measure
494e8155-22c7-5fcf-b2ee-6cf6a27346f0 | note | Frequency - Each Lot
85358741-c236-56ab-a700-0acedd100568 | note | Category - IP
56c09457-eb69-5a83-ae30-b0568f3351b2 | note | Responsible person - SE
db1a6f57-880f-504c-bc4d-d69600bee306 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| checkpoint | 5.13 - Pipes - Bedding Placement
fa07745f-f8ba-527d-8ee8-bfe8951a64a0 | note | Reference - IFC Drawings VR Section 701.16
91aa7c07-9763-53b9-bb88-5f9489744938 | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
9ccbfce7-716f-56cc-aa40-cba4bde32d99 | note | • > 100mm where D<1500mm
53745984-9d27-5cd1-81e1-b2e001575d45 | note | • > 200mmwhwere D≥1500mm
f22e8efe-0809-5916-a946-25383b1ca764 | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
263686cf-ac22-55f9-90e7-c140dffb31d5 | note | Method - Visual inspection, Measure
6a7959fa-a770-5147-8255-85d158960619 | note | Frequency - Each Lot
0263112b-b064-5407-8320-6abab1af6a18 | note | Category - IP
e198b368-348b-5ba1-a798-881e1c5f4a05 | note | Responsible person - SE
6899f1dc-6a80-5237-86fa-9ed6354756be | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| checkpoint | 5.14 - Pipes - Bedding Testting
a05f90d3-b49b-57cd-93f5-5be51533c198 | note | Reference - IFC Drawings VR Section 701.20
ed695119-c1d8-5595-bcc5-59c4358cc6f5 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
7c25a1f6-461e-511d-9da5-8a37ac489d28 | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
e16b9cb1-c649-57e3-8b4d-50e07b63d7ea | note | Method - Compaction Test
7b5bcb7e-2b1e-550b-be0f-c79ff3a9cd04 | note | Frequency - Each Lot
cafb0a46-55e9-5e4e-8229-da6923a9bad7 | note | Category - IP
164dc4e2-9478-5cb0-9005-29cebc2394f6 | note | Responsible person - SE
917dba58-312b-5634-9bcc-93e34e1bc049 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
1d1c089b-4ba4-5fe1-a637-32044ce0b1a6 | note | Reference - IFC Drawings VR Section 701.17 VR Section 701.20
31f8ae21-a529-5dd6-ba06-b9d736bd4b88 | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
ff7981d8-ee51-588d-8565-751f7ba664d0 | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
12673478-c059-5ef4-88c5-94a894be392a | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
6dab23a2-8e4f-5ad3-b7d1-e52c4c3fc50d | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
ee342e3e-6de3-5105-b0af-bbd69d364f2b | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
3bf1b8e9-05fc-531c-aec3-73dd83970287 | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
71643c3e-0dbb-57ba-bd53-b1bc4e921421 | note | Method - Visual inspection, Measure
3206e281-963a-5e3f-8bd0-3e157c8043fb | note | Frequency - Each Lot
c3e79654-ff32-5a5a-8353-503957b9f146 | note | Category - IP
68ac4b92-8add-5e24-b3d6-c32e53fd7478 | note | Responsible person - SE
a5a1d846-712b-574f-bc3a-d4c3e4558102 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| checkpoint | 5.16 - Pipes - Lifting Holes
c54f8b3f-99e5-5874-865f-bb3d4e73567d | note | Reference - VR Section 701.18
df84039c-4096-5862-8eaa-0d898dd2f714 | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
20f800dc-db11-5bea-80b5-2d925c2c5c4d | note | Method - Visual inspection
dcc71987-a14e-5456-8404-5a8199902279 | note | Frequency - Each Lot
e9013fe5-ba89-5076-84ab-0bacff747269 | note | Category - IP
5b739b73-904a-594b-bce3-6737e4a40cfa | note | Responsible person - SE
6a71fca6-0521-5693-a488-ff7dfa800ea3 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| checkpoint | 5.17 - Pipes - As-built survey pick-up
10e0de15-3a18-5281-a611-ab805252c237 | note | Reference - IFC Drawings VR Section 710.10
a00cc557-b861-5815-a1c2-c90bbbc61e14 | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
730ffbbe-c389-5db9-a1ac-d7b3b45c2b73 | note | – Offset pits to kerb +/- 20mm
95c9849e-92ff-58f9-b659-ecc4043c42d9 | note | – Plan location pits not adjacent to kerb +/- 100mm
2f0911c2-f5ef-5891-afd9-d72c3c78806d | note | – Invert level of pipes at pits +/- 50mm
1e9c5060-5c7c-53cf-bcde-7018ac1f2ea1 | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
607b9978-7228-5316-8b65-9eecd062e064 | note | Method - Survey
f55aff1c-d78d-59a3-aa22-6d2544082ba9 | note | Frequency - Each Lot
61381203-699e-53e0-9d0a-81a735eb6748 | note | Category - IP
c423da6f-efe4-5b05-a37b-4ef0c9bf366c | note | Responsible person - SE
d391a1da-97af-545d-9726-7cae58da8620 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| checkpoint | 5.18 - Pipes - Backfill Placement
f2067180-da17-5ead-bb56-1494a82b9f0c | note | Reference - IFC Drawings VR Section 701.16
4d2ecb88-a5ce-5ef9-9e23-6030203e3b13 | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
9de304b4-89ba-5068-bc33-c9d9427de064 | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
16468e4a-3bb6-5517-84e7-97de819742d2 | note | Method - Visual inspection, Measure
97d3b62c-9d9d-5118-92c2-f9e3b1f1a4b6 | note | Frequency - Each Lot
9023400d-f99e-5b02-bf62-fd524ac717c7 | note | Category - IP
e1448e5c-c9b7-5974-8f5a-05da8666ec0b | note | Responsible person - SE
2fcc708b-5b9d-573f-8cfd-6cc125ce08d7 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| checkpoint | 5.19 - Pipes - Backfill Testing
0a8eb066-6033-5199-a3d1-48e71dc22fcd | note | Reference - IFC Drawings VR Section 701.20, VR Section 701.29
589501c9-9e60-52a7-a70a-57a671e3c82b | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
8181a654-cb8c-544f-aabe-c6bab7cb7f34 | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
9fec84df-9591-5e81-b0d4-407c0138187f | note | Method - Visual inspection
e2b8ba20-d6c0-54e7-ba33-cc947160b366 | note | Frequency - Each Lot
6c424115-fb61-52af-ad04-40f81538f51b | note | Category - HP*
86765749-4929-5286-bc9d-bc4a23a21e00 | note | Responsible person - PE
d96d94c1-4353-54cf-97e1-c31337ea5240 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Flushing & CCTV
248d4bd0-9dd6-5f8f-816e-9c32f9f6460f | note | Reference - VR Section 701.28, VR Section 701.30
49e60912-8e59-5bc6-a131-14272eb57f54 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
c0469bd1-d49a-58f8-b28a-71175062e784 | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
e55b88a5-9ffc-5b31-94c4-dfe2b6b6ea76 | note | • Attach: Flushing Record, CCTV Reports
bff42331-e081-5415-aeae-01f288e879dc | note | Method - Record Review
0d110ece-336f-514d-991c-9b78aa023465 | note | Frequency - Each lot
5dfbcd92-4a34-52a6-b1af-9b11d1139e0d | note | Category - HP
354020e4-5b2d-57f4-b46f-f99c0938b03e | note | Responsible person - Nominated Authority
3e4d23c7-9fa6-56f9-b632-5d16f0e6a2c0 | note | Verifying Documents - ConQA HP Release
f9db3d03-989d-56b2-9d6b-677fc6220e65 | note | • Flushing Record
50ba27d4-5124-5812-a2ce-0265b1e0761b | note | • CCTV Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - As Built Survey
0e225f8a-4ef6-5b3c-a74c-322d40820977 | note | Reference - VR Section 701.10
fc0e9cf3-266d-50a0-ade0-c95563df34d6 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
209f19c0-ee24-5859-b80b-adbfee796373 | note | • Attach: As-Built Survey Conformance
75f73bb5-0e58-5446-825f-a2946e1ca5d6 | note | Method - Document Review
c77a35a2-8493-562d-a960-8503194ba1d3 | note | Frequency - Each lot
f18135c7-91f6-5523-ab87-fd3c7651319f | note | Category - IP
618a92bb-ee18-5112-80cc-482a4304bdd8 | note | Responsible person - SE
edcbd096-f65c-5cea-baea-05994866f11a | note | Verifying Documents - ConQA HP Release
c9e8315b-2e96-548e-b8f9-3a276174b582 | note | • As Built Survey Report
| checkpoint | 6.3 - Repairs to Damaged Pipes
7b9a097b-d2e6-5651-a8a6-4825f629a84e | note | Reference - VR Section 701.31
52e7a1d5-3c8c-53f2-81a1-250a718d99fe | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
1cbe2fd4-c1a9-5812-8219-f16d3eabe1e6 | note | • cracks wider than 0.5 mm
4a6567c7-4e4c-58e5-8282-55587e45b3ab | note | • spalling of concrete
568d0f15-c5ca-5678-be0c-92009775c7e1 | note | • exposed reinforcement
87e60f9d-55e5-54d0-b75a-76bd2c77c106 | note | • joints that are not fully engaged.
0b89da14-d72b-576d-b8f5-aee4ea5b8e1e | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
5cc0d524-e108-504c-a67f-6a833083e071 | note | • longitudinal cracks greater than 2 mm
98f3b334-54d3-5097-aa32-ba32b792dd22 | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked VR Sections exceeding 3 mm
c7fb7299-da9f-5b61-8154-de7dcb582243 | note | • circumferential cracks around part of the circumference with width greater than 4 mm
526daa26-1851-5cee-acb1-bcd51b90a2ee | note | • penetrations with area greater than 400 mm2
a51b71df-0404-5d0d-ba5f-269b09982004 | note | • pipe joints that are separated.
d6bdc9be-ac4c-5ada-aa23-acc008232089 | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
7c53dd06-e94e-5a07-b15a-f343009ef3aa | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
858f1709-aaf9-540a-9bd9-24ecd4654e7d | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
18e58c5a-ce4f-51e8-b3c6-48200f08a905 | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of VR Section 689.
55251157-71eb-5585-8557-0caba6752234 | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
0b99f227-4315-52df-97be-80ff87486999 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
5db42065-5a1d-5d9f-b0b2-76e6375714cf | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
5f1da88a-6a83-51b0-b80d-bdecbd9663ae | note | Method - Document Review for Repair Procedure
687a776a-b8a3-5e91-a7c0-561a16fdf7f1 | note | • CCTV Report Review
dff0e0f9-2755-57a9-ac35-8d5092c177f9 | note | • Visual Inspection
a662cd0e-d0cb-58a0-9413-cdc0ea99a8c4 | note | Frequency - Each lot
d24c08d0-3c27-5ad5-8da8-252743eb3a84 | note | Category - HP
fdd8f4a7-a546-5bbd-b9df-e5d5eea679dd | note | Responsible person - Nominated Authority
61b5d7bc-7ef6-5967-a6e8-59c9d20ab2a2 | note | Verifying Documents - ConQA HP Release
31c199fa-08ea-511e-9328-be3608cd1932 | note | • Approved Repair Procedure
fadb8d15-7fe8-5467-8bc8-a33dfe72ed57 | note | • Post Repair CCTV Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
dc063b04-b3e9-5a28-9640-bec24a7e6529 | note | Reference - MRPA Quality Management Plan
9396f3af-5ce2-56e8-9c27-ee6bc329da33 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
08648456-0933-5f10-9b27-2566ca57db7e | note | Method - Document Review
bc90dfc8-0c0e-5b81-8564-55f5cdbe4206 | note | Frequency - Once, prior to closure of this lot / element / Work area
0728496b-4af2-545f-bb6b-f7aa63ab06d1 | note | Category - HP*
8c75e4e4-0eaa-510c-9054-a1148d4c8ff7 | note | Responsible person - PE
65c06473-3595-583a-b041-78df49fe645f | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
0773d1c4-5b33-5bb5-90cf-370e4375ed58 | note | • CHK-002-CIV-Stormwater Drainage Pits Installation
| checkpoint | Final Inspection
40b5a903-4867-59a3-9557-7a032c934f8d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
dcaa0d72-6d0c-542e-9f51-c05689dcc9ec | textbox | Name:
7a468cba-5efe-5f9f-84bf-3a7a4330d0bc | textbox | Position:
142ff31b-27f7-50c7-abd2-f6dcaf34b1fa | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill | itp | ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill | 645f5382-e631-40dd-a051-649d8117a831
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
cbca5e68-26a0-5bcc-bd3a-9420206c9685 | note | Document Title: ITP-042-CIV-Brunt-Subgrade Prep for Embankment Fill
fc27eee5-f968-565e-aa6e-c0e2921d6f29 | note | ITP Description: Subgrade Prep for Embankment Fill
92aff006-fa3e-595c-8120-b0c1e3a9b99d | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
49505fee-8465-55e6-a816-b6fe02259a2c | note | Discipline (e.g. CIV/STR/RAIL): CIV
2932d344-427d-562d-8a78-d6155ee38e0b | note | Revision Number: 0
be7d4b48-3b2f-51d2-a54e-9eea9f52e31d | note | Revision Date: 13/06/2023
d747fd8a-3766-59c8-b14e-f238fc209cea | note | ITP created by: Jason Lee
ab1d22be-9138-5b2b-befc-198d4c6651c4 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
d7332321-2909-5a96-aee1-3c88ba6ba497 | note | Reference - VicRoads Section 204 (Dec 2015)
| checkpoint | 1.2 - Non Dependent
ab02c8a2-d7f2-5b7a-9c6a-00035ded8bf0 | note | Reference - VicRoads Section 173 (Oct 2008)
| checkpoint | 1.3 - Non Dependent
7f03e866-912e-5a63-ab2d-d4d8bca0fee9 | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Non Dependent
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Non Dependent
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Survey Set-Out
36d14348-bb2e-58e1-be6e-c9ba1e3adf26 | note | Reference - IFC Drawings
9735eae6-832b-56f4-9e10-9996af05c9de | note | Acceptance Criteria - The Area of Excavation has been set out in accordance with the drawings.
73fcc080-7916-52b6-9b42-20be3291d420 | note | • Attach: IFC Drawings with lots marked-up (Lot Maps)
e38ffbdb-e45e-5ee0-8528-a139326c129e | note | Method - Verify
5944d1f7-6321-583b-82d5-092f09c8cc62 | note | Frequency - Prior to Commencement of Excavation
2ae712dc-2d7a-5833-986d-15a4921182ba | note | Category - IP
9a9d88d7-60f3-53a7-910d-e3b49ce5be91 | note | Responsible person - PE/SE/Surveyor
67bd86d6-22f9-5507-b6d2-a3d6af371040 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Excavation to Subgrade
86b41c70-da2a-5f3f-af63-1e163b91cb0c | note | Reference - Section 204.06, Section 204.07 (b)
eb5655e8-e24b-5e97-a190-31edb3d970f3 | note | Acceptance Criteria - In situ material within 400mm of cut floor level to be consistent with IFC Drawings. Assigned CBR not less than Type A material and shall have swell less than 2.5%. If parameters are met, rip and re-compact to a depth of 150mm.
65e66d00-c8a3-5736-b5bc-3fddd331eb9f | note | • If the material have an assigned CBR less than Type A material, it shall be removed to a depth of 400 mm below Cut Floor Level and replaced with conforming Type A Material.
1b9cb9e2-fa90-53ea-b1c4-87cb2fbccc74 | note | • Attach: Laboratory Test Results
bfd2a48f-b0bb-5b5f-b775-e1f4234a1049 | note | Method - Verify - Document Review
122d6b03-32e4-575b-a7a3-25b3630b039c | note | Frequency - Each Lot
dcd20aef-e90a-56c7-aa50-3fdfb762a8ec | note | Category - HP
87d097d6-104c-5bee-91ad-d3182bec6a77 | note | Responsible person - Nominated Authority
2c78d574-f6e1-5525-b218-817e7ef890d4 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Acceptance of Rock Subgrade (where applicable)
4590097a-357c-5160-b7f6-1ec0b910f486 | note | Reference - Section 204.06 (f)
3b358771-7429-5e42-9fd3-0686c7edac51 | note | Acceptance Criteria - Material shall be excavated to a depth of not less than 150mm below subgrade level in all areas on which pavement is to be placed and all loose material and soil shall be removed from the rock floor.
d60ff72a-3036-5b84-996f-f6c903b9c42e | note | • If any depressions lower than 150mm below subgrade is visible, it shall be cleaned of loose material and backfilled with 20mm Class 3, 3% Cement Treated Crushed Rock and compacted.
7049e7f3-446d-5dee-84dc-d9f8471e2db3 | note | • A regulating Layer of Class 4, 20mm Crushed Rock shall then be placed above the rock to subgrade level in lieu of specified capping or selected material, in layers not exceeding thickness of 150mm.
414ea3d9-21c3-5103-bf7c-8d66e0d9114d | note | • Attach: Delivery Dockets for verifications.
ebd39062-1aeb-5fb6-950b-114497db5c7c | note | Method - Site Inspection/Document Review
4137f220-31d7-51b6-a345-ca6fc12efc4e | note | Frequency - Prior Construction of the regulating layer
80d95dc4-75d4-517c-b409-32384a026edf | note | Category - HP
105e8d8c-5b1c-5e9f-ae2f-219ec164b4be | note | Responsible person - Nominated Authority
4de7174e-f002-5356-8ab7-ffe24b03631d | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Groundwater (where applicable)
0a09bf71-99d7-5f1f-b10c-2949435edb74 | note | Reference - Section 204.06 (h)
5c43b626-37f6-58ed-8edf-7b192e3239fd | note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
65f552d1-c860-5dfc-99b2-9b105514d241 | note | • The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
f9ef45a9-d5f9-57a6-a19f-409a1b22e7e6 | note | • Attach: TeamBinder Approval Reference No.
6d77f956-4553-514d-865f-278002e61c35 | note | Method - Visual Inspection
a5698a0e-b54d-5db0-a89c-8ea2d870e6d3 | note | Frequency - Each Lot
77946c52-881e-5455-9f78-a037db14732f | note | Category - HP
bfa4c83b-1e2c-5004-b30f-5a82197448a9 | note | Responsible person - Nominated Authority
1237bcfe-76fc-5f37-9e3d-805647c35424 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Geotech Inspection
e135646e-4e73-5a3c-a4ff-9957309987f7 | note | Reference - IFC Drawings
d5cc26a0-ab6a-5b31-b947-656b23342a25 | note | Acceptance Criteria - Excavation is required until natural clay is exposed wiIh a minimum shear strength of 75 kPa, to be inspected by CMW prior to fill placement.
63ef6f08-7605-52dc-898b-037069f9b82d | note | Method - Visual Inspection
dc0d3740-1fc8-50c4-8388-57aa8c343313 | note | Frequency - Each lot
bb109c6c-bbd4-57a3-b605-aeb5c45ebad6 | note | Category - IP
61cee6c1-9412-5ccb-b792-38ac374df94b | note | Responsible person - SE/PE/SPE
7c4019c3-f649-5421-bb05-9c4a4a62da99 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Proof Roll
a15a20ad-df6f-5ce8-891d-b9d7e0b50093 | note | Reference - Section 173
2b9196e5-95b0-5374-abbe-d40ae5625350 | note | Acceptance Criteria - Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing.
94166d20-8c8d-5a12-a4ad-1fd51aa12b10 | note | • The plant for use in proof roll to comply with the following requirements:
b4657f61-b6a3-528f-b7e5-c83fef6169d7 | note | (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel.
b7e27d37-d21c-58ad-b41b-93b53f068f2e | note | (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre.
9ec47b98-f4b3-50b4-8aa7-31e1a013c563 | note | Method - Visual Inspection, Test Roll as per 173.03
0d0ac7ed-5019-54ec-bf0f-88b420b70173 | note | Frequency - Each Lot/Layer
3ed57775-5d33-5a97-9c21-574a4c64c8ea | note | Category - HP
ca7c941d-4d20-58a7-ade9-5c9319eba8a6 | note | Responsible person - Nominated Authority
8f35eb8c-7fba-5827-8b1a-0a1743d6dedc | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Compaction & Moisture Content Testing
6c776a5c-456b-5669-888b-02b130ca21fa | note | Reference - Table 204.131, Table 204.142
5c4c2a2d-e759-566b-b005-b9a514d0c4b5 | note | Acceptance Criteria - Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot)
d02fc6ee-2a63-5ba2-a231-9dbadcb188c5 | note | Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement.
87bdfae0-9997-5666-b1b2-36ca681d65f9 | note | • Minimum Testing Frequency: Every second lot
f6765e42-f717-58c0-834d-cb77bca8f918 | note | ○ Lot size
24ac778d-eb52-5390-98c3-b62068915579 | note | • Type A Material - the lesser of one day's production or 5000sqm
2bd24dc1-f5d2-5f16-b97d-9fc5c4808149 | note | • Attach: Compaction & Moisture Content Test Results
1b789f6c-6747-5422-99bf-1bd221277c14 | note | Method - Review Document
9dc7b191-2858-5f71-a5bf-3a0121c0ade1 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
3531bfbc-b1d3-5f36-99fb-6498216dcc90 | note | Category - IP
2b6eba39-ee80-5cda-94e8-3cc9df044868 | note | Responsible person - SE/PE/SPE
ff8e4299-3949-5dd4-8697-bf70bab9f4f0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Post Compaction Material Property Testing - Type A Replacement Fill (where applicable)
b2cc095b-4f88-58b0-b66b-9d2e941102eb | note | Reference - Table 204.131 IFC Drawings
a53db9bf-6d18-5e71-9f58-3584847231f7 | note | Acceptance Criteria - Material Properties:
f8a27e38-18e5-5812-a3f8-6043374e93c5 | note | • CBR ≥ 8% and Swell ≤ 1.5% (Applicable for Type A Replacement Material)
1154be21-15fe-5f44-8cd5-4b91a57145a5 | note | • Max Permeability = 5E-9 m/s
f4156624-575c-5036-b157-f868d51bd0b2 | note | ○ Grading:
498c7e54-9f94-5784-9a14-0706f865a6cb | note | • 75.0mm 100%
bc284619-f024-5441-b064-bc37204b9004 | note | • 4.75mm 40-80%
d77a5646-d763-5662-b913-81080cc44913 | note | • 0.075mm 10-40%
fb5ba827-48dc-52e1-9c0c-6ff2e90d6133 | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6-25
f24ce557-992f-51c4-a844-30e489cd6d5e | note | ○ Scale B:
d4283035-e5fd-5400-be2f-491459a31e9e | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
88022160-5f18-5b8d-bb58-969b91b5ca59 | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
e47eab14-04b4-5a33-b754-da5cc55d1596 | note | • Attach: Post Compaction Material Property Test Results
4aeb74ef-9d0d-5734-a77a-ad40846cd065 | note | Method - Review Document
2c2d481e-22d0-5043-b98d-448326fb7d45 | note | Frequency - Each Lot/Reduced Testing Frequency Refer to Section 204
c79ada57-19bd-5083-8259-3c2d0339c646 | note | Category - IP
007c638b-ebf8-5cdb-80de-3ba158139b2e | note | Responsible person - SE/PE/SPE
26ddd561-ddf4-503b-8bdd-b94dc84c397b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Post Compaction Material Property Testing - Natural Ground (where applicable)
a29d00d4-0e08-52ab-a686-e7b4c40dc10e | note | Reference - IFC Drawing Table 204.141
3ec83c75-6514-58bf-b094-da8d427394f0 | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
735c80c7-5e96-5e23-a168-4aeaf29cd77a | note | • CBR ≥ 2% (Applicable for Natural Ground)
e44c001f-bc37-5be5-a111-99eed0e296b2 | note | • Max Permeability = N/A
810e7f5d-f3a5-5886-9e7e-468ce97de831 | note | ○ Scale B:
47cae777-94d9-5209-afc4-aa2b4f585315 | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
43fda0b5-29b4-544b-8f07-d09c08d25286 | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
24d914fc-13e1-5048-86e0-16bea593154a | note | • Attach: Post Compaction Material Property Test Results
7d11a6ee-b1cf-5667-9ba4-ba731d9b8ef1 | note | Method - Review Document
aa8a6305-70c2-56e7-85f1-76cd971f40ce | note | Frequency - Each Lot
8765fe0f-736b-5cbb-952a-f98e84d49065 | note | Category - IP
6511b0d5-96d5-5d1a-b482-66cd07a8ad5d | note | Responsible person - SE/PE/SPE
8e075b2a-9ad5-57db-ad19-2209131d767f | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Survey Conformance
e0441fc9-6db8-5a97-a6d0-c0c3e22e884a | note | Reference - Table 204.031
13201703-6e42-543e-9c97-44ac114f5d8d | note | Acceptance Criteria - Level tolerances (Scale B):
35f54862-bcb6-538e-9a50-44c3e0fbc7b3 | note | • Range Mean = +5, -25mm
d7c0e9c9-9d51-5a2b-b5c7-92e6f053b04c | note | • Max Standard Deviation = 15 mm
d93e42ac-5d5b-5c94-8907-f2a36d81a2b5 | note | • 40 measurements per lot
94d0a78c-6a9b-5dca-ab7c-2bc6faf4ae8d | note | • Attach: Survey Conformance Report
c5cc6c94-e1f8-5cf9-a6aa-ed81e122103b | note | Method - Review Document
c7d5bef4-ae8a-5715-b3cf-0cc1a59245b4 | note | Frequency - Top of Type A
17d46b21-fe88-5836-960f-f6e4607543b8 | note | Category - IP
d94bb15b-b82b-5ad6-bdd8-6def3abf2d17 | note | Responsible person - SE/PE/Surveyor
37d0c8bf-2b68-5782-9180-b7d57f2dc01f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.1 - Non-conformance Report (NCR) Closure
e460289f-528e-5c50-9b9d-4886551cad72 | note | Reference - MRPA Quality Management Plan
5d32c9e7-b991-54e6-abf6-c14b020bff67 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f381bc78-3c95-5fa0-b31c-5d6deb21a499 | note | Method - Document Review
e6097d75-9321-52f7-8025-a77e18872954 | note | Frequency - Once, prior to closure of this lot / element / Work area
95eee745-9ceb-550d-a016-81a447707eff | note | Category - HP*
10261399-53c5-567d-bc5a-a0d89fd2f80b | note | Responsible person - SE/PE/SPE
855b7ed6-e81b-5c5a-9608-2dca3f6f861b | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
fa36a3b4-0307-557f-bb91-ff0c4db2053e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
321fe253-7058-59a6-a7c0-d8001395b0b0 | textbox | Name:
470f1429-7595-5eba-8014-46a433950cc5 | textbox | Position:
7e409433-1a9e-538f-9a71-56ac3b2b452f | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-043-CIV-Brunt-Type A Embankment Fill | itp | ITP-043-CIV-Brunt-Type A Embankment Fill | d587068f-6e9c-462b-9791-e947cd646e96
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
9aa55048-26ab-546d-8619-9c6b8b68c2ef | note | Document Title: ITP-043-CIV-Brunt-Type A Embankment Fill
43e9ff87-10b3-5968-8758-3f44b01697aa | note | ITP Description: Type A Embankment Fill
36ece767-8d0e-5d2f-9f0b-3a6c52bbd015 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
4e32b7b3-ed6e-50e3-8867-e38abaa08646 | note | Discipline (e.g. CIV/STR/RAIL): CIV
accb5953-fb53-5d3e-b951-23c6c706e729 | note | Revision Number: 0
c3ea72d0-6b1c-53e1-b4cb-79c619e43c6a | note | Revision Date: 7/07/2023
686a49f8-1755-59f8-b82e-7418da17616c | note | ITP created by: Jason Lee
5efad249-b68f-57a8-8a51-23dcaef254f2 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
f919786e-93bf-5516-8851-ce7244ae514d | note | Reference - IFC Drawings
| checkpoint | 1.2 - Non Dependent
bf02a6c9-7303-5f4a-af97-43f658689ea2 | note | Reference - VicRoads Section 173 (Oct 2008)
| checkpoint | 1.3 - Non Dependent
efebf337-a13e-5ab6-a59b-58c0ff2d56c2 | note | Reference - VicRoads Section 204 (Dec 2015)
| checkpoint | 1.4 - Non Dependent
5bed3cdd-8674-55e7-8022-d12b46dde596 | note | Reference - Code of Practice RC500.20, RC500.5
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
88dcac63-f324-5d72-89f0-4c885ffa1349 | note | Reference - IFC Drawings (MRP-089-C-ACD-DRG-30-BFD-CBR-2848) Section 204.04 b) Table 204.041
f29d7ee4-40ae-59dd-bffc-1d4f2571d985 | note | Acceptance Criteria - CBR ≥ 8% and Swell ≤ 1.5%
fd7cf5d4-f274-582c-9dd1-2fe63f0efc7d | note | • Max Permeability = 5E-9 m/s
539a90ea-350e-5d24-8461-3f7d3d621138 | note | ○ Grading:
51e5f53f-b89f-51bd-b27d-e174f6c8a090 | note | • 75.0mm 100%
6d005c35-b4f1-5d68-b3da-f4ff10eed3de | note | • 4.75mm 40-80%
0808cdae-106c-5a38-be64-e6fd11eae3e8 | note | • 0.075mm 10-40%
adc5867e-2664-5496-bb56-db870f027e6c | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
e19f6309-5a79-59ac-82b2-392ebda9a293 | textbox | Reference: TeamBinder Material Approval Ref No.
127f3655-6c52-5133-a0b9-eb24cad6e49e | note | Method - Document Review
1ad04910-d814-5aba-88b9-fdae40f8b1b8 | note | Frequency - Once, for each material type
0c7b95be-68e8-54ec-8f11-4ba166aa5b5f | note | Category - HP
8d487b84-da11-5640-8e7c-af99593bdb57 | note | Responsible person - Nominated Authority
70800ead-253f-5036-9c11-a88932fa6ce3 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - Pre-Commencement of Fill Works
1adfa66b-5a70-5d37-bc87-c6522b746beb | note | Reference - Section 204.10 (b)
399a9acf-09aa-5f68-9519-a33427e7cf9d | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
c71f6ec2-93ce-54f8-b491-b4360a1cdd4d | note | • The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
56399c4e-e92d-5a33-872e-3171443c3b0d | note | • No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
d716d2de-85c5-5c95-8366-67cd3ab71342 | textbox | Reference: Subgrade Preparation / Previous Layer Lot Number
b3d074ad-98d4-5db8-9b1e-f70e7446980a | note | • Attach: Lot Maps
09f8555d-fb66-5ae8-adfd-ec04e62ee90b | note | Method - Visual Inspection
20121d86-6888-5ba8-ae7b-da8982af3d08 | note | Frequency - Prior to commencement of fill works
21f67fb4-b66e-51a3-84d8-c9dcd11ad107 | note | Category - HP
ca6d9d19-5a9b-57da-8052-4726a0af1773 | note | Responsible person - Nominated Authority
82dfc764-14d2-51fe-87e8-9d0013c59182 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
ba167167-4b3f-5f95-8d61-30b8b1e9bc6b | note | Reference - IFC Drawings
1e0b8012-2fbd-50b8-a95a-b25381982cdd | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
59998471-80e6-5ebc-8493-148a91add776 | note | • Attach: Lot Maps
0f9c6ae5-179d-5d0f-ac92-bf04a5414bc3 | note | Method - Visual Inspection
c00200fe-9434-5fab-83cf-c3f4e6bcc876 | note | Frequency - Prior to commencement of fill works
39e5933c-edea-51b9-a725-5582fbb7d5e8 | note | Category - HP*
333eaab0-2035-5161-90d5-b94654ac5aa2 | note | Responsible person - SE/PE/SPE
cc277183-d770-5beb-95aa-f0258c80d242 | note | Verifying Documents - This ITP Signed Off
| section | 5. Type A Fill Activities
| checkpoint | 5.1 - Placing of Fill
c7573a08-a2c8-5efa-ba32-0e147da60507 | note | Reference - Section 204.10 (d)
ec0ce410-0432-5c3c-a8f6-ba9aec8537d0 | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
99ea1d7a-da0f-55e9-bc88-3ca692fae5f1 | note | Method - Visual Inspection
981392ed-e0ea-5333-b1af-44b5fea98e9b | note | Frequency - Each Lot
2788e3f1-bb23-5f0a-9337-7a3298f393f0 | note | Category - WP
59ee80dd-2532-53f6-9e7a-05d4171092f8 | note | Responsible person - PE/SE/Site Supervisor
8708c1c5-4f45-5abe-9dfd-c778c595f221 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Fill at Structures (where applicable)
e5b20d1e-1f9a-56e0-b24c-9af1625bdd7d | note | Reference - Section 204.11 (b)
90993620-1182-5f1c-8341-71f717fbc8e9 | note | Acceptance Criteria - No Fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent
05017d59-32d0-5487-bc00-2bd87be08af9 | note | • In addition to the placement of Type A material at bridge abutments as structural material, embankment material or backfilling within 3 metres of retaining walls, wing walls, all crown units, and culverts with an opening height greater than 1200 mm, shall be material of at least Type A material quality.
ea443de8-79b4-5c88-aca7-7d59718ba12e | note | Method - Site Inspection
f2f837a3-7161-575a-85d6-cbe9ee7ea842 | note | Frequency - Each Lot
8434919f-2b7c-5cc8-bc2e-343844026317 | note | Category - HP*
d97c73c7-3cd2-5ced-89ea-60671b1fc677 | note | Responsible person - PE/SE/Site Supervisor
044bd8a6-be71-5c8f-a72e-dc2e2f1819e3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Test Roll / Proof Roll
ee28546c-5542-57d7-98be-459401076ec2 | note | Reference - Section 173.03, Section 204.12
fbf75c18-9ca2-588a-8fbf-a6eb62cbf33f | note | Acceptance Criteria - Each Layer shall be proof rolled with a superintendent present. Compliance with the proof rolling requirements shall be when an area withstands proof rolling without visible deformation or springing.
ee9750c1-bf05-50cf-b195-47fa1a745b1c | note | • The plant for use in proof roll to comply with the following requirements:
c62d8753-2237-5e86-8459-eb2d42b61634 | note | (i) Static smooth steel wheeled rollers shall have a mass of not less than 12 tonnes and a load intensity under either the front or rear wheels of not less than 6 tonnes per metre width of wheel.
356bc8ae-7e18-5b5a-9755-eb5409712b64 | note | (ii) Pneumatic tyred plant shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre. The area over which this ground contact pressure shall be applied shall not be less than 0.035 m2 per tyre.
c6201fc9-083d-5f3a-8a9c-12293e57f63a | note | Method - Visual Inspection, Test Roll as per 173.03
6b1b573e-e910-58a6-a8f7-ac8ad52c3804 | note | Frequency - Each Lot/Layer
5a0755d2-63e5-563f-bb7b-85027b1bb7da | note | Category - HP
c1475976-afd3-5275-a9d2-cb2494b08e50 | note | Responsible person - Nominated Authority
7dcd1ded-1ebd-5e74-8418-db5274a3a1f1 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Compaction and Moisture Content Testing
7b039dd0-e48c-552c-a84b-40cb7028debb | note | Reference - Table 204.131, Table 204.142
aed782ec-1978-5c57-b6e4-4f197f7c5fa2 | note | Acceptance Criteria - Compaction Requirement to be Scale B: Characteristic Density Ratio 98%. (6 tests per lot)
69015c4d-4967-5e3f-910d-132ef9026a5f | note | • Once three consecutive lots of like material have achieved the requirements in the first test, minimum testing frequency can be seek with the Superintendent agreement.
50d223fe-7a52-55c9-946b-1609df420add | note | • Minimum Testing Frequency: Every second lot
dbd6bbbc-9def-509d-a575-7229c6ddf909 | note | ○ Lot size
6452aaee-75a9-5601-bc79-398f9341eece | note | • Type A Material - the lesser of one day's production or 5000sqm
2be5dab4-f391-5348-b1d9-2f4ab3e8ced8 | note | • Attach: Compaction & Moisture Content Test Results
d4efd88d-242e-5696-a8a5-ae4381fc5c12 | note | Method - Review Document
0ecd2bbe-fd9b-5513-86c4-39c8695ba4de | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
f1227353-e17d-5ff2-afd4-29e6fce510a7 | note | Category - IP
91d1ea23-179f-5cde-be2d-73af1e551511 | note | Responsible person - SE/PE/SPE
7cf22cd9-4913-50fb-abeb-d8aca7a9639c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Post Compaction Material Property Testing
9a300b30-d43f-5178-8cc2-915f36084656 | note | Reference - Table 204,041, Table 204.141 Section 204.14 (a)
9f1f5a16-9c4c-59c1-9dce-75ac044cd7bb | note | Acceptance Criteria - Material Properties:
99a410e9-6277-5e7e-994e-4d21782b2a43 | note | • CBR ≥ 8% and Swell ≤ 1.5%
92a48768-784e-569d-a689-ca25b408e1ff | note | • Max Permeability = 5E-9 m/s
170e728d-3ba3-5ec8-84d5-78992bd26163 | note | ○ Grading:
2a51e371-c1b7-5121-a75c-62a6dad0271f | note | • 75.0mm 100%
37fe420a-4cc6-52e4-b256-cbd783363bdc | note | • 4.75mm 40-80%
b14542cc-c88d-52a7-a206-862d49f0fc03 | note | • 0.075mm 10-40%
1ad4538a-a274-5835-9b92-d6919c780922 | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
9b09d95b-886f-5590-a108-1c4a03c90811 | note | ○ Scale B:
e4af1178-2ab6-5b80-9e81-a4ed03214621 | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
7bc49269-67e7-5969-a52f-4c7d2f3416a2 | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
08d74956-ef93-5727-9d5c-5c073a3049d7 | note | • Attach: Post Compaction Material Property Test Results
3050d655-0921-5e13-ad32-edfcdb78f0cd | note | Method - Review Document
1a0ffd8e-aa96-5d25-af13-66a63adc21de | note | Frequency - Each Lot/Reduced Testing Frequency, Refer to Section 204
bf12c3ff-4ed2-5614-9425-0c5b52c7b6f5 | note | Category - IP
660570cf-8a99-562b-9a68-9dbbb0417b29 | note | Responsible person - SE/PE/SPE
2225651d-d6d1-5070-be06-97b5a09642f3 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Survey Conformance
1d850ac2-524f-5588-981b-347680562794 | note | Reference - Table 204.031
f235a8ae-cefd-5308-95aa-5fef5f140a60 | note | Acceptance Criteria - Level tolerances (Scale B):
b807d4e0-cab2-5d60-a189-9c58eccf854c | note | • Range Mean = +5, -25mm
31953c40-5abd-56b2-9d19-6dfe69574d4c | note | • Max Standard Deviation = 15 mm
59a66fb4-cdc7-522d-9911-61e0015389ce | note | • 40 measurements per lot
d1c866e8-f826-5ce2-81a8-2ff45739d6f4 | note | • Attach: Survey Conformance Report
581200a9-b430-5ba0-ab95-4e6083a79f11 | note | Method - Review Document
98489305-b5a0-50d3-a23e-fae7cba6c4e0 | note | Frequency - Top of Type A
0e1586a3-e675-5067-8888-a4433af6429f | note | Category - IP
ef51a104-4441-5f5a-b1cb-41b367f0c708 | note | Responsible person - SE/PE/Surveyor
83daa6d4-bf06-5add-99e2-eb198622a2ae | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.1 - Non-conformance Report (NCR) Closure
27a1fd7d-d646-590a-837c-c11033d1e9c6 | note | Reference - MRPA Quality Management Plan
e057b7d9-2bb4-53c9-90b6-d69f42a4a266 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
e76558c4-c114-5ba3-9715-b7e4bad6d9c1 | note | Method - Document Review
31a945fc-4aee-551d-88c0-722ffb7d9ea7 | note | Frequency - Once, prior to closure of this lot / element / Work area
92842a2f-6e49-5d32-ade0-03b2d7287e38 | note | Category - HP*
8cdca31f-d408-5a75-b54d-6cf90ae13037 | note | Responsible person - SE/PE/SPE
517c4c8f-3a6d-576e-8ac0-4d69afb18277 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
f474439c-08f9-5a32-a9dd-11bb2ad9d958 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c46bad7b-ae2f-5c35-90f7-958975836b05 | textbox | Name:
1d1c94d9-3273-5bbf-9956-9d8dd488dd53 | textbox | Position:
0bda0a6d-67b6-568b-968b-b3e0d90c459a | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-044-STR-Brunt-RSS Wall Main ITP | itp | ITP-044-STR-Brunt-RSS Wall Main ITP | ba8fc09f-f0f9-4b74-a223-134d0d90427c
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
c9097b4f-ef20-5e3c-980e-5c550f1755a8 | note | Document Title: ITP-044-STR-Brunt-RSS Wall Main
780aa317-dc5b-5780-9486-b3240cbde6b8 | note | ITP Description: RSS Wall Main ITP
07552c7e-c96b-589c-a8eb-86819c0246d2 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
4964f94d-89e7-5779-84de-869e560e6f34 | note | Discipline (e.g. CIV/STR/RAIL): STR
980448fe-3519-5ba9-b29f-5e63a815514b | note | Revision Number: 0
895dd21f-151f-56f7-a12f-7f2b6ef56b2a | note | Revision Date: 7/07/2023
6586cace-9a98-5b0b-95e9-f45650124690 | note | ITP created by: Thilan Rathnayake
1f4a9db4-34ec-55b8-b130-5e1b9e27193b | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Applicable Specs/Standards
438efd69-ea15-5ca0-b9ce-3e3c963b6757 | note | Reference - VicRoads Section 682 Nov 2018
| checkpoint | 1.2 - Applicable Specs/Standards
30cde91a-ccec-51ee-a293-19f3387dd9e0 | note | Reference - VicRoads Section 204 Dec 2015
| checkpoint | 1.3 - Applicable Specs/Standards
ca695f01-971b-5a81-8f9a-92f273082c45 | note | Reference - VicRoads Section 610 Feb 2020
| checkpoint | 1.4 - Applicable Specs/Standards
d0c9eeb8-1b34-56ab-9e69-df246e67bc07 | note | Reference - IFC drawings
| checkpoint | 1.5 - Applicable Specs/Standards
104aaad7-a451-55d8-93d9-b06819eb9719 | note | Reference - BTN 009
| checkpoint | 1.6 - Applicable Specs/Standards
ecaf3412-df40-5050-b116-3bead69107d7 | note | Reference - AS5100-2007
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Concrete-Leveling Pad
f93642e9-b039-5487-bd5e-f0332951a0a4 | note | Reference - IFC drawings
cc0ac6eb-f9a1-5a85-a9b3-6d247714c83d | note | Acceptance Criteria - CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
488fbffe-62b1-5b4b-9edc-ddc3d415d113 | textbox | Teambinder MA Ref Number:
6df6d328-fa9a-504e-b573-00838588d8ae | note | Method - Document Review
3025d0e8-52e0-506c-81f3-b73beed66f51 | note | Frequency - Each element
8dc0da01-d0eb-55c3-9b9d-f758bf7c208e | note | Category - HP
ea610b66-ed5f-53ec-ac72-aff6aca754b8 | note | Responsibility - Nominated Authority
f97d9ef8-cb08-56af-b78a-cf9a232fb108 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Select Backfill
89f946cc-79c1-5ae6-969a-bd98c4c5390f | note | Reference - IFC Drawings
c5a01bc4-a303-51b9-b19e-7136c8775029 | note | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
15fa0420-f015-5735-b023-d1b93e7f2fb7 | note | ○ UNIT WEIGHT: 22 kN/m³
1486690e-e981-5b05-b8c4-ffe82bf2ff42 | note | ○ INTERNAL FRICTION ANGLE ≥ 36.0°
b3065c71-1cc8-5bb7-809a-fac294e9b570 | note | ○ COHESION: 0 kPa
e4a1bf2b-d28b-52ab-b2c5-09dbd876fa76 | note | Gradation:
f5db796d-726a-55ce-993d-31db9bcc3939 | note | ○ 150mm : 100% PASSING
9508d371-2921-5a47-b656-21726d58fba7 | note | ○ 37.5mm : 60 TO 100% PASSING
a7b3dfd3-ba55-5779-84e4-e79f6454fa3b | note | ○ 9.5mm : 25 TO 100% PASSING
0f581d06-ef80-53c3-aae3-591fdcd4d907 | note | ○ 2.36mm : 15 TO 100% PASSING
485d3747-8818-5c47-8b72-4258fdbc48c1 | note | ○ 0.6mm : 10 TO 100% PASSING
17e08f6b-a393-5a36-966b-8443a180d7a7 | note | ○ 0.075mm : 0 TO 15% PASSING
a1ae1b0e-d38b-5be5-81a9-c4d9f2397302 | note | Electrochemical Properties:
a1f1ca7e-d5bd-559f-b50f-410da920595f | note | ○ RESISTIVITY >1000 Ω-cm
487123aa-ea0a-5f7a-880b-ce173ed3dd91 | note | ○ CHLORIDES <200 mg/kg
63b6f932-e631-5946-ab81-816efb514d4b | note | ○ SULPHATES <200 mg/kg
16586241-30ae-5960-a1fb-07b983764abe | note | ○ ORGANIC CONTENT 0%
6654bfd7-200d-56ba-ae08-bb1c2d2930b6 | note | Structural Properties:
588998db-78f0-54f8-95ed-688b5c47417d | note | ○ COEFFICIENT OF UNIFORMITY ≥ 5
5f154ae3-4c7b-5db0-a82b-ce0c6deff9c7 | note | ○ LIQUID LIMIT ≤ 30%
c7888ea3-49d2-5da1-818f-2660493e23f7 | note | ○ PLASTICITY INDEX ≤ 12
e50078b9-8753-5e03-90dc-9c5bddfa8b1a | note | The select backfill must meet the minimum requirements of VicRoads Section 204 for Type A Filling.
fd024554-3886-5547-9aac-42c83707a2be | textbox | TeamBinder MA Ref Number:
7319e1f2-ef31-5efc-86e7-8b5296509596 | note | Method - Document Review
fbadd10b-fe25-59db-b569-cf094ac6065f | note | Frequency - Each material specification
3b715783-07ca-5994-b701-c9a698d43558 | note | Category - HP
5109f3c8-e202-52fa-b53a-fb9d66babf4b | note | Responsibility - Nominated Authority
70485c18-70e8-5be1-bf65-98eb2e2bc99a | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - General Backfill
2485b6d1-0053-5968-ae4d-655ef7eba578 | note | Reference - IFC Drawings
bed14a88-68b2-5e66-b436-957f98922627 | note | Acceptance Criteria - Backfill behind the reinforced block shall have the properties specified in the IFC Drawings.
6a20acd7-b4dc-5308-babd-db02369181c6 | note | ○ Geotechnical Design Parameters for Embankment (Type A) Fill:
b3a9d7a0-634d-5303-9d28-2f99d402574c | note | ○ Effective Friction Angle: ≥ 36.0°
333b8502-7dc3-548c-9d2a-7fb139c18c21 | note | ○ Effective Cohesion: 0-3 kPa
8f649962-956a-5379-9f28-c0554f1e3efc | note | ○ Unit Weight: 22 kN/m³
4a0c9fd6-69f7-5b4c-a972-72eef8984a37 | textbox | TeamBinder MA Ref Number:
9bb4c6ed-a437-5ae8-b3e6-110eb17ba560 | note | Method - Document Review
17096c2b-5172-5865-b9c5-dd842bcf84af | note | Frequency - Each material specification
05488d17-b20b-57a4-810f-dc85633b468d | note | Category - HP
cbea8285-ca4d-521a-8b15-b796b11d211c | note | Responsibility - Nominated Authority
2a2e9020-f3c2-5b27-8eb7-45f12ab8cd11 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Perforated Pipe-material
e655ed01-fd89-5cf9-8a07-4a29bd46b4dc | note | Reference - IFC Drawings
3c500f76-4a29-5815-b9fa-8e487b75fd61 | note | Acceptance Criteria - Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
b32524a0-f11d-51b9-8798-4692621ba80b | textbox | TeamBinder MA Ref Number:
85f33600-672f-5751-a745-b094d403fd16 | note | Method - Document Review, Measure
6df2b86e-05e0-561b-b494-cf4557fe9c14 | note | Frequency - Each element
c3973a53-a135-5a05-bb52-468396700901 | note | Category - HP
aac59d39-9a9e-5841-9387-34444782e601 | note | Responsibility - Nominated Authority
1944f2cc-17f1-5557-ad36-9e41f66a2455 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Material Conformance - Folded plates
b8bd79fb-ee77-5fab-bed0-c242592e2dbe | note | Reference - IFC Drawings
618777a6-d5b4-5dbd-99a0-b4e44ff1ccb5 | note | Acceptance Criteria - GRADE 250 D41
9c8617df-4f1e-5cd7-8318-8ab2300286d4 | note | ○ 300x6MM FOLDED
b81b4c12-1350-515f-bcc8-be8b41a136d1 | note | ○ GALV. PLATE
01ad248f-a460-586f-bd8c-e4ee7cafa3f9 | textbox | TeamBinder MA Ref Number:
02644190-257d-50d6-ac84-71c4c61cacc0 | note | Method - Document Review
7a6fe536-98e6-510d-9069-fb97d4ecaa8e | note | Frequency - Each raw
ccc609af-6b43-5180-ba4a-daa1f9746501 | note | Category - HP
e7b8e94b-8fa0-5398-8c4d-e1fcb8d3c3ea | note | Responsibility - Nominated Authority
d551bda7-5226-5eb4-9639-1baf26807f55 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Bearing Pads, Filter Fabric, Geotextile, Strip Drains & Chimney Drains
dd93344e-90dc-542d-aea7-46d6594b5472 | note | Reference - IFC Drawings
7a5c8068-8157-542b-8a9e-4a71745c2c5d | note | Acceptance Criteria - Refer to relevant IFC Drawings for details of these incidental materials.
7e615e27-f321-56ee-a21d-518af91fb02e | textbox | TeamBinder MA Ref Number:
0d717df5-e51d-51d4-8b1b-d7edfc71564b | note | Method - Document Review
2982a1d4-8273-53d6-ba3d-466354dd6d8d | note | Frequency - Each material specification
9e567dea-514e-58c3-9758-9efa802685fd | note | Category - HP
8db10f0b-53ff-5cc2-ad0c-159e05aa8e04 | note | Responsibility - Nominated Authority
f936a523-bfa4-57ad-bc48-865c4fc922c9 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documents
| checkpoint | 3.1 - RSS Precast Panels QA Documentations
03520754-9eba-572d-9854-d00f9888073a | note | Reference - Subcontractor Methodology and Procedures
34406f19-a086-5282-808f-bfa75a96450f | note | Acceptance Criteria - RSS Precast Panel Supplier is required to provide the following Quality Assurance documentation prior to casting of precast panels.
027cd5ec-fe44-553d-a213-b262ef1b2f82 | note | – Quality Management Plan
2118234d-97bb-5506-8617-45c65ee6f554 | note | – Works Procedures
62909649-4d59-5ea4-ac67-1882e88d1d14 | note | – Concrete mix design
9ad04767-106d-5e73-adb6-84c8000c97de | note | – Concrete crack repair procedure
041e0d77-4bd5-55cf-8593-702ed8d34e83 | note | – Concrete crack repair ITP
b0af4118-270b-5973-8ea0-8114be789a18 | note | – Weld procedure qualification records
165a14c2-cb0a-57da-9e9b-c3c1c27b9378 | note | – Precast panel liftring design
14c3532e-8674-5cdd-ad23-00fb6343ed5c | note | – ACRS cert for steel reinforcement
69b3ddb9-1a52-5b38-b92d-ebd88d5a1278 | note | – Concrete pre–pour records template
7911164f-ff93-56a4-ad0d-9d6969e05751 | note | – Concrete pour records template
0ca47c20-ecf5-586d-b3c0-1ea31cca0843 | note | – Concrete post–pour records template
a5fd8549-832b-5601-9409-5380e12e0e35 | note | – Concrete cover check records template
71df2aea-e2c1-5c7b-8061-991b683de661 | note | – Record of dimensional measurements
5702882c-b556-5817-ac4d-7c8a70d35da4 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into a Hold Point in Teambinder (don't attach here)
16ae1ddf-1933-5147-9574-a7a7151f14d8 | textbox | TeamBinder Hold Point Ref Number:
fc40d6c2-ca4d-5e5e-b28f-923018779839 | note | Method - Document Review
5b35dd48-a1de-540a-9816-34b768674a31 | note | Frequency - Once for each type of panels
98e1192f-d524-530c-9a59-12850180bce0 | note | Category - HP
e7eb4820-59ab-5d00-be73-eed4820f73af | note | Responsibility - Nominated Authority
2da3842d-fbfc-537b-a3ed-307a256bfc2a | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Levelling Pad-Survey Set out
9794f540-f8ea-5201-930f-bda4f7acd38f | note | Reference - IFC Drawings
0a8a7ac7-0a74-594e-80e0-66d8bade071e | note | Acceptance Criteria - Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the IFC Drawings and VicRoads Specification
cdeaa1c0-39a7-56d5-b2c5-fd3b00cc60ee | note | Method - Measure, Visual
0e92e28c-77e6-53e1-abb4-6a9dd995c9e2 | note | Frequency - Each retaining Wall
838299a7-185f-594e-ad7d-11157aea22f6 | note | Category - IP
9ea2eb96-1eed-5b53-907d-4b088ab4b747 | note | Responsibility - Surveyor, SE/PE
ad0f36de-d45d-5e7b-b4e3-f93150f1adee | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Form Levelling pad
4a917601-bbd8-544f-bd69-dcd5ecc05455 | note | Reference - IFC Drawings
6ee9dac3-2a40-5208-b0a2-d7a889f74cf8 | note | Acceptance Criteria - Form timber shutters to edge of levelling pad
f7ef43db-0dab-5fae-abd4-57c773fc7c15 | note | ○ Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
48ec403b-7293-5808-98d1-424d60aaac6f | note | ○ The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
fac019e6-8c6a-58d5-a3a1-7befa9d3c547 | note | ○ 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
7e450ad6-69ac-5aca-a152-b1ad4c0b3751 | note | Method - Measure, Visual
5cda7233-a6d0-597a-b7c6-a74dff0224b1 | note | Frequency - Each Lot
58f54396-b209-5b0f-ba5b-780a5114b420 | note | Category - IP
9e3c9514-ee7c-5526-82a8-e79609cc8f32 | note | Responsibility - SE/Site Supervisor
599691e7-2fbb-5b6e-86a8-5875e637d39c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Leveling Pad Concrete Pour
feff0723-0600-56fa-957b-140aa371ba58 | note | Reference - IFC Drawings
2fb59819-d755-53ca-80c3-9b22a48eb60a | note | Acceptance Criteria - Concrete to be placed in accordance with VR Section Section 610.
833b50c3-f339-5ccf-82b5-41d531ac9aba | note | ○ Leveling pad concrete strength shall be 25 MPa minimum.
754eb9d8-c053-5f46-822c-e8f8fb80cf4e | textbox | TeamBinder MA Ref Number:
c40d32e8-98f7-5848-864f-da7364cdf3cf | note | Attach: Concrete Delivery Docket & Pour Record
c59db09d-4d8b-5cb3-bf90-12aa3f4d79e0 | note | Method - Visual
89112cbc-900d-5266-b830-c85dba5a9965 | note | Frequency - Each Lot
6bfe21b2-4a2c-5ec0-aa03-6e18266afb94 | note | Category - IP
587dff0f-61b6-5140-adbc-9d0c08e86963 | note | Responsibility - SE/Site Supervisor
a4e667c8-e081-51e3-b1e3-06100d828d81 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Leveling Pad Concrete Testing
a83083c6-cdcb-536f-8683-320ef0acaf24 | note | Reference - IFC Drawings
82d0ce88-469e-5ae5-927e-0e37f7047a5a | note | Acceptance Criteria - Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
c4adace1-6234-51c5-bbd8-1bc365f225cc | note | Attach: Concrete Compcressive Test Report
5e428cec-9128-553f-91b2-c0163c5e8ba2 | note | Method - Document Review
2b182a44-d29a-5eb3-a320-6f97faab8add | note | Frequency - Each Lot
64f99cac-5805-59b7-811f-2984debb6c86 | note | Category - IP
2b25c3b1-0151-59f9-8483-72ec03413029 | note | Responsibility - PE
6941e4be-d0ee-5612-a4da-8696a6320021 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Levelling Pad-Post Pour Survey-Levelling Course
35b6b6c8-af34-5f7c-8ecd-a75463814de8 | note | Reference - IFC Drawings
b3d12bcf-a81e-53cb-8dc3-46b605930166 | note | Acceptance Criteria - Levelling course level shall not deviate from the specified level by more than ±3mm
48b72978-06ac-5b79-8643-0df59cf32583 | note | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
4289909b-e4c3-5b4b-bdbc-f78af018c5ad | note | Attach: As-built Survey Conformance
46bc6c26-fe86-53be-b3f0-ef17c15e681f | note | Method - Measure, Visual
07e6788c-ad85-5452-8b71-c82ecdabbe48 | note | Frequency - Each RSS Wall
845a3c2f-88cf-5e9a-b8a3-0eb50139b154 | note | Category - IP
fa0114bb-2615-5ba5-960c-128fb691442c | note | Responsibility - PE/SE/Surveyor
b012a713-abbb-54b1-87e4-73391f7fc879 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Precast RSS Wall Panels Installation
2a6b0fdf-4d92-5318-a796-bfb880ac9027 | note | Reference - VR Section 682.17
c3ee2d38-65c4-57f6-ab6b-13c37f5ad580 | note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
ab6018f5-c52d-5c70-b168-802a0fb9e929 | note | ○ The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
c40cbd34-411f-5ec9-9a04-8d8b9892ca01 | note | ○ Refer to Precast Panel Installation Checklist for each course of panels.
2df558cf-4adb-5fed-ae05-da1b9f3f271f | note | Attach: Lot map
aa9bd5e6-b59e-5474-b8ef-9c636d8e5e12 | note | Method - Visual Measure
07cc0a1e-710d-53e5-8f22-c9d42dc8aca2 | note | Frequency - Each course of facing panel
fd193dc0-d4ab-55e2-bbbe-164bb2a29abf | note | Category - HP*
62440afd-02a2-5fd4-b62b-573e1d9b5c3a | note | Responsibility - PE/SE
a4bd6399-ec4e-5b31-be5d-3332d0a9b68b | note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0
| checkpoint | 5.6 - Precast RSS Wall - Drainage
8e20b90f-bbc8-5eff-9706-4eee9a4420ad | note | Reference - IFC Drawings
3ac6a4f1-9843-5139-ab30-716e5d9a9d37 | note | Acceptance Criteria - 300mm Wide Strip Drain along back of RSS Precast Panel at 2m c/c with 100mm clear distance from straps.
defc3118-cc22-5f52-8051-4f0d14a6c7c0 | note | ○ 100mm dia. perforated subsurface longitudinal draiange (1:100 Fall) 500mm nominal above existing surface level wrapped in geotextile and encased in free draining material.
4db2fe27-cf4d-539a-9d69-25b455566f65 | note | ○ Chimney drain min 300mm wide comprising A5 or B2 filter material in accordance with VR Section 702. Perimiter of chimney drainage wrapped in BIDIM A24 (or approved equivalent) non-woven geotextile overlapped by 150mm min. at joints.
5f370202-5c84-596c-9b7e-8c55c5e5044b | note | ○ Refer to Precast Panel Installation Checklist for each course of panels.
4ddf26c9-58e4-551b-983f-af1d045ca7ae | note | Attach: Lot Maps
84ccc075-2514-5037-b3b5-fefcd2a15f92 | note | Method - Visual Measure
7c1f7043-1b9b-5406-8a46-29cafb881a02 | note | Frequency - Each course of facing panel
daa95c4a-6d30-57a8-88ef-7df5df6a3630 | note | Category - HP*
674f3dd6-7593-5a63-bb6b-c23e055c7270 | note | Responsibility - PE/SE
bedcde20-147f-5fd4-acbc-ed89935b4afa | note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0
| checkpoint | 5.7 - RSS Select Fill
b22cd2be-7262-5e40-92b4-b973b373cb3f | note | Reference - IFC Drawings VR Section 682.16
66945091-63cd-50d4-8dfb-7d546d57a6c3 | note | Acceptance Criteria - The Contractor shall submit Compaction & Moisture Content Test Results (Scale A) for each layer of fill placement to the Superintendent for review and acceptance.
e4dcc36a-a720-5475-a87d-49d6fa1f353c | note | ○ No further fill placement shall be allowed if the total thickness of fill placement is greater than 1m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
5fc29d0b-cee2-50d1-963e-cdd6c6613263 | note | ○ Refer to Fill Placement Checklist for each fill layer.
61c8a16c-4fc1-50ed-a757-42dd3c697a42 | note | Attach: Lot Maps
477b5a3f-b1e0-53b4-9994-6843f7d828ae | note | Method - Visual, Test, Measure
d52a9df6-df36-5b61-b886-923882c6d2d3 | note | Frequency - Each layer of fill
1fe9e49b-97f9-545f-a931-bdae1244a764 | note | Category - HP*
e8e6f109-5c28-5214-9246-28181738d8a1 | note | Responsibility - PE/SE
32f3ca40-e625-5e5c-b75d-8782dc80b76c | note | Verifying Documents - CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Conformance Survey
ed787bb6-460d-58dc-99d6-13c50e582954 | note | Reference - MRPA Quality Management Plan
87eee358-9140-5cb1-afab-63599c7dc909 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
d239bdd1-4f00-5e08-9d68-ae5ff5a1fe91 | note | Attach: Survey As-built / Survey Report
c78f45cb-56a4-5a78-bbf3-19400637aa4e | note | Method - Document Review
111e76df-a809-5c54-b927-c46e44191bad | note | Frequency - Each element
bec503ba-9c67-50b9-800a-7b7ebd2f4dcc | note | Category - IP
f44bfeda-a35d-5c7e-910c-321c1b50d570 | note | Responsibility - Surveyor, SE/PE/SPE
2bfbcf3d-4b95-5d7c-8b69-f030897fd01f | note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0, CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
| checkpoint | 6.2 - Wall Post Construction Monitoring (This is part of the on-going monitoring of the RSS panels post installation)
cf668393-89f8-5bcf-982d-f111887fb88f | note | Reference - VR Section 682.20, VR Section 682.21
bec9a661-c805-52a4-86d0-b3bac4d6fba7 | note | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in VR Section 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
57439f6e-902b-5dc0-adcc-b4ad6a1ffd39 | note | (a) plan position shown on the drawings, at base of wall shall not exceed +/-15 mm;
7ca4eb33-3c5c-535e-81ab-4db82969e07c | note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
6637f802-7955-5d0c-a7e9-5e918998c5fe | note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
bd29c081-7bc7-54a8-9690-8201e898d0eb | note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
d3c9962e-931a-52dc-b178-1eb02ef40f44 | note | (e) the wall level shall not deviate from the specified level by more than +/-20 mm;
78010f42-9ce3-52a0-9013-5b1024bdb3f1 | note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
9a02fc30-f008-5135-bc59-80600580837b | note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
c0ec5df7-4b54-50d3-b55f-a8a6b356ff61 | note | Attach: Surveyor pick-ups / measurements.
9e5f8da1-5725-5379-992c-fb18636ef8ff | note | Method - Measure, Survey
96e4c744-3d4d-5c33-ae17-21403ebcba41 | note | Frequency - In accordance with VR Section 682
292703c5-2d85-5d77-9ad6-e46b432788a4 | note | Category - IP
b5e0369a-ebe7-5755-9286-61f1943e3280 | note | Responsibility - Surveyor, Completions
fae84786-abab-5b22-acc3-695a87de67d3 | note | Verifying Documents - Survey Monitoring Report (Refer back to CND)
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
2ab7cd38-b349-5646-abc1-8760eff913b2 | note | Reference - MRPA Quality Management Plan
4fedb050-91b1-51b9-b9d6-4bfdda30b0e5 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
51a09ece-5749-5368-a5a5-44306f4acd96 | note | Method - Document Review
0c86a2de-e0c3-56dc-b272-f3d8c52910a5 | note | Frequency - Once, prior to closure of this lot / element / Work area
e719030c-0cdf-553d-b580-8a4382368e2a | note | Category - HP*
a3a5189d-4306-50e6-b699-1ea0a6018cf6 | note | Responsibility - SE/PE/SPE
40161616-9b0c-5469-b82a-fe5f5f03d9d8 | note | Verifying Documents - CHK-005-STR-BRUNT-RSS Walls-Precast Panel Installation Rev0, CHK-004-STR-BRUNT-RSS Walls-Fill Placement Rev0
| checkpoint | Final Inspection
bad1522f-a1cd-5a95-84a0-7b27a5e5f790 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
80f05c5c-041d-5e81-ab23-e06a2404221a | textbox | Name:
d3e69b36-b54e-54a9-b023-b0a714ae53ad | textbox | Position:
838fbfe9-7496-53c6-9503-dd61a444b9d8 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-059-CIV-Brunt-Supply & Installation of Recycled HDPE Drainage Pipe | itp | ITP-059-CIV-Brunt-Supply & Installation of Recycled HDPE Drainage Pipe | c9ad841b-24b5-4924-985d-5bbcd820e3bf
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
c4b8fc2a-b684-5137-a6a3-b1383471c7e4 | note | Document Title: ITP-059-CIV-Brunt-Supply/Installation of Recycled HDPE Drainage Pipe
70eb7b8d-9dc5-522b-8999-dd8efba9c156 | note | ITP Description: Installation of Recycled HDPE Drainage Pipe
3edb8d4a-6348-5707-acb8-41c4ca4624d7 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
51aafc36-fd70-536c-b148-6f255bf567dc | note | Discipline (e.g. CIV/STR/RAIL): CIV
989d3ede-fb5b-53fe-8d78-d74b41968fc0 | note | Revision Number: 0
2e64d1ed-2758-55b0-9d29-bf28b1a72ff2 | note | Revision Date: 8/08/2023
8c75d33b-9c45-596d-8f9f-c20e92d09b32 | note | ITP created by: Kamel Alshobaki
d339e222-1bab-5d8b-a7f5-76d945173fd5 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Relevant Standards/Specs
310281f9-af43-5f29-bbfc-4188e07425e9 | note | Reference - AS 2566
| checkpoint | 1.2 - Relevant Standards/Specs
61226e79-ae7b-57d6-85b2-3611b9bd6deb | note | Reference - VicRoads Sec 701
| checkpoint | 1.3 - Relevant Standards/Specs
e117b061-accd-5d93-8dc4-fec558fde90d | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Drainage Flexible Pipes
14669af9-e798-5c8c-84b7-2c2181e9837f | note | Reference - Section 701.08
802daf15-16c3-5038-91ae-4c52eb459bd2 | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
8e9dc387-ea26-59df-99f0-7750720f52ec | note | ○ Prior to incorporating into the Project Works, plastic flexible pipes and fittings, shall obtain a signed Certificate of Conformance verifying that the materials and components comply with the requirements of VR 701 Standard.
a41f4935-e01b-5407-bb62-7d406e7b0d59 | note | ○ Buried flexible pipes shall not be used directly under the road pavement area.
afa9d50d-75c4-5c4e-b3e5-67cec26f9073 | textbox | Enter: Teambinder Material Approval number
2e42b763-39a7-5beb-b4c1-9db6a8165c81 | note | Method - Document Review
0fb21f37-8822-50da-a40a-8cb2ed65fb21 | note | Frequency - Each lot
eaaec9fc-b19b-5e61-acad-5ca05329499c | note | Category - HP
bc665ac5-3bbd-5fa3-82ca-7d8721920406 | note | Responsibility - Nominated Authority
51de87fc-bcb8-568f-82c3-07c063c9460d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Precast Drainage Pit
1bf92686-45b1-5bf5-b7cc-f06d72f7c2f5 | note | Reference - Section 705.07, Section 705.04, Section 705.09
05abc854-0cf1-55cd-88c1-9cbc8bf3780b | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
4893e507-7576-50fb-a42d-9704c0b1a902 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
0436e9e0-c48a-5db5-af46-156bb5446281 | textbox | Enter: Teambinder Material Approval number
de762391-512b-5d3d-989d-73a3de7a1e56 | note | Method - Document Review
ecc711d7-1ab3-51e0-b207-0291d28c06be | note | Frequency - Each lot
f09893a2-5ee6-545a-a3bb-9ce032727d99 | note | Category - HP
c2de38a8-3066-5d50-ad96-9a8521d3d749 | note | Responsibility - Nominated Authority
fdcbd01c-39cb-50e1-8626-e9055e1cc6a8 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Cast in Place Drainage Pit
db7b4bd5-4e6d-589b-85c5-ea17ca0a5326 | note | Reference - Section 705.06 IFC Drawings
669ae4fc-5e8a-53c8-a96c-9395fabcfe92 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
44c8c680-4966-52b8-9ace-386a28fff4d6 | note | Method - Document Review
b6cdce78-780f-5bbd-be21-cc2f546265f1 | note | Frequency - Each lot
6aee3f39-a09d-5b48-81fa-352167d1e87b | note | Category - HP
2c4ef8fa-7886-54b8-8839-ccc2b378bbd8 | note | Responsibility - Nominated Authority
6244f8a7-b9d6-545d-9585-86675eae738a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Drainage Pit - Step Irons
04ef26eb-0dda-5398-8f86-81d5903cbd16 | note | Reference - Section 705.04, Section 705.12
7707b00e-cdaa-598d-a60e-8c84fc2022a6 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
14d2f984-44d8-5eaf-abfb-0f0ffafe7846 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
2aca3e8f-078c-54e4-b22d-81db4a430b3a | textbox | Enter: Teambinder Material Approval number
d42323b3-958f-553a-ad76-348be69ebf63 | note | Method - Document Review
bce6b15e-da66-5b8f-9bbc-cdd04af6615b | note | Frequency - Each lot
dbebb5cd-e0b9-574f-a5a3-204fa34150af | note | Category - HP
85a155fd-6b5f-5f21-8b65-3e9e1fe9c10e | note | Responsibility - Nominated Authority
7e4e8cfa-12b3-545a-a8c4-d724dfc82590 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Drainage Bedding Material
e41b86f0-daba-5340-a950-e2b7880d9ac1 | note | Reference - Section 701.09
4e94e2fd-86aa-55ff-95fe-3782dee547c4 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
b6a54532-8fcd-5188-9f73-d2d01c39eb29 | textbox | Enter: Teambinder Material Approval number
826784ad-890d-5294-9f82-9cb0f8674ad5 | note | Method - Document Review
00d625b0-c3e3-58ce-871d-81634da120b6 | note | Frequency - Each lot
fac56467-05ed-5db9-8f96-47613f1753cb | note | Category - HP
8392b54b-f519-57f7-bbc2-1e8b7bde9720 | note | Responsibility - Nominated Authority
a88baf57-0413-5b86-b271-63a9201d5fc0 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Drainage Backfill Material
d8a9c4bc-69cd-556d-9e5f-eb8755f68c75 | note | Reference - Section 701.09, Section 701.19
93b67a33-c39f-5dc1-8864-f25adb9e1b27 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
694e515c-5b59-5662-9993-9ec573c14646 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
b0a50869-4a7a-542a-a8f7-f884b72db5ce | textbox | Enter: Teambinder Material Approval number
0d4ab372-6bbc-5e8e-bfa1-04522ff55188 | note | Method - Document Review
a1fb1039-9d6e-5e60-8d51-2cded2b123ee | note | Frequency - Each lot
2ed4977c-dff1-5d3f-aec6-0657bb7b010a | note | Category - HP
a5957ba8-99a8-54fa-9119-0da2d3d5756a | note | Responsibility - Nominated Authority
ecfde366-3672-5e0a-ab3b-7c8225d0baf2 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Subcontractor ITP (where required)
41639b01-2342-5bc5-a116-850e55b6e60e | note | Reference - Subcontractor ITP
9e922936-d563-5719-9cf6-8f9d7ed0d2d1 | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
f23556da-ab1a-5939-af78-f69aca873d84 | note | Attach: Signed-off Subcontractor ITP
5bf82a25-7488-5a7c-8cf7-9f13d32e9fa7 | note | Method - Document Review
ca7f5ba5-ecf6-5fab-8fbb-ae5968213dc1 | note | Frequency - Each lot
cc46f36a-6f9b-53a2-88f1-a4cafe1316e4 | note | Category - HP*
fe6b7257-a766-53e4-a347-38ac2afdfe98 | note | Responsibility - PE
80353e49-df10-53ad-aa8c-2ab217e84d9c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.2 - Check the type, size and class of pipes and other drainage structures to be laid
37ac7cf9-b5ba-51d2-a629-a5f05bc56c1e | note | Reference - Work ActivityPack
a72172ae-04f1-5993-a05e-1ea949e2b8ac | note | Acceptance Criteria - Check Supplied items are:
19e509a5-fef8-5b62-bd16-57d40da1c637 | note | – To correct spec, type, size and quantity
7d4a9a2d-65c5-53f9-a198-4296f025d6ce | note | – Defect free, safely stored & prevented from UV Exposure
fd1529a8-db7e-5309-bb62-02af9a657d27 | note | – Markings have been made as required
cc83e761-4638-54cd-b850-fe0ce261559a | note | Method - Visual Review Document
510e38bf-ff7c-584c-99cf-acfba2a094ba | note | Frequency - Each lot
6fd4093e-1d75-519c-b861-3453357c893c | note | Category - IP
5f34d4ba-4f5a-5a32-873d-3651e5550e3d | note | Responsibility - Supervisor, SE/PE/SPE
99cbef64-1514-5c0b-8ff3-822205569812 | note | Verifying Documents - This ITP Signed Off
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set Out - Pits & Pipes
c9fb9c1f-1c7b-5a9b-9aef-3395ffbc661c | note | Reference - IFC Drawings Section 701.10
d1f0194a-fb50-5c66-afd0-aa0495292f83 | note | Acceptance Criteria - Prior to commencement of excavation for the flexible pipes, the Contractor shall confirm the position of all pipes with the Superintendent/Surveyor.
28140646-14a7-5c1b-94d6-c38b734da030 | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and VR701.10
17f9b2ab-e925-5768-ab67-bf2aa7ca047e | note | Method - Survey
c5225933-8fb9-5082-820e-3dd0353a9a78 | note | Frequency - Each Lot
0b5b83c0-60a8-54e3-b9cf-786b90ebd1d8 | note | Category - HP*
8feb1c15-e467-5a36-9d9d-f22295c2c2ba | note | Responsibility - PE
817b3ebd-909b-533a-8662-cdbaa67437b3 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Set out the works for each drainage system
e4a20fd3-ad6e-53ba-b702-f75c6f2aa7dd | note | Reference - AS 2566 IFC Drawing
ccc05183-9bbb-5654-9a33-0fdc92d591ee | note | Acceptance Criteria - Establish Pegs (or equivalent)survry marks to identify location, length, and levels as per design drawings and schedules and check if:
ab321dbe-9be0-5857-a1b2-aa39672fa773 | note | – Inlet/outlet heights fit in with natural surface (ie not too high or low)
a578e998-fddb-5907-96da-e589e4ca7718 | note | – Inlet/outlet location suitable for water-course (eg no drainage problems)
424162bf-0f78-51ec-a1c9-ee48639c9fa9 | note | – Pits relocated (through RFI’s) in order to avoid cutting of pipes
8130dfe4-a4aa-5ae3-8889-409be7240b88 | note | Method - Inspection Survey
d96be19b-a7cb-5c54-86fa-5764f76c0492 | note | Frequency - Each lot
d24ae50a-4490-5346-92bc-1914864db99d | note | Category - IP
1d0bfc0e-2487-5cbe-bcbc-321595d05c76 | note | Responsibility - Supervisor, SE/PE/SPE
205fee13-e957-50dd-a7a7-6b4332479744 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Confirm position of all Drainage line/culverts
8f6ad944-53a0-5dbc-92dc-c1d8ba7ed119 | note | Reference - VicRoads 701.09 IFC Drawing
aa447f5b-7744-5352-be8d-b7f790def36a | note | Acceptance Criteria - Prior to commencement of excavation for the Drainage the contractor shall confirm the position of all drainage line with the Surveyor.
65ce76ef-2f01-58bc-9eb9-15f07cb1d8df | note | Method - Visual Inspection
ba1b6f3a-3186-553a-aa1a-c21ef2e76948 | note | Frequency - Each lot
afb5b215-1f54-51b1-a52d-1f884fe52a02 | note | Category - HP*
c04e062e-1fd1-5d0b-ba4b-ccc9f7feea96 | note | Responsibility - Supervisor, SE/PE/SPE, Surveyor
007d51e5-a962-50a8-b7d5-2d733662e878 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Excavate trench to the underside of bedding to correct width
cb64517f-c630-5c9b-84ab-4ef820d951d5 | note | Reference - AS 2566 IFC Drawing
ac226b4b-3ff7-525b-89b3-f6182af347a3 | note | Acceptance Criteria - Width and depth of pipe trench as per AS 2566.1. Refer to right table
77141352-823a-5f99-b79f-f950a8c469c9 | note | ○ For other structures, the clear width between structure wall & face of excavation is ≥ 300mm or 1/3 height of excavation face, whichever is greater
4cfb7aa6-70f5-54a9-a7c8-914484af7712 | note | ○ Trenches > 1.5m deep are either shored or benched
2a97fd15-941e-5e97-818d-d62ba2aaab22 | note | ○ The excavation is ≤ 50mm beyond the specified width and depths of the trench
2b2e9fc9-a0c7-5934-a5be-5fb1d22f5448 | note | ○ For pipes under embankments
468e73b5-406f-54ab-8748-76e19f931a31 | note | – the first embankment is constructed to a height ≥ 0.7 times the external dia of the pipe above the top of the bed zone, and for a min lateral distance past the boundary of the trench of 2.5 times the external dia of the pipe
12dd1ceb-0c2d-5139-808a-c6c0cffb22b3 | note | – Trenches done after the construct of the embankment to the level of the underside of the Selected Material Layer
db2c7d28-23b8-5fb9-96c8-39bc608701b9 | note | ○ No welding/ anchor block systems etc. required. This system is just a simple lubrication of the end of pipe.
878ef899-53b7-599a-b561-7206f5566f7d | note | Method - Inspection
de02e1c2-639b-52a9-8a43-42f884bb4f51 | note | Frequency - Each lot
ebcee1df-f58f-5605-ae89-296dc39f4d93 | note | Category - IP
1b300469-4b30-5808-b578-f420aa8c6274 | note | Responsibility - Supervisor, SE/PE/SPE
957948d5-cfb3-562a-be2b-7d36416ebf74 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Install pipes in accordance to manufacturer’s instructions and design documentations
61e4f334-1c3b-5294-81d1-62a0c30b52dd | note | Reference - RPM Installation and Handling Guildelines
27c0f871-bcb6-5fc5-8a71-72b103fb64d7 | note | Acceptance Criteria - Pipe laid from inlet to outlet
9b056e21-fcb6-5430-a602-a27d264f3e88 | note | ○ Pipe support conforming to AS2566
2d12ae06-94ef-54f6-bd30-8e13a663d6ea | note | ○ Polypropylene Pipes (Blackmax or StormPro)
10f0daeb-cab3-5112-9e02-6747da0639d5 | note | ○ Correct size and class of pipes are laid with socket end placed upstream
588082d7-034a-5eea-9ca7-c6cdb0cc0c2a | note | ○ Pipe ends cleaned and rubber rings / bands installed as per manufacture’s recommendations
a27d125b-7318-574a-be6f-13922d2106fd | note | ○ Inlet/outlet heights fit in with natural surface (not too high or low)
fde650b7-a962-5761-b469-46a6418d7e5b | note | ○ HDPE Pipes to be cleaned, beaded and jointed by suitably qualified personnel.
89d23b57-958e-5aa9-9d0f-9d02469c1460 | note | ○ Electrofusion Welding or Butt Welding of pipes permissible.
006ee161-cd0e-57c0-b7a3-c6c421453aae | note | ○ Joints allowed to cool prior to lifting or shifting into position.
809d37d0-6264-5ef9-9675-760aa9e47499 | note | ○ Anchor blocks provided at 3m spacing max., at bends, junctions and where shown on drawings
424fd03b-55b6-53be-a8c3-97caf87b6c3b | note | ○ Subsurface drainage installed at the discharge end of pipes
f385104a-6813-5785-b661-81ded7c418c3 | note | ○ Add check lengths as per the minimum required
e4b0c4e7-5f75-50b5-b1ab-d8c8d8d0c47a | note | ○ Width to edge of trench, 150mm
00333e0a-84c1-5575-b7cd-8870d29f4c25 | note | ○ 300mm above pipe with selected backfill material.
42dc1e80-31dd-59f2-a9dc-c382c7859221 | note | Method - Inspection
e2538cc8-ba06-5d30-a791-a395e212e865 | note | Frequency - Each lot
98c80206-a907-5cb2-84c4-1c4fed3e514d | note | Category - IP
71b54e8d-721e-50bb-b9a4-87b9a68134e6 | note | Responsibility - Supervisor, SE/PE/SPE
1ec25ea6-d366-51b9-882b-3c0c747ba4dd | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Verify that completed pipeline against survey marksdesign level and alignments
2e4c905e-3184-5c92-8e99-f5d6e4146d39 | note | Reference - AS 2566 IFC Drawing
0b1e205d-8372-5df7-a863-c3fe789d6f53 | note | Acceptance Criteria - Completed pipeline is inline and within ±200mm of location (plan)
07517425-3260-5af5-a7d2-8f5d541b7ea4 | note | ○ Invert level are within 20mm of the design level at any point
0dc793ea-4cb8-55a4-94dc-41f463e71ff0 | note | ○ To be checked at each pit and headwall
c3c31561-64fc-55d7-aeb0-d824dca700fc | note | ○ Horizontal Position for Pits in Kerb to be
5dfa6aa3-e98c-5cc7-88b2-395a5dcc4779 | note | • +-200mm longitudinally
d80e4419-ef2e-55ba-98bf-6e713f043e8e | note | • +-20mm perpendiculat to kerb alignment
bef3ead6-d5a1-5c4d-8c29-d522aa8d9d79 | note | Method - Inspection
3a5b8515-de4c-5c16-b492-d39dae1b6895 | note | Frequency - Each lot
a54cac4f-7dd8-5037-ae6d-35e43494b10f | note | Category - IP
50424f72-8db5-5580-b736-0090b477267a | note | Responsibility - Supervisor, SE/PE/SPE
8a5f9361-d233-5e93-9f18-193cae787a1d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Place and spread haunch, side zone, overlay and backfill embedment, replacement and backfill material,, compact and test to specified densities
8661a3ed-e145-5529-adad-0d2fc65f02aa | note | Reference - VicRoads Spec. Cl. 701.26, 701.20
137441c8-7d99-5f8a-9443-10afc1287239 | note | Acceptance Criteria - Placed in 150mm layers and compact to 95% std compaction
c1520f06-96c6-55c5-972e-5bcf4d9cedcd | note | ○ If stabilised sand used, the materials been vibrated to obtain complete placement & compaction of material under & around pipe and the placed stabilised materials are firm a day after placement
a24e476c-6149-5060-92f2-655fb6ff7307 | note | ○ If 10/14mm aggregates used, the materials been vibrated to obtain complete placement & compaction of material under & around pipes.
44cffb93-955b-5b22-ae1c-17b713c5baca | note | ○ A minimum of 20% of all lots for each culvert shall be tested.
bc7889be-e1b6-5f5b-8a41-859963dc8978 | note | Method - Inspection
64b1042a-1bde-553f-ac1a-0a28fbefc00f | note | Frequency - Each lot
7db62dcf-1656-5cc3-aeaf-c5efdd1c845f | note | Category - IP
dfdd71e8-9840-574a-948a-caa0062dee90 | note | Responsibility - Supervisor, SE/PE/SPE
3d115deb-0384-5d3e-a1dc-3377deaaacd9 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Inlet/Outlet Structures
7480ee1b-22bb-5920-b833-5b29ce650b57 | note | Reference - VicRoads Spec. 701.23
30d43500-e3d9-5ee9-9381-bb5bb8415182 | note | Acceptance Criteria - Refer to Pit supply & installation ITP
5b14a500-9501-5cea-bbde-0794a07c7626 | note | Method - Inspection
d7734211-f31c-5047-b112-001c8cc6da48 | note | Frequency - Each lot
4eaced25-5ddb-5353-8c28-bf6e1ce1c4af | note | Category - IP
bbdc18e6-38f6-5fe7-a23a-1054ca55dfda | note | Responsibility - Supervisor, SE/PE/SPE
914bdbfe-1a3b-5458-99cd-7d80a0903a30 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Flushing System
461cca13-cf10-5892-9e2c-0cea56022d90 | note | Reference - VicRoads Spec. Cl. 701.26
92f6cff1-8f3b-5daf-8e20-3b321ac81656 | note | Acceptance Criteria - Each Drainage/Culvert line is to be flushed clean from end to end on completion. and maintained in proper working order.
91326ae4-0faa-5b0e-83ca-0d646cfdaea6 | note | Method - Inspection
10944ea4-5c51-5b44-bf30-d5dba5d6c589 | note | Frequency - Each lot
1ecda636-1163-5392-bb43-f2fa400616be | note | Category - HP*
dbc4a0fd-a088-513b-9896-a0d41c44da5a | note | Responsibility - Nominated Authority
c73caf8b-4ff2-512e-bd6b-1eff142639dd | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Engage pipe inspection video subcontractor to take footage of all completed new pipes.
b547e50b-3292-57ff-9801-38bef5678187 | note | Reference - VicRoads Spec 701.28
c195c818-f7be-5447-bec4-fdce377b0c74 | note | Acceptance Criteria - All Drainage line constructed shall be inspected after completion of earthworks to subgrade level and prior to construction of pavement layers, by independent Testing Organization using closed circuit television(CCTV). The report shall be provided to the Nominated Authority.
8696a383-73b8-571b-acad-46613d77d3c6 | note | Attach: CCTV Report
fa500f7a-7bbe-501c-93a5-7af008d07a13 | note | Method - Inspection
8bb7ad19-8362-5dfb-800e-1e914eee59bb | note | Frequency - Each lot
11a9453e-100e-50bc-bf65-113ff32ce336 | note | Category - HP
920de603-2bc2-58d3-9310-6299153fe061 | note | Responsibility - Nominated Authority
86dc69cc-7146-5458-9352-297420973b4e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey Conformance
3c7beddb-409a-56d0-b50a-61386c465001 | note | Reference - MRPA Quality Management Plan
232be5e0-95c4-5f5d-b883-0d319bc7124d | note | Acceptance Criteria - Survey activities undertaken to validate correct construction
a93aea09-d3dc-5821-b253-dc722b62eb2b | note | Attach: Survey Report, Engineering Asset From
284fbbe7-bc02-52c7-8b00-4cef203e7cd2 | note | Method - Survey Document Review
674fa5f3-718a-58c2-88e4-cb40907e2200 | note | Frequency - Each lot
5ce5d1e5-90ae-5d1b-9c1f-ccf3eedebc08 | note | Category - IP
677dd7bc-a3b0-5293-b7fd-0906ca0b290c | note | Responsibility - Supervisor, SE/PE/SPE
f31e051a-f671-575d-8681-fd44cd2eb796 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
1c726fd3-f736-5fa4-a198-9ab5c92f9f88 | note | Reference - MRPA Quality Management Plan
d9136753-cea5-51b2-bd8a-1c506d270bfb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
876b1960-5850-5468-8ddd-293be7132b64 | note | Method - Document Review
899ed39d-914f-51cc-a047-48df201d0550 | note | Frequency - Once, prior to closure of this lot / element / Work area
26c26380-aeee-5c45-968b-70d833f06666 | note | Category - HP*
9af1e9fa-7244-5726-a671-7fae3dc9e993 | note | Responsibility - SE/PE/SPE
986b7c8c-1fe8-5df2-a2ed-7f639b480545 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
13ca021f-f738-5f2d-8234-3ed0852e4a36 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3de7e4ac-2333-53c7-aba8-88cd680550e0 | textbox | Name:
80db104b-67f3-546a-89ac-3322783eaf58 | textbox | Position:
397f2b50-6006-5cc7-b4a3-c84a5efd6dbf | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-095-CIV-BRUNT-Unbound Flexible Pavement | itp | ITP-095-CIV-BRUNT-Unbound Flexible Pavement | d0400e69-1c17-40be-9226-874007d8ca5e
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
ee94c4c7-23a8-58af-9586-9e0bc43f15fd | note | Document Title: ITP-095-CIV-BRUNT-Unbound Flexible Pavement
fce52c6e-067d-54d9-a778-3b94fcfac20d | note | ITP Description: Unbound Flexible Pavement
012c5aa2-46ac-5810-9a21-707119641ca1 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
e637f382-06e9-5502-9563-9f6e1795afa4 | note | Discipline (e.g. CIV/STR/RAIL): CIV
88451ec3-a2c4-525e-99df-a1d52284c71e | note | Revision Number: 0
48b5f12a-a538-562f-bab1-653ba36710f5 | note | Revision Date: 26/10/2023
f3a96614-4891-59da-85c0-07acc365a9fa | note | ITP created by: Crystal D’Mello
30ae1a8b-9c28-5321-acee-64e468c225d0 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
6c5a84d1-0977-5868-9fa0-ef40ff0ac09b | note | Reference - IFC Drawings
| checkpoint | 1.2 - Non Dependent
041dbe81-a0f6-5c60-bbbe-9d8fbe656117 | note | Reference - VR Section 173
| checkpoint | 1.3 - Non Dependent
aa70a3c3-a673-5ac6-9f12-725f77c9502f | note | Reference - VR Section 304
| checkpoint | 1.4 - Non Dependent
f6663dfb-aa50-5122-ac46-dd48821d0888 | note | Reference - VR Section 801
| checkpoint | 1.5 - Non Dependent
5b6d8da2-580a-5b57-84d5-08f93179e1b7 | note | Reference - VR Section 812
| checkpoint | 1.6 - Non Dependent
772bb294-3045-57dd-8794-8ee5b9ff3e96 | note | Reference - VR Section 204
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Crushed Rock Mix Design
212228d2-4c9e-5c3e-bbc3-6528cfbd601c | note | Reference - Section 304.03, Section 304.05, Section 812.04, Table 812.121, IFC Drawings
c8097c20-027a-50a9-b2a1-7b40eb5bf761 | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
0f789fb4-a59e-5db5-a225-6113583fe0c2 | textbox | Enter: Teambinder Material Approval Number
88d340c9-67ed-527e-b348-978a47c4e000 | note | Method - Document Review
bb2ddb13-cfc1-566c-8f5b-981409fcacfa | note | Frequency - Material conformance as per Table 812.121
f782db59-3f24-5ce8-9717-e6d146e296cf | note | Category - HP
62183d08-097d-59ae-aa04-3e88000a86c8 | note | Responsibility - N/A
15ccf7d6-d5ee-51a3-a281-3049f0483d93 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentation
| checkpoint | 3.1 - Subgrade Preparation
57916c37-8d62-5261-8377-aaa30878c3a4 | note | Reference - Section 304.04
23549112-fa6a-531f-bc5a-9df7c7ceeb00 | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
6ffae8d7-853b-5617-8cbd-ae16db458e6e | note | Reference: Subgrade Preparation/Type fill Lot Number / Underlying layer Lot number
f7cfae45-f3b3-5ee5-a6a8-a50940d75921 | note | Method - Document Review
79daa7b3-c807-5547-9c7a-610c33a2783a | note | Frequency - Each Lot
d6e78b54-6ad4-5968-aa66-469ac633c605 | note | Category - HP*
abb293a6-516b-5f95-b9c6-8e9a9f83d3e1 | note | Responsibility - PE
eb86b066-a9d5-500c-8fa8-bf2012ff2044 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.2 - Select Scale
51dd1581-a20b-57e4-bbea-82f368e4c87c | note | Reference - Project Requirement Specifications IFC Drawings
9a52a05c-2d8e-5d54-b966-4e3e42e5bf2a | note | Acceptance Criteria - Scale to be determined as per the PRS and IFC Drawing requirements
068e19a0-918d-551b-b516-661b4581de92 | textbox | Enter: Teambinder Material Approval number
9f46168e-f635-5882-8646-a6d2cc98be57 | note | Method - Document Review
44f463c2-41f4-5f77-9e04-583ca542f0af | note | Frequency - Prior to Commencement, Each lot
2c427abd-9640-55d2-90d5-4e1b0edf6a2a | note | Category - IP
eaddd335-92b1-5daa-8558-1c73882d2576 | note | Responsibility - PE
c8393aaa-9291-51be-b116-ef2894ace6ee | note | Verifying Documents - This ITP Signed Off
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-out and Lot size
f6075d74-43af-5641-9641-3e506248ed28 | note | Reference - IFC Drawings Section 304.06
65cd7d7c-30d0-5559-9d74-41a338e5bba4 | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
1c136e6a-8664-5031-9135-369b6c5b5fdf | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
5731d2a5-24ca-5293-bc34-2f0961ff5705 | note | Attach: Lot marked up location on IFC Drawings (Lot Map)
7c3dc3f1-739b-522e-990c-51f854ca9900 | note | Method - Survey, Document Review, Measure
e0247a51-1f39-588d-a266-38525e262b7f | note | Frequency - Each lot
291e77b6-11b3-5f97-90bd-83184e2c545f | note | Category - IP
848061b6-98cf-55f9-a1a8-135cefe107ba | note | Responsibility - SE/Surveyor
f0322e5f-a65b-5adb-9898-7395502894cd | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Crushed Rock Delivery Dockets
df10de8c-27d3-53f9-ae40-8966d1add637 | note | Reference - Section 304.04
1375bdd3-ad4c-5f5c-9973-4eb5d8934f47 | note | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
0c9f7b31-9137-5f85-9d64-4100adc437ea | note | Attach: Delivery Docket(s)
495acccc-0154-520f-9c85-4f1c48ab60d9 | note | Method - Document Review
317fd21c-e10b-537a-8d9a-902e16f0f3bf | note | Frequency - Each Lot
84fc7e0f-6121-52bc-9d6c-a9fcb60f326e | note | Category - IP
0074f7d1-b9ae-5888-8355-6f716a025bd8 | note | Responsibility - SE
ec38da26-5035-520b-995f-8abcd105096f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Placement of Material
84721466-345d-5add-833c-eac22fae9aff | note | Reference - Section 304.03, Section 304.06, Section 304.08
70dfb373-7811-5110-84e2-08437ac79d2b | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
eb7f6d11-086e-5dff-921b-f887b391bc02 | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
d8a9b860-ab69-5e1d-b359-705a4ed506da | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
e944fe8e-8b2d-5eeb-bc49-55e06381de22 | note | ○ At no location shall water pond on the surface of any pavement layer.
5541d227-87c4-55cd-b5ac-f1f1a7b29af1 | note | Method - Visual and Measure
52f0d6e1-bbe7-55e3-a40a-90d9a498acf8 | note | Frequency - Each lot
75d94271-bf7b-52b4-af4f-d6fde19e83a2 | note | Category - IP
fb3e5a61-fee2-59fb-8d1e-4e82c1a7fba2 | note | Responsibility - SE/Surveyor
6bf79166-0b5d-5635-9d8c-845780996cff | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Construction - Jointing
4f8a4e0a-d326-5c6a-ab42-8ff746767204 | note | Reference - Section 304.07
e3c14177-409b-527d-b54b-075e3446e684 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
27b5f408-ade8-5416-b0aa-165df6a0d8ef | note | (a) material shall be spread in such a manner as to minimize the number of joints;
9a4563d6-0eb2-5f06-b569-57250347d25c | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
8bc6d8e4-e06d-57f7-a100-016fb2129c05 | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
517af554-f26f-5cff-88f1-40e54eaf8007 | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
54f11587-210c-5c4a-9b3d-2e478d27c374 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
1b2138f7-d796-54ec-b9df-6229674d80fb | note | Method - Visual and Measure
834b7a34-48fb-5ced-af3b-46296c671d11 | note | Frequency - Each lot
c58ed5f2-1f68-5e47-b6ea-f4f2470d3b45 | note | Category - IP
1860c7f2-7b64-5c8a-bee1-8bead0baac71 | note | Responsibility - SE/Surveyor
05d5a2d3-72bf-53cb-ad96-2aa37002f11d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Compaction Test (Frequency)
f5181b5f-34dc-5d7c-bf85-0b35e93964d2 | note | Reference - Section 304 .11 (b)
bf468a84-af00-51b8-a052-4c48b71fb0a8 | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
c9ec53c3-382c-5f6f-af3f-1756e12e7718 | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
4d0c4baa-aa46-5156-bcb5-8e2d3108429f | note | ○ Scales A and B: 6 samples
8ce5cbb4-da39-5ceb-98f0-e14271085132 | note | ○ Scale C: 3 Samples
91d13f82-a404-5ba1-ae73-b5cb1a03b9ba | note | Attach: Material Test Reports
224b6423-8946-5ab2-b9a5-3ae689afa812 | note | Method - Visual
89fd2cbc-dbbb-5396-8a3f-1a6a60254fe5 | note | Frequency - Each Lot Where applicable
2d17e653-a4ce-5711-bc9e-99dd44db6a03 | note | Category - IP
5250a6a8-9d76-53f3-a06f-2d5e9483eacf | note | Responsibility - SE
ae6a45f9-46e1-5e0a-b066-230182819a2f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
8b015bcb-201d-59eb-8ecc-38e9d7fb70de | note | Reference - Section 304.11 (c)
69e4898f-6701-5904-b394-6047f378c166 | note | Acceptance Criteria - SCALE A: The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
825bf017-47df-5d7e-9c26-d625daa76860 | note | Compaction:
5c4c7893-435e-57dd-be36-056e44faf81e | note | ○ Lower Subbase: none
e844b985-8401-5554-a0e3-7b9c472fdfa5 | note | ○ Upper Subbase: 1 in 4
006638fb-33d3-5b84-802d-031c54827fbe | note | ○ Base: 1 in 2
f293c53b-27ab-5e3d-aca1-eea74c98225c | note | PI:
d19bc5a1-dd7e-5c3b-975b-ec446a20ce94 | note | ○ Upper Subbase and Lower Base: 1 (two samples) in 8
c2720653-8600-53a3-914f-841d7d626379 | note | ○ Upper Base: 1 (two samples) in 4
243134bf-0812-5fce-9857-715a27c73f2a | note | SCALE B: the first lot of each pavement course shall be tested for post-compaction grading and PI.
19107205-370f-5a44-99f2-c3093c83bcda | note | SCALE C: Post compaction grading and PI testing is not required (CHOOSE N/A)
e1abc592-7fe3-5f0c-b713-145484baa62e | note | Method - Visual
5577642b-2215-5528-9b67-2bb34e929fbd | note | Frequency - Each Lot Where applicable
c3dbc9fa-70ce-5a11-b2e9-ca8830de7199 | note | Category - IP
3bb2a778-1d47-55b3-bc78-28919f79a63e | note | Responsibility - SE
5d350242-ebfe-591c-9366-07cb15b18482 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Proof Roll
13787d0f-1f8f-546e-8bdd-55f65a8f2ffe | note | Reference - Section 304.08
f7964fa2-fc5f-5b4c-a3c5-332f0d7bc180 | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
488e7090-c0bc-5132-a6f6-5393d07523e7 | note | Method - Visual
77f5a308-fe13-50eb-bfd6-4e9ed85de6c4 | note | Frequency - Each lot
fd900232-513e-58b8-a591-b656bf22dca2 | note | Category - HP
775a6e31-25ce-51ee-94ce-e87901b407ef | note | Responsibility - Nominated Authority
9cb9dc23-758e-5928-b713-df76af810bfa | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 - Protection of compacted layer
982305b1-03fc-5e12-851e-648baeb43657 | note | Reference - Section 304.09
a624b492-1401-5de7-93a0-ebcdbbea4166 | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
b9167f30-6d31-5b30-9247-756bdcc1925f | note | Method - Visual
ce62654a-517b-5cc9-b73e-bbc8db72eb80 | note | Frequency - Each lot
ee8b79c6-be16-5544-9c34-625511f3cb88 | note | Category - IP
801ed3e3-db9b-51a2-b9c2-0eeaaa48ffde | note | Responsibility - SE/Surveyor
854c8b3f-7145-5421-a17e-75f1dbc5f0db | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Compaction Testing (results)
c304e388-07c0-5f8d-914f-75b3ca2154a1 | note | Reference - Section 173, Section 304.08, Table 304.081
257f816e-5e3b-5624-93d3-616ba3e8f5ad | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
e3031f42-ef35-5874-913f-01252fcf1924 | note | ○ Density Ratio to be based on tests performed with Modified Compactive Effort.
beba6477-0231-5536-94a8-46531e150b27 | note | Scale A:
c42720c1-5aab-5d13-8904-673a1cbc13c1 | note | ○ Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
cd5519cd-3afa-5624-97ba-0589664c7bd2 | note | ○ Base Layer CDR ≥ 100%
be2f5114-cbae-5157-9465-091b64845b4e | note | Scale B:
590281f8-040e-59ee-86e7-24c7cf9acb70 | note | ○ Subbase Layer CDR ≥ 97%
ce00ef2d-9078-5683-8dad-983b6aa7441d | note | ○ Base Layer CDR ≥ 98%
a6d06ab2-7abb-5571-a37c-e9f5fc665439 | note | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
826ddd85-10a1-5165-b31e-523165a1663c | note | Scale C:
c3425f3a-f34c-5ee0-8b5b-88c8c112841e | note | ○ Mean Value of Density Ratio (3 tests):
d2e0ba88-2018-5791-ba57-4c021e867e46 | note | ○ Subbase Layers >98%
437332e8-1ec2-525e-9dc1-dfce2f69c656 | note | ○ Base Layers >100%
ca1d9f34-541f-5042-b997-6022ecb54778 | note | Attach: Compaction Test Results
bbb30f9d-ab5e-5020-9799-4e6170d34020 | note | Method - Document Review
47de2774-ae40-5103-9234-45e28684e5d9 | note | Frequency - Each Lot Where applicable
0154f8de-34e5-55a9-a7a5-84fe9eb17905 | note | Category - IP
d6c17fa1-9708-5c63-ba6f-dac800a89ae7 | note | Responsibility - SE/PE
d0e7742e-ef6f-5b89-ae8e-0ff221cfc36a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Post Compaction Materials Testing (Results)
7938fbe7-f5dc-5fdb-a4ad-c80c2a58ae7f | note | Reference - Section 304.10, Section 304.11 RC 500.02
aa7c526a-f454-5747-b04d-42a9bb9eac96 | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
663e8d51-f371-5f02-acb1-1066b2cf0bc7 | note | 20mm Class 3:
c702e525-78c1-50e5-ad97-d61f12541b2d | note | Grading
7d5d1ca4-f8d6-5040-8b5d-e553947cd208 | note | ○ 26.5mm 100%
517cb806-ecb6-57df-ab5c-d1abf3ebda62 | note | ○ 19.0mm 95-100%
72b16aa1-8973-5b0c-b20a-567feccae280 | note | ○ 13.2mm 75-95%
a1fa828e-8960-5613-9a01-777041835cda | note | ○ 9.5mm 60-90%
aac8d83d-065f-561a-8d1b-f44425d37af7 | note | ○ 4.75mm 42-76%
29d08e61-f9c8-50e6-802a-d80553cba270 | note | ○ 2.36mm 28-61%
72126c7b-4a3e-5803-a614-381f6a1132e9 | note | ○ 0.425mm 14-29%
1fba196b-dc62-5756-9e87-905f17dd5f3c | note | ○ 0.075mm 6-14%
7fee6612-18e5-5974-967c-671ea14e94f5 | note | ○ PI between 0 to 10
22c3d9f0-6a72-5d98-b99f-eeaf61bc3e38 | note | 20mm Class 4:
f0aae4ca-9938-535b-93ec-c758fe4f4335 | note | Grading
5cabbc58-7bfe-5a87-8f22-4daac4f91487 | note | ○ 26.5mm 100%
a2c638a0-b306-5836-b540-dd9174577a79 | note | ○ 4.75mm 42-76%
e3685c9b-79a2-592b-80fe-f20e24d3de43 | note | ○ 0.425mm 10-28%
db049a61-2b95-566b-9c97-6aa8d63cbac2 | note | ○ 0.075mm 2-14%
494ffa53-6fff-5624-b499-5456945e81fc | note | ○ PI between 0 to 20
05299939-7276-5c26-9f60-903a2883ef20 | note | ○ PI x % passing 0.425 mm sieve (max) 450
86038805-11c5-570e-b568-5bcbdb302793 | note | Scale C: Post compaction material testing is not required (Choose N/A)
4b09a07a-a3f5-5e8f-abcc-dfde6ceaa0eb | note | Attach: Compaction Test Results
62dddf49-722e-5b2a-9f0f-f27d252dd8f9 | note | Method - Document Review
29eda1cd-9026-5a02-9d78-95dfa4817e50 | note | Frequency - Each Lot Where applicable
266be239-1779-5999-9e2b-be5ad424535d | note | Category - IP
d8011b3a-1e77-56a0-b537-7f381eec6474 | note | Responsibility - SE/PE
61af6783-7228-5295-a56c-f15ca0ff2b22 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Survey As-Built - Surface Level
072234e8-96a2-50eb-8f76-333bbb3f60ea | note | Reference - IFC Drawings Section 304.06, Table 304.061, Table 304.062
be9b40d6-0139-5b16-9ac1-86528c5921aa | note | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
3724364a-6260-5704-a470-c0ba632c6ccf | note | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
0bf19671-f4fc-5d8f-bbd8-065fc3cf5977 | note | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
d54abb40-0481-51ec-a708-f5fabefc4c5b | note | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
70bdd686-4a58-5c97-a0b9-d47671f97796 | note | Scale A: A minimum of 80 measurements/lot
9eb970fd-3c34-57cd-956a-ce4a0a6317b7 | note | ○ Lower Subbase: mean range +6mm to -10mm, maximum Standard Deviation of 10mm
1587c076-f967-598f-90d4-14fa2e3af378 | note | ○ Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
87ee9fab-ad2f-5c0e-a2f4-0bb265ece73d | note | ○ Base: mean range ±5mm, maximum Standard Deviation of 8mm
9bac1e66-4610-5211-af6a-5aedf23a7328 | note | Scale B: A minimum of 40 measurements/lot
38820a96-6a2f-5dba-9f73-4e1ae6b22406 | note | ○ Lower Subbase: mean range +8mm to -16mm, maximum Standard Deviation of 15mm
7ba94f10-9318-5805-aeb8-3b736063576a | note | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
da83eb43-2647-5ea0-b13b-87b0777f58d3 | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
e6457c63-ae3f-5dc6-99b5-4b2177068387 | note | Scale C: Minimum of 40 measurements/lot
7e6cbf68-a46d-597d-8742-641f6373c25b | note | ○ Lower Subbase (mm) +15/ -25
80042e71-0b91-58a4-b7ca-bf393d2076b7 | note | ○ Upper Subbase (mm) +10/ -25
5c329cd1-cbde-5b3f-bacb-6a4834efccf6 | note | ○ Base (mm) +/-15
cd72f279-8f91-5166-b1e0-2157dd2fbbc2 | note | Attach: Survey Conformance Report
8ca1ab56-5ee8-5189-8ea3-06a3c32fb298 | note | Method - Document Review
3c5b372b-6235-5088-84ba-ba1e95e6cccf | note | Frequency - Each lot
36e41390-ea0b-5396-bba1-b7af2fbacaf7 | note | Category - IP
90d8d957-edf6-56cf-8e11-cb3c84592427 | note | Responsibility - SE/PE/Surveyor
70592d38-df88-56f6-bbe6-a5d86e5385a4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Non-Conformance Report (NCR) Closure
6923adcf-9bae-5039-85b2-30baf6df19af | note | Reference - MRPA Quality Management Plan
1eeafbf3-b733-586d-8ece-49f7b631ba09 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
5edd5fab-c969-590d-a4ce-c1f23ac50f6d | note | Method - Document Review
84dd7244-8dc3-5600-8daf-8cf8ceb7da79 | note | Frequency - Once, prior to closure of this lot / element / Work area
efaf7cb5-c23a-5baf-a7a2-bc73a7aaae7d | note | Category - HP*
f7bcf12d-1c67-5c89-a044-e9b262d90ff9 | note | Responsibility - SE/PE/SPE
cb9850a4-c611-543c-bd2a-fbb436e1e765 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
db80d4bb-f6bf-5d87-aa6c-1a86dcba9079 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
33b02c7d-955d-536c-b57c-0266eec638a6 | textbox | Name:
e9ea59eb-d8dc-505d-9b20-2959714cf936 | textbox | Position:
8ab252fd-a3f0-57c3-a5d9-43fb4873e380 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-096-STR-BRUNT-Precast Beams Installation |  | ITP-096-STR-BRUNT-Precast Beams Installation | 19d61f0f-36d1-430c-bac5-3c6ade2abe42
| section | Referenced Documentation
| checkpoint | Referenced Documentation
3790e5a2-0f5f-5e86-8ea6-4fa7fdef11bc | note | Document Title: ITP-096-STR-BRUNT-Precast Beams Installation
3456c577-ea0a-5bdc-8bf0-302dff5b5e8f | note | ITP Description: Precast Beam Installation
614f3115-e0cc-5e8c-94dc-5e4d415dad83 | note | Discipline (e.g. CIV/STR/RAIL: STR
b761b80d-118a-5106-9905-eed71dc1ce50 | note | Revision Number: 0
a2190287-3fbb-5eb9-9764-bf632f957eee | note | Revision Date: 26/10/23
8c83c72f-f653-5e0c-a42a-db2d3c9ca51f | note | ITP created by: Yasna Naicker
b77ee783-7203-5f64-8b61-dae01d1f7a3c | note | ITP approved for use by: Jon De Castro
78355a31-17f3-555d-9c24-49698df49c01 | note | 1.1 IFC Drawings
b37f0317-7d2a-5106-a5c6-e9060715d283 | note | 1.2 VR Section 613
3be85989-e127-53b7-b2ac-08975e157edd | note | 1.3 VR Section 610
b4c5ea0e-80ba-5d12-9af5-71bf3b0afa17 | note | 1.4 VR Section 620
| section | Preliminaries - Materials
| checkpoint | 2.1 - Flowable Grout
f300e78e-c0c8-568f-9c67-88f5d662b089 | note | REFERENCE - IFC Drawings
3cc30f04-9809-53ca-a9e5-c77cfe943e36 | note | – – – – – – – – – – – – – – – – –
ac341b7c-3bc3-5db4-a6c3-b702d74513a3 | note | ACCEPTANCE CRITERIA - Underside of beam shall be grouted as per IFC drawings using flowable grout with a minimum compressive strength of 50MPa. Grout shall achieve full strength and shall be completed prior to Stage 1 deck pour.
915a0afc-82c3-51de-81e0-2639c61ef2ff | textbox | Enter: Teambinder Material Approval Number
57c69dd6-4106-5b77-85e3-a28679cbc1bb | note | – – – – – – – – – – – – – – – – –
6c122c37-22fb-5d2d-9ba4-af698628dd96 | note | METHOD - Document Review
8bde9269-b8ae-5897-86ff-be0e84e48e12 | note | – – – – – – – – – – – – – – – – –
54ab8de3-8c57-51b1-9987-7f95e8955478 | note | FREQUENCY - Each Precast Element
31f4be2d-4c0b-5ce8-aba3-bce45482e8dc | note | – – – – – – – – – – – – – – – – –
b533087a-9e0f-5da7-8056-73e1c79c70a1 | note | CATEGORY - HP
ef719ce6-06a2-50f3-a08f-13c454e4b251 | note | – – – – – – – – – – – – – – – – –
607e5b78-1656-51c0-b37b-8393056a3e22 | note | RESPONSIBILITY - Nominated Authority
c5421095-cf8e-549b-a230-3295115f44a3 | note | – – – – – – – – – – – – – – – – –
2f2e9dcb-669f-56d5-a925-9ebcfdf73171 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
70e39443-d513-5724-9740-dbc8c4812bc9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Beam Seating Pads (HDPE)
95a690d2-1b60-5736-86df-36f9f656bc98 | note | REFERENCE - IFC Drawings
34eb33b1-5764-5014-9d9a-355cc3d126bb | note | – – – – – – – – – – – – – – – – –
4c843233-3901-59bb-86ea-0b025675153c | note | ACCEPTANCE CRITERIA - 2 No. 200 x 200 x 20mm thick high density polyethylene pads, or approved equivalent, to be designed for minimum 10MPa Stress.
aa1f1279-2602-5e45-add1-d3150fe26175 | textbox | Enter: Teambinder Material Approval Number
18cbb30b-b656-540c-af42-736f08375d29 | note | – – – – – – – – – – – – – – – – –
a6c56922-edea-5bb4-972c-81f71a3852b8 | note | METHOD - Document Review
abebc916-3ac3-5d6d-86ee-d4df7ec7a98a | note | – – – – – – – – – – – – – – – – –
97daa257-9bf6-534c-bbd5-b4b7b34a01b0 | note | FREQUENCY - Each Precast Element
b8fe0e35-5ae6-5412-ab1f-6cdfa039eb6e | note | – – – – – – – – – – – – – – – – –
b69811e2-0907-51bb-a91a-005d9a7624fc | note | CATEGORY - HP
3a8be2a9-3641-5a08-9514-6126eb25bb19 | note | – – – – – – – – – – – – – – – – –
0beaaca6-a172-5d6b-a6ed-344d217d3eda | note | RESPONSIBILITY - Nominated Authority
a36d7b3d-4e5d-56b0-944f-ad46a6a2510e | note | – – – – – – – – – – – – – – – – –
c1b90188-c731-5bdc-986a-d99681d677b7 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
6f141ab3-4588-5352-8d2b-2459ad393379 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bitumen Tape / Fibre Cement Sheet
e13516ba-a294-5cf3-89b2-9d12d7f1138a | note | REFERENCE - IFC Drawings
1bcf5971-8747-5021-8a45-154f05e6fbcb | note | – – – – – – – – – – – – – – – – –
03ea9580-ea0f-52df-99be-14d8fd9897db | note | ACCEPTANCE CRITERIA - Beam joints to be sealed at the flange as per IFC drawings using approved materials. Enter: Teambinder Material Approval Number [free text box]
83197e79-9b46-5dd3-8996-9f5a9bc0a744 | note | – – – – – – – – – – – – – – – – –
4a417117-7ada-5a63-9475-6ab1eeb6a0ee | note | METHOD - Document Review
b23566aa-9337-59f4-9c77-18bb43574a75 | note | – – – – – – – – – – – – – – – – –
d4fc94e8-4838-5b3b-82d8-9b54cd803cb4 | note | FREQUENCY - Each Precast Element
3b87b0cf-8405-52d5-bcf7-bb2b4ffb3dd2 | note | – – – – – – – – – – – – – – – – –
4dba04d9-679a-5f7d-ae72-342e1c7688b5 | note | CATEGORY - HP
024c4126-4fb7-5f4b-8a2e-0952a5b0a1bd | note | – – – – – – – – – – – – – – – – –
c500fa8f-ca74-53ae-bf9b-86fb8abd7e99 | note | RESPONSIBILITY - Nominated Authority
8421024a-63f7-54a7-ac3b-4c2fd3eb77e3 | note | – – – – – – – – – – – – – – – – –
820180a0-8f36-5508-bcfa-8696dd84bdd3 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
7a157b6f-8023-5f1d-a995-22aed624ccb8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Precast Elements
bb350eb3-816c-555a-ba98-8321e021d050 | note | REFERENCE - IFC Drawings Section 610.47 VR Table 610.473 Section 620.03
06016514-b73d-5e11-b4ed-4e3b1c7d0b7d | note | – – – – – – – – – – – – – – – – –
92f77a4b-8dad-5549-8396-a2620420f43e | note | ACCEPTANCE CRITERIA - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
88f2a0e3-b0b1-5871-8ae3-b0ee25b3a592 | note | i. Certificate of Compliance / Birth Certificate
50343d77-47a0-584c-891e-07d542cd1ba8 | note | ii. Compressive strength test results
a1f39c24-e9dc-5ad2-a52f-c39ed81db6ad | note | iii. Precast Lifting Design
e2c5c90c-4340-51f5-9c48-5f2c3198c161 | note | iv. Pre-pour check sheet / ITP
df823f43-1653-5c7a-aeeb-ed6a3a52b2a1 | note | v. Pre-stressing check sheet / ITP
e33c3aad-63e2-5b4b-b4a7-b834c73501fe | note | vi. Post-pour check sheet / ITP
3204b4d6-21c0-5ad7-81fb-6e3570e2336e | note | vii. Covermeter check record
58c27525-9438-5c41-a3e8-1eb0cf17c22e | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
937ea032-be73-5b58-92d4-5cb9d00ebb0e | note | Note: Different revisions of 610 have different clause numbers
a9ca7add-0757-5f84-8ed4-dcdd45aa0a55 | note | Collate: Precast Quality Assurance Documentation and upload into Teambinder.
541d6ac2-c30b-5a93-8b65-0d7c57217376 | textbox | Enter: Teambinder MDR Lot number
b847f56e-feb3-5e76-b4c0-42c7640aa604 | note | – – – – – – – – – – – – – – – – –
62ab490f-fb71-5259-8495-be463892a9f4 | note | METHOD - Document Review
d1a528f2-4695-5e53-9747-82f5a238191f | note | – – – – – – – – – – – – – – – – –
67c5799d-2598-5b5b-b9dd-4584f7528056 | note | FREQUENCY - Each Precast Element
ebbf5bc6-87d7-558e-95f7-16225571dc26 | note | – – – – – – – – – – – – – – – – –
cf4d2f0d-e98d-5dad-aa22-37e09857c561 | note | CATEGORY - HP*
be925253-f6e9-5380-b186-a29dcf558b1b | note | – – – – – – – – – – – – – – – – –
509f8a07-e29e-575a-840f-64d6c587f891 | note | RESPONSIBILITY - PE/SE/SPE
46f276a8-f332-5025-9b2f-04d4798dc58e | note | – – – – – – – – – – – – – – – – –
e70a9f3f-6440-5b5e-ae41-9ac0dc805006 | note | VERIFYING DOCUMENTS - This ITP Signed Off
86fb8a1d-bdc8-5a2d-b9df-6100d9ecfcb0 | date | Date Completed:
| checkpoint | 3.2 - Temporary Works Designs
e5ce3821-9673-5776-9a04-c7a99df5856c | note | REFERENCE - Section 610.27 Section 613.04 Section 613.05 Section 613.16
96a71859-41a2-5869-b556-37e32b800bce | note | – – – – – – – – – – – – – – – – –
c48c58e2-3e30-5cc6-883f-6008ead6a3b8 | note | ACCEPTANCE CRITERIA - All temp works design shall be certified by a design engineer who is a member of Engineers Australia and with a minimum of 5 years experience in the design and construction of falsework. The temp works design shall also be proof engineered by a Proof Engineer who is independent of the design consultant’s firm and is prequalified at Level PE under the VicRoads’ prequalification scheme. Attach: Temporary Works Design
e1095dd4-cf5d-5191-9b79-9d33b61c7f49 | note | – – – – – – – – – – – – – – – – –
948cb2f9-e3c1-5814-ab23-02f0438efa0c | note | METHOD - Document Review
de75929f-f583-58e2-b363-56a5fb9779dd | note | – – – – – – – – – – – – – – – – –
0a3bdf9a-c13f-574d-b16c-416f33120eaa | note | FREQUENCY - 2 weeks prior to installation of falsework
c2a80294-85d7-5e3b-8d7c-f2bc38491e60 | note | – – – – – – – – – – – – – – – – –
2559360c-69a6-5f42-9d74-b4531c0cf401 | note | CATEGORY - HP
9349482f-b1a2-54ae-ae34-bdee7e113879 | note | – – – – – – – – – – – – – – – – –
fb2e0e0e-d7d4-52c5-a065-d741ea94b88c | note | RESPONSIBILITY - Nominated Authority
696a1112-1ca2-508d-aefb-3bbef159cfcc | note | – – – – – – – – – – – – – – – – –
70d58ed0-a1b5-560c-8cb6-186e3e7003cd | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
7e904c2b-9df6-507c-a893-f92b772bb6a8 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
1301dbbd-38e7-5f8f-a9b2-3f5a722396ad | note | REFERENCE - MRPA Quality Management Plan
0544c241-1fcc-5ae1-a76a-a839b0049d90 | note | – – – – – – – – – – – – – – – – –
be699a78-555c-510e-8cab-ab801fb3386e | note | ACCEPTANCE CRITERIA - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
d2bfe1ee-7847-59da-9e84-d712f21399ef | note | – – – – – – – – – – – – – – – – –
6e0fc3c6-1fb1-599f-88e9-fc50dfd48de7 | note | METHOD - Document Review
b9e06a28-df15-57c8-aa5f-ea68a22dbbb6 | note | – – – – – – – – – – – – – – – – –
c44a0520-82db-5fb2-9380-a9b42055c7ea | note | FREQUENCY - Prior to starting Works and at regular intervals
e3c14c79-50a9-5994-9688-ff669860d74f | note | – – – – – – – – – – – – – – – – –
ec12ff3d-bae9-5aba-bbd7-2b452ca78be0 | note | CATEGORY - HP*
1f10357b-bbf0-5b2d-9c62-60805a62ed0f | note | – – – – – – – – – – – – – – – – –
65c2b460-e1f3-5d41-ad58-25710b39f929 | note | RESPONSIBILITY - All
3d02baac-b78a-5910-ad3d-7f861c7bcf23 | note | – – – – – – – – – – – – – – – – –
2f0b00b6-eb0e-5d70-9f1f-d29a859d0791 | note | VERIFYING DOCUMENTS - This ITP Signed Off
c75e2618-28c5-5d20-b597-267fc30338e0 | date | Date Completed:
| checkpoint | 4.2 - Beam Seating Pads Check
7a7f1a57-bdd3-506c-b5a0-bd32f03f3b19 | note | REFERENCE - IFC Drawings
359abec1-9096-59d0-965f-80d664f11011 | note | – – – – – – – – – – – – – – – – –
822b7a7f-2133-5bee-b74c-948790cdb9c1 | note | ACCEPTANCE CRITERIA - Beam seating pads shall be inspected after fixing to the abutments and prior to the landing of the precast beams. Ensure the setting and orientation of the seating pads are correct.
c00188e3-1c4c-5bb8-880e-875b71aeb982 | note | – – – – – – – – – – – – – – – – –
5a94950c-68ba-5aa0-bb2f-1b9e4fb86c9e | note | METHOD - Visual Measure
a2ccb32d-c5bf-5042-a13f-d61caf67a7ef | note | – – – – – – – – – – – – – – – – –
7289a055-fcdc-5518-8804-868c541ae893 | note | FREQUENCY - Each Precast Element
432f59c5-b4c3-56eb-9100-a4118ce997de | note | – – – – – – – – – – – – – – – – –
c9ecff50-0ab6-5c18-8944-e8007cd6e4bb | note | CATEGORY - HP*
0ac44b59-413a-5f71-824e-4ae07f8f2b2b | note | – – – – – – – – – – – – – – – – –
105a55c3-4f2f-5749-8902-f280b1b85508 | note | RESPONSIBILITY - SE/PE
b8a286e6-4c0a-5fb1-83f9-29abf1fc589b | note | – – – – – – – – – – – – – – – – –
09aa146a-e19d-5c12-ba26-c907837108cc | note | VERIFYING DOCUMENTS - This ITP Signed Off
7214bf60-e6f2-5a40-8d2f-e60d59e97d2a | date | Date Completed:
| checkpoint | 4.3 - Crosshead Tolerances
8e93c614-2bd6-5300-b76f-df6e12aaaba8 | note | REFERENCE - Survey As-builts IFC Drawings
378eb8de-c9f7-5f6c-b638-3c0ca16e14ff | note | – – – – – – – – – – – – – – – – –
a235d966-5ac0-5296-9e45-ac8ebb8f05da | note | ACCEPTANCE CRITERIA - Re-check that the As-built dimensional tolerances comply with the requirements as per IFC drawings.
f0510f8d-0714-58ac-9b5e-35428d50d303 | note | – – – – – – – – – – – – – – – – –
a2dd6026-58c2-5fc9-bb50-8be560254a77 | note | METHOD - Document Review
259fe4f3-44a2-53ba-92bf-a78fedacb82c | note | – – – – – – – – – – – – – – – – –
a70d8887-6909-55a9-bf23-64c1657f54bc | note | FREQUENCY - Each Precast Element
69552646-8544-5c88-ac58-4e54b5510692 | note | – – – – – – – – – – – – – – – – –
af319183-f4c5-5eaf-85f8-c533a87a9e26 | note | CATEGORY - IP
a6154853-ead2-505d-9e3f-7296d6bcf54f | note | – – – – – – – – – – – – – – – – –
4c4a3e74-505d-507f-a88c-04be3fc9c251 | note | RESPONSIBILITY - PE/SE/SPE
bdfbe39f-cd1d-503e-9970-13798ecd42d1 | note | – – – – – – – – – – – – – – – – –
65056a62-eb1d-50df-b6d7-776bee7c608e | note | VERIFYING DOCUMENTS - This ITP Signed Off
706b6779-fa45-524e-afb0-946765db9a3d | date | Date Completed:
| checkpoint | 4.4 - Precast Beams Estimated Hog Values
4739e23a-8523-5329-b33a-e9fb94305c8a | note | REFERENCE - IFC Drawings
bb33242d-6c01-5ea3-a487-bf7be99fd66f | note | – – – – – – – – – – – – – – – – –
355bb169-7e73-568d-bfab-aea60fe90a31 | note | ACCEPTANCE CRITERIA - Re-check hog values for each precast beams to ensure within tolerance prior to landing of beams.
229d8be2-c0ae-5704-8326-e3fa027257c1 | note | Estimated Hog at Transfer (B1-B10) = 30mm
cab7094e-063e-53fe-8b03-a6f95b01d667 | note | Estimated Hog at Transfer (B11-B20) = 21mm
10cc4fe8-f352-50f4-856b-ed2da693afde | note | Estimated Hog at 30 Days (B1-B10) = 54mm
991f6062-e347-51a2-8ae0-8938b2927691 | note | Estimated Hog at 30 Days (B11-B20) = 42mm
570b6e6b-53ba-5ddd-bc7a-117157d5b105 | note | – – – – – – – – – – – – – – – – –
f48b6dec-f941-58d3-8959-2a488442b9b8 | note | METHOD - Visual Measure
a67cf293-f85e-53dc-ba1c-7bca5c87822d | note | – – – – – – – – – – – – – – – – –
f190a4e0-b06f-5689-949b-0e1ee9697164 | note | FREQUENCY - Each Precast Element
7ff0de5d-f8bb-5301-af0f-ff4a414ebcce | note | – – – – – – – – – – – – – – – – –
e8ddfc30-dc13-59b2-9d34-a57ff1c1e002 | note | CATEGORY - IP
cde36d9b-560d-5f99-ab0e-7237034fbb7d | note | – – – – – – – – – – – – – – – – –
f9790d84-a3c8-5133-bfef-0447752c00af | note | RESPONSIBILITY - SE/PE
18a82f21-e745-5478-a771-7e79fc76dd0b | note | – – – – – – – – – – – – – – – – –
64a18673-6495-5c03-8f2f-ee23e1a3788e | note | VERIFYING DOCUMENTS - This ITP Signed Off
63cd8d94-cfc7-5147-8222-ecdfc1e6fd4c | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 - Seating Pad Survey Set-out
3ab1d93f-089a-55ac-9b8e-6e5a4779d352 | note | REFERENCE - IFC Drawings
8bd7796c-723f-5e81-a630-a8ed9c87b629 | note | – – – – – – – – – – – – – – – – –
80f85cc9-db41-5d4b-8226-e637754a4b8a | note | ACCEPTANCE CRITERIA - Survey activities undertaken to ensure seating pads' locations are in accordance with IFC drawings.
34e2c8d6-9a38-576f-9523-8a894cde101d | note | – – – – – – – – – – – – – – – – –
1380c87b-073a-5895-a9ad-e0b96e54797d | note | METHOD - Measure Visual
9bed499b-a3ba-59b6-b017-c2d04bc6d7c9 | note | – – – – – – – – – – – – – – – – –
9b7849eb-5e74-5c23-a642-a953a5041155 | note | FREQUENCY - Each Precast Element
4457da53-d7b0-5bdc-b683-4db665449fdf | note | – – – – – – – – – – – – – – – – –
9d49b939-86fa-54bb-aacf-8d61cf456ad7 | note | CATEGORY - IP
22911281-ae80-56cc-9060-67153d1f529a | note | – – – – – – – – – – – – – – – – –
8b372b22-6091-5890-aeb4-29139c9485fe | note | RESPONSIBILITY - Surveyor SE/PE/SPE
9230cd28-058c-5636-a69c-a7c0d620e50a | note | – – – – – – – – – – – – – – – – –
e14c056f-99a2-5944-8bc7-9df50d77ae7e | note | VERIFYING DOCUMENTS - This ITP Signed Off
eb3e9ef7-fe70-5128-a2f9-e19a987c8602 | date | Date Completed:
| checkpoint | 5.2 - Install Seating Pads (HDPE)
b37059b9-e58a-5d80-afb8-adb912367e1e | note | REFERENCE - IFC Drawings
5d0d390a-1a19-5ed3-a2da-c9d3c083ee79 | note | – – – – – – – – – – – – – – – – –
47444f81-d32e-57e4-afaa-be30350793db | note | ACCEPTANCE CRITERIA - 2 Nos of 200x200x35mm HDPE packers are to be installed in designated recesses on restraining blocks.
6fc33705-17b3-5017-98b6-d871f05a3be2 | note | – – – – – – – – – – – – – – – – –
44ef4898-9381-51aa-a8ad-f1ffceeb6b79 | note | METHOD - Visual
ed87b6fe-cc7c-59eb-bcce-a5fdc452b66f | note | – – – – – – – – – – – – – – – – –
40332e4e-331f-544b-ba40-114a7d172daa | note | FREQUENCY - Each Precast Element
d4c39883-7852-5a2f-8916-a977dfe8b0cf | note | – – – – – – – – – – – – – – – – –
2fb3681a-751a-522a-8f6c-e0ee8dbe60b1 | note | CATEGORY - IP
4beb68b5-b521-5a1a-9202-044a8c69c33e | note | – – – – – – – – – – – – – – – – –
57e2d3bd-aff6-5642-be4e-51dca9fad2e3 | note | RESPONSIBILITY - SE/PE
b7af73ea-b7f1-53ae-9dcd-d00720f51104 | note | – – – – – – – – – – – – – – – – –
e58e034e-972d-58fd-a133-7fa9adc977d0 | note | VERIFYING DOCUMENTS - This ITP Signed Off
7ec51bd0-78b3-5641-b6bc-a2104f243660 | date | Date Completed:
| checkpoint | 5.3 - Precast Beams Handling
af2be272-ae74-58ed-ada6-68d9f4b106b7 | note | REFERENCE - IFC Drawings Section 620.07 Crane Lift Study Beam Certified Lifting Design
8f0644cf-3075-55cf-803e-d08439135503 | note | – – – – – – – – – – – – – – – – –
4262ddfe-e597-5ab5-b9da-a31234620133 | note | ACCEPTANCE CRITERIA - Unless otherwise specified, precast elements shall be lifted using approved lifting points in accordance with the Crane Lift Study and Precast Beams Certified Lifting Design.
7507cfb5-755c-5cf8-a256-25652ebc50d4 | note | During storage, transport and handling, precast beams shall be kept in an upright position and supported not more than 400mm from each end. Beams shall only be lifted by the approved lifting anchors provided. Sling Angles not to exceed 300 from the vertical
20bd98f2-a146-5c57-94e7-98ef10d89722 | note | – – – – – – – – – – – – – – – – –
81139164-a9b3-5bc1-b1b4-341bbfc5e0cb | note | METHOD - Visual Document Review
6d69970e-bab6-5363-acc0-8afcb99d3aab | note | – – – – – – – – – – – – – – – – –
b8a42d89-a7c0-500b-b4f2-40bbe0795845 | note | FREQUENCY - Each Precast Element
30d4b36e-8f62-5be6-985a-b754bdf73f21 | note | – – – – – – – – – – – – – – – – –
8aa169b0-b39e-57da-b237-b947f0a3bf0c | note | CATEGORY - IP
e02cc147-4af4-5eec-bda1-ecebed0935c6 | note | – – – – – – – – – – – – – – – – –
a8a100c2-6812-5d60-8f7c-71cd3c25c34b | note | RESPONSIBILITY - SE/PE/SPE
46165d37-d7c3-5e58-82db-f63ce6c4d4b3 | note | – – – – – – – – – – – – – – – – –
144a160f-8d03-516e-ac1d-24bf552ae74e | note | VERIFYING DOCUMENTS - This ITP Signed Off
b54d18c2-ae15-5914-8e43-7ab6b9f3cf79 | date | Date Completed:
| checkpoint | 5.4 - Precast Beams Placement
3ebe686c-e4a6-5f6e-87a4-417199f5694f | note | REFERENCE - IFC Drawings Section 610.27
40e73089-f349-5ba8-849a-5f6ced44c88c | note | – – – – – – – – – – – – – – – – –
51cb6cab-eced-5355-b3fc-05f23ae3d7e1 | note | ACCEPTANCE CRITERIA - Precast beams shall be placed onto the seating pads and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings. The nominal gap between elements is as per the IFC Drawings. Precast beams shall not be erected and landed until the specified 28 day concrete compressive strength for abutment/pier crossheads have been achieved, and not before 14 days after casting. Beams shall be braced in accordance with the approved Temp Works to prevent overturning at all stages of construction.
69a66e59-4504-5c20-a3a1-fac48cacebb4 | note | – – – – – – – – – – – – – – – – –
fb1f86f6-5e04-532d-b419-10b5e0886c0e | note | METHOD - Measure Visual Document Review
98cc1153-41b6-55db-91f8-7c481a479f36 | note | – – – – – – – – – – – – – – – – –
b653f885-7b20-5b4b-8f82-ae293a85edcc | note | FREQUENCY - Each element
996b68d3-ef01-5baf-8894-ad4a032d12a2 | note | – – – – – – – – – – – – – – – – –
5d3ca2ea-dc02-59bc-afe6-32ab33db8e0f | note | CATEGORY - IP
3de31fce-13a6-51a4-9edd-f252d8ce608a | note | – – – – – – – – – – – – – – – – –
00f9e36f-3260-5c75-95cc-f89f085d8e6e | note | RESPONSIBILITY - Surveyor SE/PE/SPE
7186987b-cfed-58f9-b13f-9055b8c32917 | note | – – – – – – – – – – – – – – – – –
2288b503-6b19-5dbf-a549-857f9e24d6d8 | note | VERIFYING DOCUMENTS - This ITP Signed Off
8ce3ca7f-1538-55ea-9b14-7c91e99d6313 | date | Date Completed:
| checkpoint | 5.5 - Precast Traceability
dfc75f93-89db-58ee-848b-6216216d6677 | note | REFERENCE - Section 620.09
bbbaefe4-176a-5923-9d0d-4869a3beed1b | note | – – – – – – – – – – – – – – – – –
c10a051a-01a4-5bf5-9f9a-74024dc45853 | note | ACCEPTANCE CRITERIA - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed. Attach: Lot Maps showing beam individual IDs
bdb102a8-7aff-5f4b-a578-132ca12fe1bd | note | – – – – – – – – – – – – – – – – –
ba2d7b1d-e46b-57c1-bce9-ae8e7417bdb5 | note | METHOD - Visual
fe222b5b-aedb-5878-b427-7be4ab6bc5cc | note | – – – – – – – – – – – – – – – – –
accfc9f5-97a7-5a52-aab3-5c7ca77c2cfe | note | FREQUENCY - Each element
121a30d3-4b24-5953-835c-5813c808d353 | note | – – – – – – – – – – – – – – – – –
ac9fe5c2-2b47-5e03-a614-be21700adf76 | note | CATEGORY - IP
9864d78b-2de8-57e0-9c66-535a6102d798 | note | – – – – – – – – – – – – – – – – –
da84959a-ee93-511a-8365-a611fe74aada | note | RESPONSIBILITY - SE/PE/SPE
1ef37228-38ab-5413-a929-e61620e0c2a5 | note | – – – – – – – – – – – – – – – – –
30bd0ffb-18a1-51f9-9aae-c3c2f2db17d5 | note | VERIFYING DOCUMENTS - This ITP Signed Off
2b02fa13-56e3-5356-87d4-48a906f08527 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 - As-built Survey
a0e61d31-c564-5d5e-9b95-1f91480a0a46 | note | REFERENCE - IFC Drawings Section 610.47 VR Table 610.472
d273a2d7-b7a1-543a-916a-fb693e9b0ce2 | note | – – – – – – – – – – – – – – – – –
9b274dde-3da2-5f06-81c5-ad26ac059f74 | note | ACCEPTANCE CRITERIA - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances. Attach: Survey As-builts / Survey Report
c564ed42-0e1e-56c1-a792-ea133fa0970a | note | – – – – – – – – – – – – – – – – –
a4811cfe-80ee-5128-90ca-c646a3daa3a3 | note | METHOD - Document Review
72669463-50c0-5a7a-a606-0c53582863e4 | note | – – – – – – – – – – – – – – – – –
38053970-38c4-54b2-ade0-072578bd0c22 | note | FREQUENCY - Each element
d3f7e6db-9efd-5c65-87b8-76d179eb52e8 | note | – – – – – – – – – – – – – – – – –
15d4a2e6-261a-58d3-8cb0-3cdd2a2795c2 | note | CATEGORY - IP
b57e6cf2-eefe-5d4c-b18c-4577d6903259 | note | – – – – – – – – – – – – – – – – –
f5dbb4c7-c9fe-58a5-a21f-46268d7b8f81 | note | RESPONSIBILITY - Surveyor SE/PE/SPE
bd6a0129-657f-5af4-a5b2-1613389c0690 | note | – – – – – – – – – – – – – – – – –
541ce899-9fea-5734-9866-31ae80128275 | note | VERIFYING DOCUMENTS - This ITP Signed Off
13f8b4d3-adff-5023-9a17-e892be36e6aa | date | Date Completed:
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
c4c735be-02ff-5201-b140-b37f22a84983 | note | REFERENCE - MRPA Quality Management Plan
b45c8e43-98a0-5fa5-b270-304f7d120bbb | note | – – – – – – – – – – – – – – – – –
214be0a0-2e0c-54f2-8f3d-3ca0f6c32915 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
1262d37a-03d6-5184-9b41-374779d41bfe | note | – – – – – – – – – – – – – – – – –
9a571efb-2f98-5ed7-bec6-ac6e04b5fb6e | note | METHOD - Document Review
13e63cba-7740-5af0-87ec-b616b27ba9db | note | – – – – – – – – – – – – – – – – –
dce9a41d-cba6-5125-9cc4-e4a95406d822 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
ac4e2724-8259-51ee-9c05-e1ea48f827d5 | note | – – – – – – – – – – – – – – – – –
d6ea92e9-4de0-548d-8c10-bb962838b588 | note | CATEGORY - HP*
2439fbc0-2bd6-5d97-9c5e-8bbda6615191 | note | – – – – – – – – – – – – – – – – –
903e8b84-7e0b-5ea9-8830-0eaf4a9995fd | note | RESPONSIBILITY - SE/PE/SPE
413f7882-6328-5219-89de-28fbf47c7237 | note | – – – – – – – – – – – – – – – – –
4ecb51e5-79d9-5c1a-911d-b756abbad441 | note | VERIFYING DOCUMENTS - This ITP Signed Off
dcfa7dcb-e9c7-532d-bd6a-67f3b59b21e9 | date | Date Completed:
| checkpoint | Final Inspection
c0961ad5-6c9d-5ffd-bbea-697d09305963 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0230539e-3165-5e3e-b721-ac858414ce9f | textbox | Name:
24615ba2-ee48-5a7c-b93e-8b8cd1eded78 | textbox | Position:
7625a361-edaf-5e80-b383-cf97b71f0fce | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-097-STR-BRUNT-Precast Kerbs Installation Rev.1 | itp | ITP-097-STR-BRUNT-Precast Kerbs Installation Rev.1 | 8adadd4f-aeef-43ee-b4b8-295aec4ff88f
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
326c2f61-7a44-54bf-9e32-09a1637e4a8c | note | Document Title: ITP-097-STR-BRUNT-Precast Kerbs Installation
bcd4c56b-fe3f-5dc5-9f3d-8c4e2014fc73 | note | ITP Description: Precast Kerbs Installation
7a476abd-9da4-5764-a5ea-e9d25ad21861 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ceff529e-a1d3-5e98-ae41-90b150975ce6 | note | Discipline (e.g. CIV/STR/RAIL): STR
b2cd36cc-b138-5159-a7ca-b7070f9dbaf6 | note | Revision Number: 1
8df8fe15-09a3-5e46-ab5a-ff049b2d58bc | note | Revision Date: 15/12/2023
9bbcc773-ce0f-5aff-9f5b-1542c0778213 | note | ITP created by: Yasna Naicker
4eeec4df-64dc-5713-a973-271d383d190d | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
62bbd1fe-b392-57c8-af50-0ee3eb69c8c9 | note | Reference - VR Section 610
| checkpoint | 1.2 - Non Dependent
cc8e8c4e-f92f-532a-b1c2-4e49a29782dc | note | Reference - VR Section 620
| checkpoint | 1.3 - Non Dependent
a5f1a14e-b0b8-5f98-80d7-24ff0aadc923 | note | Reference - IFC Drawings
| section | 2. Preliminaries Materials
| checkpoint | 2.1 - Grout
1c5ac215-c4b1-58ea-8d5a-21b330e343f4 | note | Reference - IFC Drawings
9f0ef455-cda0-548c-bb6f-d68cb2cda960 | note | Acceptance Criteria - 40MPa min strength grout or approved equivalent to be used to fill lifting anchor recesses post installation.
710df100-fb74-548f-af73-7229740c5c3a | textbox | Enter: Teambinder Material Approval number
0acfbbc0-30b4-51c0-8aa3-132ec888d0d1 | note | Method - Document Review
3695cafd-8af9-5a7c-91b6-ea8fa231e9d8 | note | Frequency - Once, for each product
c050e3b7-8cd8-5b94-9c4c-29c4c209c914 | note | Category - HP
0371f3e5-7b55-52e0-93a5-2fce79f2277c | note | Responsibility - Nominated Authority
6c1d7cd4-48be-540b-b1f9-0c86a5a0a37c | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Elastomeric Bearing Strip
66a8a676-605b-5a8f-897b-3291e81bc574 | note | Reference - IFC Drawings
f9cdb6e1-e0f7-5e34-afcf-bda18d20fce3 | note | Acceptance Criteria - 10mm THK x 100mm wide continuous elastomeric bearing strip to bond to beam flange prior to installation of precast barriers.
37d5a3f7-8f84-5797-8d79-394bb994f414 | textbox | Enter: Teambinder Material Approval number
c290f0e6-20cc-5539-9bc8-41d4ba85115a | note | Method - Document Review
85ea675f-df3c-5ec1-b2b5-9a03bddd1e74 | note | Frequency - Once, for each product
1585b4ec-8193-5741-b755-c2cf320058a2 | note | Category - HP
b81cbd7f-d5e1-5a21-afa9-a9a45ec55dca | note | Responsibility - Nominated Authority
58dd343c-68a7-569c-9a19-613bef03adf9 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Precast Barrier Brackets, M16 4.6/S bolts with nuts and washers, 5mm/10mm glav shim plates
2939de86-a3fa-584d-b6ce-de2d107f72a4 | note | Reference - IFC Drawings
9cb74996-2937-5db1-a18d-3a91a926d7cf | note | Acceptance Criteria - Bespoke brackets to suit flange width as per IFC drawings to be inslatted in contact with the underside of the beam flange.
1f0b1adc-d1e0-56ae-a3ae-097c2de860f2 | textbox | Enter: Teambinder Material Approval number
b556dd2b-632a-5a0e-993e-7957c8364fea | note | Method - Document Review
0bb5b0a3-9793-5274-8400-0d7e2cbeb186 | note | Frequency - Once, for each product
4381af9f-d511-58e6-ac2b-d58617b52f9c | note | Category - HP
aa3bd952-452e-5ebc-ad97-450ca3359480 | note | Responsibility - Nominated Authority
65bbc7f9-7995-5e77-9a0f-07ffee4ef634 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Hold Down Bracket - M20 Nuts, Tapered Plates, 150 x 32mm thick plate Gr350
b913b6b6-ddc5-529c-821e-6930d17981f9 | note | Reference - IFC Drawings
33ff2567-101f-5ec8-bc32-fb6f9c234521 | note | Acceptance Criteria - M20 nuts, tapered washers and plates to be installed as part of the assembly of the hold down brackates of precast barriers connection into the precast beams in accordance to IFC drawings.
852ea314-9705-59d3-adcc-308c3d008b42 | textbox | Enter: Teambinder Material Approval number
e8eaf077-0233-5f91-b057-d3598611aca4 | note | Method - Document Review
6f6c1555-cff2-5f06-9abc-679c75bf3fe2 | note | Frequency - Once, for each product
983dc2fc-c529-5ca7-933c-bd98fd9c35fd | note | Category - HP
b8f68ede-a9b0-5b52-a2c1-7fc388b72c94 | note | Responsibility - Nominated Authority
7abe6a80-1ea1-5381-839c-bbb9ee3629db | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Precast Elements
4c6553e4-1966-55a3-95e8-50ce63eb555a | note | Reference - IFC Drawings Section 610
16ec99ba-de25-5f7f-bd9e-44e7afc18fb9 | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
3f744de7-11a9-57ba-b890-2cf4e5b5c049 | note | i. Certificate of Compliance / Birth Certificate
74b7c8a3-7434-508b-b28e-f5479562f75e | note | ii. Compressive strength test results
f6f822c3-f74b-52c4-8194-2308df2a5ce1 | note | iii. Precast Lifting Design
0c59042e-48a4-5458-bbf8-f1a5fb203978 | note | iv. Pre-pour check sheet / ITP
c9497311-a45a-5820-bb4c-40a0a5bf8cfa | note | v. Post-pour check sheet / ITP
dc2a52ce-f902-565a-a5df-34e5ba929b35 | note | vi. Covermeter check record
55d516d3-b97e-5b8d-8af8-e0ff23794623 | note | vii. Record of dimensional measurements
05198224-5e00-5991-b912-3628117d72cf | note | These documents are typically stored in a MDR Lot in Team Binder.
61bb9251-d79a-5697-be76-1799163df13c | textbox | Enter: Teambinder Material Approval number
2b343054-ea68-5fa7-86fd-b30b08d68223 | note | Method - Document Review
10b9dedf-d5ec-5cbf-a350-726656a69a8b | note | Frequency - Each element
d9e162f4-13dd-59ae-9e6a-f8226cd9b0d4 | note | Category - IP
1e5d89bf-9a37-5b01-8b08-d2da37ae2e7a | note | Responsibility - PE/SE/SPE
9c515245-a5a5-59e3-bd31-2a6cba2aff2d | note | Verifying Documents - This ITP Signed Off
| section | 4. Pre-installation Activities
| checkpoint | 4.1 - IFC Drawings
1ffd80a5-00d9-5f98-a58b-c6a77a7480e4 | note | Reference - MRPA Quality Management Plan
132a78b7-e855-540e-9b39-17262ec6a80d | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
77063c3b-2ba9-550f-bf97-57979ff9b658 | note | Method - Document Review
62e67a0d-4bda-5bbd-b16e-1c82cdd1fd9c | note | Frequency - Prior to starting Works and at regular intervals
f837f650-69e5-5bba-9fcd-d4a55e8ba162 | note | Category - HP*
b209af74-996f-57fc-b32d-380a2f25938c | note | Responsibility - All
debf717a-594b-5423-82f7-5af47ed31c39 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out of Precast Elements
b0ef3974-93be-54cd-bf1c-1b4e4604d3c5 | note | Reference - IFC Drawings
d52e716e-3b9d-512d-a9e5-28392c34a64c | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
8b59715c-4a06-5ae8-ad15-1b8a71048689 | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
2a995e7d-507f-53ba-ac5c-69cecfa87df8 | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
1a592f42-1aa8-58c6-bf94-e6bef7f15681 | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
34489e0d-468e-53ee-801f-54554f74aee3 | note | Method - Measure, Visual
b07938d7-6310-5334-a0c5-9cb93bb004fa | note | Frequency - Each element
1f772e2f-7613-59f7-abb3-ccd44e2e1743 | note | Category - IP
07dda973-2d00-5f6d-a694-02fdce214e69 | note | Responsibility - Surveyor, SE/PE/SPE
9fa81476-d5d1-5910-a320-92d7bf88427a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Precast kerbs roughened surface
d809160f-6812-5b3f-bb42-b6fdf0e762f1 | note | Reference - IFC Drawings Section 610
0bc09890-1ff2-57ab-9b5a-7ca6704a4063 | note | Acceptance Criteria - Roughened surface means concrete surface shall be roughned as construction joint in accordance with IFC drawings and VR Section 610.
8e3f707a-1e7c-57d3-b3e9-53b19fe3211b | note | Method - Visual
94489689-023a-5e2b-88ee-b58089cfee1c | note | Frequency - Each element
7c0abca0-efd5-52ca-be7c-d0ce314851de | note | Category - IP
860cb8d8-c683-53c3-887c-16ed72c8858c | note | Responsibility - Surveyor, SE/PE/SPE
3b2d15d2-dbab-5cab-9214-78add4403299 | note | Verifying Documents - This ITP Signed Off
| section | 5. Installation Activities
| checkpoint | 5.1 - Precast Handling
ebc09068-24bd-5bde-a86b-7727710e18ea | note | Reference - IFC Drawings Section 620.07 Crane Lift Study
ba12bad3-0a90-5268-b688-797929577a85 | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using approved lifting points in accordance with the Crane Lift Study and Precast Beams Certified Lifting Design.
286946f6-fec7-5c84-8086-a0333395a3e3 | note | Method - Visual, Document Review
5338fc72-b227-53ec-9a45-02b321c98352 | note | Frequency - Each element
d0a57a70-97e5-58a8-98fd-acfeff72f81c | note | Category - IP
267ea1e7-3882-5078-b717-f075bc94f45c | note | Responsibility - SE/PE/SPE
099239eb-7881-5394-85fb-6ecc3709738f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Precast Kerbs Placement
6e6d98e9-fab0-544c-bf4d-19f7539264db | note | Reference - IFC Drawings
8d143b99-3c99-51cc-868f-1d5f8610fb79 | note | Acceptance Criteria - Precast kerbs shall be placed onto position and orientation and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
c5c7bdd3-c745-5c93-b9ca-d91431fd96d8 | note | ○ Precast barrier brackets installed as per IFC Drawings.
bf87f50c-f00d-5b39-94a0-d0a0a9ffdc79 | note | ○ The nominal gap between precast elements is as per the IFC Drawings.
258cc9f2-2433-5316-8093-3380ba6f4cf9 | note | Method - Measure, Visual
1bd78147-fa0d-5334-8228-d62aff993513 | note | Frequency - Each element
d260de7d-3f7d-57f9-9e95-f45eb4843d6d | note | Category - IP
314c7ae6-c457-547a-a6a6-efe4c9903c4c | note | Responsibility - Surveyor, SE/PE/SPE
2fb974ec-1411-5133-a629-507708947993 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Hold-Down Bracket Fastener Tightening - Snug Tight Condition (4.6/S)
876fb4ec-a0dc-54a8-ac7d-9bcb88fac419 | note | Reference - IFC Drawings
7460482e-128a-5845-ba8f-96b6040f67a3 | note | Acceptance Criteria - Place washers, nuts, and plates onto the embedded thread as detailed on the IFC Drawings. Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
39f5c2c8-3645-5ac2-94a0-f0d536e46075 | note | Method - Visual
68698097-7c11-595c-859e-1c6cae650077 | note | Frequency - Where applicable, each bolted connection
b036d8e3-793e-53c5-b047-e1c997b28dba | note | Category - IP
019f7b27-8642-5ff5-87ca-62f8bd9e9619 | note | Responsibility - SE/PE/SPE
5440b84f-35b1-56fd-aa03-df80cf26ac3e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Precast Traceability
4a3a06f7-e73e-5259-acd5-71c360120c66 | note | Reference - Section 620.09
1d8cec5b-bf99-5182-93f1-d298a8c4405a | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
df0555a8-9699-5aa4-8561-1df169d47663 | note | Record: The final location of each precast element, showing individual ID and date installed.
831d5685-1ef2-5649-9ce2-6bb7f6bf79f3 | note | Attach: Lot Maps showing beam individual IDs
67c91a3a-94ce-5c1a-b9f7-66594a0774d0 | note | Method - Visual
6638cd52-ab2d-5b82-84ce-0f3d411f1d1b | note | Frequency - Each element
57063c4a-d7f1-554b-88ec-d3c8b72c10d2 | note | Category - IP
ef9835a9-c244-5a49-8c31-2719edffc2e5 | note | Responsibility - SE/PE/SPE
657f3c3d-20d8-5bfd-9935-97463107e697 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-installation Activities
| checkpoint | 6.1 - As-built Survey
d11fc2fa-ffca-5eec-84d0-687a17b6008f | note | Reference - IFC Drawings Section 610.47 VR Table 610.472
62242614-0a27-52cb-badd-015443d7f2ca | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
9cd90803-95cf-5131-a385-5bc36b364061 | note | Attach: Survey As-builts / Survey Report
72fcef58-744f-508a-b60f-d9112e41c1f1 | note | Method - Document Review
1db1a408-8411-52c8-92e9-df4a1a49f017 | note | Frequency - Each element
8e1e1489-e137-5206-9ecc-db7ad909be71 | note | Category - IP
59e1d50e-9b9e-5761-b6d8-33ab59a7356f | note | Responsibility - Surveyor, SE/PE/SPE
3c69b0d9-9d90-5d9f-b5d6-81a946015977 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
285783b6-a416-58d4-a906-057d92d7ce18 | note | Reference - MRPA Quality Management Plan
39f5a29c-9207-5c69-9644-021cb56f94c9 | note | Acceptance Criteria - MRPA Quality Management Plan
50c3e5cc-63f2-5a33-9a7d-9fc3a1e450b6 | note | Method - Document Review
56f4b1c2-da58-5988-b429-05b69e3319e1 | note | Frequency - Once, prior to closure of this lot / element / Work area
9065ea1c-f578-5f81-a600-690c37394511 | note | Category - HP*
64f71c31-9d89-5443-8490-36e90fa79c79 | note | Responsibility - SE/PE/SPE
96b27116-b590-5ed2-9420-0145cc83e171 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
542b16ae-3197-568e-a572-74eaf9c62d55 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3e8a3bc8-1e8a-562d-a681-5c1f09c9d563 | textbox | Name:
ad9e0f19-8e59-5383-baa0-826b1631adef | textbox | Position:
9a2ec432-8dd1-5754-8007-17a51224a7ac | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-098-STR-BRUNT-Steel Structures Installation | itp | ITP-098-STR-BRUNT-Steel Structures Installation | 85153149-0c7a-43ea-86ce-3bf9cac6bef7
| section | Referenced Documentation
| checkpoint | Reference Documentation
34662a2c-e8dc-5863-b03a-489a27414636 | note | Document Title: ITP-098-STR-BRUNT-Steel Structures Installation
dfdc30ae-27b8-5343-9764-a4173634f1a8 | note | ITP Description: Steel Structures Installation
2507b9ef-2d85-59bd-8840-48381ff354de | note | Discipline (e.g. CIV/STR/RAIL: STR
29a42d55-20bf-5de4-b839-d723663bf00b | note | Revision Number: 0
37f7b9c8-4f7a-5c2f-be16-1530d3a70350 | note | Revision Date: 26/10/23
c734ce49-4d40-556c-9dc9-22c9f7b818a2 | note | ITP created by: Yasna Naicker
5a24f6a3-652b-5dd4-b73f-0f89d13a9c16 | note | ITP approved for use by: Jon De Castro
fc5ff356-55c3-5719-8be4-83ccf8cb5b89 | note | 1.1 VR Section 610
71925593-84d6-5cd0-80c4-c765312b0bfc | note | 1.2 VR Section 630
57cd91a3-c665-56f6-b84b-32a62a731bf0 | note | 1.3 VR Section 631
ca2a3ea0-a065-5d92-90df-47631e707ac6 | note | 1.4 IFC Drawings
577e4cac-5207-500a-a48d-e4de08e8f83a | note | 1.5 AS4100
e40b6743-9e5a-5840-9c5a-293412d40d4e | note | 1.6 AS5131
| section | Preliminaries - Materials
| checkpoint | 2.1 - Structural Steel Components
d12cc957-6297-53d8-bf6f-b98c4d0ef37f | note | REFERENCE - IFC Drawings MRPA Quality Management Plan
8427456b-bb22-5c25-910d-c897e63a3934 | note | – – – – – – – – – – – – – – – – –
cce51a50-6b48-5a12-9e40-e51b77fd67c6 | note | ACCEPTANCE CRITERIA - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. Typically this consists of but not limited to:
bb81c751-20ba-5d28-b6fa-2892f27806e6 | note | i. Certificate of Compliance
035b19d8-451a-57c7-a295-a0d31bfa706f | note | ii. Completed Fabrication ITP
49e19ed5-c79a-5913-a7f6-566ee02b79a8 | note | iii. Weld Procedure Specifications
69215250-2a62-539c-92ae-c71a1ff394bd | note | iv. Weld Procedure Qualifications
3846c117-2922-5565-ae2b-34431e241520 | note | v. Welder Qualifications
79956f45-9e2c-5157-aeeb-734c1aac4061 | note | vi. Material Certificates and traceability
09d5dc47-44c0-5390-b099-672ea66bcc40 | note | vii. Quality Assurance check sheets
ba982228-ebe9-5e4f-a534-9dc643ca96ad | note | viii. Welding Consumable batch certificates
d4e8e48b-77a3-5725-94e8-fb3d61eafaa2 | note | ix. Coating certificate(s)
7ccbafc9-0033-5942-b1a8-0205b18f6a48 | note | x. Non-destructive Testing (NDT) Reports
ab9c30ab-29c7-552d-bc90-2bd6e1f348e1 | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
d620a35c-4294-5e0d-8806-544ac45a0a19 | note | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
0875204d-8b94-512b-a354-6c3ff94dd781 | textbox | Enter: Teambinder Material Approval number
bd59517a-f6fa-50f2-befb-f22ebe375fa2 | note | – – – – – – – – – – – – – – – – –
cd604e66-71a8-51c6-b6bc-cd397f22a17c | note | METHOD - Document Review
99ffcc92-3990-5b7b-81bb-347491fde723 | note | – – – – – – – – – – – – – – – – –
ae9f3ec2-145d-517e-a079-8d4b9638ffc0 | note | FREQUENCY - Each component
6ad538f9-ea8e-5f94-9bfe-dfcff3dd8ca9 | note | – – – – – – – – – – – – – – – – –
797540ce-a70f-5e69-b77b-6508cb2337a3 | note | CATEGORY - HP
68113837-eb2e-5848-933f-68c9fcc59a1e | note | – – – – – – – – – – – – – – – – –
0eeed4b3-5c8d-5d11-8edc-9d10dba5d60b | note | RESPONSIBILITY - Nominated Authority
1cdaa802-48c3-542e-b3bb-59b10592025a | note | – – – – – – – – – – – – – – – – –
7d573c97-22c7-58eb-81f3-d29c2a08367c | note | VERIFYING DOCUMENTS - Conqa HP Release
79ca9408-b9d2-58f0-8a81-b491632e8296 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Fasteners
ffde4772-1d02-5139-90f6-e86563ac8cea | note | REFERENCE - Section 630.20 IFC Drawing
ccb1b35e-f4e6-50e4-9ea5-c1ab3c1f93ec | note | – – – – – – – – – – – – – – – – –
662ceef2-b53c-5510-a805-e4546234030a | note | ACCEPTANCE CRITERIA - Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
dad92b61-86cb-5249-880d-582a44387352 | textbox | Enter: Teambinder Material Approval number
38013e6b-399a-5ce3-a023-ac135966421c | note | – – – – – – – – – – – – – – – – –
435cf751-f808-5040-931c-909faaba6fa0 | note | METHOD - Document review
5089b8fd-032b-5e50-9508-327dc23fc494 | note | – – – – – – – – – – – – – – – – –
df2b961b-1fd4-5cee-b551-ba3c2f8cab29 | note | FREQUENCY - Each component
2796812f-9b8e-561b-a498-7a7c057c22bb | note | – – – – – – – – – – – – – – – – –
283488d4-a6ec-52f3-b421-edf29db8e4a9 | note | CATEGORY - HP
fafe347d-e407-538d-bff9-27cfb917246b | note | – – – – – – – – – – – – – – – – –
7db6cfd6-b86d-5d07-8d01-fce1ed2e6430 | note | RESPONSIBILITY - Nominated Authority
1ca9a70e-2479-5622-8f09-439087c9296b | note | – – – – – – – – – – – – – – – – –
0e003d5b-8ca3-5c29-a235-5c81c60e7dda | note | VERIFYING DOCUMENTS - Conqa HP Release
b7231f61-ea49-5968-a40f-f846499a72f9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Base Plate Structural Grout or Mortar
5d4d9266-26f1-51ca-b4b6-f3d659c37f03 | note | REFERENCE - IFC Drawings Section 610.33
8124c706-92dd-570c-bd67-031883ff7954 | note | – – – – – – – – – – – – – – – – –
3f6531a3-6c3d-51fb-9194-5242dbd177a2 | note | ACCEPTANCE CRITERIA - Product to be selected based on the following criteria:
be6c67ee-6e53-56fb-91ac-dd9c5b9c1f87 | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
d80a4c9d-4eee-5cf0-af40-5ed84d28553f | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
f0df3ecb-7659-5665-a153-f35cb4f215bf | note | iii. have a flowable consistency
a44704ef-840c-5802-909b-b3c3091eb267 | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings
6da42729-9c9f-5d88-b3e1-08445ca5e26f | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
03a79b59-9451-52ec-b9bd-0a0c2496685e | textbox | Enter: Teambinder Material Approval number
f798b0f5-021a-5263-a49f-c1845b5a6fa0 | note | – – – – – – – – – – – – – – – – –
a2164432-7640-57c2-9dd2-c2f412859084 | note | METHOD - Document Review
879fd9ac-2c98-579c-a354-4edbba1b59c1 | note | – – – – – – – – – – – – – – – – –
c39f19ce-8c25-59a1-98fb-0bc05335840b | note | FREQUENCY - Once, for each product, prior to placement of product
3837e977-e197-5f96-bb13-5ddb684dd258 | note | – – – – – – – – – – – – – – – – –
6cb3e1b4-3ce7-5685-9732-953e13e16340 | note | CATEGORY - HP
89ef77b4-5657-5429-a13a-ae5e735e7218 | note | – – – – – – – – – – – – – – – – –
32bddf60-56b7-5078-b37b-b6267e91f30e | note | RESPONSIBILITY - Nominated Authority
fa7e2a24-fff8-50e3-a2ab-15497894076e | note | – – – – – – – – – – – – – – – – –
8e7b6ab5-69b7-5172-9f61-697509a6655f | note | VERIFYING DOCUMENTS - Conqa HP Release
3308e52f-d337-51ac-bf52-2a04213048bc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures
| checkpoint | 3.1 - Handling, Transport and Erection of Structural Steel Element
d27a40d0-a346-5dd8-a34c-ba0158a9eaad | note | REFERENCE - Section 630.09
383874ea-f8e0-5ec9-8cd0-b41412c24718 | note | – – – – – – – – – – – – – – – – –
a0c21ae6-cc15-57d2-992c-a6717c129204 | note | ACCEPTANCE CRITERIA - Methods of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
f3a8d294-b1f5-5912-8681-dd3eed1321f9 | note | An installation methodology and ITP in accordance with AS 5131 shall be submitted prior to installation. As a minimum, the installation methodology shall include the following procedures below, when appropriate:
1edf5a82-2181-59d1-8a0a-784e682d23c7 | note | (a) Lifting procedures for each component; transport to and handling on site
fe3ab868-ca1b-5db6-be72-bd62053355da | note | (b) Bolt tightening procedures for snug tight bolting
d332ad62-19b2-5ddb-9d09-6be76ea98756 | note | (c) Procedures for grouting of base plates
9346d4a5-c53a-5259-9483-2a706b99e5a3 | note | (d) Procedures for ensuring that components are erected in the correct sequence and position.
a819b56b-ca7a-514a-a67f-88302c5e12d5 | note | Attach: Subcontractor Installation ITP and Procedures
11e3b0dc-0b95-5bdb-b3dc-8382fd7c3dae | textbox | Enter: Teambinder Approval number
3d778556-7c69-50d3-a5f6-a4baecb72b79 | note | – – – – – – – – – – – – – – – – –
a158c0f4-388b-5845-bd1b-daa2001e65ce | note | METHOD - Document Review
1f6ce1db-38c3-5864-9437-8cab7dcd2fee | note | – – – – – – – – – – – – – – – – –
72267111-9c28-5469-a7ee-4acc9ab20626 | note | FREQUENCY - 4 weeks prior to installation
02852b98-6957-5b11-b418-39d3fba7b268 | note | – – – – – – – – – – – – – – – – –
db787b9f-a60f-51af-821b-4e8987538311 | note | CATEGORY - HP
1fa1e7cf-0f41-5646-ab60-1869b625753b | note | – – – – – – – – – – – – – – – – –
06c0f30f-5ba0-5a84-910d-b205cd1f54a6 | note | RESPONSIBILITY - Nominated Authority
4e280d15-6967-5807-b8ea-e8b388b346c3 | note | – – – – – – – – – – – – – – – – –
d7a9a511-2e87-5112-b479-923b3e5cc451 | note | VERIFYING DOCUMENTS - Conqa HP Release
962383fd-98ff-5e44-ba28-e0c33709d1dc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-installation Activities
| checkpoint | 4.1 - IFC Drawings
0b0747df-4f26-5bc6-8d15-6987c758b5a3 | note | REFERENCE - MRPA Quality Management Plan
cbe95727-6b6c-58d5-a3e9-b8fcc53946dd | note | – – – – – – – – – – – – – – – – –
c2cee5c9-192b-5ff2-aae7-62219c5537af | note | ACCEPTANCE CRITERIA - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
f2c220da-66c5-529c-bd67-badcbd88c209 | note | – – – – – – – – – – – – – – – – –
5d26d7ce-0f68-5d2c-8ffc-24b60e83b76d | note | METHOD - Document Review
def93e42-3b57-5581-bde7-f7b07cd3c054 | note | – – – – – – – – – – – – – – – – –
1893ecfe-f6ed-55db-a41f-03684e596901 | note | FREQUENCY - Prior to starting Works and at regular intervals
be50e3e6-8420-563a-bc96-8403ce5fee61 | note | – – – – – – – – – – – – – – – – –
4f361322-61ca-5ac7-b6a1-8a822dc4ffe4 | note | CATEGORY - HP*
5cf5182a-be93-5b92-bbaa-33b5b3b2fed8 | note | – – – – – – – – – – – – – – – – –
ed41d510-f122-5abd-8717-f7ae1282224d | note | RESPONSIBILITY - All
abf11074-5ed2-5ea4-ac93-f8a0683769fe | note | – – – – – – – – – – – – – – – – –
07529e00-75f6-5c74-920c-1eb8540a0258 | note | VERIFYING DOCUMENTS - This ITP Signed Off
e82e362c-c0c9-563a-9f05-62e9d4cdef28 | date | Date Completed:
| checkpoint | 4.2 - Materials Inspection Checklist
5fb7af4f-83e4-5808-bc07-fa51e93ccf51 | note | REFERENCE - IFC Drawings Section 630
9e527713-40b0-57f2-b98d-b9452d5c603c | note | – – – – – – – – – – – – – – – – –
834bd2c8-7ef4-52dc-ab0c-9ef368ed44f7 | note | ACCEPTANCE CRITERIA - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
59b435f7-d076-5d10-9d89-6a92720769ef | note | – – – – – – – – – – – – – – – – –
8bd5083b-2537-5579-bb0f-9e823634ced7 | note | METHOD - Measure Visual
0f0d0339-d6c4-56ad-8b71-72f3c2f57ca5 | note | – – – – – – – – – – – – – – – – –
87f9271e-7671-5a6b-b1e5-1d38bca5a67f | note | FREQUENCY - Each component
93853d64-a4df-56cf-b5bd-72c45c11d830 | note | – – – – – – – – – – – – – – – – –
2ec0e1df-cb27-5490-9023-4e13a9c03fc2 | note | CATEGORY - IP
b0776098-7d97-5a72-965a-b5ecc6307dec | note | – – – – – – – – – – – – – – – – –
5d60f789-0a76-540c-bc88-60539cfdf286 | note | RESPONSIBILITY - SE/PE/SPE
2d485422-d239-5eee-8827-516eec8ce6c0 | note | – – – – – – – – – – – – – – – – –
7cf11004-655a-5ec7-9b89-37fbab752649 | note | VERIFYING DOCUMENTS - This ITP Signed Off
1bad5356-df43-5c8d-91a8-1fd047fec6c3 | date | Date Completed:
| checkpoint | 4.3 - Materials Inspection Checklist
c208bb21-162c-59d9-9435-41bdb4874696 | note | REFERENCE - IFC Drawings Section 630
9af8b009-9c41-56aa-ad2e-f78ebcba7c13 | note | – – – – – – – – – – – – – – – – –
eacf6790-a8b4-5494-8a27-e9e94928a4dc | note | ACCEPTANCE CRITERIA - Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
a0141429-04c1-52d2-8767-4444ae7373a7 | note | – – – – – – – – – – – – – – – – –
8b05b40d-eb98-5e49-877e-b25f6c376141 | note | METHOD - Measure Visual
f48ef67a-e814-515e-b693-e3907d33086f | note | – – – – – – – – – – – – – – – – –
47f0a84c-8050-5d87-8542-34d143eb3b14 | note | FREQUENCY - Each component
c90548c4-4fa4-5aae-b120-d8a9879a7055 | note | – – – – – – – – – – – – – – – – –
d9c473a3-248c-5d3f-badc-81fa68729bef | note | CATEGORY - IP
63054d32-bf3d-539e-b6e7-09e7699b7b11 | note | – – – – – – – – – – – – – – – – –
259cc3bf-7683-5d9b-87e3-0afecc6f12d3 | note | RESPONSIBILITY - SE/PE/SPE
addcc11f-bdb6-50ee-998b-fe18ef779e80 | note | – – – – – – – – – – – – – – – – –
15905d7b-534d-5361-bbef-7852f579083f | note | VERIFYING DOCUMENTS - This ITP Signed Off
f91764e0-8ca3-564f-9ca8-2401683bea90 | date | Date Completed:
| checkpoint | 4.4 - Materials Inspection Checklist
f7e3d082-919c-5ba1-ba3a-8f6ee8ecd576 | note | REFERENCE - IFC Drawings Section 631
e9e280fc-a96a-5ef4-8ff3-7462cec6be68 | note | – – – – – – – – – – – – – – – – –
7038a6af-ae89-59b2-ad59-77979a4ff616 | note | ACCEPTANCE CRITERIA - Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
d4e0122f-5130-5861-8236-4990206d30ac | note | – – – – – – – – – – – – – – – – –
2d53ce70-66a2-5d96-a1cb-90a8e7f9d0e4 | note | METHOD - Measure Visual
bb24a248-18e3-5ef5-8c18-696c256c020e | note | – – – – – – – – – – – – – – – – –
0de5082f-63c7-5d57-a7ab-abf52e859b51 | note | FREQUENCY - Each component
e60539f8-7a25-5dd0-b6c1-1152cf4be142 | note | – – – – – – – – – – – – – – – – –
3c8f62d5-d3ef-5892-aba8-1b0bf0176530 | note | CATEGORY - IP
680144fc-a0ab-531f-8270-aaec44db9e5a | note | – – – – – – – – – – – – – – – – –
cab59f37-3baa-5c1a-8245-63755d6093b2 | note | RESPONSIBILITY - SE/PE/SPE
d5bb2134-c735-574f-914e-403b3341c57e | note | – – – – – – – – – – – – – – – – –
36dc0071-63e1-5998-a304-e6cf564b1815 | note | VERIFYING DOCUMENTS - This ITP Signed Off
21bac8e5-a0e6-5ee3-96fa-6977fc44e69d | date | Date Completed:
| checkpoint | 4.5 - Materials Inspection Checklist
93377102-76ee-5ce7-9055-7463a812dac7 | note | REFERENCE - IFC Drawings Section 631
de3ab3e0-ef2c-5cbd-a017-626639df6c4e | note | – – – – – – – – – – – – – – – – –
27f6f389-edca-52f3-a6af-8d282184bc48 | note | ACCEPTANCE CRITERIA - Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
060d95ac-1ea1-58e8-93cb-333ad99b00e9 | note | – – – – – – – – – – – – – – – – –
98400bb4-becd-5578-bc27-74e1494795fd | note | METHOD - Measure Visual
6b6b7aac-8f32-563a-9173-04fba737e30d | note | – – – – – – – – – – – – – – – – –
40dde489-7377-54b6-8693-3fa2f791d2a5 | note | FREQUENCY - Each component
26be6d6d-bbc0-5a20-961c-6347e220fcaf | note | – – – – – – – – – – – – – – – – –
2d539992-40cc-51bf-a6cf-e4ac02f6b195 | note | CATEGORY - IP
a113016a-bb79-5481-88bf-c1bbc42a8296 | note | – – – – – – – – – – – – – – – – –
ce7bc568-3cfe-5c4b-a137-1127a9c39822 | note | RESPONSIBILITY - SE/PE/SPE
2ca5439e-265c-5be9-b20e-96adb1c716a8 | note | – – – – – – – – – – – – – – – – –
bc8303af-b58e-5449-a979-096b6ef6d3f5 | note | VERIFYING DOCUMENTS - This ITP Signed Off
1eda08f8-838c-5c1a-a603-c2b7ac8135b4 | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 - Bearing / Mounting Surface Preparation
0e789896-b8ba-535c-a362-33b6bd1300cc | note | REFERENCE - IFC Drawings Product TDS
501e1e3b-b53d-51f6-ace0-a37571de72ff | note | – – – – – – – – – – – – – – – – –
e3c9a018-bca9-5e3a-a8ee-5cb94eae46c5 | note | ACCEPTANCE CRITERIA - Ensure the bearing surface is clean and free from any loose particles that will prevent solid seating of the parts.
34879e4e-2ac8-5e06-aba7-023a1b675620 | note | – – – – – – – – – – – – – – – – –
9b4a8e87-7f94-5a77-a976-e5e4d96b9662 | note | METHOD - Measure Visual
e091898c-5488-5acc-9b1e-e074761d4aee | note | – – – – – – – – – – – – – – – – –
3aa4c235-4167-5924-ba15-405e0d1c6b07 | note | FREQUENCY - Where applicable, each installation location
c3c46688-740c-5b37-9788-8dcb40fd2d66 | note | – – – – – – – – – – – – – – – – –
5613961e-de34-5d39-9826-f846861a4ac0 | note | CATEGORY - IP
232726c0-fdc4-53d6-a10a-296bd1888166 | note | – – – – – – – – – – – – – – – – –
2185bdd6-7fb3-5ff7-8484-593948022bb3 | note | RESPONSIBILITY - SE/PE/SPE
1db94c06-082b-5728-a805-42579b4f7a00 | note | – – – – – – – – – – – – – – – – –
b0ab2024-1744-5174-9aa7-1e092332c665 | note | VERIFYING DOCUMENTS - This ITP Signed Off
7c1babf2-649c-58c1-a27e-116a1c859a15 | date | Date Completed:
| checkpoint | 5.2 - Structural Steel Handling
3e567892-357c-563b-8e8f-de4e7af10a71 | note | REFERENCE - Section 630.09 Section 631.14
c85104d8-81cc-5d33-8832-b75a4362c258 | note | – – – – – – – – – – – – – – – – –
5051292c-cfc4-5657-94b2-a2c1fe4fe2ae | note | ACCEPTANCE CRITERIA - The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
5b61d416-2e98-5dd6-85ab-ee35c742bb17 | note | – – – – – – – – – – – – – – – – –
fa7a9c10-955d-56f0-89c8-8f1738ac01c2 | note | METHOD - Visual
0416a4d9-5ea3-523f-ba3d-0c04ed633a6a | note | – – – – – – – – – – – – – – – – –
2b61a678-7d09-5b95-9eb3-5e19340f90ac | note | FREQUENCY - Each component
34be7c39-8fa3-5e64-88b8-08c2c5418859 | note | – – – – – – – – – – – – – – – – –
6d08ec1a-773c-59f5-86d6-e9ca44b14404 | note | CATEGORY - IP
051a1b10-f57e-56dc-aa61-db83b74cf333 | note | – – – – – – – – – – – – – – – – –
ea0cadfe-749f-5bf3-990b-a374d8512b44 | note | RESPONSIBILITY - SE/PE/SPE
f9a27963-fa8b-578c-a582-bee2789ea545 | note | – – – – – – – – – – – – – – – – –
5d49bf35-b1ca-5a0d-a1ef-30c7b5b3db7d | note | VERIFYING DOCUMENTS - This ITP Signed Off
a9b83848-cb81-515d-9531-7eabe8882380 | date | Date Completed:
| checkpoint | 5.3 - Structural Steel Erection
96d0281f-00b4-5a9e-bbe3-8bcbfab49649 | note | REFERENCE - AS4100 AS5131 Section 630.12
a920ae30-650c-56c9-8671-4aa5da1bb12f | note | – – – – – – – – – – – – – – – – –
969a67f1-d4e2-5417-a52b-7b444fa998c7 | note | ACCEPTANCE CRITERIA - Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
94162bdb-9d12-5bc7-84db-6df1cf6e7bd6 | note | Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
c629888c-4919-57cd-91c9-09bcee043d8d | note | Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
9a63e1dd-7f8a-5ba8-bb13-73f120aa88e2 | note | – – – – – – – – – – – – – – – – –
dc58cf69-ee48-57b2-a5ab-17989f5133af | note | METHOD - Measure Visual
ab6bf258-661e-50b0-9341-621d3febb76d | note | – – – – – – – – – – – – – – – – –
ea143dd4-0aee-570b-b241-ee93379d431e | note | FREQUENCY - Each component
ed053b2a-2c32-59b9-a86e-dd21c1122478 | note | – – – – – – – – – – – – – – – – –
a47acbf8-8231-5927-8d63-b591cf1fd250 | note | CATEGORY - IP
08512e14-930d-5731-ae2c-c2801e2ab7d7 | note | – – – – – – – – – – – – – – – – –
9c582af9-4456-5947-a795-d2e2141dcc74 | note | RESPONSIBILITY - SE/PE/SPE
9cbc2a59-b67e-5bd6-a09a-19ecf95d98fc | note | – – – – – – – – – – – – – – – – –
307e9d4d-c98c-5ced-a551-5f90ec796438 | note | VERIFYING DOCUMENTS - This ITP Signed Off
20a93fa2-5476-5f68-b1bd-42a85e696181 | date | Date Completed:
| checkpoint | 5.4 - Fastener Tightening - Snug Tight Condition
446c6fbb-a224-5ab9-924a-41a222c5a61f | note | REFERENCE - IFC Drawings Section 630.09 Section 630.21
638d504e-695d-5e47-8513-a6e9839c2c4f | note | – – – – – – – – – – – – – – – – –
ac0429f7-133c-50d5-b7dd-216943b45888 | note | ACCEPTANCE CRITERIA - Place bolts, washers and nuts as detailed on the IFC Drawings. For posts base plates, the arrangement is to be (from the base plate):
0f0d74b5-9d05-53f7-944f-deb56a925ca9 | note | Base Plate
1db4c720-f9ec-5969-b170-ff5d7d8b0445 | note | Washer as specified
c8228126-3463-5c66-836e-2e62b0026541 | note | Lock Nut as specified
6035da28-f62b-5edc-95bb-93b8d890e502 | note | Nut
3807b419-0c4c-513b-95f1-6be9fa8a0ece | note | Bolt protrusion (1 clear tread)
d748e3bf-69ad-5b8f-93dd-bf0d881d363e | note | – – – – – – – – – – – – – – – – –
356dcf7d-745c-59d4-9a4e-4c5ec7e14a5b | note | METHOD - Measure Visual
46cc3394-aa2f-5e31-975b-71d9734220d6 | note | – – – – – – – – – – – – – – – – –
060d92f1-9e60-5fb3-8092-3a58adb82417 | note | FREQUENCY - Where applicable, each bolted connection
eefe02d5-91d9-5f86-ba23-439a3e9ef190 | note | – – – – – – – – – – – – – – – – –
4649ffe6-277d-5066-96f7-df80eb48272d | note | CATEGORY - IP
b040e8cc-7139-5c2a-a133-e54a2326f573 | note | – – – – – – – – – – – – – – – – –
8e3f6ead-888b-5b9c-b0e9-2e1f3c09f7b1 | note | RESPONSIBILITY - SE/PE/SPE
eac3fc5b-33bd-54d8-a80d-26615f8837d4 | note | – – – – – – – – – – – – – – – – –
8a9ba65d-512b-5de6-bfc3-e970ffbc933e | note | VERIFYING DOCUMENTS - This ITP Signed Off
ee239b03-6678-5e6c-b19b-a8c02db4f989 | date | Date Completed:
| checkpoint | 5.5 - Fastener Tightening - Snug Tight Condition
7bcd069f-7518-5da2-8801-5491d2b82b3d | note | REFERENCE - IFC Drawings Section 630
72627ecc-d6c0-54e7-997f-7ed200a895cd | note | – – – – – – – – – – – – – – – – –
fd2dd89f-22cc-57b1-aa6b-fe59b01fdc48 | note | ACCEPTANCE CRITERIA - Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter. Tapered washers shall be positioned if specified. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
1734c863-0456-5e12-9b7a-32b09c6af878 | note | – – – – – – – – – – – – – – – – –
11fa15e4-0b00-5145-8521-a524f7fe75df | note | METHOD - Measure Visual
e057671d-2f52-5efa-a829-6da6dde50b30 | note | – – – – – – – – – – – – – – – – –
45eb029d-0534-5cec-bf30-24f7e36dda76 | note | FREQUENCY - Where applicable, each bolted connection
46550688-afda-59e9-a143-85bd7d7fa7bd | note | – – – – – – – – – – – – – – – – –
d10186f1-ef06-503b-becd-cf48309557e8 | note | CATEGORY - IP
3dc9f963-f7e7-5d90-87ad-ce1d6162d92f | note | – – – – – – – – – – – – – – – – –
5bdfb178-3cdd-5f9b-8c5f-c7765e94b195 | note | RESPONSIBILITY - SE/PE/SPE
a418da65-bcba-5ee5-a6f8-203a3dfd8c10 | note | – – – – – – – – – – – – – – – – –
4757744c-770a-56be-9556-14fcdad76f39 | note | VERIFYING DOCUMENTS - This ITP Signed Off
b4b04292-6a78-540f-b481-e1f03bb8fa68 | date | Date Completed:
| checkpoint | 5.6 - Survey Conformance
cc5cd8c9-e9d5-5d1a-a14e-4642545c1169 | note | REFERENCE - IFC Drawings AS4100 AS5131
cbc2f8a0-e6b5-5e00-a47a-3c9d90bb89ad | note | – – – – – – – – – – – – – – – – –
71e8e720-8d44-5590-8a1f-501e61c17824 | note | ACCEPTANCE CRITERIA - Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
eceb2831-aaec-584b-8dd1-175e9b70fe91 | note | Departure from RL = ±10mm
c69944c2-9480-5ca6-81a4-c7474c5f893e | note | Departure from plan position = ±6mm
c85ea13f-4230-50c5-92b6-89100fd81617 | note | Departure from alignment = ±6mm
f91c5af2-9771-5c74-bf3f-733a3f80ebbb | note | Irregularities in alignment = 25mm in 30m
c7595bbf-3d32-5cfd-9076-b559fe57da21 | note | Projection of bolt = +25mm, 5mm
6501eb50-1e02-5929-8869-564a8d055321 | note | Location of beam = ±3mm
1fd9e581-d79a-5e23-9b82-3c1f9059903c | note | Location of column = height/500, 10mm max.
01b0830e-5665-5362-b9ea-91515a8e70f4 | note | – – – – – – – – – – – – – – – – –
298e9825-07dd-5340-b814-4af65ae2c199 | note | METHOD - Measure Visual
08ecb3a4-bbff-5b7e-85b4-da32c933ea3a | note | – – – – – – – – – – – – – – – – –
00cca3f1-c411-558d-97c3-d345b7374dee | note | FREQUENCY - Each element
ba9a753d-c78c-5d21-9ae1-adb1bebfece0 | note | – – – – – – – – – – – – – – – – –
a82ffa8a-1671-5474-acbe-c4779b1cbb19 | note | CATEGORY - HP*
8f6e2a69-d777-5a08-8a09-24d22eaf6424 | note | – – – – – – – – – – – – – – – – –
f2227a87-c969-5c81-989e-a9cd987b762f | note | RESPONSIBILITY - SE/PE/SPE Surveyor
6a4fae96-a571-5d8e-a968-58d091c73d17 | note | – – – – – – – – – – – – – – – – –
7074c312-390d-5db9-addb-32248dabce74 | note | VERIFYING DOCUMENTS - This ITP Signed Off
898e8e0c-319a-5f8f-93fc-5da6b103c14b | date | Date Completed:
| checkpoint | 5.7 - Base Plate Formwork Construction & Placement
63c3b994-bd0c-54f3-beff-bcdaa45bce98 | note | REFERENCE - IFC Drawings
369b360e-33df-52d5-86ec-e39bd2a1b054 | note | – – – – – – – – – – – – – – – – –
1fd67e50-ca7a-51e4-891a-c6f408505368 | note | ACCEPTANCE CRITERIA - Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
7e0ccd53-e2b1-5d9e-86a6-a3e1ce6bb115 | note | – – – – – – – – – – – – – – – – –
c055cff2-e691-51e9-9fd1-02766500182d | note | METHOD - Measure Visual
0d432557-14ce-5024-9cf6-82f1e0cdc0fc | note | – – – – – – – – – – – – – – – – –
cfd0c41c-e750-54de-bb74-bba4295f9607 | note | FREQUENCY - Each post location
9f7de8d7-b5d0-5c0c-a2d1-5b14ae89ed91 | note | – – – – – – – – – – – – – – – – –
77489d6e-44d3-54d5-8018-9ce7902ec19b | note | CATEGORY - IP
6cd4f9aa-c4ce-58c9-a431-b7c76d7ddce6 | note | – – – – – – – – – – – – – – – – –
6f608e35-f6d2-5aa5-b27d-c2f24b197894 | note | RESPONSIBILITY - SE/PE/SPE
545f4cb4-f572-5fad-b6c8-729261b72f07 | note | – – – – – – – – – – – – – – – – –
c9892bd5-2068-5803-88bb-4a9bed2c031f | note | VERIFYING DOCUMENTS - This ITP Signed Off
22742977-d776-5f41-b6ca-3a7db4f95061 | date | Date Completed:
| checkpoint | 5.8 - Pre-soaking Concrete Surface
95394d2b-67b2-5ac9-8fb1-deea89070b15 | note | REFERENCE - Product TDS
f05a9e05-2779-5e9f-a66e-0b2954345d89 | note | – – – – – – – – – – – – – – – – –
d265df97-805e-5d52-9352-b5afe0938e19 | note | ACCEPTANCE CRITERIA - Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS. Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
1ccc1e1c-eac5-5c7b-a365-c27a481d9695 | note | – – – – – – – – – – – – – – – – –
3ce03ef9-da3c-5660-b1fc-afc04f619a01 | note | METHOD - Visual
b099d011-5d4e-5f4e-95c0-e0abc17b1966 | note | – – – – – – – – – – – – – – – – –
299ede16-dd41-5423-82ab-0947419a697d | note | FREQUENCY - Each post location
6403945c-d27f-512c-bdad-4f21a642b94f | note | – – – – – – – – – – – – – – – – –
affe15e7-bbf7-5526-b834-822c6c28b2b4 | note | CATEGORY - IP
2cbf71ee-c784-5a63-9912-792766c19482 | note | – – – – – – – – – – – – – – – – –
985e0998-5733-5e06-b220-a4bad152a444 | note | RESPONSIBILITY - SE/PE/SPE
8fcd9111-6d8c-55e6-b539-02b8d9aaffa3 | note | – – – – – – – – – – – – – – – – –
4e0dffda-5174-5e61-908c-4ca4f26e964b | note | VERIFYING DOCUMENTS - This ITP Signed Off
ccc88bb9-c27c-5bed-9591-723cb594cddf | date | Date Completed:
| checkpoint | 5.9 - Weather Conditions
2d03b071-5502-57bb-bfb6-41bcee85befa | note | REFERENCE - Section 610.17 VR Table 610.171
138f181c-982f-519b-a809-e3f1db360119 | note | – – – – – – – – – – – – – – – – –
fc863d05-0c6b-51a8-a239-caa52ae7f571 | note | ACCEPTANCE CRITERIA - Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected. The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
68a37d5c-eb99-52c7-80d3-8600683f9b95 | note | Record: Required information on the Grout Pour Record.
854ce2e2-ed29-507f-9d60-dc4f69163dc5 | note | – – – – – – – – – – – – – – – – –
f462e305-28a8-5130-9776-4fe1f8fa4f57 | note | METHOD - Measure Visual
2daa8f8c-38a9-587c-842d-f2dabe9544e1 | note | – – – – – – – – – – – – – – – – –
dfaccf9f-c18f-5bf5-8319-93c9f7321909 | note | FREQUENCY - Each lot
54293279-26cc-574b-ac76-ab80f2d8cb3e | note | – – – – – – – – – – – – – – – – –
0c9e08b1-cad3-5949-a915-416aee7f8f54 | note | CATEGORY - IP
eb52ceff-53e8-51f6-a275-81ba15262fc1 | note | – – – – – – – – – – – – – – – – –
d23dc8c7-3323-5c09-ba9c-3ef505745a5d | note | RESPONSIBILITY - Supervisor SE/PE/SPE
34ba42c7-5334-5159-95ee-ddf540e820a3 | note | – – – – – – – – – – – – – – – – –
872b4a45-e25a-57b1-b023-823354d3f148 | note | VERIFYING DOCUMENTS - This ITP Signed Off
b519672b-7902-5be0-85d3-1e650d876c5c | date | Date Completed:
| checkpoint | 5.10 - Mixing Product
2c708bcb-ab1e-58f6-8246-65a732ac5590 | note | REFERENCE - Product TDS Section 610.28
564514f2-4c9d-59c4-b667-7a6b47806aa4 | note | – – – – – – – – – – – – – – – – –
1d94676b-7394-59be-be7d-738262eddf8c | note | ACCEPTANCE CRITERIA - Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained.
0940c682-bcf8-5c55-83d4-5a2540f341e3 | note | Enter: Required information on the Grout Pour Record.
ca9002b0-be64-5174-8c73-1364498320bb | note | – – – – – – – – – – – – – – – – –
999b3fb4-1092-5779-9738-f69831c96986 | note | METHOD - Measure Visual
304afcde-c310-5801-a4b2-156c80549c19 | note | – – – – – – – – – – – – – – – – –
01a77d4c-d79f-598f-88f8-009cad46a5c6 | note | FREQUENCY - Each lot
63ed60cd-6b15-5d1f-ae96-1e5cbc26af19 | note | – – – – – – – – – – – – – – – – –
fa79858e-ce25-5a6d-80c6-64bb213242fc | note | CATEGORY - IP
6c62b8d7-86c8-58c5-9294-55c7663f3f46 | note | – – – – – – – – – – – – – – – – –
acaf9ae2-f2fc-547a-b231-8da0d5f52559 | note | RESPONSIBILITY - Supervisor SE/PE/SPE
90a607b8-3470-52b0-bd38-1554111eae87 | note | – – – – – – – – – – – – – – – – –
ff0b1b5a-124d-5f87-b995-38c847e557b8 | note | VERIFYING DOCUMENTS - This ITP Signed Off
3860c7f8-61d5-5467-96df-fbdf2511277c | date | Date Completed:
| checkpoint | 5.11 - Product Testing - Compressive Strength Cubes
31a6bfcb-4db0-5b81-93fd-9d2714657df7 | note | REFERENCE - Section 610.28 Section 610.33
7ddd3d4c-04a0-523d-aa3f-238eab5d0de4 | note | – – – – – – – – – – – – – – – – –
899dfa0d-787e-5545-ad50-e93284fb1d40 | note | ACCEPTANCE CRITERIA - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
acad7e1f-133a-5a20-a308-59278c62d9da | note | Testing is to be in accordance with the following frequencies:
3e5b45c8-3d56-5c47-8669-8d359caa74da | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
d8e49598-388c-5a38-b33c-ac25c479d3d1 | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
cbf51382-b0c5-545b-b136-3fdaba2bbc9c | note | Enter: Required information on the Grout Pour Record.
38c4029e-0676-57d3-92f3-067c534f69a4 | note | – – – – – – – – – – – – – – – – –
03624736-7478-5411-94d6-4d8629b8f192 | note | METHOD - Test
c8c2efdd-a3e9-5528-a9c7-b1263443ae3c | note | – – – – – – – – – – – – – – – – –
03bdd0ed-3910-5faf-a96a-8bbd308e25ca | note | FREQUENCY - Each lot
f38f6945-257d-52a2-bdfc-6796b183c087 | note | – – – – – – – – – – – – – – – – –
8fc2d37a-7798-5e27-b122-cfcf988a8174 | note | CATEGORY - IP
e7ef5303-68af-59bf-8d7a-bfe2cb215de9 | note | – – – – – – – – – – – – – – – – –
b4582199-abab-53b2-9faf-d5f2e4daa9c6 | note | RESPONSIBILITY - Supervisor SE/PE/SPE
e22882e1-e220-5de6-843d-97a8b005fda5 | note | – – – – – – – – – – – – – – – – –
4e7e70a2-174d-5cad-9091-cc3ad93d1a66 | note | VERIFYING DOCUMENTS - This ITP Signed Off
30b8768d-5599-52f4-b07a-c6298b9dd9f3 | date | Date Completed:
| checkpoint | 5.12 - Placement & Compaction
7bea0f8e-e05b-5190-8350-c0211003dfdc | note | REFERENCE - Product TDS
a20b915f-1693-51a3-bde2-106493cbf2cc | note | – – – – – – – – – – – – – – – – –
a418aaca-cf03-5a47-93c1-0740042530e3 | note | ACCEPTANCE CRITERIA - All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used.
c6815a89-73c3-5bf0-b739-b9a38a18f677 | note | Enter: Required information on the Grout Pour Record
e5e92564-6e58-589c-983a-948830e1aa19 | note | – – – – – – – – – – – – – – – – –
f927a1a8-cf86-5e59-bd76-6bf0f06bd899 | note | METHOD - Visual
bf74cd4f-2254-50db-9190-40f0a9da10a3 | note | – – – – – – – – – – – – – – – – –
2f6d9aa2-0b35-5bbc-aae3-0e232a4ce0a9 | note | FREQUENCY - Each post location
6104bcef-b896-5a91-9f99-0796909c1386 | note | – – – – – – – – – – – – – – – – –
90603b6d-1f73-5dbd-8837-67820feceb37 | note | CATEGORY - IP
a0e8ed87-601c-5fb4-84a0-d87f1f9559db | note | – – – – – – – – – – – – – – – – –
f5981f3b-e085-5689-a71a-e18627ba212b | note | RESPONSIBILITY - Supervisor SE/PE/SPE
3b79fe88-1611-5150-b743-2cc6e6f6265b | note | – – – – – – – – – – – – – – – – –
de1cc68a-ce91-59aa-9bea-7ad88e6443fe | note | VERIFYING DOCUMENTS - This ITP Signed Off
14069751-ca0c-5f21-90e1-38232ed92f61 | date | Date Completed:
| checkpoint | 5.13 - Surface Finishes & Protection of Works
ebe274a3-44f5-5717-bae9-b65c4343ec15 | note | REFERENCE - IFC Drawings Section 610.17
fc55fba5-1f9f-5eac-95f3-c23c216f5e16 | note | – – – – – – – – – – – – – – – – –
46194280-c609-5b0b-b0c7-a34f0f1f23d5 | note | ACCEPTANCE CRITERIA - If shaping of the unformed surface is required, shape prior to the product fully hardening. All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
26d6e843-53b2-5f77-a044-42da686cb732 | note | – – – – – – – – – – – – – – – – –
14d14eaa-6ad1-559c-9b59-3ba669a940ae | note | METHOD - Visual
1b39fa09-db85-5ee7-a174-09c7f1c4a67b | note | – – – – – – – – – – – – – – – – –
81cde355-aac3-5c12-9741-8fd0e8a94888 | note | FREQUENCY - Where applicable, each post location
11884813-1033-50f6-8216-803bbec6f42a | note | – – – – – – – – – – – – – – – – –
db73cb77-ab5b-52bc-9fb6-59f85f2eb52e | note | CATEGORY - IP
3e675b80-2f14-5ef5-84f1-5ef4542ffe5e | note | – – – – – – – – – – – – – – – – –
74a3f4a4-0f59-5d19-9ec5-6d3c79883e7d | note | RESPONSIBILITY - Supervisor SE/PE/SPE
8de1d55b-d99a-5829-bef8-0b5d93a9f653 | note | – – – – – – – – – – – – – – – – –
fba50a25-d3dd-5063-9c8f-b77f8f1b4a82 | note | VERIFYING DOCUMENTS - This ITP Signed Off
cd24544d-29a9-5c06-a5ba-bfc07adffa1d | date | Date Completed:
| checkpoint | 5.14 - Curing
8a35586f-8dac-5061-8457-9d6c110b6a86 | note | REFERENCE - Curing Methodology 610.23 Table 610.231
876ced0f-1da7-58b3-87c8-3bca4243fc3c | note | – – – – – – – – – – – – – – – – –
f67bd7e0-5165-5f7f-be48-211acc70ff21 | note | ACCEPTANCE CRITERIA - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
b49d215f-024c-5858-a3ef-836e16dd25e1 | note | – – – – – – – – – – – – – – – – –
3be5a95a-0c61-57c8-8c43-b7ededce4f29 | note | METHOD - Visual
9c621a74-957d-53eb-83e0-3e7b3548458f | note | – – – – – – – – – – – – – – – – –
dd547d05-e9a2-503d-80ab-2cc34796b596 | note | FREQUENCY - Where applicable, each post location
c88bd440-2f47-53e4-b2bc-d4086dbc9311 | note | – – – – – – – – – – – – – – – – –
81b41381-d119-516b-b501-8f2f01c577a8 | note | CATEGORY - IP
38200632-6b34-5ea9-9f55-5e2f989b93c6 | note | – – – – – – – – – – – – – – – – –
08e1bef0-9cad-5646-86a3-d502826bdca6 | note | RESPONSIBILITY - Supervisor SE/PE/SPE
0ed0ca7e-1e86-5fa8-ab91-a16427c69d97 | note | – – – – – – – – – – – – – – – – –
a0ac664d-c92a-564b-80b8-595ddcdc27f8 | note | VERIFYING DOCUMENTS - This ITP Signed Off
215b2e99-4fbc-5069-9380-63cd22323b82 | date | Date Completed:
| checkpoint | 5.15 - Architectural Steel Erection
739b1742-1b3f-5bd2-a717-761e2994c8f9 | note | REFERENCE - AS4100 Clause 15.2.3 AS5131 Clause 11.5.7 630.12
b4c6c461-19fa-5a70-a121-90b9d4bcf5d6 | note | – – – – – – – – – – – – – – – – –
8d349b57-e83c-50f9-9e7b-2d215bfbf386 | note | ACCEPTANCE CRITERIA - Place steel component into position, ensuring that it is plumb, level and square Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely
a82e71d7-6980-5462-8b00-3323d761087e | note | – – – – – – – – – – – – – – – – –
576892f3-cf75-5851-8c04-c7ce7efc0f4b | note | METHOD - Measure Visual
2e5a95e1-bd01-5123-b829-fcb90217fa14 | note | – – – – – – – – – – – – – – – – –
2f56309a-847f-57af-852a-a40c084dfd94 | note | FREQUENCY - Each component
0d91eed5-6955-5c19-9dab-783be10542e1 | note | – – – – – – – – – – – – – – – – –
a68b46d6-d60b-5a97-bd63-9c186741ffb1 | note | CATEGORY - IP
415fcd45-776d-5303-99cd-b70dd86d5590 | note | – – – – – – – – – – – – – – – – –
67990b45-388d-51ec-ba72-386558083668 | note | RESPONSIBILITY - SE/PE/SPE
c374451b-d983-5d6e-b7e9-57f637894f4b | note | – – – – – – – – – – – – – – – – –
dbe558c9-8fe3-537c-af9e-6a5b2e638b95 | note | VERIFYING DOCUMENTS - This ITP Signed Off
ac3e67de-af53-5549-abbd-dfc833293a84 | date | Date Completed:
| checkpoint | 5.16 - Architectural Steel Erection-Fasteners
86a96cc2-1a64-5a37-ab41-d9a4819a1431 | note | REFERENCE - IFC Drawings Section VR 630
ff63820d-fdd4-5239-b619-6f4787d37afc | note | – – – – – – – – – – – – – – – – –
cd23b194-dfd6-5b00-bed1-20499d03cdeb | note | ACCEPTANCE CRITERIA - Place bolts, washers and nuts as detailed on the IFC Drawings. For architectural/Security screens, the arrangement is to be (from the mounting post):
775246b5-a4bf-5ad6-8c96-a4a43506d5e5 | note | Post
95fd1380-6271-5e0c-90f3-8003797e658f | note | Washer (s) as specified
176802cd-c601-5ef7-bbd5-c03f66011bf1 | note | insulating washer
b80887e1-5765-557a-aaef-541a2e84066a | note | insulating bush
b18ff091-45e9-5756-bd2e-c3547e5cacf9 | note | Insulating washer
6d8a5de6-a21b-5376-8173-8daa5c7279d2 | note | washer as specified
70d19137-fe7c-5912-9e3f-d5326fcc95cd | note | Lock nut
54113278-dd98-5191-a88b-d66c52c0be8a | note | Nut
55ae7066-5957-55be-90e4-8ed81a40e812 | note | Bolt protrusion (1 clear tread)
7902c65e-b1cc-5d3e-948f-d9a248402dfd | note | – – – – – – – – – – – – – – – – –
40fb4cba-e3f5-58e7-bcb9-9690e0ce75a8 | note | METHOD - Measure Visual
4ba8841e-8a15-5543-ad7a-078e8b3084ed | note | – – – – – – – – – – – – – – – – –
e6844ec3-9325-58b7-9868-30d06068dd3c | note | FREQUENCY - Where applicable, each bolted connection
b5b6008b-5879-5953-9d9b-33c679cb94eb | note | – – – – – – – – – – – – – – – – –
20e535dc-8e6a-55f2-ad78-9f15f5da355e | note | CATEGORY - IP
9acb3758-972f-5d82-b382-cb3260be7e4c | note | – – – – – – – – – – – – – – – – –
f80ef89f-1288-5dbb-85a6-f150c856e5cf | note | RESPONSIBILITY - SE/PE/SPE
31c89575-efec-533d-905d-ff8811d2eee4 | note | – – – – – – – – – – – – – – – – –
0b3adb09-f643-5af8-a840-337c28d66319 | note | VERIFYING DOCUMENTS - This ITP Signed Off
3f2abe8a-532d-58c5-8a8e-e4d2ce47bacd | date | Date Completed:
| checkpoint | 5.17 - Installation of Electrical Isolation Materials
e8b2e317-2681-5107-92f1-b924a2d00d28 | note | REFERENCE - IFC Drawings
60d04347-f62c-5991-ab68-7e49b604000d | note | – – – – – – – – – – – – – – – – –
e227b369-2e88-5307-a96d-96e00257727a | note | ACCEPTANCE CRITERIA - Installation of Electrical Isolation Material in locations specified on the IFC drawings (where applicable).
1584caa3-4251-5ce2-9e09-19b3bf1a3c66 | note | – – – – – – – – – – – – – – – – –
57333aab-d72b-5ba3-87b4-1f74d9d9f74f | note | METHOD - Visual
e62ebb44-fa65-574e-a7ba-0366f6381a81 | note | – – – – – – – – – – – – – – – – –
2ba8dd07-a0e5-58c8-b6a2-04acabd176ef | note | FREQUENCY - Each component
fadb5f4f-0689-5928-9da1-16dd62589dd6 | note | – – – – – – – – – – – – – – – – –
298265de-2ac5-5096-8b56-4f13e65d2c6a | note | CATEGORY - IP
9fb8dcb0-d6d7-540a-83a6-0cf34ebef27f | note | – – – – – – – – – – – – – – – – –
c0524910-a301-5bb5-a5ae-e6471f463ffc | note | RESPONSIBILITY - SE/PE/SPE
cb785011-48f9-5583-b610-d0bbae943163 | note | – – – – – – – – – – – – – – – – –
6a02d2aa-a9e2-51c1-8d1d-5e6a3062ce7d | note | VERIFYING DOCUMENTS - This ITP Signed Off
ccf5d9e0-1ad7-5875-a902-473a88e08a14 | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 - Inspection of Coating
b33196a4-8e85-55c6-b818-0ad4d8e0d895 | note | REFERENCE - IFC Drawings Section 630
8ea5886f-bc57-579a-8538-e9608a6d3def | note | – – – – – – – – – – – – – – – – –
1cdbc889-12d5-5248-86e3-8d0cb71da6e6 | note | ACCEPTANCE CRITERIA - After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure.
ec731d67-26f6-5692-b302-fc5d78e2661c | note | – – – – – – – – – – – – – – – – –
574d046c-f05f-50ee-afb9-93adefd03e57 | note | METHOD - Visual
2eaeab42-25a3-5cb5-9679-669eee4ca792 | note | – – – – – – – – – – – – – – – – –
be7941af-4e5d-5f71-9f1b-66b958dfa602 | note | FREQUENCY - Each component
b305462c-ce24-5da8-a9cd-48c65342cfc8 | note | – – – – – – – – – – – – – – – – –
3f01cde1-5345-5841-a4ed-742828efee1b | note | CATEGORY - IP
566b91d4-4851-553a-8a50-fd6359dc82e6 | note | – – – – – – – – – – – – – – – – –
c463e35f-b83a-52fb-9799-aaabcfcd0da3 | note | RESPONSIBILITY - SE/PE/SPE
e416c5ff-4786-57de-aed8-ea5b242ce9b8 | note | – – – – – – – – – – – – – – – – –
2ea8bb88-3541-50b0-a393-1a6f617d2579 | note | VERIFYING DOCUMENTS - This ITP Signed Off
0883f11b-73cc-58aa-9ad7-2a29f48eac5c | date | Date Completed:
| checkpoint | 6.2 - Compressive Strength Test Results
dd07337f-3ca6-5b8c-b10b-a10a44ada631 | note | REFERENCE - IFC Drawings Product TDS Section 610
a53def1f-960e-59e4-ab35-f3cd50d4aba8 | note | – – – – – – – – – – – – – – – – –
0b7ae529-9571-5c73-af41-336c0776dc0e | note | ACCEPTANCE CRITERIA - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Attach: Compressive Strength Test Results
d344dff5-189f-54c3-8894-fc114481b502 | note | – – – – – – – – – – – – – – – – –
4f912755-573b-566f-b4c6-d2ab453ed5c6 | note | METHOD - Document Review
205afede-31fb-527b-aa0a-f4c8fbee52bd | note | – – – – – – – – – – – – – – – – –
c29114e4-e6cf-575d-816f-167162ff7e00 | note | FREQUENCY - Each Sample
eb870c8d-a0d4-56ee-809c-2fe52cc8c6c7 | note | – – – – – – – – – – – – – – – – –
6ee42e8d-31d1-5626-98bf-f5073bd12ef3 | note | CATEGORY - IP
16609ba0-ef6d-5184-93da-c087b4f2bce5 | note | – – – – – – – – – – – – – – – – –
23b281c3-a747-54b4-96e9-3f463f449fd2 | note | RESPONSIBILITY - SE/PE/SPE
60a97b96-c41e-5c73-9b87-5de7ea3cfeb1 | note | – – – – – – – – – – – – – – – – –
d6d3197a-d1b8-5ac5-b3fa-a0561a292043 | note | VERIFYING DOCUMENTS - This ITP Signed Off
6246a5cf-930d-563f-b315-e1863667fa0b | date | Date Completed:
| checkpoint | 6.3 - As-built Survey
ac536a24-ad87-5b97-af94-a9c9d1e15ff6 | note | REFERENCE - IFC Drawings AS5131
e868e8fe-867c-56f0-9e0e-5df53e01fee6 | note | – – – – – – – – – – – – – – – – –
3b90de42-c92d-5195-8a20-e3c3364ec2c3 | note | ACCEPTANCE CRITERIA - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Attach: Survey As-builts / Survey Report
7f330783-8f35-5b10-bae3-9a826f2a0569 | note | Departure from RL = ±10mm
1001e96c-949f-5024-b467-04797e7023b5 | note | Departure from plan position = ±6mm
d6d141e1-8c66-5a01-a389-7eb10ef2aee7 | note | Departure from alignment = ±6mm
d837afbe-d9d0-5abf-a49c-6fd5a3f3a57d | note | Irregularities in alignment = 25mm in 30m
217916e6-0591-5c6c-bb02-370e75446fe4 | note | Projection of bolt = +25mm, 5mm
aa6dfc0c-04df-508a-b737-d0c681d7d007 | note | Location of beam = ±3mm
d42f1a00-cea7-54fa-b1bd-721267150401 | note | Location of column = height/500, 10mm max.
2b814d56-98d4-5cf7-b5df-bfc66a939ee1 | note | – – – – – – – – – – – – – – – – –
e7c3f0f3-91c7-5cad-b633-c3677a82291b | note | METHOD - Document Review
e0326bb7-b06b-5ccf-a372-814e74f8b9bf | note | – – – – – – – – – – – – – – – – –
f08f27ef-2496-55f6-96a7-39bdca3bba37 | note | FREQUENCY - Each element
7415e082-8aed-573e-b035-c7f509c5f9fc | note | – – – – – – – – – – – – – – – – –
1678346c-029c-5f8e-a557-8f8e6c3c7539 | note | CATEGORY - IP
f963398e-c90d-5cb2-b614-6f5263ea3352 | note | – – – – – – – – – – – – – – – – –
4585c1ad-1f52-593f-8102-e3ad573f828f | note | RESPONSIBILITY - Surveyor SE/PE/SPE
3740a088-7ca2-57a7-88de-c2ec525b7b36 | note | – – – – – – – – – – – – – – – – –
29633791-d474-5031-b434-4fb972de5647 | note | VERIFYING DOCUMENTS - This ITP Signed Off
b05ace4a-9a48-55b5-8768-c0dba41ef60b | date | Date Completed:
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
daf65c7d-639c-5946-a3eb-c31d1b1cafe3 | note | REFERENCE - MRPA Quality Management Plan
932bf6f8-6cf0-5dc5-b156-5b71eb9950f4 | note | – – – – – – – – – – – – – – – – –
23417a05-4068-57f5-8d14-5146c74d4201 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
379c31dc-f6a3-50ac-b4c2-1bf7e25adf0d | note | – – – – – – – – – – – – – – – – –
8b3e1efd-0fce-5ac6-aecc-6cedd9594c40 | note | METHOD - Document Review
bc2e4e4e-d6ca-5b45-806c-5842e7583716 | note | – – – – – – – – – – – – – – – – –
0b383f03-c7e5-5497-bc9e-5dda5f00b1ac | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
57a2ad11-0546-56df-afc7-acfc3590b8e8 | note | – – – – – – – – – – – – – – – – –
75a70ed2-f309-5e5a-be5e-e26c86e59492 | note | CATEGORY - HP*
c0be4301-85b8-5b21-8a59-72cc65d30f38 | note | – – – – – – – – – – – – – – – – –
d62fcbea-1bbc-5e5b-9c2d-6272196e938a | note | RESPONSIBILITY - SE/PE/SPE
cd2a5e16-8c52-5c34-b42c-f3568797c18a | note | – – – – – – – – – – – – – – – – –
eccd08aa-1842-5275-b0b8-7821710573e5 | note | VERIFYING DOCUMENTS - This ITP Signed Off
4b6bfdf1-54c6-5111-a71d-9a2fb21d7e7a | date | Date Completed:
| checkpoint | Final Inspection
2ec72e15-7852-5d05-978a-cf0797dd1d9a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
117728e5-b0cc-552c-8855-bab8613090ec | textbox | Name:
03e0125f-f99e-5243-8785-4e79d521d744 | textbox | Position:
a5c15533-5410-5ef0-9edf-80aeed434c71 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-099-CIV-BRUNT-Subgrade Preparation - Road | itp | ITP-099-CIV-BRUNT-Subgrade Preparation - Road | b6a12bf5-71be-4b46-b8dc-63ca3f87bc1b
| section | Referenced Documentation
| checkpoint | Referenced Documentation
a4b2893c-5b0f-5510-bddc-f828a895159f | note | Document Title: ITP-099-CIV-BRUNT-Subgrade Preparation - Road
f708d255-0dec-585a-9738-72419c937942 | note | ITP Description:Subgrade Preparation - Road
95fd1f1c-6b20-518b-9338-36732be5bbb4 | note | Discipline (e.g. CIV/STR/RAIL:CIV
407e311a-d003-5cd8-a83a-b7d197248e1d | note | Revision Number:0
9be1d377-8ac4-5af5-ba8f-ae1c48ab2015 | note | Revision Date: 26/10/23
6464193e-0ae8-511b-9d8d-83a74150c0f4 | note | ITP created by: Crystal D’Mello
2de5c36f-442e-56be-89b4-e0a964f0d22d | note | ITP approved for use by: Jon De Castro
34e6ae21-a7cc-570a-bf74-b65411f9b686 | note | 1.1 VR Section 204
dd7ab530-32c5-5346-b0ff-2ec640355627 | note | 1.2 VR Section 173
d8644a7a-192c-5f79-95ef-fdd0db982deb | note | Preliminaries-Materials N/A
972e3290-987f-5f8c-aad7-bc631471a02d | note | Preliminaries-Documentations N/A
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-Out
a113441b-4c61-5540-81c1-511f8a2e70b8 | note | REFERENCE - IFC Drawings
855f10d3-bf1b-57bc-8d80-ced8e9d99b25 | note | – – – – – – – – – – – – – – – – –
e1deb3d3-1b28-55b4-beaa-bb5265bf8eba | note | ACCEPTANCE CRITERIA - Area has been set out in accordance with the drawings ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
92db706a-c0e7-5819-8fe4-38421ba62ed4 | note | – – – – – – – – – – – – – – – – –
9f633a3c-aa32-554e-8622-893109224ce3 | note | METHOD - Verify-Document Review
61f63c83-0099-539d-ace1-c4394b51d98a | note | – – – – – – – – – – – – – – – – –
66d7af62-1229-5179-a8c2-19d38b27b07e | note | FREQUENCY - Prior to commencement of excavation
724d6d08-960f-58b0-b1f2-36ea6804fab9 | note | – – – – – – – – – – – – – – – – –
0bcbb79d-3079-54aa-922f-3240cb423c7c | note | CATEGORY - IP
db118312-543a-50bd-a49f-5aab004fcb77 | note | – – – – – – – – – – – – – – – – –
c8570c2d-96e2-5258-aed0-95f7838afed6 | note | RESPONSIBILITY - SE/Surveyor
7f25c95e-5b17-5e21-9fba-b400a301351c | note | – – – – – – – – – – – – – – – – –
7f577c48-bf33-51ac-b48c-d34598e35d4d | note | VERIFYING DOCUMENTS - This ITP Signed Off
56e965a2-00dd-5e1f-8e33-c60150a6cf10 | date | Date Completed:
| section | Preliminaries-Documentations
| checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
048c41cd-3476-5b20-b96f-c77b1f3b814f | note | REFERENCE - Section 204.06 ( c) Section 204.06 ( e) IFC Drawings
65237993-d404-50a3-8d48-5a1c93a89a24 | note | – – – – – – – – – – – – – – – – –
985d8209-c356-5419-9503-488fda435555 | note | ACCEPTANCE CRITERIA - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
512be6d4-0e62-50e4-ad02-e6e5a937acd2 | note | In situ material within 400mm of cut floor level to be consistent with IFC Drawings. Assigned CBR Min 2%. If parameters are met, rip and re compact to a depth of 150mm. If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill. If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised. Type A material within 300mm of cut floor level to be consistent with IFC Drawings. Assigned CBR ≥ 8% and Swell ≤ 1.5% Attach: Laboratory testing Verification:
ccacf42b-4d69-5814-9159-09b3afff2eef | textbox | Test Report Enter: Type A fill Lot Number:
f5da5d58-80d2-5bbe-be94-2d7e29aef87f | note | – – – – – – – – – – – – – – – – –
387069ba-65ca-5534-921a-1bea0dd63a46 | note | METHOD - Verify-Document Review
3542665b-c984-5aec-b988-5ddffd8c6188 | note | – – – – – – – – – – – – – – – – –
000a330a-4c8c-538f-a749-49dcf5f6c40b | note | FREQUENCY - Each lot
22eafe0b-a5f7-536b-9eb7-01ddcb0804a0 | note | – – – – – – – – – – – – – – – – –
87c7cc32-be32-5edc-97de-2f1282dc63b3 | note | CATEGORY - HP
864e2448-d925-5f94-9f92-f2a5df36cef7 | note | – – – – – – – – – – – – – – – – –
e4eef375-26c4-51dd-ab8a-bb4cfc19ec41 | note | RESPONSIBILITY - PE/Nominated Authority
ad001371-e394-5d41-b51c-e5d80516e5f6 | note | – – – – – – – – – – – – – – – – –
c8406a33-d2d7-5e45-a4d3-1e84bd09ca97 | note | VERIFYING DOCUMENTS - Conqa HP Release
289d7abd-bf83-5447-93c7-1d312bedec37 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Material classified as silt
82e9b680-1c58-5071-b970-4b2cae83de54 | note | REFERENCE - Section 204.04 b)
96c8fa1f-2fba-5e52-ad7f-03514eecb501 | note | – – – – – – – – – – – – – – – – –
cbdf319b-849e-5b93-8ede-5aa1f1ca9ced | note | ACCEPTANCE CRITERIA - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority. Attach: Subgrade Stabilisation Procedure / ITP
5b2783ff-d8dd-5bc6-9340-c8755ee6ac76 | note | – – – – – – – – – – – – – – – – –
a0260ff9-0d00-530b-bb3d-434893b83ccb | note | METHOD - Document Review
c71d71bc-2f56-517d-92e3-1a9c8967749c | note | – – – – – – – – – – – – – – – – –
b1e8cbfa-17d1-5f65-9d1b-b974d08ee794 | note | FREQUENCY - Prior to commencing
b2cffd13-1cb9-59a7-b807-6b178974382d | note | – – – – – – – – – – – – – – – – –
e2db273c-21bd-546e-b48e-249988df7f39 | note | CATEGORY - HP
da211956-09d6-571b-903f-25b71b9df392 | note | – – – – – – – – – – – – – – – – –
623733c4-7dad-541d-9e72-a44c80dcbabd | note | RESPONSIBILITY - PE/Nominated Authority
0c69bb46-d938-5c58-a73c-43b5e72022d0 | note | – – – – – – – – – – – – – – – – –
04ab585a-e908-5dab-af8e-7275fe8d3c25 | note | VERIFYING DOCUMENTS - Conqa HP Release
9f1dfa2a-c71c-5a9d-b14e-d4cef419ef2c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
f1e7b066-a070-5f71-b559-9d7deaaf6150 | note | REFERENCE - Section 204.06 f)
7a6921b5-f1e1-5d1c-9742-fe19b8a785b8 | note | – – – – – – – – – – – – – – – – –
685a89d7-8acd-5815-8afa-9669e16473fb | note | ACCEPTANCE CRITERIA - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
02f13ded-cd53-5342-9ce1-5f263472626b | note | – – – – – – – – – – – – – – – – –
378fb441-0d85-52d6-a4a1-b76a65188119 | note | METHOD - Site Inspection/ Document Review
f51911f6-4d1a-543a-88aa-99a559bf1cfe | note | – – – – – – – – – – – – – – – – –
7f544004-0ac7-51f3-a8b8-363415420fa0 | note | FREQUENCY - Prior construction of the regulating layer
9e5275a5-0e88-58c6-b089-68f595d260f6 | note | – – – – – – – – – – – – – – – – –
91674b02-db60-5418-bf71-9468f69e132e | note | CATEGORY - HP
caa6a899-4050-596a-b713-e50f5f1e8f22 | note | – – – – – – – – – – – – – – – – –
6cb1be0e-6605-5b1d-9172-bcf284e1889d | note | RESPONSIBILITY - PE/Nominated Authority
a40ca2f6-0f83-57ae-a259-de7ac7a4696b | note | – – – – – – – – – – – – – – – – –
be6e7f1c-1fe9-56ff-96d2-2ce6639a3edb | note | VERIFYING DOCUMENTS - Conqa HP Release
b54529dc-abde-5f07-9947-6b00c44e89ec | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Unsuitable Material
854ace5b-07cd-5086-b331-ad623ad474dc | note | REFERENCE - Section 204.07 d)
c00f253c-5a02-5b0e-acf3-ee2fbb71e06f | note | – – – – – – – – – – – – – – – – –
7f01a3ee-dc1a-57d8-a203-11b2e7e0dfa1 | note | ACCEPTANCE CRITERIA - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
dc4829da-cf2e-5009-8da2-20f9f3567825 | note | – – – – – – – – – – – – – – – – –
aef8d1c2-b2cb-5eef-ab41-6481f29e8a50 | note | METHOD - Visual inspection
4e8149d7-5448-5564-81e5-655a5c3df272 | note | – – – – – – – – – – – – – – – – –
ac0ce060-ea8a-5a7e-9577-a91351bc3cca | note | FREQUENCY - Each lot
c981e92b-c5e4-5031-9ba5-7e67db275c69 | note | – – – – – – – – – – – – – – – – –
d40e6b67-f25b-56d4-a21a-5b208a45b1b5 | note | CATEGORY - HP
72d02477-a980-5dd8-9112-3893e5b870c6 | note | – – – – – – – – – – – – – – – – –
d9e60fce-2ac1-59a3-a5ad-ad633627cea2 | note | RESPONSIBILITY - PE/Nominated Authority
89c8425a-8d0a-5516-a820-dcb8e78bc21b | note | – – – – – – – – – – – – – – – – –
6ee2be22-fd0d-5595-a474-8fe7a22e9ab9 | note | VERIFYING DOCUMENTS - Conqa HP Release
acdfa2ba-024a-56fb-8b17-b207bd5e535c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Groundwater
ad89bf43-04ce-5c7b-9fa1-c7206bfebc69 | note | REFERENCE - Section 204.06 h)
e79f1df3-72a0-5ec9-8d1a-570469ceea42 | note | – – – – – – – – – – – – – – – – –
1d07a3d2-48e8-538e-803c-9127224f8a63 | note | ACCEPTANCE CRITERIA - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
78991802-de3a-5519-9fb7-e6dee1260e59 | note | – – – – – – – – – – – – – – – – –
d122c445-0f94-589a-902a-37441d79f5a2 | note | METHOD - Visual inspection
9d822753-60d5-509b-9e63-8e7ea546886d | note | – – – – – – – – – – – – – – – – –
39825926-d8b7-518d-be06-7915c7e48492 | note | FREQUENCY - Each lot
0393e692-74fa-5093-a866-0b6906241c75 | note | – – – – – – – – – – – – – – – – –
81bef171-de32-57a7-8cc0-02d959127304 | note | CATEGORY - HP
df65a0ff-b4d1-5a5d-b764-5c311884b7e2 | note | – – – – – – – – – – – – – – – – –
bae04e0f-4cde-5db8-ab99-897731097405 | note | RESPONSIBILITY - PE/Nominated Authority
a2708003-946c-56c4-9da0-ec99611f57f9 | note | – – – – – – – – – – – – – – – – –
9f71b6d6-3eb6-5134-9161-fbcfef5fcc4a | note | VERIFYING DOCUMENTS - Conqa HP Release
3237f43a-460e-56be-bd24-b71e4dbea3fa | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Cut to Fill Zones
f3df38a5-1852-532f-a0f6-2596f6b0db08 | note | REFERENCE - Section 204.06 g)
25de007e-0fc3-5bce-aadf-3a887999ce3f | note | – – – – – – – – – – – – – – – – –
4daa8886-68bc-529c-9d41-a25bfb3daa7a | note | ACCEPTANCE CRITERIA - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
03720e96-056f-53f1-8748-d25edd730ec7 | note | – – – – – – – – – – – – – – – – –
bc0f0f46-4d20-5dcf-986f-5ffaa4e97ab8 | note | METHOD - Site Inspection
7598898f-8705-5b3d-bde1-cea6ce2707f6 | note | – – – – – – – – – – – – – – – – –
10ae1631-f4f7-5a8e-8415-52b8b0c9a2a1 | note | FREQUENCY - Each lot
385219cb-1e74-5f58-8e14-fd05011da64a | note | – – – – – – – – – – – – – – – – –
9b930781-d04b-5d77-ba32-a5c1ced2da6b | note | CATEGORY - IP
05824ba0-c1bb-5310-88b1-1eec9bcc4382 | note | – – – – – – – – – – – – – – – – –
aae2fdd8-cc37-558f-b886-3ff52923c9de | note | RESPONSIBILITY - SE/Site Supervisor
5bf68016-fea8-5dac-a2e8-d2105b1e7ebe | note | – – – – – – – – – – – – – – – – –
a99847da-6358-5532-9450-22388b2c0d48 | note | VERIFYING DOCUMENTS - This ITP Signed Off
7b17596e-eac3-5865-b4fa-9b21683db1c4 | date | Date Completed:
| checkpoint | 5.7 - Proof Roll
a3f45e3c-ef3d-5bd7-8fd1-aacaa674d398 | note | REFERENCE - Section 173
bc69c0c5-85c7-5434-b197-718acfa2fdec | note | – – – – – – – – – – – – – – – – –
504ea63b-84dd-5c1b-b0e5-cd88c95c02e7 | note | ACCEPTANCE CRITERIA - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
150ab510-476b-563f-94b9-216c3b97e785 | note | – – – – – – – – – – – – – – – – –
c8148abb-5aaa-50eb-a825-1f659d4bbd0c | note | METHOD - Visual inspection
b9cf94ab-f477-5470-905b-49ed836be326 | note | – – – – – – – – – – – – – – – – –
a0442e13-8dfd-5228-971d-0f2e7a4c0712 | note | FREQUENCY - Each lot
149e6284-df99-5bf7-9781-b70c33ba6f0a | note | – – – – – – – – – – – – – – – – –
8aadb74b-82e3-5524-a06e-8352099ce195 | note | CATEGORY - HP
41599216-a41c-5ac4-afb2-cb4e749e1ec9 | note | – – – – – – – – – – – – – – – – –
b38ab64d-1ba4-5037-9df0-6b1420bd8f79 | note | RESPONSIBILITY - Nominated Authority
f6c08a29-3f4a-5d9e-9164-25f961eb0737 | note | – – – – – – – – – – – – – – – – –
0fb404a4-3dd0-5b25-9f6a-6d40bba52040 | note | VERIFYING DOCUMENTS - Conqa HP Release
4685fa8c-f65c-582b-9e0b-9fa410457c58 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Compaction Testing
64999237-d459-5f34-9b78-acbdd6042fbc | note | REFERENCE - Table 204.131
46751d83-576c-51a9-a210-1136cc3e96a8 | note | – – – – – – – – – – – – – – – – –
ada084b4-6e87-5ba5-97e8-14f167b5b875 | note | ACCEPTANCE CRITERIA - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
0b868b0d-8138-5fed-8453-91e8db72f0fd | note | Scale A: Characteristic Density Ratio 99%.
184fb496-e177-535c-8be8-c5acc766ec6b | note | Scale B: Characteristic Density Ratio 98%.
3d4bd8e2-f58e-57b3-a7f3-cf9a4840fdee | note | Scale C: Mean Value of Density Ratio: 100%
0b29d0a7-be63-5aa0-aeba-a268705bda85 | note | Attach: Compaction Test Result
46798b68-09bb-568b-bf45-7322a098f114 | note | – – – – – – – – – – – – – – – – –
0cdc7ddb-47a0-5f54-bde3-c97faaf1fbf6 | note | METHOD - Document Review
ea2aea71-1ac4-5ab4-befe-3f55b4d49d46 | note | – – – – – – – – – – – – – – – – –
65df2e02-f6a8-5778-a2c2-e7e1c079fb83 | note | FREQUENCY - Each lot
0d9d1474-8909-56fb-8837-61cc470c35fb | note | – – – – – – – – – – – – – – – – –
ad81911d-e096-5963-876d-1c1252474979 | note | CATEGORY - IP
b940597e-5b3e-5031-a20c-047521baea32 | note | – – – – – – – – – – – – – – – – –
2fa97c45-2c94-5099-b34c-6c9dec14e7c0 | note | RESPONSIBILITY - PE/SE
c00c370a-cd77-5e77-bc7d-db7864df232d | note | – – – – – – – – – – – – – – – – –
6ffcd9b6-8c6b-5220-85a5-fd2750d7e9c5 | note | VERIFYING DOCUMENTS - This ITP Signed Off
95d622dc-2f34-53c9-b683-29013e2cd912 | date | Date Completed:
| checkpoint | 5.9 - Post Compaction Material Property Testing
c68e1330-d3f3-5fff-8254-fca41ac5d342 | note | REFERENCE - Table 204,041 Table 204.141 Section 204.14 a) or b)
2d3286c7-bd40-5509-9919-98caa04afa99 | note | – – – – – – – – – – – – – – – – –
540a6c39-5d6e-59f8-bf44-2340823ff4c7 | note | ACCEPTANCE CRITERIA - Material Properties (Not Applicable for Scale C):
adae7103-5beb-5860-a736-fab6441046a0 | note | Insitu: CBR = 2% min
ad0127d9-87ca-5c04-a51c-922dd51eee3b | note | Type A: CBR ≥ 8% and Swell ≤ 1.5%
3c82a0e3-d8ad-564f-9004-1fcbf134079f | note | Max Permeability = N/A
f1543922-19f0-5ffa-9e35-83238da4df4f | note | Grading: 75.0mm 100%
886ed10b-80bb-5a03-b6ca-55cfd2c6ff12 | note | 4.75mm 40-80%
18726f13-c175-534b-9241-6266e32047ba | note | 0.075mm 10-40%
94874b0d-4b2f-57af-9b08-d19b4c13adf7 | note | Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
12b84642-eb38-5fcc-a4e0-1ab032eebdf1 | note | Scale B: 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability. Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
452caa09-242c-58be-9250-f5a71ca9b984 | note | Attach: Post Compaction Material Property Test Report
6dec8c17-89ef-5605-a5f0-64f54632601f | note | – – – – – – – – – – – – – – – – –
a7660a11-0d35-5d66-a078-50bf088f9116 | note | METHOD - Review Document
3b74547a-96d5-560f-af76-1dc1e244cc0f | note | – – – – – – – – – – – – – – – – –
50e0a283-b6f4-55b2-93e9-78b5898f22ae | note | FREQUENCY - Refer to Section 204
2f895203-a570-53bc-bc11-3db44313a113 | note | – – – – – – – – – – – – – – – – –
5fef97ef-0028-5e5a-b307-73f092db7aec | note | CATEGORY - IP
a34d9926-5e9a-5f56-b800-04d0b256fa75 | note | – – – – – – – – – – – – – – – – –
882c3fed-8acd-51a0-b9d9-9c0fbd48930f | note | RESPONSIBILITY - PE/SE
8893395e-5bee-58f8-9837-d6a60250bde9 | note | – – – – – – – – – – – – – – – – –
f5fc9b5f-341c-512e-8ddd-62174aed3e45 | note | VERIFYING DOCUMENTS - This ITP Signed Off
ce59a09b-1f12-519c-b400-585f53c6799c | date | Date Completed:
| section | Post Construction Activities
| checkpoint | 6.1 - Survey Conformance
93f10e77-3e9d-59dc-9b05-cfa077ef5f15 | note | REFERENCE - VicRoads 204.03f,g and h
b6aa1877-c916-5a64-9847-2e8916495a90 | note | – – – – – – – – – – – – – – – – –
2a33b1cf-3559-54e9-b463-ee23861044d5 | note | ACCEPTANCE CRITERIA - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
95e6fca8-5b0f-5a2d-9129-f0fb10859ba6 | note | Level tolerances (Scale A):
5ae1a42f-28f8-5653-b56d-9f0e6b5cd7e4 | note | Range x = +5, -15mm
05227a8e-de04-53a7-a472-6c232ced38b9 | note | Max S = 12 mm
54e01dfc-b02a-5ab1-8799-2e96b21d5904 | note | 80 measurements per lot
931dd61b-514b-58ca-bde3-c29154359203 | note | Level tolerances (Scale B):
c6f140a0-545e-54be-92ec-1c38fcc7e1ce | note | Range x = +5, -25mm
3ad5b801-d7c2-53d6-93eb-2619a0f90c27 | note | Max S = 15 mm
ed972aee-98d9-529a-bb6e-fe8fc6e58d67 | note | 40 measurements per lot
80524b52-b829-5fab-b894-822a8ab1d6f1 | note | Level tolerances (Scale C):
1b5e4bd3-de42-574b-a255-057787a0aaf0 | note | Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
abcb083e-2f9d-516d-b290-478ad5637979 | note | Adopt 40 measurements per lot
7675b6f4-ad9f-5a3d-b7cf-e34f690f1d4a | note | Attach: Survey Report
b633b684-a273-5391-85b6-4eb101fc05c2 | note | – – – – – – – – – – – – – – – – –
1b50f276-bc9e-55bf-b423-d15226990f00 | note | METHOD - Review Document
7d752a87-d858-553f-83c0-c5ebade46392 | note | – – – – – – – – – – – – – – – – –
46ca8d32-c2a4-50a4-a6f8-da7cac06d1be | note | FREQUENCY - Each lot
88ca7866-d074-5408-83e2-4e30b1557846 | note | – – – – – – – – – – – – – – – – –
722808cf-6788-5437-a479-01504d1165f3 | note | CATEGORY - SP
c1702dd8-9f83-551d-92bc-21e9dad74396 | note | – – – – – – – – – – – – – – – – –
eb42ffc7-f2c2-5022-ae0b-0002237d25bc | note | RESPONSIBILITY - SE/Surveyor
44f4b0db-7d8a-5075-8b12-d4f48510e465 | note | – – – – – – – – – – – – – – – – –
18c9ad75-e7fc-5b29-b956-d2a638316129 | note | VERIFYING DOCUMENTS - This ITP Signed Off
1bf929c1-6e92-5966-8321-2fc4eee4cc7e | date | Date Completed:
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
cf7257dd-aa80-5a8a-a6ad-6d2043d29da5 | note | REFERENCE - MRPA Quality Management Plan
367c0c5a-60ee-5e96-83fe-d373dfcf7553 | note | – – – – – – – – – – – – – – – – –
f00dd01f-a894-5580-a482-3db8c2369bef | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
8cf4736e-2bbb-5c83-8b32-f832014570c8 | note | – – – – – – – – – – – – – – – – –
7c9afb2a-c237-5629-84cc-4cdf93d076e1 | note | METHOD - Document Review
383f319e-39f7-5e17-9f84-b118038e07c4 | note | – – – – – – – – – – – – – – – – –
006aae62-f143-5d0e-8def-416f7652afc4 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
bf0e7375-4a97-51a8-a6e5-336505ddab28 | note | – – – – – – – – – – – – – – – – –
45c0c5fe-9132-5d48-889e-7c399f9cdb5d | note | CATEGORY - HP*
80572849-1c09-501c-9878-88b4d40d6e41 | note | – – – – – – – – – – – – – – – – –
242a2bff-2363-5b5c-a28d-a17eb7dddb76 | note | RESPONSIBILITY - SE/PE/SPE
ed367cfe-926f-5a44-a288-67e25983cb1d | note | – – – – – – – – – – – – – – – – –
5e6d9ae8-cb9e-506e-bf75-7f08347eded3 | note | VERIFYING DOCUMENTS - This ITP Signed Off
e932b097-c183-5d11-bb0f-3d59ce93d550 | date | Date Completed:
| checkpoint | Final Inspection
f058a128-af24-562e-a31e-daf1f39abce6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
df507fbe-86fe-54b7-814f-b35642b86576 | textbox | Name:
4480a483-15bc-5d3d-9803-95b99a10f25f | textbox | Position:
42110a7a-0339-5617-a2b8-3448952587ab | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-103-STR-BRUNT-Structural Concrete - Bridge Deck | itp | ITP-103-STR-BRUNT-Structural Concrete - Bridge Deck | 0a3087ed-a5f4-4616-b5ec-b4cb953d12a9
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
5fd63f95-cd13-562e-8cbc-94a7bd625f9c | note | Document Title: ITP-103-STR-BRUNT-Structural Concrete - Bridge Deck
a4de3ee4-2b54-5bb3-a226-07cae44c50a4 | note | ITP Description: Bridge Deck FRP
23b068c1-e7bc-504d-b680-8f9c6be93be3 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
22969a43-a468-55ec-9544-1d5a7dfd6194 | note | Discipline (e.g. CIV/STR/RAIL): STR
a49876dc-46a4-53b0-83ab-81f5e7936df4 | note | Revision Number: 0
5fe2eefd-ad63-5b6f-8176-477a2e9d8bb2 | note | Revision Date: 31/10/2023
56987ca1-b1e9-5f41-9441-5366106e28b1 | note | ITP created by: Yasna Naicker
86c87bc4-34e5-5b1b-83a6-68e86f980189 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
775e320e-df34-5be1-ab86-1e162fd6254e | note | Reference - VicRoads Section 602 October 2007
| checkpoint | 1.2 - Non Dependent
c1318f2a-973f-5a23-9c22-6bc26a9cdd59 | note | Reference - VicRoads Section 610 February 2020
| checkpoint | 1.3 - Non Dependent
078199de-dc78-5f12-95d8-61f2cda04959 | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
6314737e-856d-55e4-ac3f-45bff07ef7c4 | note | Reference - VicRoads Section 614 June 2017
| checkpoint | 1.5 - Non Dependent
0548f62b-8a97-5307-9ef6-32b72d971b28 | note | Reference - AS3810.1 2018
| checkpoint | 1.6 - Non Dependent
b6de8db8-1755-555e-820e-735291d5930f | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
b2ab8913-213d-5555-9635-d49cf033477b | note | Reference - 610.07 Table 610.071 IFC Drawings
60b10fc2-069d-5bb7-8462-77dcd17679bf | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
54587604-ef79-558e-89cc-dbdaec578cdd | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
dde221d3-918b-5992-93b1-c71ec75e544c | textbox | Enter: Teambinder Material Approval number
ff9a16f8-1777-5374-a918-d79eca718d6f | note | Method - Document Review
2471f054-737d-55d1-9f64-835ef6e7650c | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
e6e97c95-b5e1-53a7-a8cb-c2f4e67b8824 | note | Category - HP
fc718200-9487-5dfd-9476-3d6a4d2e9093 | note | Responsibility - Nominated Authority
4d9dac75-9893-5d31-a3ec-ce6463342a01 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
a89e4937-6e9d-5744-abb4-9d192b3e6dcc | note | Reference - 611.05 (a)
82fd42e5-d25e-54aa-8841-13c7813ef379 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
7ddb84ee-f35e-5145-af59-25b8654c59b9 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
0a24d56f-ec0e-515f-98de-9fdf72d06c85 | textbox | Enter: Teambinder Material Approval number
300de597-aa65-51f3-9c80-623c50b43b20 | note | Method - Document Review
e6f0f8ee-d562-581d-b1ed-e6501ffd5212 | note | Frequency - Once for each supplier, 14 days of award of contract
3f305d11-5485-518b-bda8-24a02608bafa | note | Category - HP
ae01ca42-ae05-5cde-958d-01269f929fa2 | note | Responsibility - Nominated Authority
5384e88a-51f4-59c1-aee5-9a47d6edda74 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
9e65cc04-d26e-5c3f-9eb2-1d4ee7cae952 | note | Reference - 610.26 (a)
6ea1eb3a-33d3-5578-8495-d19da847f7b1 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
cb0c3d40-fa0f-5e94-97ef-f0af00e469ba | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
b0e02ca7-23e4-5835-a9d9-6c0d915411bf | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
97dc93e1-8b7e-55e4-8e88-5b7bf0558964 | textbox | Enter: Teambinder Material Approval number
73907b97-4b60-5083-81b2-1c865ab5431e | note | Method - Document Review
626cc132-41ac-54fa-bd3b-4272d37cce56 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
0e077fcf-f13f-52c3-9ab8-67129fe1431b | note | Category - HP
29936db2-6cdb-5115-8f62-682b6723839c | note | Responsibility - Nominated Authority
a38e86c2-7ed9-52fd-ac72-01ca824db28e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
f8d541bf-d306-55bd-aa58-9f6b15d8386c | note | Reference - 610.17 (f)
dd4e153f-0b96-56cf-883a-f2f0351dd559 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
9310bcfa-4b88-51cf-af3d-25cb224a40bc | textbox | Enter: Teambinder Material Approval number
aa83ee53-fa46-5832-b32b-99db6e89340d | note | Method - Document Review
0d59718a-3dbe-5c2d-abb9-2da2952be19b | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
360a407b-6a32-5d2e-9c7d-a5e3c7c0b2a9 | note | Category - HP
4da72ce3-4990-5b90-9785-da6ca1bb4208 | note | Responsibility - Nominated Authority
6b09824a-469c-56fc-8748-7c94247ad8db | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
82785048-7b2d-5513-b36e-1f415f52e7c1 | note | Reference - 610.23 (d)
987e39e4-51db-5a0f-917d-0993e6106df1 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
252c8f4a-9760-5a79-9460-c34dc7b2a4fe | textbox | Enter: Teambinder Material Approval number
61d53a3a-0dc1-5ab9-9302-be78b4aa4cc7 | note | Method - Document Review
abe8ed01-bb30-52e8-8d43-898067e79fbe | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
29e923d3-6b88-54fe-bcbe-17ea3c188b6f | note | Category - HP
602b0c28-b944-5d3b-a789-d5340c9be720 | note | Responsibility - Nominated Authority
613758a1-d73a-5f4a-bb2a-ef3bbcafe1fc | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
d13f84e6-5558-5ec7-9b14-cbea1f5130c9 | note | Reference - 610.18 (a) (i)
231c0ebe-1f2a-5694-a009-fe0f3d02bbe8 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
47b03b28-6db5-5b57-9969-afc4f4083951 | textbox | Enter: Teambinder Hold Point Ref Number
9dc46461-d5bf-5ee1-8aab-6b6456070d07 | note | Method - Document Review
5adccc87-aefa-5816-9953-3f8f2ddfc4b3 | note | Frequency - Once, 4 weeks prior to placement of concrete
b7c6bb37-d993-5d38-8d55-cd0489e34e62 | note | Category - HP
e8995593-659b-5075-a55a-6dcc64b66ed5 | note | Responsibility - Nominated Authority
a1838ded-953b-512c-8ccd-d63b324c1ea1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
33af1eb8-8f18-5b1e-8f3e-9b40ff0d1cc6 | note | Reference - 610.18 (a) (v)
d0b9f446-01e0-5666-b567-a8ee13f30d75 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
88a74198-8b76-59c1-9854-d50f35a46c6a | textbox | Enter: Teambinder Hold Point Ref Number
bf81fc32-5582-5c36-b2ea-d044b4ddf1f0 | note | Method - Document Review
aa64c302-f68f-5da9-a595-8f9c581a8e02 | note | Frequency - Once, 4 weeks prior to placement of concrete
0b067fdf-a53d-5537-a4d1-68fcf842a307 | note | Category - HP
53e4d4b9-ffb9-5460-9e96-3599bb2f6127 | note | Responsibility - Nominated Authority
fc9a39bb-9758-54a5-976b-9b6a01dd2d14 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
3597b866-7788-525b-bf8d-dbaeb5503351 | note | Reference - 610.18 (a) (iv)
584311d2-a9c6-588a-9b94-dfa0d13f653a | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
24b66980-705f-53cb-9e5a-612a8a10c20b | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
007b308d-eaaa-51c5-adf8-3ad55210f402 | textbox | Enter: Teambinder Hold Point Ref Number
6d0e33fa-ef4b-58dc-9b88-688091bbdecb | note | Method - Document Review
84656219-8e08-5a15-9a19-d794bc0b764a | note | Frequency - Once, 1 week prior to placement of concrete
aec89102-e893-5a8f-ac68-196040e04e81 | note | Category - HP
2225c5e8-1e9a-5294-aabf-684f5c1d2845 | note | Responsibility - Nominated Authority
d9a60d87-3932-52f7-8abe-71c7133e3af5 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
09e91ee7-7147-51bc-8ac9-c67a1c4d27f8 | note | Reference - 610.17 (a)
3489ecce-947c-5788-a889-9a68bd76c5f2 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
ce6ca6e3-a078-5f61-b0f6-3468ccac6888 | textbox | Enter: Teambinder Hold Point Ref Number
30904d6b-3f19-563a-a5c5-0aedf24977a8 | note | Method - Document Review
ec33a01e-bb09-5023-9d8b-557e137856ef | note | Frequency - Once, 2 weeks prior to placement of concrete
690b13e2-54c6-5276-9cd2-da3de93363fb | note | Category - HP
442a79b7-a36f-5b4a-ab0b-43c1a81b366d | note | Responsibility - Nominated Authority
56d395a9-9be8-54fc-90c1-327d62fb25ed | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
5bdace70-8527-5d75-8cd1-eef63cd776ae | note | Reference - 610.23 (a)
bf5e0ada-96d8-5d27-93e8-b09803cab892 | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
45cc8505-806d-50d6-bf85-ee8467e53a50 | textbox | Enter: Teambinder Hold Point Ref Number
eed5c9ec-cfd9-51e8-9af8-17871f8509d7 | note | Method - Document Review
398e9a6b-5db3-5789-bcaf-235fffbc2380 | note | Frequency - Once, 4 weeks prior to placement of concrete
528ff256-d821-5015-b566-26922e621c4a | note | Category - HP
2258310e-8f7e-55cc-97ed-667ed689be6f | note | Responsibility - Nominated Authority
4680eef2-91c4-5472-98eb-ee2567f88cbb | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Concrete Drilling Procedure
a923e96d-83f5-5f7f-99fb-d856837fbbfb | note | Reference - 610.46
9786d218-5451-5d42-bb5c-e3d947423c65 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
babe30f9-fcfa-5b69-a919-6e392726a6da | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
ec25d3ca-3216-55c2-8e58-5454edc93477 | textbox | Enter: Teambinder Hold Point Ref Number
67301686-fb29-5f60-aac8-3e1210c81d08 | note | Method - Document Review
ff6077b0-6571-53e5-a292-1d438af0c10d | note | Frequency - Where applicable, once, 2 days prior to drilling
8681acda-1ae6-555a-9a0d-659ab4f9482b | note | Category - HP
252ab516-7241-5d72-b410-3f6a5edd400e | note | Responsibility - Nominated Authority
b8048650-c94d-52ff-950e-7fd2e9e93164 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Temprature difference measuring-Calibration
184824e0-cdec-5a1e-a9db-fcd84c6211f3 | note | Reference - MRPA Quality Management Plan
03758b40-a620-5806-8566-0c4dade2ef97 | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date.
9f1a0e1b-b8e6-5b81-a7b2-e36cf1aca9e0 | note | Attach: Calibration certificate
9be39e6c-969a-5b52-a620-c6e32f4e3d58 | note | Method - Document review
26e93b40-0050-597e-93ca-57de0cb3967a | note | Frequency - Where applicable
3f989691-3da5-5ab3-b294-3330feae37f4 | note | Category - HP*
e77e8be8-4961-5589-846f-52ba0b0759e4 | note | Responsibility - PE
8773dbe0-1628-5b7e-b585-33c3b5d353c1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
3dcd7c1e-cb3b-5f55-959b-f242211c83ab | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
254dae47-779b-50d3-a777-4ed9a5a00f53 | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
7aad841d-6a21-533f-8f73-b1d989454973 | textbox | Enter: Teambinder Hold Point Ref Number
efcb06a3-47ed-5943-8dc6-e6480cc6b505 | note | Method - Document Review
556073e1-8c13-5e47-babd-2a67c2efa696 | note | Frequency - Where applicable, once, prior to welding
62cbdd3b-a989-53c5-b81f-d9da6461402c | note | Category - HP
049012ce-fae3-5c1f-a4d1-27c9194f499b | note | Responsibility - Nominated Authority
1284aca4-d59d-5e15-9f14-8595a2e5a58f | note | Verifying Documents - ConQA Hold Point Release
b3b2a58b-f942-55fd-9faa-11a8f19f79fa | textbox | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
847209ea-5844-558d-ba46-132d3a623745 | note | Reference - MRPA Quality Management Plan
3310a262-671a-5c86-87c6-ae340c9fbcd2 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
31984653-0265-55a9-9f4e-fef85e0288fa | note | Method - Document Review
473e4c0f-bb4e-5598-8e45-12d63584b73a | note | Frequency - Prior to starting Works and at regular intervals
cd1e1953-a9f1-577d-aa93-ee4499d6e5a9 | note | Category - HP*
31f883e4-d00c-567e-b20f-d492645f6082 | note | Responsibility - All
8818359e-8930-582c-9ce7-1bea15f4892f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out
521fea41-bdc2-53d8-949a-4335dde5e284 | note | Reference - IFC Drawings 610.47 (a) Table 610.472
cf604f9e-4578-573c-af58-f5479e0dd7c7 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
1051eaec-5732-5633-8043-e97d2424275c | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
72745bf1-8463-5236-91cb-4b782f177f2c | note | Method - Measure, Visual
fd6588a2-d385-5db2-bafe-968002f2b48c | note | Frequency - Each element
1491b2b8-c57e-5ca3-a3e4-64a50940a3f8 | note | Category - IP
6b84e299-13ac-5fe6-ae81-8b280792b381 | note | Responsibility - Surveyor, SE/PE
53e765f7-e380-50e1-a5ee-c5f60b009c4c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Grout Underside of Beams
d751d4e6-5e3d-5f44-b3d5-6d0bae04a284 | note | Reference - IFC Drawings
81d67f81-1885-52bf-beba-ff4c788cb922 | note | Acceptance Criteria - Underside of beam shall be grouted using flowable grout to the extent shown in the IFC drawings. Grout shall have a minimum compressive strength of 50MPa. Grout shall achieve full strength and shall be completed prior to deck pour.
ad8afeaf-4ae1-5ab2-98f6-134f53f0c8f0 | note | Attach: Grout compressive strength rest result
387e47db-396f-5de5-8a85-543d2889a7a3 | note | Method - Visual Document Review
b90214d7-9d83-5dcb-af8e-b8890f8bd3f1 | note | Frequency - Each element
e1dd32ac-6257-51ef-9b04-a0fdeefc6283 | note | Category - HP*
718d63f7-0494-5fb8-9bf5-7565f417a8af | note | Responsibility - SE/PE
370c1d85-552b-56ba-a4e4-9c5878ce4e0b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.4 - Substructure Work Lots
0deb169b-af0f-5075-b2b6-1a63b85c67ae | note | Reference - TeamBinder Work Lots
f0ac6f48-ba18-5a16-95f5-35a787f4b1f5 | note | Acceptance Criteria - Related substructure work lots are closed.
4abd8831-6b10-5264-890e-4c6ea22b99be | note | – Design strength is achieved for pilecaps, walls , crossheads
0f19e9f8-5711-56b4-82c9-0f6eb6cfec67 | note | – As-Built Survey performed
4d2ee72c-5843-5b61-a2ab-d9bdda69a57a | note | – Related substructure NCMs are closed.
c22d8483-921f-5a7b-9bd0-009e3bda6fa8 | note | Method - Document Check
6a764f05-589b-5d10-97d9-50eaedfc761a | note | Frequency - Each Element
c2a4a14e-6547-53fc-922b-2ab768b2ca6e | note | Category - HP*
8e926aee-03f0-55cd-b35f-799771efef5b | note | Responsibility - PE
b16dfdd2-df70-5098-8812-65f88d8ee2dd | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
4f8e61ff-a2d9-58e5-aac1-60ef09e17c87 | note | Reference - IFC Drawings 614.04, 614.05, 614.06
a4a31f6c-68a3-5977-96d4-15a70c2bf99d | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
38975c28-6478-54d9-b726-45ea78d06c4b | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
f7d2c121-2785-5118-abfb-93a4998446be | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
24de0493-b353-5375-90b9-f204eb17a5c4 | note | Method - Document Review Visual Measure
457f49fb-034f-52ae-a579-34238219f398 | note | Frequency - Each type of element
4615d825-e72e-5ec3-b348-fa1fec4ffe5d | note | Category - IP
3bad5f4f-6cfd-5f2f-b7dc-8dc8828bbdbd | note | Responsibility - SE/PE/SPE
f11f675a-7b8a-5d64-a534-2a0551e74dd1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
76b877ac-b96b-52cc-8ae9-7c335b6eae20 | note | Reference - 614.08
9f4002f0-1679-5804-9e75-1eb945133085 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
f2bf6362-16b5-58f7-a5fa-8ae0c0dafd72 | note | ○ Abutment / Pier Walls with heights greater than 2.0 metres
72ff048a-7e77-51ef-b4e1-7e126700d7a2 | note | ○ Any member for which self-compacting concrete is proposed.
7868c01c-ac0a-570a-a7c6-c91808f5668a | note | Attach: Attachment A
be837431-c61d-5f65-b19b-52e1f664606b | note | Attach: Attachment B
031a6669-d145-5ffa-96be-99b8ddfd5775 | note | Method - Document Review Visual Measure
f9526c85-2dd4-55f0-96f7-ba7f40065cf6 | note | Frequency - Each element (where greater than 2m)
7a1a4d40-188d-57d5-bac7-4b6e5d380950 | note | Category - HP
9e62286e-93f3-50ed-bcee-707eb8d9985c | note | Responsibility - Nominated Authority
f15ce834-bb7d-5fd3-8988-e184e6d31480 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
011386a0-c334-5c73-857f-e4db1b94d3be | note | Reference - 614.08
b651b14e-871d-5a34-92ef-c78ed2bff7d0 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
b14b62ba-d4c8-5da8-bf9a-301deaa46430 | note | ○ Abutment / Pier Walls with heights less than 2.0 metres
785d41f5-ab76-5723-a003-80c8fd564173 | note | Attach: Attachment C
62b4ae9e-963a-5104-8e91-8c562d22442f | note | Method - Document Review Visual Measure
d56ce79d-2584-5e4a-94cd-032acc82fa09 | note | Frequency - Each element (where 2m or less)
5b310398-57da-5cdd-b281-130c267feb32 | note | Category - HP
bc8f81ff-d575-57fe-aa46-7214f2ec16b4 | note | Responsibility - Nominated Authority
b9c51e71-db06-504a-99d8-ff9ebc5ca37f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
0f326a3a-84bd-525f-b8e9-0286277e4e33 | note | Reference - 610.47 (a) Table 610.472
fb121a3c-af8c-51c6-a819-e7d42a625fe3 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor. Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
42eae4e2-65cf-5b44-9943-36e82b8e6d2e | note | Method - Measure Visual
8f7b4727-ba08-532f-a2a1-c9df7836acab | note | Frequency - Each element
fab95558-0c48-50ee-9914-6634afe8a2d6 | note | Category - HP*
9deec010-37ba-54fe-b57e-9a9cb65f7d85 | note | Responsibility - Surveyor, SE/PE/SPE
e6b2d4a7-cdbe-5308-866c-62dd3809dc7d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Reinforcement Placement
8c276d3a-6cc8-5be3-bb96-6dfcc8e12d18 | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
d8310a15-4ca0-5695-9a68-a9fd6396fe85 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
0fb35cee-255a-52bc-9aca-6da256a2e05b | note | ○ Projecting reinforcement is the correct length and location.
dae3692e-a8a1-5df6-9c2f-bf778ad20ccc | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
f111f4ac-6b54-5e1d-ae7b-f59c5fc16f07 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
cdb83848-a6fb-5140-882d-43df751b1b7b | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
ccfdc1d4-f1ac-5bff-b43a-c3a1eece072d | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
a2df5d04-61ca-54eb-94b1-75ce211f7a18 | note | Method - Measure Visual
aedb503f-44b7-5d6e-8df4-4cc4f9c60b5b | note | Frequency - Each element
e575234f-f692-5fbf-b9ff-5cb1ff709a65 | note | Category - IP
9e07c9d6-887c-5764-bb1b-ff099dd7b44a | note | Responsibility - SE/PE/SPE
f367df8b-ea44-5be6-ab9e-a51ee51d99e9 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Cast-in Items
646a2cc8-bcc9-5344-b4d0-522045c0d59f | note | Reference - IFC Drawings 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
f0387634-2123-50d7-909b-5653ac19cc16 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
b2f8ccb6-dbd9-512c-9b2b-27e8cf0c74fe | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
ae69e47c-0a15-59e9-bd82-54993770b315 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
3dbf5cb5-2a6f-5af3-8143-52ade3ea4f59 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
70307477-addf-5b4b-8272-2127fa09795f | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
598fba33-026e-53fd-987d-2ad0ff1da097 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
d3f06522-2ba1-577e-8b7a-3666ef22f738 | note | ii. Running dimensions of a group of the above = ±6mm
a7037ab5-817e-57da-9a8b-09fe25513358 | note | iii. Ducts and conduit location = ±12mm
672aa8d7-66cf-51d2-a0ca-35881abdcb31 | note | iv. Diameter of ducts and conduits = ±3mm
9c135e1b-87e6-5695-a0e8-f3c4302a5227 | note | Method - Measure Visual
c98b49ac-f9c3-51ec-b468-1f9253c5c73f | note | Frequency - Where applicable, each element
99d7582e-12cf-5e9e-a780-8d9d655b05a5 | note | Category - IP
c96ebfda-1df6-54b6-bfe4-1c364fd47c18 | note | Responsibility - SE/PE/SPE
ecc3e83b-8625-5c41-aa7f-1e0946e4924b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Thermal Differential Monitoring
a8202013-11ef-5f86-999c-be2b61ed637f | note | Reference - 610.22
f14a1acc-ade6-5518-845b-b36580b2ad15 | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
ca621573-7cd9-59c4-92fa-13dad2ff306b | note | ○ Only applicable if the element has:
7d286dba-023c-5969-956a-044b8770ba93 | note | i. the smallest sectional dimension exceeding 500mm
c0acdba0-a9f1-5a59-87fc-16f686d9a05b | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
d91171a9-4fc2-5f98-b438-6c3874487f54 | note | Method - Measure
6b7a86d6-9b4e-5281-9972-3c4102ed71cb | note | Frequency - Where applicable, each element
f03b3ad4-af35-59ae-b035-511c3fb498d4 | note | Category - IP
e26a4e38-14b1-5cce-a571-8af8ba51e636 | note | Responsibility - SE/PE/SPE
4805aaff-f9cb-5e26-8359-2234aa3826b8 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Pre-pour Inspection
36452197-d5c9-5a02-8b05-659328353ac4 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
7226bb6e-5fc2-5688-a504-3f260e13e04b | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
d8a78fc5-113f-551b-98ec-e9eb835e0e8b | note | ○ All foreign material has been completely removed from the forms.
59c63b70-bfab-5f54-a1ea-643d17724901 | note | ATTACH: Pre-Pour Checklist
334521af-6d14-5fae-b924-f9209ce56c84 | note | Method - Measure Visual
9a75ad8f-cbaf-51bd-b757-9e56d735cc78 | note | Frequency - Each element
f81cce6b-229e-5bda-8a49-07def86dc079 | note | Category - HP
93b44549-fd3e-514a-895f-55984728a756 | note | Responsibility - Nominated Authority
e796bf63-11b7-525f-9f4e-ec2ad6e864c3 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Weather Conditions & Evaporation Limits
b876c851-13ad-5d4e-8db5-7d7529b60161 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
a5da213e-0499-504c-b9fa-f81444006bcf | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
ffad82c8-dc38-5565-a829-0e4df8e9fe47 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
f275f17c-b997-530c-9090-63d48fb9e463 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
0a5bbb98-b7e0-519b-9f3c-a13613ebc934 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
6f1c1977-f953-5cca-84a4-eac11ff40fa2 | note | Record: Required information on the Concrete Pour Record.
96878de6-d6f8-5b9c-99c8-34cd73ab1cd2 | note | Method - Measure Visual
fcf2cebd-a494-5d81-90be-b4b6f748b8b3 | note | Frequency - Each element
6dc03ac3-6195-5d24-b616-56692e614f7a | note | Category - IP
82a9845b-ac4a-53d0-bf94-26d55f880b8d | note | Responsibility - SE/PE/SPE
43cc381f-7589-5e0c-96ca-4d47cf6f1673 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Concrete Testing - Sampling Frequency
6cebc993-35ab-5d71-be0f-4151da398f14 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
69c96add-0515-54ce-95f0-95817db8f3a3 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
2e982dbf-c60c-5879-b9d9-96196f0c2e54 | note | 0m³ to 10m³ = 1 sample
6d69af78-9b48-5f20-9943-f6a6ccf9f684 | note | 10m³ to 25m³ = 2 samples
9324c0d2-239b-50c0-b1d1-060e7c53f2df | note | 25m³ to 50m³ = 3 samples
62b378bc-d2f4-52c8-bdf9-4aeef9575cf0 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
33af46ee-b4a9-51a3-8e00-a11e518bd8cc | note | ○ For each additional 50m³ and additional sample shall be taken.
9c9a8e57-7869-5815-a9e3-4a5f33b7a0cd | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
2682ac73-381d-560e-9d5d-9ffee1c00808 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
de258d69-4d80-501f-8057-45ba375ae6c2 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
3c9a4b66-d6b5-5ea6-9e60-9f9de619c1d1 | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
3d8e2bcd-1a97-58d2-90e0-6f65ba2a0e38 | note | Record: Required information on the Concrete Pour Record.
366763af-ccae-5d62-a811-14200c13b9b8 | note | Method - Test
ad79db09-728f-50b0-ba2b-7bad75845e01 | note | Frequency - Each element
ab531d2a-22a9-5692-8488-d8fdac7a8555 | note | Category - IP
030ef53b-dc98-56bc-948a-62e5664d19b8 | note | Responsibility - SE/PE/SPE
5d81b865-2a91-5a9e-9329-8317abb29172 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - Concrete Testing - Slump
1cf18193-eaf2-5c53-8999-fc9e2385b540 | note | Reference - 610.16 (c)
2ced3554-bd21-5538-ae43-3b7f7032290f | note | Acceptance Criteria - Slump testing tolerances =
547e0212-fcc7-520a-af33-a67fc1c28583 | note | <60mm = ±10mm
7da866a8-6987-5f3a-bc23-c072a4722299 | note | ≥60mm to ≤80mm = ±15mm
b4485e0a-ed7f-5887-ae77-20dc56a4a915 | note | >80mm to ≤110mm = ±20mm
24dcf123-08e8-562a-86af-eda9d4b28722 | note | >110mm to ≤150mm = ±30mm
02e3131c-0ee1-5c30-9c8b-f1598a1817a6 | note | >150mm = ±40mm
76c12f8b-760a-52f3-97a4-75c1750c5067 | note | Record: Required information on the Concrete Pour Record.
809b953f-3d04-5c5b-bbbf-7de19466fff5 | note | Method - Test
b07100ea-3878-5946-a4ba-ab1d264c693c | note | Frequency - Each sample of Standard or Superplasticised Concrete
95f6ba66-420d-5aac-9aaa-8466ec7a0d89 | note | Category - IP
03b888ac-4d17-5b37-b405-678a9e827eea | note | Responsibility - SE/PE
cccb95f6-d511-5f65-9943-19a996e6c1a0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
4709a242-c6ad-561e-a9b5-71ff8143a3e3 | note | Reference - 610.13 (b)
b594f2a7-63a3-5429-93f9-4a2f231474de | note | Acceptance Criteria - Spread range = 550mm to 750mm
313a9ad8-50f4-5f8a-8b44-d45a107c5112 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
04371c7a-9b95-5d20-b5a8-a5be64f8e57d | note | ○ Passability = ≤10mm (aggregate height differential)
4016fb3b-0b6e-54a5-ad52-a0d5362e7895 | note | Record: Required information on the Concrete Pour Record.
a91f3b9f-3668-5c89-a50f-8c6c8a01fc91 | note | Method - Test
a3b7a9ff-f186-5e14-9036-b0c3867eaf5c | note | Frequency - Each sample of Self-compacting Concrete
4edb7774-66a8-5113-b143-5eccf7a6fef5 | note | Category - IP
feeca06f-866c-514f-9dc0-4d78740c73d0 | note | Responsibility - SE/PE
44d45716-4a14-5fb8-b734-61e41ee6beea | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
7f2633aa-5999-58a7-8ca6-343036590de8 | note | Reference - Site Sampling & Testing Procedure
4e6e8ee2-c01c-5db3-a37b-dff9e72878f8 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
6bd41850-b446-5380-a36f-13101f597af0 | note | Record: Required information on the Concrete Pour Record.
be144930-05ab-5e1a-8983-9cc938218ad2 | note | Method - Test
7fc2ec30-9019-56a7-9d34-447913639208 | note | Frequency - Each sample
b5bc9922-1a1b-524b-aaf8-dbe318a451dd | note | Category - IP
99cd1cff-2eb9-5c63-bb9d-fdd5606a6396 | note | Responsibility - SE/PE
01e8c5fe-c9b9-58c4-88cb-9197c1b8d0c8 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.14 - Supply & Discharge Rates
8d18a3eb-dac2-566c-8ed2-a3bf78efd524 | note | Reference - 610.13 (a) & (f)
e5a153ac-897f-53b4-a243-a0a53083d697 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
167c8628-f3d4-5137-a2fe-ed2285c4fc70 | note | ○ No water is to be added once discharge commences.
c1c7cbb1-14ab-5722-887c-5d70ea84cac9 | note | ○ Maximum time between batching trucks is 25 minutes.
1004b980-e1e0-5644-bff4-7ec7abc302e2 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
35629a35-b0ee-5a9f-8583-d6127619ca8b | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
30cd0650-8c60-5d84-b555-3b2db07ba204 | note | Record: Required information on the Concrete Pour Record.
d7338f19-5748-5288-a5be-96136fcff6ca | note | Method - Measure Visual
443386f5-8a32-5bc2-a297-d2ba8a23ca57 | note | Frequency - Each load
130d3ef8-2e75-55e3-a0d5-4b847f0f891d | note | Category - IP
b80f138c-f5a0-56d8-94a5-aa57c0f3fa9d | note | Responsibility - SE/PE
84b2f6d4-c846-59e9-8a89-8fbcad7b793e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.15 - Placement & Compaction
5470c3d2-35aa-59b6-b841-2c9e714ef671 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
3569e555-232c-5291-873b-cac2c6438af9 | note | Acceptance Criteria - All concrete batches are traceable.
c74e8431-cbb9-55fa-8bdb-4a813fa888fd | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
798517a2-0409-5a9b-bf59-9f89bbdcf011 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
b16f0833-738c-5647-b07e-cebed38f17e6 | note | ○ Concrete is not moved horizontally by use of vibrators.
38601b10-6458-5941-bd3c-2f4b4f31e50a | note | ○ Adequate compaction is ensured
4580f012-53fd-5e6c-a44e-d485210f0238 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
36bd5c11-ce92-5f09-95ea-4cc5fc801864 | note | ○ Concrete layers are not more than 350mm
4320412f-83e9-51a0-be4d-0d1f0ba3346f | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
9e345ea0-2a80-5eb5-bc06-8500d1d14373 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
0c9aae75-1b1d-5f55-85d7-63b266f5466a | note | Record: Required information on the Concrete Pour Record.
eeb53bd6-f9dc-5bcc-b811-c07397f2dce7 | note | Attach: Concrete Pour Record
7098e6d5-e102-57a0-bae4-81ccfc2b27f9 | note | Attach: Concrete Dockets
03d93f23-863a-5e34-8ddc-11c69e13616d | note | Method - Visual
56938a83-b8a2-5d2b-b282-7ef7af46935e | note | Frequency - Each load
f3051ce4-ae2a-510f-9e1d-8bc938aef973 | note | Category - SP
1f2679a6-44a7-5cf0-81a0-a1b4e1f4cbd1 | note | Responsibility - SE/PE
63db3ef7-578b-52c2-83ca-07d7f3728d83 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.16 - Surface Finishes
db0f08fc-115e-593f-8134-8a8a8cde2045 | note | Reference - IFC Drawings 610.31, 610.20
af3d53f9-2d3b-5362-8d6d-06fbbc55388e | note | Acceptance Criteria - Surface finish as per IFC drawings.
56d7a6bb-9b1f-5e41-a9f4-5ce028ebc9e3 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
323811e5-8203-5ae3-bb70-6eedc9c516a9 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
b32b970e-0b75-573c-bd49-5bbfa595399b | note | Method - Visual
20f4c125-a9f4-5dce-bdf7-e57dbea1153e | note | Frequency - Each element
01609da6-0767-5817-9236-e2342be269c4 | note | Category - IP
f3b3b62a-9326-5bdf-80bb-8826ecb91672 | note | Responsibility - SE/PE
fe6c7fef-75f9-5cfd-b324-8481d57922a5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.17 - Curing-Top Surface
f3f37003-9a00-57e4-b6d4-e2fc1245e395 | note | Reference - 610.23
854dcf5c-abcd-5472-9447-18f8a652f26c | note | Acceptance Criteria - Curing performed in accordance with approved method of curing item 3.5. Minumum curing time per Table 610.231.
a5f18e0b-1439-57c2-92ae-d2d797536e05 | note | Method - Visual
86eb43e9-02ea-5677-ade5-cf450311398b | note | Frequency - Each element
0a2fa990-8d72-58d2-8e5c-73eaba23a5b2 | note | Category - IP
75a26a0a-9c8f-5250-b28e-74770f4a6f2c | note | Responsibility - SE/PE
34a2658c-82c0-59de-a387-2e6bc19dbca8 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
3f71ac54-8a0d-51d2-82c8-f317e4c5f136 | note | Reference - 610.22
025bc053-fbd6-5e1f-ad8f-b84cc78a21c6 | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
e973ffe2-adb8-5df6-8fe5-23ee860af502 | note | Only applicable if the element has:
940ca0f8-fc14-5156-a287-ec5f805491f0 | note | i. the smallest sectional dimension exceeding 500mm
50645f7b-1bee-501d-9fed-22dda19de8be | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
e829d9d1-97a4-55c4-a61a-63e666131f81 | note | ○ The maximum internal temperature of all concrete members following concrete placement shall not exceed 75°C.
daaf505c-7e8a-50e3-bc7e-ae06082fca65 | note | Attach: Thermal Monitoring Report
684e847b-a159-5891-81aa-14015c6217ad | note | Method - Document Review
2c2de264-20e6-5d21-ba7e-e5a6dbbd45aa | note | Frequency - Where applicable, each element
40c30355-95e3-5cad-9bcb-4f1d0ee6f44c | note | Category - IP
920d090e-bbc6-56de-8bdf-5f6f339f9c85 | note | Responsibility - SE/PE
7b9c9fcc-7db1-58c6-b70b-e8b37b9d79eb | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Early Loading
78249ff0-6c8c-5d0a-a762-2bd7f180c0c4 | note | Reference - 610.16, 610.23, 610.36
9aa15222-8f53-562a-a6b1-37cfbb058b87 | note | Acceptance Criteria - Bridge decks, deck overlays and approach slabs shall not be loaded or open to traffic until concrete is at least 4 days (96 hours) old and a minimum compressive strength of 32MPa after casting has been achieved.
2e46a818-82c3-5f0c-97be-46a8c73f0f42 | note | ○ Additionally, early loading and trafficking of bridge decks, concrete deck overlays and approach slabs shall not proceed until:
98392af1-9208-5e7e-a430-c2ded4094487 | note | (i) the Contractor’s early loading and trafficking quality procedure and inspection and test plan(s) have been reviewed by the Superintendent
4586f174-f46a-508b-b87e-526d48dcdd8e | note | (ii) the evidence that the minimum periods stated in this clause have been satisfied and maturity testing, temperature monitoring and compressive strength test results have been reviewed by the Superintendent.
32024b01-af3e-55e6-95a2-4f304516d9fc | note | Attach: Concrete Test Results or Maturity Test Results
8ed32170-39d8-5758-a24c-1bcf1c40e388 | note | Method - Document Review
07a79bed-edeb-5556-85e1-f43a458b2280 | note | Frequency - Where applicable, each element
a5369af9-c8e6-5eae-afa4-a2fb4e2763cf | note | Category - HP
9024f14c-18b5-504e-bb3a-29078b71c545 | note | Responsibility - Nominated Authority
253a1dcb-9966-5573-aa71-beca22222167 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Surface Inspection - Cracks
0da6c72e-3b88-5023-bb02-0464a4b63d84 | note | Reference - 610.24
73235ebe-2ccb-51ad-b483-869d898f8b30 | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
9963ea30-8eb5-5dad-848f-33809623479f | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
c1df77c1-2954-50e4-908e-ef46570c0730 | note | Attach: Post-pour Checklist
7cdf5482-336a-5f52-b782-85eefb0ffe0d | note | Method - Visual Measure
0220259f-699d-59b3-bb73-088a009776db | note | Frequency - Each element
5ddde942-f2e6-50a4-b3e5-71371cb5620b | note | Category - IP
5d8a52d6-2357-5035-b957-87a2b9f9bd18 | note | Responsibility - SE/PE/SPE
cda30299-a2d1-5f97-8bdd-fec82275b4b7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Surface Inspection - Surface Finish
9dd8ee5a-fde2-5097-aa61-bf312f3d96d4 | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
008928aa-167d-561f-a5dc-331e64d0428d | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
24ec8d48-8630-5784-9fed-8902c7510242 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
c422cdca-d632-559e-9497-fc7824952bb9 | note | Attach: Post-pour Checklist
480e7f0a-1d40-580d-8d88-d125c74bdd57 | note | Method - Visual
f02c2429-c44b-5e68-a7f0-377cc0ce10ee | note | Frequency - Each element
279ba513-b334-5651-b4f3-3e0b3cd46d94 | note | Category - IP
16ddf465-52c2-5cf1-a530-33fa3fdd5b69 | note | Responsibility - SE/PE/SPE
f46ceecc-b4fe-5f01-b5c7-04506d5ec4dd | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Measurement of Concrete Cover
976ec870-2171-5b4f-a05e-abf987f2947a | note | Reference - 610.34
23a2e446-9a3e-56bf-b186-bb0bad3c4023 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
890049f5-07e2-51bd-b315-d487430c3c45 | note | ○ Minimum 10 no. measurements recorded in each area.
e429cf39-d33f-5290-b795-514887536070 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
defc3e53-3273-539c-9e5a-a36e709e0b85 | note | Attach: Covermeter Check Record
6106acb1-a3cc-56ba-a32d-84b277f2031f | note | Method - Measure
c2daa536-41c9-5e8b-98f5-a7416b78ff82 | note | Frequency - Each element
64995d05-bfcf-5d44-bb42-587c7ed4b803 | note | Category - IP
16223a86-a147-5b1d-93b1-f932622e2747 | note | Responsibility - SE/PE/SPE
caace0f9-1de0-54a3-857b-c88bc39d985a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
47f14d67-adb8-5a46-a77d-8584ad97c5c3 | note | Reference - Placement of Fill Material Against Concrete 610.35
0b16355d-8b4a-575d-b130-ad1aca446f9f | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
e7f4f0d4-e55d-5908-b6d1-0419b2a987b6 | note | ○ Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements as per VR610.16(l) or maturity testing requirements as per VR610.16(m).
d7be559b-4788-5623-b5c9-1037e3076614 | note | Attach: Concrete Test Results or Maturity Test Results
bc23aa16-af41-5e4c-accc-073cbec7ab85 | note | Method - Document Review
ee83776f-9af0-5e13-9218-0a5c6bd15b9e | note | Frequency - Where applicable, each substructure element
f86e11dc-445b-5d52-8d3b-a3d98985286c | note | Category - SP
0713becf-d8f1-5818-be1d-b4b63d108440 | note | Responsibility - SE/PE/SPE
2b4826a8-6233-5b11-8227-ce0d72cb96ae | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Compressive Strength Test Results
1b0a9739-be1e-5d8f-8564-0ade903704a2 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
c9927e44-f482-5796-a723-6a794f65f418 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
5d696e94-63d1-51ce-bacd-2f1dfcc5e1c9 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
b7e92b5e-4f05-5074-acb2-0d74a8fe79c4 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
40d3c69e-a733-5268-9419-f773e7c73b7b | note | Attach: Compressive Strength Test Results
bdfad011-f9c9-50a0-89b7-d4a113655764 | note | Method - Document Review
1864bc14-74bd-5cbb-bf62-28bf42c5a0fd | note | Frequency - Each cylinder
2caac40c-4fce-5743-9c90-3f9f104c0e97 | note | Category - IP
6a05eed5-f6b3-5726-a824-299424605c79 | note | Responsibility - SE/PE/SPE
f96cbba1-d903-5475-a674-72a9fda1ebf6 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.8 - As-built Survey
984a1472-cefb-5590-9050-45e2159ac79f | note | Reference - IFC Drawings 610.47 Table 610.472
3532f5bf-9ef7-5059-9eab-37439cafe2d9 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
a18dd80d-9ba0-5ad8-b083-2a2eff4cf314 | note | Attach: Survey As-builts / Survey Report
ba57426f-fa68-5996-88c6-369f5d0625df | note | Method - Document Review
2a818aed-3ea8-58e7-9707-4b0174260758 | note | Frequency - Each element
abf3ff78-a1e8-5d98-b5d2-aa50236022e2 | note | Category - IP
580b22bb-0e19-5593-a24a-382fbcd1bd1d | note | Responsibility - Surveyor, SE/PE/SPE
dc081eb2-f69c-573f-ba7f-6d5cfe30961f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
fe59a14c-38a2-5317-aa06-dfb06e5dc590 | note | Reference - MRPA Quality Management Plan
27f2727b-aadf-55e3-b9dc-5a30bf1aaab4 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
71a2c445-bcd0-5c96-bf65-9ec86a74ed60 | note | Method - Document Review
2acfa167-a9c9-5653-99a1-aa246cb79639 | note | Frequency - Once, prior to closure of this lot / element / Work area
ae83a69d-6205-5e5d-995e-5a7169645f9a | note | Category - HP*
dc5e2224-b53e-5a95-8ef6-96d94bb0cb9a | note | Responsibility - SE/PE/SPE
e0bb57a4-dde8-56db-a520-d2d3a23c7aae | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
a80c0761-eb82-589a-95d0-a6fb7fd29bbb | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9975b968-60cd-5c05-b609-6e8b45bb33ca | textbox | Name:
e35660b6-a269-5754-a74d-9e612a71b714 | textbox | Position:
fb51cb57-b4c0-5ed4-b626-da8a8d269cad | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-104-STR-BRUNT-Structural Concrete - Bridge Diaphragm | itp | ITP-104-STR-BRUNT-Structural Concrete - Bridge Diaphragm | fbaaaeff-e216-4eb1-8153-6e6c54dab383
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
70845ec0-f2fc-5658-9ee3-facdfa075607 | note | Document Title: ITP-104-STR-BRUNT-Structural Concrete - Bridge Diaphragm
e41fef3e-5d58-56c6-a4f3-82b51adf1024 | note | ITP Description: Diaphragm FRP
4994e6e9-0c3a-5fe0-91d8-bf66ca779be4 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ec7e657e-abb7-5f71-95b9-14f589ec993b | note | Discipline (e.g. CIV/STR/RAIL): STR
e77aa636-d84d-53d2-9866-b513bd7b5bbe | note | Revision Number: 0
5b1bf125-c9cb-5c16-8799-1d194c198bd7 | note | Revision Date: 31/10/2023
d2eaa0d0-a271-554f-81a0-6decf9621378 | note | ITP created by: Yasna Naicker
f1a42e23-342b-5095-900c-0e207c280029 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
9e619646-d977-54a7-a27c-9db3b0da9a68 | note | Reference - VicRoads Section 602 October 2007
| checkpoint | 1.2 - Non Dependent
6560ca94-ec36-581c-b47e-ce4f2964610b | note | Reference - VicRoads Section 610 February 2020
| checkpoint | 1.3 - Non Dependent
863d7969-0397-5fd7-8833-23e7171bb5d6 | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
c7d24802-9d96-5824-b37b-1ece0d449484 | note | Reference - VicRoads Section 614 June 2017
| checkpoint | 1.5 - Non Dependent
58337738-e510-579a-a64c-fe536d158036 | note | Reference - AS3810.1 2018
| checkpoint | 1.6 - Non Dependent
75391a86-f789-5e50-8377-990a00fdc7a1 | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
95a745b0-e67d-5b54-8bb7-307eb1f53ee6 | note | Reference - 610.07 Table 610.071 IFC Drawings
90788ec3-d31d-58d8-a6d2-c5a5b327fb27 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
91ed31eb-a5d0-5139-a254-2649be9a1246 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
3f3c2634-2566-5775-8640-b7914e72fc60 | textbox | Enter: Teambinder Material Approval number
03619d26-7a4e-5967-9204-0e5f0c75bea1 | note | Method - Document Review
468aa27a-1ca4-500e-afb2-e2091712764a | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
88ac9c4a-254a-5e75-b738-7ae215465cb0 | note | Category - HP
b2dd4e88-ede2-5cb2-970d-6a6aba49f33c | note | Responsibility - Nominated Authority
f2e1d4aa-9984-5ec8-952a-b0e4c09459ae | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
fab038d2-be24-58fc-8980-ebb23016e2d1 | note | Reference - 611.05 (a)
e82fae9f-491a-54dd-86a3-25287cd2e4c2 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
dfd2f920-6572-5d8f-81a1-d529d3ad6fce | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
94ed4f99-fefd-5349-a808-c0961e8813f7 | textbox | Enter: Teambinder Material Approval number
b86ce75e-af7f-589a-b957-c899a957a496 | note | Method - Document Review
e88f032f-4e2a-5f00-bb76-31415636ce01 | note | Frequency - Once for each supplier, 14 days of award of contract
62ace6eb-4383-5205-bc81-0d3db4579416 | note | Category - HP
b3b854d3-d711-5c85-83d6-dcd95dc7f524 | note | Responsibility - Nominated Authority
0d06f6e9-0879-57a4-b843-89e0f323990f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
58d1a80b-7153-5fbb-9795-c28ec9873eee | note | Reference - 610.26 (a)
626059af-7b6b-52c2-a60f-7438bf72b8fa | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
a807ee4c-3ccb-5888-85fd-0033896777af | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
ac73830a-41c0-5cc8-8be8-f1c1fa29d4be | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
4b4879bc-5672-5429-ba4c-0f9a0654ae62 | textbox | Enter: Teambinder Material Approval number
03973472-8066-5267-b98a-cea4cca8f930 | note | Method - Document Review
5340cc3a-43f3-5f4f-9eab-7eefa6c4f8fd | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
76dcaaba-757f-5bed-aa74-d64c0ace4a1e | note | Category - HP
7fe7ab20-7df0-5940-b268-411f91a6dca3 | note | Responsibility - Nominated Authority
70ab0965-7aa8-5421-bd98-44dc814c5232 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
81fce02c-9987-5560-b5b6-f2fc12825fbc | note | Reference - 610.17 (f)
0a31618b-c353-55cc-9f2c-703d587eedbb | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
2160266e-6133-52dc-9206-985b4e69302f | textbox | Enter: Teambinder Material Approval number
a28f02b5-1894-5446-b163-d916739442a2 | note | Method - Document Review
ee6cfac4-cc80-50bd-b663-e85f3e02cec3 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
fe82fd3f-397b-515a-8c3b-985f81f68cdb | note | Category - HP
fd884d4d-d833-5372-9887-eec8d875549b | note | Responsibility - Nominated Authority
9690e9ca-1d51-51bc-975a-20756d1e9064 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
276eb2f1-0da9-5f45-9cd6-dbfc06fefe4e | note | Reference - 610.23 (d)
c0ef7f33-f48e-59ce-9e98-5959b64cc52e | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
9d83785d-491b-58dd-bd12-b82e51731d12 | textbox | Enter: Teambinder Material Approval number
6efa6f07-0e4c-5650-ad7c-f74aed933a07 | note | Method - Document Review
2b0f3903-d80e-528c-b6f1-4e292bb4e121 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
14e28a58-6620-5dd6-81e5-1369d2391972 | note | Category - HP
ca6a151d-cd9e-54b6-844e-efd6a7c05c77 | note | Responsibility - Nominated Authority
23cd0c09-aae6-5351-b9a6-a4cec3ca6ffb | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
afdd07b5-a95e-5992-a11a-9ff8b682e7bf | note | Reference - 610.18 (a) (i)
6a64afa0-fe8f-5a17-9ad1-21a026458684 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
ba749a77-7c53-543d-8a78-eb3937b94a90 | textbox | Enter: Teambinder Hold Point Ref Number
d6f4798f-abac-5102-a85e-a0caba895f11 | note | Method - Document Review
6d0055fb-47b4-5d3f-a157-03c2032494f2 | note | Frequency - Once, 4 weeks prior to placement of concrete
4ab42b78-5ec1-527b-a345-aa8f23bf065b | note | Category - HP
903a3503-c320-5024-8f24-c98bda575491 | note | Responsibility - Nominated Authority
78fc32e6-a387-55fb-a49f-fb897747e57a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
f02690d5-c4cb-56bd-a668-6d1b7efb8711 | note | Reference - 610.18 (a) (v)
a085b624-b824-5d2a-a508-5048fe5a4303 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
b46775c0-2748-5ee9-bed4-60438aec44d1 | textbox | Enter: Teambinder Hold Point Ref Number
517bcdab-57f1-56d8-9b57-a5c59a42bda2 | note | Method - Document Review
27e52b7b-251a-56ad-9fe7-09961f351c10 | note | Frequency - Once, 4 weeks prior to placement of concrete
8484c673-5aba-59c8-b8fc-78123381379d | note | Category - HP
391382db-bb30-5f05-b5e1-86ea1a03a3f1 | note | Responsibility - Nominated Authority
a9e727c9-ec5a-544d-98ae-9746b77d41f5 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
30364584-a2d3-5e35-b57e-e5463b71e8fc | note | Reference - 610.18 (a) (iv)
e7de72e6-870a-5c08-9a5f-4748f2ea95c8 | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
e220e5d4-31e3-50cd-9f1a-06e0ecb01427 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
76c85fc0-cc51-5594-9885-17ad6d8b6f89 | textbox | Enter: Teambinder Hold Point Ref Number
dba8b650-ef5d-5d07-b1d8-8b651b1eb400 | note | Method - Document Review
0730a31d-45ce-5323-be66-ecaf4c82e323 | note | Frequency - Once, 1 week prior to placement of concrete
0d3f777f-4d5f-5efd-b87b-918878520810 | note | Category - HP
3bc94652-04d2-5ad7-8cda-c5a3a6e1d416 | note | Responsibility - Nominated Authority
dffea76c-0554-5c5d-99ae-c29338f8e954 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
6fa350c1-1a85-5ebb-aab6-185b534a9a00 | note | Reference - 610.17 (a)
b356d154-18d3-5c8f-86ba-4fe6bdfba616 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
543d271d-9e68-563e-bf8a-a02992aedafd | textbox | Enter: Teambinder Hold Point Ref Number
8d59d88b-d969-5588-a411-63cb0154539b | note | Method - Document Review
22696e09-3c26-568f-884e-e92379ae8839 | note | Frequency - Once, 2 weeks prior to placement of concrete
fa60c055-6c7b-5568-9288-6ad77e8dc7c5 | note | Category - HP
32241c5f-cbf4-5f93-81a9-48ea102b0ccc | note | Responsibility - Nominated Authority
c34e734b-6a17-5457-a518-ff1a62799c6d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
a7c5baa8-1910-5908-9b24-8ad0518c5546 | note | Reference - 610.23 (a)
e82e6f3d-e7fb-5e1f-82a4-7731af5f7d1d | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
47e3c3af-352e-5922-89f9-61458f1d4240 | textbox | Enter: Teambinder Hold Point Ref Number
657dc915-6b9e-564f-8077-df3bb5848ba3 | note | Method - Document Review
e59fa4e5-0b3c-5adb-b470-4a746668356e | note | Frequency - Once, 4 weeks prior to placement of concrete
511dd94c-f9a4-5ae6-820f-8e8d86e74316 | note | Category - HP
99a6cdcc-4b59-5cc0-8947-2ca69455d56d | note | Responsibility - Nominated Authority
02380df9-cfe1-5a97-b267-96755399c3c6 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Concrete Drilling Procedure
e1df8930-2d5b-5c2d-93e5-830261b91efd | note | Reference - 610.46
6a42faa5-6736-5905-8b6f-a86be2e5eba4 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
26108313-9dde-5eac-bfed-828e132b66ca | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
661d16f2-f2cc-588a-bea8-442ccb80ad39 | textbox | Enter: Teambinder Hold Point Ref Number
156f0337-d51f-5c81-b589-bc5b4b5f6726 | note | Method - Document Review
aa6f3f69-b107-54b0-981e-2001e3460cb5 | note | Frequency - Where applicable, once, 2 days prior to drilling
28ee3cf3-2dcf-5681-a811-da3362696cc9 | note | Category - HP
198d2caf-3a55-53b3-a566-87afb10fe1a1 | note | Responsibility - Nominated Authority
a7c1f692-ae23-57d1-b5c4-e85b9d577b0a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Temprature difference measuring-Calibration
82004001-f92f-580c-861c-e57087fc57c8 | note | Reference - MRPA Quality Management Plan
5f103692-76e0-5be0-9116-d68a6390d5c5 | note | Acceptance Criteria - Calibration records for Themocouples are valid and up to date.
9433c1cb-58f8-5155-a61f-354be71f6e9f | note | Attach: Calibration certificate
70849938-52f0-57b8-83a7-558e79bdc9bf | note | Method - Document review
db845aa2-9010-597a-bcd7-7f184bbea2f7 | note | Frequency - Where applicable
fbcf1777-ba0a-5761-9082-1288de077d79 | note | Category - HP*
faeea5c6-9ec1-54ac-9298-e7fe576ea779 | note | Responsibility - PE
8a83442d-88aa-560e-853a-22bf64827ab1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
bc8d2322-91cd-52a9-b364-06a073bf0d37 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
8513b706-7f8f-57ad-b8b7-805a6868e1e1 | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
c4c35dd4-ec3e-56a9-b6ce-774fa7441655 | note | Method - Document Review
cdb89ac8-0d0f-5398-b491-6b7d7cfc80d3 | note | Frequency - Where applicable, once, prior to welding
34666a9d-e0af-5fa4-bdd2-3212c108c78c | note | Category - HP
755349cd-4843-5ec5-88d8-b5ecdfe1cbc2 | note | Responsibility - Nominated Authority
07a25732-8dc4-5dba-a7e9-ec4705ad335c | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
0983ccd2-e39a-5065-91d4-f320eac4b989 | note | Reference - MRPA Quality Management Plan
b5f24957-cd91-515c-afd7-259e22c25e0e | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
00e03b22-d9f6-530d-abe9-a9ac17fb9def | note | Method - Document Review
7789e4ba-0c7e-5b3c-beeb-3bbe20dc7ed7 | note | Frequency - Prior to starting Works and at regular intervals
6d591ded-86c8-5623-b058-079be133b610 | note | Category - HP*
c0f75afd-bb26-57b2-80ac-c5914509a890 | note | Responsibility - All
d48829e7-3f09-55e6-8836-9f76d7f1042e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out
7f839a42-f319-5b99-b633-cc5eeee6f35d | note | Reference - IFC Drawings 610.47 (a) Table 610.472
2a86f471-573b-5acd-b5e7-4c3f016323fa | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
ce222207-eb3d-5e0c-81b9-8682dadc0fa5 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
721e746a-383c-5cda-b557-a2722ab47db5 | note | Method - Measure Visual
c983c9ac-7467-525e-9ded-05d4dd0b52d9 | note | Frequency - Each element
f3ef27ab-60f4-53f2-8653-c18426aab321 | note | Category - IP
df05417d-6593-5d74-96c7-9df04ff4744b | note | Responsibility - Surveyor, SE/PE
e0fb6823-4082-51f1-9dd2-226f023d6c22 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Substructure Work Lots
8930553c-acd3-59b9-8517-42f0b64e859b | note | Reference - TeamBinder Work Lots
7d4e16f2-1693-59a9-aa92-4b01973d53d2 | note | Acceptance Criteria - Related substructure work lots are closed.
60eef6b2-d049-5da4-adde-10f9e0cfe139 | note | – Design strength is achieved for pilecaps, walls , crossheads
426613fc-d841-52cc-8b74-af237078a8a4 | note | – As-Built Survey performed
d2da88e5-c5ab-5721-a73a-8f29d1b63c4c | note | – Related substructure NCMs are closed.
c511e58d-5e07-5c98-a36c-d7ad0262ffae | note | Method - Document Check
2e0706ca-e227-530b-aa9c-fa1c234bce72 | note | Frequency - Each Element
919a4110-0f95-5dca-8ca4-7ebc49755746 | note | Category - HP*
ef9311c6-8df0-5619-8940-755c6aae33d5 | note | Responsibility - PE
6935ecb1-dfdc-58b8-af45-f64f618bfa0a | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
ec07e0ee-af03-54cb-8fe4-c791ceee27af | note | Reference - IFC Drawings 614.04, 614.05, 614.06
df074e73-095d-5672-a59a-7a0a10f5164c | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
ee69fe19-0776-5ebb-a566-6ede04d48eca | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
672f8070-f48f-5087-909b-ce4912e46c7c | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
ea2e9236-bd59-59c2-8cc4-76015eff9bea | note | Method - Document Review Visual Measure
45e45cec-119e-5ef1-99b5-018f1113c9d1 | note | Frequency - Each type of element
ce417146-2be2-5cbb-a25b-30e9f3488bf8 | note | Category - IP
052dc7ef-7225-5e5f-bdc9-77bc62488515 | note | Responsibility - SE/PE/SPE
16145dcc-333c-53ec-890f-7821c0fbb667 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
1c8f86bc-e7b9-555b-9533-71c674c9de82 | note | Reference - 614.08
1e385c85-8ba7-5f83-bc82-376987c995d8 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
b3ee5f7f-b512-52c0-a52d-dcb9f3b4ec01 | note | ○ Abutment / Pier Walls with heights greater than 2.0 metres
ba461b3d-658d-5ce9-80c4-2ba014c92dab | note | ○ Any member for which self-compacting concrete is proposed.
600bbbf1-fbc3-59d2-a372-0ea70c62a610 | note | Attach: Attachment A
0bff7299-e8c1-59c9-b765-4dc6047f3977 | note | Attach: Attachment B
4697596b-2ec2-562e-a0a4-aa5fba222651 | note | Method - Document Review Visual Measure
3ecc6ff9-1e83-5f74-8794-fe3cf2d9ab4d | note | Frequency - Each element (where greater than 2m)
49e676b7-94f7-5427-8553-d4f1c4776313 | note | Category - HP
34ed1c68-695b-5f75-b751-b6aebe883272 | note | Responsibility - Nominated Authority
517a801c-611c-5e0b-82a3-e57a1da4e15d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
bc732d7f-4291-5473-ac7e-6a7a38542e45 | note | Reference - 614.08
3e3215fd-0b63-58c1-bfda-5215da15a6f3 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
392f89d6-e389-5b38-89b4-118bc44df56e | note | ○ Abutment / Pier Walls with heights less than 2.0 metres
25475c4a-8137-5d6f-957c-dd2da52ecf1e | note | Attach: Attachment C
6cad838f-89ac-5713-92d9-5877c7bae216 | note | Method - Document Review Visual Measure
480ac442-0c33-57e4-87f6-b429d2b19f85 | note | Frequency - Each element (where 2m or less)
043e65b6-30c3-5692-b7e9-76e4c30ce9dc | note | Category - HP
8a354b42-8e22-5d06-9252-8843f711db3a | note | Responsibility - Nominated Authority
ca122675-e06e-5b31-bd04-7c6d6d363d4a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
9fc20df3-d6ff-5c6f-af81-f80799b2cc51 | note | Reference - 610.47 (a) Table 610.472
943f818b-8853-5898-a581-64d11717fb18 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
aec3b4e6-e931-51ed-9952-459cbb2cd16d | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
76fcd3da-6fe3-500e-b7a3-35a9465a1112 | note | Method - Measure Visual
eef1b2dd-e014-5971-8d6a-a8c294026ded | note | Frequency - Each element
c632d194-e6f0-56f5-8a10-644c19ac1a1b | note | Category - HP*
ccacd81d-462d-5e7d-ade1-750369d26350 | note | Responsibility - Surveyor, SE/PE/SPE
376a9e08-9819-5e28-9951-772891209fa6 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Reinforcement Placement
8dd0bf91-6172-5f78-b311-eb4053d3ea67 | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
8df2f5b6-f852-597a-80b8-f7b6203c2cb4 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
fa2aff87-e1d4-57ff-b35a-9a96e334fcba | note | ○ Projecting reinforcement is the correct length and location.
7012d63f-8478-59a7-af5c-f5adb072845b | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
7ff43705-bc2d-59f3-a89c-3629ed90a900 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
17c893a4-90d1-5f2f-b0fb-3fe45360ec20 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
0381e004-25cc-5be2-a6ae-34f7be285309 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
450394a7-6c82-58fd-8986-afeae8e73fbb | note | Method - Measure Visual
b4db8513-fe07-51f1-b289-5b89489b7564 | note | Frequency - Each element
206d49df-82cd-5e63-97bf-2cb1f617f6f6 | note | Category - IP
3305913b-8f48-5165-ada6-6bbaa4d57278 | note | Responsibility - SE/PE/SPE
e1de13cb-126d-5f37-94ff-0e850fb18493 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Cast-in Items
8490407b-d81e-5e7f-b558-bd85100b6ef3 | note | Reference - IFC Drawings 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
d925f320-f023-57a2-a572-80a569b7ea6f | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
59f1f684-c7b9-52e9-904b-63b6bccf33b1 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
55bd91e1-b015-545e-aa0b-cc0ba20084bf | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
466e0add-adb2-5222-809d-9c0b34dc5be8 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
0ae337b2-bcc4-5729-9d5c-15b644e9b0a4 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
187e9de7-731d-5141-8f8b-9c4067c0ed1c | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
7c7d4d46-7ec1-5edf-b3b7-18db75da4e7b | note | ii. Running dimensions of a group of the above = ±6mm
c02fabb7-efcb-5af2-ac8e-785b6d8521e1 | note | iii. Ducts and conduit location = ±12mm
58d8204b-6b60-5313-bb6d-7bced3954da9 | note | iv. Diameter of ducts and conduits = ±3mm
6f6a73ed-1842-569e-9489-cead428f67a3 | note | Method - Measure Visual
ab6c279d-0eb0-5c04-aa9f-71cbfffdd9d6 | note | Frequency - Where applicable, each element
a226f414-386f-5b6d-8842-c0c5539b2cfc | note | Category - IP
f32c37d3-386a-5e6f-b83c-01c6d2a47ee4 | note | Responsibility - SE/PE/SPE
14e28648-d3d2-5d9b-a33a-5e0114bf76a6 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Thermal Differential Monitoring
835732c8-5209-5f87-8613-98212064ad9f | note | Reference - 610.22
f6f2843f-09c2-5fd5-b2c8-c72461f28bb3 | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
6a2735a0-ce93-5748-a297-a7f8be6f55e6 | note | ○ Only applicable if the element has:
6b825006-5c8c-5c18-a204-ae77bd57c3a8 | note | i. the smallest sectional dimension exceeding 500mm
de2d94ee-f164-5143-8d13-8285ad2c637d | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
344db5e4-b614-5ea1-953a-d011207861fe | note | Method - Measure
654fa473-a386-57db-adb9-0cd6331a425c | note | Frequency - Where applicable, each element
4fc2921c-a231-5f13-9623-0636308d4840 | note | Category - IP
a11cbe48-da80-5fd9-86fc-266216214e42 | note | Responsibility - SE/PE/SPE
5cebc70c-64d3-5239-b86a-721b6dbde0fe | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Pre-pour Inspection
cf2cb935-9809-5895-9bc0-be1fde0edd60 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
d87c3145-e5f7-5cf1-99ff-5709e107e5c9 | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
4e3ab4cc-258a-564b-95a6-5a714211176b | note | ○ All foreign material has been completely removed from the forms.
c153338a-9eb7-5906-b775-c46b9efedba7 | note | ATTACH: Pre-Pour Checklist
69baa190-1eee-574b-9ff3-df68812288ab | note | Method - Measure Visual
3a2b1ce8-a97e-5d4f-b59b-776f89a7cc43 | note | Frequency - Each element
fd9bc441-56ee-5e1e-a6a4-aeeee77b7067 | note | Category - HP
e5a4ef47-c91b-54c0-9fdf-a185cfae9e43 | note | Responsibility - Nominated Authority
f5529d75-6bb4-5d70-9b01-3a16f24ac18f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Weather Conditions & Evaporation Limits
67324544-5e90-5c8f-9396-8e4e2fab93d3 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
1f3db232-e90b-5c2a-ac63-7ae9ef16ba21 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
68d1d5c3-6497-5566-b687-35e3b63fb123 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
040b8a44-cf57-5c05-a870-241b428a28c2 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
530b7755-38a9-5eae-8106-7e9d65dd96b3 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
408bfef1-d11a-59b9-a8d6-bbcc81ab96c0 | note | Record: Required information on the Concrete Pour Record.
c27b98d1-3b5a-5d15-ba9b-409552e83d6e | note | Method - Measure Visual
dc079504-9ab3-5ccc-b2fa-0eac7f2369ae | note | Frequency - Each element
813be2e8-5687-5dae-83af-ea565923872f | note | Category - IP
2dc65598-f1be-515c-8786-a40da0c7c7dd | note | Responsibility - SE/PE/SPE
ebc3c3c5-3088-59de-9cd4-a119103bc9cb | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Concrete Testing - Sampling Frequency
0429f317-d184-5a2a-85b3-e89ad334031b | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
6733748f-21cc-5bc2-88f2-701c9033271c | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
03ee384e-e30d-565e-a381-4de559363e4e | note | 0m³ to 10m³ = 1 sample
efaa93cb-7167-5b0a-b83f-05c9be84ab23 | note | 10m³ to 25m³ = 2 samples
75a794be-cbb6-5d7b-b092-cb1bb39725a2 | note | 25m³ to 50m³ = 3 samples
f6676c25-d448-549c-a4cf-c54faade1834 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
9ea06bae-d040-5a98-8780-96c2b8c90a53 | note | ○ For each additional 50m³ and additional sample shall be taken.
fabbb3f6-08c5-50b3-ac8a-e0594977500a | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
52b34d7d-f685-54e3-8f6c-383b9dbafcaf | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
da65fafe-e2ff-5de8-9f7b-9ea30a8fb941 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
e39f3300-0cc3-5583-bdfa-e7a8f003af33 | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
459f41be-8d1d-51ad-8dc6-83d66278bd40 | note | Record: Required information on the Concrete Pour Record.
6c21d60c-2d98-541d-92fc-52abb6284240 | note | Method - Test
ebf3b69b-6eae-55fb-8940-5f5c8248d97e | note | Frequency - Each element
0844ac0c-dc62-5a9d-98d4-01cef3296c57 | note | Category - IP
3e0db8d1-cdd9-547e-b407-7ea5604cecb5 | note | Responsibility - SE/PE/SPE
d67db20f-10d2-5121-8916-62ef3dd6f8c5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - Concrete Testing - Slump
fb39965f-4b08-5c75-8550-a2bbab4bf23e | note | Reference - 610.16 (c)
1467e0f5-f9b0-58ad-9f20-7532d1bcee3e | note | Acceptance Criteria - Slump testing tolerances =
abebb718-f50e-51b8-8c52-5745ca564359 | note | <60mm = ±10mm
24c94434-0c70-59bf-9cf9-64a9c673ea0b | note | ≥60mm to ≤80mm = ±15mm
c4b63afb-0d03-5bc1-b515-272784438e3c | note | >80mm to ≤110mm = ±20mm
2b2b4c43-9425-5623-9198-6d36122e8215 | note | >110mm to ≤150mm = ±30mm
90b5923c-feeb-5193-a704-9c648672afd4 | note | >150mm = ±40mm
dd20fb8d-4c4a-554b-8ae9-66a2bb68fe3e | note | Record: Required information on the Concrete Pour Record.
e3495b7c-c735-55f6-99ef-1488db98e47a | note | Method - Test
45980ff4-c58c-5191-a448-1dc102dd5022 | note | Frequency - Each sample of Standard or Superplasticised Concrete
20d3eb49-7f72-5bbb-8636-ac126132a307 | note | Category - IP
b027383b-78b9-500a-9e20-3d7f9394172f | note | Responsibility - SE/PE
4b747c38-9a79-5ce5-872f-3c428df63b8a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
2a669993-f967-5986-86e4-0a865155ca47 | note | Reference - 610.13 (b)
d5ed2a8c-01fc-5632-8b58-55c138faba92 | note | Acceptance Criteria - Spread range = 550mm to 750mm
e53d1720-e9f4-51ad-baba-808411be0ec2 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
5e39e1b7-b123-51df-830b-fa74c16aa611 | note | ○ Passability = ≤10mm (aggregate height differential)
855b6796-2dee-559c-b140-216b0cd52b3d | note | Record: Required information on the Concrete Pour Record.
010f61ec-8bd8-55b6-b565-8facc41b8abb | note | Method - Test
9b2de051-bd13-59ed-874a-21b3c3c9d623 | note | Frequency - Each sample of Self-compacting Concrete
af27f7b3-ddfa-5b26-9aa4-d683a98044d6 | note | Category - IP
312947df-51d8-5c0d-98d9-9738b16a20b7 | note | Responsibility - SE/PE
8d8c9ba4-fa30-56c5-9b3a-a4500c1de9f2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
53f9e18a-2cfd-54fb-926d-3a43f9aeb2c0 | note | Reference - Site Sampling & Testing Procedure
a646988c-85d0-5316-9fda-2d9a25c06569 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
321f495a-2e0e-5ca8-99c6-08619e4805d3 | note | Record: Required information on the Concrete Pour Record.
b6b0f23c-76e7-5734-8c12-4c6ac0cbb3c1 | note | Method - Test
2a31da53-163a-56d2-bca0-2b9304335a44 | note | Frequency - Each sample
e3c59549-9394-5201-ad17-3993c068c52a | note | Category - IP
c8c29c3c-ee01-5883-8e58-ffac97dd1c2c | note | Responsibility - SE/PE
83e6a9b9-58dd-56c9-be63-cef6e011c4c3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.14 - Supply & Discharge Rates
81d898c7-2dca-5144-b927-42e188f8b19e | note | Reference - 610.13 (a) & (f)
9af2b053-6c5d-5e96-8230-0c251f0dfd5b | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
7d42cd03-2999-5c91-ba53-3ef31848b100 | note | ○ No water is to be added once discharge commences.
2f970917-b08e-5521-a293-5cd6f84b7c34 | note | ○ Maximum time between batching trucks is 25 minutes.
45d1d0f3-8e19-519b-ae68-6eb277f400ae | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
6ef9dd84-0ff4-5d7f-86d6-ac63be7ac8be | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
f671209c-1fd1-598e-9a59-d6206dc7d669 | note | Record: Required information on the Concrete Pour Record.
9965adf0-a873-5e99-923d-a49a3e578bf4 | note | Method - Measure Visual
ca4f4b43-b6c5-5761-8381-62bf3f35d675 | note | Frequency - Each load
6db16667-e2c1-5c2a-b25a-bb66163d4d3d | note | Category - IP
a2e8f2f4-f7e8-5829-8fcd-d438628d7363 | note | Responsibility - SE/PE
503e85cc-f18a-591c-8d8f-98c4bf2f31ef | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.15 - Placement & Compaction
d0ccd757-e0e3-5011-9ce6-1cc55587eea2 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
3184663c-9f60-5016-93c6-44f44f3993b6 | note | Acceptance Criteria - All concrete batches are traceable.
5373ead3-1b47-5d67-a77c-80131aa2ee74 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
6d94c32a-6aaa-53f4-a200-651e21a440e1 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
72f459c5-a88c-551b-9484-6a37397a4336 | note | ○ Concrete is not moved horizontally by use of vibrators.
5e6f8d52-cf0d-514e-a3b3-9820fa8631bb | note | ○ Adequate compaction is ensured
f24bbafd-5338-5bf7-b6b0-73575a3c6693 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
932052f9-6c65-55e5-a399-8a680bf20d77 | note | ○ Concrete layers are not more than 350mm
62f92629-14a2-5e50-9c70-44104d7f0fdf | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
4cad35dd-fba2-543d-ad60-8344898e9145 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
01fe7357-620f-55ee-a07c-572afe23b74b | note | Record: Required information on the Concrete Pour Record.
7af37036-412a-522a-9ea1-e082563f520f | note | Attach: Concrete Pour Record
1e64748e-1354-5d42-b099-6458c4a5a1a8 | note | Attach: Concrete Dockets
b1b6d558-44fd-599a-8d12-32fbc776f921 | note | Method - Visual
7b118340-a7f0-55ac-9123-18bc4c7a64bf | note | Frequency - Each load
ec885080-0fa8-568a-acb7-742805871064 | note | Category - SP
4363f6e9-a6fd-5dc6-b3d1-a06d114457dd | note | Responsibility - SE/PE
14aacd14-5b80-5998-bd3a-ac1e0870c03e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.16 - Surface Finishes
548131eb-34c9-52e1-b4f9-2e862b427f15 | note | Reference - IFC Drawings 610.31, 610.20
bdcbc4b2-3c45-5c98-abc3-da62c562e3f6 | note | Acceptance Criteria - Surface finish as per IFC drawings.
25bd9858-eeff-59dd-aa79-49845c6e3d57 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
03bc110a-c227-54d9-9ed4-76db34b23b5d | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
7772092b-838f-57d5-b287-1ac336ba5dbb | note | Method - Visual
6f1a51f5-9fb0-50e1-ab96-06317962f5d5 | note | Frequency - Each element
d8f81067-782c-5d53-900d-ee1d8f682be0 | note | Category - IP
a14ca012-f4a1-5457-9488-409e4ba3f542 | note | Responsibility - SE/PE
72bdd6cf-29a1-5576-8982-009910ddb3e2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.17 - Curing-Top Surface
ea791957-17df-582e-8b19-51d0e1c78a0a | note | Reference - 610.23
3ccc2b3d-e5d8-5213-b52b-82cea2be5b3a | note | Acceptance Criteria - Curing performed in accordance with approved method of curing item 3.5. Minumum curing time per Table 610.231.
c8875579-3229-57e2-825c-fa103b1349f4 | note | Method - Visual
36c6f105-f9c9-5f93-9e0e-c00a7ae11478 | note | Frequency - Each element
0ef150ee-68bd-5b55-bd36-6ad42ed4a481 | note | Category - IP
ba5ac689-6c49-5132-8855-67e94008d57b | note | Responsibility - Foreman, SE/PE/SPE
6d7d4f63-da32-5e21-b5a0-426acf53f4c1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.18 - Curing after formwork removal
f2af256a-e6fc-5663-b2ad-8b58c7654554 | note | Reference - IFC Drawings
ff985eed-7583-5bf0-9ec3-8f80b89b8902 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
0c546542-fa5c-5afb-987c-a7dca3b3201b | note | Method - Visual
a8a59b6b-ac2b-57c7-839f-5ce20ab07591 | note | Frequency - Each element
b1797ead-b71d-56bd-bd06-5562351e30a7 | note | Category - IP
21ec2621-fa85-583a-86cf-c76eacf184ff | note | Responsibility - SE/PE
bf7e3402-069b-545e-ad69-10c4b1fd873c | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
5c4a7f7d-b2d6-587f-a765-d7e6ffb580cc | note | Reference - 610.22
ff46c171-4f22-55a2-a0d4-e9a6939d56dd | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
7ad023a4-2fc5-5264-ad7f-ac6c862ded5c | note | ○ Only applicable if the element has:
da7823f1-80d9-5e78-b193-a0a80fb2d3ea | note | i. the smallest sectional dimension exceeding 500mm
dad2ae1e-dd92-5a46-abc0-ae57a783c9cc | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
39184be0-55cf-51e0-b6c8-e791a1461898 | note | ○ The maximum internal temperature of all concrete members following concrete placement shall not exceed 75°C.
3c3e9b09-304c-5d3f-ad04-fc54185d835d | note | Attach: Thermal Monitoring Report
51cf9e76-d9e4-5702-8b85-78fcaae4b53c | note | Method - Document Review
315dbde0-2ed0-516b-9e19-212f91ce4acf | note | Frequency - Where applicable, each element
bd25226d-8abe-5322-bc2f-87eb0263f4e6 | note | Category - IP
6d28de1d-f617-52ee-8903-9664df1e0687 | note | Responsibility - SE/PE
79c1f10d-257b-55cb-bf2d-9aa3a271e339 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
7616acce-69d7-5891-bdf2-9a634f271287 | note | Reference - IFC Drawings
17ad3fd9-fd95-53d4-bb6c-e0056153ab33 | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
f31eb2db-96a5-5edd-94b5-db799ddcb80d | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
440d593e-4ad8-53a4-bc69-b129122128ce | note | Method - Document Review
39e455a2-ef4f-57e8-9ad0-d3983934f14b | note | Frequency - Where applicable, each element
cbbeb4da-5dc7-5709-8ddb-1a63fac9e24f | note | Category - IP
278819f5-1fb2-53d1-8730-8361c27dc06c | note | Responsibility - SE/PE
4549859a-f58e-5cf9-8c1f-c4d55c19ae91 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Surface Inspection - Cracks
c61e5a72-2f1e-52ff-b095-527758f3d8a9 | note | Reference - 610.24
3add0644-b560-5cdf-97e9-9b64ad46dddb | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
ad41e1bf-54a2-5d1d-af28-1b3488b68433 | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
77b6378b-8446-5283-b19d-4569d5ec02f4 | note | Attach: Post-pour Checklist
f592ca00-01ff-531a-a07c-2751067d1fa0 | note | Method - Visual Measure
e3b51298-78fb-53bb-8e5c-b8b888cb4839 | note | Frequency - Each element
64304ed9-5930-570e-9c8d-5edaa757e412 | note | Category - IP
a5d5820a-b9c9-5032-a3ac-b3bcd5fabd6f | note | Responsibility - SE/PE/SPE
c1a3fe54-8eb7-5562-b877-2bcc45778ec2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Surface Inspection - Surface Finish
eebbf23d-3fde-56f2-9e27-893f9cb7d4fb | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
a5cdc179-d014-57ec-917a-65c88c9363ff | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
1911c46d-949c-5aea-8f7c-2a94ce102bfd | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
6f6d056a-6c59-546c-84b7-8180534046e2 | note | Attach: Post-pour Checklist
13fcbd94-98b3-59c0-8865-a8d05271781c | note | Method - Visual
d952477b-f9d5-5260-9aab-56662140992f | note | Frequency - Each element
149af8b2-fe9b-5f51-861a-b3fecbc542e9 | note | Category - IP
1d52539a-a19e-5f9b-b953-e6689b61c04d | note | Responsibility - SE/PE/SPE
096dd83b-c719-57ca-ab4f-94eb254aad52 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Measurement of Concrete Cover
af3c8468-81df-57bb-b1a0-1882ff1c65c8 | note | Reference - 610.34
35c10ffb-897a-5745-988b-451baa772aaf | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
0d313ed5-ff6b-530f-b65b-e54deeabe937 | note | ○ Minimum 10 no. measurements recorded in each area.
7cdb7bdb-e74b-5cae-8c64-e6992fe13fda | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
5343d011-6ec6-5d51-930d-ab36d3f5ae8f | note | Attach: Covermeter Check Record
8994a4e5-bda3-5d2e-a450-d9dd73bc090f | note | Method - Measure
a9b0c039-cace-5ffb-a54b-35f2b87e39ff | note | Frequency - Each element
79ed7b61-8163-5d7f-a903-681639f319ab | note | Category - IP
bf2ea72b-8c78-5232-b62b-0502fb59864f | note | Responsibility - SE/PE/SPE
47fcea55-abd5-55be-afdc-a221999928ba | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
1b6c2034-3ddc-5130-acc3-6d4dca4ff5e3 | note | Reference - Placement of Fill Material Against Concrete 610.35
fc55054d-b5ba-5083-a1ca-422433dddd46 | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
52587acc-3ed1-5a19-a710-27ea7a7f0883 | note | ○ Proposed placement of fill material against concrete prior to 14 days from casting shall comply with the early application of loading requirements as per VR610.16(l) or maturity testing requirements as per VR610.16(m).
0908f1e5-0c9f-554c-ad61-80137942a526 | note | Attach: Concrete Test Results or Maturity Test Results
6f6a15d1-ff4e-5b80-9817-a26a0c10d656 | note | Method - Document Review
977a32c4-aa31-52f3-b89d-2d540a1ce5db | note | Frequency - Where applicable, each substructure element
bf7bd6b2-d707-532b-a5fc-deca124218ec | note | Category - SP
c98ddf6c-9003-5606-b239-d6e18f30363c | note | Responsibility - SE/PE/SPE
b72fdf78-c1e0-59a2-97af-a9c9242bcb05 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Compressive Strength Test Results
8e632c0d-37b8-5002-a54b-5b28b76aa80b | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
f7dab94c-e2c5-5ee1-b8a4-37603d0b7213 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
dab34ac3-2ce9-549d-a5c0-04e1edbb9b12 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
6c5b2f49-d48a-598f-808e-a08832c28ece | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
dcf5e138-0a98-5059-b3f7-bc706ec177f9 | note | Attach: Compressive Strength Test Results
ce999c88-0246-5830-9484-7c844ca3be7f | note | Method - Document Review
a74fd543-c6c8-55c2-9fc1-42f3b6b86849 | note | Frequency - Each cylinder
c89a9ae8-2d23-57cb-9ca4-d97ac813e8c7 | note | Category - IP
56a53c04-b96b-56dd-b3d7-8e09ef15ef7d | note | Responsibility - SE/PE/SPE
a7278d81-58a5-5f6e-b305-79cd8215ecb4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.8 - As-built Survey
cee49cdd-3bda-5be8-9d32-1d4649b7f36f | note | Reference - IFC Drawings 610.47 Table 610.472
3f0aa22c-d692-5891-a184-3e7168ab4ed8 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
3105e17e-8610-575b-a2a5-edbabb281888 | note | Attach: Survey As-builts / Survey Report
d451a6e5-92dc-5276-ba05-500b30d42b16 | note | Method - Document Review
9a7c4e36-04cf-5818-889c-c3c862577e74 | note | Frequency - Each element
6832fd15-e0d5-53b3-b583-a69a8c6afc52 | note | Category - IP
fb872162-e888-5c7d-b894-1de3be0f73d5 | note | Responsibility - Surveyor, SE/PE/SPE
247e76db-4d67-5d67-b259-8a382ea4ccc4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
900710fc-abf5-5740-a018-50ba320c2090 | note | Reference - MRPA Quality Management Plan
39b5d766-2bfd-5df3-ab59-da6d86ff52fb | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
3b81e32f-a65f-5100-b87d-94d717d11dc2 | note | Method - Document Review
63f03743-7a3e-56ce-beab-e11be6a49464 | note | Frequency - Once, prior to closure of this lot / element / Work area
1cb97a48-79f4-5530-8877-4eaae1adffbe | note | Category - HP*
5e6df854-6b9e-59ad-b09a-ce2bc88b7099 | note | Responsibility - SE/PE/SPE
994e19a7-4006-5956-ba7d-e3b1e4c5281f | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
8e964052-d27e-50a2-a31a-fb3050a4bec9 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
574a1bfa-7b78-5263-83e5-19db7acd7132 | textbox | Name:
e3402fbf-c4ae-5918-8ac2-1c6110cd8dcc | textbox | Position:
b80165c0-54c3-591f-be70-33ebfaf27e5d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-109-CIV-BRUNT-Street Lighting (Supply and Install) | itp | ITP-109-CIV-BRUNT-Street Lighting (Supply and Install) | 1981b585-4339-433f-93be-f522a73591c6
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
3094d2a5-ac54-503f-bf6e-9acd0ed99aef | note | Document Title: ITP-109-CIV-BRUNT-Street Lighting (Supply and Install)
2006e5c8-a6f9-53f5-ac1d-9fd37f5ed0fc | note | ITP Description: Street Lighting (Supply and Install)
74abe8fe-55ea-5122-a116-b07633b5b7d4 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
763853ee-4148-5d64-81f2-29e8fc21c287 | note | Discipline (e.g. CIV/STR/RAIL): CIV
71b7af2e-f800-5b43-af21-506b748f9c3e | note | Revision Number: 0
6bcfb2c5-f5fd-524d-bede-a13b858c7d42 | note | Revision Date: 24/11/2023
71207a4b-7fbb-5431-bbed-d626ce6b410f | note | ITP created by: Crystal D’Mello
0af6de1d-5ce0-59fe-89df-4dfdf7212e4e | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
d8f5f4e8-adb6-52e3-9ca1-9b34341e30aa | note | Reference - IFC Drawings
| checkpoint | 1.2 - Non Dependent
b0bc0d67-337e-5d21-947f-cdf5b72a31ce | note | Reference - AusNet Services
| checkpoint | 1.3 - Non Dependent
148590ef-2331-5901-b98b-3f38f0a60200 | note | Reference - VR Section 733
| checkpoint | 1.4 - Non Dependent
fdb63a06-2eb7-51f4-b86c-20b115f56584 | note | Reference - AS/NZS 3000
| checkpoint | 1.5 - Non Dependent
22cd9a19-c657-5f11-a37a-19f399480f9a | note | Reference - AS/NZS 1158.3.1
| section | 2. Preliminaries - Preliminaries - Materials
| checkpoint | 2.1 - Material Compliance - Obtain and review manufacturer documentations for the supply of materials.
caa1d68c-b0da-57f9-b567-04a8860fe004 | note | Reference - IFC Drawings Section 733
7af9f508-5e82-5b19-998d-f4b0d8c50fa7 | note | Acceptance Criteria - Materials comply with IFC Drawings,VESI Standards.
7f6b306f-cf76-5860-96f7-b3b078936660 | note | All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
0aa6a895-51fc-5fac-929c-f3a393642f41 | textbox | Enter: Teambinder Hold Point Release Number
e5c4643d-9daa-5456-85ad-b04ad9a7bd0b | note | Method - Document Review
1a40b58d-5ca6-5653-a89b-bb7edc5a5d6c | note | Frequency - Per Source
9245508b-a2a6-5f11-a314-debdc0530133 | note | Category - HP
d48742a9-1a5f-56bf-958c-db6a43981c7e | note | Responsibility - Nominated Authority
0814e9f0-528a-5cb5-a205-f8d6f0b1d972 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Inspection of supplied items upon delivery.
0db14a7d-e748-59d8-860b-52464b00d68a | note | Reference - IFC Drawings VR Std Dwg TC1064, TC1065
60bfab79-5f09-5e26-afb3-b23b56f256cf | note | Acceptance Criteria - Supplied items are to correct spec, class, size, undamaged and brand new.
c54dcb09-3132-5a0a-a372-e811743e03c5 | note | Luminaires: At the time of delivery, the supplier shall provide hard copies of the following:
1126fd49-5272-5f74-bf58-fa2490b957e2 | note | ○ Installation Instruction Manual
98d1691e-12f0-5fa4-8808-707fd3a49d66 | note | ○ Operation Instruction Manual
4c753c59-3534-5820-9779-9c31840e97a0 | note | ○ Storage, handling, loading and off–loading instructions
c939a048-2c69-507c-8d95-ffabf3b9fb75 | note | ○ Test Certificates
93c6e4db-512a-591d-b6ba-e85b8aac79a7 | note | ○ Warranty Information
a5837f2e-a377-50e3-ab25-3f4153947d4b | note | Attach Delivery Dockets & Records Required
1aab801c-2780-5d56-b062-54f66a97c5f0 | note | Method - Visual /Site Inspection & Document Review
0aad9743-4dd6-572b-923b-d511416032f5 | note | Frequency - Per Delivery
6f6b4b7e-c528-5a05-b415-e3dc71b33c42 | note | Category - IP
90979ab4-1be4-5685-bc02-7e72a73daad8 | note | Responsibility - SE/PE/SPE
53c8e024-b5b8-5ad2-be84-dd1908896a35 | note | Verifying Documents - This ITP Signed Off
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - ACCC Form (Australian Competition and Consumer Commission)
8b884a0c-06e0-548f-9e26-3e72965078c8 | note | Reference - AusNet Services MRPA Quality Management Plan
b3a6a1c1-a752-5368-a613-502b18c27947 | note | Acceptance Criteria - Before any works commence, the accredited contractor shall obtain an "ACCC Form" from AusNet Services representative for permission to commence works.
a607a204-18c9-5200-9ce6-49102ca6e9ac | textbox | Enter: Teambinder Hold Point Release Number
f4b3c4ef-2f52-5e6d-b816-5f29023b4477 | note | Method - Document Review
c012a8f9-7c45-5104-976e-b919b123f413 | note | Frequency - Once prior to works commencing
25262cc3-a33f-5dce-b96e-9d00a3f37d83 | note | Category - HP
0f94e012-1ce0-5fb4-a18e-c3b4b39242ad | note | Responsibility - Nominated Authority
ca066e67-c89a-505b-87a4-9576a9448b62 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Subcontractor Prequalification
5efe8d81-d9c0-5d40-ba90-1749438b82d4 | note | Reference - AusNet Services MRPA Quality Management Plan
8eabdf3d-5783-52c4-868a-7144afce526a | note | Acceptance Criteria - Subcontractor to be a VEDN (Victorian Electrical Distribution Networks) accredited contractor.
bc47d2ee-5f96-592c-b322-b3c8d471a11c | textbox | Enter: Teambinder Hold Point Release Number
3127c2bf-745a-51fa-a6e8-be82d5387a78 | note | Method - Document Review
43aa84ba-0fe3-50dd-8bf5-1985df6654df | note | Frequency - Once prior to works commencing
6e527348-191e-51ea-8898-3b2f4633f05d | note | Category - HP
983cbe6c-fd22-5113-bcae-69e60d66d726 | note | Responsibility - Nominated Authority
12e263f6-5d8d-5cde-97c9-577086be7a17 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - VESI (Victorian Electricity Supply Industry) Auditor
0dfb0bda-d264-5cd0-9c6a-2cc1f1870762 | note | Reference - AusNet Services MRPA Quality Management Plan
d18cc931-469f-5a0d-b253-4c5d3f00f96e | note | Acceptance Criteria - VEDN approved civil auditor. (VESI Auditor Register)
72978060-e228-544a-aa8d-0cccb1042f92 | textbox | Enter: Teambinder Hold Point Release Number
d05e7aa1-9e08-50a4-91b3-9f2c03600280 | note | Method - Document Review
8d685d76-e0c1-57a6-bc21-5687bd54c61f | note | Frequency - Once prior to works commencing
e420e1a3-43ef-54e2-aa36-90eefdf48d06 | note | Category - HP
a7266fef-9b8e-5ae3-8301-bd7482d028b5 | note | Responsibility - Nominated Authority
68f7f437-fa8d-57a8-9695-442c110f15e2 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-installation Activities
| checkpoint | 4.1 - IFC Drawings
52e548c2-18e0-5b90-a8b8-3821c2cf1b9f | note | Reference - MRPA Quality Management Plan
e8f5c4a4-0959-5cdc-82d3-65bc4cb0b4bb | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
fe81ee5e-1501-5628-a0d4-5b58bc67b7dc | note | Method - Document Review
f25604ac-e2f0-5ae4-b982-7ec4ddf4390b | note | Frequency - Prior to starting Works and at regular intervals
56f359a5-259f-5044-8bd9-0afbf2ca2e10 | note | Category - HP*
90225433-9509-5ad6-898a-fa78c8399d81 | note | Responsibility - SE/PE/SPE
dfee4f9d-e48b-5ff0-95ad-51b2adf4950d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey set out
917ac46d-a4d0-5ac8-9097-cc4e6306b65e | note | Reference - IFC Drawings AusNet Services Technical Specifications
c250c113-6208-5f1a-9216-2ed8563df02c | note | Acceptance Criteria - Set-out survey carried out by a surveyor and within the tolerances as per IFC Drawings and AusNet drawings/specs.
3e0a575f-e613-5727-841c-a5eb409768d1 | note | Method - Visual Survey
48a016b7-c2a2-55d6-9ccb-26cde8e5bd5f | note | Frequency - Each Element
0c706742-1080-5ef8-bda0-6f80032731b9 | note | Category - IP
602eb3e1-3613-5a68-bf58-f1fd2935c20f | note | Responsibility - SE/PE/SPE
bec48522-46fe-5105-a189-65f4af29606b | note | Verifying Documents - This ITP Signed Off
| section | 5. Installation Activities
| checkpoint | 5.1 - Pit and Conduit Installation
01ba70c8-fa57-500b-a112-27a256ac12a6 | note | Reference - IFC Drawings
11dd080e-ccdd-531b-8f76-52ef5fb0b821 | note | Acceptance Criteria - Conduits and pits to be installed as per IFC Drawings
3ff632f6-cd2e-5091-8643-3db76505761b | note | Attach: Subcontractor Installation Checklist
af2705b7-87d7-5a94-ad65-3954d2c7ceb8 | note | Method - Document Review Visual
54a73ff5-d998-5050-a8f5-c5b281e9d7c0 | note | Frequency - Prior to commencement
83fff920-4d89-5761-a326-0ce8ccdced59 | note | Category - WP
e96cbb10-9d96-5945-9504-6bd015c98c49 | note | Responsibility - SE/PE
e4b2eff8-bd0f-518a-8674-82923b71569e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Conduit and Cable Detailing
458e4b65-2ef8-55ac-b2a0-2df719b4e489 | note | Reference - AusNet Services Technical Specification
ae75e188-6f9b-5bba-8d6e-6f43d94e44b8 | note | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer.
4ca71a6a-680e-5a36-a9fd-d5aaf68d7836 | note | Attach: Verification Document (As-Builts)
d633ec56-a932-5431-86bc-f8252077661b | note | Method - Site Inspection
23e6e322-fa04-5c7a-866b-1862f33ac178 | note | Frequency - Upon completion of each section
e826cabe-5cc7-534a-8d64-6c169968587e | note | Category - IP
c5244e99-7d66-5b80-ac46-7c77a9e39298 | note | Responsibility - SE/PE/SPE Services Engineer
a27e0107-a95e-5097-89db-fa8be992777d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Prepare the plinth foundation (Excavation & levels)
ded54ce7-04b8-50a1-8e30-c68f207999a7 | note | Reference - IFC Drawings
eff78351-a798-56c5-b979-8f1f3c88163c | note | Acceptance Criteria - Check levels conform to relevant drawing depending on type of pole to be installed.
5fc5778a-618e-526e-813c-6cec4d7f7dca | note | Method - Visual Survey
98258fd3-0c45-5b4d-bbaa-71c2aa8e2f20 | note | Frequency - Per Lot
1e719ac9-a19c-5b36-a57b-8d82165ded33 | note | Category - IP
1a8317c7-6c49-5255-b478-e9a93d5de1f9 | note | Responsibility - SE/PE/SPE
eff8c619-a3bf-5964-aeb7-87996a10ca8a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Installation of Light poles
c4f92327-43c5-5f08-96fe-31b47b7e1901 | note | Reference - IFC Drawings
bddde884-af1a-53fb-a243-14eb41d87cf1 | note | Acceptance Criteria - Light Poles to be installed as per IFC drawings in accordance with VESI requirements.
b1cc26bb-c9de-58f1-b692-9809d6012bda | note | Method - Visual /Site Inspection & Document Review
6ca24e0e-e7a9-5090-8162-ffd1a4742342 | note | Frequency - Per Lot
3ab0b82d-7433-58e4-bd9b-02c7b9f87ef4 | note | Category - IP
d3a3e961-9bae-52da-a978-9bd7e61c65b6 | note | Responsibility - SE/PE/SPE
71a8a2a7-67ee-52d7-818c-d84077a00183 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Asset Labelling
898ffaf5-caae-5647-be87-a66a5cb57a43 | note | Reference - IFC Drawings
2a067ffd-e635-53c2-bbcd-4d9b6fadf103 | note | Acceptance Criteria - Pole Labelling to be as per IFC Drawings.
447a33e2-f39a-5da5-a4c1-bdd48c3d3cda | note | Method - Visual Inspection
db11e422-4d6a-5029-8795-f6e19aa55f70 | note | Frequency - Per Lot
66bc364d-837f-538b-a3c2-2a5a285dc64d | note | Category - IP
d30bad78-e271-5b16-9b4b-f8171c37be95 | note | Responsibility - SE/PE/SPE
2e12be9c-cb73-53c9-abe1-e33e586957c4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Commissioning & Testing (Civil Audit)
1a912ff1-b8cd-557c-86e5-b6197b7f5a82 | note | Reference - AusNet Services Technical Specification
49b214bc-c5ee-50ef-adc1-346e72996c16 | note | Acceptance Criteria - Upon completion of all trenching and conduit install, a Civil audit by a VEDN approved Civil auditor will be completed and approved before procceding.
fbf0f1d4-56d4-5940-8685-12ccfb92b6a0 | note | Method - Commissioning & testing
fcd35cb4-9dc1-5870-847f-ca373309fb9d | note | Frequency - Upon completion of each section
c183a999-dd43-52fe-91c3-6d543157c9d2 | note | Category - IP
16fc1f4d-f5cc-53d3-9901-3ca742d304dc | note | Responsibility - SE/PE/SPE Services Engineer
c8cb8cff-d395-5dc2-a9ee-3854362104d5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Commissioning & Testing (Trench Inspection)
3d947529-a856-51f4-9f72-920ef5da98c8 | note | Reference - AusNet Services Technical Specification
215cf54c-bd5d-56b5-990d-0fb0f1ce89f4 | note | Acceptance Criteria - Trench inspection detailing all conduits and cables being installed by a AusNet services approved detailer
593ebf33-f67c-5615-a40c-348883fa41d8 | note | Verification document: As-Builts
d92542ed-edf6-5536-bde5-a2a32ea132fd | note | Method - Commissioning & testing
3a7f63f2-1fee-5f48-a394-ecb34a83119d | note | Frequency - Upon completion of each section
6675f34a-2866-5619-9f03-5136268f5c54 | note | Category - IP
b150573f-d17b-59d6-b469-fe879816a10c | note | Responsibility - SE/PE/SPE Services Engineer
0e9b1eb1-2c27-5f7b-96c3-f805bebfd9da | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Commissioning & Testing (Pre-commissioning)
e2b4dd13-6328-521f-911f-0c7869282506 | note | Reference - AusNet Services Technical Specification
65d6be15-615a-5716-a400-508dcd202ae9 | note | Acceptance Criteria - Passing of the pre-commissioning audit with all non-conformances rectified.
18b218cc-f55e-5e49-91e5-b7abd9105ae3 | note | Method - Commissioning & testing
e29da13a-6256-5bb5-a715-41035242e331 | note | Frequency - Upon completion of each section
f49e7535-434c-57d5-9d51-31864534890e | note | Category - IP
aabdec53-093e-5cc9-9fa1-519dd5bb45f8 | note | Responsibility - SE/PE/SPE Services Engineer
257f4a99-6b3a-5fae-91d4-7cf61fe9411b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Commissioning & Testing (Final Audit)
92169f1d-25ba-5a7b-a1ea-9a8dda811ba7 | note | Reference - AusNet Services Technical Specification
9c3b7a47-ee7b-52e6-8558-178ef2644ced | note | Acceptance Criteria - Passing of the final audit will be completed by AusNet Services to inspect the completed works with all non-conformances rectified.
041f96c3-2c59-5d4d-82eb-083abc142daa | note | Method - Commissioning & testing
0b0bf91c-3ca3-525b-9930-81088f1b1a8f | note | Frequency - Upon completion of each section
02ab2e71-7311-576f-b285-52341f788760 | note | Category - IP
038a8d70-2a7e-5499-92d8-9356033b9b9e | note | Responsibility - SE/PE/SPE Services Engineer
59acbcce-ed24-5e27-ba40-6832232b0bbe | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Testing and Certificate of Electrical Safety
ad284736-9f8c-5220-8aa5-1b425bfcd8c5 | note | Reference - AusNet Services Technical Specification IFC Drawings
1fbbb48e-6fb5-5d98-919e-499c8c744a57 | note | Acceptance Criteria - Prior to final acceptance, the contractor shall test all distribution cabinets, circuits, switches, PE Cells, luminaires, and all other electrical and electronic components for correct installation and operation
06b9d6aa-9068-5372-ae68-9506114bd21b | note | Attach Documentation: Certificate of Electrical Safety for electrical installation
bb21ab11-4f34-54d8-b598-e6bc71dbea32 | note | Method - Document Review
d677db1b-c49f-5715-bfb8-5292e0881979 | note | Frequency - Upon completion/ Work area
aee27a5e-1c7d-53ae-a3f0-234bc1e0751b | note | Category - IP
153d3a7e-09e2-53cb-aa70-306b235f879a | note | Responsibility - SE/PE/SPE Services Engineer
f22fcbf9-1e6b-5ce5-9b62-9769afe21d7e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - PC Cert of AusNet Agreement
bf7dd435-729f-5294-8d26-e597b64cadc4 | note | Reference - AusNet Services Technical Specification IFC Drawings
12357089-52d8-5a21-bf43-7b6109119b65 | note | Acceptance Criteria - To be accepted and signed-off by MRPA and AusNet
80470da2-9ae9-5074-bed2-12efab5ff582 | note | Method - Document Review
d0445931-d480-52a4-8c39-7d5089f65f4a | note | Frequency - Upon completion/ Work area
929b7ce0-0226-516d-b691-3b1d828fbc51 | note | Category - IP
cbcd80f4-9802-50fe-93c6-c108419cd6cf | note | Responsibility - SE/PE/SPE Services Engineer
75fa721a-f2e7-5bb9-a5dd-d665b33d8ffe | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-installation Activities
| checkpoint | 6.1 - Verification of Subcontractor conformance records / signed ITPs including any relevant verification sheets.
243a2c25-8214-5e4b-be2f-52b0b169b07d | note | Reference - IFC Drawings Notes
5b0a5df6-ae59-58be-bca4-7ec0b36794fb | note | Acceptance Criteria - Check conformance report against project conformance criteria.
b9703207-ee14-5084-97bb-56a2b08083fd | note | Attach Verification Docs: QA Records, Signed ITP including any verification documents, Commissioning & Testing Certificates.
4f6c4f50-3fb5-547c-b119-297eac3765c2 | note | Method - Visual /Site Inspection & Document Review
ef295db2-9ea0-5091-ac3d-fe1af5ecd174 | note | Frequency - Per Lot
c23db857-7a2d-558f-a356-3d702104004e | note | Category - IP
bc2e4b4c-166c-54e7-9eb7-345b7c5bd010 | note | Responsibility - SE/PE/SPE
093ee74a-ff4b-57ee-bd3b-a3ebea4972f5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - As-Built Drawings
80a939a6-97be-5a85-a285-5db4493e5975 | note | Reference - IFC Drawings Notes
46c1e58d-308d-56c6-bbef-64412b61c35d | note | Acceptance Criteria - As built drawings for the metered lighting installations to be provided to the satisfaction of MRPA & Cardinia Shire Council.
daa1db70-fab0-51c9-960b-6c01f04db74c | note | Attach: As Constructured Plans / As-Builts
e24b5237-805d-55d2-b93b-ce74920ce7ff | note | Method - Document Review
a99920b6-0456-57e6-96a0-8acfc639dfbb | note | Frequency - Upon completion/ Work area
bb0e8470-9cb3-5cb3-a505-3996f9fa40e3 | note | Category - IP
3219ee36-49a4-5ac3-8d47-1c204b08fd33 | note | Responsibility - SE/PE/SPE
521676d5-2953-5fc7-9f85-93d088372590 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
1290c3b9-beca-58bb-8819-b545667c04e9 | note | Reference - MRPA Quality Management Plan
b7beeac1-c684-53d4-8088-b15fdad9efb8 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in TeamBinder.
38725408-db79-584a-9f82-17ab0283c2ed | note | Method - Document Review
055a78be-58b8-58e4-beb2-58a67319cc6d | note | Frequency - Once, prior to closure of this lot / element / Work area
bc4d1bc7-64a4-5544-8a8d-b2091e963a39 | note | Category - WP
758fcb9f-c8b6-54a0-93f6-7d2986ea4fda | note | Responsibility - SE/PE/SPE
688f3627-66d7-54ab-9975-2aa830ae3ca2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
c2eaaf84-66cb-5564-bed5-0abea6573df0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
af43114d-061b-5834-a105-7c8231bd2f2d | textbox | Name:
61c2ac93-9501-57b9-8a0c-8ea3b3be446f | textbox | Position:
edde8149-ea49-5c75-8c57-6501d24d9529 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-116-CIV-BRUNT-Melbourne Water - Stormwater Pit Installation Rev.0 | itp | ITP-116-CIV-BRUNT-Melbourne Water - Stormwater Pit Installation Rev.0 | 56057660-07dc-4154-87c6-2f122cd42fdf
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
196d8b77-7b5e-56e2-a6c6-bb68894651dc | note | Document Title: ITP-116-CIV-BRUNT-Melbourne Water - Stormwater Pit Supply & Installation
7237e49a-8ef0-5ec5-9ca2-35ebbb321c55 | note | ITP Description: Melbourne Water - Stormwater Pit Suppy & Installation
e9fb1010-c6e7-5986-89c4-635418039121 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
511959b9-e9cb-5b1b-b3d0-a94d43bfa6e6 | note | Discipline (e.g. CIV/STR/RAIL): CIV
369c1b32-50dd-51a3-a330-3c1a7c0c892f | note | Revision Number: 0
eb783e5a-a695-5c97-a230-8629b52054b2 | note | Revision Date: 07/12/2023
9dd04431-653a-5aa2-a00b-adcbe766a0e4 | note | ITP created by: Sammy (Shubham Bajaj)
2265333d-93e9-584c-8648-e604f720e573 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
9e22ac37-5925-52f9-b90e-de48885c8a79 | note | Reference - VicRoads Section 701
| checkpoint | 1.2 - Non Dependent
4a8493dc-1b2d-5ae6-889b-8174b6921e1c | note | Reference - VicRoads Section 705
| checkpoint | 1.3 - Non Dependent
05929fce-ce24-51f2-8023-be97333bdb88 | note | Reference - VicRoads Section 610
| checkpoint | 1.4 - Non Dependent
b17bb012-a3c1-5b3a-839f-a3d1bda34618 | note | Reference - VicRoads Section 611
| checkpoint | 1.5 - Non Dependent
64b2811d-5d5a-59bc-9630-5f6cc60eee44 | note | Reference - Melbourne Water Standard Drawing 7251/08/416
| checkpoint | 1.6 - Non Dependent
bbf470d9-bccb-5a12-b6a5-7f53af5c8f0a | note | Reference - Melbourne Water Standard Drawing 7251/08/423
| checkpoint | 1.7 - Non Dependent
f5602399-b5eb-5036-a6e2-918ebf2e856d | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Drainage Pit - Step Irons
05f42c8a-0046-554f-932d-3db4b55bfb82 | note | Reference - Melbourne Water Standard Drawing 7251/08/416 Section 705.04(d), 705.12
89ebb9d5-bb4f-5f71-a1c7-c3f658b872d8 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04(d).
f5d4d500-3d1e-51d7-a582-b88f06d80e25 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12 and Melbourne Water - 7251/08/416
f160a21c-b310-5203-9846-b57c5c8cce34 | textbox | Enter: Teambinder Material Approval number
b279ba76-73f0-52b3-9ebd-61ef9c7e0803 | note | Method - Document Review
1d7fc4c3-7978-5c4e-b5ba-91ba3ec20a32 | note | Frequency - Each lot
9ef413d7-4e1d-53ff-b1b4-575aaecf1685 | note | Category - HP
b93470af-3e3f-5fae-b9dc-120d00c94326 | note | Responsibility - Nominated Authority
06db45de-e01d-579b-9f92-2a7bd3dd720c | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Drainage Pit Bedding
6b0f7e26-eb66-520d-b9c8-88e427e83ce1 | note | Reference - IFC drawings
dc6667f5-d020-55b4-8059-056503723472 | note | Acceptance Criteria - Pit shall be installed on nominal 50mm thick 200 Sq concrete packers. positioned at 1m centres around perimeter of pit. Underside of pit to be flood grouted with Min 25Mpa grout.
ec2afbb6-e7d6-5de4-ac5f-825c3ef52644 | textbox | Enter: Teambinder Material Approval number
81dd07be-b88b-5d07-92b2-0dfbc08da99d | note | Method - Document Review
2eea2060-0228-5714-a9f2-3b5e553adc7a | note | Frequency - Each lot
840b33a8-9fdc-5d34-9f1b-6e92e66aefc1 | note | Category - HP
cfed4691-475c-5b6c-b04e-60cb0b9bb97c | note | Responsibility - Nominated Authority
69bdd06c-7433-5686-bbe5-344d80837771 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Drainage Backfill Material
f937ad0e-17f9-5b7d-8957-f93baed34e78 | note | Reference - IFC drawings Melbourne Water Backfilling the excavation - Backfilling materials 6.8.2
1f2385bb-e11b-5dfc-97a6-2e62a1354fae | note | Acceptance Criteria - Approved Backfill Material in accordance with Mebourne Water Requirements.
b5e3ab3a-4ed8-5ebd-9fdf-10eecea44dbc | textbox | Enter: Teambinder Material Approval number
bb5f3757-461c-5a42-9269-27c10280158c | note | Method - Document Review
98ae4a4c-265a-5bc4-8948-70a319c4a76f | note | Frequency - Each lot
b125b94c-94f2-5b60-a7f6-f58300d67f59 | note | Category - HP
c07ca941-19fb-579c-9d39-dd8e744c1e4d | note | Responsibility - Nominated Authority
4f71e0ee-9cda-5804-87fd-5f115a81d306 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Precast Pit Lids
7e3ab35c-c6a8-5723-816a-4267836726c1 | note | Reference - IFC drawings
7b6d0bc6-37ed-556b-9d4a-f54024b44380 | note | Acceptance Criteria - Precast steel reinforced concrete drainage lid shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
3938276e-8fa0-5b75-bda8-343d0f858a59 | textbox | Enter: Teambinder Material Approval number
991d37f2-c8ee-5d84-83cd-343104ac9392 | note | Method - Document Review
6240bd26-d725-5152-beec-dc5fb758f0de | note | Frequency - Each lot
e41c549d-a254-557e-8a35-b3b159810230 | note | Category - HP
fc7d6681-64c4-52b2-a415-0d4616fdbcc0 | note | Responsibility - Nominated Authority
90f17fc5-d717-585f-b843-ffc0cfd4b956 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Subcontractor ITP (where required)
00cc2731-4aec-5de7-a230-915caaf9adbe | note | Reference - Subcontractor ITP
b27661b6-b97d-516d-88f5-460b31a6ad23 | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
8c1b8c38-f0fa-5dca-87c9-2e26d801ee81 | note | Attach: Approved Subcontractor ITP
2d3ef4d8-67e5-5e94-8555-dd1c3e3261f7 | note | Method - Document Review
60bbb4fa-8d85-5598-adc9-e1583bbca388 | note | Frequency - Each Lot
5aa073ee-b70b-52a3-bcf0-d81cc3e80a4b | note | Category - HP
d791261b-5930-5f90-b63e-d10a5fd8acfb | note | Responsibility - Nominated Authority
f7ae3d0a-4210-5ac0-879e-f38dad43f0c8 | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set Out - Pits
c4e31174-c2c1-5117-819a-2fc9a9d64061 | note | Reference - IFC Drawings VR Section 701.10
6b49f6b5-c628-5fd7-8a16-94911a916fb5 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
0f681d0e-9eba-5ea2-9d7c-d70a2a5a7fcc | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
1f961c49-8b12-5399-863d-ff031ed0b6ef | note | Attach: Survey Records
eba71efd-528c-5615-ab4f-8cb8c533aa6a | note | Method - Survey
752b044d-a9da-5ab0-932c-5ce858da08cb | note | Frequency - Each Lot
5139416b-371f-5313-b080-15e30e4799a2 | note | Category - HP*
51863697-04c4-5886-81ca-64626b110a77 | note | Responsibility - PE
21618c06-185a-5237-99f5-d119141260cb | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Pits - Excavation
85affa9c-6fa3-5504-9540-27b0a4d20054 | note | Reference - IFC Drawings VR Section 705.05
6d0f3272-e9b2-5560-b8d9-c9d6a3a6e9b8 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
7f2c68a8-6ddc-5f48-9ad3-41fe7cecfcaf | note | Method - Visual Inspection, Measure
86cc2eba-3be5-5917-8851-cb45220a7fe8 | note | Frequency - Each Lot
55e9d437-6f3b-515b-a26e-45983e729219 | note | Category - IP
eceb6c4c-0cf7-5f4d-9cfd-e724cf3496c0 | note | Responsibility - SE
090837a1-b639-5e8d-b529-6d7189d0b62a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Pits - Placement of Bedding Material
a7789905-a5d6-5dda-8a3f-3c041cb9a54a | note | Reference - IFC Drawings
d8f1979e-0371-5a8d-ab1b-d97b5f2d5f4e | note | Acceptance Criteria - Underside of pit to be flood grouted with Min 25Mpa grout - As IFC Drawings
48dd24a7-cf94-5d70-98d1-45cc668a1dda | note | Attach: Delivery Docket for approved grout material
b1f0bad6-207e-5748-8f7d-fda19de1abad | note | Method - Visual Inspection, Measure
e6d546ea-211c-5a1d-a8e6-6f2e4f1340ae | note | Frequency - Each Lot
76f4f128-894a-5015-aed8-c715adab5ebb | note | Category - IP
dcd4197a-ed3a-5360-b61d-44b1c30c94d2 | note | Responsibility - SE
e46dd8e7-5ba4-53df-9bb7-4c96f77bf230 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Pits - Bedding Testing
f8cf3809-b55e-59ce-b47a-1953e6ec31d0 | note | Reference - IFC Drawings
96a7409a-d6ce-54fb-8bc3-22cf516db129 | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
502e4c04-1dfe-5345-8470-49b6ea70fbf5 | note | ○ 28 day compressive strength per sample comply with the design strength.
fce28d97-4d31-574a-9b05-e8e62898c3f3 | note | Attach: Compressive strength test results
38479fbe-6189-5813-b4bc-382647e46a4b | note | Method - Document Review
b4f1e74f-9af3-5e54-93c8-ca943a57021c | note | Frequency - Each Lot
3967d567-658b-5e8a-8b79-92c4562e3f29 | note | Category - IP
beafac9d-17fb-59c4-8496-99363ce6fd8c | note | Responsibility - SE
b0d364e1-6c8d-560d-aa9b-0da5c5ccabc8 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Pits - Cast in Place Drainage Pit
29956f76-8737-558f-a7d8-8e255bf51be5 | note | Reference - IFC Drawings Section 705.06, Section 610, Section 611
378d4bb4-95c9-5aa0-bf4f-d36c0b93e41d | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
0c0067ed-82d7-53b3-bb99-56bcaa93a439 | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
a8ea31da-07b2-530d-a5ef-4919aaa679e6 | note | Attach: Concrete Pour Record
04c69311-483d-50da-9fdd-18ad78491243 | note | Method - Survey, Measure
8f480550-e1c8-54a6-8653-29e7e3477898 | note | Frequency - Each Lot
1155a17a-67cd-5615-b8fe-d0b358cf3527 | note | Category - IP
672c4676-e94f-5230-9d05-7528d98406b7 | note | Responsibility - SE
678c1504-c40e-536e-97e9-793b081f9ab7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Pits - Jointing & Drainage Connections
65a9f89d-e1ac-500f-b1b4-b4fd88383c69 | note | Reference - IFC Drawings Section 705.11
cb601ca3-ed10-5bf3-9b8d-065b6ac62ca5 | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with Section 705.11.
d157d8ba-25b2-5cb2-a0cf-2f61098e4c0b | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
3f0bff46-fed1-5ec3-a1a1-67d1eb942d17 | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
0f07e222-f00f-51d0-853f-6e1a141efaa4 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
4ab66cc1-8ac9-5ebf-983a-f507b8095c1a | note | ○ Joints to be sealed with Hydrophilic seal around pipe as per IFC drawings
8c6658bb-59b5-58a0-b34e-e0ef2cf9b700 | note | Method - Visual Inspection, Measure
96e6220e-2874-5527-b021-58545b9be0f8 | note | Frequency - Each Lot
ac51643e-3f44-540d-be7d-d154560266fe | note | Category - IP
965d3579-ff61-5fec-9f84-234d6b01f900 | note | Responsibility - SE
8ba1c069-5455-5c55-8c01-c8fb82b32468 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Pits - Shaping of Floor
cf020d01-908d-5719-9811-d98cd5a22c88 | note | Reference - IFC Drawings Section 705.13
0c5eaf67-486a-5caf-a3b6-2ac3f49b64a5 | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
28d95033-4f54-5cd5-9d31-0f2306be6b50 | note | Method - Visual Inspection, Measure
dbd69e9d-56a7-56b2-9558-10085af9cff6 | note | Frequency - Each Lot
0347fb2a-c31f-5cd9-8f05-368ede612ef4 | note | Category - IP
e74014fa-9000-540d-ba88-375bb000d6b7 | note | Responsibility - SE
8950639e-562b-5f6e-b89b-f5b676498a39 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Pits - Step Irons
b4177ace-a4f8-5cd1-adb1-3bb448d3ac59 | note | Reference - Melbourne Water Standard Drawing 7251/08/41
cbd9d254-8ba8-5a55-afde-f7e0b246f726 | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with Melbourne Water 7251/08/416. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
71dd4d5b-5a49-5aa2-8c25-11a3e2b7599c | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
f179b1c7-5858-5c0b-b7a2-be78c9dfc595 | note | Method - Visual Inspection, Measure
3ef896d8-9cc5-5e3f-b176-d1720ba34570 | note | Frequency - Each Lot
18965d0d-d713-5749-9df6-4995f75bea80 | note | Category - IP
5476b1da-ef0c-51d2-9b01-55d5a1d57ac5 | note | Responsibility - SE
a7a84898-9d54-545b-997d-aa100407d2b1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Pits - Fitting of Covers
e2e95274-93bc-53b5-b869-b39182c2cc02 | note | Reference - IFC Drawings Section 705.17
43cf1c24-739a-5845-87dd-32cf3482d2aa | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh shrinkage compensated grout with a minimum of 40MPa.
d552a07f-a1b5-5091-b4f9-a3523593b2c3 | note | ○ Height shall be within 10mm of the design level.
1d2f8d45-d969-5f19-9a6c-808d61cb0ecc | note | Method - Visual Inspection, Measure
5130d9c6-1b3c-59a4-87ba-733229c4c856 | note | Frequency - Each Lot
85fa2c8e-50db-5df0-b490-3ba20cb2f667 | note | Category - IP
82e76c94-e74b-5d65-88ac-adb06c6648a4 | note | Responsibility - SE
5a3c657d-b27d-5bfe-a125-bc21dce8218b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Pits - Pit Lids
a546db0b-50a6-564c-b8f9-7f8addff502a | note | Reference - IFC Drawings Section 705.04
dd48582a-52bc-5b16-bf72-55dd03d558d2 | note | Acceptance Criteria - Precast steel reinforced concrete drainage lid shall be manufactured, supplied and installed in accordance with design drawings marked as IFC.
f63b1b66-6273-583c-884f-3770f9a83bce | note | ○ Stitch pour concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
a0768b0f-973b-5227-9fc9-9335b730eec1 | note | Method - Visual Inspection
743eaa04-7d1b-5954-bc24-6d6b67218a02 | note | Frequency - Each Lot
f6f0298c-5d70-57af-9e84-798d1a897433 | note | Category - IP
a62aac45-42bd-5fb4-8543-1033d2a63477 | note | Responsibility - SE
00578dce-ccad-579b-a29c-df1115d34346 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Pits - Backfilling Around Drainage Pits
39385246-9c9a-565a-bab1-e5d9b28d2be3 | note | Reference - IFC Drawings Section 705.18
a7040614-b5b8-5d0f-9389-b2a681efd706 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
56200937-dc86-51ee-845a-fce7a3135f1c | note | Method - Visual Inspection, Measure
f79087eb-eba1-5f98-8868-9ca2f8db1546 | note | Frequency - Each Lot
09b2ace8-a67c-541a-9870-85c6b31b94ab | note | Category - IP
a6bd6df7-c0fd-547d-976e-d839b5d61121 | note | Responsibility - SE
528b907e-bcb2-518c-96c8-b7f7f2df3547 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction / Post-installation Activities
| checkpoint | 6.1 - Flushing & CCTV
09dc7f98-0d3c-56f1-85b0-34200ff1ec72 | note | Reference - Section 701.28, Section 701.30
b7f56798-cc8c-5882-984a-bbf919bde10b | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
cd9646b4-0072-5b40-a5f6-eaf3d25222ce | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
20c362a2-f9a6-5389-a44c-df42e84ca250 | note | Attach: CCTV Reports
ecbc2b8c-09fa-5b74-99d0-e2756fc90efd | note | Method - Document Review
4301ce90-a877-5f0e-8cc4-a0cf1cc5af79 | note | Frequency - Each lot
8556dadc-c39f-5d3a-b7ac-82902dc51c27 | note | Category - HP
ce378851-dac0-5a0d-bc43-7b4851ba3279 | note | Responsibility - Nominated Authority
4851a1ff-2055-5e05-8f22-8d1187a22b7b | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - As Built Survey
cba313c7-9b07-5ac1-a2c1-ebdf62eebd98 | note | Reference - Section 701.10
5d8ca926-afd9-5970-a77b-98fc556cdbd2 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
25442efe-24d5-5594-b596-70d266141363 | note | Attach: As-built Survey Report
a3661928-a648-5470-a0ed-71d9caa46a8c | note | Method - Document Review
dff49d16-defa-52be-9294-96f570a72165 | note | Frequency - Each lot
c3827a99-a3ac-5e12-ab7a-5786d09a166c | note | Category - IP
15e55f8b-2cf4-51c4-bead-34f9bfbc2de8 | note | Responsibility - SE
f85c8a2c-e68b-5a9b-a17f-e47186339846 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Repairs to Damaged Pits/Pipes
3c76b9ce-0a71-5b96-aa00-7319a4136551 | note | Reference - Section 701.31
0f7c04a8-efd9-5fa6-bab0-34941116c0c0 | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
4144ca45-13e1-5ccf-9345-bc3532745f45 | note | ○ cracks wider than 0.5 mm
2a65bbb1-5719-5bfb-9c51-04a293cf3701 | note | ○ spalling of concrete
aec19f51-fe06-5375-92f4-0f2b4d7150a6 | note | ○ exposed reinforcement
6b0e417a-afca-55ca-a5da-d06a810d2faa | note | ○ joints that are not fully engaged.
235f860c-7215-5f05-a34c-45b4f5a3cc05 | note | Any pipes with defects greater than the following limits shall be removed and replaced:
014d6f91-dfb1-5f8e-b7f4-f57ba3b886c7 | note | ○ longitudinal cracks greater than 2 mm
bf74a57f-b4ed-5082-a6aa-66c57856d499 | note | ○ circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
04bb3da6-1e31-55b0-9c11-eefcc3961fc7 | note | circumferential cracks around part of the circumference with width greater than 4 mm
6e0a67c9-cad5-5feb-8b4d-424707c14b03 | note | ○ penetrations with area greater than 400 mm2
066e6161-b018-5e4a-9763-1b360cdcc74f | note | ○ pipe joints that are separated.
37dca482-20f3-5464-98e3-3c79b84e2ba0 | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
2d766e36-5865-5fa3-81bb-d5f2f1912fee | note | ○ hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
5e46c6bb-b3f7-59c7-9561-d59658b6a575 | note | ○ fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
72df34b4-d6b7-5e27-94d7-5036cf9f8e7b | note | ○ spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
fec110b3-841a-57f3-94b0-fe6e388fbf40 | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
abafa821-6748-5ad6-93cf-7dcf5da14a4b | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
297bb982-3473-5e03-80c8-bc12ab6de7b7 | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
0c0586e1-bcbb-511e-9652-2f1f7dfcf0b6 | note | Attach: CCTV Report Review and Post Repair CCTV Report
4c3af28d-a993-5ca9-aa78-94d8e275d1c5 | textbox | Enter: Teambinder Approval Number for Repair Procedure.
c0c07e2c-7edd-5821-a779-bc35947a737a | note | Method - Document Review of Repair Procedure
044980a2-0b52-5a4c-ac9b-a311aba5f480 | note | Frequency - Each lot
d85846f0-c96c-50dd-bcc2-f526727a649f | note | Category - HP
b5a0e516-d8d3-5b62-97e0-046256979aa2 | note | Responsibility - Nominated Authority
0655bbce-9710-549e-87c2-03f9c601316e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
c49f8268-f823-5b9c-be4f-824b90d1013f | note | Reference - MRPA Quality Management Plan
c5412385-dff1-5995-9ee0-b6770f1dbee8 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
b28505e5-2fbb-51ca-ac1a-eddf270696c5 | note | Method - Document Review
97f8e0e7-6b1b-54aa-9c54-013f650a3147 | note | Frequency - Once, prior to closure of this lot / element / Work area
53f78474-2bbf-5609-9c1d-52ad05890234 | note | Category - HP*
91a34c10-b6ae-520c-8955-eeccff9b28c3 | note | Responsibility - PE
267cfeb8-20a6-5b23-9ba0-a01f39a5993f | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
2d08ffde-8c2c-59d6-9ba6-710abd5ec064 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3a65af7f-8f35-53cd-aa16-0f976451213d | textbox | Name:
4c106481-b52a-55f4-b5a1-55829e57289d | textbox | Position:
fc85fbbd-6cdb-5d82-960b-a50e3d78a48c | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-117-CIV-BRUNT-Melbourne Water - General Concrete Cast-in-situ Rev.0 | itp | ITP-117-CIV-BRUNT-Melbourne Water - General Concrete Cast-in-situ Rev.0 | 3b45ab60-bd37-46ae-bcde-41d52b5dff82
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
149b51d9-3915-5e6e-951a-0e47237dd2bc | note | Document Title: ITP-117-CIV-BRUNT- Melbourne Water - General Concrete Works
dacf1b16-6afa-5759-9706-27d6139fc8e9 | note | ITP Description: General Concrete Works - Melbourne Water
5dcc6845-22c3-5437-b773-7b6bce752517 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
580b35db-9759-5443-bf18-2f1098fe35aa | note | Discipline (e.g. CIV/STR/RAIL): CIV
dbc59c8f-ea42-5f68-91fd-919e4a7a387f | note | Revision Number: 0
22651a12-89c2-52c3-8aa2-9cb48a3485e1 | note | Revision Date: 7/12/2023
c5a90201-0001-577d-87e8-54691a9da610 | note | ITP created by: Samy (Shubham Bajaj)
0df2c238-0cc6-5f2d-9790-e17be82b99dd | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
745f393c-b983-5040-bf3d-57a861bd898a | note | Reference - VicRoads Section 703
| checkpoint | 1.2 - Non Dependent
2a1baad9-0080-514f-a3ef-2acf7a81d938 | note | Reference - VicRoads Section 812
| checkpoint | 1.3 - Non Dependent
f18a2e0e-b111-5dd4-a24e-1b4d15048c3c | note | Reference - Melbourne Water 7251/08/420
| checkpoint | 1.4 - Non Dependent
dc32d7f1-3a93-5e69-ae13-ef69427d8241 | note | Reference - AS1379-2007
| checkpoint | 1.5 - Non Dependent
01cf7b11-4673-5cff-a637-2494fae4526c | note | Reference - AS3610-2018
| checkpoint | 1.6 - Non Dependent
42944d6b-4df5-5e26-bd51-d7fdb11a7414 | note | Reference - AS4671-2019
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Bedding Material / Base Layer
4f7ff155-0abc-5ef1-b4ab-6e7b12fd043b | note | Reference - IFC Drawings Section 703.21, Section 812.04
dcae3e42-2831-50da-9aa0-578304ed4873 | note | Acceptance Criteria - 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
6d0f37ff-f62d-51d7-aca0-b8a88da29eec | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
83e6ed11-f71e-50f7-ab41-ef3bb4ad3a2d | textbox | Enter: Teambinder Material Approval number
e2903216-6608-57fd-b512-22a1259d6aa6 | note | Method - Document Review
14f664a5-046f-5b86-8a9a-360764a0ed1f | note | Frequency - Once, for each mix design, prior to placement of material
f59ac0ce-7aa2-51cd-b4c3-3aa2d952e9d0 | note | Category - HP
84849312-f3c5-5f88-9495-d9a3adb37077 | note | Responsibility - Nominated Authority
374d76e4-413a-52b0-a701-19db070840ad | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete Mix
743f8172-260a-5586-bb40-e24468047265 | note | Reference - IFC Drawings Section 703.05 (a), Section 703.07 Melbourne Water 7251/08/420
4af8f258-bb0d-5fc8-a76f-eb47a96f7faf | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
af4e1c1d-3367-5e17-ac4b-7a70d703b656 | note | ○ Paving concrete mix conforms to AS1379.
19c8d968-7497-5bda-a7d8-22f2e967417e | note | ○ SUP concrete mix is registered with VicRoads.
88c9a677-109b-50e3-adf3-003b619aaa81 | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
b7dcb277-be8f-51c9-b399-0d7438afe4eb | textbox | Enter: Teambinder Material Approval number
9cfe94d1-0aba-53f4-8890-78e203b80c10 | note | Method - Document Review
e7de0efe-ef87-5941-b2a3-12bb289cbe16 | note | Frequency - Once, for each mix design, prior to placement of concrete
6fb7dff2-fc96-5b70-a2db-3e477b5bedfa | note | Category - HP
7cdf02b2-fb0a-5b90-917f-43be0e9aeb46 | note | Responsibility - Nominated Authority
4a33de53-292f-53b1-9a93-059697e5332d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Reinforcement Certification (or ACRS Certification)
1425d879-d8c3-5848-84bf-9dd806f3fe9c | note | Reference - Section 703.13 MRPA Quality Management Plan
0fd84481-ace4-5026-98da-04b8563e7061 | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
63b1d3e5-2179-582a-9c5e-018d86b4d961 | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
5aaad3fb-f5fd-564c-98f7-fed4fc116b6d | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
b86db152-5857-5057-8307-c15062294bba | textbox | Enter: Teambinder Material Approval number
0574ac42-234e-5bef-96db-8b444da35b6e | note | Method - Document Review
d8998778-d2f4-50f8-a70d-5d5af092cb72 | note | Frequency - Once for each supplier, prior to placement of order
721d0b5a-f385-5d68-9e38-c0e7d74e3dfa | note | Category - HP
f2c54cea-38ca-5f0a-b281-b72d59ce0f58 | note | Responsibility - Nominated Authority
52652094-06b6-58c6-b17f-ef4d92c899be | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
211b19ef-54c8-58ef-a88f-c34f9c6a7850 | note | Reference - Section 703.09
f607c502-ab23-5031-965a-bf8f5b7bdbe8 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
c90f4f77-9162-5fb0-93c1-5ff89938c842 | textbox | Enter: Teambinder Material Approval number
04d36ee4-341c-5680-bac2-c407955356db | note | Method - Document Review
7c626ab6-f2c0-54a3-8c58-7208163e4075 | note | Frequency - Once for each supplier, prior to placement of order
13b5bc21-e96f-5ed3-9fda-0c79b2277468 | note | Category - HP
6979361b-0272-5c8e-9eea-3a3a251ca579 | note | Responsibility - Nominated Authority
eb6584f2-e46f-55e4-916d-85d3f677ec77 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
9eb08984-2056-5ea5-a974-3d053c5cea21 | note | Reference - Section 703.10 (a)
49eaabf4-4751-56f0-b74d-db434537d766 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
7639cc7d-dd25-5e92-9b66-87208a60aa0d | textbox | Enter: Teambinder Material Approval number
0b500ae2-3255-5650-810e-6db499305fd6 | note | Method - Document Review
e4875bf9-88fa-50fe-b010-61a11c247bc6 | note | Frequency - Once, for each product, prior to placement of concrete
41c85806-81ee-51c5-91ea-6d46c4cdb46b | note | Category - HP
f5d38476-c1df-5747-98e3-9737abd11ecf | note | Responsibility - Nominated Authority
62bc18ba-e774-5ae6-a7bd-3dcfbc93441f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Subcontractor ITP (where required)
0d0e90d9-25af-5f1d-b6f7-3b91cb7778b8 | note | Reference - Subcontractor ITP
703580a9-5b4b-5112-a12e-99ed0fe7deeb | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
ded4cb80-ace1-579f-8f47-36fb55732a8c | note | Attach: Approved Subcontractor ITP
02a77e2e-0edd-5d0d-962a-0cbb27b98c07 | note | Method - Document Review
0072e271-9b4f-5a87-98a7-cf93d3cb2c4f | note | Frequency - Each Lot
08c85bf1-3a23-5526-8b2d-a6f8a54d7d4d | note | Category - HP
81562e8e-1a90-57e9-80f8-64c77966ea5b | note | Responsibility - Nominated Authority
7d83225b-f146-5dd2-baf0-417b51f857a2 | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - IFC Drawings
f87ae1b2-baff-52b7-8da4-71d1eacfd1f4 | note | Reference - MRPA Quality Management Plan
fa8fcc23-ea0e-56ca-83bb-6c91d6fa1407 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
40354d3a-042f-5dc0-908b-546276720110 | note | Method - Document Review
47f45287-c3d4-540d-9e38-a394fc29c585 | note | Frequency - Prior to starting Works and at regular intervals
d12dd32e-3615-5eb4-ab4d-d696a24749a4 | note | Category - HP*
57d049fd-6d50-5317-9d43-5d6c76233499 | note | Responsibility - SE/PE/SPE
8f72e98e-e706-5663-af79-5f281a6b6a4f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out
4e64d1a6-4887-52ef-b5e4-dbaaacb02c81 | note | Reference - IFC Drawings Section 703.17
e114b4fe-b4de-5b6b-9e09-12daa29cc319 | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. Maximum deflection angle of 18 degrees
fe3a9dee-2da8-50aa-a5de-1e5707556788 | note | Attach: Survey Report
a508bb01-7ee3-5ae4-833d-80de715cdd7a | note | Method - Document Review, Measure, Visual
0d31b660-5a04-59bf-9866-3d109a53da53 | note | Frequency - Where applicable, each lot
e3f725e4-303c-5a18-8ae9-46af82af40f8 | note | Category - HP*
8f6d96cf-f75f-550b-bfa0-e2d0dd33f232 | note | Responsibility - SE/PE/SPE
0886482d-9b33-5884-b415-e8dfbf0996b0 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Excavation
a621220a-4b50-5546-a939-960679b4e536 | note | Reference - Section 703.20 Melbourne Water 7251/08/420
4df57554-153a-5704-ae94-73698c400e34 | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
63b54f96-87cf-5539-aac1-0e45d1a50056 | note | ○ Excavation to allow for a minimum of 50mm reinforcement cover on earth face and a minimum of 375mm from pipe joint.
7a11a107-be5c-520a-a427-099f987d9017 | note | Method - Visual, Measure
20306516-6798-56d3-a7d6-714613d2152e | note | Frequency - Where applicable, each lot
8712fa85-a19d-5865-966c-03769aa831fc | note | Category - IP
e3723c34-828e-5b20-acbb-11c1f4eb2467 | note | Responsibility - SE/PE/SPE
997673b4-5bf7-5f8f-9df7-f7e0e1443d83 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Bedding Material Placement & Compaction
4e4b182b-1866-5f19-aa32-4ed5032e68d9 | note | Reference - Section 703.21
a23ca4d5-3da6-54e5-980b-727ff1f9e986 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings (equal to or greater than the relevant Council drawings).
2f7ed2ca-0d28-55cd-843e-7007d58a9ace | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
9f890aca-0e54-5f07-b26a-6b04265e7d87 | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
aa0f3910-cddb-5850-afee-db17d0298415 | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
9d0bba15-55b8-5e3f-933b-bb4d147919e7 | note | Attach: Bedding Material Delivery Dockets
95076f37-806c-51d0-afbb-c0f0b1dda1a4 | note | Method - Visual, Measure
27b729f0-87c4-5b21-8117-8333dcd1858b | note | Frequency - Where applicable, each lot
e7b7942c-699d-5f21-af03-54b8f40b5338 | note | Category - IP
970305d7-de77-5594-9acd-5e840689328f | note | Responsibility - SE/PE/SPE
ead43519-4a77-5066-bbd2-2bc0b5e8bb5c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Formwork Construction & Placement
ac4618b9-6f9e-54ec-ab6d-a4adfd63de99 | note | Reference - IFC Drawings Section 703.12
58dbc380-68de-509a-a74b-13ac06d7b3c1 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
fd2fa878-dc73-572a-8887-0ea6bb8bbf0a | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional comformance.
f23e10cd-6ed4-579c-8f91-de2ddc910d23 | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
9b025f08-8cc4-5c86-a294-578dfc97a9d4 | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
030164a0-9c28-51ef-bd1e-ef7da6bace0f | note | Method - Visual, Measure
61b0f1a0-cbb0-50b7-957f-4efb19b0196a | note | Frequency - Each lot
9908008d-66d3-5f88-b57f-3c21b66b3834 | note | Category - IP
56d00eac-d3e8-52eb-9b43-b99b02f65158 | note | Responsibility - SE/PE/SPE
05d30503-1012-5e76-8d8f-cd2f6d95c597 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Construction Joints & Matching Exisiting Surfaces
16138324-3311-5aa1-88f9-a8ac42e29780 | note | Reference - IFC Drawings Section 703.24
a153b887-ad27-54fa-80f9-f338c272f713 | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
36dac088-15ca-5ff9-ba2f-b61fde04a292 | note | ○ Consult the relevant Council Standard drawings for the joint detail, these may require:
f801f9ad-85b2-58fb-839a-1f1f03b8e193 | note | i. Concrete cutting of a shear-key
8851d367-fc30-5d25-9b50-62daa1e24f12 | note | ii. Surface rouighening
eb5c22ce-a53e-502d-b347-736ca4324d24 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
c2be33ef-400d-5976-84c3-a3c709284482 | note | iv. Cutting a groove for sealant
51b4a4a1-f7d7-5622-b00b-3749413dae52 | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
3fc78622-ef1f-52a0-8990-1c330c3efdb2 | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
27fcb916-96fe-5a6e-a19b-acaff31b8a49 | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
dbb9c992-0229-5a7c-8230-a1c8599a3300 | note | Method - Visual, Measure
92af8682-887d-532a-92bf-17813fa7c979 | note | Frequency - Where applicable, each lot
1dc954f0-cc1f-5456-942c-c81278de319f | note | Category - IP
894e04b8-859c-5c17-ad6c-090c378e46ff | note | Responsibility - SE/PE/SPE
428f84a0-a92d-5067-a991-e24e803e8900 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Isolation Joints
e14ac1c9-5ea5-588f-8cf8-3f5462c70224 | note | Reference - IFC Drawings Section 703.26 (c)
c4476877-62f3-52de-b59b-39f01244c2bf | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
b0ae9e98-63fb-520c-abd4-706bc46fee5f | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
d4dd71d3-1cba-55a4-804f-1b2aae585a2f | note | ii. at any location marked on the drawings
c3ac0294-beee-5d09-90e0-5e27aac71a3b | note | ○ The joint shall be made with a compressable material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
f4b01ee7-3b81-5ce0-b4e3-b71082a22114 | note | Method - Visual, Measure
002d3cf3-a402-5770-a213-e88d5b92f15a | note | Frequency - Where applicable, each lot
24ccb1f8-0dd2-56b9-9ac3-70e93549b14d | note | Category - IP
fe0f7918-c08f-55f3-90a4-74731984d92d | note | Responsibility - SE/PE/SPE
97112de3-c281-5b80-a496-38b4174ac607 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Reinforcement Placement
8b722235-ef86-5573-bd38-4202ad90066a | note | Reference - IFC Drawings Section 703.13 Melbourne Water 7251/08/420
5e53e016-868e-5d64-a3c1-140ec0444733 | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
b265b7ef-d79b-5532-b74c-089975391868 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
91c40c02-4900-5a84-b037-0b6779c6773c | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
664f8f1c-be0d-5d1f-a944-50bbed6d798b | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
94440f33-4fa4-5148-aff9-aacfb70a0ca6 | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used to support steel reinforcement.
b504c398-ac20-54c4-b133-f6f2ceeb12ff | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
b82fdb4a-8ef7-5cc5-aa55-65dce360d53a | note | Method - Measure, Visual
8d79d166-0bb5-548b-8065-3f0642037130 | note | Frequency - Each element
f2af12ad-9808-5b24-9b2a-2f8e55619a3b | note | Category - IP
d0b0a694-d679-5521-bc71-0051cd355512 | note | Responsibility - Foreman, SE/PE/SPE
ca3f64e4-e4cf-501e-b314-7f4b784a3a0b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Pre-pour Inspection
974a2388-acd5-5355-8c60-c0a448de8997 | note | Reference - IFC Drawings Section 703.15, Section 703.21 Melbourne Water 7251/08/420
13f7e26f-5be4-53b4-be8c-c297c5b70df5 | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
7b64e29b-b603-5d94-b32c-34d24724751a | note | Method - Measure, Visual
f72bf60a-6282-5609-b886-47b693d66572 | note | Frequency - Each lot
6374df00-cb92-55fb-8b8d-d006b5a292d9 | note | Category - IP
a4b4e495-6ec1-561d-9132-2f4510fa9536 | note | Responsibility - Foreman, SE/PE/SPE
ea9461c1-487d-5b9d-b645-457c4bdc73e9 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Weather Conditions & Evaporation Limits
7d059f1b-6165-5cb1-aee3-e52388ebdc9d | note | Reference - Section 703.09
28598e40-bdfc-5407-9440-191612a85483 | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
e8d6e072-b254-5599-b8e6-9e1714c35438 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
25c0e98d-0da8-5594-a119-7de699d72dd7 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
952def4e-114a-5db8-8639-3e30f5e9a39f | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
6f425d25-9543-5bc2-93fd-767b832faa10 | note | Record: Required information on the Concrete Pour Record.
86547eae-e382-5f4e-a241-7ffe65f85d95 | note | Attach: Concrete Dockets
def8eade-666f-52f4-8402-5f3c403d7bcb | note | Method - Measure, Visual
cb73b640-0a52-5988-9f0b-59d17ee33b05 | note | Frequency - Each lot
23a328c1-54cb-5373-bacf-1eb877e50d73 | note | Category - IP
1d48db3a-fd6f-50e8-b9fa-c27b51024fe0 | note | Responsibility - Foreman, SE/PE/SPE
b8e6c909-80d1-5a0c-bcb5-640d8d0e1aa6 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Concrete Testing - Sampling Frequencies
8dfd1ba5-a607-50c4-a17b-6de7d852edc1 | note | Reference - Section 703.11 Melbourne Water 7251/08/420
ccf94ad1-efe3-5f7f-a109-5922876ee0cd | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
c98ea9ed-9331-5603-99c9-7fbebc269aca | note | ○ 0m³ to 50m³ = 1 sample
78ff0a8c-aeb9-59c0-9624-36774f2b6f94 | note | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
b16645ea-777c-5c19-b4e7-a757820532e0 | note | ○ Compressive strength cylinders = 2 no. 28 day strength.
0fce46fc-5638-5637-a462-97e68ea84b24 | note | Record: Required information on the Concrete Pour Record.
913c53e5-9355-551f-b074-e997e11db493 | note | Method - Test
c7c36fe1-19df-53f2-9b3a-ae26060d96a4 | note | Frequency - Each lot
9b4ec6ce-4a83-5264-86ff-c568bba3dd73 | note | Category - IP
d62a00a4-d924-5cff-a8c5-4cf8b8c9e901 | note | Responsibility - SE/PE/SPE
7ad557bd-0832-5d62-9e4e-78a3a4e2552f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Concrete Testing - Slump
9b14a17d-8d69-5166-a9b8-cfb29bfcbefb | note | Reference - Section 703.11 Melbourne Water 7251/08/420
9559c917-5113-5a2a-b812-9fb565a43860 | note | Acceptance Criteria - Slump testing tolerances =
510138d6-302f-59a6-b691-f708f4897c19 | note | ○ <60mm = ±10mm
df4ff477-d04d-5b19-9041-3c7b8a5839e7 | note | ○ ≥60mm to ≤80mm = ±15mm
4cc656dd-1b0e-5b8a-bce8-66b39465102e | note | ○ >80mm to ≤110mm = ±20mm
1b8b2e5d-03cc-5e30-aeb3-28317f65a9a9 | note | ○ >110mm to ≤150mm = ±30mm
e1f28a93-5507-59fe-a7b6-1bdf126f756f | note | ○ >150mm = ±40mm
4657afd8-0434-513d-a780-0c3346ee69bd | note | Record: Required information on the Concrete Pour Record.
21b46f2f-7731-51b8-a165-af93a926b61c | note | Method - Test
d6b99719-f04f-5cf9-b833-6ef5967b33ae | note | Frequency - Each sample
5e563977-1e79-50a0-b3cb-2bb4e6d9f7a9 | note | Category - IP
56ed5f14-0234-5df7-a973-a3bbe4410cb3 | note | Responsibility - SE/PE/SPE
6436e545-c992-5914-bf20-90af14337bce | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
a81fec12-dac7-5bb2-8838-435e112ae2e9 | note | Reference - Section 703.11
6135ad2e-0a6f-55bf-9bef-c820c90cad9e | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
fde36eed-be77-5f49-a1a9-b3b1d2d61273 | note | Record: Required information on the Concrete Pour Record.
3173b2fc-3495-5efc-850f-57a8753911be | note | Method - Test
3d81b56e-4907-5fe3-9aa6-030533bad598 | note | Frequency - Each sample
8b13c711-5a82-5e6d-a240-afe655ebc959 | note | Category - IP
12db80ad-b0b9-5a28-8959-2f5f59206262 | note | Responsibility - SE/PE/SPE
5633e69b-5bae-5d86-aab0-3f41a06e5e58 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.12 - Supply & Discharge Rates
bf610a19-dbe8-5dac-8355-d26cc7363f13 | note | Reference - Section 703.08 AS1379 Clause 4.4.1, AS1379 Clause 4.2.3, AS1379 Clause 4.2.5
153681f9-8689-5960-bf6c-38c59f5b2902 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
1d0abf00-7755-5848-97df-9099f8e4ed48 | note | ○ Maximum elapsed time for discharge (including compaction) is 90 minutes from batching.
4319e8b9-68cf-512f-9a1f-3489b7cfadf3 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
50808efc-050a-57f5-9b57-55ffcde54bdb | note | ○ If water is added once discharge commences, the volume shall not exceed the water-cement ratio for the mix design and the water volume is recorded on the concrete pour record.
3dd747c4-5879-52ce-8f5d-749bf159c2f5 | note | Record: Required information on the Concrete Pour Record.
0b1861b6-d0b4-5be0-8e67-13442623f3ec | note | Method - Measure, Visual
41484890-4d83-5e73-96d8-bd72266a73cd | note | Frequency - Each load
3e18f5b9-09c1-5e9d-b914-acadb9198119 | note | Category - IP
0d4b0fe8-e680-5bb4-953d-8f969429d9b7 | note | Responsibility - SE/PE/SPE
83f43470-d41c-5164-ae41-d90f62980536 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.13 - Placement & Compaction
3ec1c56b-db43-5fcd-85bf-9e100e11c798 | note | Reference - Section 703.08 Melbourne Water 7251/08/420
d607d9f4-dc2a-5385-a17c-c84ddcf2aa9e | note | Acceptance Criteria - All concrete batches are traceable.
a431f680-a4c5-5ce9-a410-46ccb809a3e7 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
8bcd4707-4f7b-5442-aacd-a8c62c170270 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
03f0db3e-7063-534f-85ba-d58894ad5711 | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
3db86e88-96a3-5425-9fb6-2b7670f535c5 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
c073d1ff-4dc0-510f-9c74-18b0e1f6d368 | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
9a7bfdb1-ae79-584c-a13e-cbedae0d1110 | note | Record: Required information on the Concrete Pour Record.
6197987b-3fb2-5e24-a827-7badad02a4f8 | note | Attach: Concrete Pour Record
3b908437-b89e-5060-87ce-f777b51dfda9 | note | Attach: Concrete Dockets
ac076024-5712-5820-b8c9-b85ebbc73ebe | note | Method - Visual
9bba5001-0332-5426-afcb-a9c597472e89 | note | Frequency - Each load
51ba9be6-f002-5bc1-aab9-9053cfe53184 | note | Category - SP
88027ea2-434b-55f4-831e-9e71a5d0b138 | note | Responsibility - SE/PE/SPE
c90ae6a3-b0b4-5d68-a45b-e76a171e3f5d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.14 - Surface Finishes
d3b82168-1cc3-5a44-a944-d9c40465dd49 | note | Reference - IFC Drawings Melbourne Water 7251/08/420 Section 703.25
9d084651-6d16-5583-b559-afeff2ac5eb8 | note | Acceptance Criteria - Surface finish shall be as per the drawings or; as a minimum, finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
21361bb4-87e9-5efb-9367-310907640eef | note | ○ All outside edges of slabs and all joints shall be finished with a suitable edging tool.
fb0229ba-bfc1-5f7c-b077-31d073a2782b | note | Method - Visual
ca69450b-bdd2-5c70-9838-6196a838cb4c | note | Frequency - Each lot
8ee77ad5-7ec2-572c-aad7-f8ac83887ad7 | note | Category - IP
39ee3417-745c-5e41-9ec3-b4164209a563 | note | Responsibility - SE/PE/SPE
e0bcf852-535b-514b-805b-53c362dbeea2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.15 - Marking of Conduit Locations
3079608a-e447-587a-9687-e17208aac4c9 | note | Reference - IFC Drawings Relevant Council Drawings Section 703.28
7f555ec9-edf5-5298-a9d2-8ac9ff0ce0e8 | note | Acceptance Criteria - The positions of any existing conduits passing under edgings shall be marked by a chase in the edging immediately above the conduit together with the nominated identification mark shown on the drawings.
5cbcc425-378d-5d95-85c3-992d84987409 | note | Method - Visual, Measure
eba264b4-fbce-5014-b6f5-e51fb3407c91 | note | Frequency - Each lot
dd713d0e-27ba-51b9-ba71-f85fecac8426 | note | Category - IP
e3a4c33d-a965-5af8-a10d-ff8d23fee808 | note | Responsibility - SE/PE/SPE
6a7ab03f-014b-5203-8bc6-c0ee873a7782 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.16 - Crack-control Joints / Weaken Plane Joints
6f8cab59-24db-5ea8-9961-8a1d51e13b5c | note | Reference - IFC Drawings Relevant Council Drawings Section 703.26 (b) (ii)
479cd143-a9ca-5436-abbe-040bf522c56b | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
4964dcaa-2c6d-5c93-9547-c09ee0793bb3 | note | Method - Visual
e798a059-d4e9-50b7-ab9b-e2321c796b2e | note | Frequency - Where applicable, each lot
31c97db6-2553-5457-9d55-183987e79b5f | note | Category - IP
73ab9d3f-83c5-51b3-8430-17de82edf76f | note | Responsibility - SE/PE/SPE
0c71d27f-20d6-573c-9359-d4bca0d2e9ef | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.17 - Curing
2e63af47-4bbf-5f3a-81f0-8e975c3fa3d2 | note | Reference - Section 703.10 Melbourne Water 7251/08/420
a706fc01-0785-535c-8831-455769b4f592 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
c38c2bed-5094-54f4-8344-2604437a42a6 | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
160ee02e-ee6a-58c8-9087-b900dc5eaed2 | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
4c1d8b29-03a7-59c0-b18b-9f11b668f78d | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
ebf5be17-e328-50ff-a625-a23f349f9133 | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
23297f15-ea60-5b8c-8faf-8b3082993f1d | note | Method - Visual
568f7cd4-3a96-58e2-a78e-807d237aef6c | note | Frequency - Each lot
3e604755-c1f4-53f5-9682-38b698e7eb10 | note | Category - IP
fa42f02b-f066-586b-a448-a326b48c630a | note | Responsibility - SE/PE/SPE
bc1332c5-1a8d-5bb8-9bea-01dde5143063 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.18 - Protection of Newly Poured Concrete
acf6df8e-7265-538c-ad24-369985c875a0 | note | Reference - Section 703.27
3194ffc5-3d88-5390-a027-68ac1a89f518 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
623ae09f-0b3c-5c52-ac9f-b693fd1352c1 | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
a9620469-235a-5684-94a7-a8453e9f54dc | note | Method - Visual
f407b7c2-5915-5d60-9793-d6f76a8fa47d | note | Frequency - Where applicable, each lot
2e83d2dc-fe9b-5660-a092-8b6b5ae2f70f | note | Category - IP
b47e19d2-08cb-55d6-b6a4-ebfc09185646 | note | Responsibility - Foreman, SE/PE/SPE
0ff0c4cc-ea50-59d7-95cb-50fcb9c55543 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.19 - Stripping Formwork
59770cb8-efac-591e-89af-fa228d6a9fab | note | Reference - Section 703.12 AS3610 Table 5.4.1
683394d6-852a-5bb8-8858-d061be64584d | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
15ed1adc-dc51-5baa-b9a7-2e866c2397a4 | note | i. 2 days for vertical formwork on external surfaces; and
bcd8624d-a670-5047-9412-a5dade3069f7 | note | ii. 1 day for vertical forms on permanently hidden surfaces
bc7203dd-d609-5289-91d2-85736129583f | note | Method - Visual
e441d83a-6fc3-58d4-a110-e0a11f48b18a | note | Frequency - Each lot
da04cf0a-3f0e-5c9a-89a9-d55fd887d45f | note | Category - IP
72c2655d-6efd-56ed-bc3f-fdbcb793737c | note | Responsibility - Foreman, SE/PE/SPE
aaad4ce2-2897-58aa-91dd-7b4b9777d375 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.20 - Surface Inspection - Cracks
20c9df13-9c41-5d0f-8df3-b5519b96741c | note | Reference - Section 703.3
d6c0bc8a-e56c-534e-8cc8-3bc73e1d9e0e | note | Acceptance Criteria - No cracks greater than 0.2mm.
524a1b8a-5f5d-54e9-8331-a1a39d358ace | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
321bcb20-5f28-5cc2-b06d-5677d207eed6 | note | Method - Visual, Measure
3299788f-7036-5602-8a0f-091755139edb | note | Frequency - Where applicable, each lot
5ebef6e5-bc82-59dc-8cc5-841d3b5ee2f3 | note | Category - IP
75cd104d-6611-5d65-8cef-4fd755bbc3cc | note | Responsibility - SE/PE/SPE
001515eb-3aaa-5a45-aded-a00adc8f4c6c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.21 - Surface Inspection - Surface Finish
17e8123b-358d-5ac3-bcd1-519b28a4ba42 | note | Reference - IFC Drawings Melbourne Water 7251/08/420 Section 703.25, Section 703.10 (a) AS3610 Clause 3.2
ba905b34-2782-57dd-900c-2a5297e5001e | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
7b02b381-da8c-53d9-8147-d9a3b0e2478b | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
f7f46777-fe05-5073-aa16-e65b502a30f8 | note | Class of finish:
b3f9e484-8bcc-5cdb-b215-23b25e46a875 | note | ○ Permanently hidden surfaces = Class 4
e72d9852-7299-5b51-88e1-56397d2538d1 | note | ○ All other surfaces = Class 3
9902885b-3915-517b-a7dd-8342fd8f83da | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
9761ec18-2d42-5610-972a-878aa1136903 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
35acd66b-4af2-5d03-8875-13480bdcf593 | note | Method - Visual
a90e6f81-ad9a-545c-8091-c04b0565a113 | note | Frequency - Each lot
73015aad-a1bd-5f46-90ac-9bf4f15aa7c4 | note | Category - IP
66a22b6d-463e-54a0-b136-26800b52dfb1 | note | Responsibility - SE/PE/SPE
d231129b-d450-5ede-91cd-87e1b329b7b7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.22 - Backfilling & Pavement Restoration
8286d9b7-c823-5b1f-b792-cf27e4c7db9f | note | Reference - Section 703.29
c545e55c-81cc-55ba-91a3-91a2af4c36d2 | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
9eb7ba36-dc82-56f5-b99e-b01b7398de31 | note | Method - Visual, Measure
c2fb1fb4-08b9-5e92-9bf5-d5b8405acd04 | note | Frequency - Each lot
ca656454-4bad-5528-98a8-8683585c2584 | note | Category - IP
5c8e2fec-e045-5953-b067-7e040d1b9345 | note | Responsibility - Foreman, SE/PE/SPE
a25fbd8d-3cb7-50cf-8a35-927c24828f70 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.23 - Compressive Strength Test Results
19a6ad6b-3af8-5613-afb3-734caa7e386d | note | Reference - IFC Drawings Melbourne Water 7251/08/420 Section 703.11 Table 703.111
a062b9ab-ed6a-5bf4-a6a0-33dafdbf2c12 | note | Acceptance Criteria - 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
73d0d109-c07b-5e19-b482-f197e664e754 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
84f139cf-bcb8-5ac8-9a14-9e1dce1d7ea1 | note | Attach: Compressive Strength Test Results
b30f941b-6b00-5c0b-9b6c-7f8eaba0409f | note | Method - Document Review
e54cffa8-c625-5d1e-9ee2-2d099ea43149 | note | Frequency - Each cylinder
9c3c1aa0-26cf-5a1c-85d2-c29961c78fe7 | note | Category - IP
4dfc66b6-21af-5416-a714-361e57a6b312 | note | Responsibility - SE/PE/SPE
d56861a8-182f-553a-aaea-292154bdd5da | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - As-built Survey
c4e02118-42b2-50dc-96ea-3663b9045457 | note | Reference - IFC Drawings Section 703.15
9c7e65ad-555d-51c0-9fc0-8b2fabba5489 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
ddca4e6c-3f74-5245-9fa1-f5546ca1c2db | note | ○ Departure from RL = ±10mm
096056f6-9d43-567b-a952-d82289ada080 | note | ○ Departure from alinment = ±10mm
1a335cae-05b4-54c6-85a6-7d3e2c77c064 | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
c95ac1fa-5204-5c48-a268-b57c958ef01e | note | ○ Irregularities in alignment = 5mm in 3m
ba390596-e898-504b-8fcf-054313ec6eb0 | note | ○ Section dimensions = ±5mm
a9c5cc2e-7ba7-5c0f-8a32-17642b29117e | note | ○ Section dimensions (less than 25mm) = ±3mm
085c5a18-1267-58ba-8c71-b05f130ddaf7 | note | ○ Width of pavement = -5mm, +15mm
32ec69f5-9201-5f0f-8cf2-f9af85130723 | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
2e191bf4-1ab9-5dc7-9d98-f0cb8cb9c8d6 | note | Attach: Survey As-builts / Survey Report
49736a19-03e4-592b-b836-cb61a251a9bf | note | Method - Document Review
72446eb4-2d06-5006-ad6b-adf0f12c6bf2 | note | Frequency - Where applicable, each lot
ceacb133-d684-592b-8e7f-9f24868a6ca9 | note | Category - IP
540d8901-a2aa-580d-a59b-a5b7b89877ae | note | Responsibility - Surveyor, SE/PE/SPE
f05d88c4-605e-59e5-ae87-62007262fb34 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
bc5d087e-b6ad-5b06-8006-ef8cd0343a2d | note | Reference - MRPA Quality Management Plan
65fd2924-7437-55e6-98d7-0fbaa214bfe0 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
530b18e7-8af1-5372-aa9b-bd5cfddd8108 | note | Method - Document Review
78bbbf2d-c0b1-555b-abbe-0bb2fc0bfca5 | note | Frequency - Once, prior to closure of this lot / element / Work area
2710b8de-8e3b-52e1-ac7e-93c952c0dce0 | note | Category - HP*
aecf6255-2ea4-54c3-bf50-8fa147c9c621 | note | Responsibility - SE/PE/SPE
63cbccd3-7a01-5c88-814a-997196fef33a | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
1e65d891-a66b-5a26-9de3-b680a4784a0e | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
626dce4c-80c2-5dd3-8486-9efcaa506dcb | textbox | Name:
434ddff4-5f54-5bc3-b23b-ead012a80a8f | textbox | Position:
8363e908-e847-57e8-acc2-60777f2dbb3d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-119-STR-BRUNT-Concrete Coating (Anti-Graffiti and or Architectural) Rev.0 | itp | ITP-119-STR-BRUNT-Concrete Coating (Anti-Graffiti and or Architectural) Rev.0 | 35fc3203-c4bc-46d2-b2fa-d3a79ad44b88
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
db65015a-dc91-5bf4-8344-0392708216e9 | note | Document Title: ITP-119-STR-BRUNT-Concrete Coating (Anti-Graffiti and/or Architectural)
703a1bbc-bf9e-5898-84d4-3fa4112eb7b3 | note | ITP Description: Concrete Coating (Anti-Graffiti and/or Architectural)
9326b649-98b7-57fe-bba3-9366df328c20 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
6bb13153-02ab-550b-acb2-d4a5eacdf722 | note | Discipline (e.g. CIV/STR/RAIL): STR
2d50f598-8db7-586a-a7ef-db61b7e82cf2 | note | Revision Number: 0
0758b63e-6a07-558d-b223-5e75740fad09 | note | Revision Date: 8/11/2023
f4edde0b-d690-552e-a483-b9eaeeac3c99 | note | ITP created by: Mike Freeman
6b62647e-a1e0-50f3-b0e9-f5d4c96f4911 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
eddc9c6b-a9fe-531c-8f07-5e10d6d5a10a | note | Reference - VicRoads Section 685 November 2018
| checkpoint | 1.2 - Non Dependent
c6de3268-ae63-5b01-9e7c-3081a63949d3 | note | Reference - VicRoads Section 686 November 2018
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Anti-graffiti System Selection
d7601b56-af32-5562-8772-1c7794e0a528 | note | Reference - IFC Drawings Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (e)
29e9eaff-8b78-5c34-957e-96d00c74ff38 | note | Acceptance Criteria - The system shall be selected based on the following criteria:
161efbd4-862f-5649-8c67-68e4c5e9b6f2 | note | i. be either a film-forming or a penetrant system
7b031087-04cd-50e0-b8e4-c9940025a182 | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
e3a8f34c-8f1b-5324-a5f2-a51e7431b0be | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
9349cb17-3867-5ed9-9e6e-4774f4b9d353 | note | iv. be non-yellowing, colour-fast and not subject to fading
681c5f49-f975-5afd-90fa-963603fd473f | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
afef0c93-a18a-52f2-87d7-5d50b5134ab3 | note | vi. application thicknesses (film-forming):
da21d1a1-5886-55c4-b121-a064f423a4b0 | note | ○ WFT total = 175µm min. OR
f5db087f-3207-5c4c-8429-4497b35c153c | note | ○ WTF per coat = 88µm min.
4a12804f-10d9-56c0-97ac-f430a98e69e1 | note | ○ DFT total = 100µm min.
1cb0f8ef-2351-542d-a767-331ea57e6b90 | note | vii. adhesion to substrate (film-forming):
9ff7357c-f7d9-53c2-9b3a-c9e766e22454 | note | ○ 0.75 MPa min.
b66b9e56-9000-58eb-8742-f7a6ca5a0cd6 | note | viii. application rate (penetrants)
4a515344-1b3b-5eeb-9a33-3ba452db523d | note | ○ as per the minimum thickness on the manufacturer's TDS
b018ebc8-67ab-5326-adae-6024178f8694 | textbox | Enter: Teambinder Material Approval number
e5585f63-6380-5f34-a25d-9cb744ab6919 | note | Method - Document Review
6dc2a2c8-8b25-549c-b665-f74e0ee36889 | note | Frequency - Once, for each coating system, 14 days prior to application
c2a825ea-8a23-59e0-a9db-ea5c37571168 | note | Category - HP
85add2db-23c9-5df5-a0a7-fe70c7e3dc4e | note | Responsibility - Nominated Authority
975d4f1f-43c3-5f87-a2d9-d199bdbcda0f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
3102ba9e-7638-54bd-9365-05e629be8d24 | note | Reference - IFC Drawings Coating System TDS, Surface Cleaner TDS 686.04, 686.05 (a) & (b) Table 686.051
e197985f-5dbe-5d0a-bf9f-9a4147fd867f | note | Acceptance Criteria - The system shall be selected based on the following criteria:
38ae15f1-d36f-52bd-b594-ab676de2ebb7 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
efe9b386-c5e6-5ee9-b20a-45f18fc14f35 | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
65d26649-b382-508f-ad8c-17eac9be952e | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
c21cea90-5385-5c22-9a91-505375ff397c | note | iv. be non-yellowing, colour-fast and not subject to fading
09268d87-4885-5d99-9a92-06ff7211ba95 | note | v. be guaranteed to last for 10 years of outdoor exposure
412f342b-12b2-5fe2-9e78-e687524c0c33 | note | vi. application thicknesses:
7eb9fa0a-67d5-573a-b9fe-a48fc4f6b906 | note | ○ WFT per coat = enough to achieve the total DFT
8964d9e1-0663-5085-9e43-64afb39a1bc9 | note | ○ DFT total = 150µm min.
d1b77378-42d2-5158-b01c-b46dd64b6977 | note | vii. adhesion to substrate:
f848982f-90a7-51d4-95de-bb048170eb58 | note | ○ 0.75 MPa min.
d9c2a661-ec32-50d2-9c13-26fcbccd84e8 | note | viii. able to bridge cracks up to 0.3mm wide
289dbe58-76b4-5675-a2fa-ee6e37b8aa14 | note | ix. able to be re-coated within 24 hours
5f863bed-4ad7-5b45-8d4b-2479a58e6094 | note | x. have a minimum pot life of 1 hour
9daba6cb-43be-5a8a-98cf-71d06fc5e2c1 | note | xi. compatibility to an alkaline surface
fb13dfb4-f41d-517a-be77-2d67b9625bec | note | xii. equivalent air thickness >150m
a89ac291-1137-5e20-905f-5a4ac2e5c3d7 | note | xiii. equivalent concrete thickness >450mm
1ff1b87f-71f8-5c62-b1f0-c3534432955d | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
e3e647d1-bc3a-5a48-bf0f-3759a4f4b18b | note | xv. Water vapour equivalent air layer <4m
be73784f-21b6-5727-ac5a-7083fb4c5762 | textbox | Enter: Teambinder Material Approval number
c431c7d2-5497-5b48-9a46-b8312514a6d4 | note | Method - Document Review
9e567297-d493-5405-ae0d-c1ad38130091 | note | Frequency - Once, for each coating system, 21 days prior to application
cc5ce9bb-1432-52d4-bd51-e50ee7a9b3f0 | note | Category - HP
82539dc9-c7fd-5d7b-bfe9-9b564dc7e12d | note | Responsibility - Nominated Authority
99408547-448b-53a1-85ab-e83a97ebacd2 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
65e95548-b757-50e7-8229-24218908b859 | note | Reference - IFC Drawings Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051
41b8d431-f810-58bf-a8e9-2e98458d0c4a | note | Acceptance Criteria - The system shall be selected based on the following criteria:
cfc786ad-b163-5023-b6e0-2f1329e555f3 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
abb977f7-c514-5b84-840d-3b2907c14b70 | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
996f77a2-0ceb-55fd-852b-b874777d07af | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
ea7adcaf-cb6a-5466-8b49-49e69077eaa0 | note | iv. be non-yellowing, colour-fast and not subject to fading
bd84f6b9-730c-55fc-afa7-3ed60d7dbafd | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
03dc3508-2451-54d2-8cc4-b040127b9d7b | note | vi. application thicknesses:
a70a566c-1ecf-5b9b-a5da-53677adafe69 | note | ○ WFT per coat = enough to achieve the total DFT
6ab5b18d-eb69-5aa8-ae3f-af217be22c0d | note | ○ DFT total = 150µm min.
1e2eebf4-20cb-5f9f-b20b-3c2522554a7f | note | vii. adhesion to substrate:
14692f13-ab9f-5ebe-8e34-1957309812e7 | note | ○ 0.75MPa min.
8e17e337-5203-5e99-a541-694e0a300837 | note | viii. able to bridge cracks up to 0.3mm wide
4f2b0d5b-8c19-5079-b57c-a407246a080b | note | ix. able to be re-coated within 24 hours
9a25dc9a-11d8-54d7-89bc-af5d17d64c9d | note | x. have a minimum pot life of 1 hour
9d493c59-6a7e-520b-a362-6d68ea52dd08 | note | xi. compatibility to an alkaline surface
dda143c4-5583-5cbf-995d-03675a4c5b97 | note | xii. equivalent air thickness >150m
6677cbef-0da7-5c74-af5a-f93622f0ba11 | note | xiii. equivalent concrete thickness >450mm
0f9701b2-d086-57dc-90f0-7aca7edaa66e | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
819d6dfe-a5c7-5e23-bb39-a80e99f3dda0 | note | xv. Water vapour equivalent air layer <4m
48043b5a-5d79-509f-b182-d8144c269f40 | textbox | Enter: Teambinder Material Approval number
8e2ef543-be2f-5118-809e-e6fe421c8d68 | note | Method - Document Review
18836959-8149-54c9-92e6-76e4555dc945 | note | Frequency - Once, for each coating system, 21 days prior to application
ef339e0d-442e-50bd-82bc-f7f4cf79b7a1 | note | Category - HP
8e462617-c101-576d-8394-8eec43e1f305 | note | Responsibility - Nominated Authority
aeb17213-8e17-5c33-a48f-e3982490a79b | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
6b43c6ba-8213-5a63-9840-4d78f0f594a9 | note | Reference - IFC Drawings Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051, 686.05 (c) (i) & (iii)
2cc1e0ae-a28e-5992-aea3-4fc73ee5de86 | note | Acceptance Criteria - The system shall be selected based on the following criteria:
f71d6083-9ae1-50e9-829e-9ba50c677eae | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
8dfec640-da8a-5cec-877a-a5fbedf733c9 | note | ii. all coats to be compatible with each other
d6b1e472-52ae-5f18-906e-04f8a785b292 | note | Penetrants:
8f488e8b-0018-5ab0-b41d-ec89d33dc4bb | note | iii. active ingredients:
a1b51c91-bc46-5aee-935b-198ee49b3d9d | note | ○ Silane = at least 95%
305c574d-db2e-5c77-880c-17dbc31838ac | note | ○ Solid silane & silane cream = at least 80%
4440406d-e663-5782-b15d-43781faa8d63 | note | ○ Silane-siloxane & siloxane = not specified
01037203-55cf-5f34-b23f-9982942401ba | note | iv. application rates:
c6c7bbe5-4d22-5aea-9f04-22fd70de42b7 | note | ○ Silane = 2 applications of 0.3L/m² min.
d949ea27-3f8f-5566-8741-681f10d3f72c | note | ○ Solid silane & silane cream = 1 application of 0.4L/m² min.
f0ca93a8-3c67-557e-87bb-fcff25bfbb39 | note | ○ Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
f25a44fc-21e1-55db-9568-0999d75647b3 | note | Film-forming coat:
95a49245-8c08-5b7d-aec7-ec7e46bd835e | note | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
f1119b1b-386d-5fd1-8df4-81800ea1e39d | note | vi. to be water or acrylic based, solvent-free
dd54d86e-75f2-5240-945a-6a3aa0a319b3 | note | vii. to be non-yellowing, colour-fast and not subject to fading
960296c2-bdc9-567c-b435-1307a0882133 | note | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
8a5225b2-34c1-5dab-aada-3c9db39f205b | note | ix. application thicknesses:
2da2a6aa-8dbf-5819-b908-fc0287775491 | note | ○ WFT per coat = enough to achieve the total DFT
16a65c68-7ed8-58d2-a717-cd35ee10d742 | note | ○ DFT total = 200µm min.
d1dc793a-065c-5cba-876a-f28b6fddbd7a | note | x. adhesion to substrate:
c77f5d49-98ae-54be-941a-9b1282b75acb | note | ○ 0.75MPa min.
02f1908c-94f8-5d28-a80d-cabd57993cd7 | note | xi. able to bridge cracks up to 0.3mm wide
04b4c85e-ddd1-5c99-a0a6-4589a41dce1b | note | xii. able to be re-coated within 24 hours
6f363c7c-177d-5eaa-a0f1-e8d2d5c13a29 | note | xiii. have a minimum pot life of 1 hour
95909869-54c0-513b-b772-9351557e00f4 | note | xiv. compatibility to an alkaline surface
9fc2206d-7cea-56b5-b208-40fdef59e068 | note | xv. equivalent air thickness >150m
0b6ce612-fc18-54d6-a357-6de386ce141a | note | xvi. equivalent concrete thickness >450mm
3826eff5-6bc8-53bb-9585-2238b6ba4231 | note | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
34d389c8-d1e6-5922-b707-a6802c48a410 | note | xviii. Water vapour equivalent air layer <4m
c847c5ae-e839-5047-b227-93e352f3fe0e | note | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
551ae848-ba68-5ffa-b134-a73348d02237 | note | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
bcb4e856-ee8b-5de9-a3a4-2844df598044 | note | Enter: Teambinder Material Approval number
27972539-eba7-5c3a-ab30-2364a3634685 | note | Method - Document Review
ff1bf8cd-907e-5e6a-873c-3b35a2bf372e | note | Frequency - Once, for each coating system, 21 days prior to application
de4798e1-c516-560c-81a7-37236daba248 | note | Category - HP
4269eb80-fa12-554f-a92c-14d43931123e | note | Responsibility - Nominated Authority
39a03d3f-e338-528d-939e-c43d91f9dac5 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Work Procedures
4de2f293-f20f-5aaa-b0d7-8d63e65dd0d5 | note | Reference - 685.05, 686.04
deb9bdfd-3a83-5671-887b-02d4b6f10f3f | note | Acceptance Criteria - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
5a49e8eb-28db-5b98-9ece-f72c9f05ee6a | textbox | Enter: Teambinder Hold Point number [free text box]
5d2b90e1-2d99-5e86-8497-7b0388b0aed7 | note | Method - Document Review
bdffaa35-9650-514c-a6af-b4ae4864b028 | note | Frequency - Once, for each coating system, 21 days prior to application
877b4b1b-9a7d-5f94-834c-122212223408 | note | Category - HP
9430f837-2461-5f07-b2ae-fed8ab5e1c48 | note | Responsibility - Nominated Authority
eafc8d04-26ef-525b-830a-26215fa7d299 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Coating Personnel & Equipment
703d665d-fe7c-5e40-be28-7d955c78a60f | note | Reference - Coating System TDS, Surface Cleaner TDS 685.16, 686.18, 686.08
72971ac2-91cd-5204-9b98-e3d55c560ac4 | note | Acceptance Criteria - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. The supervisor shall remain present at all times.
1d5f9a02-1ebf-5ab2-9925-827269123207 | note | ○ Application personnel require 2 years minimum experience and accredited by Paint/Coating System Supplier.
824c92bb-b0b4-5141-bc25-d1608e493698 | note | ○ Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
fd860136-f089-574a-bfde-4c226fc84dc5 | note | Method - Document Review
6fbd6066-715a-5c21-b003-c94cf9751671 | note | Frequency - Once, prior to application.
2fd98035-a57d-5e42-8680-881a544a81b5 | note | Category - IP
c7bc9802-437d-57bd-9913-6f42b11f7bd7 | note | Responsibility - SE/PE/SPE
d4aa339b-8aee-584d-b4a7-e821cecea0e4 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 3.3 - Protection of Adjacent Works & Property
ab41044f-f304-58e7-be72-a16ccefb71e2 | note | Reference - 685.17, 686.10
26f2a97a-3cae-5b1f-a780-44f47d68945a | note | Acceptance Criteria - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
6e24d381-3285-54a0-8bf0-7bf97065b348 | note | ○ No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
cc31ff90-f6fc-5dca-95c5-2777a646d929 | note | Method - Visual, Document Review
8bea7462-9e98-5a0e-96fa-21d4c4075b12 | note | Frequency - Where applicable, 2 days prior to application.
d60bf14f-692f-5117-baf7-be8df87b89a1 | note | Category - HP
2c8d996e-4407-5504-bb60-88defaac692b | note | Responsibility - Nominated Authority
c14ce419-fafd-5678-94ad-6bf6ce833fdb | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Minimum Concrete Curing Period
fa2a4316-9e1f-5fe6-b016-9a5dd9a2ef53 | note | Reference - 685.08, 686.16
8dd8e165-3756-5158-8db2-08a047edc4cc | note | Acceptance Criteria - Concrete shall not be coated until the minimum concrete curing times have elapsed:
8fe0599f-ef35-5004-bfea-dd5163c62f99 | note | ○ Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
835edfc1-073c-597d-a98e-58d642cac204 | note | ○ Accelerated cured concrete = 14 days
9dba8064-315e-5d4b-82fb-571bbb4d9244 | note | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
92e2c773-a470-54b2-85a2-f275e47c9e81 | note | Method - Visual, Document Review
5f652397-06c3-58d3-80b3-187eed943f33 | note | Frequency - Once, prior to application.
a15247c9-339d-54b9-a65f-00fd2faecaf8 | note | Category - IP
7f2f3073-9d76-5d63-8665-b4cc4bb4cc66 | note | Responsibility - SE/PE/SPE
a8689bbc-c46d-5c61-aeed-3675e6be9995 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 3.5 - Trial Application (or Past Performance) Inspection
51c17e7a-49d2-53cc-a9a1-a7e895c40e97 | note | Reference - 685.11, 686.13
a5ddadc4-69ef-5b6d-ac3d-fa675ceb3b51 | note | Acceptance Criteria - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
f7dc5c3b-706d-501f-b04e-7985b2fe74c5 | note | ○ Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
97949602-b90c-5acc-a891-6802b6c2af44 | note | Attach: Inspection Photographs OR
70e1f7b7-d957-5efa-8624-0f64fd38597f | textbox | Enter: Teambinder Hold Point number
45166210-88a2-5b77-9817-0b28644bc81e | note | Method - Document Review
2562c7eb-b3e2-5ec4-8703-3aa275b6f00d | note | Frequency - Once, for each coating system, 7 days prior to full coating application
4376122c-052f-538b-981c-47cd9991d236 | note | Category - HP
67259f05-de02-5527-8f12-30c985296743 | note | Responsibility - Nominated Authority
b4742d6a-8ea3-5f6e-89b1-3d88d2e8f3a6 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Application Activities
| checkpoint | 4.1 - Coating Material Records, Handling and Storage
352c4fbe-01ca-51ee-9602-3df755e59a90 | note | Reference - Coating System TDS, Surface Cleaner TDS 686.12, 685.10
ad5991ba-6ce1-50d5-92f2-8fe939cefb4e | note | Acceptance Criteria - Contractor to ensure that the following requirements are met;
d16664ff-06c5-5988-8c81-8aa7be0d6015 | note | i. Materials are left in their original, sealed containers until time of use and stored in accordance with the manufacture’s recommendations;
6ba576e2-191b-5682-8f73-26e768e391b8 | note | ii. All materials; shall be brought to site in the original unopened cans clearly labelled;
d49de142-3c35-5ad4-825c-25b2d52c008f | note | iii. The contractor shall maintain records showing which elements were treated with each batch.
279a305a-6271-58ad-9cea-505a7774e82f | note | iv. Materials stored beyond the manufacture’s recommendation shelf life are not used.
da29695b-355b-5f79-b862-09c95f46a3be | note | v. All coating materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients.
3d6fffd1-28cb-5703-a988-8830ef59acdb | note | vi. Coating materials which have exceeded the pot life recommended by the manufacturer shall not be used.
b30c4e10-defc-5b3e-8438-e9332e5246fe | note | Contractor to record the following information and attached the this ITP.
b42a8ba1-0fb1-5f73-8ecd-1ab444f2fabb | note | i. Manufactures’s name and address;
bb343bc0-cb00-5aef-9521-f5d70890b81f | note | ii. Product reference;
4d62245b-bedd-5782-bd05-fb59ab244be2 | note | iii. Batch number of identification;
53d3b22f-d628-5eb5-b5c6-225081cd9a0e | note | iv. Quantity manufactured in the batch;
2329d351-72fb-5722-9e68-c026805ea444 | note | v. Date of manufacture;
f4cdbc8d-449a-5f69-84c7-2d861e347889 | note | Attach: Sheets/Records with the required information above.
7a5fe2df-3125-5294-8039-55ecefd82497 | note | Method - Document Review, Visual
baecfda0-8c70-51d1-9e05-9bf28798172a | note | Frequency - Once, prior to application.
0f175273-cfe4-500d-b2d8-d80a7855f5de | note | Category - IP
a7d0da7e-88e6-566e-8c4e-832e98f48c2a | note | Responsibility - SE/PE/SPE
01e5bf67-efa8-5f43-b593-9979650199d4 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.2 - Weather Conditions
002309bc-4834-59a5-9252-c76fe29e8c98 | note | Reference - Coating System TDS, Surface Cleaner TDS 685.09, 685.12 (a), 686.11, 686.14 (a) (iii)
408e0695-5ffb-5f43-9a00-ffbc7a1f608e | note | Acceptance Criteria - Coating systems shall not be applied under any of the following conditions:
33517276-7f5f-5269-abb5-a16f3fb721dd | note | i. windy conditions where spray/splatter may be generated
d1e496e5-c6b1-5238-9599-558e77320e31 | note | ii. when wind-borne debris is likely to contaminate the uncured surface
d01f2587-7d74-536d-8f1a-229cb97fd346 | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
95483a5a-eed5-54d5-a5de-098bbb280ecc | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
e13932cb-e3cf-5a38-9fb2-4e285926cbb8 | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
8a048257-7e9a-5ccf-8c6c-34cba83d0476 | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
bc1c8f94-ef05-540e-870a-966daa7c78a8 | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
ba098a87-9b7a-58c3-a5ab-07398861e70b | note | Attach: Weather conditions are to be recorded.
c2effd06-e2b8-5cc9-b1ee-daf99932b83c | note | Method - Visual, Measure
7a33036c-8fc9-5c64-ad52-8675ff8c62a8 | note | Frequency - Prior to application and every 4 hours per shift
20bdb80d-fe8b-5d96-8762-08b903b2aedc | note | Category - IP
9db82394-cff1-566b-b7bc-75fffd20ebfd | note | Responsibility - SE/PE/SPE
91dbe000-a384-5292-8d55-26ac8f01b08f | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.3 - Surface Preparation
f1c8ea2d-1668-5ab1-b1bd-268000d76944 | note | Reference - Surface Cleaner TDS, Coating System TDS 685.05, 686.06
2b864669-39db-5f48-b43c-eb229b8efba5 | note | Acceptance Criteria - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
0df4b607-cf62-5353-add5-63c353c8f882 | note | ○ The surface shall then be flushed with water.
6ae50618-5ac5-5331-8c23-a20897175c54 | note | ○ Any concrete defects exposed during the surface preparation shall be repaired accordingly.
22cbdff8-fb7b-5832-923f-729f3532a476 | note | Method - Visual
8cd50042-b3ea-5a3b-9735-8c44cb82a78f | note | Frequency - Once, prior to application.
a408fff0-3fd5-55cd-bb9e-1ddf7ae6d92a | note | Category - IP
46bed111-adb1-51c5-bb32-76e52c7a8eee | note | Responsibility - SE/PE/SPE
ffdc5891-3c05-5090-8e53-46829c7845c2 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.4 - Surface Moisture Testing
55d965b6-a306-5c61-af66-b33c80e4a4ce | note | Reference - 685.12 (a), 686.14 (a) (iii)
5c182bb1-0d7d-5f99-a53a-23c42ad89438 | note | Acceptance Criteria - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
518872ad-b8e1-5737-a200-ba7dd70afeeb | note | Attach: Surface moisture conditions are to be recorded.
ed326d22-dab0-523e-ae31-dad30c549444 | note | Method - Test
be6e58e2-a416-5cc7-a422-45c8a948c727 | note | Frequency - Immediately prior to application, 1 no. test every 50m²
b4d2dc0b-2a12-517d-8027-8f716930ff50 | note | Category - IP
045ddb6f-ade6-5517-b20c-0b3c2e06685d | note | Responsibility - SE/PE/SPE
a3193379-8dc9-5f27-9be0-0a102914d03f | note | Verifying Documents - This ITP Signed-off
| section | 5. Application Activities
| checkpoint | 5.1 - Method of Application
250b10b5-ee7f-57ea-bf69-f3e0b2aa6a00 | note | Reference - Coating System TDS 685.07, 686.07, 686.09
be7887e9-b933-55b9-afe0-392b34300cd0 | note | Acceptance Criteria - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
9c987775-b392-55e9-af57-d7fd156fb3d4 | note | ○ Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
65a2057f-dbb7-5706-a148-ebbbef30b2bf | note | ○ For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
9f6c04d9-1d7e-5481-9efe-e619d6d523a2 | note | ○ Times of coating(s), material names, locations coated and volumes used shall be recorded.
c79ef8cf-b395-51b1-9faf-f7bfaff5bc2b | note | Attach: Coating Application Record
a87f11cb-e68b-5908-a8c3-d95fda905c8d | note | Method - Visual, Measure
19d15795-2f08-5178-88c5-ce46ac653967 | note | Frequency - Each coat
d2448d20-6c65-511f-807a-fe7f99da8a3a | note | Category - IP
e6270a38-fe80-5325-bbf6-182e07b286a5 | note | Responsibility - SE/PE/SPE
8ffb569e-f780-5736-a6f1-7f57894ca803 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.2 - Wet Film Thickness (WFT) Testing
277086b1-3eb8-500e-83d7-0dcde9a25b79 | note | Reference - Coating System TDS 685.12 (b) (ii), 686.14 (b) (ii)
3630bfaf-3bb0-56f7-842e-d30d0b61cd7c | note | Acceptance Criteria - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
3f7ce241-fa23-5907-9fac-dcbd049d4e4c | note | Attach: WFT Test Results
a3c53483-a0dc-571c-981e-b0eb2345783a | note | Method - Test
117d879e-7bd5-5852-9ceb-53ed31c6feab | note | Frequency - Where required, 1 no. test every 50m², 3 tests minimum
9caffeb9-3884-51a6-a7d2-f773e27fd9ba | note | Category - IP
ef60bfdd-b705-51fb-be35-72ab02659018 | note | Responsibility - SE/PE/SPE
36e505d2-d344-5984-b0a5-853f8dec5ec7 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.3 - Inspection & Defect Identification
9a19707c-be30-5f56-bc0c-29dae449dc49 | note | Reference - 685.07, 685.13 (d), 686.07, 686.15
7b27bdb6-d211-5d7c-b9ea-a719e6939d05 | note | Acceptance Criteria - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
246f7146-981a-5bc8-a7c1-7aba4e142067 | note | ○ Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
a6fb9793-dc28-5127-94c1-5e3fb479f162 | note | Method - Visual
bc0478c2-9153-5ab2-94a1-26443c9baccd | note | Frequency - After each coat
fca5821f-c3ff-537e-ac9a-27f29d2cff27 | note | Category - IP
9eb46508-8f3d-5774-8c62-73b22d772cac | note | Responsibility - SE/PE/SPE
cffc73af-cbdc-5a74-80e7-604466b6d8f1 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.4 - Drying and Curing
1d4a427f-bb84-5e62-a236-3377fc7f68e2 | note | Reference - Coating System TDS 685.17, 686.10
38610148-0d9d-56df-8419-b644db1d9c72 | note | Acceptance Criteria - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
baaa9eb9-cf23-5c3a-8de8-f43dbfd4fa96 | note | Method - Visual
50741183-3c45-50ca-9955-8b8018f223f6 | note | Frequency - After each coat
7eafcd81-5963-585d-afec-faf8f5d36b6e | note | Category - IP
95bc57ec-6859-5d6e-bf90-91a95d1e8888 | note | Responsibility - SE/PE/SPE
2848f454-3dc4-542f-bfc6-47a24ce2d267 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.5 - Clean-up & Waste Disposal
21d4011a-3c61-56ee-9f21-828a2a449a73 | note | Reference - 685.09 (c), 686.10
42048cc0-9654-5fb0-94a8-91571a8be9f2 | note | Acceptance Criteria - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated.
ca8727fe-3e08-5866-bfdf-3cc2f37f768f | note | ○ All rubbish and remaining coating products shall be removed from site.
4fdddeaf-f168-5c5f-b080-0f804c73b0c4 | note | Method - Visual
9449a6de-db8d-50a4-b7be-152120687f95 | note | Frequency - At completion of Works
cbe3efe8-6241-5d33-8258-4e09b558be30 | note | Category - IP
2dd69b0d-006f-5249-9d86-a3a7668a7383 | note | Responsibility - SE/PE/SPE
95076ae6-3e42-5744-8a27-fb3fe04f6423 | note | Verifying Documents - This ITP Signed-off
| section | 6. Post-Application Activities
| checkpoint | 6.1 - Dry Film Thickness (DFT) Testing
a5417400-c871-5f0e-8457-1754bc835a8e | note | Reference - 685.12 (b) (iii), 686.14 (b) (iii)
4a2d5b47-027b-5512-9f53-246a3a449f64 | note | Acceptance Criteria - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
cf61e41a-c26e-571d-a1fd-09e2692b95cf | note | i. Anti-graffiti system = 100µm
429a3b90-2ea0-5dd4-9abd-39e99b6ed19d | note | Ii. Decorative & anti-carbonation = 150µm
046be2a2-cd71-52c0-8af3-d4e69e1c59f8 | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
2b27d35b-df78-5d3d-ba02-64ecbce12747 | note | iv. Atmospheric & splash zone (dual protective) = 200µm
23c9dd1a-37cd-5ff0-bf25-b1cf31f29bfc | note | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
884a4a41-ea99-5664-8e89-b82913f6e30e | note | Attach: DFT Test Results
8da3be0c-8329-57d0-9177-174c5e9cc300 | note | Method - Test
362f685a-cfb2-5fb1-a7ef-5482a08bb35e | note | Frequency - Where required, 1 no. test every 50m², 3 tests minimum
c736fbbd-b422-533f-b30d-bcd455ad4828 | note | Category - IP
b4de8ac3-9ce0-5617-99bb-a61fc274852c | note | Responsibility - SE/PE/SPE
27412c50-605f-5b1e-8058-ad2a43676a85 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.2 - Adhesion Bond Strength Testing
b229a18f-9982-5e38-af03-8cf8f95509ef | note | Reference - 685.12 (b) (i), 686.14 (b) (i)
b33ed5c0-4dd8-51fb-82a4-b1e97461d529 | note | Acceptance Criteria - A minimum of 14 days after application, the bond-strengths between:
35098db9-a139-5524-94b0-6c39c6650a3a | note | i. the coating system to the substrate, and
e1b472ec-8e09-5e84-90dc-8ab838a46869 | note | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
fbc4d5f3-5113-5029-9f96-ec2858f8dda8 | note | ○ The subsequent results shall be greater than 0.75 MPa.
5080dd25-53bb-5df6-b867-cf0efa44c43c | note | Attach: Adhesive Bond Strength Testing Results
55535a72-c1e3-5453-99f7-2016fe2a2372 | note | Method - Test
872ca2f1-543e-50ec-b113-4e8e9a2cbe67 | note | Frequency - Where required, 1 no. test every 50m², 3 tests minimum
5566b61f-8458-5c83-a4f6-b03d28cbc8eb | note | Category - IP
807d5edd-c06b-5a8d-ab71-8b38720680e1 | note | Responsibility - SE/PE/SPE
acd12f22-0034-5c88-b72d-717cf54bec18 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.3 - Penetration Depth Testing
d22d678c-dad5-5209-a6d2-92045b2991c2 | note | Reference - 685.12 (b) (v), 686.14 (b) (v)
be554ca0-e3f4-5882-97e2-e4bd71afb4f7 | note | Acceptance Criteria - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
4c6f7c2c-9313-584f-ac22-d6e66fcb97a4 | note | The subsequent results shall be:
81975a1b-671d-5e35-8e8d-5dba2b3cb46a | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
e2b84298-fc7d-57b3-b0ac-15370b4ede71 | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
948d9e03-8c28-575a-975c-2bff05a45793 | note | iii. Silane-Siloxane or Siloxane = 3mm min.
9a98ad5a-dff8-559d-af44-e0a98cbe879f | note | Attach: Penetration Depth Testing Results
27e9f0dd-501b-5f9f-b548-68dbf76516fe | note | Method - Test
ce506b5f-b767-59e0-b8f8-cbea433db5c3 | note | Frequency - Where required, 1 no. test every 50m², 3 tests minimum
73a38676-e620-55a0-8df3-01dd42338f79 | note | Category - IP
6c67d2be-9e98-5e2f-a69b-b9f70ebf6ae6 | note | Responsibility - SE/PE/SPE
023c003d-f20b-5a37-8748-992a0f0c2f66 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.4 - Non-conforming Coatings
036983d9-2729-5372-aeb1-b81b81b45199 | note | Reference - 685.14, 686.17
66995729-72ab-5269-9966-637c8fdfa15a | note | Acceptance Criteria - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired.
df896a36-c9c5-5632-9c76-5bd56306c11e | note | ○ Such Work may include removal of the coating, surface preparation and re-application.
2851a222-5029-5e62-8f26-567a6d9db823 | note | ○ Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
d76f86d2-9545-5060-a498-c4f26b6a42bc | note | Method - Visual
c0434014-aa3d-5181-861b-b1d220bd0979 | note | Frequency - Where required
ccdbb669-a568-57f5-bc45-23a1a2715b9c | note | Category - IP
5f04ae47-80e1-597f-8764-c5ce3725a255 | note | Responsibility - SE/PE/SPE
5b418d53-fef0-52c8-aef7-76966e34cff4 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.5 - Coating Application Guarantee
6c719c17-3fd5-5f3f-8c3d-b82c1895046d | note | Reference - 685.06 (b), 686.05 (a)
194e8f4c-2cbc-5969-9e7a-8cb4d70884a4 | note | Acceptance Criteria - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
d420468a-dbbf-5efe-a810-77015e3ebde6 | note | Attach: Coating Application Guarantee
0d4f6b2b-1a32-53cc-9eca-ea6f7f2af83d | note | Method - Document Review
1b202e8e-ae92-5634-9658-ca6ed16bc8dd | note | Frequency - At completion of Works
b415b2ea-3920-50d2-b91c-e44aed1f39de | note | Category - SP
c0094027-6fbc-52a8-9614-6dc8901178f9 | note | Responsibility - SE/PE/SPE
f197ae04-981b-5b8b-97a7-3ee3374dccec | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.6 - Repair to Damaged Coating
05c9c27f-5fef-5727-aba1-fa19d905cb3c | note | Reference - 686.17
b8e592ec-b56b-5f78-8329-7f4fd3fb3bb8 | note | Acceptance Criteria - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
7ba644b7-bcf3-52be-9376-527c74a467ac | note | Method - Visual
ee2203f3-2de0-5e68-99b6-f9ed98445292 | note | Frequency - Where required
7923e2fc-8b9e-508b-9fde-1f8abcceb84d | note | Category - IP
07280bbe-b327-50ff-8594-beb6d520ed21 | note | Responsibility - SE/PE/SPE
b37022f5-216a-5685-820d-5239fd73a200 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.7 - Non-conformance Report (NCR) Closure
11c2c217-d661-5eb1-8533-ab80e3e9be4d | note | Reference - MRPA Quality Management Plan
9739efb4-010b-54ea-b7f1-58f2c14148fe | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
8ac0b718-ffa7-5381-bdc7-b41206f28520 | note | Method - Document Review
f0248e10-0512-5385-93cb-9ca3281800f3 | note | Frequency - Once, prior to closure of this lot / element / Work area
4c99c2e4-2d81-5676-b9ab-ae2408a331d9 | note | Category - HP*
f2d70659-5a16-5485-b45b-bcd28e5172d9 | note | Responsibility - SE/PE/SPE
76ffaa17-bb0f-50c4-a325-e3b58d55bde5 | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
2e0b978f-082e-501b-ad50-7bdb14ddd6ba | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0bb11294-3568-51b9-afe3-ab6e627690c3 | textbox | Name:
19564015-f1c6-50e2-b093-8a2185108a76 | textbox | Position:
1e9977d6-80d6-571a-b80f-6251834d855e | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-127-STR-BRUNT-Structural Concrete - Friction and Approach Slabs Rev.0 | itp | ITP-127-STR-BRUNT-Structural Concrete - Friction and Approach Slabs Rev.0 | 4658fe4e-9a84-48c3-a482-3394071c7484
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
61147535-67c0-5325-9206-26634309fdf9 | note | Document Title: ITP-127-STR-BRUNT-Structural Concrete - Friction and Approach Slabs
ee6193b0-fe5c-5371-bcb6-7c8d9010e3ce | note | ITP Description: Structural Concrete - Friction and Approach Slabs
f5d775a6-f57b-5767-8fb6-f94950ac7769 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c2dccae5-905d-5c52-9586-e1cca57e9177 | note | Discipline (e.g. CIV/STR/RAIL): STR
9cdb3588-5561-5361-b23a-4ac80b4c06ce | note | Revision Number: 0
325bda9d-c6f6-5875-8060-7d41d0f159fe | note | Revision Date: 25/01/2024
f5a7ac92-dd7e-5196-8a4a-0145f1c78a05 | note | ITP created by: Yasna Naicker
934f4a35-5bdc-5721-9d6e-615f481c043c | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
b508b197-e908-5c4c-b9ae-acd1e40086a8 | note | Reference - VicRoads Section 602 October 2007
| checkpoint | 1.2 - Non Dependent
697c9369-02dd-5b4e-8036-f05f3803c230 | note | Reference - VicRoads Section 610 February 2020
| checkpoint | 1.3 - Non Dependent
b9eaf4ca-85ad-5a36-8836-59e6202818c1 | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
8ef001ed-c798-539a-bb95-f0e66078113c | note | Reference - VicRoads Section 614 June 2017
| checkpoint | 1.5 - Non Dependent
ff7ba512-caf4-5680-968b-0f0babe687b5 | note | Reference - AS3810.1 2018
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
1389cb7e-9c4b-5dd7-afdb-b2546962ea87 | note | Reference - 610.07 Table 610.071 IFC Drawings
bc2f2259-e98f-5fa0-9f87-f9e4eb59e7f6 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
9cbb342a-3ec7-57e7-a0c6-3bfa268840d6 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
d59a06ba-d915-57d4-9fdb-eb9614edcc7a | textbox | Enter: Teambinder Material Approval number
c9631031-1b48-5a50-90b4-ecbb359c7e22 | note | Method - Document Review
e266b3b5-287f-58e3-ab76-02a5d0eb41c3 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
d886b381-66a0-5c67-a9ee-ce9736eaeedf | note | Category - HP
23d65bc5-9ef1-5fc0-bf78-eef03b663e2b | note | Responsibility - Nominated Authority
3b56825e-0c24-50bd-9e9d-90d395e51b3d | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
a8aeede5-fc0e-57de-869e-2d0a357f48c8 | note | Reference - 611.05 (a)
b73e2fab-3c1a-5d90-b106-0c0379a90900 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
e305ce5a-e7c7-50c6-8e8d-9725d4f6b380 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
c17b3ec2-68c7-55cb-9e28-a51438db82c9 | textbox | Enter: Teambinder Material Approval number
e9383f0c-e030-5b20-8c3c-17793af6aefe | note | Method - Document Review
fbec4988-16a5-5838-8667-8f0e3c5ab9d0 | note | Frequency - Once for each supplier, 14 days of award of contract
9ef346e6-2c07-583a-adf3-17165bd8cf05 | note | Category - HP
46581ca4-2329-5c03-83c6-9a922b4520a2 | note | Responsibility - Nominated Authority
a5401d8f-c8d5-5bb9-ac18-3d0d92a2c8ed | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
d89c76c3-1ed5-5c70-8878-18cecfbb6217 | note | Reference - 610.26 (a)
f14ef951-51a9-5ea0-8ed5-698ec307c441 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
18bc8cbb-4a38-5f84-9125-4b79fb1cfc05 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
7a5f4dfb-d2de-5799-8114-641230cbf98d | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
ecd72732-a96f-5500-844d-572d9caacb99 | textbox | Enter: Teambinder Material Approval number
73762484-9b01-510d-9209-7d5807050575 | note | Method - Document Review
c6eda9a4-626d-51ec-847f-15e9bf117f08 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
1d975790-87f7-5b3c-b639-789489bcd9ff | note | Category - HP
98e4bc79-0c43-578d-928e-26dd1b79e268 | note | Responsibility - Nominated Authority
bf413bcf-463e-5def-852a-a2e770f17c91 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
10cef446-b0f0-5466-97f3-184d3070c792 | note | Reference - 610.17 (f)
f16257b4-84ca-5fe9-8d9d-60f5cb6860ab | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
a7412c73-2634-5370-ba76-2c7a6883d092 | textbox | Enter: Teambinder Material Approval number
8a3f9596-24e6-517c-8f66-1cf966f5df7a | note | Method - Document Review
9fb88589-4eb6-5b2b-8dce-ae5bb4c4cd76 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
7eb1a6b2-dd43-56c6-83a3-b52b79af7b45 | note | Category - HP
4a1d24f5-f469-5249-b5e3-aa83b37fea49 | note | Responsibility - Nominated Authority
8b5f074f-9849-5496-8e2d-77db3bf63fc7 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
f47e5326-fd90-5661-8ced-c8d87008de04 | note | Reference - 610.23 (d)
a12e607e-e502-5230-8736-0cef532f5d20 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
4ccdf0b8-d4c4-55d0-b39d-80b709797908 | textbox | Enter: Teambinder Material Approval number
d6e03693-a24f-5803-bf39-10b9ee20c159 | note | Method - Document Review
cedc45cb-8f85-5ba8-af1e-a8b61a787698 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
55e26d72-accd-5283-aa4b-13ac92f71340 | note | Category - HP
66246b2f-4f88-5998-adc0-50c985d0071d | note | Responsibility - Nominated Authority
27bb469a-dcac-5b96-adca-2a9d5bf2c31b | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
3f96ede8-b94a-589d-86ff-b554bb499c1b | note | Reference - 610.18 (a) (i)
be591daa-33ca-5d2e-a184-2ea7b2a71ba8 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
d9ecb88b-8f1f-5182-988c-1e0fee739998 | textbox | Enter: Teambinder Approval number
21b7179f-2cf4-577b-ad73-222ef2ab4c00 | note | Method - Document Review
d95fe09a-d69e-5daf-95f7-7107aee46959 | note | Frequency - Once, 4 weeks prior to placement of concrete
2d7e5a56-1542-5cd4-b47f-f6e4ff5ac9ec | note | Category - HP
f9e15378-2f97-5f61-8472-836eba4e4093 | note | Responsibility - Nominated Authority
7ac63729-d816-506e-a57f-84930ecf9981 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
09c70886-e7d4-55fd-a249-48cf3aa31e61 | note | Reference - 610.18 (a) (v)
fc27774c-dc7b-5515-b565-33b00e547af1 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
47dce9e1-8ffe-5d27-bfb9-ca3978df81fb | textbox | Enter: Teambinder Approval number
5d9af261-1a2a-599f-af8f-60f9376529ff | note | Method - Document Review
055b8f4c-99e2-5da4-bf87-ca0027f08815 | note | Frequency - Once, 4 weeks prior to placement of concrete
49b14ef3-5352-549b-8365-ede3b5b18c2c | note | Category - HP
de12188f-67c7-54d2-974e-f9e56e9c0b47 | note | Responsibility - Nominated Authority
e5a0100e-ca22-5105-a2d3-df1372ee048f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
8619bb0a-1d7d-58eb-bb1d-37b3dc965529 | note | Reference - 610.18 (a) (iv)
0de40359-1c33-5eee-ac1b-03b3bb5a9ad4 | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
69dfaf94-d6e1-57ea-8aa6-04d5b81ab8d8 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
1b50d518-0bb2-5b5c-88f6-9ffea16b0be4 | textbox | Enter: Teambinder Approval number
f8916cfe-4364-5f95-b324-70d0f11141a7 | note | Method - Document Review
5ac024ee-bd90-5f77-ad5a-67afba86a023 | note | Frequency - Once, 4 weeks prior to placement of concrete
4294890c-fd4c-5026-9ee0-cf5cc9e72552 | note | Category - HP
5c3da317-cf74-5616-af55-041dd48293ca | note | Responsibility - Nominated Authority
33f72d1b-8f6e-5002-b038-0b3dc5aa91ee | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
0f7ab57a-84d8-5949-9f04-8f89bffc1db8 | note | Reference - 610.17 (a)
47e9feb8-06ca-5690-a789-026b593445ce | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
4a4877a2-ff07-5e3b-b499-8e34a73a8ac0 | textbox | Enter: Teambinder Approval number
4029d235-9395-5299-a376-85e94a4e5f74 | note | Method - Document Review
5e171f47-07b4-5fbd-9615-307bd9e2d995 | note | Frequency - Once, 2 weeks prior to placement of concrete
ec40be5e-7888-5dca-9360-ab71d9bf1c25 | note | Category - HP
6893080d-ce99-5f93-b624-216cc88e411f | note | Responsibility - Nominated Authority
5b91fc86-0095-569c-b3aa-57dcad090ca1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
557b97e8-831f-5f07-b570-ff4b9908ccd7 | note | Reference - 610.23 (a)
59d0236e-65ba-5877-bf62-35a2f702786f | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
00528088-745d-573c-ae26-3d8d5d30273d | textbox | Enter: Teambinder Approval number
573de90d-8c18-5cb7-b346-2155e24b96fb | note | Method - Document Review
c276c044-199a-5e78-8631-5faa8ebaf039 | note | Frequency - Once, 4 weeks prior to placement of concrete
5eca8c83-33f1-578e-b2fd-9fbc55443196 | note | Category - HP
b78a6c8e-3125-582b-bbe8-672f0feecf77 | note | Responsibility - Nominated Authority
ff79dc86-d317-54ce-a9a2-10f02e842cb5 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Concrete Drilling Procedure
446f3c33-cc01-55c7-b4db-2c54df5768c5 | note | Reference - 610.46
db5ae10d-b27a-5fbd-82ae-7e55ed4effdd | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
6050772b-76d5-5a07-8c2c-31805d3b8580 | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
cbc6d13a-0721-5ee3-a408-6223269736a9 | textbox | Enter: Teambinder Approval number
c76e2400-a98c-5a3e-a489-a272c002875c | note | Method - Document Review
d2339eb9-5940-5277-8fe8-b3b9935e65a9 | note | Frequency - Where applicable, once, 2 days prior to drilling
24d0a497-cd0e-5162-85ed-0a9da2ad9ae5 | note | Category - HP
a560d88b-130d-5af2-82e8-4c3338aae17b | note | Responsibility - Nominated Authority
57e346b4-ff48-5872-ac15-f245ef73b75e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Temprature difference measuring-Calibration
047fcd0f-e8b2-56f4-87c7-027d5c3bf641 | note | Reference - MRPA Quality Management Plan
5721a042-346f-540c-8f0e-ad8240ae2937 | note | Acceptance Criteria - Calibration records are valid and up to date.
09b8877c-ce88-53c5-9b32-b3a15d2dbb55 | note | Attach: Calibration certificate
40fade3e-fd6b-5263-b4c1-2f5fefea9510 | note | Method - Document review
ea87d2cd-2d15-532a-970e-5bfeb90a48bc | note | Frequency - Where applicable
a03dcc83-3ce1-5f43-888d-96accfd8a0e7 | note | Category - HP*
35476b69-cfb1-5976-8c78-3d3c5f6c12ac | note | Responsibility - SE/PE/SPE
07cd2f86-88dd-5626-bea4-8de90da90566 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
3fb188c0-8b99-5419-9823-1d8dc8a54106 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
a0add404-b1b6-5cbd-a7f5-cf4fe3aa9938 | note | Acceptance Criteria - Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
befa30b8-c6c0-525f-918a-8d6c77e595fb | note | Method - Document Review
dc0536c0-db2e-5fd6-ac75-450bd597148d | note | Frequency - Where applicable, once, prior to welding
2bc6d7d8-5e91-5a63-bfb9-a2a1c4930b9a | note | Category - HP
31d5027b-4cb3-5662-b2d9-3354baa0f57e | note | Responsibility - Nominated Authority
6108619d-06d4-52f7-89ea-211505ceadd4 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
47f9b463-db9d-57f2-8d27-186315601587 | note | Reference - MRPA Quality Management Plan
70a3e772-5647-5e39-bd35-30b0b7497ead | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
5b9e5083-68d0-508e-a18f-a1a1aba51c8b | note | Method - Document Review
ecfdb64b-95f8-5849-95fa-ee45e848301a | note | Frequency - Prior to starting Works and at regular intervals
75841f5d-249c-58d2-84cc-6044cfc257ba | note | Category - HP*
b0285bfc-613f-54e4-a4fc-5c1f67ae7ae0 | note | Responsibility - All
29c34a12-774b-565d-87d4-eec5d67c4454 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.2 - Survey Set-out
6634c91e-5074-563a-b241-e13ce70978f3 | note | Reference - IFC Drawings 610.47 (a) Table 610.472
d931ede8-c498-5a93-9685-0bfeddb6fd9e | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
df96b1c7-68a7-5fe7-8d13-38ff7ed9e14e | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
8c9b1850-6cea-5ef5-9317-cbbf62e4530f | note | Method - Measure, Visual
cff1c9a9-9440-50cd-a39e-68bb05e28592 | note | Frequency - Each element
1890249b-72c6-52e3-aa78-a37398b18dad | note | Category - IP
61744e6c-eaaf-5d83-9e19-7d288b54321e | note | Responsibility - Surveyor, SE/PE
084ec987-ce79-5b62-9490-681e2bf6db83 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.3 - Excavation support
3cfad49a-a1d3-5ed0-874a-da35ece43211 | note | Reference - 602.02
8ac7f88a-559a-5e0e-884f-b11f9c4c93ac | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
a4a3f5e6-1ff7-58dd-ad8c-b7c87edafac3 | textbox | Enter: Teambinder Approval number
dbd8d1f2-0ca3-58d1-ad49-3772f40bcf6a | note | Method - Document Review
75f76407-27af-59fd-bd4e-f8c0172da99d | note | Frequency - Where applicable, not less than 10 business days prior to excavation
8606f73c-d2fe-5f26-886f-33a697644452 | note | Category - WP
e3a81b97-a932-516c-8520-400456ac52b3 | note | Responsibility - SE/PE/SPE
26eada94-8f4e-56fb-beec-8f95fe55d9f9 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.4 - Excavation Inspection
e7c64a07-7f23-55be-8f26-685f0865c936 | note | Reference - 602.03
9d3ab35b-0f30-524a-aa03-5528813bd35f | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
5c094087-1ce9-599c-9e44-a128ed01d856 | note | Method - Visual
66e92e9d-6282-5f70-a2fd-66308b64845a | note | Frequency - Where applicable, prior to placing blinding concrete
440b091b-d9d4-573c-8e83-b9402c7b0e89 | note | Category - HP
afece559-3fae-5520-b2f7-b24fbd5218bb | note | Responsibility - Nominated Authority
9c4afb6c-299f-5a23-b0e5-edf8083a03fc | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Blinding / Bedding Placement
7008d3cc-e950-5776-9512-61978dfb938e | note | Reference - IFC Drawings
fb81d507-1817-573e-95f3-55ec65e2abb5 | note | Acceptance Criteria - Approach Slab
bf8ceddd-02e9-59b9-ac4d-1d80d16bab0c | note | ○ 50mm thick compacted sand
d8248b77-016c-5b99-beb1-9edcd246eefc | note | ○ 2 layers of 300 microns thick polyethylene sheeting placed full extent of approach slab
47a20277-b9cb-5f83-9c87-905bd697a125 | note | Friction Slab
ff726133-3714-5ea0-994f-25d1ac174129 | note | ○ 50mm thick concrete blinding N20
8c1b8889-27ad-5b69-8227-269cebc5338b | note | Method - Measure, Visual
d92d04e2-b528-5fc0-a5ef-b81eabe30886 | note | Frequency - Each element
dc1cf6d0-4425-5862-b48b-1b32c8a25f4b | note | Category - IP
f7e16453-5438-5440-b1ac-8e934e6f3268 | note | Responsibility - Surveyor, SE/PE
053bea5c-e02b-56b2-8c78-4919497ad8ac | note | Verifying Documents - This ITP Signed-off
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
ef9ee0fb-b8ea-5a31-822a-3847737e58f2 | note | Reference - IFC Drawings 614.04, 614.05, 614.06
dad044e6-0995-5a43-8459-530e628e7586 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
066be57c-9f95-5188-8106-ef0a83124934 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
c6d6830b-a01a-5084-a13a-f38a6261c913 | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
681af087-e4bd-556d-9546-0a31fe2159c3 | note | Method - Document Review, Visual, Measure
629df978-27ff-5c1c-b3c4-4a6bd1d2ce09 | note | Frequency - Each type of element
05cd5e61-4919-5eae-9977-89b4cfa50eca | note | Category - IP
9fd6912c-9d67-5878-bec2-7d0185a69ed9 | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
8b1078d6-bf30-5104-9d8d-3b54129ab32e | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
83f96891-930c-502d-ae34-d203ac700357 | note | Reference - 614.08
132b6b97-4646-5cf1-8319-d647e746600f | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
9ceda020-80db-58f1-964f-095fc9a6c6b5 | note | ○ Walls with heights greater than 2.0 metres
2cd03b01-f030-5868-8471-7a69b2a48a85 | note | ○ Any member for which self-compacting concrete is proposed.
08272057-9bb4-519d-be07-1dd16de6b9c7 | note | Attach: Attachment A
092101ff-5e39-5e8e-a050-d87e393ae628 | note | Attach: Attachment B
a11b93d7-89f5-56ff-93e0-c3a63d69230e | note | Method - Document Review, Visual, Measure
a5e10e37-221f-5426-b146-c317c483abbe | note | Frequency - Each element (where greater than 2m)
05da8752-7eeb-5d04-94c0-9519a624e631 | note | Category - HP
85f91319-256c-553c-8090-4742cbb0b7d1 | note | Responsibility - Temporary Works Designer, Proof Engineer
e459b3a5-b818-5060-8a8e-8d43b01a4be8 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
00a017b6-05dd-542e-a24a-b172d6fa47df | note | Reference - 614.08
b2743fd1-43b0-51de-9703-c9f594bfbc33 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
b0316e96-f977-5c25-bda1-027e95926bb7 | note | ○ Walls with heights less than 2.0 metres
dc3a0a44-6fa3-589e-ab12-c94398b8b781 | note | Attach: Attachment C
a8108e6b-a034-5f8e-9f2f-3375694395d7 | note | Method - Document Review, Visual, Measure
807d0e9c-32e1-596d-9c84-9a508fec1f1c | note | Frequency - Each element (where 2m or less)
8bd96005-01fb-59bd-8b24-a9cbb6b4a690 | note | Category - HP
71c5a50f-756b-5a26-96bb-85598cc8c488 | note | Responsibility - Temporary Works Designer, Proof Engineer
d9874415-dc53-510b-8b36-73eb5d02b543 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Pre-pour Survey
3b352f82-d22c-5dcf-aca7-51e7830bc4e8 | note | Reference - 610.47 (a) Table 610.472
4f772a0d-23fd-5bb3-92b7-43d98a0a7249 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
fd70affd-3447-5897-8948-5f96a6171b9d | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
57d279ad-130f-5fb8-981e-dd7111349649 | note | Method - Measure, Visual
80e21497-c45d-5068-9628-bfbb19bc2de9 | note | Frequency - Each element
e97454c2-f453-5605-a6f0-2c75bb67cb13 | note | Category - HP*
f5c886f0-09af-5b3d-99e6-e00efc326131 | note | Responsibility - Surveyor, SE/PE/SPE
f347929f-0f0c-5479-8006-bd616ccc0dc5 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.5 - Reinforcement Placement
eb3308be-fcea-5d18-91be-d1b28818b944 | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 611.17
d28d77b2-9435-5915-b42a-35f4a7ff21ca | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
e8494924-253e-59f2-ad07-87e5ad334b4c | note | ○ Projecting reinforcement is the correct length and location.
bab7395d-7cd2-58c3-9581-fed2bc03bf23 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
58d9b7d1-523f-59f5-a4a1-20d29047e42f | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
4f3aa64e-411a-5ce7-a584-63ede4bda0cc | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
d9a8ed2a-ba66-549c-a70f-73ec5cde40f1 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
71ef357c-ab6e-5ded-89f1-a42bd3bd6341 | note | ○ Where contact between dissimilar metals embedded in concrete is unavoidable, the two different metals shall be electrically isolated to prevent galvanic or bimetallic corrosion.
7c00eed6-ef90-5450-9072-7537e5afd37a | note | ○ Electrical isolation may be effected by using PVC conduit sleeves, suitable soft plastic wrapping or tapes or by other approved means.
3630ba29-36af-5945-8d8b-5810647142aa | note | Method - Measure, Visual
f2a8a7fc-794b-5d92-b53e-734a618fd97d | note | Frequency - Each element
b99a02cf-d720-5665-b5d5-6a72bdbecfc4 | note | Category - HP*
147bb2bc-04ca-5086-85cf-588d61bbb3e6 | note | Responsibility - Foreman, SE/PE/SPE
f586ddd3-9726-5301-a741-47b41e17e2aa | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.6 - Cast-in Items
021a07af-7d5c-5342-9537-a645b1970943 | note | Reference - IFC Drawings 610.47 (a) Table 610.472 AS3810.1 Table 3.3.6.2
54c6137e-2bc5-553f-8fde-08a86ea9fdff | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
2c456f04-ae42-5280-940e-3bc06e368253 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
da5275db-6755-5ad2-b591-2e7c1bb5ed98 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
5e18f1d3-cef6-5635-b22a-9aa8e3575299 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
80073809-a288-5679-be1e-41749e92aed2 | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
acc29879-dcf3-5ecf-8f35-f653183ee689 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
de8bed1e-313f-5cc6-bcff-f9771d933ea2 | note | ii. Running dimensions of a group of the above = ±6mm
2e96a9f8-4199-52c6-8007-782f9ed0b322 | note | iii. Ducts and conduit location = ±12mm
3eaef80b-3ef5-50bc-9dd9-e8bd49d8db78 | note | iv. Diameter of ducts and conduits = ±3mm
cafe29b1-7eca-5eb9-88cf-91de2a5ed602 | note | ○ Surveyor to check and confirm correct set-up and correct heights of M20 4.6/S Cast-in Bolts 300 long for screen posts.
fcbbc94b-54a3-5eb6-b5c8-666971bffb80 | note | Method - Measure, Visual
2c674eec-16c1-58aa-bf4f-e5aafdc37a54 | note | Frequency - Where applicable, each element
3c1fd1fd-a2fc-5598-a4c5-7bc58c799145 | note | Category - HP*
2bd16df9-40dc-5560-9a1e-6a33d7bddf69 | note | Responsibility - Surveyor, Foreman, SE/PE/SPE
08d5b301-d529-589f-bb35-f1a43fe4d6db | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.7 - Thermal Differential Monitoring
3efd43a2-1777-5d66-b0d1-b6bc73d9c620 | note | Reference - 610.22
bf39c802-952d-53a1-8eac-b6c9b4759c7e | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
dfd23f0d-f938-5421-9b5c-01b8f55f3fcb | note | Only applicable if the element has:
6688e44a-88c3-516c-a35b-55fdd7a9041f | note | i. the smallest sectional dimension exceeding 500mm
933a2b4c-4a50-5a7b-aea4-06db6b7a852e | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
b641f122-15ba-5d90-aff7-0b28837f7de0 | note | Method - Measure
2699e4dc-a065-59c1-9abf-0c12f003e84c | note | Frequency - Where applicable, each element
d841190a-b89f-5d8d-a585-b940260c9263 | note | Category - IP
b33dc05d-a12f-575e-b2fa-5d37c1160447 | note | Responsibility - Foreman, SE/PE/SPE
c06b2554-b9db-53a8-83ed-c2fc7233f11d | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.8 - Pre-pour Inspection
ac4b079c-4c09-5e30-82a9-115bfab6a952 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
6fe0548d-a300-590a-a9fe-d3414eff253c | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
c646f2ca-2915-5312-9c03-3866465ae3d9 | note | ○ All foreign material has been completely removed from the forms
43ffefc9-5709-503c-a14e-1804a5a59872 | note | ATTACH: Pre-Pour Checklist
889ada96-906a-5191-966a-299f8eab7b62 | note | Method - Measure, Visual
fd6221cb-7b31-5c72-b1bc-c11718f606a9 | note | Frequency - Each element
b6dc8582-9177-5dee-a3e6-06706759e561 | note | Category - HP
9827f5fc-3e4f-56e8-9f83-6efe9112916c | note | Responsibility - Nominated Authority
d24af711-ef34-58a7-9ebf-10083d0db708 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.9 - Weather Conditions & Evaporation Limits
051bc843-e788-5573-b2fd-977144e6ede3 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
9bd42ce5-f8d8-550c-a38d-60d6c802ba0c | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
b651f889-6ee0-5725-9c61-5934301cfecb | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
ca77b281-33ab-5e4e-a49c-cafeaae4aa9e | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
45211101-186e-5b61-9428-b772cf3ce591 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
53d96483-9821-5266-83d0-6c7025a11b0d | note | Attach: Concrete Pour Record.
92e0b4b1-dbc4-582f-87a3-3c6514c3a629 | note | Method - Measure, Visual
520227ab-2a10-52fd-a634-934f0d9bab4b | note | Frequency - Each element
3e2518ff-96f5-5bdd-9a37-947a939149d6 | note | Category - IP
186526c9-33dc-53b4-a898-040924a88aea | note | Responsibility - Foreman, SE/PE/SPE
892ae5f1-8257-5d9f-812f-c181d9f16078 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.10 - Concrete Testing - Sampling Frequency
d8853a38-31da-5bba-8838-ec85e948ee01 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
27a18ec9-9f6b-5477-8347-f59a235c55cb | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
251dd89b-2b48-54fb-9dba-936cc945b9ab | note | 0m³ to 10m³ = 1 sample
d71b9107-f04f-5a4e-9c0c-bf5abde3d004 | note | 10m³ to 25m³ = 2 samples
4b22fc4a-6c7d-5193-8e36-35f351e50669 | note | 25m³ to 50m³ = 3 samples
0d26968b-ed8f-5cd7-a35c-62ea9668be02 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
d5c3df38-6bbe-5b19-a33e-ea24db4ea585 | note | ○ For each additional 50m³ and additional sample shall be taken.
9153192b-3502-5c1d-8eba-c3ba89c7273c | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
29430a23-33c2-5200-8d04-f8bb35eb04df | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
7419361d-a7a0-5f38-98c6-d4f3619e65b0 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
845744c8-d2db-5c42-99f2-d33eb67dac47 | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
7756d8bf-78c8-5ea8-94a9-edbb40d0dc2e | note | Attach: Concrete Pour Record.
7b8d02b8-9dcc-5e09-b02f-38f7b85f1419 | note | Method - Test
278a8278-ac04-566f-b168-d16f7981a00e | note | Frequency - Each element
0c31b084-9f12-55f9-a46f-a39493a93825 | note | Category - SP
8324103d-6515-5a6a-89a9-846b83412c1e | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
86d29713-32c0-5fe0-9edd-3cb7bc3cd381 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.11 - Concrete Testing - Slump
2fce522d-78a0-5057-8939-5a4ab8c14201 | note | Reference - 610.16 (c)
7cea7c84-7589-560a-bbf0-0e8c8124b997 | note | Acceptance Criteria - Slump testing tolerances =
6d05eec4-9e3d-53bd-928f-e5e8c4aa0031 | note | ○ <60mm = ±10mm
daf20e55-2f0a-52f2-b300-c1c0d687e184 | note | ○ ≥60mm to ≤80mm = ±15mm
9b040df5-c476-5200-b4d9-45cc5f5a05b2 | note | ○ >80mm to ≤110mm = ±20mm
0db83af4-b41b-5301-b1ca-9cee80b1c253 | note | ○ >110mm to ≤150mm = ±30mm
7be3188e-7e46-5d46-8a94-a05e8f51845d | note | ○ >150mm = ±40mm
a4b29f8d-0fe1-5c69-82f9-57766203ff92 | note | Attach: Concrete Pour Record.
0e4485e5-5244-5553-9824-3075d30f55e7 | note | Method - Test
84c66f07-745c-50ae-91ea-5e0488e0e533 | note | Frequency - Each sample of Standard or Superplasticised Concrete
1847c932-3bf5-5a79-ba6b-6d6245c85e00 | note | Category - IP
16b84e86-fb22-562f-bb4e-8bab983dce3d | note | Responsibility - Concrete Tester
87a4e813-de5a-500a-85dd-bf515633f3aa | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
76d9d422-78f5-5615-9a1c-e8fc110638d0 | note | Reference - 610.13 (b)
4198d267-8a80-5c1c-bd2f-8de52ddd1f87 | note | Acceptance Criteria - Spread range = 550mm to 750mm
46e30a0f-ccb0-5cbe-953a-f09e32be999e | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
c6b02cbc-7e42-56bd-8262-baf341297ae9 | note | ○ Passability = ≤10mm (aggregate height differential)
007b42b3-eea2-5065-acd2-fb0dc456bf9d | note | Attach: Concrete Pour Record.
b26233d1-f5d1-568f-941f-71e9cc540c97 | note | Method - Test
a947d5be-e963-596a-b5d6-6fee22740f3b | note | Frequency - Each sample of Self-compacting Concrete
f81415da-b5bc-56ea-902c-345087d41e49 | note | Category - IP
0922160a-8425-548c-9409-a01d92fbf89b | note | Responsibility - Concrete Tester
c1632be4-3773-55c2-a4f3-186d7d82e73f | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
044d0fbf-81bc-501c-90f2-0eee7ac3740f | note | Reference - Site Sampling & Testing Procedure
0968e1b6-e72f-5661-b4e4-49f093d538c6 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
d3ae7ca8-5e20-54a0-aab0-0e13e5efcb05 | note | Attach: Concrete Pour Record.
1f61b607-7a7d-5590-885f-6645abf241b3 | note | Method - Test
557f69a1-70fd-53f1-8a11-8370f4ca61ea | note | Frequency - Each sample
21610138-8fcd-51e5-bfce-44de2e3ebfc2 | note | Category - IP
09e416d7-337c-51e0-bccf-599b3646fb29 | note | Responsibility - Concrete Tester
e1989744-0719-56dd-8aea-4267279917fc | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.14 - Supply & Discharge Rates
ca5e4c76-0ae2-5197-8d87-b7cfdc99fe1f | note | Reference - 610.13 (a) & (f)
6ef59ad0-7a67-5adc-90eb-09702a7ce4c5 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
65a01114-db52-5a9d-8448-b44d5d439c9d | note | ○ No water is to be added once discharge commences.
f838efc8-ac63-5b3b-be32-aca86f00b1ba | note | ○ Maximum time between batching trucks is 25 minutes.
90d49fd7-83c9-57f1-a05b-29623129ea22 | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
077b0fe6-a0fc-572c-87ad-e0afab368f87 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
736273a6-44b7-5188-867e-4cf8d89d40d2 | note | Attach: Concrete Pour Record.
f42d4684-8307-5cf7-ba51-1e1aed751119 | note | Method - Measure, Visual
8dad87a4-e570-502f-864a-e15ca5865569 | note | Frequency - Each load
3fa3ccbf-907f-565b-bf87-0d1f3dfa69f3 | note | Category - IP
2e24fa4d-c3a5-52ab-8f2f-0ad0617db42e | note | Responsibility - Foreman, SE/PE/SPE
03bc3527-39b8-53fb-9f60-404a3343f9c3 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.15 - Placement & Compaction
10cd1da6-5786-579c-bebe-4fdf2b9bcef5 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
b0b966c8-73e4-50c8-8797-ca9cd1d85a02 | note | Acceptance Criteria - All concrete batches are traceable.
e60fb94f-d160-58bf-bd6e-0bd660d00d96 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
900d3244-942c-5137-95c1-c99e49ee847c | note | ○ Concrete is not dropped freely from a height exceeding 2m.
ec3f73d5-5d8b-5b90-b612-0a2f83580c64 | note | ○ Concrete is not moved horizontally by use of vibrators.
d2aa795d-044a-5af9-9fd3-e79c313b6795 | note | ○ Adequate compaction is ensured
c3814e6c-288d-57c4-889c-bfda5ce7578e | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
2b74717c-ffbe-5bde-a007-575fd59dbb56 | note | ○ Concrete layers are not more than 350mm
beb8a7b2-01ee-510b-b114-474c4980f590 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
50bb6b3d-1d60-56ed-b045-331d85a89d75 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
a556116b-0dfe-5050-a778-fcb97981a02f | note | Record: Required information on the Concrete Pour Record.
bcaf8fd8-6849-54df-8b06-ec0e5e618101 | note | Attach: Concrete Pour Record
d8b66051-f39e-5162-98db-06000459a886 | note | Attach: Concrete Dockets
b8b0fc3b-955d-5dfa-8d0a-479ff8fce201 | note | Method - Visual
c1a82e13-6b97-5074-a024-972168ae251f | note | Frequency - Each load
bf0525ab-b8ce-5356-8683-418cb4368408 | note | Category - SP
50c5cdc9-eabf-5f03-9746-9185316e3c42 | note | Responsibility - Foreman, SE/PE/SPE
b15d4e38-bdb4-5645-9022-b4738968bba7 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.16 - Surface Finishes
689e3e6b-2d51-5dec-bcf1-0042f93101ef | note | Reference - IFC Drawings 610.31, 610.20
aeb507f0-3157-581c-8930-0d25af268b31 | note | Acceptance Criteria - Surface finish as per IFC drawings.
393c42ad-b6dc-5290-aa30-485c469156de | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
feb2990a-bbe7-5a27-9b4b-fc4f5cc1fcd1 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
a9a8ecb0-ec91-5b0e-9be3-062ff46b9284 | note | Method - Visual
0e4905b9-c67a-5145-bc02-293c230fb5cf | note | Frequency - Each element
21bed057-d738-5cf6-b5e0-b4104584679e | note | Category - IP
d97f3247-4db0-558d-8fa6-50c17da39fd5 | note | Responsibility - Foreman, SE/PE/SPE
88dc017b-e53f-536f-9ea6-dcb99fff1715 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.17 - Curing-Top Surface
57c2ef1c-89f4-5874-8439-2b8afacb1287 | note | Reference - IFC Drawings
cc8d8d58-2fe9-57f9-b2de-e7ba89f82468 | note | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
f93b33b0-50fa-56f7-8c08-9af1d509ce12 | note | Method - Visual
b763361d-0457-5f0f-8e52-7588bb52afd8 | note | Frequency - Each element
818e85de-7910-5467-a2c0-54ddcc97738e | note | Category - IP
dc925eff-9fdc-5d1d-917b-4bcb6ae01ec9 | note | Responsibility - Foreman, SE/PE/SPE
8628bb24-cab1-5fed-9292-8db103a7efb1 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 5.18 - Curing after formwork removal
d2a1e044-931d-5fe0-afb1-0194b7a5e168 | note | Reference - IFC Drawings
e983d866-294b-5e1a-a1c2-120b45184611 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
fba66924-5198-56e0-b317-ca559f792da0 | note | Method - Visual
9c839d82-2159-52e8-aecb-5df789e5a452 | note | Frequency - Each element
850547d6-a4ff-589e-a821-0caabdb91287 | note | Category - IP
23cd1b84-7f36-56b6-a736-eaa8f6a10604 | note | Responsibility - SE
a918becd-95e5-5bc7-ae0a-cd64eb65bb3f | note | Verifying Documents - This ITP Signed-off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Thermal Differential Monitoring
b12edee4-cfad-53c5-88b2-b5d1d1f34bc3 | note | Reference - 610.22
7b214a3a-dc09-5906-b100-298d176f64b7 | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
f97ad181-52f0-5fa7-a3da-f4bc1bc9f85a | note | Only applicable if the element has:
1e449708-8d6d-525f-9a8d-76014df42c14 | note | i. the smallest sectional dimension exceeding 500mm
4104d964-8ba9-5465-8516-11afdf89f712 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
ff349965-a65a-56d0-9287-b45551f1bb33 | note | Attach: Thermal Monitoring Report
985e7f15-2a62-58a9-9979-c076e9ab73c7 | note | Method - Document Review
9c1a670c-d0eb-5c7a-9c8c-7f4b2f2eee3e | note | Frequency - Where applicable, each element
3828d58c-0669-5d8b-b730-d9364243756a | note | Category - IP
e28e48c2-f872-5080-b8ab-86e67430586b | note | Responsibility - Foreman, SE/PE/SPE
33abdc9b-fed9-5f4a-84c3-53e1aee2f49e | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
77f3bc6a-58d6-5eba-b1f8-1c8dca3044eb | note | Reference - IFC Drawings
9f19b85c-0dc2-5907-b335-a98aedcad00a | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
4c95308a-8a2b-52fe-bfe1-2d764fc3c280 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
cdb7796f-43ff-57ce-ac1e-335f06e8502a | note | Attach: Concrete Test Results or Maturity Test Results
1029215e-d4ec-52ed-80b0-f3f3f3760d3a | note | Method - Document Review
29caf9ad-5f67-57e1-bf16-41b488e46c31 | note | Frequency - Where applicable, each element
212306a2-a68d-56ce-beac-fe173c0e5854 | note | Category - IP
c7d69a84-c107-53c4-8132-0b2eb68a575d | note | Responsibility - Foreman, SE/PE/SPE
feff2c84-b833-5c83-bb00-8cdb78369129 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.3 - Surface Inspection - Cracks
ee57b075-2f40-5a50-bf40-0c5559736dd8 | note | Reference - 610.24
92fac2ee-f566-512a-81a9-d3b7c296db6d | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
aff9fc41-e44a-57af-9ac5-d0c3efb073ca | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
e83f304f-a526-55c4-96b0-0ce7121ecad3 | note | Method - Visual, Measure
8bc379e1-44c5-518e-be27-ef9b603766e8 | note | Frequency - Each element
bcf9f5e9-cc1e-526e-861f-55c8d38dfa24 | note | Category - IP
5a013281-2e44-59f3-b7e5-00b7f8eb70b2 | note | Responsibility - SE/PE/SPE
6beafa44-887e-5400-b24a-5ae546891818 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.4 - Surface Inspection - Surface Finish
23407926-88d8-5fe5-9121-2f8a3edf2686 | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
0debfa8a-1679-56e3-9502-a7a7fbfdce41 | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
5a0fbfb1-7217-5c96-b1bd-7a697dc8259d | note | ○ All deck and approach slab surfaces shall have a broomed finish in accordance with clause 610.31(n).
f78212bc-920b-5ebd-81a2-169c125311be | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
e3b57748-6478-5b96-b45d-8fa40b1e8978 | note | Method - Visual
61b1fb43-86cf-5ef2-8e56-7c1a292ecdeb | note | Frequency - Each element
440af673-7760-5c26-b251-ae42396e97d0 | note | Category - IP
65c835bc-836c-5c92-a0ae-8d7b618bb2ad | note | Responsibility - SE/PE/SPE
dfe00482-e70a-56f5-bdf7-b7d423a0c426 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.5 - Measurement of Concrete Cover
4a042eb4-45be-503f-8f15-8a1619b82da5 | note | Reference - 610.34
2f8c999a-ed45-59ab-bf64-5a888734e541 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
990f4f99-6745-555f-8b6f-35eb92854e48 | note | ○ Minimum 10 no. measurements recorded in each area.
daef3a18-26de-53d3-b22c-52f467e1ca74 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
95792bcc-bb8f-585b-8e7a-94425f329343 | note | Attach: Covermeter Check Record
3fd73a98-98b7-5622-b29d-847afb844a43 | note | Method - Measure
227bcb09-2306-5b28-a0cb-b7f2d95b057f | note | Frequency - Each element
10b972fd-1faf-5dcd-ab97-9a88cd26bbe4 | note | Category - IP
9a26ec90-a733-5170-b250-556de454da89 | note | Responsibility - SE/PE/SPE
f40fb178-7d4b-5d31-b4c4-220215f54839 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
58d0a8e3-7854-5389-9056-04b920cc3aa6 | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35, 610.36
c7894627-27f7-5311-b109-85110dc25204 | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
a990b458-441d-5a19-bbf6-af925f61dbaa | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
396bf804-3d31-5a2b-b8f1-c4bb63a57a19 | note | ○ Bridge decks, deck overlays and approach slabs shall not be loaded or opened to traffic until the concrete is at least 4 days (96 hours) old and not before a minimum compressive strength of 32 MPa after casting has been achieved.
9ccb23ae-6e53-5d34-8c79-8f4eabb748d2 | note | ○ Additional test cylinders shall be sampled and tested as required in order to demonstrate when the required strength has been achieved
a9c83323-464b-515b-a65b-598672f674a9 | note | Attach: Concrete Test Results or Maturity Test Results
37a714e4-a736-5144-a07d-88c0c8510916 | note | Method - Document Review
4e38bf91-6331-523b-80b2-ddd471ea7d62 | note | Frequency - Where applicable, each substructure element
41e723c2-1783-5a96-b024-f6fe7818d9d2 | note | Category - HP
d4d51714-4abe-5a0e-9b40-2afd349539e6 | note | Responsibility - Foreman, SE/PE/SPE
65f48f36-811f-5412-991a-0c5d4661c8b9 | note | Verifying Documents - This ITP Signed-off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.7 - Compressive Strength Test Results
9ab76abe-1728-5d50-b47e-2837c71cd062 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
1ec45c8a-3e1f-5e51-a7b4-c14fdf5170dd | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
cb683eea-6a67-5666-a95c-98cb4ff8ea62 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
5b1f5506-b603-5eff-bd4f-4fe99ea8f5ef | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
438a950e-8ba8-5d80-90eb-f1a42dab4ddd | note | Attach: Compressive Strength Test Results
8190bf46-0881-5cc0-888f-c9d32370df8b | note | Method - Document Review
8c858741-8c86-56b2-99b4-d659f9aa0ec2 | note | Frequency - Each cylinder
71c5ee1b-6dfd-5e84-a8cd-7040422f9678 | note | Category - IP
c662843f-077e-5d47-b1e9-f5d38cba97df | note | Responsibility - SE/PE/SPE
34f58c30-3ee9-5c48-9567-08d1e465ac68 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.8 - As-built Survey
a876a845-b9cc-58e6-a513-2181f886950d | note | Reference - IFC Drawings 610.47 Table 610.472
f211d369-9412-5059-a416-fc68dfde2499 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
a7ad7311-3bef-5ba5-bae1-8eb117df67f6 | note | Attach: Survey As-builts / Survey Report
12e7ab51-4a1a-59a4-9ae0-8aab6ec33433 | note | Method - Document Review
bcf3b456-ce30-533b-9918-6f022e5d58aa | note | Frequency - Each element
073b9390-9ea2-5854-b672-0a64d8d0d8d3 | note | Category - IP
1ac6388d-e412-52d0-bcd9-69cf45da587e | note | Responsibility - Surveyor, SE/PE/SPE
83b46e98-13a9-599f-ac1d-6fbe9fe3293d | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
a60958fb-9fcf-58df-8f3e-845e9021aa86 | note | Reference - MRPA Quality Management Plan
1a15e0e6-6fd5-595c-a3d7-9d059bb4e210 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
11a41c2d-1e77-5932-9015-1bba7a8c7a08 | note | Method - Document Review
37f58c37-d188-5043-b148-93f141ee084d | note | Frequency - Once, prior to closure of this lot / element / Work area
c98f51c5-6f1a-5be5-82d2-a8996b40b483 | note | Category - HP*
f71ce2a4-604f-586d-805b-fd40cca07f9d | note | Responsibility - SE/PE/SPE
98e8ba77-5246-533b-8c8f-224fd2b387b8 | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
eae9fce3-7bd5-56b1-96a4-932e2a8b43b7 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
519eedd3-835c-5ebd-9bae-fddf6f0cbbfb | textbox | Name:
b345d9aa-b209-5c9c-9b84-102d28e84897 | textbox | Position:
b7f87902-00ab-5bc2-989d-baa067055446 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-130-CIV-BRUNT-Guard Rail Supply and Installation Rev.0 | itp | ITP-130-CIV-BRUNT-Guard Rail Supply and Installation Rev.0 | b023b856-db97-4fc4-89e9-c78b579454fd
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
98d4e06a-670e-5c6d-b26c-34ad2f1a86d6 | note | Document Title: ITP-130-CIV-BRUNT-Guard Rail Supply and Installation
f66c67b9-160e-52aa-a41e-f986ace717a2 | note | ITP Description: Guard Rail Supply and Installation
37c1b432-253d-55af-9c75-0516418488cc | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
4409710b-9de0-58e1-80a1-998c874b93c2 | note | Discipline (e.g. CIV/STR/RAIL): CIV
36c0e975-fe27-5910-83b3-bbe35979e2f5 | note | Revision Number: 0
424b6655-b52c-5b4c-be90-d12873c288a5 | note | Revision Date: 25/01/2024
4cc01c18-db92-5956-bbcd-263d65ed9ca8 | note | ITP created by: Yasna Naicker
a0b5030c-dd32-5878-b7e3-0b2ce4d0c7f2 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
c7bcd9d2-149b-5584-b5b0-77841eb5ff9e | note | Reference - VicRoads Section 708 July 2023
| checkpoint | 1.2 - Non Dependent
b90a1f3a-1ca2-50ba-a442-a638b61b5c50 | note | Reference - VicRoads Section 703 Aug 2021
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Accepted Products and material confirmation
bf2892a8-3774-5a95-889e-1ac1ed73fb8a | note | Reference - VicRoads Spec. Cl.708.04
0c9954a0-8b8e-5bfa-87f8-25b49fafc5a8 | note | Acceptance Criteria - Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
12519315-d0d1-51b8-adac-dbcd2b01303f | note | ○ Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
9ee482a1-99a6-51bc-8170-c40ebbfc992c | note | Attach: TeamBinder HP Reference No.
3d616221-bc0a-5eb1-b145-aef1562bd973 | note | Method - Document Review
9e3c6569-21da-5c07-a025-8312c4d055a2 | note | Frequency - Each member material component
b9db6efa-6729-590b-9b22-0e4f4c6f517a | note | Category - HP
e9838fdd-eca9-5f1f-80bc-c1c5c3029c92 | note | Responsibility - Nominated Authority
4fc59ff0-1990-5f16-a534-ef0c94ec3e22 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Obtain and submit Material Test Certificate of Compliance for the barrier systems
f0607bd0-2784-5334-9ff7-ee2f84bc0dc7 | note | Reference - VicRoads Spec. Cl.708.05(b & c) and Cl.708.10 AS/NZS 1594, AS1627, AS 4680 ISO/IEC 17025 a
313d037c-cc25-5c7f-af5a-7414aca9a5eb | note | Acceptance Criteria - The properties of all steel for the Works shall be evidenced by test certificates
663995c9-9c91-5ed1-a030-c42b77997ea2 | note | ○ Laboratories that perform tests required by this Section shall meet the requirements of AS ISO/IEC 17025
019f3499-5934-50ef-a87c-36384786476b | note | ○ W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350.
919a965b-df19-596f-ac52-acce64a0dcb0 | note | ○ Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
7ec1bc8e-523b-5e56-b0c0-a95f15b9af33 | note | Attach: TeamBinder HP Reference No.
8f92ae1f-452a-56ae-8998-ef6b7c27a92a | note | Method - Document Review
0dc7dfd5-a692-57d7-a5ef-104fe5bcf09d | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
0605313d-b56a-5c28-b795-5e1b29d705f4 | note | Category - HP
2df298ef-8bf5-5efe-aa00-21f3ba8655ef | note | Responsibility - Nominated Authority
662d3dfe-5e33-5966-b700-7ba1a4835b08 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - CERTIFICATE OF COMPLIANCE
ff4ab591-9be9-5cb8-9241-22cc891fc6ec | note | Reference - VicRoads Spec. Cl.708.10
e1d0d5b2-b2d4-5c44-92f3-7e034aa14092 | note | Acceptance Criteria - July 2023 individuals which install, repair, and maintain road safety barriers and terminals, and are accredited under the Austroads Safety Hardware Training and Accreditation Scheme (ASHTAS). July 2024 all barrier and terminal installations, maintenance and repairs must be done by an Austroads Safety Hardware Training and Accreditation Scheme (ASHTAS) accredited individual. Individuals shall be accredited under the ASHTAS and for the product which is being installed, repaired or maintained.
c0e03c51-7e31-5f23-808f-d7afdcc563fa | note | Attach: TeamBinder HP Reference No.
bac5e9a6-7280-555e-bdd8-7521cb8d10f7 | note | Method - Document Review
d1969103-e9d3-58d7-bb55-5ea39f0dd67f | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
e71cf6ac-2e1c-5a04-8275-986eb49752dd | note | Category - HP
c725da1b-aad0-5eef-b6f3-857dc3ae87a1 | note | Responsibility - Nominated Authority
79e6d2a9-920f-5175-8ec8-060b5145bd58 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Verification of Protective treament/ galvanisation records
5cbdc887-9191-50f5-901a-28471d7a709f | note | Reference - VicRoads Spec. Cl.708.05(d)
05a05c3a-2a71-5d47-832e-f5f4108f2b28 | note | Acceptance Criteria - Unless stated otherwise in the manufacturer’s recommendations, the surfaces of all ferrous metal components including posts, blocks, beam elements, anchor plates, connectors and end treatment pieces must, after fabrication, be treated in accordance with the requirements of AS 16–7 Parts 1 and 4, and finished by hot-dipped galvanising in accordance with AS/NZS 4680.All galvanised coatings shall be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions.
49efba0c-537a-5774-9bcb-49b2a7b95e99 | note | ○ Hot-dipped galvanised coating on bolts, nuts and washers shall comply with AS 1214.
6272d423-6a13-5474-a45c-5b4adb7ca1f9 | note | ○ Where the galvanising on guard rail or associated fittings has been damaged, the coating shall be repaired by regalvanising or by painting with a minimum of two coats of a zinc rich inorganic paint in accordance with AS/NZS 3750.9 and one coat of aluminium paint.
89903905-b3d7-538d-8d70-f209d6919636 | note | Attach: TeamBinder HP Reference No.
c939aa0c-b906-5313-9c2b-7deb3120e902 | note | Method - Document Review
aee70f03-16fe-5fcb-8e1a-cb01f7ce3b8f | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
8ae20482-fad9-55af-b98f-9fe8d0e073cd | note | Category - HP
bd5dcc1e-083c-5864-bcab-bad54bb66423 | note | Responsibility - Nominated Authority
3e6cf833-e183-585f-ab20-e8c5abdddb3a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Concrete mix design
96bc9548-b8f1-502c-bb7b-dd6a200ca81f | note | Reference - VicRoads Spec. Cl.703, Cl.708.05(g) AS1379
e5b4ef63-7381-5fbb-ad11-6955154f3904 | note | Acceptance Criteria - Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
83d0cce7-8e9b-5ae5-a19a-b0aaaffe06be | note | (i) Portland cement-based concrete, N20 strength grade, or
e3fb0cb9-a81c-5c9c-933d-997924d7681e | note | (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
7b653f0f-1610-5bd6-9777-15b48425308b | note | The use of chemical admixtures shall comply with the requirements of Section 703.
c6043fc8-bb86-5e7a-a33e-0b50ebdf0fad | note | Attach: TeamBinder HP Reference No.
3ebe0cc3-18c9-5619-95f1-e33cc8ef4a59 | note | Method - Document Review
cab7a863-e097-5f22-a807-5e21ac5ad8be | note | Frequency - Min 14 days prior to commencing, 1 per 1000m of material
7a019753-7a18-57a4-9d69-fdb4495364e8 | note | Category - HP
05b8b893-3d76-51bf-b933-b26934c2d317 | note | Responsibility - Nominated Authority
ddc4076f-36c2-5084-962a-5a10f6a1282a | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Identification of guard fence components
4e893f15-f664-5312-965e-946bcd88c757 | note | Reference - VicRoads Spec. Cl.708.05 (a)
85aedd92-9e33-5087-9b47-110f72c0bb32 | note | Acceptance Criteria - Mark on any steel w-beams, posts at both ends and all plastic components of proprietary end treatments unobtrusively and permanently in text not more than 20 mm high, the following information:
5904c981-b90f-5cee-8c2e-db445fa945cd | note | (i) name of the manufacturer
68449604-6d11-5cda-8bfb-2123922cb547 | note | (ii) batch number, or date of manufacture
2c471a93-f673-584d-8eb7-f2e3f99fb565 | note | (iii) strength grade and base metal thickness of the steel w-beams.
b698632d-8f9f-532a-a465-17cdca831ab8 | note | Method - Visual
bca3e3c4-45dd-5616-b42c-01136a2b0095 | note | Frequency - Each member material component
fe9e6640-9560-53cb-927c-b109fa91932e | note | Category - IP
21714f45-d9f2-5a64-95ff-04e6e1921ec5 | note | Responsibility - SE/PE/SPE
1f01a149-4220-561f-8e49-0ac5666ee4b7 | note | Verifying Documents - This ITP Signed Off
| section | 3. Preliminaries - Documents & Procedures
| checkpoint | 3.1 - Subcontractor Installation Procedure and Inspection & Test Plan (where applicable)
a1c89c9b-cd3b-5ebd-b2d1-13d17319098f | note | Reference - IFC Drawings
750e6010-fcc6-5098-bf2b-41bc4b8e7005 | note | Acceptance Criteria - Subcontractor Installation Procedure and ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
7bb3a011-ab5d-5617-a54b-4015a42469f6 | note | Attach: Approved Subcontractor Work Procedure and ITP
a2273f65-a151-5387-9845-3345ad7f5a54 | note | Method - Document Review
5bcb3976-358b-57bf-8f39-42c4a167f357 | note | Frequency - Each Lot
e672cf7b-5bab-5f13-be59-a04c9d541bce | note | Category - HP
b79d346c-0a22-5e4f-972c-03f9eec151ae | note | Responsibility - Nominated Authority
de41164f-5084-5072-9ba6-45a0168a0097 | note | Verifying Documents - ConQa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Survey Set-out
a28865a4-2d53-5804-922a-f18ef596f37f | note | Reference - IFC Drawings
a3014df1-3b7b-54cc-a2e8-eadea499e5b6 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table VR610.464 (February 2020) / 610.473
f82b60e1-77f8-526d-a073-3f0ff959089f | note | Attach: Survey As-builts / Survey Report
3e317dc8-87f2-5490-a1f9-e3b6de80569c | note | Method - Measure, Visual
07fa5d15-077d-5192-b30e-a5dc89f7eb66 | note | Frequency - Prior to Commencing Excavation
1cd1e4e7-c756-5a2b-b5c4-cb66b10e5328 | note | Category - HP*
50a67207-cc98-5d8e-9aae-f43af8c6b723 | note | Responsibility - Surveyor, SE/PE/SPE
ddb3b67e-78f1-5674-b6fa-a33b6fce3f4b | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Obtain approval of location and length
d2576937-0bcd-5052-bb10-c09503550df0 | note | Reference - VicRoads Spec. Cl.708.08 IFC Drawings
f133605f-c0ca-5ad0-b7e6-8596a6c9c3bd | note | Acceptance Criteria - The required location and length of all guard fence shall be confirmed with the Superintendent.
ea5a1c5e-1cab-56c5-b9c2-76a18a6ea6e2 | note | Attach: TeamBinder HP Reference No.
a8f613de-56b2-5e85-abd8-f4783163eb00 | note | Method - Measure, Visual
aaa8af31-c735-5899-b404-f972f299ebca | note | Frequency - Prior to Installation
eb293af2-eb3f-5637-ab63-bce9c37a3007 | note | Category - HP
347b9ba6-2b06-59da-902a-178c5158dccf | note | Responsibility - Nominated Authority
bc5a32df-f074-5b21-8d26-506bd14a5d5f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - W-beam barrier system where non standard post lengths are used
f13e1e0e-fbf7-513c-bfb2-96a9038130cf | note | Reference - VicRoads Spec. Cl.708.08 IFC Drawings
39bda0c6-a0d7-587c-a667-259605c7cf3f | note | Acceptance Criteria - Prior to installation of any w-beam barrier system where non-standard post lengths are required or shallow concrete foundations are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained.
73d3e8cd-c8e3-5565-a6d9-8e7c16787a96 | note | ○ Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a Department of Transport and Planning appropriately prequalified consultant.
d0139d11-09b7-5406-814e-92db84df14a6 | note | Attach: TeamBinder HP Reference No.
df3d5dbc-bba8-5a31-9a07-9acb577c4f4c | note | Method - Document Review
ae79084a-f0ec-59de-8b67-ca4de81e3daa | note | Frequency - Prior to Installation
e6898200-24bd-5ff9-90bb-1c4a192d6186 | note | Category - HP
99fbb47d-1ad9-572c-8959-db6bc4721eb4 | note | Responsibility - Nominated Authority
4f9c96ac-547f-50af-9dc9-168f01a873ea | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Install posts, rails and terminations
3232feb5-6cbd-5830-a5de-3162c46f0228 | note | Reference - IFC Drawings VicRoads Spec. Cl.708 .07(a & d ) IFC Drawings
2aaf17da-4026-5123-86e0-69b67112c5ea | note | Acceptance Criteria - Posts shall be installed to the depth, line and spacing shown on the drawings, and to the tolerances in clause 708.08(d).
3a78a3f9-f070-5230-b25a-6a5e9a6426a9 | note | Posts shall be installed by driving, provided there is no distortion or damage which may reduce their effectiveness. The installation must not cause any damage to the pavement beyond 100 mm from any part of any post
ea4591aa-5183-5bb4-bbed-7bbe2dd904c7 | note | If posts cannot be driven, then the posts shall be installed in holeswith a 75 mm minimum clearance from the back of the post to the face of the hole.
ee5bdbce-e8d1-50fd-923c-88e71bfa62ce | note | Post holes in rock shall be backfilled with granular material, that is firmly compacted in layers not exceeding 100 mm compacted thickness. Where posts are located in areas to be paved, the backfilling of the post holes shall be finished 50 mm below the underside of such paving and the remaining depth of the holes compacted with material similar to the surrounding material.
ca87a549-878f-5fde-ad3e-d88af646b2c7 | note | W-beam guard fence shall be erected to the following tolerances:
18626a6b-c1f7-546b-9ed2-88165713bf7c | note | (i) Variation from true plan position of posts ±20 mm
76e9b535-4e10-5c4d-ae8a-6e17b417c73c | note | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
62dcff58-a4a3-5a11-b969-75687d6683ff | note | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
2d12f042-fdfa-577f-a848-9f91f7f0c050 | note | (iv) Variation of posts from vertical (measured at top of the post) ±15 mm
468afd66-a0e6-54af-88c8-f4d3fc6b4ea2 | note | (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam)
a1b94ea6-638c-5f39-a71b-d9e1847bb726 | note | (vi) Dimension of holes -0 mm, +50 mm
a76b4dda-5c38-5d36-8fa2-55acbc5ae517 | note | (vii) Top of bolt head relative to w-beam -0 mm, +5 mm
3dfb760a-54c9-52d6-b452-85dee0c77589 | note | ○ After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
1ff5f3ce-e848-561f-9957-a9a80c50cd7d | note | ○ Guard fence shall be installed at the offsets shown on Standard Drawing SD 3502. The desirable level shall be adopted unless otherwise approved by the Superintendent. Posts shall be installed such that the back of post is not less than 500 mm from hinge point
71fc379a-5e81-5056-97ef-ff513db2a22d | note | Method - Measure, Visual
505caa59-9b53-5fb9-a2fa-a845d0b94be6 | note | Frequency - Each Lot
fd616ac6-58c1-5fd1-96de-e36535b27486 | note | Category - IP
654d93a3-36ca-5338-9f65-b0cc11175ada | note | Responsibility - SE/PE/SPE
48d6647d-c288-53c9-a3fc-71719d6c093b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Construct crushed rock base for maintenance strip
09770eba-be5c-5f54-b492-b1f844579ff7 | note | Reference - VicRoads Spec. Cl.708 .11, Cl.812
18b6b195-3632-527d-9100-c46e979df920 | note | Acceptance Criteria - All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock.
3dcb36d0-d665-5264-80e0-a09fa283e612 | note | Method - Measure, Visual
79a5cd3e-b676-5277-b04f-a461512ca721 | note | Frequency - Each Lot
b3b60b3e-750f-5965-b5e9-9618120869d5 | note | Category - IP
ced631fa-5b42-5ce5-9a79-77c506406d9f | note | Responsibility - SE/PE/SPE
3d91d9aa-9845-5d5f-9aa1-bef1b3ecacbc | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Construct concrete maintenance strip
54f55f65-9408-5047-bdec-c4afc159ebb9 | note | Reference - VicRoads Spec. Cl.708.12a, Cl.708.5g, Cl.703.11
4f30991c-1530-54e0-9e1d-627b2e06109a | note | Acceptance Criteria - The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road
a8eeaa89-37a5-53ed-8222-564b8c2e6513 | note | ○ The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
540b2b01-7e17-5f50-a3f6-9d7c87f53c41 | note | Method - Measure, Visual
1d55f66b-c215-5a76-b9f3-2907bab342f2 | note | Frequency - Each Lot
39b3a062-bbc6-5b6c-a7b2-11388897aa8e | note | Category - IP
eeab2f08-0e4f-5f7f-a811-6e7278cad5d4 | note | Responsibility - SE/PE/SPE
e3b5f28f-807e-5744-893e-09033ac1070e | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Delineators
0ac9b3c5-9137-5dab-bbbb-cadea3a3615a | note | Reference - VicRoads Spec. Cl.708.11, Cl.703.12
c6992a0d-7716-5ecc-95b0-aedc38557e45 | note | Acceptance Criteria - The Contractor shall supply and fasten delineators to the top of the w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2. These shall be installed in accordance with VicRoads Traffic Engineering Manual Volume 2.
1f2d403c-63ab-54e5-8a0f-bd96649b97c0 | note | Red delineators on the left side of one-way and two-way roadways;
9fae39a3-bc47-524a-875a-777c627b6000 | note | ○ white delineators on the right side of two-way roadways; and
f68fd2a0-0f16-55ed-8d2a-5b3b4b9ddc31 | note | ○ yellow delineators on the right side of one-way roadways.
d12017b2-73b6-53a6-8f2e-36c35feae0bf | note | – Delineators shall not be installed on guard fence when the barrier offset is greater than 4 m from the traffic lane. White guide posts with delineators shall be installed in accordance with VicRoads Traffic Engineering Manual Volume 2 Part 2.02 clause 4.2.4 – Guide Posts (TEM Vol 2 Part 2.02).
abf3e806-9ee9-59fb-87c2-c8e5e169368d | note | Method - Visual, Document Review
6276b19e-e34e-5449-83c9-7f53ce4fc33e | note | Frequency - Once, immediately following the installation and prior to any Work commencing on the members
eeed1b15-c3db-5cce-a55b-d079e372c806 | note | Category - IP
04dc5941-e545-543b-9daa-a5c4c0f5120d | note | Responsibility - SE/PE/SPE
e465f6ee-98fb-54ea-afee-b5c698b853ec | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Existing Sign & markings Reinstatement
8588456c-fd42-52b7-83e7-8c954325b65c | note | Reference - VicRoads Spec. Cl.708.17 IFC Drawings
e5b8bd67-f839-5bae-ac24-153962544d1c | note | Acceptance Criteria - The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
b82ef956-da39-5d61-828c-b79ce7af30af | note | Method - Document Review
24cbaf4c-026c-58c1-bfbc-87027446b263 | note | Frequency - Each element
a7681377-f151-5711-ab85-e0ac3942903a | note | Category - HP*
223727f8-a649-5ec8-aed0-d44f7f7232a4 | note | Responsibility - SE/PE/SPE
49ce5d4e-5441-537d-9e87-19ed3acdf161 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Compliance Audit of Safety Barrier System Installation
2e404918-48bd-5eed-b5a6-09c2de210c28 | note | Reference - VicRoads Spec. Cl.708.10
719f91d3-68fa-5ea3-b350-71de565c6bf2 | note | Acceptance Criteria - A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system.
f1ca3f69-87b1-5ca2-929b-22fc7d96ccf1 | note | ○ A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufactures installation Manual and specifiction for each end treatment installed.
2c1d1581-a5d6-5631-ace5-cb984bfe2b64 | note | ○ A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
7743d328-b69e-5538-aeb2-115d83f4d417 | note | Method - Visual, Document Review
52b2310b-7fd9-5741-a257-0a3421bbad6b | note | Frequency - Each bridge beam
97bbc19e-b05d-5bbb-b349-3eb183918ce2 | note | Category - HP
53f7caf8-4b64-5883-9274-1bcadf8eefaf | note | Responsibility - Nominated Authority
450568f5-b4eb-54e7-a97b-c97a8e60ec9f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Survey data captured for as-built purposes
1b4daef6-f4ee-532f-8f51-f7a14e475772 | note | Reference - IFC Drawings VicRoads Spec. Cl.708
5eebf9c2-d81f-532a-ac21-04bee85ea387 | note | Acceptance Criteria - As-built Drawings Tolerances as per VicRoads Specifications, Clause 708.
434bc67d-8dd0-55b1-88ea-bd761bd2c12b | note | Method - Visual, Document Review
82f62fc6-2667-5de5-89b4-b7e2223c76c1 | note | Frequency - Where applicable
19ac7ce8-4b9d-5493-805c-412258f6612a | note | Category - IP
75c01a87-2e84-5184-b4e4-2d223bb37360 | note | Responsibility - Surveyor, SE/PE/SPE
fb0a6ffc-c014-56a8-9ac6-56e11e48d77a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Non-conformance Report (NCR) Closure
14dd9c06-3a28-5b66-bdcd-4660d7dd50b1 | note | Reference - MRPA Quality Management Plan
b2f35b6c-001b-5a49-b9f7-91b103d06517 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
b49fcfc4-303a-5ef5-8acd-2dd0f83f2ccd | note | Method - Document Review
699a91a4-b04c-5930-a6de-1d0c992c99d9 | note | Frequency - Once, prior to closure of this lot / element / Work area
d01a5840-3ac8-50b1-ba95-0a31aec6476c | note | Category - HP*
fed58c1a-1f46-5279-8ad1-24a3e1d1cc5b | note | Responsibility - SE/PE/SPE
ca565b09-84f9-5ed6-a8e4-ae5d1fb63dee | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
76bd8ffd-68eb-5fbb-a9ee-13b04ce9a0b3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
e7908e78-2f9c-525c-99fc-53c4e4451a2e | textbox | Name:
da18fd99-6475-547b-93c2-63be6d5fc65f | textbox | Position:
b3274b00-4a33-52fa-b93d-b40a66b09cbf | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-131-STR-BRUNT-Waterproofing - Bridge Deck CJ Rev.0 | itp | ITP-131-STR-BRUNT-Waterproofing - Bridge Deck CJ Rev.0 | f16cff6b-fdd2-4f81-9354-001e22543688
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
e41e18fe-f2bd-5fa1-b6e0-83efeccd15e9 | note | Document Title: ITP-131-STR-BRUNT-Waterproofing - Bridge Deck CJ
5a1bef6a-3278-536f-bfc7-23d5ca649a17 | note | ITP Description: Waterproofing - Bridge Deck CJ
7c9382e4-e827-5980-895a-dd5e3645c4ec | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
daa158d5-2441-5ba7-a9a1-ce419e34bca0 | note | Discipline (e.g. CIV/STR/RAIL): STR
55fa0fc2-dce9-58e7-af10-0a210f3c010b | note | Revision Number: 0
1a34d74d-1176-561b-b602-4230f5e406ad | note | Revision Date: 24/01/2024
fd7a87a0-a036-54fb-a15e-6e37788d6078 | note | ITP created by: Yasna Naicker
75c43ed0-948e-50a8-b587-f68ebc1d892f | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
702e1bda-65bf-51e5-977c-78165afd6cf5 | note | Reference - VicRoads Section 660 January 2018
| checkpoint | 1.2 - Non Dependent
65313e7a-7f60-53a7-ae2c-a34f60fc7619 | note | Reference - VicRoads Section 691 November 2018
| checkpoint | 1.3 - Non Dependent
a1df8bc2-e8ae-5a30-866f-31f3cf4fe0c7 | note | Reference - AC-AR Installation Guide
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Waterproofing Membrane System Materials
bb85ffd2-fa8b-59f8-b34b-a411a7fd6a4e | note | Reference - VR 691.05, VR 691.07
f71cf182-da8b-5293-b311-f507f60c30d8 | note | Acceptance Criteria - Certificate from the manufacturer in the form of a guarantee confirming that the waterproofing system and materials comply with the requirements of this section, including a guaranteed in-service performance of not less than ten (10) years from the date of installation.
c8b921d8-7c6e-55c3-9d96-89b743592a7a | note | ○ Submit Certificate of Conformity, including all relevant test results shown in Table 691.071 and Table 691.072, verifying conformity of the supplied materials for every lot/batch delivered, to be submitted for review to the Nominated Authority.
b95cc4b4-03e6-5be2-a73e-eea083b93a77 | textbox | Enter: Teambinder Approval Number
0a91c379-218b-52f0-b803-846354df3415 | note | Method - Document Review
3119a3a8-aafb-5d4d-8379-85dc2dd0e3c6 | note | Frequency - Prior installation
5b9fd5c0-d3cc-558a-b0e4-ce2ce62ea467 | note | Category - HP
932e5136-8067-55a6-9f32-33718f386b38 | note | Responsibility - Nominated Authority
b70feb3a-daf9-599f-a551-257adcf48882 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Procedures
| checkpoint | 3.1 - Waterproofing System installation Procedures
318cfb9c-462a-5fdf-94e5-af3b9b751d36 | note | Reference - VR 691.04
7c0b0649-c4cb-52c4-b823-8a3af07356c2 | note | Acceptance Criteria - Details of proposed procedures and surface preparation in accordance with clause 691.08 to be submitted for review to the Nominated Authority.
39185afc-3062-592b-916e-327abcba6114 | note | ○ Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent.
886cf8b8-02b0-5bcb-bf08-c60548997c3f | textbox | Enter: Teambinder Approval Number
346af27a-11c1-5d04-aa03-edc7901a4e8a | note | Method - Document Review
ea44f83b-74a6-513e-9ad4-64979b2b94a9 | note | Frequency - Prior installation
bf9fdec3-280d-51ad-b1d9-6007e9e451a8 | note | Category - HP
d298cb7c-09ca-5301-b66a-9f1bed5b840c | note | Responsibility - Nominated Authority
d8cafe7f-b930-54af-9670-205365e6b493 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Material Handling and storage
530995f1-3fec-5b10-9699-b16d7bb3bca5 | note | Reference - VR 691.15
1ea0ce8d-7838-54b2-913d-77314536b085 | note | Acceptance Criteria - Where applicable the joint material including joint sealant shall match the drawings or be an equivalent product
780b6145-40c7-5dd9-afe0-d67676bb11fc | note | ○ All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers.
0bf9d706-be71-56b0-b43b-273b48669b55 | note | ○ The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming:
1c9a16c7-afb3-59bc-a08b-148e08556836 | note | (a) manufacturer’s name and address
2c84e2a6-6749-5418-b32f-adf16494c3b3 | note | (b) product reference
65b9594e-1515-5f8e-a09d-5d5f31708f21 | note | (c) batch number of identification
44a57d88-de16-59a3-b153-60efd69af407 | note | (d) quantity manufactured in the batch
6743013f-4082-5700-b7e4-60baa19d66fa | note | (e) date of manufacture.
e1525524-4393-5555-8d96-b703863251b3 | note | ○ All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients.
70ecef08-6367-5001-9057-1e7c00f3e620 | note | ○ Attach Delivery dockets/Proof of purchase
3aab2c6d-b68e-55cc-be0b-e91c01c72837 | note | Method - Document Review/Inspection
bbe31fd5-f2c3-5a85-b18d-d63229c04f8b | note | Frequency - When applicable
f26a3849-fd98-550a-a835-d6433b2d78cc | note | Category - IP
a52981f4-e10e-5805-bcaf-c9e3d638b413 | note | Responsibility - PE/SPE
51ac419e-3ad5-53db-91a3-43c1f8bf8dd7 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Surface Preparation
7bd64a1c-baa1-5fcd-b8a3-6f18714c2b1d | note | Reference - 691.08 (a) and (b)
61814358-c9e4-53a0-a524-4e31b74d6fc3 | note | Acceptance Criteria - The surface preparation shall be in accordance with the manufacturer’s recommendations for the waterproofing membrane system to be applied and as specified in this section.
c8cb82f3-b778-5084-9e73-3cfbebc638e5 | note | ○ Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles.
2cb376f3-ef4d-55d3-9514-9064e15e278f | note | Method - Visual Inspection
16b9d6c3-184c-51e1-9928-c55c721a8800 | note | Frequency - Before Primerbeing applied
dc8240fd-ce08-5788-8212-036f0b18e0cb | note | Category - IP
0878032f-80ce-575c-ab8b-8b4a3dc20fd3 | note | Responsibility - SE/PE
7c2d8a30-ddb4-5aad-881f-0ed8a9d173a4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Primer application
fbc107cd-ae9f-55c7-8691-b9c9cdad51e3 | note | Reference - 691.08 (c )
56fc84fa-024a-5ba0-8e27-36ce2f8fdb3e | note | Acceptance Criteria - Primers shall be applied by brush, mop, broom or spray in accordance with the manufacturer's recommendations.
7b562957-1b3f-5f10-8ac0-139b44006cfa | note | Method - Visual Inspection
cb93d40d-9b69-56c3-b262-c0e0b6383b4e | note | Frequency - When applicable
544724ce-4f11-58ab-994a-00b5f42487ff | note | Category - IP
ed9c03d3-56f4-5d8f-874d-47aefa71f38e | note | Responsibility - SE/PE
e0e7b7d8-42fd-5e1b-b629-9fcac5a3b74f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Environmental Conditions
7a3b62d1-563d-519f-a3d7-ebbb6128838b | note | Reference - 691.14
edcd21cf-f0a9-5d87-b8ba-67d8fc395d05 | note | Acceptance Criteria - Waterproofing systems shall not be applied under any of the following conditions:
9ac64c8d-29c3-5046-966d-dc1f3b883bc7 | note | (a) windy conditions where over spray and/or spatter may be generated
30807f3f-c8be-5478-8914-32aac552dcc5 | note | (b) when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane
b34d8054-252a-5c84-b0be-d1490f26573c | note | (c) when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer
31ccf750-8d2c-5ab5-b1d4-705728cbb1ac | note | (d) when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period
7cafb38f-ceaf-522a-b75a-db81c62226a1 | note | (e) when rain spatter contaminating the surface and adversely affecting the adhesion to the substrate
0bf958d7-46a4-5386-a619-b4569243e262 | note | (f) when the substrate surface is wet or damp,
4970e607-02ed-5bc1-b1b1-d08b580e4a77 | note | (g) the surface temperature of the substrate exceeds 40°C.
f5a00ee7-3b56-5972-9a6d-53e2ec5dbae8 | note | Method - Visual Inspection, Measure
519815da-71c8-5f51-abe7-ed6b9bd7639f | note | Frequency - Prior installation
e163c48a-dadf-5824-8a82-3b6d9a4e7b58 | note | Category - IP
b47f4af6-b396-54f7-a763-0e7b8cc73665 | note | Responsibility - SE/PE
fa9f21f6-c34d-5bb5-9c74-4bd6c13051b1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Waterproofing membrane application
ce0af241-44d2-568b-b409-0dbfaed10169 | note | Reference - 691.09 (a)
72437358-f9c3-5033-954a-b6b49bad699d | note | Acceptance Criteria - All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application.
cb76858e-bda3-5b57-9daf-ed252a072c3f | note | ○ The waterproofing membrane system shall be applied within 24 hours unless otherwise expressed in writing by the manufacturer after the preparation of the concrete surface.
5fcb9125-2511-5872-9214-3f7f06d892a0 | note | ○ The prepared surface shall be protected against contamination and rain or expected rain if the waterproofing is not undertaken within 24 hours.
d78450b0-c452-56e4-8061-b26684ee76f6 | note | Method - Visual Inspection
d75b9dfc-1a3d-5775-8cf5-c13b7091bc27 | note | Frequency - Prior installation
3edefc7d-8d63-5866-b688-e2f599a35946 | note | Category - IP
f0320cc6-480b-59fd-b48e-1ed8ec062c07 | note | Responsibility - SE/PE
32bb79ed-1f04-531b-98d4-224067fdd5d4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Waterproofing membrane application
e659002d-edb7-55fc-ba98-db84b4b5b78a | note | Reference - 691.09 (c)
809facaf-db92-54f4-9032-9fe93f14019a | note | Acceptance Criteria - Placement of preformed sheets shall commence at the lowest section and proceed to higher sections, so that water does not flow into any joints during service.
a5642be9-d612-5396-a41d-ee0963b7a443 | note | ○ The Contractor shall ensure compliance with the manufacturer's recommendations for heating method, duration of heating and temperature of oxidised bitumen adhesives.
f61fd58d-d3db-5dfd-85f8-a2dcdfc146a8 | note | Method - Visual Inspection
7dc2d449-26dc-5573-b53b-e6cadb022f9c | note | Frequency - When applicable
f453760b-c233-5b89-be59-f076766e2aaf | note | Category - IP
0eb3810c-f2c5-5286-85fd-53c3ba3d3919 | note | Responsibility - SE/PE
990baeed-6ab7-5ba5-90a1-bd4cb8c4d51a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Waterproofing membrane application
58a34173-1a3b-52d3-997d-05112c9abb2e | note | Reference - 691.09 (c)
27ec54e1-14a4-55fa-803e-ef16bc42513d | note | Acceptance Criteria - Self-adhesive membranes shall be rolled out and manual pressure applied immediately to ensure satisfactory adherence to the concrete deck.
e302113f-a578-5a9a-98b8-c96aab12df67 | note | Method - Visual Inspection
5704f80e-eee1-5ffc-9643-d29b5747ba75 | note | Frequency - When applicable
8c5f6a75-fc6a-5d06-b605-35dbf21e98db | note | Category - IP
afe57641-403e-5d47-b5c1-0ca3a1628959 | note | Responsibility - SE/PE
4d87c738-5803-5250-85ba-717c5291ed01 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Waterproofing membrane coverage
ab534a1a-5304-535a-9c09-27241c85d9f1 | note | Reference - 691.09 (d)
2edc2464-e6db-5fa9-bc99-fce6c04eadc7 | note | Acceptance Criteria - Coverage of the waterproofing membrane must be continuous over the entire deck area, including service bays, between parapets, medians and kerbs.
d1d32bf8-f132-5892-9587-dcf6c7498db4 | note | ○ The layout of the waterproofing membrane shall be detailed such that water seepage beneath the membrane is prevented,
cc8100eb-b9fd-5b61-a501-0124e9b27c37 | note | Method - Visual Inspection
db386e72-2a9c-5169-93a1-941667ebdda9 | note | Frequency - When applicable
15e821f4-918d-59e5-9955-a2cdc1efcad5 | note | Category - IP
25e7cc4b-fcd8-5b55-a68b-e1f70685702c | note | Responsibility - SE/PE
ef4d7531-48e5-53ca-8e2a-604660024698 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Waterproofing membrane coverage
24761f6f-5313-510f-b079-8b582e3a4e94 | note | Reference - 691.09 (d )
2c738aba-afd8-5674-9489-b83d59050b8b | note | Acceptance Criteria - At the junction with vertical concrete surfaces, the membrane shall continue up the vertical concrete surface, terminating at a level 10 mm below the top level of the proposed asphalt surface.
cd942c09-b53e-5757-9be2-8ffd314a188f | note | Method - Visual Inspection
db58fef4-3534-52b0-b43d-cc9c65774f17 | note | Frequency - When applicable
1bb47176-ec85-50cf-83fb-7b13c693c7bd | note | Category - IP
3a2e95f1-1cdd-5a2a-a592-1ce6b311668d | note | Responsibility - SE/PE
9d37f7c6-81dc-5dc2-b460-d7e6586f9cb9 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Waterproofing membrane coverage
bac03164-6d31-5bfa-801b-66749fbc69c4 | note | Reference - 691.09 (d)
a79d9915-d0cc-57e6-a023-20367503c5a3 | note | Acceptance Criteria - The waterproofing membrane shall be applied with minimum side and end overlaps of 100 mm and 150 mm respectively.
d973e1cd-71b3-570f-9c3e-5c7d6a7e8c55 | note | Method - Visual Inspection
97aba5a2-4bf2-5642-8c3a-6c29a24d8635 | note | Frequency - When applicable
67573f46-d05c-5cb6-adc1-cd0a83b8d29f | note | Category - IP
6e1e31cb-b7c0-5985-a030-0cde23c8cd67 | note | Responsibility - SE/PE
a622db2f-8264-5453-b14f-af68a49ea718 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Tack Coat
59e75e9a-6f14-5e3f-b781-db7c3eae343a | note | Reference - 691.05 (f)
67b793ba-ad0b-56dc-bf04-741ced8e97a0 | note | Acceptance Criteria - Tack coat shall be applied as required, in accordance with the manufacturer’s recommendations to provide adequate adhesion of asphalt to the waterproofing membrane over its service life. The tack coat shall be applied uniformly to the waterproofing membrane
0dc3b62b-64b4-5e6f-9e77-75aae0619733 | note | Method - Visual Inspection
3fd0fcce-b26c-5591-9097-dd5f988164f1 | note | Frequency - When applicable
1739f3d7-0012-565e-9806-c08426fe2e39 | note | Category - IP
7718fd2c-dda3-5fef-88de-c4087a67857d | note | Responsibility - SE/PE
89a6efda-23dc-50bb-b02f-313c304b9c64 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - Drying and curing
f7b29eb6-2e8f-55d4-ab3d-bc68a7e8483e | note | Reference - 691.13
8c7d7a13-59e0-5928-9fd7-679f4027a76c | note | Acceptance Criteria - The Contractor shall adhere to the manufacturer’s instructions regarding drying and curing requirements, and overcoating time intervals, for the prevailing weather conditions.
0c17fce5-89e1-535b-86ee-ee8161e17096 | note | Method - Inspection
6dbbbc08-b809-5f23-bb4c-07052af5b03d | note | Frequency - When applicable
ba15f447-e181-5af2-9ad8-b1b496e6dd7e | note | Category - IP
1f4abbca-7842-5cc0-9d03-aae1f1de0e9a | note | Responsibility - SE/PE
76fcdbf6-f81b-5b67-a332-c4d64d1852e7 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Subcontractor Product warranties obtained
9db25acc-aaec-50b0-b8ef-bfd9f1906342 | note | Reference - 691.05
dcb08218-5745-50a0-b60e-e3dc3f1e4d08 | note | Acceptance Criteria - Product warranties obtained and are compliant with 691.05
148bb2c9-a688-5461-90c7-7082df5615f4 | note | Attach: Copies of product warranties
0cd55036-2d32-5b5c-84c5-102943cbead6 | note | Method - Inspection Document Review
1b6d3249-ab29-51c4-9a64-1bccbdb38bdf | note | Frequency - Once per Lot
506b6bfa-4a69-5c0f-b75b-3818cef95137 | note | Category - WP
cc3bd04d-9bf8-56ed-a446-a4fa637ac1ea | note | Responsibility - SE/PE
5b028572-b1f9-563a-98e4-64e36ceb5691 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
57bde5af-5166-5994-846c-66a073bf8ff8 | note | Reference - MRPA Quality Management Plan
27aac0ff-b4eb-5d8a-80bc-f902d42501b8 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
e47feb21-cea1-51f6-946e-d8e48b266d48 | note | Method - Document Review
6a91db02-6bf6-507c-b6f6-cece14cd58c3 | note | Frequency - Once, prior to closure of this lot / element / Work area
6e6954d3-2625-59fa-89dc-a51f34f90ff5 | note | Category - HP*
12482f39-635e-596c-8185-6bee55a31c7f | note | Responsibility - SE/PE/SPE
8badb3b6-0d94-5e42-9269-b471d2dac3be | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
68637e10-849f-5165-9380-f8d5d9882a7a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
143f2b7e-7234-540c-b314-316c04986a5c | textbox | Name:
0ab08842-37cc-53da-8b09-539cafa2c591 | textbox | Position:
d23a7e32-ce4a-58f1-86c9-18e498305896 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-136-CIV-BRUNT-Footpaths & Shared Use Paths Rev.2 | itp | ITP-136-CIV-BRUNT-Footpaths & Shared Use Paths Rev.2 | e48fbef5-37dd-47a3-bb8c-c23461515e98
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
bd9ec8fb-682b-5b1e-b124-579cc4a6fb18 | note | Document Title: ITP-136-CIV-BRUNT-Footpaths & Shared Use Paths
67b40083-2e15-57b1-985f-b6b7218ba5aa | note | ITP Description: Footpaths & Shared Use Paths
6748eac1-12d8-5701-8d3c-1b5f48a62dbc | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
751fb6cb-29d9-5549-9de0-31a0a6fc06b1 | note | Discipline (e.g. CIV/STR/RAIL): CIV
43bde19b-ca89-58d9-a62b-cc0b8a2ace47 | note | Revision Number: 2
1f9bce5e-225d-59fd-b68e-2e2c299ff303 | note | Revision Date: 4/02/2024
caa18082-257e-51cf-9a9b-a0310097fe4e | note | ITP created by: Nipuna Athukorala
949020f7-b259-5abe-8f58-b2842441ba07 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
67c0a0ac-6185-5bee-b838-d1986dc40980 | note | Reference - VicRoads Section 304 August 2013
| checkpoint | 1.2 - Non Dependent
fbe88057-c7c9-5ece-9d6d-5c72b183e1e3 | note | Reference - VicRoads Section 703 August 2021
| checkpoint | 1.3 - Non Dependent
7c91847a-3f29-5345-b6a1-5973be0f5e88 | note | Reference - VicRoads Section 610 February 2023
| checkpoint | 1.4 - Non Dependent
980370f6-2d51-5326-baf5-f31de0bb71d5 | note | Reference - Council EDCM 401
| checkpoint | 1.5 - Non Dependent
3441ec85-0015-543c-b4b7-e529dc6c13ac | note | Reference - AS4586
| checkpoint | 1.6 - Non Dependent
326c70ed-3c82-5380-8e4b-5daa17559bc3 | note | Reference - VicRoads Section 812 July 2016
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Bedding Material Placement & Compaction
24391c3e-0b62-5826-a8d3-d4a365bda6e4 | note | Reference - IFC Drawings Section 812.04, Section 703.21
d932cde7-4078-5b4c-be88-5d7fb887c10e | note | Acceptance Criteria - Footpaths: 20mm CLASS 3 CRUSHED ROCK
37a280b9-7dbd-50d9-86c9-0a156725ea93 | note | ○ SUP: 20mm CLASS 3 CRUSHED ROCK
5bb42ef5-b51f-5d7a-a30a-a1749fb2fb83 | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
04d9c84c-ea07-5029-8e67-ff5289d8e48f | textbox | Enter: Teambinder Material Approval number
96a610af-f839-5fc3-854d-a6eae239d141 | note | Method - Document Review
363bc727-5464-5614-a597-1f35a4371bb6 | note | Frequency - Each Lot
f5ffe1dd-2651-5e03-b832-66f955153f16 | note | Category - HP
d5f08d02-9758-56ac-b7a2-5c948a84f71c | note | Responsibility - Nominated Authority
e5537614-30c0-5e09-97b9-3b993574357c | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete Mix
b9b56123-1d32-5340-b11e-2b83ec95cc35 | note | Reference - IFC Drawings Section 703.05 (a), Section 703.07
81d090ca-e6b3-5ff4-ba89-05fbb47d2c13 | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
ac553a8a-22b6-556e-b4f1-aa4c7c6a67e2 | note | ○ Footpaths: 25MPa CONCRETE WITH eMESH FIBRES APPLIED AT 5.6kg/m AT 100mm SLUMP
08f05632-00e0-57b3-9e72-8b4f885ac3ea | note | ○ SUP: 32MPa CONCRETE WITH eMESH FIBRES APPLIED AT 5.6kg/m AT 100mm SLUMP
837147ae-7da9-51fa-b8c3-c10cb1d5a97b | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
523a98df-8590-5094-b857-79e02dbc655d | textbox | Enter: Teambinder Material Approval number
149444cc-e8de-55a1-bce1-b3236a5e47cf | note | Method - Document Review
27f15621-af11-5836-b4f3-988ed22e6701 | note | Frequency - Each Lot
a4894577-216b-518b-aec7-89fc8cd3d00d | note | Category - HP
64a590af-7f4d-558a-9df3-5fc8d3ffddba | note | Responsibility - Nominated Authority
d288c85a-ae73-5779-9223-cd2bee5b9fc9 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Reinforcement
2ec699e6-17ce-5525-bb79-159fa69a009f | note | Reference - IFC Drawings Section 703.16
9fdb411d-2568-5c28-9294-e5ba1b744fbc | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
9bab1d5a-73ce-514c-a0c5-1b878979518d | note | Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification) following steel mesh requirements shall apply as per IFC Drawings:
06e6d256-0e7e-5da9-930d-2f979f4f5246 | note | – Footpaths, Residential driveways and Median islands infills: SL72
945da526-e53a-57ef-85d4-1ea057099b30 | note | – Industrial Crossovers: SL82
a81da3fa-9fb5-50ea-a439-31d55f08b389 | note | – Traffic Islands: SL82
56053e86-eacf-5921-84c1-8b2e77dc5779 | note | – SUP: SL92
15eac123-9ff0-57ae-8758-d7734db66602 | textbox | Enter: Teambinder Material Approval number
bb95e04a-e2db-5a1f-b95b-a056792fc018 | note | Method - Document Review
0e2d1dc0-7d05-5e7d-beee-049dfd80e112 | note | Frequency - Each Lot
2e9db164-e789-519a-bdbd-db638e265d2b | note | Category - HP
e264f415-6c56-5ff1-8ad7-f8fd4ba92f1f | note | Responsibility - Nominated Authority
2736cb52-25bb-561b-97b4-103da41a6262 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant (if required)
a96ab288-ecaf-57c6-9336-3e9992ed201f | note | Reference - Section 703.09, Section 610.17 (f)
ee8a3fb9-a73b-5307-afd4-a2ce538014f5 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
f99d23a3-f7ae-5b82-8f23-76f17aba63e8 | textbox | Enter: Teambinder Material Approval number
10d153e5-dac4-5125-a202-d152366a9fc8 | note | Method - Document Review
3f5987c6-ea3d-5827-a3b1-1f2b3721d917 | note | Frequency - Once, for each product, prior to placement of concrete
adbcc9d9-3318-51f3-b49a-b7a1af40fbd3 | note | Category - HP
bdab1d3c-0c76-50ae-85f4-8170c7eaffd5 | note | Responsibility - Nominated Authority
b6cad63e-95e1-5c39-b135-b322d9a233bd | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound (if required)
80a6492f-eb6a-583f-b39e-de27c5f25e15 | note | Reference - Section 703.10 (a), Section 610.23 (d)
5a7319af-e75b-516a-996b-b7802a2746ab | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
6b487ed0-92d8-506c-9ff3-ccc4f80d173e | textbox | Enter: Teambinder Material Approval number
45e74c41-aeeb-57f7-8d0b-35158fdd1c47 | note | Method - Document Review
461a5d14-7447-54f0-afe6-9d5a5e3c517d | note | Frequency - Once, for each product, prior to placement of concrete
a3af8947-9c86-54d0-8e48-4b8c5a9aa185 | note | Category - HP
c6b02cca-c453-5b83-a51d-077d3c63c1ea | note | Responsibility - Nominated Authority
23371677-9d3a-52d2-9db9-2a23044c8271 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Survey Set-out
e2bd8088-a40f-5830-b44f-0732f987fc94 | note | Reference - IFC Drawings Section 703.17
c36ea2dd-fc2f-5d90-a3f0-93697b52d7bf | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
13d2508a-f196-5d14-be32-1a17e253f441 | note | ○ The Nominated Authority will review and confirm the set out.
9f079a9c-1c50-5de4-a407-4b6b82d41b52 | note | Attach: Survey Report
c9ec1e86-c278-5b22-af0f-6ea6f24fb293 | note | Method - Document Review, Measure, Visual
4107a0c8-dfe7-5856-b0b1-53a41cce6921 | note | Frequency - Each lot
747d2f84-b27a-57d6-a33c-772d5f3f663b | note | Category - HP*
c1260c32-7922-5d4d-b9e4-b9de70c24cf7 | note | Responsibility - SE/PE, Surveyor
059b9795-2b32-5df0-b739-b56f45d900c8 | note | Verifying Documents - This ITP Signed Off
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Site Clearing & Grubbing
aec6a228-5b38-5f0c-ad9a-076a476565bd | note | Reference - IFC Drawings
84b1765d-58bb-5e8a-a25f-d6ae84ef157b | note | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed.
da8395b7-322a-5bd9-8280-52484b5b3462 | note | ○ Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
9a8d3289-3d89-55db-8cb3-9e39bf373dd4 | note | Method - Visual
75fb1080-ef28-5c78-b424-0c978de6b3a1 | note | Frequency - Each Area
ad326b7f-5e35-56f7-9ac5-02779340ca3c | note | Category - IP
5a776d8c-3683-5054-aa74-679e8ded407a | note | Responsibility - SE/PE/SPE
cd941dab-804c-5510-a587-bec2051b0f5f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - IFC Drawings
f3ff879c-1341-5e67-a676-1926ac93406a | note | Reference - MRPA Quality Management Plan
bf7657d7-4b38-5862-bade-5fc434f99289 | note | Acceptance Criteria - Ensure that all employee and sub contractors are: – Using the correct and complete set of drawings
56ca7649-b8d0-516c-8cd3-f0364b26e15f | note | Method - Document Review
5eca4f58-b885-5856-96ff-4861f2edda8f | note | Frequency - Prior to starting Works and at regular intervals
8319127d-29d3-556d-be04-e8a5311f2941 | note | Category - HP*
d55372ba-6d6d-5e37-abb4-be09f61095d6 | note | Responsibility - SE/PE/SPE
0479cfda-f298-5bd3-bbff-60c1d6c87231 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Excavation
310ff4c9-ada8-58d0-af6c-2618dca7efe3 | note | Reference - Section 703.20 IFC Drawings
78b67017-91e7-5ade-ad8f-75f6a31eecc7 | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
f51aeb37-b429-5b0b-aa92-a6606c2f18a3 | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
0e455f3f-1491-5600-a529-6baa4377139f | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
2dd9a6e0-b06f-53fa-88c3-de1a97f4b3bf | note | Method - Visual, Measure
98a6d85a-198b-53dc-8d76-a0ada999e986 | note | Frequency - Each lot
0abc00f6-1448-54bc-92d9-ec53ce69a5af | note | Category - IP
34d0aec8-3269-567c-ae28-66ca992f46c3 | note | Responsibility - SE/PE/SPE
1d9b07a2-bbc7-5766-9ac9-16fc9cc38f26 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Excavation-Pavement Thickness Increases for Crossings
3c74c10e-f69f-5c9e-ad51-c0de0cf98217 | note | Reference - IFC Drawings, Relevant Council drawings
a3f29f2d-4f3c-5740-86ab-9e03497b9e96 | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
428dbf9b-7ee9-55c2-b4f4-b4f9886df5d6 | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
9cb3ad90-8c58-5548-8887-a6af5881bb74 | note | Method - Visual, Measure
06fadac3-1082-5957-969c-4d036bc7f53d | note | Frequency - Each lot
33d2b0b9-82e2-5c7d-b4ff-b0d093af3ec9 | note | Category - IP
080d0ec4-2de3-5e4f-8cdb-47effbb23f53 | note | Responsibility - SE/PE/SPE
527502f7-75c0-5e37-bba0-c5601778b803 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Bedding Material Placement & Compaction
1a2be43a-7708-5b56-a4ef-3b49bcbd8928 | note | Reference - Section 703.21 IFC Drawings, Relevant Council drawings: EDCM 401
41849240-555e-563e-ad4c-0df1baad8ce9 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
1f2a0c0d-3953-5dd8-980c-afa4a8ca0403 | note | ○ Footpath: Bedding shall be 100mm as per drawings
46a526ee-67b4-54aa-9d92-07650dd52a54 | note | ○ SUP: BEdding shall be 150mm as per drawings
07d7465a-05b2-5ec1-a955-9622df71eb19 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
defdd855-c405-5553-bc30-5a429ec0157c | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
17786921-e8ca-5748-aeef-2ab09157862e | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
a626b4bc-0b33-5072-8eaf-5b5b531fca13 | note | Attach: Bedding Material Delivery Dockets
638031ae-08eb-54c4-ae79-3750f6f39d5c | note | Method - Visual, Measure
5b0c145f-1240-58b0-9065-48010e9c421b | note | Frequency - Each lot
5a9556de-9fa8-5a10-8986-a2df0edcde32 | note | Category - IP
fa2a0b35-b88a-54c9-a72b-63485fc7bddb | note | Responsibility - SE/PE/SPE
61c2bead-f364-5eec-8de6-06cbb5d3cd51 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Shared User Path - Compaction Testing
da8e9235-ade0-5246-94aa-9d5d9d433363 | note | Reference - Section 703.21, Section 304.08(a),(b), Section 304.11 (a)
d2f67c13-c1ea-55be-a602-1c410366b7be | note | Acceptance Criteria - Compaction shall meet the following requirements:
500bba56-d071-5f59-adb3-87b165fd3a0b | note | ○ Scale of Surface Level Measurement = Scale C
1d4cc091-3498-5772-894b-9df94c49aa7c | note | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
a2197eed-e9a5-59d5-a4f9-612a2fef3b74 | note | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
ad02d51b-c372-58c9-96d6-377018d7d6e4 | note | Attach: Moisture Content Test Results
7e87e05f-33b1-550f-94e9-4491f05a65a6 | note | Attach: Mean Value of Density Ratio
05e77275-381f-526e-8bea-da1a9053627f | note | Method - Document Review, Visual
e20a289f-33d5-51c6-875a-ade143f778e0 | note | Frequency - Where applicable, each lot
4de1cdba-a39b-542d-be01-70a8fd696122 | note | Category - HP*
f93e041e-29bb-5209-9c30-9d081921671e | note | Responsibility - SE/PE/SPE
4a020e05-0931-59af-8805-25b4464940a3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Shared User Path - Proof-rolling
8e8a05f0-bb2d-599a-a93d-ca9e64370754 | note | Reference - Section 703.21, Section 304.08 (b)
10788495-50df-51fb-a5ad-ec32ce7343b1 | note | Acceptance Criteria - Bedding material to be compacted and proof rolled before any construction.
9ffee389-3fe4-561f-ba6b-271ae461f981 | note | ○ Withstands Test rolling without visible deformation or springing.
f055813d-639a-520a-8724-7d5a7a0046eb | note | Method - Visual
2bc4f6f4-a99b-52cc-ae09-3b5a7c76e736 | note | Frequency - Where applicable, each lot
f66cf0de-5ef7-5a6f-99e4-e57717b5f1b0 | note | Category - HP
0fb0b789-0c6a-5e18-9667-2a27e669d7db | note | Responsibility - Nominated Authority
08ab0abc-8fae-532e-be4b-574c916c3a9c | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Formwork Construction & Placement
66f5bf85-69e9-5769-b7f8-9ebdf4a538fa | note | Reference - IFC Drawings Section 703.12
2ccba4ad-9d2b-54f9-bef3-75f1bac2e860 | note | Acceptance Criteria - Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
3a021426-c3d3-563c-9f7f-dda0d89a97d6 | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
e6b9c664-0974-5548-b086-6270e8759706 | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
bdf05b16-4cbb-5a1f-94fe-aedeacc563fe | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
f4c43113-28c4-52e4-b73c-8e88fb9a9e81 | note | Method - Visual, Measure
02f92ee3-b7ab-5c26-a974-73121c0c2781 | note | Frequency - Each lot
17a7a335-a835-5d61-817d-4b83d1f26026 | note | Category - IP
a5e9e400-3914-529f-81b0-a93bf11297a0 | note | Responsibility - SE/PE/SPE
4633ec5b-c670-59cc-b02b-cbf83d06c050 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Construction Joints & Matching Existing Surfaces
658e50a7-bd1d-5fd7-8810-9c585f638cb6 | note | Reference - IFC Drawings Section 703.24, Relevant Council Standard DrawingsRelevant Council drawings: EDCM 401
4353552d-7e91-5b17-9106-b91e1eb3654c | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
dd5310ed-4d4a-576b-b2a6-750672aeb5ff | note | – Consult the relevant Council Standard drawings for the joint detail, these may require:
1e6b8505-c8e8-5ba9-9b75-e792f2adc84c | note | i. Concrete cutting of a shear-key
e7bb8a31-4a30-5624-ae82-294a02cbd3b0 | note | ii. Surface roughening
63b39ec2-b0d1-58e4-a565-86e315def961 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
810eff96-070a-592c-96bd-541dddf99fe7 | note | iv. Cutting a groove for sealant
6c4a6c2f-b8ff-57ec-976b-7ffe70e96e79 | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
4dbce762-9bdf-5fda-a54f-05193bde15f8 | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
d1be34e6-bff4-5900-a131-d4223a138a61 | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
3bca754f-4ac0-5a03-846d-6764b6d07829 | note | Method - Visual, Measure
6cac1c99-b284-52e6-9235-35649fc4e474 | note | Frequency - Where applicable, each lot
8e0b15be-351d-55bd-bfab-36a3dc513abd | note | Category - IP
2b652950-81be-5d67-8da5-b08571f21fb7 | note | Responsibility - SE/PE/SPE
dcfb858e-4210-5bcb-90fa-f96b25bedae7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Isolation Joints
722de19b-e4bb-5787-9dd9-da5a08e0c008 | note | Reference - IFC Drawings Section 703.26 (c), Relevant Council Standard Drawings EDCM 401
d51f3895-b0af-5f55-8a71-4202b822bb58 | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
a3989df6-9f91-5101-9abf-42b996f7a469 | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
767f995a-8052-5317-b461-bf0361a13167 | note | ii. at any location marked on the drawings
efb1a76f-caa2-5b4c-8a40-17427591d7d7 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
1297d586-dd82-59b2-8fdd-a04249023112 | note | Method - Visual, Measure
3ed177d4-c7cd-5fb8-b036-79e38787c373 | note | Frequency - Where applicable, each lot
7dc58cee-7df9-57db-b03f-d89db5ebd16d | note | Category - SP
9d75f88f-8a78-5f2f-b700-a44e4a4a9700 | note | Responsibility - SE/PE/SPE
f81f15fc-dfaf-5cae-a6ea-8cdb35bd2941 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Expansion Joints
216b1723-aa36-5c0a-8ef0-56d5184785ae | note | Reference - IFC Drawings Section 703.26 (a) (ii) & (b) (i), Relevant Council Standard Drawings EDCM 401
ede87b62-f5f9-5287-8936-c6edc09c2461 | note | Acceptance Criteria - Where applicable, expansion joints shall be placed:
b7f74115-8554-55b4-9262-d8d14d3313db | note | i. on either side of vehicle crossings
b5c7ce8b-4da8-5c13-806b-d9793660ef0e | note | ii. at junctions with existing footpaths and shared use paths
29744d70-9712-52ce-b3ff-cdb7db1ea043 | note | iii. at junctions with bridges
6d36c53d-fcea-590b-ad67-6e3f6f8e2931 | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
219fda8c-66f2-59d9-918b-0e93d6d0adc3 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
a1226778-1900-5c9e-ab40-7943467b89c7 | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
923dd923-4007-58d2-8eab-e777981992ec | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
fc5902b4-5fcf-5cb9-84b1-8a81e9e8f279 | note | Method - Visual, Measure
f56d4ed7-5df6-57e1-adf9-466cee3a479a | note | Frequency - Where applicable, each lot
0e28e5f3-0c55-56f9-be78-0dd93441c98c | note | Category - SP
6c33c44b-25b4-5ee6-a848-df63c424b836 | note | Responsibility - SE/PE/SPE
de06686b-b682-55a8-8b3d-02ccab1ae12a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Reinforcement Placement
ce13e859-d760-5a45-9a50-cfb0cc2a657f | note | Reference - IFC Drawings Section 703.13 EDCM 401
710750fd-cdd0-5006-8c83-414515877262 | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
18b9b51e-5a77-5bc9-bada-9ed4ec376ea0 | note | – Footpaths & SUP: SL72
5c1d1404-8011-55ab-aa78-479cfa074f7d | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
f6e4a270-0493-5806-bf1a-83ab79b7fba6 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
567fd053-f4dd-568d-b86e-58cd51530474 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
acbe3b95-8a72-5ad2-b37b-8d87f137253a | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
2e833e7f-f8a9-5b56-8b29-009aace55796 | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
7c7c04c5-8546-5641-b4f0-b39a0f8e1091 | note | Method - Measure, Visual
4ddc78f0-5aa7-5eaa-9e74-8056fce89e1a | note | Frequency - Each element
f1ddf776-efbe-5ce7-b159-86db7a26268c | note | Category - IP
a13daa4e-78f0-5066-89a6-a877814a128e | note | Responsibility - Supervisor, SE/PE/SPE
56f941f0-ffc1-5cf2-95d2-7a5ba79ce215 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - Pre-pour Survey
5538be18-3862-51ff-b95c-e1df5e0e2e75 | note | Reference - IFC Drawings Section 703.15
27219be9-66eb-56a2-acf8-be07597d2e50 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
81698ab8-23e5-52d4-847f-8cc231f72653 | note | – Erected formwork and base layer within the tolerances below:
4627f0ea-fe26-5d6a-a2d6-2752df81508a | note | ○ Departure from RL = ±10mm
af83c573-fe16-5b54-b88d-5afa7cad2eac | note | ○ Departure from alignment = ±10mm
e9d96f13-f3f2-56d5-be88-cb35b25a91f6 | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
7b4da624-396c-54d5-b160-07fd69aa6170 | note | ○ Irregularities in alignment = 5mm in 3m
08b7a4f0-44e8-51b3-986e-c080f2f1d798 | note | ○ Section dimensions = ±5mm
5d56bdeb-ea1e-5663-949c-61bb4b0fa3cb | note | ○ Section dimensions (less than 25mm) = ±3mm
5bf10964-85db-5c18-8571-728996d6bf2d | note | ○ Width of pavement = -5mm, +15mm
70616e08-ec17-5f51-81fc-2a0a2e683f25 | note | Method - Measure, Visual
6d53e907-a769-5e0b-95c2-dd6e018cd88c | note | Frequency - Each lot
98bd3714-9e23-58b2-94ad-fc97dc46e979 | note | Category - HP*
2e375d21-de61-5d70-9985-c37daf7711c1 | note | Responsibility - Surveyor, SE/PE/SPE
4c6532f5-ac12-5d16-9f26-2ccd799fb734 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.12 - Pre-pour Inspection
d9f02497-f790-5688-87c2-c3278e199efc | note | Reference - Section 703.09, Section 703.21 Section 610.17a), b) & c)
299c4bf1-d780-5236-b441-c81346dddf5b | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
e4159dc1-920f-5673-8843-0860df98675c | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
f8ace5d7-f1fc-52f8-84fb-262e73f370af | note | ○ Attach prepour inspection sheet
dcec122c-0899-5be3-a39d-4d62ab3293ad | note | Method - Measure, Visual
c9b1e85b-72d8-51d7-a1b0-4ded880aea08 | note | Frequency - Each lot
a98b1da4-247b-5d72-9c73-0dc785e6a52c | note | Category - HP*
77677b05-6ed0-55a3-a407-91dee5dc7f6e | note | Responsibility - SE/PE/SPE
86eeaaf9-0442-52c2-ae9e-b09b0c39fc42 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.13 - Weather Conditions & Evaporation Limits
31752192-ff8c-5fe6-86a2-b0230bd38ea7 | note | Reference - Section 703.09, Section 610.17(a-f) Table 610.171
ca692a24-97e1-53d8-853a-8444e06e56d0 | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
c993a00f-65d5-5d33-bc02-8de743be356a | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
751d3152-41d0-540e-a858-69c40945a3fe | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
9a5a9327-2f28-532e-883d-041a54e714da | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
b09c1b09-ed76-5c1a-b903-1629f36e819e | note | Record: Required information on the Concrete Pour Record.
3d56d82a-423d-504a-a519-83e0f5a5620a | note | Method - Measure, Visual
1d7af5a4-5ac2-594b-af16-50b7f269eb26 | note | Frequency - Each lot
f891d1b3-356c-55a2-bc8a-73209a2ec472 | note | Category - IP
317c8c10-ca11-58eb-827b-cd13f6e2d2e9 | note | Responsibility - Supervisor, SE/PE/SPE
7e0c5051-0d46-5c3b-aac1-bc5bf4cdcad0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.14 - Concrete Testing - Sampling Frequencies-Footpath
478607bd-c7c3-53bc-b468-5c9f533b88b7 | note | Reference - Section 703.11 AS 1379-2007 Cluse 6.2
e9ef3d87-3d4c-5c49-aadc-277068fe8452 | note | Acceptance Criteria - The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
9c3d017f-7f9f-5153-8418-aa8dc9de5269 | note | ○ Correct quantity of cylinders manufactured per sample.
0e750166-2f9a-5556-831c-ee32f077b0e9 | note | Record: Required information on the Concrete Pour Record.
b5e63714-b45d-59a3-b620-57fdc5411f7a | note | Method - Test
87affe2b-92ad-5785-aff5-15585f616e69 | note | Frequency - Each lot
a3116c8c-d886-5b4f-86b6-fe8004b59937 | note | Category - IP
b5de0a89-c2de-5de6-b92f-21bad50f1aac | note | Responsibility - Concrete Tester, Supervisor, SE/PE/SPE
98fe687b-a4dc-5a54-9637-4ced424e4784 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.15 - Concrete Testing - Sampling Frequencies - SUP
fc99e6ca-adb7-5971-abb0-a414c537cab0 | note | Reference - Section 703.11, Section 610.16 (b)
a536c3d7-723f-5118-b458-144ae59d0bcc | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
53c6bcd1-3c38-5472-bacb-ab76413f378b | note | Shared User Path:
7b165ab9-afd4-506f-b4a5-f156839e0a42 | note | 0m³ to 10m³ = 1 sample
b6e16466-da70-5053-8a4e-491e03d204a9 | note | 10m³ to 25m³ = 2 samples
984ffe93-6105-5d27-adc2-c3f1a0ad5a1d | note | 25m³ to 50m³ = 3 samples
433ccb22-c13b-572b-8224-aa8bb2397b2b | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
dc33681f-d82b-5049-b18f-5f739a22070e | note | ○ For each additional 50m³ and additional sample shall be taken.
95a1dd95-2709-5a0b-9b1a-671ca2025330 | note | ○ Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
c2d3fc5d-63ac-581e-a2eb-b13b5c9be453 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
2d2cc84e-ebd2-5460-a600-69552656345d | note | Footpaths:
8f555a57-5ae5-51b4-a91a-355d9b2b5c03 | note | 0m³ to 50m³ = 1 sample
56f03d38-ef21-544a-b9d6-47a1160f0b4b | note | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
7eaf0fe1-4269-5845-af83-572bca410825 | note | ○ Compressive strength cylinders = 2 no. 28 day strength.
0c578a75-6285-56ce-833a-4bf3421a9036 | note | ○ Correct quantity of cylinders manufactured per sample.
c49cb9bc-c5e3-5be1-9a26-7561e4734605 | note | Record: Required information on the Concrete Pour Record.
f12f0f7d-ef2f-5606-8fcc-fece6018108f | note | Method - Test
d4a8c3e2-7307-55c7-b8a9-d59523eb2b3a | note | Frequency - Each lot
2c7fb65a-c925-5ef0-ac71-6f5dddf9c692 | note | Category - IP
0463938a-f5b9-5e32-8756-98718d05ba0f | note | Responsibility - Concrete Tester, Supervisor, SE/PE/SPE
a9b5e047-e06d-579b-9247-a25bd4fb1548 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.16 - Concrete Testing - Slump
74742f37-62a3-5559-986b-1b26848c111e | note | Reference - Section 703.11, Section 610.16 (c)
7ecd973e-1c30-5574-bd3c-0adb539d6e5e | note | Acceptance Criteria - Slump testing tolerances =
bf1e36a1-dea7-57bc-bb41-ebbd213178ad | note | ○ <60mm = ±10mm
ba810997-1b24-5370-8fc9-71abf8cfae4e | note | ○ ≥60mm to ≤80mm = ±15mm
9c87c4cb-15c8-53f0-9948-996d639324eb | note | ○ >80mm to ≤110mm = ±20mm
b28319ac-04f7-55a9-9eb5-9fc82cf85cb5 | note | ○ >110mm to ≤150mm = ±30mm
6f579325-0e33-5cde-bb64-a7c0d1cf1b82 | note | ○ >150mm = ±40mm
a363b5f3-7d62-507c-93e4-28999fec57ef | note | Record: Required information on the Concrete Pour Record.
4a1e9b7b-15b6-5ae2-a515-555defebdb08 | note | Method - Test
4b441322-48b8-5842-9b78-2355ca073602 | note | Frequency - Each sample
f1c64788-e5b0-5103-98c0-4498bb3d43f8 | note | Category - IP
37482323-d6b9-5139-9ae2-379a97d31233 | note | Responsibility - Concrete Tester, Supervisor, SE/PE
f9c2f795-8c2b-58b2-8aa3-199d0b43ff0a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.17 - Placement & Compaction
8a0459d1-4578-5455-9c7a-d02e730c8869 | note | Reference - Section 703.08
664ab810-18d3-503a-80ad-54c435b0cd7f | note | Acceptance Criteria - All concrete batches are traceable.
6efba3de-4a8d-5b54-a20d-9301a25b36f2 | note | ○ Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
ab8f11fb-271f-5040-a9fd-6e2c47190838 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
e2549dac-ba78-5563-bc75-3b389054c08f | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
42851979-b64e-599c-9cea-8bfa23694415 | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
95f06196-d7d0-53b0-9934-17f894a5afb9 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
fade77cd-65c6-5965-ae35-c29f9be5a1f7 | note | ○ Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
afff1999-b716-5317-9328-92a8b5d9c173 | note | Record: Required information on the Concrete Pour Record.
0500fa4e-fa07-596f-91c7-959dd772aecb | note | Attach: Concrete Pour Record
7d844ff9-65e0-5ec4-b047-a6bb08b1dbcc | note | Attach: Concrete Dockets
05df78b6-8534-5f77-82d3-55428b06a3a0 | note | Method - Visual
9219c847-5494-5043-a16a-bd5e6516a8e5 | note | Frequency - Each load
d4cdd20f-c6bb-59aa-a513-9a0f86e6cdca | note | Category - IP
70539f78-d1fe-5bec-9739-f7baea73e2ec | note | Responsibility - Supervisor, SE/PE/SPE
2954ebdc-7f83-54a6-830b-6eb3b97c7407 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.18 - Surface Finishes
3539f94f-0b41-5c57-acff-1335da4e5174 | note | Reference - IFC Drawings, Relevant Council Drawings Section 703.25
1d5400d9-661b-5332-aaad-83e20bf55b69 | note | Acceptance Criteria - Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
06b1d4e2-1915-54b2-90d9-48bb4ee306f0 | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
3458a401-164a-5b84-b01c-d31c2a90ffc1 | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
62d92882-75ba-528c-9b75-20c2cb2d6078 | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
11b8b259-90da-5778-99db-0369bd15ff20 | note | Method - Visual
c2113258-4b67-55a3-ba9d-35e2bb5c56ff | note | Frequency - Each lot
cd57dac8-48dc-5a11-9f1a-46efef7bd2c5 | note | Category - IP
4ea1389d-6221-519a-8046-69ce8909cb14 | note | Responsibility - Supervisor, SE/PE/SPE
ddd9e21e-3fa8-541a-829d-d7a3a2f682d1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.19 - Footpaths - Crack-control Joints / Weaken Plane Joints
46863163-9023-584e-b7ec-907aed5a380a | note | Reference - IFC Drawings, Relevant Council Drawings Section 703.26 (b) (ii)
822d10fa-ff81-5d47-99f1-9b32fe485a33 | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
4dbdf097-4f52-5b4b-b11c-fc9888023cf0 | note | Method - Visual
d16ab947-94f0-5529-9f83-61fb944f57c2 | note | Frequency - Where applicable, each lot
4c0b4038-b4fc-5e7e-b19c-098df1c445c9 | note | Category - HP*
6ddc5fd3-7e38-598e-a343-805bd792f9d5 | note | Responsibility - Supervisor, SE/PE/SPE
9e3a7b1d-cb97-5023-a0a1-8cfa6abe8eb0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.20 - Curing
d783a9b9-69d8-5d4b-b711-428a1b2153ca | note | Reference - Section 703.10
8fd43055-866b-5f3c-bbc0-0e04a42fc8a8 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
625471d6-8125-5ad1-b065-01f23505d72a | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
4da378f4-3b28-5ebd-a86c-46ce30d61d8d | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
5abb279d-f300-5e1f-bdd1-19c650654830 | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
3ed571f7-d700-538f-b90a-042465a38aad | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
151611e5-4ef4-5e3b-bbc5-4ab6cf9ce6cb | note | Method - Visual
e548c846-7fc7-5eff-804d-136fdbb6bc0b | note | Frequency - Each lot
6e15731e-b9ac-5f6f-9863-49c98c64f451 | note | Category - IP
92ad7d8b-fa8d-5771-b59a-ec600ce94be9 | note | Responsibility - Supervisor, SE/PE/SPE
e20d97ee-9eea-519e-8283-b0896dde05a5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.21 - Hardstand Grade (where required)
9fda5ba7-b6a2-56e8-8f44-65fb1bf27089 | note | Reference - STD S0075
4f7cac9f-31ee-586e-b158-5653480d1af8 | note | Acceptance Criteria - Hardstand that are connected to the Bus stop must have a grade between 1% to 2.5%
52739465-74bd-502e-ab73-b24fd2468d60 | note | Attach: Survey As-built
706d8e77-7898-54c5-b906-4a0c7f517156 | note | Method - Visual
a1d05ffe-85b5-582b-8cef-80124dd59a7f | note | Frequency - Each lot
84702265-49d3-56e8-8c21-8091c13ba8f9 | note | Category - HP*
739bd611-f304-5810-9848-162ad1cbd0ca | note | Responsibility - Supervisor, Surveyor, SE/PE/SPE
40afe888-7be0-5895-9a9e-27454067160c | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Shared User Paths - Crack-control Joints / Weaken Plane Joints
42fa6ea8-eae1-5388-96c5-d47145b1380b | note | Reference - IFC Drawings, Relevant Council Drawings Section 703.26 (b) (ii)
ac970c9c-985d-5eca-8ee6-177500efb4ff | note | Acceptance Criteria - Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
8fba5948-d2b7-58b2-9899-05e080d3889d | note | – Provide min 30mm deep saw cuts along the full width at abutment and pier locations, and at 2.5m spacing for SUP, and 1.8m spacing for footpath.
cb2e2760-55ea-5f82-b363-d003bc80c746 | note | – Control joints/saw cuts shall be formed with a cutting tool within:
79afacb3-4128-58e6-b346-4e939a871042 | note | ○ <20°C = within 24 hours of finishing operations
9509e127-31aa-5437-99f4-179f91afad0b | note | ○ ≥20°C - 35°C = within 4 hours of finishing operations
27e6bf4e-a867-5988-b208-a1a59c59a7d2 | note | Method - Visual
1f5603c2-d858-5f29-8e24-e99f5c1b7d64 | note | Frequency - Where applicable, each lot
95c7e7c5-fe2e-5183-a9f8-12c0577ba2b9 | note | Category - SP
3ed4c288-2b67-5e99-9acb-f865bc24dfaf | note | Responsibility - Supervisor, SE/PE/SPE
bf4ed5c3-bd28-5b6c-a7d7-08fec7ab0925 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Protection of Newly Poured Concrete
a1926c98-4281-587c-a908-23f009170e78 | note | Reference - Section 703.27
98daee31-4ec6-5a5e-91c3-c4515a94b363 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
b677806f-1394-5e53-bda3-ccf355c0e92e | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
fc1a975a-01c2-5c6f-b19c-aaf78b17dfcd | note | Method - Visual
87409ef5-f9b0-59f3-8711-a276a05b0214 | note | Frequency - Where applicable, each lot
2949fe21-cc32-57dc-b0c1-e5ddf4f19254 | note | Category - IP
0d3c7da3-6870-5c8a-bf64-ffd835134ecc | note | Responsibility - Supervisor, SE/PE/SPE
379866e0-769d-50ec-885f-8196eb5beeef | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Stripping Formwork
b5583705-aeff-57d0-9217-d281e9352cd4 | note | Reference - Section 703.12 AS3610 Table C2
dca933e3-237f-50aa-89b2-138a1c4ac72c | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
545d1463-f67b-56bd-9850-9c74ef3db067 | note | i. 2 days for vertical formwork on external surfaces; and
c7c02be4-2b47-5159-9cef-14e4d49f5ecf | note | ii. 1 day for vertical forms on permanently hidden surfaces
3a17df10-2160-50b1-9c21-9f0b21bcf8c6 | note | Method - Visual
74eac144-a8ab-57fb-9479-7344b82f2ad6 | note | Frequency - Each lot
c3da0f98-1fc0-5949-ad8c-49b40dc9c3e2 | note | Category - IP
5368cb15-2a6c-567a-aea3-f6bee36cbf67 | note | Responsibility - Supervisor, SE/PE/SPE
98dc0799-8b99-519f-9fca-c13b50ab88a0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Backfilling & Pavement Restoration
7e0701d3-83e5-5726-a118-7f1b9836633b | note | Reference - Section 703.29
29a7cc12-a3d5-517a-b876-f0218866f830 | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
165956a8-92e6-52c8-9d70-fbfc1349a7d3 | note | Method - Visual, Measure
4ee2cf8f-857e-532a-9e2d-d2fc3f29a3b6 | note | Frequency - Each lot
469eca78-a203-541b-b5d1-73efdcead6d0 | note | Category - IP
7e5b4202-cea5-5c1f-a9b3-724423ab1b4a | note | Responsibility - Supervisor, SE/PE/SPE
69e42c10-703e-5215-a041-ac3a03741b13 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Surface Inspection - Cracks
ff97756c-3433-5a11-a54d-fcd744a9c0dc | note | Reference - Section 703.3
0a6db2bd-3b75-524b-8a30-21d8a753570e | note | Acceptance Criteria - No cracks greater than 0.2mm.
7bb5dac1-4125-5a6a-a07a-f76bbea3e2cf | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
aefcf332-e9a7-5f6d-8d48-0b292d1272d6 | note | Method - Visual, Measure
054b47a7-3562-562a-a818-d5965b533f01 | note | Frequency - Where applicable, each lot
370ce430-9eb9-5a98-a0c0-8aefc98b3f09 | note | Category - IP
c12e09fa-4ee3-585e-affb-ebc1626f9309 | note | Responsibility - SE/PE/SPE
16148bb8-f8ef-5a06-9e65-4b91483722f5 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Surface Inspection - Surface Finish
a6277542-3d85-5e9e-94de-0d7c5172922f | note | Reference - IFC Drawings, Relevant Council Drawings Section 703.25, Section 703.10 (a) AS4586
b8dd372d-74c2-5dec-b9f1-562dae84f736 | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
e3659711-b90d-50db-ae2c-af81332d08a1 | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
b5f9dacc-49b9-5c19-9013-e41d16bab1a2 | note | ○ All Finished Surfaces to comply with AS 4586 Slip Resistant Classification of New Pedestrian Surface Material
db27d68a-36ef-583e-8121-001f9781db6b | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
c64aebbe-7a31-59d9-928c-d3ec3be6ec7f | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
90df3a49-c8f2-594b-b541-26f3c70a4d85 | note | Method - Visual
cee35df8-7e52-5f3a-82b1-7a08f220dbf3 | note | Frequency - Each lot
1a823c1a-8df9-5703-8da7-680dbcbec344 | note | Category - IP
6a3425c0-33e7-56c3-b9d8-a65158d49fe2 | note | Responsibility - SE/PE/SPE
f2faedf4-e98f-5662-bed5-63b56a7cef35 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Compressive Strength Test Results
d7237f25-e9f7-5e8f-889e-0ae8f82e926b | note | Reference - IFC Drawings, Relevant Council Drawings Section 703.11 Table 703.111, Table 610.05.051, Section 610.16 (g)
28803610-e2c7-5952-9c2f-09fee308739b | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
1f22dabe-4aa7-5bdc-8fe7-0a5ddc9aaf59 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
c66761f4-8ecd-5a65-b4d7-ac444f405792 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
610656e1-9ebb-53d2-b478-e97229d8cfd8 | note | Attach: Compressive Strength Test Results
598fa161-4802-519d-98c9-322539c3f612 | note | Method - Document Review
357eb6da-0b92-5319-b8e0-8b6921836453 | note | Frequency - Each cylinder
2cae6253-c8be-5a96-9a4d-18bcdcf1e1d7 | note | Category - IP
20d70531-2f01-56f8-9362-f1c709926531 | note | Responsibility - SE/PE/SPE
dac28c07-f7a9-5039-b703-72fcf8fc62a7 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.8 - As-built Survey
d53d71f3-ed9c-5f59-a382-5791fe2c3647 | note | Reference - IFC Drawings Section 703.15
33309381-bca3-5d2d-946a-9d3b9098cb64 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
627751b3-099a-5268-98c7-d1f2f985c6bd | note | ○ Departure from RL = ±10mm
94ca8a97-058a-5756-bc89-705b76132a72 | note | ○ Departure from alignment = ±10mm
9aa4a8cc-1958-5c93-aae8-00177a66708c | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
65d85236-7275-5a93-9148-c0bd4e7e66ea | note | ○ Irregularities in alignment = 5mm in 3m
92b53dba-1bf7-5624-9b3d-841ea191bb60 | note | ○ Section dimensions = ±5mm
0cc2bbb2-81fa-55fc-8414-203dca04a9ed | note | ○ Section dimensions (less than 25mm) = ±3mm
7eb47404-20ec-5286-ab56-e3da010dba22 | note | ○ Width of pavement = -5mm, +15mm
0ba76585-4269-5fe1-a351-ef0639bb2b3b | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
b50d855b-0cd6-5e4c-8f6c-1a7246bd196f | note | Attach: Survey As-builts / Survey Report
f6e689c1-c3b7-5eee-81c5-59f409f89656 | note | Method - Document Review
9385be5f-0bc5-57c2-87e4-47995cf265d8 | note | Frequency - Each lot
1dc0bfda-dfff-549e-8b5d-c7f7cac7396e | note | Category - IP
6991059f-2a80-508a-bcd0-7c08e84b21e5 | note | Responsibility - Surveyor, SE/PE/SPE
c025af98-e062-5200-a575-7d9b61185e1d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.9 - Non-conformance Report (NCR) Closure
a5b58fa8-9af5-5f4d-b30b-2a43e0c9aa25 | note | Reference - MRPA Quality Management Plan
8d5d110b-c15f-5bf9-aabf-961d6d98a104 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
dfeeee03-e88e-56ed-94f8-9bde37a45c9d | note | Method - Document Review
19312885-ecf4-5280-9d45-c607fbc49213 | note | Frequency - Once, prior to closure of this lot / element / Work area
4680d726-364c-5a84-8f27-844cd1da1c67 | note | Category - HP*
c0ff52d1-d592-535b-8e25-c96dafe5062a | note | Responsibility - SE/PE/SPE
a82a483f-8257-58cd-b142-2b92db8675ba | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
6b6726f6-63b0-5f58-b9b1-1c75074a9b09 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3e0bda4f-956c-5d3b-a755-bb059481c54d | textbox | Name:
cca76d09-0686-53f0-b50b-582655c1022f | textbox | Position:
a8b105b3-7b93-5443-89ac-f7dd347e616c | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-138-RAIL-BRUNT-Aluminothermic Welding and Stressing Rev.0 | itp | ITP-138-RAIL-BRUNT-Aluminothermic Welding and Stressing Rev.0 | 75fd373d-9771-4d78-8ca8-e2214b1e0f55
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
f8286acf-8ea0-59c1-b749-a1a5967c7fb2 | note | Document Title: ITP-138-RAIL-BRUNT-Aluminothermic Welding and Stressing
1d890e14-81b1-54e0-9ddb-deefaecb981b | note | ITP Description: Aluminothermic Welding and Stressing
add5c4ad-7246-5acb-a543-902ba921f0b1 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
7ae51f61-9c46-5d0e-be9c-649841c77337 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
17713aa4-d4d0-5117-aff1-34bfc6f43a11 | note | Revision Number: 0
bb3a15e2-0701-589d-a49f-656067dbbd95 | note | Revision Date: 14/03/2024
0c2922ba-7fa9-5f17-8196-b1feef5565bf | note | ITP created by: Mac Cameron
a67dc3aa-1c8f-5738-adcd-9ea6846109a6 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
06a99105-dade-5e9c-9621-811704e6eb25 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
| checkpoint | 1.2 - Railway Track Materials – Part 1: Steel Rails
7bd4fbcf-a208-51c1-bd88-43f6c9616651 | note | Reference - AS 1085.1
| checkpoint | 1.3 - Welding Rail Steels
4cea4d2a-6df5-5f96-bd91-8f7dcaf51954 | note | Reference - AS 1085.2
| checkpoint | 1.4 - Flash Butt Welding Specification
bfa7c18b-c324-5904-872c-fae86b8e54e3 | note | Reference - A1340
| checkpoint | 1.5 - Hot Works Procedure
1daf30cc-0664-5269-8f81-14bf9f289d6d | note | Reference - A1606
| checkpoint | 1.6 - Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure
b0966c75-2389-5efa-8c23-93aab3618135 | note | Reference - A4597
| checkpoint | 1.7 - Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure
676f01d9-b6ea-5efc-9c3f-92b5e3895764 | note | Reference - A4589
| checkpoint | 1.8 - Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure
dc02b7ba-95ee-5c3f-ac67-ecbd6e123a08 | note | Reference - A4598
| checkpoint | 1.9 - PTDT Form B - Track Certifier Booking Form
fc1ad89f-2f82-5343-a946-8109b3cbfacf | note | Reference - A4263a
| checkpoint | 1.10 - Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
96a566ed-18a2-5f4e-a8de-ca46d7a7129c | note | Reference - A4588
| checkpoint | 1.11 - Non-Destructive Hand Testing Of Rail - Track Procedure
de978b22-2f8b-579b-ba9b-859436f6131b | note | Reference - A4550
| checkpoint | 1.12 - Track Construction - ITP
8755b354-61b9-5104-aa56-9e9d07026323 | note | Reference - ITP-139-RAIL-BRUNT-Track Construction
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Supply of Weld Kits
a4f542bf-894d-59d0-bf32-4af3cc2baca3 | note | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
33a3a455-d2fb-59dc-91e0-6604d9c43705 | note | Acceptance Criteria - Weld kits supplied are within expiry period and conform to the requirements of applicable standards.
d00792a3-4e69-57f3-9c57-85ce3d893a1b | note | Method - Visual Measure, Document Review
0b46e621-3a52-5d6e-a057-73dff37d34e4 | note | Frequency - Upon Delivery
4f9e224c-40af-5c54-8823-441daf63d8a1 | note | Category - HP
c14f32b6-6ddf-5c86-8c00-c5e71bd7d530 | note | Responsibility - SE/PE
2e1f018e-e648-5406-a959-f54d78f1ffff | note | Verifying Documents - This ITP Signed Off
8002fe3c-96c5-5b72-8368-7ae8326c33bc | note | Attach: Delivery Dockets/Site Photos
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Primary Documentations
95d0677c-2b4c-55ee-89ab-29310f91d6c8 | note | Reference - A4263 PTDT Form B - Track Certifier Booking Form A1606 Hot Works Procedure
7b29b318-148f-5e38-ac93-a12eb2a68d76 | note | Acceptance Criteria - Approved PTDT Works to be completed in accordance with Hot Work Procedure.
01fe66f9-9c64-5eb4-80a3-a384c75c8f0b | note | Method - Document review and approval
d2860c5b-add5-57ab-a081-c97205236b23 | note | Frequency - Prior to works commencing
37f2510f-a339-5245-b51d-77851ad71091 | note | Category - HP
ef0ec5b8-c4a2-58a1-9402-576d4e4978cc | note | Responsibility - SE/PE
6e26e18e-95f7-5576-a915-f731aa948a9d | note | Verifying Documents - This ITP Signed Off
4bc44b17-92b7-5f44-83b2-a8d5bac40942 | note | Attach: Approved PTDT
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Pre-Commencement of Work
c72dfef0-ef1b-568e-9b05-da376d3df53f | note | Reference - ITP, Quality Checklist, SWMS,
c72a7cb1-711d-5731-8ce3-ab9e8cec70bd | note | Acceptance Criteria - All approved by relevant representative.
c89f6e93-2ff7-59b6-bb7a-48862248fa2b | note | Method - Document review and approval
07ff1dfd-9756-5160-afbe-1ea426920df0 | note | Frequency - Once (Prior to Works)
26ebebec-eb2d-5e58-a236-599e1f3595e1 | note | Category - HP
94cb21bd-132c-59f1-a3c9-7f7db973e810 | note | Responsibility - SE/PE
cd83acc6-8ae0-5d87-9c7d-c893583394aa | note | Verifying Documents - This ITP Signed Off
b3a23587-8419-503f-b664-ea99c87e3927 | note | Attach: Approved templates
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Welding Procedures & Quality Documentation
aaba69f4-05d2-5428-9321-42127163f8c1 | note | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
734475a8-af79-5b22-abba-5c8c3cda45f6 | note | Acceptance Criteria - WPS (Welding Procedure Specifications), WPQR (Welding Procedure Qualification Records), WQR (Welder Qualification Register)
425a9e59-2cb7-5b83-a61a-d9eef58b645d | note | Method - Document review and approval
efe01f87-5582-5abf-90cf-f67c67a2f0af | note | Frequency - Once (Prior to Works)
8958a0f7-a56f-5693-839d-c3b0f2b831e1 | note | Category - HP
18293dc9-d1f4-553c-959e-379169a00dbf | note | Responsibility - SE/PE
380c35bb-94b9-5d6f-b2e0-e55451340c28 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
4dabfd9d-c4c6-5ff8-9e88-c937ac489e83 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
0cf5e364-1167-5d83-832e-a8aef1957b2e | note | Acceptance Criteria - Approved IFC Drawings
d4f6a194-29e6-5f5d-8f1e-3010fa9c6337 | note | Method - Document review and approval
5b7f9da6-8442-5b76-a732-83ead466b1a7 | note | Frequency - Prior to works commencing
c79495dd-2295-5fa8-89e8-cf54dd8293a1 | note | Category - HP
b0a1950e-8d52-5c2e-ac94-b353f0bc4bcf | note | Responsibility - SE/PE
9da4f458-ecfd-5e34-ac5d-ebfe2868e812 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction Activities
| checkpoint | 5.1 - Aluminothermic Welding
77a5b19d-9c04-5d62-903f-e46348edcd45 | note | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails
cb6e42b1-e155-504e-8028-31cd7d162627 | note | Acceptance Criteria - Verify Aluminothermic welding carried out in accordance with AS1085.20
3bfd4483-0a85-5cec-8e9d-26e5bc14895c | note | Method - Visual Inspection
d774bb77-465d-59da-aa78-dbb2608e82e3 | note | Frequency - As Task Progresses
a8c6eb36-6e1b-5dd6-be03-41d49663370c | note | Category - IP
e4e5d4ef-8c1c-5bef-b5f3-5d4937375ffe | note | Responsibility - SE/PE, Track Supervisor, Welder
af5a62ca-e429-5a25-a0cc-49a4a49e84d7 | note | Verifying Documents - This ITP Signed Off
246061af-468d-5e56-b88a-8d22da86acec | note | Attach: Site Photos
| checkpoint | 5.2 - Alignment of Welds
9defe191-4b77-5541-adc0-ba93734a6796 | note | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails L2-TRK-PRO-014 Welded Track Management Manual Chapter 11 – Rail Welding Process Section 4.9
d82000f2-8f02-565e-bbbe-b95d5bd37bc0 | note | Acceptance Criteria - Alignment inspection shall be carried out on each weld and record results.
a53b2e7d-f157-59ce-aca1-e6bdd2fad972 | note | ○ Horizontal Alignment ± 0.5mm
767dde22-b730-5674-ad39-5c929db8e743 | note | ○ Vertical Alignment + 0.5mm, - 0.0mm
d09591e4-86b2-5703-af7c-4bee916cdf78 | note | Method - Visual Inspection, Test & Measure
10a50898-76e6-56bc-a68a-bea64fbe2b15 | note | Frequency - Each Weld
45466e29-9131-50de-9edf-e965dbb5975a | note | Category - IP
a9ad5839-31e1-557d-8e90-c9327dc0eb25 | note | Responsibility - SE/PE, Track Supervisor, Welder
ec35ef48-751e-5988-80bb-10ebed9c0226 | note | Verifying Documents - This ITP Signed Off
668889cd-3024-5c1c-9e4e-e4c7dde084f1 | note | Attach: Inspection Records & site photos
| checkpoint | 5.3 - Welder's Identification Marks
175efab7-ffff-5bc5-b3f1-28f4621274ae | note | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A1340 Flash Butt Welding Specification Section 4.3.5
f457f5c8-9819-5d63-bc5e-557e779b571e | note | Acceptance Criteria - Stamp ID on the field side of the rail head adjacent to the weld.
c645f1dc-7694-572a-b20e-5cf6f7eb0b69 | note | Method - Visual Inspection
1c8c3bc9-3bd1-5e1c-8852-f2869ed2326b | note | Frequency - Each Weld
98cc2887-6d5b-5b34-b133-8bdbad968a63 | note | Category - IP
33d40d30-e569-5cf0-ad8e-d6ad4bc961ea | note | Responsibility - SE/PE, Track Supervisor, Welder
669d6256-0103-5c73-95ab-0785daa1305a | note | Verifying Documents - This ITP Signed Off
1fa8c13d-2b31-5ecf-b4b5-a928802bebb8 | note | Attach: Site Photos
| checkpoint | 5.4 - Stressing Track Lengths
af9b0b75-c770-512c-9957-9e50d614e0b0 | note | Reference - AS1085.20 Railway Track Material Part 1: Steel Rails A4200 Metro Track - Management Chapter 11 Welding Process Procedure Section 5 A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Table 7.
37f42ff3-ba1a-5ec1-b6e5-32068d8dcce8 | note | Acceptance Criteria - Ensure track lengths area stressing accordance with Metro Track - Management Chapter 11 Welding Process Procedure (A4200), Minimum Closure Length taken as 13. 7 meters if not Detailed in Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure (A4598) table 7.
ce5ea31a-ead5-5aa9-82bf-c7eb0910e734 | note | Method - Survey and Visual Inspection
122a1a01-e057-5def-b9f9-38d816c9dfc2 | note | Frequency - As Task Progresses
1054644b-fe54-59b8-ae55-9afc04f6758e | note | Category - IP
54457e8b-9b92-5068-aefc-2bc5dd1e3def | note | Responsibility - SE/PE, Track Supervisor, Track Surveyor
34694204-a2a1-5f99-a9f3-50ccd4d3bf72 | note | Verifying Documents - This ITP Signed Off
620f37e5-a66b-5e2c-8a0a-e83d2a8a314c | note | Attach: Inspection Records & site photos
| checkpoint | 5.5 - Stress Free Temperature
4e86b54d-44c5-508d-a175-f22096f23871 | note | Reference - A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 5.1.2
2d0f944a-d6e0-5e82-87ad-b7ee4b1c46f7 | note | Acceptance Criteria - The design SFT is 38°C and all stressing is to be carried out to this design SFT.
c45e9170-c2ab-5bb9-b9a7-84a5eafbb431 | note | Method - Test and Measure
07430550-8402-5b9e-8969-c93b3dc5c6b2 | note | Frequency - Each Weld
f9376b2d-7a31-585c-a446-89381e04abdc | note | Category - IP
b0393209-d3fc-5ce6-8095-0135fcdb51d5 | note | Responsibility - SE/PE, Track Supervisor, Welder
17fadfd2-7827-5d38-9bd0-932f4474522f | note | Verifying Documents - This ITP Signed Off
a9802f16-693e-5093-a521-1db03852c817 | note | Attach: Inspection Records & site photos
| checkpoint | 5.6 - Weld Ultrasonic Testing
a5ef3439-3744-5895-a4a9-2643280fbadb | note | Reference - A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2. A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.20
3dea3a76-398c-527b-b6e3-b9ead1657832 | note | Acceptance Criteria - Ultrasonic testing to be carried out within 14 days and in accordance with A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure
2b2f868a-3e21-534f-a25a-3eb099c91791 | note | ○ The cross section of the area of the head and web shall be completely scanned;
62fc6518-2275-5efd-b3ae-bcb57d7967d7 | note | – The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
12caa247-9cd5-5511-a412-1648e217f031 | note | – Welds shall be scanned to both directions.
655890f6-1fb1-5ef3-8e04-37f79239fe87 | note | Method - Inspection / Test
be5480d8-c6ae-5dbb-95c4-b23938e8e399 | note | Frequency - Each Weld within 14 days
11ff4101-938e-5cb1-babb-6b8ca410db0d | note | Category - IP
e1605b58-88d4-531b-baa4-cd131cce3f6d | note | Responsibility - SE/PE, Track Supervisor
b8cba7a5-de05-5bcf-86f8-7d6a856b5abb | note | Verifying Documents - This ITP Signed Off
4bde4e6f-7553-5660-a33f-79013ff0dc74 | note | Attach: Ultrasonic Weld Test Results
| section | 6. Post-Construction Activities
| checkpoint | 6.1 - Rail Stressing Records
5648cdcc-643a-55b8-b511-2daf2caa06a6 | note | Reference - A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.21
6cce3a71-7996-506e-be72-408f738d9f15 | note | Acceptance Criteria - Complete Stressing Recorded documentation
821bef16-38c4-5059-97b9-159ff438336d | note | Method - Measure and Document Review
bf282bbc-4a23-52b5-b5df-367dceed2f64 | note | Frequency - Each Weld
22eca657-71dc-5ecf-ae70-3633f8ca2245 | note | Category - IP
c2ccbc91-cc6a-50e4-8e5f-1f394128cf01 | note | Responsibility - SE/PE, Track Supervisor
39877237-e1ea-57e2-8f84-d30d7ab64903 | note | Verifying Documents - This ITP Signed Off
1aab2561-6cae-50fe-9c7e-ea5e657cfdf3 | note | Attach: Rail Stressing Documentation
| checkpoint | 6.2 - Track Certification
c71c2a51-1cff-5994-b055-a21e03e9b749 | note | Reference - MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
5a253c30-7453-5a23-8ed2-a2f2e1650ad3 | note | Acceptance Criteria - - Track Geometry Conformance Certificate - Track System and Component
bc0de364-ba1c-58ef-b085-3fd78bd72723 | note | Method - Visual Measure, Document Review
410936bc-5849-522c-a2e7-508bb67e9176 | note | Frequency - Once (upon completion of occupation works)
7ae0c743-da59-51f0-988b-e6f82b761f1e | note | Category - HP
11bcb115-f0bd-5818-aea4-389b5798ae18 | note | Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure
4713e990-222b-59fb-8ad9-05c1202d922a | note | Verifying Documents - This ITP Signed Off
3392af87-3b2b-538b-b83e-4bbd68639881 | note | Attach: Relevant Conformance Certs as per acceptance criteria
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - As-Built Drawings
b180d283-b19f-559b-84d8-37bc97057bb5 | note | Reference - As-Built Drawing Management Procedure (A8197)
4155f17b-cc7e-5b13-9e2c-65daffebeb5e | note | Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines and supplied the Project and MTM.
3279026d-6515-5704-9d8b-f7726545e8ed | note | Method - Document review and approval
04988c17-2fe4-545d-b9a9-6489feda4218 | note | Frequency - Once
bb28f5b8-8cee-5769-9501-93d13c2dc1f1 | note | Category - HP
8d836d83-009b-5723-9db2-1326af3d5483 | note | Responsibility - SE/PE
526ac78e-9f97-5abf-ad53-e8e756bc8b04 | note | Verifying Documents - This ITP Signed Off
a18d776e-5c64-57c4-968a-d39afaeaa052 | note | Attach: Redline mark-up drawings
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
e0fd3558-6d26-542e-9c31-a61512b42935 | note | Reference - MTM Quality Management Plan
b0e1b078-307f-5087-9a5c-38e1e6182aed | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f3042769-5219-5944-a164-e90cd1b7221f | note | Method - Document Review
9fb80c83-72d0-5b4f-b336-84f3fc77d1a9 | note | Frequency - Once, prior to closure of this lot / element / Work area
9d17d475-04d6-5530-8209-10ebeded7b5e | note | Category - HP
e0283e0d-d760-54c8-806a-6cc586c7c7f6 | note | Responsibility - SE/PE
e2019f85-dcf5-5581-b540-14129bcc7caa | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
dd9e38c0-c2be-5fc1-b0c1-3b66891feb5b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
65ecfe1e-ffd6-567e-9fd0-a72d6d05e6a9 | textbox | Name:
8750d4d3-1509-5ffd-b502-db1a740d5f28 | textbox | Position:
8338234a-4abf-545c-ace7-236901b492ba | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-139-RAIL-BRUNT-Track Construction Rev.0 | itp | ITP-139-RAIL-BRUNT-Track Construction Rev.0 | d315c8e6-fd80-41ea-9f8b-cb4d4ce4c0bb
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
526061e1-2500-52a9-ae2f-e6f3e1a99d22 | note | Document Title: ITP-139-RAIL-BRUNT-Track Construction
62c2101f-9027-59a4-ac46-648ceb9c3341 | note | ITP Description: Track Construction
160cc6c6-5da6-53a6-b385-fc2f80dfcb27 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
5da601f4-85f6-513f-a81b-1b168fec3d06 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
7ec15eda-9831-50a0-8786-34a3967436b4 | note | Revision Number: 0
88997f04-ef27-5942-a771-51d5a432a2c9 | note | Revision Date: 14/03/2024
9a623209-3e48-598a-84bb-b793d11734e7 | note | ITP created by: Mac Cameron
e25692da-34ae-5ce4-9680-db069c13d531 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
40305408-2d79-5ba6-b6fc-e91e58ede0cb | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
| checkpoint | 1.2 - Railway Track Materials – Part 1: Steel Rails
5996c0da-7186-56ea-8bd0-910adf53b244 | note | Reference - AS 1085.1
| checkpoint | 1.3 - Welding Rail Steels
5c0c9606-dc4e-54fa-be70-6dd58106363a | note | Reference - AS 1085.2
| checkpoint | 1.4 - Concrete Sleepers Specification
7e502bbc-cd3d-55ec-800c-ff8b3204bf7f | note | Reference - A1504
| checkpoint | 1.5 - Track Geometry Tolerances
fc15cf60-e2fb-5db6-99c5-92c4f1424caa | note | Reference - A1303
| checkpoint | 1.6 - Ballast Supply Specification
bb83fe05-d480-5ea8-947a-b7bafa0fa1c4 | note | Reference - A1341
| checkpoint | 1.7 - Transit Space Clearances
27e272e2-18de-5cad-b22f-a577939826e6 | note | Reference - A1536
| checkpoint | 1.8 - Track Design And Construction
6027a0cd-87c6-52ef-a531-25ed5f0e1887 | note | Reference - A1545
| checkpoint | 1.9 - Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure
945e048c-209f-5153-9c2a-e2f4c0f22109 | note | Reference - A4598
| checkpoint | 1.10 - Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure
97f52101-b9b3-5580-8dcf-64e233219514 | note | Reference - A4597
| checkpoint | 1.11 - Aluminothermic Weld and Stressing - Inspection and Test Plan Template
2e29eb7d-fa87-53ac-a347-0603639291d0 | note | Reference - A7949
| checkpoint | 1.12 - PTC Heavy Rail Track Construction Standards
e372573c-8109-5226-b3de-63c75bd90636 | note | Reference - N/A - no document reference number
| checkpoint | 1.13 - PTC Heavy Rail Track Construction Standards Drawing
abf75469-5542-5b3e-912a-ed01a03a04bf | note | Reference - F598
| checkpoint | 1.14 - Earthworks & Formation Specification
d7c3e350-0b10-5f1e-920e-1695effb859d | note | Reference - L1-CHE-SPE-178 (VERSION 3)
| checkpoint | 1.15 - Earthworks & Formation Standard
718e0bf2-6482-5d19-bdb2-8125978b97c1 | note | Reference - L1-CHE-STD-029 (VERSION 4)
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Supply of 60mm Ballast
2304276c-26a2-5543-a943-a1ddc86cbb20 | note | Reference - A1341 Ballast Supply Specification Section 4.2.2
d70ca206-7fe2-52d5-8695-3fd53fa9f8ee | note | Acceptance Criteria - The Ballast supplied must be tested and meet requirements in MTM standard Ballast Supply Specification (A1341) Table 3
f87f808f-19a4-518e-ab21-4bd0ff8cbaac | note | Method - Visual Measure, Document Review
76ea897d-e11b-5eab-a3f1-4a3a28c3c394 | note | Frequency - Prior to works commencing
4c61d2d0-8133-5dff-bfe8-c8f8e62aa1e9 | note | Category - HP
3f6b724b-8c31-524d-a0d5-ee931d2f8d6d | note | Responsibility - SE/PE
2947a865-f8d7-5c61-9927-1083a9feb5c8 | note | Verifying Documents - This ITP Signed Off
842bbbe8-a06d-505e-985a-7384097eec9f | note | Attach: Supplier Material Conformance Certificate, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Supply of FDCS Sleepers
0d6fa3ed-f706-5a6f-9ee8-bb51f94237ca | note | Reference - A1303 Track Geometry Tolerances Section 8.1.13 A1504 Concrete Sleepers Specification Table 2
ecd6ca6c-f20b-5b79-bdbc-7386c7f3bbeb | note | Acceptance Criteria - Sleepers supplied must be type approved by MTM and in accordance with the relevant standard.
dd8bcf88-7cdd-5c7d-8710-ba17c2fdfe05 | note | Method - Visual Measure, Document Review
fc6be3c8-54dc-5c30-bba7-202e531f8577 | note | Frequency - Prior to works commencing
9b9fd194-1564-5033-9cfc-3e5e1150534d | note | Category - HP
51524cd1-6026-5456-8c61-af8e2a5aadeb | note | Responsibility - SE/PE
c7b2aaf9-cf45-5c57-937f-9f904152b063 | note | Verifying Documents - This ITP Signed Off
b93a5033-6526-5ef6-aeca-e1946fe528dc | note | Attach: Supplier Material Conformance Certificate, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Supply of 53kg/m Rail
d28af1a3-eef8-55ad-a12f-4c58330e4f09 | note | Reference - One Steel Certificate, Flashbutt Weld Reports
0e374ed5-4070-5107-8c40-9733e5671b89 | note | Acceptance Criteria - AS 1085.1 Railway Track Materials – Part 1: Steel Rails AS 1085.20 Welding Rail Steels Section 2
61bfc69f-6dd6-5a13-9a73-2da6a623bd7b | note | Method - Visual Measure Document Review
fb64dc5c-ac09-5ae8-afe1-f53c02c97d40 | note | Frequency - Prior to works commencing
47c7b863-80b1-5dec-8b5f-95926f19d20c | note | Category - HP
eed4f827-f9e1-576d-940e-8cc169bc0283 | note | Responsibility - SE/PE
888b520e-cc4c-51c1-a96a-7b06d738e1ed | note | Verifying Documents - This ITP Signed Off
ddd87030-38d9-5ed6-9469-ed0256a4cf2d | note | Attach: One Steel Certificate, Flashbutt Weld Reports, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Supply of: Track Jewellery, Geofabric
a594b07d-3f1e-5bc9-9e21-b8592673eca0 | note | Acceptance Criteria - To be type approved by MTM.
b1ad3089-7ecf-56b0-9cbe-4925cb0f5464 | note | ○ To be inspected upon delivery to have no damage or rust.
788e5ab2-ba35-5b17-bce2-574f601d2e99 | note | Method - Visual Measure
3b6cdb31-8524-5377-a84e-c5604756dacd | note | Frequency - Prior to works commencing
d923260b-bab0-51f8-9c71-2f4db1bacef9 | note | Category - HP
0105dff5-a69b-51dc-9d00-b0da944172d6 | note | Responsibility - SE/PE
a92c98af-c08c-5f2b-8c6f-c042b9d000d4 | note | Verifying Documents - This ITP Signed Off
bc9cfe92-032b-5c82-b78e-cb006b86131b | note | Attach: Supplier Material Conformance Certificate, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Primary Documentations
4d3a576f-1aab-504b-9895-1f39c608e42c | note | Reference - A4263 PTDT Form B - Track Certifier Booking Form A1606 Hot Works Procedure
4c087173-e944-5053-ac57-c79f74d66a56 | note | Acceptance Criteria - Approved PTDT
001976ee-a6e9-5b8d-b616-93050d36f7e8 | note | Method - Document review and approval
c51025e1-d061-56ed-a7ab-4dfc250311ad | note | Frequency - Prior to works commencing
d025949c-a19a-5e3f-96ac-6076c47e6364 | note | Category - HP
1b0f51bf-99aa-5497-ab37-b4cb418dffa4 | note | Responsibility - SE/PE
6cb5abba-fc4c-5b43-abed-16cc1d7d9095 | note | Verifying Documents - This ITP Signed Off
2fa2dc7e-b517-5dc3-8fbf-828412c60e89 | note | Attach: Approved PTDT
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Pre-Commencement of Work
d03b1b4a-4dc9-537e-8803-8450d459cf87 | note | Reference - ITP, Quality Checklist, SWMS
f9f439b7-25c2-52ef-bd41-1ec2de18c426 | note | Acceptance Criteria - All approved by relevant representative.
4904f2fa-ac00-5f6f-8b3f-a0ec8e246373 | note | Method - Document review and approval
0f38b38c-989f-53b1-9112-9a4e981d91cd | note | Frequency - Once (Prior to Works)
6e48d4c7-8cb8-57b9-9a63-1bfef75c3d42 | note | Category - HP
157e2656-a862-5de1-8ae1-3aa038aa089e | note | Responsibility - SE/PE
5de3a909-bc92-5776-8181-d731bc46eed3 | note | Verifying Documents - This ITP Signed Off
83e095cf-05e8-5e83-8a67-ddd0db802287 | note | Attach: Approved Templates
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
bca0c3e1-9e60-57e0-8635-d97406a86ce2 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
ff8cb91e-7494-5dd6-be72-d2e5587d3a96 | note | Acceptance Criteria - Approved IFC Drawings
f9ed70a0-daae-57b0-8150-980edff70fdd | note | Method - Document review and approval
c0a569a7-ec63-574c-a829-ff799878ea0f | note | Frequency - Prior to works commencing
3892db8b-b0d5-5571-91c1-eacc98deb7ae | note | Category - HP
32b9abae-487e-5b15-a2ca-b6f44ece9ca5 | note | Responsibility - SE/PE
476adf08-42bb-5df4-b59e-8dc3def45cf2 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction Activities
| checkpoint | 5.1 - Survey Track Alignment
c208d2ed-a649-5233-8a26-ac84abacc9f0 | note | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
dd6db59a-66b9-50e7-82d8-e8b71bb13015 | note | Acceptance Criteria - Correct line and level established for placement of Sleepers and Ballast as per IFC.
8b7d58ab-34f9-585d-9577-b432876ef712 | note | Method - Visual Inspection, Survey / Measure
a2c9c32a-1ca2-5c4d-b665-719e811b33e9 | note | Frequency - As Task Progresses
4489c889-49f8-54be-9465-432618af51c7 | note | Category - HP
b736507d-54da-53e5-9e41-8d5119a2a0bb | note | Responsibility - SE/PE, Track Supervisor, Track Surveyor
2a8c1ec4-4ef1-5984-a431-a0e1928d7555 | note | Verifying Documents - This ITP Signed Off
7f57eef2-ab6e-505f-b3c4-5ef0647a7152 | note | Attach: Survey Records & Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Lay Bottom Ballast
371df3c0-6b87-54b8-b2d5-21c49e6a7940 | note | Reference - PTC Heavy Rail Track Construction Standards Drawing F598
f6e0e574-1ca0-5ab3-a77c-1eda40c3e825 | note | Acceptance Criteria - Ballast to be placed in 150mm max layers. Bottom Ballast to be left 20-40mm below final design level – Tolerance (under sleeper) -0mm, +25mm
e5ed0f8e-70de-59ea-9a21-972f6fdf36a4 | note | Method - Visual Inspection Survey / Measure
61cd17d7-2946-53b9-b9c2-8aeef43801b1 | note | Frequency - As Task Progresses
ee07403e-c5a9-55d9-ac0b-0d12725c7314 | note | Category - HP
cf8b818e-820c-5e73-acbf-5b9901fbf99d | note | Responsibility - SE/PE, Track Supervisor, Track Surveyor
3db0f1de-dd4b-5a0e-b9f9-ba8a5a2ad3bf | note | Verifying Documents - This ITP Signed Off
26a407e8-9ae7-52f3-b107-ebe8965dfa6f | note | Attach: Survey Records & Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Place Sleepers
c7b0d2e0-88a0-5aae-b9a4-aae8d021a46e | note | Reference - A1303 Track Geometry Tolerances Table 1 A4597 Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure Section 4.8
740a92d3-b76d-516c-b1b7-d3eb32c3be46 | note | Acceptance Criteria - Sleepers Square at nominal 685mm ±25mm.
5092f1c6-72ac-5ede-8520-8baf95a81cc0 | note | ○ 2 concrete sleepers either side of welds
f8f110ae-6106-5ef1-8890-abcfe537f042 | note | ○ Up to 50mm variation in spacing to allow for clearance around a thermit weld (only over two sleepers)
bddd1195-ed4c-5a09-9961-91881b800bff | note | Method - Visual Inspection, Survey / Measure
d16134c2-84c7-57eb-9817-1afe8f377c7b | note | Frequency - As Task Progresses
25adf026-ef36-567a-9005-4cc8faed9b7d | note | Category - HP
b8da51f6-9968-56bc-a63f-0c68fb939c48 | note | Responsibility - SE/PE, Track Supervisor, Track Surveyor
45a9c880-f5cc-59e6-a5be-0d80c81493b6 | note | Verifying Documents - This ITP Signed Off
ff7fa838-53fa-5c02-acc3-3a23a95d1c6b | note | Attach: Survey Records & Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Rail Installation
f4803e85-dbcd-5204-90bb-ec114acd5cb6 | note | Reference - A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Section 4.1.1, 4.1.2 and Table 7 Aluminothermic Weld and Stressing - Inspection and Test Plan
4100e9c9-9201-5ede-865b-7bb5afa9c65d | note | Acceptance Criteria - Plain line Aluminothermic welds square and centrally located in beds.
4a58f4a1-5edb-5821-b534-faf343629cce | note | ○ Alignment inspection shall be carried out on each weld and record results.
d2aea119-0e9b-5986-8bf0-66721e043c34 | note | ○ Horizontal Alignment ± 0.5mm
14259091-8a14-5e39-920f-f6b94da33b3c | note | ○ Vertical Alignment + 0.5mm, - 0.0mm
e7d3c359-6925-5ddf-a21f-ad3cd430ed49 | note | ○ Rail ends identified & clearly marked for visibility of joint.
bcf39fde-6ead-56ba-b80d-d027ada3c333 | note | ○ All fastenings must be fully applied.
ce058424-92f3-54f5-bad5-da17c69d81fc | note | ○ Minimum Closure Length taken as 13. 7meters if not Detailed in A4598 table 7.
61c504b6-70c6-5cf1-ad05-e41d9e645edf | note | ○ Complete Aluminothermic Weld and Stressing - Refer to Aluminothermic Weld and Stressing ITP
b95fba4f-4f26-5c18-b2dd-90426478176e | note | Method - Visual Inspection, Measure
3549b26c-f95f-5800-be84-cb0e21815cc2 | note | Frequency - As Task Progresses
454cc8f5-ccca-5296-a3db-f40f79fafa25 | note | Category - HP
731fa07a-4751-5f0d-a141-d516a8f10e37 | note | Responsibility - SE/PE, Track Supervisor
8c85a569-8231-5606-85ea-b6c043789ccb | note | Verifying Documents - This ITP Signed Off
00fa1f72-daab-574a-ad4c-65cf71a30b8d | note | Attach: Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Sleeper Alignment and Rail Jewellery
9fe8e677-34f7-56d9-a795-e8b8e94a77e6 | note | Reference - PTC Heavy Rail Track Construction Standards Drawing F598
0aefb9e8-7075-5821-a1a5-dd0905b9a22a | note | Acceptance Criteria - Sleeper alignment complies to square with centreline for tangent track.
f965a6f1-6c6b-5194-8905-472c9f5a4e9e | note | ○ Rail jewellery secure and installed correctly
f8602e4a-5c69-5716-88af-3dca804fa9d4 | note | Method - Visual Inspection
aac0722f-8163-5807-8531-af85f5d3be9f | note | Frequency - As Task Progresses
764f68c7-7a91-5a69-a18f-29a196110e3d | note | Category - HP
fd9a46fa-93d5-59a4-b376-2c617a6a4f3f | note | Responsibility - SE/PE, Track Supervisor
b825caf6-a890-571a-827c-ae11d797d189 | note | Verifying Documents - This ITP Signed Off
860502bd-5eb6-50f9-8473-eb61de996ee4 | note | Attach: Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Tamp New Track
333ecc17-0280-5b53-adbf-001d10d67a9f | note | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61 A1536 Transit Space Clearances Figure 1 and section 9.2
f2fc81f7-a5d9-5de2-90d5-b27472a522f1 | note | Acceptance Criteria - Tamp track as per IFC design and within below tolerances:
0e7ab68b-fbd2-5837-afe3-666e7e571529 | note | ○ Gauge +3 / -3
ba53d8e5-c563-5ff9-ba07-eeeecfdbc7f2 | note | ○ Gauge Variation in 2m 4
1550be46-3cf9-5972-9ab1-32689a166fb7 | note | ○ Line (10m Chord) +4 / -4
8e22e2c1-8d2e-52e7-aa98-6556d11e3085 | note | ○ Twist (3.5m Chord) +2 / -2
bbec0c4c-4e75-5321-98fb-bc6ca7586bea | note | ○ Top (10m Chord) +5 / -5
da9f6df0-934c-5101-869d-2fce952fe1c4 | note | ○ Cant +5 / -5
c08801a3-da52-5def-a7f7-558be96e5e42 | note | ○ General Alignment +15/ -15
f99c3d9e-7139-5e52-b25f-baa1a443fa65 | note | – A minimum horizontal clearance of 3.0m from track centreline to structure.
ebab7e7f-1fdc-500f-a62b-241fd59a4110 | note | – Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
a8c9583a-1889-5bfb-b318-39942fbab696 | note | Method - Visual Inspection, Tamping Geometry Recording, Measure / Survey Pickup
f7b71a10-bad4-5eb9-bb8f-96116e4a03ff | note | Frequency - Once (Post Tamping)
5be4037f-cacf-539b-9df0-0bd5fb20caba | note | Category - HP
e013547f-e6a6-5bff-9f0e-f160e3e64acd | note | Responsibility - Tamping Operator, Track Surveyor, Overhead Engineer, Track Supervisor, SE/PE
a786b7d5-a7a3-58eb-8b28-051c69c67668 | note | Verifying Documents - This ITP Signed Off
a1d67cd1-017d-5061-b577-a6386da07c13 | note | Attach: Photos on site, Tamping Geometry Report, Survey Records
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.7 - Regulate and Check Ballast profile
b4e355cc-ed79-5f0f-8d93-ab67b0295e52 | note | Reference - A1537 Earthworks And Formation Standard Section 9 PTC Heavy Rail Track Construction Standards Drawing F598
68542f04-f3e8-57e0-b905-fa28d3511de8 | note | Acceptance Criteria - As per IFC drawings; 405mm from sleeper end tangent track
e272f8bc-0f14-5bf8-ace8-2301551ac08a | note | ○ 1 in 1.5 steepest shoulder slope.
20c30a5f-8241-5f40-b8ae-2319c60035c1 | note | Method - Visual Inspection, Measure
711f16aa-22c8-50a2-8907-d157ed82ca4c | note | Frequency - Once
a4d1b69e-b04a-52c3-b07a-aa4354b2856e | note | Category - HP
3946637f-45e4-5264-8434-1ce9478de969 | note | Responsibility - SE/PE, Track Supervisor
9b269e55-11ba-5591-b70d-894a18239d5a | note | Verifying Documents - This ITP Signed Off
9496cb06-6258-50e8-8ca3-7f8739b44037 | note | Attach: Photos on site
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-Construction Activities
| checkpoint | 6.1 - As-Built Survey
da609be4-4e29-5200-ad64-53843678b6c9 | note | Reference - As-Built Drawing Management Procedure (A8197)
c19c00c2-127a-5624-9eae-09833e6dc259 | note | Acceptance Criteria - Track survey to be carried out at completion of works. Track levels compared to IFC and ensure tolerances are met
d3bb4b48-2ada-5c85-b5e7-0a85ce335222 | note | Method - Survey and Review
1d1fe867-066d-5e60-bd35-0b1a3ce18886 | note | Frequency - Once
7008e354-1c85-507c-9298-869c5f272811 | note | Category - HP
172fdb45-9618-5ae1-9b39-167537404ff3 | note | Responsibility - Track Surveyor, SE/PE
bd440200-e31b-5d0b-9532-b9da3ce178d4 | note | Verifying Documents - This ITP Signed Off
4366f194-fae6-585b-b647-4b3da92b428c | note | Attach: As-Built survey report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Track Certification
909f5c03-9ec4-5040-873f-56dc6c783eec | note | Reference - MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
b9780b32-053f-5142-98c7-86bc8b4233b5 | note | Acceptance Criteria - - Track Geometry Conformance Certificate - Track System and Component
f3a80a1d-5822-5ac5-9e28-7436171e0db0 | note | Method - Visual Measure, Document Review
0599bf41-cd5b-588c-b72e-61fe9a026fdd | note | Frequency - Once (upon completion of occupation works)
df177352-b286-5aed-9715-d56266c9cb18 | note | Category - HP
e6fffa49-25c1-51f8-ad1d-1afbee5eb9d8 | note | Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure
504f435d-c456-5555-b732-ddfa3ff636da | note | Verifying Documents - This ITP Signed Off
f4deb045-2bba-5da5-83ce-773c3c9a9cf5 | note | Attach: Relevant Conformance Certs as per acceptance criteria
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - As-Built Drawings
bf7a8847-b0f9-501a-a64f-f647d16905b4 | note | Reference - As-Built Drawing Management Procedure (A8197)
fa57a8ee-7f78-5f8c-acee-d60198cc36a0 | note | Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM.
90699978-47c8-5876-920d-252062cfb0c7 | note | Method - Document review and approval
fbf3173c-9c62-502f-991c-30eba4b0b5b1 | note | Frequency - Once
99d89467-fa48-5ee3-a02f-232c550e69e2 | note | Category - HP
e2e0a6b9-41c2-5761-8c8c-75d3d6159f77 | note | Responsibility - SE/PE
e8b851b5-98af-59be-9a3d-6767aa88a96e | note | Verifying Documents - This ITP Signed Off
3ba99d22-2946-5bd4-ab52-bdec77e3c868 | note | Attach: Redline mark-up drawings
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
95bc872b-0cdb-54c6-b8bc-253b27ee28fa | note | Reference - MTM Quality Management Plan
d89f1e07-33bf-542b-ad45-d64d44164e29 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
17342eb4-a3ce-5d9b-bbd4-bd5f75b6a28f | note | Method - Document Review
5cfcc6cb-de7e-5750-9edd-89e8277534a1 | note | Frequency - Once, prior to closure of this lot / element / Work area
69fe8f5e-26f3-535d-a98a-8d5492e0898c | note | Category - HP
194baed7-6eb3-5065-b8be-b7603c04b792 | note | Responsibility - SE/PE
683f2672-540a-5bcf-8a80-b7206e2355d0 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
46e9085a-8c65-5961-b658-3d80b2687c12 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c3e4259d-f767-5c1b-bac4-2b5cae24c4e8 | textbox | Name:
5eecb0a6-6c98-592e-9d35-b0c60425857b | textbox | Position:
99c0e5e9-6c39-5efa-bde8-0f0a5838eb81 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-140-RAIL-BRUNT-Track Formation - Capping Layer Rev.0 | itp | ITP-140-RAIL-BRUNT-Track Formation - Capping Layer Rev.0 | 9ccd1b7c-8092-43bd-8495-512570ce9c16
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
c547c59e-4714-5782-bd12-623672364edb | note | Document Title: ITP-140-RAIL-BRUNT-Track Formation - Capping Layer
a6c94aa6-9fba-509b-b6f6-12cdf0231682 | note | ITP Description: Track Formation - Capping Layer
2690d106-1714-5eef-8e99-ddc15a203259 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c54b1294-2be8-5557-87e5-a6aeb0b8c4f1 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
a2964450-a135-526a-828d-3723bee55fa0 | note | Revision Number: 0
52a835a6-f363-5beb-b82f-25bd4c4dd69e | note | Revision Date: 14/03/2024
64e59203-45db-5ae3-a8a6-d8f294b25aa8 | note | ITP created by: Mac Cameron
0a5374f9-5052-501b-99f6-19a9702e64f2 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
8597606f-a6a8-5ed4-b83e-d91a62e71883 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
| checkpoint | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification
7fcb8fb6-60e5-56de-8956-de6d864d1cff | note | Reference - L1-CHE-SPE-178 (VERSION 3)
| checkpoint | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard
62d19f2d-4570-579d-9fcd-7f89b9602a5a | note | Reference - L1-CHE-STD-029 (VERSION 4)
| checkpoint | 1.4 - Australian Standard - Methods of testing soils for engineering purposes
35ba120c-8052-585c-b594-8bf410937fb6 | note | Reference - AS 1289
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Capping Material Conformance (1 of 2)
6f3425ac-354e-5542-9f9b-fa5940f861c8 | note | Reference - L1-CHE-SPE-178 - Clause 5.12.3. Table 6
bb39dc1f-4f92-5c66-88ab-506396f22cf8 | note | Acceptance Criteria - Capping material shall comply with the following grading requirements:
328a372b-c613-5cfa-ab86-d700de72445c | note | ○ % passing 53.0mm sieve 100%
a564902a-664f-50bc-9afb-13f1ed2a3929 | note | ○ % passing 37.5mm sieve 100%
aebc7061-0606-5c95-aa65-9a6eee8a8d44 | note | ○ % passing 26.5mm sieve 100%
bc64ee22-9282-56f3-8be8-3d58e2c96ac1 | note | ○ % passing 19.0mm sieve 95-100%
a8249a17-bf3e-511e-a55d-690cf0422143 | note | ○ % passing 9.5mm sieve 60-90%
63ce7093-b91c-50a6-bbcd-f3655d5a7d0a | note | ○ % passing 4.75mm sieve 40-70%
60dd04c9-9716-5d4f-a735-fce69a7d8158 | note | ○ % passing 2.36mm sieve 30-60%
d305eb40-edce-57d8-9054-e69426b852d6 | note | ○ % passing 0.075mm sieve 6-10%
ac554834-b5a9-543a-9b4a-85c71b7b43a5 | note | Method - Document Review
0c1a5107-b954-5b9f-8cf6-12aa88bfb7b4 | note | Frequency - Once, for each material type - prior to works commencement
bb0f5853-8b63-58e2-952e-1ca730cda49e | note | Category - HP
9d90bfab-9e98-57c1-84c0-ca468d843368 | note | Responsibility - SE/PE
2fe56e62-aefe-50a2-bd6d-cba35bec60c7 | note | Verifying Documents - This ITP Signed Off
6b7c70e5-c613-5f54-a7d1-e24b694fa73b | note | Attach: Supplier Material Conformance Certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Capping Material Conformance (2 of 2)
4f362acd-9554-56a6-af67-94bb16136e0e | note | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
75f7de10-a152-575a-b340-61a4f13e5666 | note | Acceptance Criteria - The following tests shall be carried out on samples of the capping layer material:
21dca5a5-2b5b-57e8-922b-5454baf86284 | note | ○ Soaked CBR - minimum 50% compacted to 98% modified dry density
99971f98-17a8-58b9-b55f-1cf9c2da9388 | note | ○ Liquid Limit - 30% Max
789f780b-a801-597f-ac8b-d1a48aba19bc | note | ○ Plastic Limit - 20% Max.
1d8a0d3c-27a2-5586-aa78-9ccfac9ca7af | note | ○ Plasiticity Index - 4-15%
4180bc35-0720-5127-b9c2-706ebb818546 | note | ○ Linear Shrinkage - 4.5%
72128f70-2c4d-51b8-b5a9-2eb44131152e | note | ○ Dry Density - 2.0t/m³ MIn.
e45711f8-4ba6-53e1-93e6-4ab3414ca616 | note | – Refer to AS 1289 for Tests
6c1e8c0c-32e5-5443-b53b-33a1cd853658 | note | Method - Document Review
199fe864-4a86-506d-ad7e-78781aac31d7 | note | Frequency - Once, for each material type - prior to works commencement
97e35270-f763-52d3-b4c3-48fd69d98fb2 | note | Category - HP
6fa640d1-2eff-50b4-8398-69b727da4ddf | note | Responsibility - SE/PE
4036284c-4555-50ab-a5c3-7bb2ae519286 | note | Verifying Documents - This ITP Signed Off
ad9453d5-e3fc-55c2-9471-c4c76ddc8603 | note | Attach: Supplier Material Conformance Certificate
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Pre-Commencement of Fill Works
f6a81020-b23c-5795-bc7a-6955c6863899 | note | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
790a7810-24da-585d-8cf4-7a1310686f9b | note | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
db27d409-4083-5c67-a054-1f7628bc8c16 | note | Method - Visual Inspection
f2e4c8a2-8580-5f0e-aba2-d1bd94f50d2a | note | Frequency - Prior to commencement of fill works
78c94a9d-68cd-5c7d-81b3-4710966ae36a | note | Category - HP
29e230da-e70b-592d-bca3-ddbbe19398bf | note | Responsibility - SE/PE
9d27fabd-118d-56b9-a39f-796f162ca36c | note | Verifying Documents - This ITP Signed Off, MTM representative signoff
5c388c90-589f-53de-8c2b-904b4f4be12c | note | Attach: Site Photos
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
35ad7215-88d7-5ac4-afb4-662dfecf318f | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
fbcd2207-6beb-503c-b390-bfd022261575 | note | Acceptance Criteria - Approved IFC Drawings
564f1b78-c7c8-5fe7-9eb7-3708102d1ecd | note | Method - Document review and approval
e995bd71-afe9-5b73-b71a-f05c03ca6783 | note | Frequency - Prior to works commencing
172c1022-dfb4-577f-af4b-dc041076f0c4 | note | Category - HP
7304342d-31a0-55d1-b9b6-552fc8f69b6b | note | Responsibility - SE/PE
22c17001-0d44-5bf7-b434-e8bebe0b2157 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Survey Set Out
002ab2fa-560f-5c9c-9a51-ca6caa47d589 | note | Reference - IFC Drawings
3fe47b0f-1ed8-50bf-acba-b9c9f6e07cf7 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
b145e4ea-9a40-51d1-8c91-a2aacea63101 | note | Method - Visual Inspection
3d04fa63-743d-593a-a515-5ea31e6325fe | note | Frequency - Prior to commencement of fill works
2fc04f46-b988-5901-b50e-3d4d4379e260 | note | Category - HP*
4233978a-6c42-5897-9cd7-935a80afdf66 | note | Responsibility - SE/PE/SPE
f7593896-4746-53ce-ade9-45b6835300b2 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Capping Layer Preparation and Installation (1 of 3)
8e70afaf-42af-5a60-a4d2-9c622d15fdb5 | note | Reference - L1-CHE-SPE-178 - Clause 5.12.4.
fb20e487-2e9e-5b5d-8e2c-f2a3a9cb561b | note | Acceptance Criteria - Capping layer shall be constructed in one layer and compacted to a total compacted thickness of no less than 150mm.
fc32cdca-fc00-5487-9180-751cc6f223f0 | note | Method - Visual / Measure, Review Test
abe0edd6-6707-594d-8ab2-70f22561f03a | note | Frequency - Each Lot
3a896968-08e3-553a-8594-de3d976b184b | note | Category - IP
e81aeb87-0071-5033-9645-4c944977b4cd | note | Responsibility - SE/Nominated Authority
090af8fa-ad3a-507c-91f8-4251281ec259 | note | Verifying Documents - Sign ITP Signed Off, MTM representative Signoff
| checkpoint | 5.2 - Capping Layer Preparation and Installation (2 of 3)
9018bc84-4c98-5998-b751-9b4748af6968 | note | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
8ddb8258-0499-5926-8732-2a16a3231ccd | note | Acceptance Criteria - The following tests shall be carried out on samples of the capping layer material:
7f6947bf-c6d9-5266-a67b-4ab2fb97406c | note | • Soaked CBR - minimum 50% compacted to 98% modified dry density
503f1b8f-88cf-5290-9c67-768a3a4c40e3 | note | • Liquid Limit - 30% Max
0570ef10-6ea6-5540-bc8c-4f6823a01171 | note | • Plastic Limit - 20% Max.
db2ca3b6-43c5-588e-92a4-e9d7e4b81b48 | note | • Plasiticity Index - 4-15%
4c6176f5-291b-543f-8894-ba68f938bb79 | note | • Linear Shrinkage - 4.5%
e7443115-eb7e-56ce-88ea-121025c797cf | note | • Dry Density - 2.0t/m³ MIn.
467b2f3d-53ca-5e41-99ed-6c7b2f700c38 | note | Method - Modified Compaction Test
ca7d620e-9a7f-5fc7-b43e-775b4bea90c4 | note | Frequency - Each lot
551602e2-b31f-5df6-bd15-980b1d0bb53a | note | Category - HP
8fe72026-c957-593a-9f37-7e4a74a54633 | note | Responsibility - SE/Nominated Authority
92cfc730-f54c-5c36-80a2-186e4bf626ce | note | Verifying Documents - This ITP Signed Off
3f001245-195c-559a-852e-00a59657bc95 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Capping Layer Preparation and Installation (3 of 3)
3425ed07-96b0-5132-b7d9-74bfd1032d0b | note | Reference - L1-CHE-SPE-178 - Clause 5.12.6. AS 1289
2c4edfa5-faae-50a0-a0d7-d5105dc1fa39 | note | Acceptance Criteria - 99% Compaction (Modified Compaction Test)
086abcad-96a9-533e-beac-837a3e26ed67 | note | Method - Modified Compaction Test
ae6019ac-d99b-5ca9-8178-cf09ae6e2f3b | note | Frequency - 3 tests per 500m³
8cae8dd3-8f69-5daa-9283-b0d7df115777 | note | ○ atleast 2 tests if < 500m³
6e9144fb-30e8-5f51-ab59-9cd879ca5356 | note | Category - HP
078d5255-89a0-56db-8142-fd286fdf0c57 | note | Responsibility - SE/Nominated Authority
b4f899d4-f7e9-5ff0-b3f0-954e38200d94 | note | Verifying Documents - This ITP Signed Off
3d6dbca4-31bf-5bc7-8111-0e13bdf0f7d9 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Proof rolling
e8178bd2-a259-5936-a61b-d6f6cbcacac6 | note | Reference - L1-CHE-SPE-178 - Clause 4.6.
efaec864-b4ae-57ca-84c6-af8003dbbb15 | note | Acceptance Criteria - Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
06aa3ae1-0d65-57ca-a06a-98fd891b0d9d | note | Method - Proof roll
f5471aaa-44c7-553e-b424-8e8a1be4d07c | note | Frequency - Each Lot
3c269079-07d6-598b-889d-a146aead4b04 | note | Category - HP
3fedc58d-810d-58a6-9caa-d60aefce0513 | note | Responsibility - SE/Nominated Authority
d372c5cb-d41e-5eea-9c1c-cbbca966c35e | note | Verifying Documents - This ITP Signed Off, MTM representative Signoff
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-Construction Activities
| checkpoint | 6.1 - Survey Conformance / Capping Layer Finishing and Tolerances
b37b98f2-f6dc-5aef-9b9e-4da47d10a6cd | note | Reference - L1-CHE-SPE-178 - Clause 5.12.7.
88261dfb-43f4-5ef3-b217-e2d71e200d45 | note | Acceptance Criteria - The finished surface level of capping layer shall:
ac869425-787e-5483-a02e-f930341bd950 | note | ○ Be within -25 to +0mm of approved design level
73a40175-ca28-5cdd-98b9-08fc735b139a | note | ○ Be within 10mm of algebraic difference of the deviations from the correct level for any two points 20m apart on the centreline
65fe1cb9-716c-54ff-8f2b-3e3ed80902c7 | note | ○ Be within -0mm to +10mm of 3m straightedge laid on final capping layer surface parallel and perpendicular to centreline
6c1ccfb2-1b12-524b-9ce3-882f94728b50 | note | Method - Document Review
2eddb429-83c6-57f4-bbc0-4b79015581fa | note | Frequency - Each Lot
d9e0b447-5973-5bc2-b930-5c8a5239b6d6 | note | Category - IP
8ea5e545-0d8c-533a-83e1-9116946abe7b | note | Responsibility - SE/Surveyor
6db2c065-3c71-5067-a57d-dc40d2b86714 | note | Verifying Documents - This ITP Signed Off
7dfbcd7e-d463-57e7-96d0-50dde4c6be61 | note | Attach: Survey Conformance Report
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
f10f4fe9-f7e2-56f8-bcc9-d8922951ba53 | note | Reference - MRPA Quality Management Plan
c28cf5b9-3381-5f27-83e4-0aabd8735c41 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
c61e566c-741f-5008-b5fa-c96a6932e9ca | note | Method - Document Review
13629be4-5238-593a-bc77-7f19026a7fc6 | note | Frequency - Once, prior to closure of this lot / element / Work area
1b0a9d71-5638-57e1-9c76-70656ee5d6d4 | note | Category - HP*
0ea8519c-59c1-5751-bc62-e4890ac1ef97 | note | Responsibility - SE/PE/SPE
7cadec1b-191e-55f1-8484-e4174be225b1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
fa1f5689-afff-5125-91f0-66dfb0aad8b0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0246940b-47fa-586b-9a34-39de9d568275 | textbox | Name:
65c8931a-2f03-5133-a353-9d716afa08a9 | textbox | Position:
8873a999-c54d-591a-84e1-51514babe1a5 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-141-RAIL-BRUNT-Track Formation - General Fill Rev.0 | itp | ITP-141-RAIL-BRUNT-Track Formation - General Fill Rev.0 | 4599e879-2e2d-42fa-ab7a-49c2c8340473
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
6683489d-db47-5b02-be54-011b9ec15cbf | note | Document Title: ITP-141-RAIL-BRUNT-Track Formation - General Fill
1b95edd9-367e-51d4-8e45-abe9fbd34695 | note | ITP Description: Track Formation - General Fill
4112c851-1308-592e-a1c4-15226edc3bf1 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
617ae565-3d2c-5eb6-bfd7-05dabb08dcb3 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
ff50c646-5c51-512e-89eb-329cbff21f79 | note | Revision Number: 0
ff654ebd-cfc0-5675-a2d8-6040be153530 | note | Revision Date: 14/03/2024
f5fc246c-1b49-513b-bb50-3c66ded14e6c | note | ITP created by: Mac Cameron
2f3d31e0-f505-5831-bc29-a94351f4016e | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
16a33697-d760-5b9e-8b45-6c40582f2871 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
| checkpoint | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification
2548dc3e-0777-559d-ac39-5e5f615fc18b | note | Reference - L1-CHE-SPE-178 (VERSION 3)
| checkpoint | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard
e99d75c5-6b63-51c6-acd5-671212458a5c | note | Reference - L1-CHE-STD-029 (VERSION 4)
| checkpoint | 1.4 - Australian Standard - Methods of testing soils for engineering purposes
e8f0f596-f29c-572e-967f-eab88d6e08a6 | note | Reference - AS 1289
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - General Fill Material Conformance (1 of 2)
df445cc8-e359-5202-8696-d3d69734c277 | note | Reference - L1-CHE-SPE-178 - Clause 5.10.1. Australian Standard - AS1289
dbdd90d8-7907-591e-b82f-00ca28e80c89 | note | Acceptance Criteria - General Fill shall consist of suitable material that shall be compacted to a minimum characteristic value of density ratio 98%
b0c7ead1-f9fa-58c7-b206-0f3cb91a7f40 | note | ○ Refer to AS1289 for tests
69a1f378-aaaa-5e2c-b61d-0b04d9537aa5 | note | Method - Visual, Review Test
58426f62-1a19-50d5-9d39-b285a551f835 | note | Frequency - Once, for each material type - prior to works commencement
3a5f82c7-60ac-5d26-914c-e070811d5a07 | note | Category - HP
f969a2d9-2cf9-54dd-892b-8745d04a87b2 | note | Responsibility - SE/PE
f9793bbe-c675-5b3d-b040-8b7c2b5829b3 | note | Verifying Documents - This ITP Signed Off
a155f6a3-352b-5651-93fa-79e7572b294a | note | Attach: Supplier Material Conformance Certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - General Fill Material Conformance (2 of 2)
3874d98c-dfb2-5bce-8782-ecf27750e7a1 | note | Reference - L1-CHE-SPE-178 - Clause 5.10.4.1. Table 1 AS 1289
23c0ef51-a54b-5f07-92ef-8fed16e2ca2e | note | Acceptance Criteria - General fill shall comply with the criteria listed in Table 1 (L1-CHE-SPE-178 - Clause 5.10.4.1.):
77893f8b-a1b8-58d2-9905-8c9c08c2e945 | note | ○ Soaked CBR - 3% min nominal
527eb8a3-0fe3-5b86-a74e-39a2e3a426ae | note | ○ Plasticity Index 9-20%
8813795b-0353-56d0-960e-9150e93944be | note | ○ Dispersion (pin hole dispersity) - ND1/ND2
80c5e7bc-969d-547f-9ff5-e57342743b18 | note | ○ Dispersion (Emerson class number of soil) - not to be class 1 or 2
c0c28dbf-201e-5f36-866b-a38906bf07ed | note | ○ Collapse strain - to be agreed by MTM geotechnical engineer
b89a3b31-fe6c-52ae-ab88-762681a7d2e2 | note | ○ Free swell index - 2.5% max.
0b38da26-ca96-5580-84ec-dc91154ffa6e | note | ○ Soil soluble salt content - 3%
aa9a00a8-13d7-5e15-be21-e60cfa6edab6 | note | ○ Organic content (dry weight) - 2% max.
e22d9edd-80a8-5d2a-aa77-a7278bb7359e | note | – Refer to AS 1289 for Tests
6f0df42c-1a6a-559a-a79f-c38ae445dad9 | note | Method - Visual, Review Test
7893c7c0-a86e-5580-b2d6-cc56af8c0ef4 | note | Frequency - Once, for each material type - prior to works commencement
492b6d89-fcdb-563e-a29a-92fe70fcfebd | note | Category - HP
37751632-4167-5e95-8cea-0efb90dd132f | note | Responsibility - SE/PE
bc6512d3-d046-573f-a238-8ff1de3f4669 | note | Verifying Documents - This ITP Signed Off
cdf290c2-c77f-5575-b472-49e89219dd66 | note | Attach: Supplier Material Conformance Certificate
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Pre-Commencement of Fill Works
4331795c-6d08-5c31-9f82-85397a175ddd | note | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
6cf3fd9f-300d-5ee1-ad7e-7fedad86b841 | note | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
40296c4a-f2a9-5cd4-88dd-af4f7be08dde | note | Method - Visual Inspection
55cccfd2-ca7e-5b81-9371-cbd6b5e03121 | note | Frequency - Prior to commencement of fill works
19f1dff4-cac6-5694-9822-d5e6eef4e64c | note | Category - HP
b4bce265-6928-5c67-a319-3f18830a6c75 | note | Responsibility - SE/PE
7bf3191b-08cd-5c11-81ab-8637937c7d40 | note | Verifying Documents - This ITP Signed Off, MTM representative signoff
0f2eeef7-8199-5990-860f-ec374cefaf4c | note | Attach: Site Photos
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
4ac2c0fe-ce1e-5f7f-8dd4-cd241870b81f | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
0bb69df0-35cc-5f27-94f4-b0603e00e3fe | note | Acceptance Criteria - Approved IFC Drawings
f26fcb89-41a2-5eff-b9bc-04ca23684191 | note | Method - Document review and approval
83065237-5b47-5b99-90a7-a4a6cd564a67 | note | Frequency - Prior to works commencing
deb01622-1172-5265-bf81-8688c0778b7b | note | Category - HP
50dcf62b-cda2-557a-908e-68f80a63d30a | note | Responsibility - SE/PE
43ad15e6-a4f6-5093-9bb3-435bc29fa69e | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Survey Set Out
a610775c-9682-5626-8d31-ab7b1cf57a6c | note | Reference - IFC Drawings
efc0c808-cb98-5f58-b0aa-2af01957436b | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
317e0384-a102-5bed-836a-4f919d572d8a | note | Method - Visual Inspection
32214068-c663-5605-8bff-8e81aa7096c0 | note | Frequency - Prior to commencement of fill works
e42ff32a-2d96-59c1-89e3-10e27c9530f5 | note | Category - HP*
e0979d3f-a05e-5fa5-b9ad-2da606c0cd3e | note | Responsibility - SE/PE/SPE
902e3669-5239-5558-9ee1-ce5819fa879f | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - General Fill Preparation and Installation - For track constructed on embankment (1 of 2)
0fcb8087-fcd7-574b-82ea-6e20e0eeae8b | note | Reference - L1-CHE-SPE-178 - Clause 5.10.3.1. Australian Standard - AS1289 IFC Drawings.
e337d79f-bd21-552c-a3d2-ab0999e990d1 | note | Acceptance Criteria - Any surface on which fills are to be constructed shall be proof rolled.
b6e3ecea-bd10-5673-b216-7db808bb0032 | note | ○ All layers of general fill material shall be compacted to a minimum characteristic value of density ratio of 98% (Standard Compaction)
51acb62e-127e-588f-a8dd-98de102aa13f | note | ○ Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
7d1e8b09-8c1a-5300-8511-a8e84764fb9c | note | – One test per 1000m³
cf45404e-d154-557e-995d-425d4b32beda | note | – Volume < 1000m³ atleast one set of tests shall be carried out
c16dee1a-2e2f-55f0-bdd4-d999bcfee7fc | note | Method - Standard Compaction
b452aeaf-0dbc-5468-9b7d-c1d5d08c5236 | note | Frequency - Each Lot
89d90e13-90b7-54e7-9815-2e7d5035b915 | note | Category - HP
c05e8861-ce52-59d4-ac7d-f0fd7f87dc69 | note | Responsibility - SE/PE
ae844824-48ef-5626-a05f-dc11e127f03b | note | Verifying Documents - This ITP Signed Off
64bf950d-971c-5207-b84c-8975b948a6b6 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - General Fill Preparation and Installation - For track constructed on embankment (2 of 2)
c4bdf2c4-8dba-5d23-8867-2d3bb0cdbc0d | note | Reference - L1-CHE-SPE-178 - Clause 5.10.3.1. Australian Standard - AS1289 IFC Drawings.
f3ff25d8-4ea7-5bc8-ad64-ddf1fc2d0f59 | note | Acceptance Criteria - General fill shall comply with the criteria listed in Table 1 (L1-CHE-SPE-178 - Clause 5.10.4.1.):
b4ff69d1-50b4-5e03-b1e7-cb974194aeba | note | ○ Soaked CBR - 3% min nominal
a1895427-e911-5c5c-8ab0-0232518d09e7 | note | ○ Plasticity Index 9-20%
77e216e8-6c09-5328-ada1-3f9f3eb64484 | note | ○ Dispersion (pin hole dispersity) - ND1/ND2
2302c541-6c5a-55b8-88c4-dcd4e22469ef | note | ○ Dispersion (Emerson class number of soil) - not to be class 1 or 2
8d970225-8723-5803-82d0-a7b2b8d7483d | note | ○ Collapse strain - to be agreed by MTM geotechnical engineer
6a7c5104-9baf-553e-89d9-a14de6154ac4 | note | ○ Free swell index - 2.5% max.
2839e796-4e0f-5eff-bd8e-79911ff56889 | note | ○ Soil soluble salt content - 3%
065c9644-43b3-5690-ad82-fd6b1c035b36 | note | ○ Organic content (dry weight) - 2% max.
1081fc99-b081-5739-8630-f7cb73b2b91a | note | Refer to AS 1289 for Tests
731b4a3b-c3d9-55fc-9e07-19e2ceec3916 | note | ○ One test per 1000m³
244cfa19-00e2-5d79-80c5-952eae505bcd | note | ○ Volume < 1000m³ atleast one set of tests shall be carried out
c597b96f-a356-521c-9558-ffaa9a649464 | note | Method - Standard Compaction
f5d9dd7c-0ac8-52a8-ae79-4443091bcc7a | note | Frequency - Each Lot
37d12820-3298-5eee-87ba-457554a525fd | note | Category - HP
e832bf9b-2ab0-51b7-9316-ac15209a566e | note | Responsibility - SE/PE
7fd5de64-6a42-5da5-927d-78cd2b65d738 | note | Verifying Documents - This ITP Signed Off
b9f9633b-f4d4-5f58-9243-d5e25848aa13 | note | Attach: Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Proof rolling
a5c77858-fd63-58f1-83a5-00a688bb53c7 | note | Reference - L1-CHE-SPE-178 - Clause 5.4.1. and Clause 5.10.3.1.
9ca8ed4f-dc1e-558c-8169-2a86e64ccfb3 | note | Acceptance Criteria - Proof roll as per L1-CHE-SPE-178 - Clause 5.10.3.1.
2581a962-7ede-5399-a593-fa76a5e7d897 | note | Method - Proof roll
a9efb761-a4d8-5017-bdb1-df78e881e52b | note | Frequency - Each Lot
094f58bd-44ea-5d31-b2d4-568c3f13fe30 | note | Category - HP
b4f5bc7e-32a0-54db-99f8-95539deb9c95 | note | Responsibility - SE/PE
b2bd5205-faa0-5eea-a082-c820779b9d31 | note | Verifying Documents - This ITP Signed Off, MTM representative Signoff
fbd9e4c7-ba42-50dd-b811-f97da612386d | note | Attach: Site Photos
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-Construction Activities
| checkpoint | 6.1 - General Fill Finishing and Tolerances - For track constructed on embankment / Survey Conformance
5c061ed3-797f-5baf-a15b-176be22a1b53 | note | Reference - L1-CHE-SPE-178 - Clause 5.10.6.1.
a33b996a-007d-5088-b4cd-108d9d6756e0 | note | Acceptance Criteria - General fill on embankments shall be installed within +/- 40mm of approved design surface level
ea55d25d-ba47-5d8f-8bd4-8dfe1210dee1 | note | Method - Document Review
cba81237-d0d3-5426-a7dd-854bb0a13d23 | note | Frequency - Each Lot
c6eb3c85-bfb0-5be0-8fc6-46d806209124 | note | Category - IP
1d0b92f5-d669-519d-881c-7fa788755da7 | note | Responsibility - SE/Surveyor
fa0f4369-0ada-560c-8056-9a08cae92ce2 | note | Verifying Documents - This ITP Signed Off
65985ec9-72ef-5a63-a060-1f9fd5b1b2f4 | note | Attach: Survey Conformance Report
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
c6fa0f32-5722-533b-9e3b-d42db6d534ab | note | Reference - MRPA Quality Management Plan
50169d7f-1e4f-5370-99cd-a149bf21e8e5 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
bd0e0354-24b8-5229-99f2-9d6c19f30c30 | note | Method - Document Review
ba3368ab-81ee-5858-a26f-d13ed720c456 | note | Frequency - Once, prior to closure of this lot / element / Work area
38d0cdaa-4c02-5bad-9059-33a1981e6664 | note | Category - HP*
712a76b0-9d29-5fe9-8629-412ac829c3bc | note | Responsibility - SE/PE/SPE
d29c2175-9d24-57fb-8dc9-2932a2692176 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
c4a50bdc-d292-5ae6-b900-99b7f83a3a36 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f4861e3f-4a12-5e49-bcfe-1a9255ec7687 | textbox | Name:
99a37de5-78ab-56ff-93a9-ac8e17d699f6 | textbox | Position:
7d6c46b6-9b92-5fe0-adff-3ea9c27059d3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-142-RAIL-BRUNT-Track Formation - Structural Fill Rev.0 | itp | ITP-142-RAIL-BRUNT-Track Formation - Structural Fill Rev.0 | aa66895c-d7af-49d9-afb6-3d9cdb7e3b6c
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
0077b3bb-5843-50c4-90e5-6ea9a9c23f8b | note | Document Title: ITP-142-RAIL-BRUNT-Track Formation - Structural Fill
c74cca86-3b5c-5de5-b243-ad3f2b4a3830 | note | ITP Description: Track Formation - Structural Fill
30ec36b5-635e-5c7c-af3f-23118c8f111c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
60fc720c-1dc9-5da3-bf2c-5ec062782ad1 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
c45adb40-d772-5519-bdca-08c12ea4b11d | note | Revision Number: 0
5169326e-1bff-5626-bf74-1d33fdd50dea | note | Revision Date: 14/03/2024
b1060cce-fc3c-540b-9492-9620dc5d7948 | note | ITP created by: Mac Cameron
c5c762c1-ffad-5c70-8b91-62a7a923e575 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
f360a72a-9487-5366-ba3c-92aef8c296ed | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
| checkpoint | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification
b8bb1cd6-929a-5ab4-b45b-a8f729d59401 | note | Reference - L1-CHE-SPE-178 (VERSION 3)
| checkpoint | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard
493cca21-3cb7-5bcc-92e2-045e7bf098d9 | note | Reference - L1-CHE-STD-029 (VERSION 4)
| checkpoint | 1.4 - Australian Standard - Methods of testing soils for engineering purposes
155c0fc0-b981-5bb4-99c2-1cb255920459 | note | Reference - AS 1289
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Structural Fill Material Conformance (1 of 2)
f79e9704-3cf7-53e2-bd36-4c5e4460b1f1 | note | Reference - L1-CHE-SPE-178 - Clause 5.11.2.1. Table 4
82f47266-8c10-5e11-89be-c15e6d11cc95 | note | Acceptance Criteria - Structural fill materias shall have the following properties:
cce365f4-4532-5366-b3ff-bf2ff974a6ca | note | ○ % passing 53.0mm sieve 80-100%
ce0f9f81-80e1-531d-93f5-225119f28abf | note | ○ % passing 2.36mm sieve 15-100%
998d08b3-63ae-5b32-9eb8-2b1097c77e57 | note | ○ % passing 0.425mm sieve 0-70%
6a8f280e-e82f-55e4-a6f3-7afabba38a36 | note | ○ % passing0.075mm sieve 0-30%
4f1a4423-8822-59ab-8833-5dc042ad2a49 | note | Method - Document Review
13487882-690a-52ea-8c31-706db8d152a1 | note | Frequency - Once, for each material type - prior to works commencement
25e048b6-3fec-58da-a126-37a826dec79c | note | Category - HP
cbac7e0c-9781-518e-ac70-d9e13bb1f9c7 | note | Responsibility - SE/PE
f76ba385-c3fa-55a9-b7b3-e9927c1dfe85 | note | Verifying Documents - This ITP Signed Off
2c1bc733-46b1-5ade-a43f-9cb5a5084936 | note | Attach: Supplier Material Conformance Certificate
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Structural Fill Material Conformance (2 of 2)
0b52a595-4764-51de-8ad0-115235bccfa2 | note | Reference - L1-CHE-SPE-178 - Clause 5.11.4.1. Table 5 AS 1289
b04ee952-6e65-5e6c-97e8-2af33453cc1d | note | Acceptance Criteria - Structural fill must comply with the following requirements:
50f2d039-a99e-5921-9c33-1bbbddad31eb | note | ○ Soaked CBR 8% min compacted to 100% standard dry density
2d06eaf1-2272-5152-951a-92a2fa090b5e | note | ○ Liquid Limit 40% Max.
78342703-ebd5-5d9c-8fa2-58795039146f | note | ○ Plasticity Index 20% Max.
050c0778-9bd2-50fe-81c5-318df82bc93a | note | ○ Dry Density 1.8t/m³ Min.
2c03c53f-088d-524e-bb33-7742fb2d6537 | note | – Refer to AS 1289 for Tests
cab63091-f170-5d70-a21f-f7ba0bd7a15e | note | Method - Document Review
d9866462-a4ae-5c96-8a62-158e6e911a31 | note | Frequency - Once, for each material type - prior to works commencement
356c184b-8e48-56e3-807b-c4adacab0644 | note | Category - HP
57146b98-30df-5e9f-b08f-3e3b187fadb1 | note | Responsibility - SE/PE
9c94b11e-0d89-50d4-acc5-105520652eb2 | note | Verifying Documents - This ITP Signed Off
1a87c905-be3a-5373-8033-6b2b9731fbd4 | note | Attach: Supplier Material Conformance Certificate
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Pre-Commencement of Fill Works
573e9201-53cc-5e3a-8b3f-f21325a3ed2c | note | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
c52db40f-0bed-5086-bdfa-b74b2d09d7c1 | note | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
749c7ee6-ecff-58bd-ab09-184651b94c3d | note | Method - Visual Inspection
ba7e235f-751e-526b-b3ba-4ebef980486c | note | Frequency - Prior to commencement of fill works
41f1abd6-0857-5b18-9044-2ced84308a2c | note | Category - HP
2afea879-6dae-59e1-b332-7df86859833c | note | Responsibility - SE/PE
2aa3e84a-0139-5985-9bc1-9dc903243ea4 | note | Verifying Documents - This ITP Signed Off, MTM representative signoff
30a0d7e7-7518-5e43-ae51-1cc2c26c5bb3 | note | Attach: Site Photos
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
4f8c3807-1585-5171-ada5-3ec69ef20876 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
c1b8090c-70c7-5ce2-8b59-be80fe417fd1 | note | Acceptance Criteria - Approved IFC Drawings
7c120f52-9ceb-580c-b8fb-fd1c03ff1937 | note | Method - Document review and approval
fec384a1-bffd-5805-87fa-13c47e4fc198 | note | Frequency - Prior to works commencing
78dd5f22-e0d5-5067-b93b-9b9db8e0e000 | note | Category - HP
eb239e9b-88fa-5f78-be81-bfab5c3bf3c4 | note | Responsibility - SE/PE
c61bc13d-4d00-55f3-a663-eb213522fdff | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Survey Set Out
72253adb-3ce9-58af-88f1-becb2aa2b11d | note | Reference - IFC Drawings
1b3939ed-3096-52d2-b54c-a3a7ea50649c | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
114372d3-b1cf-5706-9cb6-2ff840818965 | note | Method - Visual Inspection
43b48217-dbd6-5040-bc21-994e4580304c | note | Frequency - Prior to commencement of fill works
93988a30-87ce-538e-88f2-6675a10a272b | note | Category - HP*
6715bdee-33be-5ad6-8c14-ec3aa3d463a8 | note | Responsibility - SE/PE/SPE
58008683-fa3e-5e6a-841f-7469fa436c47 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Structural Fill Preparation and Installation - (1 of 3)
780016b0-29a5-503e-8f19-65404a80b43c | note | Reference - L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1.
67fbd758-da4f-53a8-a5fb-6744f6427f01 | note | Acceptance Criteria - Where Rail Subgrade CBR < 3%:
c7d8a236-2107-56a4-9cfc-fe4f8f99061c | note | ○ Required minimum depth of structural fill is 1000mm
7aabc158-22a3-5228-ae78-0d1683fc3fbf | note | ○ 8% min CBR, Compacted to 100% (Standard Compaction Test)
f9a7e714-7cb2-585f-9aac-8532a07c0c7b | note | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
734fc8c2-1460-529a-a1f2-4de66d57dd2e | note | ○ 3 tests per 1000m³
7be216fe-cabe-5e8a-92f1-daead7af31d8 | note | ○ 3 tests if 500-1000m³
1b29912d-6852-540c-82d2-649378f1a3a7 | note | ○ Atleast 2 tests if < 500m³
4bf8b9e1-7f75-537e-8aca-07e9fc833101 | note | Method - Standard Compaction Test
f27779b9-631d-50aa-b584-a358be00bd33 | note | Frequency - each lot
42d0ab55-b50a-5a34-9866-8772b32ad116 | note | Category - HP
9d611c23-e6b7-53c7-a799-bf2ecde729b8 | note | Responsibility - SE/PE
72d2ec80-9919-5266-8332-a5300f9b36b7 | note | Verifying Documents - This ITP Signed Off
a258cf00-f0b0-5fc6-8132-50aea56e2824 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Structural Fill Preparation and Installation - (2 of 3)
5717c1ad-7aa5-5abc-abac-c7d2324b35ea | note | Reference - L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1.
999e491a-8bcc-5e73-b24c-d5eb7513552a | note | Acceptance Criteria - Where Rail Subgrade 3% < CBR < 8%:
af41172b-25a6-5c51-860b-54eca63dc4e3 | note | ○ Required minimum depth of structural fill is 500mm
c7845025-912d-5141-bd7c-e48405919373 | note | ○ 8% min CBR, Compacted to 100% (Standard Compaction Test)
c142f578-ca10-5552-99b1-788aa9d4c23b | note | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
1e6f3fbf-bbcb-5441-a4ee-23830b42b208 | note | ○ 3 tests per 1000m³
439f1351-58ae-5e7b-9d04-abcdbbb2f441 | note | ○ 3 tests if 500-1000m³
20bd02de-428e-5579-a71e-4c0ce586a919 | note | ○ Atleast 2 tests if < 500m³
fecf5a0b-8a92-5ea1-bf12-b1989ae12bf9 | note | Method - Standard Compaction Test
2b668b0b-9ddd-53c4-ba3e-a01ecd508db1 | note | Frequency - each lot
adf87be4-7ea8-52f1-9c5b-895722f3427b | note | Category - HP
680c47df-9be0-568e-b1c2-a8b819b724fb | note | Responsibility - SE/
a552a839-6387-5abd-bfd6-6ae789809c64 | note | Verifying Documents - This ITP Signed Off
3d224730-8d0f-5bdc-a931-719d1eb4cee2 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Structural Fill Preparation and Installation - (3 of 3)
a75d01c9-c481-5d7b-82d3-001081ded9a5 | note | Reference - L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1.
f8c258cc-6b46-5637-ab70-fafd874ac8e3 | note | Acceptance Criteria - Where Rail Subgrade CBR > 8%:
c3f3a13f-e567-5ba1-acca-969bd0920ac0 | note | ○ Structural fill can directly be placed onto subgrade and compacted to 100%
0b93fac1-d33d-53cf-b515-1e09902cc54e | note | ○ 8% min CBR, Compacted to 100% (Standard Compaction Test)
2b3936b8-2d63-59f8-ba64-859bed6ba75a | note | Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose.
e510d987-8901-5678-bb60-d34fcc621c9f | note | ○ 3 tests per 1000m³
3f214fc3-a058-5941-b041-5cd3fb19c6d0 | note | ○ 3 tests if 500-1000m³
15173377-7d5d-54b4-9e39-911f1422fdf2 | note | ○ Atleast 2 tests if < 500m³
efc5662c-c27d-5ee4-af59-36bad1c9d008 | note | Method - Standard Compaction Test
e4dd1ef1-5fc2-5ec7-820d-ba7c925aa06a | note | Frequency - each lot
04f4b52b-2a0e-5964-95d4-a730ca0b5b62 | note | Category - HP
21939557-cd56-53fd-b203-6687ad621751 | note | Responsibility - SE
9bad66ea-ea2b-567d-94b0-b57161449987 | note | Verifying Documents - This ITP Signed Off
8941c7dc-1b38-5a85-8553-75107698a973 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Proof rolling
be744d47-523e-5912-a42d-12903e2faaa5 | note | Reference - L1-CHE-SPE-178 - Clause 4.6.
f81dcab6-bd16-5671-95ed-1320cf487189 | note | Acceptance Criteria - Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
23cda121-4a74-53b3-a959-281dc8ab2b02 | note | Method - Proof roll
e9d9b4a5-3bb9-5d09-a951-a38ef495c475 | note | Frequency - Each Lot
9a4b42c8-356b-597a-8cfe-e3225c5f8f9e | note | Category - HP
8f752431-be0b-5825-ade9-34058661b298 | note | Responsibility - SE/Nominated Authority
1a29e5a3-7ce6-53eb-9e0e-62083c03bf21 | note | Verifying Documents - This ITP Signed Off, MTM representative Signoff
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-Construction Activities
| checkpoint | 6.1 - Structural Fill Finishing and Tolerances - For track constructed on embankment / Survey Conformance
4bcb6b13-d5ae-5fce-afff-002d32e715fe | note | Reference - L1-CHE-SPE-178 - Clause 5.11.6.
aaea7170-bbdc-57e1-bc3a-7a3bd289365f | note | Acceptance Criteria - Structural fill shall be within +0 to -35mm of approved design surface level
6cba2206-45e1-5af6-bf46-053c49f36eeb | note | ○ Structural fill shall be within +0 to +50mm of 3m straightedge laid on final structural surface parallel and perpendicular to centreline
6cbbf60e-434e-5910-83fb-d67f67f1cebc | note | Method - Document Review
fe1bc2d8-4a05-5e13-bbc6-ae3548f58c3b | note | Frequency - Each Lot
858d6e83-754c-5fbb-83dd-5fc3757f958c | note | Category - IP
64571623-db0b-5789-8371-92405889a2be | note | Responsibility - SE/Surveyor
7ecbdf4b-d001-5c2f-afb5-452ea10ba290 | note | Verifying Documents - This ITP Signed Off
de344c1f-3716-5386-9f9a-540856f38672 | note | Attach: Survey Conformance Report
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
0f18acc2-00d3-5219-898c-3506ac3c4ff0 | note | Reference - MRPA Quality Management Plan
97b15510-69c9-58cb-bf40-af476344e7b9 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
87a7fe5c-cc63-5633-9717-8558d5635f5d | note | Method - Document Review
6e4a394c-0507-5180-bc07-aad39634f52e | note | Frequency - Once, prior to closure of this lot / element / Work area
830496c9-47f8-5fee-9a1b-2da6f875cc85 | note | Category - HP*
efb971dc-c7d8-5fe8-813c-0d47d88c8b49 | note | Responsibility - SE/PE/SPE
b1a2fdcd-139d-507c-bf58-82327aab532f | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
1a3dc4ba-cbad-554c-bd56-63425d7c5a33 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
06e21e30-af25-53c6-a54a-5fc193e73b17 | textbox | Name:
dc1fed81-808b-512c-8ea0-72b714125b9e | textbox | Position:
10f4aeef-5e25-57d5-bb92-b88ed28f64b3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-143-RAIL-BRUNT-Track Formation - Subgrade Rev.0 | itp | ITP-143-RAIL-BRUNT-Track Formation - Subgrade Rev.0 | cdf2ac8c-e5ca-4cd2-ab69-227af33e32bf
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
b17e1e89-e646-5d51-94e0-38367b622cf8 | note | Document Title: ITP-143-RAIL-BRUNT-Track Formation - Subgrade
b9cb26af-d2aa-5c51-9755-cea89442fddf | note | ITP Description: Track Formation - Subgrade
e5521373-a1ab-5e44-818f-9b2b15aff08d | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
bf9e8ab4-9c28-5ad7-82a6-2f92b51e085f | note | Discipline (e.g. CIV/STR/RAIL): RAIL
be8f6ba4-942d-5f92-8f52-328708adf0f2 | note | Revision Number: 0
2173b0d4-8f09-50b2-833e-850acde71943 | note | Revision Date: 26/03/2024
b09c7c33-1402-561e-94aa-189358e1d745 | note | ITP created by: Mac Cameron
f0184fd1-8b59-5baf-9e3e-b9e793a316ff | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
a5029029-bf32-53f2-94b0-ae2cc306c654 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
| checkpoint | 1.2 - Metro Engineering Specifications - Earthworks & Formation Specification
ba6f7b87-de56-5847-9c78-2d08f3723c1d | note | Reference - L1-CHE-SPE-178 (VERSION 3)
| checkpoint | 1.3 - Metro Engineering Specifications - Earthworks & Formation Standard
fdc9a6b3-9969-520b-b32c-dfdd64f89cde | note | Reference - L1-CHE-STD-029 (VERSION 4)
| checkpoint | 1.4 - Australian Standard - Methods of testing soils for engineering purposes
c93ae9f8-5e09-56d6-b0c8-8e6319f35b62 | note | Reference - AS 1289
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Subgrade Description
b5a950e1-6f7a-5f34-b70c-aa6bf9db07bb | note | Reference - L1-CHE-SPE-178 - Clause 5.5.1. Table 1 AS1289 Tests 5.1.1 & 5.3.1
4e3ba49f-4c87-5cd7-93a2-8645f4e02b79 | note | Acceptance Criteria - Subgrade shall comply with the following criteria:
88d3aa20-a2f0-5376-94a2-3e121c43edd4 | note | ○ Soaked CBR - 3% min nominal
ce46b276-734d-5338-90ee-b1838c21cc11 | note | ○ Plasticity Index 9-20%
3f651a78-2316-5478-b01f-056a54268915 | note | ○ Dispersion (pin hole dispersity) - ND1/ND2
c152c3c0-e47a-5864-9679-a43fd51d3f97 | note | ○ Dispersion (Emerson class number of soil) - not to be class 1 or 2
81dcb8fd-85ff-59af-8112-caee2fbcca1f | note | ○ Collapse strain - to be agreed by MTM geotechnical engineer
6d03b176-d8ce-5567-acfe-50be8b2e73d5 | note | ○ Free swell index - 2.5% max.
9a3179a4-c9da-5e30-a9aa-902e8bc32e8a | note | ○ Soil soluble salt content - 3%
035909ba-ffd1-5195-a316-4d5eab8618c8 | note | ○ Organic content (dry weight) - 2% max.
9957f4c7-7a3a-5d45-adc1-dc541b22221d | note | – Refer to AS 1289 for Tests
38c4bedc-2c70-5bd5-9960-ba88e1a3a13e | note | Method - Document Review
f4d600cb-0e30-5176-9c05-eb8bf6adc07c | note | Frequency - Once, for each material type - prior to works commencement
346971a9-2169-522e-962f-f660d4ce1412 | note | Category - HP
deeebc8b-64c5-5629-865f-a4eb80e06955 | note | Responsibility - SE/PE
51af10a5-7d8d-5bc7-8c0f-7f43b1747551 | note | Verifying Documents - This ITP Signed Off
623cc502-3f73-567a-a82d-816d50766ab7 | note | Attach: Supplier Material Conformance Certificate
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Pre-Commencement of Fill Works
1b3da17a-cf2a-5340-9c02-d320bcafbd0a | note | Reference - L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests
9cdee971-c569-5f37-a6a4-f5c11b509973 | note | Acceptance Criteria - The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer.
7f54326d-95c3-55bc-8590-150f138c92b3 | note | Method - Visual Inspection
009c1a09-9377-5df0-a599-0c9da57ea283 | note | Frequency - Prior to commencement of fill works
6e4d50ae-f002-53bd-a140-5526d691ee2c | note | Category - HP
305bb4c2-98fb-59ef-b3b2-cd005f3ec2a3 | note | Responsibility - SE/PE
8e68d3db-25ae-5c1f-9d5c-6b2f7b031290 | note | Verifying Documents - This ITP Signed Off, MTM representative signoff
06c15d76-9658-5060-9ae5-30634a05f09e | note | Attach: Site Photos
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
f5bd99dc-7e3d-5621-baeb-b80e31156730 | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
a708e7a4-14ee-5da6-b57e-69e16e074d2c | note | Acceptance Criteria - Approved IFC Drawings
7db6a327-0de0-5665-b7d1-6069ea9075e7 | note | Method - Document review and approval
aabe6ee3-34a3-58cf-b8b3-b683fcc3b1cf | note | Frequency - Prior to works commencing
a7699adb-6000-56c3-b122-f7cfede59853 | note | Category - HP
9ff1da36-1081-5245-8b01-625068c1e8c7 | note | Responsibility - SE/PE
5a7eb202-9a88-5939-8a82-a7dde5c2c676 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Survey Set Out
fab5d89b-148e-5bf3-a789-c811843860a1 | note | Reference - IFC Drawings
3e6a0c60-15ae-5bc7-b0ec-7223301d2fb1 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
b5c32b54-23aa-5bc7-a424-a5f90205dd70 | note | Method - Visual Inspection
6d93d0c9-fc56-5219-a8b6-b2a214e356db | note | Frequency - Prior to commencement of fill works
94e97f8b-b323-5d5b-b259-5fec09263ca0 | note | Category - HP*
1f72b699-d8a7-58c8-834d-928080fe4b12 | note | Responsibility - SE/PE/SPE
16f94524-737a-578f-b403-4288a72f829a | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Subgrade Preparation and Installation - For track constructed on embankment (1 of 3)
470ae444-6b60-5482-a4a8-9e0bc52dcfc9 | note | Reference - L1-CHE-SPE-178 - Clause 5.4.
54e30843-9763-5616-a56d-4c692bab3cf7 | note | Acceptance Criteria - If min CBR < 3%:
253107a0-5b1d-50ed-baeb-f97294da94b5 | note | ○ Install min 1m structural fill
f9851d4e-90d0-5a86-8ec2-e37e91b3904c | note | If general fill is to be placed directly over subgrade:
38f6f563-dd68-5ae0-81b7-16cecc85c975 | note | ○ Subgrade to be compacted to 98%
5da0ee36-7f06-5772-9a52-03012ca351a5 | note | If structural fill is to be placed directly over subgrade:
c002bec4-ecbd-572e-a9eb-e2c7e73ec9ea | note | ○ Subgrade shall be scarified to 200mm and re-compacted to 100%
9df6b3c1-28c9-56e3-875f-b07df5a3710d | note | – One test per 1000m³
49a34b90-ec9c-5f04-81d9-ab8c1985cefd | note | – Volume < 1000m³ atleast one set of tests shall be carried out
3578aa30-6f19-5fcd-aa8e-00d9f4eb6985 | note | Method - Standard Compaction Test
0a95178f-bed4-56d6-8274-61841b7f7ad1 | note | Frequency - Each Lot
011affec-5fc6-5fc6-b379-1d6b2caf0f31 | note | Category - HP
68859824-52b9-5714-922a-b035cfde03a2 | note | Responsibility - SE/PE
b77f7097-3f58-5718-a31a-23819878e592 | note | Verifying Documents - This ITP Signed Off
bdf280e6-3f37-5648-80b6-9471ee5f55c4 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Subgrade Preparation and Installation - For track constructed on embankment (2 of 3)
8bdcfa43-54a9-529e-9f91-57e8cf821438 | note | Reference - L1-CHE-SPE-178 - Clause 5.4.
3685728a-e8c9-545b-9beb-5ebaf5a71d82 | note | Acceptance Criteria - If min 3%< CBR < 8%:
2fafb3d9-f8ab-5828-8149-5d2a8da4926b | note | If general fill is to be placed directly over subgrade
2add3aab-8bdf-50f6-8c26-3f0380a45dbc | note | – Subgrade to be compacted to 98% (Standard Compaction Test)
384ea04f-2888-5812-be27-1be4533ae066 | note | If structural fill is to be placed directly over subgrade
d3379b46-b3fc-5d15-8ccd-4283564fdd1d | note | – Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
18dc52c1-0e6e-5780-b266-8ec02d03ea45 | note | ○ One test per 1000m³
385bce0e-f824-5a05-af89-d35d979e00ea | note | ○ Volume < 1000m³ atleast one set of tests shall be carried out
af58255b-2d4f-5ef2-9a8c-de0306a04e89 | note | Method - Standard Compaction Test
923e1397-7a11-59d9-981d-e8ef5f80a5c9 | note | Frequency - Each Lot
1b237af7-6e4d-5e8f-b64e-697c297f41a0 | note | Category - HP
14b16211-a4b1-545b-8b59-4110c4ead291 | note | Responsibility - SE/PE
51d2545f-12ec-538a-8471-a37c6002ef60 | note | Verifying Documents - This ITP Signed Off
2c418ff0-3d82-53eb-9330-df6c174fd546 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Subgrade Preparation and Installation - For track constructed on embankment (3 of 3)
5befe5ff-b7c9-50f2-a022-eba01778bd72 | note | Reference - L1-CHE-SPE-178 - Clause 5.4.
1a00311a-3dea-5234-9684-0e9d0139f854 | note | Acceptance Criteria - If min CBR > 8%
f32463c5-6b4a-587f-bff6-6f50dbf4af9d | note | – Excavation can be stopped to suit capping layer or at top of section with CBR > 8%
e8af7ed5-646d-5a30-9fd8-6e3c992e6014 | note | – Subgrade shall be scarified to 200mm and re-compacted to 100% (Standard Compaction Test)
0f2ab93a-d501-57ca-b447-da9ea5c6cba6 | note | ○ One test per 1000m³
b30d038f-f23d-5871-b6e0-e1c3c3cd0303 | note | ○ Volume < 1000m³ atleast one set of tests shall be carried out
fa49c191-057f-5f5b-a1cd-047f052b5ea8 | note | Method - Standard Compaction Test
2b861c14-c940-5c95-8bad-94e5d0e9a8c2 | note | Frequency - Each Lot
40be43f8-1d20-5c4f-ab0a-1b8c8529fceb | note | Category - HP
0e174114-7c81-59c1-9ef2-89a65f694aed | note | Responsibility - SE/PE
02212809-bc68-55b7-865c-324f2652c0b3 | note | Verifying Documents - This ITP Signed Off
47abcc67-59f8-52db-b70b-089218b869c7 | note | Attach: Compaction Test Report
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Proof rolling
6568f32e-4271-5137-af1c-b5e266bb1932 | note | Reference - L1-CHE-SPE-178 - Clause 4.6. and 5.4.1.
14f8aecb-4515-5b85-99e8-83419f736620 | note | Acceptance Criteria - Proof roll as per L1-CHE-SPE-178 - Clause 4.6.
574f87c8-ea39-53fb-b6ea-bc8b64b17621 | note | Method - Proof roll
72556b0f-3629-55d7-8488-68f37d05b23c | note | Frequency - Each Lot
4ac625a5-9322-561e-8c90-029a02e2c556 | note | Category - HP
7b8a70da-a980-54ad-a9b7-3d84b1603e55 | note | Responsibility - SE
6b787088-f5a4-527e-9dcb-9e23f61e2be2 | note | Verifying Documents - This ITP Signed Off, MTM representative Signoff
| signoff | AUTHORITY HOLDPOINT
| section | 6. Subgrade Finishing and Tolerances
| checkpoint | 6.1 - Subgrade Finishing and Tolerances - For track constructed on embankment / Survey Conformance
d6ca77a1-a16e-5e01-bbbd-67094d2d4c04 | note | Reference - L1-CHE-SPE-178 - Clause 5.7.
2ed7efbc-1a1c-5cc4-b322-6263b1d97ea8 | note | Acceptance Criteria - Subgrade on embankments shall be installed within +/- 40mm of approved design surface level
0b692766-cf31-54aa-b861-36aebc9d5e0f | note | Method - Document Review
d30a7dd4-20f2-5b7c-b322-eda0969f4bff | note | Frequency - Each Lot
e18edc24-214e-5ed6-abec-e902e6ecb497 | note | Category - IP
80ab16da-f72d-54cc-8921-d3a604e8e1a4 | note | Responsibility - SE/Surveyor
d9f9489d-1493-56f8-b038-b023e0779296 | note | Verifying Documents - This ITP Signed Off
a4a4ac42-a62a-535c-8605-6a1c8c6e4b9b | note | Attach: Survey Conformance Report
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
24dbba54-74ff-55f7-a484-253de150aa62 | note | Reference - MRPA Quality Management Plan
fa827cef-e461-57ce-b88d-49aa0c09d106 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
cebff16b-d617-5afa-8bda-1f3a11e8d2ad | note | Method - Document Review
1909e4f1-eaa5-5455-b1ac-b20f13674428 | note | Frequency - Once, prior to closure of this lot / element / Work area
aa57ad61-6f34-5669-9b31-bb275d5becb0 | note | Category - HP*
5fa4b529-f2d3-53ec-9526-943b308d0cbc | note | Responsibility - SE/PE/SPE
ec5c11e5-5b16-5306-b4c6-c29452a1924c | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
a984566b-d9e1-50e0-82ed-667d6605fec4 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f3825fda-d2b1-50b0-90f5-a854011aa9b3 | textbox | Name:
06e0be81-6685-5a83-8cde-8a350781e521 | textbox | Position:
c7713b7a-9c4d-5cca-8966-368db7eb3385 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-145-CIV-BRUNT-Hot Mix Asphalt (Supply and Install) Rev.0 | itp | ITP-145-CIV-BRUNT-Hot Mix Asphalt (Supply and Install) Rev.0 | 51fafb63-882a-4f09-8544-38e29a6acd4a
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
8bebf7db-d7b6-57bb-8d22-4721dd8d340c | note | Document Title: ITP-145-CIV-BRUNT-Hot Mix Asphalt (Supply and Install)
b07ae783-cf0a-59c0-a38e-f7028e7cfee6 | note | ITP Description: Hot Mix Asphalt (Supply and Install)
75f02d6a-3a65-5241-9ca6-d2960f4475f1 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
f0167b96-1b3f-52f2-a280-5ec0c1fe2553 | note | Discipline (e.g. CIV/STR/RAIL): CIV
da9f63df-cd12-5863-a998-a0f25e590086 | note | Revision Number: 0
bbe6e96f-36a3-5ce7-80c4-ff49b0ad9af5 | note | Revision Date: 19/03/2024
af604611-014f-5b01-a5c7-12016359178a | note | ITP created by: Crystal D’Mello
5b6ccd3f-e124-50d9-ba02-7812c3580a9a | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
bcca48bb-8fa6-5bf2-9b26-8c94027bfc39 | note | Reference - VR Section 404
| checkpoint | 1.2 - Non Dependent
68c22ad9-c8a5-50ee-a67c-7a842ce4e2cf | note | Reference - VR Section 407
| checkpoint | 1.3 - Non Dependent
279fde6b-4c09-5bca-abb0-786e395b21b2 | note | Reference - VR Section 408
| checkpoint | 1.4 - Non Dependent
8e1f03f8-8815-5bb5-ad3d-1b2a97e54e2d | note | Reference - VR Section 417
| checkpoint | 1.5 - Non Dependent
f80f745d-8570-5ccf-ad37-01f23981e864 | note | Reference - VR Section 173
| checkpoint | 1.6 - Non Dependent
81ea7cae-b24f-554f-8625-0d8f65ad59e6 | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Mix Design
06f45008-fcb0-549c-8187-31daec063bc4 | note | Reference - VR 407.09
192d411c-d5c3-5c23-a99b-bb93848374d1 | note | Acceptance Criteria - All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use.
f3e42abc-bbf1-5a3b-9f2c-89c53004b5c0 | textbox | Enter: Teambinder Approval number
38dc1c35-10e6-5813-968b-15a1d6c2ee86 | note | Method - Document Review
73b1e376-4836-518c-9ac1-05be0990d8b0 | note | Frequency - Each Mix, Prior to commencing works
7886acc3-9349-54cc-83d7-969712869dc1 | note | Category - HP
59e02dd0-e193-5e39-9fcd-a6dbcb898895 | note | Responsibility - Nominated authority
f2408cd9-d9ed-53f2-8122-800077f72ca5 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Bituminous Materials-Tack Coat (where applicable)
663c5c89-00da-5a70-8438-dee0a72e7985 | note | Reference - VR 407.08 (d)
6043d1fa-1310-5838-85c7-de26e4ad45bc | note | Acceptance Criteria - Tack coat shall consist of a bituminous based binder.
37eb95e8-cab0-5f88-8960-3b5b8cead55d | note | ○ Only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used.
a8bf37cb-9164-5432-80bd-5e624fcb679c | note | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
b1226ccc-7d07-5fa9-8d5e-453ebf59ecba | textbox | Enter: Teambinder Approval number
9a413055-24aa-55b1-85e0-5e83988c82a3 | note | Method - Document Review
8442e0ad-c50f-589f-87bc-b47430310d9e | note | Frequency - Each Material prior to commencing works
f8af8aea-7f08-53a0-9215-88220b6e87d4 | note | Category - HP
3d22cf8f-061b-5a6c-8183-4627d87baac6 | note | Responsibility - Nominated authority
08fb9757-6787-5a4e-8ca7-8dd89043bb55 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Primer Material documents (where applicable)
cbe06162-eca7-5806-8fb4-f6b55f7cfc8a | note | Reference - VR 408.08 (c), (e)
ad6326ba-90e6-564f-a5b4-d4cbcc1f2ce7 | note | Acceptance Criteria - The primer shall be cutback bitumen complying with the requirements of clause 408.08(c) and shall be water resistant, of uniform appearance and capable of providing a strong bond between the bituminous surfacing and the pavement.
e7c43852-4e72-5743-bb84-af2f3f5512fe | textbox | Enter: Teambinder Approval number
17d19196-5126-5dd4-a65f-7d92a7fff893 | note | Method - Document Review
0155961a-c487-5361-818e-ea7060504412 | note | Frequency - Each Material prior to commencing works
6ffb692e-1507-5c02-bb1f-dc785e3097a8 | note | Category - HP
b192f44e-00ab-50bc-ae3a-4a7eb10d7833 | note | Responsibility - Nominated authority
db1f9ae7-3d50-5533-8568-b43c60f84aaf | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Asphalt Quality Plan
1e0d7d0c-5f49-5622-97ce-e3fe712bb548 | note | Reference - VR 407.04, VR 407.11
6c682729-f013-52b9-9a56-e160924d37e6 | note | Acceptance Criteria - the Contractor shall provide an asphalt quality plan that addresses the following requirements:
12397824-5a9d-52f6-88ee-99b334c81f6b | note | ○ RAP Management plan (Approved by DTP)
d8e0f9f7-c464-5d82-8e8c-c3d87f9a4283 | note | ○ asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
55c215ae-a5b9-5b27-b5ba-a9ce1a6d4eac | note | ○ measuring and recording of pavement temperature, wind speed and weather conditions
a0ea472a-af20-57c1-af96-54cb8cad41f0 | note | ○ achieving a uniform application of tack coat
12be7a40-4fe6-5614-8ff4-38919063bd36 | note | ○ achieving uniform asphalt placement including determination of paving speed and paving plans
acb31d68-a624-5505-bdb7-0752e0dcf034 | note | ○ determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
cb8b2db3-2bdd-5052-9e59-c99058c386c0 | note | ○ procedures to maximise density at joints.
51deef0c-5fdc-55e9-a674-4b6e21677ca0 | note | Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan.
d89c03d0-738e-5f4d-b1bb-4e4822e25423 | textbox | Enter: Teambinder Approval number
afe8f2c1-8a83-52cb-84f8-98832d7904df | note | Method - Document Review
533bddfd-c6a2-5baf-ae7e-b8c1bc92ea8d | note | Frequency - Each Lot, prior to commencing works
d9fc84ec-7913-56dc-bb64-dabdbb0fd560 | note | Category - HP
03c6f17f-fb49-52ea-98ee-94e45d97c8d2 | note | Responsibility - Nominated authority
53bca4cc-04a6-575d-b588-70c3e17ac9dc | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - RAP Management Plan
02f6b294-bd19-5ef2-ad0a-2661427694a9 | note | Reference - VR 407.13 (f)
23771ad0-7578-5ae8-aa43-d8446207bc32 | note | Acceptance Criteria - No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent.
55f200ad-e823-5eb8-86dd-a4ff8facc804 | textbox | Enter: Teambinder Approval number
47db9b3d-77f6-5f27-8719-a47a84ce654f | note | Method - Document Review
26ee624f-3410-59b6-9639-21b461985dcc | note | Frequency - Each Lot, prior to commencing works
cf95a854-9d67-5400-b2e3-bf3d3cf81e6b | note | Category - HP
24b1691d-b5ed-5da2-968c-f1dd746b1a84 | note | Responsibility - Nominated authority
636e18a7-dd97-589d-a64f-21d021c399d0 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Cold weather placement
a58a45da-97ba-51b0-9efc-b5ded3eb01bf | note | Reference - VR 407.17 (b)
8c4231a0-9bef-5ce1-8995-80008cb2fd02 | note | Acceptance Criteria - Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171.
2af8e407-7951-57d2-89d8-1aa1c38ca947 | note | Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
df72840a-e403-56d9-85fe-b41ecccdd0e0 | textbox | Enter: Teambinder Approval number
678d8f24-2d9f-5997-89f2-193f26ba416e | note | Method - Document Review
c39a1a7c-e0b7-583b-a1e2-3afa9b620244 | note | Frequency - Each Lot, prior to commencing works
5fdbcdcf-71c7-50b8-b433-a6213202feee | note | Category - HP
8ed86940-60b5-59be-893f-d9f142f5bd7a | note | Responsibility - Nominated authority
45a767f3-475a-5054-8042-73c8badba32d | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - IFC Drawings
f5776ff2-9586-5383-8da8-2216a711014c | note | Reference - MRPA Quality Management Plan
3cb9205a-d4e4-5a9a-82b5-55550ade21de | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
579d09f3-29e7-57cc-a760-17012fca9972 | note | Method - Document Review
c02eed52-355f-58b6-8c9e-ab759e9e0350 | note | Frequency - Prior to starting Works and at regular intervals
bbffaa86-534f-566d-8f84-f3b4c1fee118 | note | Category - HP*
2588ac4e-ca65-5594-8689-559eb4c4d3d5 | note | Responsibility - PE/SE
813a3ede-cea5-5ee2-9898-d4d30127678d | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Lot Map-and Lot size
ce763917-3495-5e2f-b1ff-d6ce8b1a377c | note | Reference - VR 407.21 (a), VR 407.27 (b) (i)
f3eeb36d-2bca-5b6c-8021-200474b94316 | note | Acceptance Criteria - A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance.
ef52eeb0-9a3e-5c70-b30c-89eb194cf0bd | note | ○ The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course.
be94fc16-06b0-50df-a6d0-dee86c6b7eed | note | ATTACH: Lot Map with planned location of Joints
71c4bd74-4380-5816-b63e-1925fafacb3d | note | Method - Document review
dabbd342-fc96-53b6-996a-10186c898449 | note | Frequency - Each Lot
cac9c5c7-22a0-5094-870e-4362ab049080 | note | Category - HP*
196b3e55-3e27-5300-bfbf-ccb462a2566b | note | Responsibility - PE/SE
78ebc02f-a41f-544a-a671-0f445f078712 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Ambient Conditions-Surface conditions
cb26b50b-4753-5c18-a14f-62d2cbf7db2b | note | Reference - VR 407.17 (a), VR 407.18
7fd03117-3037-5e4d-9a50-0965b921a036 | note | Acceptance Criteria - The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
9fc71a5d-a8fc-5790-afd7-1f55e942bcd8 | note | ○ The Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed.
484b9f52-e820-5649-b5fe-7a3efa0248e9 | note | Method - Visual
64cb0ee2-a258-5b10-854e-556ebc98dccf | note | Frequency - Each Lot
7c1c8e25-3118-5292-bbb8-87d266b259d0 | note | Category - IP
054c990e-1068-537e-8b57-a9588da07d38 | note | Responsibility - SE/PE
887f58c5-6fc5-5c4b-a71e-d3359e2b50d1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Ambient Conditions-Surface Temperature
d361f9de-cf27-50d6-b81a-a6e9a1a3cd46 | note | Reference - VR 407.17 (a)
a5d12db9-5f1d-5b0e-b40b-d62c14b07d4d | note | Acceptance Criteria - Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below:
eb8120c6-d047-512d-b34b-ec6efac43a94 | note | ○ Specified binder class of C170 or C320:
807e75e9-fa86-5c1c-8ad5-aba344ee2015 | note | – Wearing course: 10°C
1655035d-1927-5e35-9112-15ce0d9a79f6 | note | – Other courses: 5°C
8bafbff1-98e3-5194-bb16-e364bb148b48 | note | ○ Specified binder class of C600 or containing a PMB:
71db1319-c8a1-5314-ab45-f5990df61244 | note | – Wearing Course 15°C
8c5a394e-a1eb-5263-9d3f-820e627a6849 | note | – Other courses 10°C
a4edaf2f-a7fa-54db-a681-528b21afb450 | note | Method - Measure
f9aa9efa-9dc9-50e9-a999-c989a516d734 | note | Frequency - Each Lot
18510e3b-6a93-5036-ad8a-d7e1fb13aef9 | note | Category - IP
688fda75-e88b-54fb-a6e6-17c1cc0b7dbb | note | Responsibility - SE/PE
fbe2f907-8caf-5b1d-b7e2-8ad11f4d589e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Joints and Junctions-Layer by Layer-Transverse Joints
cf22a1a6-206f-5882-9d13-a276ef67dc46 | note | Reference - VR 407.21 (b)
5c7a9aee-ca54-5757-8dda-f1bd5bc6f554 | note | Acceptance Criteria - Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
53be0201-0ce2-5079-93a8-a7b3c505ec8c | note | ○ All transverse joints shall be offset from layer to layer by not less than 2 m.
3b2fbeca-1acb-5504-9b70-7f28605a2c1f | note | Method - Visual, Measure
78adee98-414b-58f4-9cdb-a5df55701581 | note | Frequency - Each Lot
d38155bf-d4fa-5eab-b6f9-e7d9772f7ab6 | note | Category - IP
6c31385c-12fb-54a2-b491-e173b1b25b49 | note | Responsibility - SE/PE
8f15b902-1c62-5e92-a345-a8060240a946 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Joints and Junctions-Layer by Layer-Longitudinal Joints
5fd7f85d-d61d-50c5-87d1-04f94adf2c2d | note | Reference - VR 407.21 (c)
93816f45-2232-5b4e-b466-7589df99dcb8 | note | Acceptance Criteria - Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
d16272b6-9993-588f-9a37-b47358ce714c | note | ○ Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
ec6852f3-9f6b-57b1-9c10-3fcd759ad03e | note | ○ Longitudinal joints shall be parallel to the traffic lanes.
838d7c7d-1645-54e0-aa7a-556908c84387 | note | ○ Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
bf46f8bb-b9d9-5320-82f2-5df20dd8133b | note | Method - Visual, Measure
26ae403b-cbe6-5baa-9a34-d6df3470c263 | note | Frequency - Each Lot
4ac3bf71-0e39-5130-9bb8-cb642e40d1db | note | Category - IP
81607321-b91e-5fcf-a528-5723ff160c93 | note | Responsibility - SE/PE
7c6dbb17-ee66-53be-a5b4-35b17e53e3c3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Joints and Junctions-Abutting existing pavement
4a5502f7-a717-5863-9eb2-c35e7d6f05d4 | note | Reference - VR 407.21 (c)
5cc40aff-180e-5640-a7c7-f4d315836f07 | note | Acceptance Criteria - Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
7610f484-4d7e-580c-81e5-0957631808be | note | ○ At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
a43aba72-14a7-536f-bcff-78fb54245f95 | note | Method - Visual, Measure
7d343193-e149-566f-84e2-8c40afc80470 | note | Frequency - Where applicable
2defe1d9-903d-5903-b7dc-31ad7eb838a8 | note | Category - IP
585f9eee-9969-59d6-b232-f3f5428b9a32 | note | Responsibility - SE/PE
bb250c0b-4ab9-5104-b220-339d38373630 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Joints and Junctions-Junctions at limits of works
3931e0e7-12c0-592f-9189-ac23c6e9768c | note | Reference - VR 407.21 (d), VR 402
90c19791-12a4-53d3-bbcf-6b2de58faf74 | note | Acceptance Criteria - At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
390220a4-fde1-5a34-ab51-744db76fa87a | note | The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows:
9d6d1ad4-f3c2-5f30-81fd-c82a70c9960e | note | (i) at side streets and median openings – 600 mm
0d5757e2-d336-5147-8784-db0dc94ab494 | note | (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m
61b661fe-2a0a-5242-a007-b075c2b1d5ad | note | (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m.
47ea8351-42a1-539a-b97d-6050b3c3e774 | note | Method - Visual, Measure
7cea29aa-f4f6-53a7-97d4-434f953ccf88 | note | Frequency - Where applicable
03a88c10-e762-5885-8f82-3ad51cbb72dc | note | Category - IP
24b463f4-46e3-50e4-8f3e-b7e98cfe4949 | note | Responsibility - SE/PE
8be89c74-8112-5791-abad-b16c777b58f3 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Application of Tack Coat (where applicable)
45d7569f-7c4c-528a-a620-ee034516cba9 | note | Reference - VR 407.19
e3c01673-4672-530a-940f-50acdd1b3631 | note | Acceptance Criteria - A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed.
eee279df-7ac0-542b-aad8-d4cd6697d309 | note | ○ The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen for joints and chases rates shall be doubled.
5723e144-ee03-53ee-9e34-2bd7fa13e3b2 | note | ○ The Contractor may omit the tack coat where asphalt is to be spread over
94277f17-1dad-567c-a500-af954a8ce2c7 | note | – A clean, un-trafficked, freshly laid asphalt, or
592907ba-4f0d-5560-b081-c0f55cfa5d52 | note | – A clean primed surface, or
cb227ffe-1429-562d-b5a9-14d08030536a | note | – Granular material where the overall asphalt depth is 150mm or greater.
5662e4da-9dae-5113-b875-71cffbd36cd7 | note | ○ PHOTOGRAPHIC EVIDENCE shall be supplied to show that tack has been applied.
8881c5e0-60ce-5e19-b87b-c1c0c8df7605 | note | ATTACH: Photographic Evidence
726e65ee-3a23-5044-8e0d-7064dc9557bf | note | ATTACH: Subcontractor ITP (complete)
8cb4cd1e-4381-5ffc-b563-af8af5383b29 | note | Method - Visual
6d27d2c6-bed0-5b63-b629-3cf38b54f0e3 | note | Frequency - Where applicable
16999590-ec74-5b0c-8446-c2b349fd7ffd | note | Category - SP
b814965f-8e5d-5e26-96a2-c29cf9b6a759 | note | Responsibility - SE/PE
df05e48c-dcee-5b41-9c0d-354ef2420415 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.8 - Application Rates for Primer (where applicable)
8e8ce589-3625-5011-b37a-90596e30edd5 | note | Reference - VR 408.13 a
26d2fe08-77d0-5777-b64e-91d265f1dbb2 | note | Acceptance Criteria - All rates of application of bituminous material shall be expressed in L/m². In the case of binder, rates of application shall refer to residual binder at 15°C.
d823b35b-d3c1-5453-a2b7-2bf71a13f142 | note | ○ All rates of application of aggregates shall be expressed in m2/m3 and rates of application of precoat shall be expressed in L/m3.
0f8b13e0-bd5c-5570-a35d-17bcb9140b97 | note | ○ At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent
f00e53cb-c2e8-53b6-96da-c043d16cc2bf | note | ATTACH: Photographic Evidence
95b5977a-9ac1-5822-8886-c73b7e22064f | note | ATTACH: Subcontractor ITP (complete)
4bf67b79-1386-5add-8103-b85ccf81d3ac | note | Method - Visual
ca25d73e-50bd-50f2-935b-71ba07e36e04 | note | Frequency - Where applicable
16f0531c-2a2d-5b7c-9a61-e1a423adbfc9 | note | Category - SP
69549ef8-4827-5d42-b648-a4d5f92f870d | note | Responsibility - SE/PE
9cc70bfd-50d0-502d-9861-6044eb429250 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Joints and Junctions
1423288e-cc1e-57e3-ad59-30cd0877d2e2 | note | Reference - VR 407.21 (a)
9939d5a5-9599-52c6-8e1f-80d3aadc0e9f | note | Acceptance Criteria - All joints shall be well bonded and sealed
6f377995-9321-54e3-8f91-79f29d753dad | note | ○ All cold joints and abutting concrete edges shall be tack coated
f71be9e9-456b-538a-8741-4d268f37ecd6 | note | Method - Visual
c0fbadcd-cd02-55c7-8d23-326866480ac0 | note | Frequency - Where applicable
73b86e0b-c8a4-5a03-a909-f62d5b0c57d0 | note | Category - SP
99ce959a-2ef2-5f07-9c44-8d5ad8ca6097 | note | Responsibility - SE/PE
4c8abcc9-d793-552e-88a0-bf7d6bbe5bbc | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Delivery Dockets
4015d623-6cf1-52d8-829e-29433f370181 | note | Reference - VR 407.20
58292369-70f2-5411-b589-eb9dfaf16ef2 | note | Acceptance Criteria - Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
c41eea02-1b0e-59cb-9195-4623751edb06 | note | ○ Maximum Asphalt temperature at discharge from the plant is 175°C
c041b9e4-7cc8-5b85-8525-798ae48fde45 | note | ATTACH: Mix Delivery Docket
e30e04b3-a06f-5b83-809c-de7fc0ff9d98 | note | Method - Document review
e751d419-e868-5feb-b56b-c99c728ba833 | note | Frequency - Each Lot
d6c9399d-a76d-5937-8d1f-5d1a6776ac35 | note | Category - IP
3c6f23e0-eae2-5d60-ad00-6ec6de1c3021 | note | Responsibility - SE/PE
0f8511e3-6d82-5c03-9d6e-d41868bcdea9 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - Commencement of Placement
fe7ccc8a-4fbd-5331-8493-1a128e5e678c | note | Reference - VR 407.23
0b953b95-fcfb-5d65-a40f-0f394d2058a7 | note | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
08fe04be-15b7-5e16-9db0-db2b21b5e6d1 | textbox | Enter: Teambinder Approval number
1dcbcbc9-5634-5b77-852e-0809292a4ad2 | note | Method - Visual
a1068c4d-9cde-58bc-8695-2c37b5420cdc | note | Frequency - Each Lot
aecf7a1f-12af-5977-bf54-12a0bf86a722 | note | Category - HP
0ccfd265-2613-5737-8a2b-cff727608c25 | note | Responsibility - Nominated authority
d233067c-4569-553b-b555-8494a5ba8ec9 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.12 - Paving of Asphalt
6d0930eb-e4f0-5a1b-87b0-1a92bad49c6e | note | Reference - VR 407.25
15ab69c7-c7f7-5f2e-bf19-eb51cf2abe57 | note | Acceptance Criteria - Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings.
33afcf75-e42f-5d62-ab87-dcf7be3de4ca | note | ○ All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging.
f70257f1-1ab1-5855-b128-af2c2317a978 | note | Method - Visual
6d8c41f0-eaa8-56a5-88c6-5bca20943712 | note | Frequency - Each Lot
53a21f0e-1077-5aa4-ae9c-5271cc4852ef | note | Category - SP
d7fc494f-8901-511d-9177-83ebf7707486 | note | Responsibility - SE/PE
0b75d492-7326-5e79-bb15-973371330ea4 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.13 - Paving of Asphalt
cb1e70d7-70b6-5a91-ba00-c0f39b7d2065 | note | Reference - VR 407.25
82138b5a-ed4b-57b5-95bc-a5dabc46ee4c | note | Acceptance Criteria - If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed.
46110482-9732-5405-b8ec-fd39464b7751 | note | Method - Measure
debd6e79-79a7-5abe-b84a-b94088a8cf8e | note | Frequency - Where applicable
895f3e27-1cb7-55cd-a869-ab292d314fdf | note | Category - IP
9754c390-11e8-5f9a-ba77-1117a4ae0509 | note | Responsibility - SE/PE
2d477588-1bca-5e31-80bf-c69d5c362087 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.14 - Compaction
00a9c2d1-ad3e-579d-adcb-61e3c5626893 | note | Reference - VR 407.26
5b619f49-69c0-5218-a23e-249f9cf2989b | note | Acceptance Criteria - Asphalt shall be uniformly . Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
736be398-ce0b-5f92-aed8-f9c3c7562b32 | note | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
386ffc59-696f-5c3a-a508-b77d24663f6d | note | Method - Visual
035d05d5-b4be-5a6b-a620-5f40e93572da | note | Frequency - Each Lot
8bfb46e9-a638-5d9c-974b-45b6fa00f4b1 | note | Category - SP
7425441f-f39b-5478-aa8e-bf8dcc33e1d4 | note | Responsibility - SE/PE
e6e1c907-c87a-5f45-a275-efec2ffb3048 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-Construction Activities
| checkpoint | 6.1 - Compaction test-Lots larger than 500 sqm
3441437f-2cdf-5d54-99e2-eca224d65ff8 | note | Reference - VR 407.27 (b) (i)
0ee5a240-d074-5f7e-8edf-a10be1d0dab0 | note | Acceptance Criteria - The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271.
dc7c1e86-b71c-5700-bbe6-cbe4ac357515 | note | ○ For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot.
8bbf2969-eb6e-5d20-856c-11c5d403fd55 | note | ○ The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only
c553e387-dda9-57f3-a2ea-7f00ec93e887 | note | ATTACH: Compaction test report
2481e054-7bd4-5684-b0ae-38ec7827c1f3 | note | ATTACH: Wearing course joint strip compaction test results
03a12e27-c80c-5438-82b2-cc849d4b627b | note | Method - Document Review
b9fa4780-95dc-505d-89da-7f51ff93caba | note | Frequency - Each Lot Where Applicable
7526fdc6-2ac7-53d8-b712-6185950319d1 | note | Category - HP
43b7fda8-c874-5c7e-99c6-3d85a0875406 | note | Responsibility - Nominated authority
a0ca0f94-9d8d-5fb6-a18c-fe07c5c01c90 | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Compaction test frequency-Lots smaller than 500 sqm
2a258d29-32bd-538b-aa1c-c47f6a18a8ce | note | Reference - VR 407.27 (b) (ii), VR 173.04 (d)
60440677-7157-5b75-a47d-3ed17b57d86f | note | Acceptance Criteria - acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
bafcc559-95cf-5a68-8cae-28aa795a1157 | note | ATTACH: Compaction test results
648f1f5e-3c2a-5ef6-afa7-8081387e33c5 | note | Method - Document Review
bc947262-683a-5f62-8864-5a37205cd443 | note | Frequency - Each Lot Where Applicable
b6883484-c424-5a7b-b34e-f9de2639ceda | note | Category - HP
b24ef165-2dad-59e5-8fff-881a4bd2d0d1 | note | Responsibility - Nominated authority
68835103-4628-5ad3-847d-2810be12cbef | note | Verifying Documents - Conqa HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - Surface finish and conformity with drawings-Surface Finish and shape
dad177dd-dccf-5d90-8e4c-2a0075a12ed1 | note | Reference - VR 407.29 (a) (i), VR 407.29 (a) (ii), VR 407.29 (a) (iii)
a9c70223-0672-5456-bf77-2bf2a6be2fa5 | note | Acceptance Criteria - The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks.
c34f8743-0ade-5e97-8d02-e936b7f4af96 | note | No point on the finished surface of the wearing course:
37cec562-711c-572d-aae5-6785f2d46aed | note | – shall lie more than 4 mm below a 3 m straight edge
d0b59675-01c6-5c30-809e-def9c2c99f43 | note | For intermediate and base course layers:
57882249-17e8-534e-a54a-2514e2a4a02e | note | – the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
f5fca4bd-4dfb-5bf0-b6f7-5fd8b2c1a893 | note | ○ Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
b830684a-d42a-5ea6-8c57-54fc6b55c422 | note | Method - Measure
d354fd26-a3d7-5e17-bd42-aee20e31c803 | note | Frequency - Each Lot Where Applicable
59bf0a8b-dcb1-5a90-8a15-03e490ba1b97 | note | Category - IP
564ad6aa-c98f-5b0d-8563-7a776812dec1 | note | Responsibility - Surveyor, SE/PE
df9e47d9-c8b9-5ce3-af9e-982d39080196 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Surface finish and conformity with drawings-Alignment and width
63bc6d64-e204-5279-9a43-90959e7037d8 | note | Reference - VR 407.29 (a) (iv), VR 407.29 (a) (v)
542f96d6-2e9a-5f69-a759-7a20abc6ae0d | note | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging:
a3fe544b-dfbc-5bb3-94d7-85450a2322a3 | note | ○ the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
d58f6e27-0d17-5227-90b8-4cd11d04c2bf | note | ○ the width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design.
d695753d-8b79-5f93-8db5-271792895a06 | note | Method - Measure
90777f53-1c65-5c33-8914-4c56ca91ddcb | note | Frequency - Each Lot Where Applicable
ce9f8bea-f482-57b2-a095-00f2e6106534 | note | Category - IP
99842e7f-d7c6-563e-968f-dca5a5e34a94 | note | Responsibility - Surveyor, SE/PE
7a2256d0-099c-5da0-bb3c-903848aba5da | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Conformity with drawings - Scale A and Scale B
bfae57bd-28d2-5625-84cd-af3a7f623aeb | note | Reference - VR 407.29 (b) (i), VR 407.292, VR 407.293, VR 173.05
9223078f-a2f0-5cba-8acb-f364e2642fe1 | note | Acceptance Criteria - The surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05
bdab5c0c-c7ca-5bf7-b3c3-bcb2b969f910 | note | ○ Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293
f49ac8ab-b491-5145-bb4c-e231fbf8fecd | note | Method - Measure
2364e1ec-e673-5144-9f14-6002d676e89d | note | Frequency - Each Lot Where Applicable
8cff1b5b-8534-53ae-8b96-b8bad804548c | note | Category - IP
d49cbe68-d9c0-5ff5-bf65-e72d7e3a24e1 | note | Responsibility - Surveyor, SE/PE
3cb60b41-dbb6-5753-b3b4-34d6c4dfd9fa | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - Conformity with drawings-Scale C
041a41a8-f3c7-5199-aae7-1ac8c1223e94 | note | Reference - VR 407.29 (b) (ii), VR 173.06 (c), VR 173.06 (d)
cab1aca7-e9b5-524e-9b4a-06cb13890fa0 | note | Acceptance Criteria - The surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06
abf98e9e-5b89-5b5e-80df-d60a1f030301 | note | ○ The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course.
19a5da4b-df0c-5c70-a711-430d5ddc535c | note | ○ For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area.
627e8cd5-bc9e-57e8-885d-8b8729383147 | note | Method - Measure
65ef094a-4de1-502b-bf0a-11137da5fff1 | note | Frequency - Each Lot Where Applicable
c35e5f97-da93-55b8-8068-8fe769ff72d7 | note | Category - IP
2e51daa7-2b26-5f7d-851e-224ef5bb27a5 | note | Responsibility - Surveyor, SE/PE
b74ce834-de28-5a32-b525-7a0f2360a437 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Non-conformance Report (NCR) Closure
668cae61-e5a8-558d-9911-c2817d5bea37 | note | Reference - MRPA Quality Management Plan
deeedb74-b183-536c-90b0-87f96af6461b | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
ed3053de-cc4e-58d5-9621-567da8f3a1d1 | note | Method - Document Review
e6f935c4-6a06-566b-bac2-5a91469510b2 | note | Frequency - Once, prior to closure of this lot / element / Work area
330169b4-7975-50fc-8214-da95f835b55f | note | Category - HP*
a14f2fc3-e630-5768-a51e-1e49c0e72b2a | note | Responsibility - SE/PE/SPE
85b8f74a-b8fb-5987-a3a5-587357791014 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
a2e1262a-6438-5093-8496-8f138f028bdd | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
01e06eb3-617a-5e80-9e16-8e5ebde28481 | textbox | Name:
a8232743-5a31-5927-a74e-1de48606bbc9 | textbox | Position:
cfb75caa-cdbc-50ba-98c8-0667ad2a73df | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer Rev.0 | itp | ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer Rev.0 | 0002d552-c118-4ff1-ba16-3e72dfe9a302
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
9d06b095-2f36-57f8-bba4-409defdd6baa | note | Document Title: ITP-146-CIV-BRUNT-Cement Treated Crushed Rock Layer
5b356b3f-f912-59ca-8710-1f32f42ea963 | note | ITP Description: Cement Treated Crushed Rock Layer
ee3746f9-3ab3-59a0-ae0f-2cd9259c4748 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
0a39b9a0-fc38-58b8-9f4f-c05d9a55932a | note | Discipline (e.g. CIV/STR/RAIL): CIV
588917e1-38a1-5047-b847-21634ef31fb6 | note | Revision Number: 0
fcd98111-3b04-5bcf-970e-790318d7930c | note | Revision Date: 4/04/2024
56e308f4-ced6-5b1b-9f18-faa1a20f8d72 | note | ITP created by: Jason Lee
4ea744f8-a782-5634-8031-b25f76c00f69 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
dab41de2-bb07-58cd-bb2b-9f34b90c6ca5 | note | Reference - VicRoads Section 204 (Dec 2015)
| checkpoint | 1.2 - Non Dependent
f655b699-9cd5-5c30-97eb-b0c5a7c5818e | note | Reference - VicRoads Section 173 (Oct 2008)
| checkpoint | 1.3 - Non Dependent
d8769a6a-d564-58a0-8074-7c27baf2d24e | note | Reference - VicRoads Section 306 (Feb 2023)
| checkpoint | 1.4 - Non Dependent
7f1c5b93-ad1a-51c8-907a-c0a8fd0d893d | note | Reference - IFC Drawings
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
2d99f334-e746-5635-ab1f-74df214bc7cf | note | Reference - Section 306.04, Section 815.04 IFC Drawings
e181b00a-c509-598a-a8bf-4fa434b7d32b | note | Acceptance Criteria - Cementitious Treated material shall comply with the requirements of Section 815.
255d7dae-c5c2-5bbf-91eb-dc4eaaaab9bf | note | ○ CTCR mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02
0952e1e9-377a-5e3e-b18b-f2998d15398b | textbox | Enter: Teambinder Material Approval number
0c4d8676-0982-5d96-ab9c-37bd0060d4af | note | Method - Document Review
be55b71e-8713-535f-b4b4-a62e5c6b5cf5 | note | Frequency - Once, for each material type prior to start of works
661e9e9b-188c-5d67-8c93-c74795f84c3b | note | Category - HP
05d44f89-05d9-58fe-8db9-ff1bc2779965 | note | Responsibility - Nominated Authority
7206c942-be17-50c6-aef0-3c3f6db99fe2 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - IFC Drawings
89deaf54-e609-5719-8d06-731b704dd02a | note | Reference - MRPA Quality Management Plan
d7eb5d02-2f8c-5f85-a40f-85d041b60132 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
e5367e48-24e2-5ace-af43-6d4459eb629c | note | Method - Document Review
8fd5dd6f-0982-5919-97ba-e1343a834c1f | note | Frequency - Prior to starting Works and at regular intervals
ae94b7f5-c77e-5cfd-a766-ae2e42870206 | note | Category - HP*
8ab105e6-4d91-546b-826c-ce0470e375e6 | note | Responsibility - All
8912434b-20ce-50ba-a2a3-a671348c2d67 | note | Verifying Documents - This ITP Signed-off
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-Out
cecb2215-c685-5449-8369-073be7562474 | note | Reference - IFC Drawings
1a1cceb4-dee0-5ac4-8a5c-4ab268676d2f | note | Acceptance Criteria - Area has been set out in accordance with the IFC Drawings.
8475606a-1220-51e0-b55d-53a29bf69b1d | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
37edb3bf-7f2f-581c-ab5f-6ee255ce036d | note | Method - Verify
8459f709-da78-527c-be33-2b1aa3ef103d | note | Frequency - Prior to commencement
cf595541-cffc-5753-b2cc-9cce88d8dcb7 | note | Category - HP*
a6c60e28-1295-59cf-b3d7-66e8ba08fccd | note | Responsibility - SE/Surveyor
bbde7198-25c8-5bd8-a929-78a7565e3023 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 4.2 - Pre-Commencement of Fill
9413c94e-10ed-55de-934b-b954b405a477 | note | Reference - Section 204.10 (b)
0f357627-b2be-55d6-96e4-4e1e62012de3 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
ac30cc77-be67-5ec8-95f7-37bebd0fd625 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
afa08317-7572-5266-b2db-9df107899557 | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
1764c5c4-256f-55d3-b29a-b3272dedb9d7 | note | Reference: Previous Layer Lot Number
180e484a-ed69-5e5e-b2f4-3bdf74942ec4 | note | Method - Visual inspection
ef190bb8-5695-524a-b719-ba10482afef0 | note | Frequency - Prior to commencement
bf34b7f4-e2ab-53ec-8882-d414674258c6 | note | Category - HP*
8ed6ff08-b596-5e1d-b69a-b54e7d7c48b0 | note | Responsibility - SE/PE
50504f58-a966-51e8-b9a4-8ad11cab9589 | note | Verifying Documents - This ITP Signed-off
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Test Roll
c9222a19-3ca3-5544-a59f-366453c58d3a | note | Reference - Section 306.10 Table 306.091
bdf0abe6-f5d5-5c13-90be-b8869a60d316 | note | Acceptance Criteria - Shall be test rolled in accordance with Section 173 within maximum allowable working time for the relevant binder and time of year as specified in Table 306.091
54e47d7f-5a38-5069-9052-ade7e0059b00 | note | – Table 306.091 –
45ed41ef-ad95-55c1-8518-3841e376aeef | note | ○ Type GP - 2 hrs (Oct to Apr), 3 hrs (May to Sep)
0c93b992-ec47-5ac7-8746-f335bd094eb9 | note | ○ Type GB - 3 hrs (Oct to Apr), 5 hrs (May to Sep)
efbd0268-ddf3-5c63-ad14-cef9af093a4b | note | ○ Slag/Lime Blend - 8 hrs (Oct to Apr), 12 hrs (May to Sep)
31bbd0c9-9ae9-51d8-9c3e-713bf02ddb6e | note | Method - Testing
d021c70d-8aaf-5372-96f6-951dc810f907 | note | Frequency - Each Lot/Layer
8dd89d7d-d73a-5670-b237-42499824168a | note | Category - HP
9c4bd510-777e-5f7e-ade5-a53717f65a2e | note | Responsibility - Nominated Authority
dc368667-7ae0-58d4-90fd-9ba2b828bef3 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Compaction Testing
3caa6746-353f-53b4-ad60-b3864ad57c60 | note | Reference - Section 306.09 Table 306.091
5b144265-63ab-5001-aa13-e898c3dc8493 | note | Acceptance Criteria - Characteristic Value of Density Ratio
0cad37c0-ba4c-56c3-a19b-e361f8f4f2a8 | note | ○ Scale A - Not less than 96%
aabe351c-dc30-5bf9-9f3d-8018b4d29bd9 | note | Mean Density Ratio
42a3e9ee-0aa0-50b0-9496-ed8c372e132f | note | ○ Scale B - Not Less than 96%
88de7144-1a86-530b-9c1a-05b684071824 | note | Attach Compaction Test Report
b019ce8d-05e5-5e80-a2ef-c8c9689ef218 | note | Method - Review Document
7ae4b6c6-1570-5278-af1c-11eb6f24fbe8 | note | Frequency - Scale A - 6 per lot, Scale B - 3 per Lot
5b9a5d0d-85f6-5fd4-ae2b-cd02f02aae65 | note | Category - IP
b970b4f6-f107-5e4c-8968-0740a78b887e | note | Responsibility - SE/Site Supervisor, Superintendent
8934abea-12c6-5975-80db-3a622e030803 | note | Verifying Documents - This ITP Signed-off
| section | 6. Post Construction Activities
| checkpoint | 6.1 - Survey Conformance
c4cd7052-467b-5aa4-b4e7-5f0e7447509d | note | Reference - VicRoads Section 306.03
0c19561e-cd69-50d7-bbcc-21322ec9179e | note | Acceptance Criteria - Level tolerances Scale A:
2f79163b-9b12-5534-9b84-4cdd3b611045 | note | ○ Range x = +4, -8mm
1d52904c-f0f8-5cef-a00d-c30a4edf8d07 | note | ○ Max S = 8 mm
18f2980a-9f55-5be9-a15a-99101ad0be75 | note | ○ 80 measurements per lot
bfb0d720-f523-594f-b70a-9c244f21b782 | note | Level tolerances Scale B:
43270b5a-4927-509a-9671-fdd97fcbe7a6 | note | ○ Range x = +6, -12mm
73525d38-1bb2-52ff-8d5f-80df2b18f85e | note | ○ Max S = 13 mm
583f2c45-91a9-5b9a-92e9-7199184eeb3b | note | ○ 40 measurements per lot
8cbe9173-fb4d-5af7-ba30-bfee0d651ed7 | note | Level tolerances Scale C:
3393c704-5a5d-5c32-8bfa-2cbd95c813f6 | note | ○ No point on the subbase surface shall be more than 10 mm above or 25 mm below the specified level.
789506a6-46c7-5483-942d-60aa64ba193b | note | Attach: Survey Conformance Report/Data
c4f82a8e-295a-59d9-ae21-fdcff815c58c | note | Method - Document Review
836db036-2eb6-5cef-9976-a0ae21ca63c6 | note | Frequency - Each lot
e54683b1-a6ec-5015-92c0-4d7307a6f074 | note | Category - HP*
7589cc52-b731-5b08-bf6b-f3000aea8090 | note | Responsibility - SE/Surveyor
7d9416cb-1db5-5030-acbb-721bbf75c347 | note | Verifying Documents - This ITP Signed-off
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
ea7754d5-8b3f-5dbd-adfb-adb5d838f545 | note | Reference - MRPA Quality Management Plan
4084fc3e-ad4e-5e97-9a25-2956b9925843 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
89dbea5a-0347-5fef-82e1-59981d76e994 | note | Method - Document Review
32993500-03b6-55b0-8e62-dc82a13e3c93 | note | Frequency - Once, prior to closure of this lot / element / Work area
bb199957-223f-507d-aba5-bd37cf94a254 | note | Category - HP*
82f021bb-08a8-513e-b34f-9ec907411543 | note | Responsibility - SE/PE/SPE
71c452e7-907d-5767-b7ee-0f8fb7d1ae2a | note | Verifying Documents - This ITP Signed-off
| checkpoint | Final Inspection
9c7b3b1f-7954-5409-80d4-36526aad1852 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
7a9deae6-6322-52c3-8ce1-bccb175670e4 | textbox | Name:
f7b31320-c231-5b71-9d99-45eb28513cf2 | textbox | Position:
ca0d3bda-0a61-5a7c-b9fe-7807198ea914 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-147-RAIL-BRUNT-Track Drainage Rev.1 | itp | ITP-147-RAIL-BRUNT-Track Drainage Rev.1 | 792f36e4-fc7d-4dbc-a978-a6f5e83ba15b
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
73ff4cf2-86e6-5eba-9aec-9f72f5b07bf3 | note | Document Title: ITP-147-RAIL-BRUNT-Track Drainage
ad125d10-17d0-571c-97eb-bfb030f51c83 | note | ITP Description: Track Drainage
338513cf-0628-5870-b0e7-5168976a5d9d | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
31470f95-1268-5387-af29-d9807a06c31a | note | Discipline (e.g. CIV/STR/RAIL): RAIL
1e7119d7-6550-5f07-ac5a-cc0bf35fc628 | note | Revision Number: 1
56d48a7f-a243-56de-85d8-a8c1d72a632c | note | Revision Date: 14/05/2024
931bad95-5a51-5c82-b30f-37b9bf02364e | note | ITP created by: Mac Cameron
92dcfb59-dc0a-51a1-8678-9a7fe447ba17 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Drawing Pack - Rail Track and Civil
40f61393-2002-574f-85a0-0158a18180bb | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
| checkpoint | 1.2 - MTM Type Approval Product Register
c0d89774-5c48-5fdf-96cc-fc97536dc478 | note | Reference - A9402
| checkpoint | 1.3 - MTM Track Drainage Standard
f228e535-7583-5dda-af57-edc9f35c7b2f | note | Reference - L1-CHE-STD-030
| checkpoint | 1.4 - VicRoads Section 701
824ac0c3-e1ea-5d0f-aece-78fcff2e91fb | note | Reference - VicRoads Section 701
| checkpoint | 1.5 - VicRoads Section 705
a7b4dde3-db17-52a5-9924-ed738a00d34d | note | Reference - VicRoads Section 705
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Supply of: HDPE Slotted Pipe, Geofabric
3e961161-b666-555b-aa3b-01b0e32d5704 | note | Reference - A9402 L1-CHE-STD-030 Section 701
c2e73629-d5a8-5863-bcfd-1ea962c2a2b0 | note | Acceptance Criteria - To be type approved by MTM.
8beba169-9098-5ca7-a4ca-baf976905e69 | note | ○ Drainage Pipes to be supplied in accordance to Section 701
0c43b3e3-4005-5fc3-b539-47cce9b2ce24 | note | ○ To be inspected upon delivery to have no damage.
bed2f3eb-6760-5aaa-b7c1-5a6f17fadb28 | note | Method - Visual Measure, Document Review
2e3bddbf-65ac-52fb-bb92-9bbda2ce6061 | note | Frequency - Prior to works commencing
e1bd4cd9-d242-59ec-b44c-d5b28fc13cc9 | note | Category - HP
f861a5f9-5c9f-5f6f-9718-2ef206204544 | note | Responsibility - SE/PE
729d11c9-8f7e-5844-ad68-7cc940834282 | note | Verifying Documents - This ITP Signed Off
a8774cb5-61e9-5bde-b0dd-26a39aa1e5b6 | note | ○ Attach: Supplier Material Conformance Certificate, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Supply of: LDPE Liner, Clean Stone, Bedding Sand, Beaching Rock
bc211677-b3f2-515a-bf51-8db80401e759 | note | Reference - L1-CHE-STD-030 Section 701
e5a817a0-565c-5062-8420-ee0dd36ae57e | note | Acceptance Criteria - To meet L1-CHE-STD-030 requirements.
0b4f10d4-3f3a-5e00-bb36-70a5fa7b88f8 | note | ○ Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 & Table 701.092
dc704e61-443b-5efc-aaa2-fbc4f586fe09 | note | ○ To be inspected upon delivery to have no damage.
33b61da4-d5c4-5213-a81c-0f9fb5d26bef | note | Method - Visual Measure, Document Review
42f06140-ef9c-5861-9b84-828e2d33ea34 | note | Frequency - Prior to works commencing
8b316863-2c43-53d0-bd4a-1105276460cc | note | Category - HP
9c4dfc57-dc85-583f-8e52-6c2691414aeb | note | Responsibility - SE/PE
04118b57-836b-59ff-8dcb-5ffc2a44e006 | note | Verifying Documents - This ITP Signed Off
38574ad9-46c4-5265-aa91-13d8fda190d9 | note | ○ Attach: Supplier Material Conformance Certificate, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Supply of: Riser, Standard Headwall, Class D Pit Cover
ea352e0a-2f13-534d-8bdf-f5352641e8db | note | Reference - L1-CHE-STD-030 Section 705
f871a10f-7515-5ff0-bccd-c0f4a301ec10 | note | Acceptance Criteria - To meet L1-CHE-STD-030 requirements.
af997ba7-d703-5d11-95a4-5ecfb6a27554 | note | ○ To be supplied in accordance to Section 705
3b66e3c6-c405-51bf-9562-c75a61a73495 | note | ○ To be inspected upon delivery to have no damage.
96a696f4-a2a8-5d12-a57e-746784bd45ce | note | Method - Visual Measure, Document Review
c7340aa9-4a6e-5473-976c-f58305833ead | note | Frequency - Prior to works commencing
43ac1ee8-6bfd-5680-985f-45c41939690b | note | Category - HP
1dd41cb9-9d6f-5086-b1af-5eb9067a68d1 | note | Responsibility - SE/PE
07af0772-c8d8-5b34-bd3f-30229e437658 | note | Verifying Documents - This ITP Signed Off
6a2e29d2-04da-5299-8dfb-329de9362c55 | note | ○ Attach: Supplier Material Conformance Certificate, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Primary Documentations
d8602c56-82fe-5053-bf8f-c6d6bb6795f2 | note | Reference - A4263 PTDT Form B - Track Certifier Booking Form
f15c257f-c5c2-5b99-99cd-055b387c5096 | note | Acceptance Criteria - Approved PTDT
00d08782-7fa6-54f0-a8d5-32c8c675b978 | note | Method - Document review and approval
eff3c637-4dd9-54ea-9cc4-75f25fc5f462 | note | Frequency - Prior to works commencing
8ff216fe-bc53-57b5-9a4a-a4243ad71422 | note | Category - HP
5619b5d7-c6cb-5a9c-9103-18e97db3d94e | note | Responsibility - SE/PE
d4778ae3-67b6-589c-98f9-3b09315140c2 | note | Verifying Documents - This ITP Signed Off
507de2ad-ed1a-544f-9f76-132043d3594b | note | ○ Attach: Approved Permit
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Pre-Commencement of Work
0e20e0cb-eeca-5c42-8503-d8c4f12db47b | note | Reference - ITP, Quality Checklist, SWMS
e56ea58d-1cf6-5927-9d6f-36520de9438c | note | Acceptance Criteria - All approved by relevant representative.
cfb628a9-15dc-512c-9469-f5b0c959f256 | note | Method - Document review and approval
322b40bf-1896-54ed-95ef-2dcb8f49415e | note | Frequency - Once (Prior to Works)
b2483bfe-a9a5-53ce-86f7-10c2fa6d9522 | note | Category - HP
9adc389c-e6dc-5b34-87a1-3c84cde9440a | note | Responsibility - SE/PE
49e3cdba-cee7-5718-84f8-0da0f00062db | note | Verifying Documents - This ITP Signed Off
ad78ec05-41e6-5ae8-affa-ae7dc27ddf1f | note | ○ Attach: Approved Templates
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Approval of IFC drawings
8f2a01d7-d34c-5fb4-a012-f4da5e10697e | note | Reference - GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
b7fb2348-a01a-5059-b36a-3f4e3adbecf3 | note | Acceptance Criteria - Approved IFC Drawings
e7fe7729-03b4-51bc-b92d-fc72e1c303ad | note | Method - Document review and approval
3a26a007-7eb2-5b76-b7b8-e46a067c7c9c | note | Frequency - Prior to works commencing
1b2912a8-7105-584a-9316-e0cb007b2daf | note | Category - HP
1acab02e-7d1e-52f7-95f7-be6817369c98 | note | Responsibility - SE/PE
83548b5e-8a58-5dbb-b728-67b50a858372 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| section | 5. Construction Activities
| checkpoint | 5.1 - Survey Track Drainage Alignment & Pits
0c5e5625-b914-5dab-93ab-78604e30df4f | note | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
c16f249e-824c-5a1d-ae90-dde25eb75cfc | note | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation.
3e218a23-26fc-5393-9690-2b8473bea397 | note | Method - Visual Inspection, Survey / Measure
f6541daf-673b-55bc-851b-98af277f1222 | note | Frequency - As Task Progresses
bcae861b-7f21-550e-b13d-f11713cd97b2 | note | Category - HP
91a13c8d-9ab0-55af-bfa0-6c270bbc95d2 | note | Responsibility - SE/PE, Supervisor, Surveyor
86863962-2013-54da-bd95-59f4059c4f78 | note | Verifying Documents - This ITP Signed Off
5b706995-0d6b-5c50-9914-4fa9a8073219 | note | ○ Attach: Survey Records & Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Grade Existing Open Cess Drain
ebb9e573-5602-5928-be49-45b45543f7fe | note | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
ab0be244-82f8-5a34-9dda-9d8f271980e5 | note | Acceptance Criteria - Grade through existing cess drain alignment to depth indicated on design documentation.
bed0f7eb-f584-5cf4-8012-4e903cad6055 | note | Method - Visual Inspection, Survey / Measure
71bb5f85-dbe8-566f-b607-d6cd763e6e28 | note | Frequency - As Task Progresses
8d4865c0-89c9-5c1c-989d-bc0f67352f4d | note | Category - HP
0726e20b-a779-5c19-bbaa-9d8e1dec482d | note | Responsibility - SE/PE, Supervisor
3554d591-651d-561f-944e-d545b0568567 | note | Verifying Documents - This ITP Signed Off
d479b53d-bc4d-5381-b4d5-adcc2fdcfbae | note | ○ Attach: Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Excavate Slotted Pipe Drainage Trench
f7f0d1f9-15e3-5f84-b8a1-0d54cab87199 | note | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
be6d3d6b-fff3-53aa-860e-466fb0b6e4c1 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation
77fa8958-9381-51c1-af30-ad12bfe58a2e | note | Method - Visual Inspection, Survey / Measure
79bafc10-d9cb-5634-95bb-60d2cf697f16 | note | Frequency - As Task Progresses
25fd773e-1874-5716-93c4-8e554497f924 | note | Category - HP
1030b61a-1d76-58c6-a0c3-842354b57866 | note | Responsibility - SE/PE, Supervisor
a34b06b4-f136-5699-9bf2-e2a369c5fb17 | note | Verifying Documents - This ITP Signed Off
f5b66f8d-552a-5e66-ac1a-82b52f97c657 | note | ○ Attach: Photos on site
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Place the Following and Compact: Bedding Sand, Geofabric, Slotted Pipe, Stone
09cd17d6-3c6a-5070-ad06-8ad2dd601d9a | note | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
efe1adca-e3dc-5570-9bf0-9961a95edbcf | note | Acceptance Criteria - Bedding conforming to to Section 701.09 shall be supplied, placed and compacted. Compaction and moisture content testing to be in accordance with Section 701.20 (where applicable).
c1169b22-8c3d-52ee-b87f-cdfca32b54a5 | note | ○ Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three (3). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
19fd1e04-7dcc-5758-b245-af0f195b410d | note | (a) Bedding
be80d723-b6be-51db-855d-f2e87287183c | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
f98e1bd1-36ec-58f7-b083-3026ac78ac3d | note | (b) Backfill
3b2617e4-c21c-5eca-afa8-aa0055ba1c96 | note | (i) Material of nominal size 40 mm or less after compaction
e133c010-0b2f-5086-b2eb-4b383cd7b209 | note | – Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
2d11120c-499d-5b1b-8746-5f26184a876e | note | (ii) Material of nominal size greater than 40 mm after compaction
10156525-1e47-52fe-841e-eb77fea25fca | note | – Backfill material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure.
bccdad7a-7df9-5b88-87d9-1b2d6714af7f | note | – Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
783177ab-9758-5a22-9eb6-54f7efe3219d | note | ○ Trench to be wrapped with geotextile in accordance with the manufacturers specifications and design documentation.
55b074f3-9e6d-512d-b4f7-350f9b95f2d5 | note | ○ Attach: Compaction Test Reports
fe44e1b2-d261-5ae0-b3f8-5cd5599bc818 | note | Method - Visual Inspection, Survey / Measure
328633f4-9cf2-5d08-9d9e-5d4eceb1c032 | note | Frequency - As Task Progresses
5934d785-8375-5d31-a01f-5b5a94935cf7 | note | Category - HP
655d20b5-8365-5b30-bcc2-5df1adfe77c2 | note | Responsibility - SE/PE, Supervisor
aa67bbcd-0f71-5a06-8345-b9ef5129acfe | note | Verifying Documents - This ITP Signed Off
dd7a7296-ab74-57ca-bdb9-73adf932bdfe | note | ○ Attach: Photos on site, Compaction Test Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Pit, Headwall & Beaching Rock Installation
5f334999-7298-54eb-9b48-d751e73ffc91 | note | Reference - IFC Drawings: GNC-MRP-ACD-GNC-XDM-1304-20230714_Brunt Rd _PKG-61
41b9e2c7-ca9b-5f70-a03b-98bb9f48f7c0 | note | Acceptance Criteria - All stormwater pits shall be provided with a lockable minimum Class D pit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030
6ccea587-3727-54b3-8dbc-cea1334cd961 | note | Method - Visual Inspection, Measure
13504b25-2863-558d-8ef2-0d4dc10acab0 | note | Frequency - As Task Progresses
0626c3c6-ab43-5bf2-acd5-7b0c8a36d4f1 | note | Category - HP
dc375640-dfb8-5f59-b3ed-f20ce49b4aa2 | note | Responsibility - SE/PE, Supervisor
e95d5752-650e-5d6c-a31b-14663228190e | note | Verifying Documents - This ITP Signed Off
86485b01-176f-5eca-a72d-de24afa0beb9 | note | Attach: Photos on site
| signoff | AUTHORITY HOLDPOINT
| section | 6. Post-Construction Activities
| checkpoint | 6.1 - Track Certification
e0986318-3c40-578f-ae08-dac43916557a | note | Reference - MTMF020000-1 – Track Form A T, MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE
c4406e5a-c9ce-5e72-8cff-048ae0d8e6ca | note | Acceptance Criteria - Track Geometry Conformance Certificate, Track System and Component
fb96b0a8-23f1-5826-9d6c-b3dadc4555b6 | note | Method - Visual Measure, Document Review
d56cca03-8411-5a61-b902-d0b7f07c1316 | note | Frequency - Once (upon completion of occupation works)
d94442bd-9f75-5b37-8230-afdab0f725c0 | note | Category - HP
e8cd1a74-c72d-5784-b190-28efc1c6643b | note | Responsibility - Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure
250eebe9-e2cd-5ac4-8531-9f7c3a32f72e | note | Verifying Documents - This ITP Signed Off
e79805d9-b473-5ab2-b17d-ffe0f392d0ff | note | ○ Attach: Relevant Conformance Certs as per acceptance criteria
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.2 - Flushing & CCTV
2f1765d5-22de-511e-ab20-454051876145 | note | Reference - VR Section 701.28, VR Section 701.30
bc2b3302-cc15-571e-b004-8c5132d79cfd | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
40ed2850-f62d-574a-82c9-ef6924bcb4b3 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
e5823a0a-42a6-5228-9b77-aed13de4381c | note | ○ Attach: Flushing Record, CCTV Reports
7728c77a-aaa3-5fc0-bb6e-93c97d2737b0 | note | Method - Record Review
d83aeaea-4764-533b-be69-5be08acdef13 | note | Frequency - Each lot
d785db0f-9a0c-56e7-9539-20c32341b2ec | note | Category - HP
b6f66d21-799f-5f1b-b7ff-27e136833aa9 | note | Responsibility - SE/PE
c814138c-a9fb-532d-a4e5-e71a547a87a7 | note | Verifying Documents - This ITP Signed Off
04992cdc-a869-51f4-9410-e79c72483c6a | note | ○ Attach: Flushing Records, and CCTV Reports
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.3 - As-Built Drawings
803b4068-b966-52a9-8204-484beb4f8ec2 | note | Reference - As-Built Drawing Management Procedure (A8197) Section 701
8c2c1ae1-d48b-527b-9e9a-126bae2448e8 | note | Acceptance Criteria - IFC drawings (including cables, patches and labels) are marked up with redlines if applicable and supplied the Project and MTM.
ed01dd7e-efe4-5135-ab83-5150d068daf2 | note | ○ Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10
db0e1451-4f38-5f41-b4eb-6b52e24258c6 | note | Method - Document review and approval
a9c0355f-f1ca-58f0-8bb1-78c2a613f18f | note | Frequency - Once
71026a78-6fcc-5af0-b657-744cff37dc88 | note | Category - HP
7b3fbb47-6c18-5906-8b49-142c847cbd29 | note | Responsibility - SE/PE, Supervisor
7650abd4-30c6-57cb-a159-06b13a1fd8b5 | note | Verifying Documents - This ITP Signed Off
87bc0d97-0c89-5bcd-a19e-f1d001359a61 | note | ○ Attach: As-Built Survey Pickup
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Non-conformance Report (NCR) Closure
c2f84f18-400d-58f6-8491-9cc14dff145b | note | Reference - MTM Quality Management Plan
85319657-2aaf-5949-be9d-86182dae998d | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
dc6970cf-826d-5898-8e24-1cb065af6ab3 | note | Method - Document Review
177511fc-4c78-5e0b-ba76-8b0b6cb33170 | note | Frequency - Once, prior to closure of this lot / element / Work area
08139832-5726-5cc4-bdaf-1e63eb35c616 | note | Category - HP
a46fc220-538f-50bd-ad37-ac3f53e516be | note | Responsibility - SE/PE
fa915a49-cda8-5d52-8090-9788bda38b00 | note | Verifying Documents - This ITP Signed Off
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
e170270c-f76f-5a59-9a6f-3ef9005441d2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ff67cf10-6663-55fc-855c-70064bdecc56 | textbox | Name:
de43b596-6e28-5b51-a63f-d327acae3342 | textbox | Position:
f68df28f-907e-500d-a5cb-e1c172d4d41a | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing Rev 1 | itp | ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing Rev 1 | faf72238-b5a3-423f-a401-7c94bfc3ebe7
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
b3151586-0975-51a3-a57a-62c631d512b3 | note | Document Title: ITP-169-RAIL-BRUNT-Rail Delineation Permanent Fencing
679cb857-8599-5808-b08e-23d16b72143c | note | ITP Description: BRUNT-Rail Delineation Permanent Fencing
7f26d3e6-a7f2-5c4b-a4df-1b9ca9518c6e | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
f21c3d9f-54a3-50b9-8262-c5750304731d | note | Discipline (e.g. CIV/STR/RAIL): 169-RAIL
e5904453-b019-5726-83ae-90e5d4806d21 | note | Revision Number: 1
c6d1510a-752b-52f5-845d-313b2d1dfe9b | note | Revision Date: 20/05/2024
92d0a809-82d3-5f48-923a-c2dffd332602 | note | ITP created by: Jason Lee
e4317549-5cfd-56c6-9c05-211c2ca9d9a1 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
a63ce7c3-da84-5a7f-b004-c649d567de98 | note | Reference - IFC Drawings VicRoads Section 610, VicRoads Section 630, VicTrack STD_C0031
| section | 2. Materials
| checkpoint | 2.1 - Concrete Mix for Footings
4be130f8-e550-59cb-aaff-d27ef89b3b39 | note | Reference - IFC Drawings
04f87a93-219f-51f1-b716-cf4c2f1f9549 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
4ace9808-4641-5dc3-8306-86eb8e4b19a9 | note | ○ Minimum Strength of 20MPa concrete to be used as per IFC drawings.
d6612057-a706-540c-9e27-d59c2055ef8c | note | Method - Document Review
647c565a-4410-5444-8ce6-fbdcce34b4dc | note | Frequency - Each Mix
cf2511e7-6188-56ce-a95d-dd479297bc12 | note | Category - HP
0e65bcc6-beb0-5301-8ef3-b2e8a6c1bff4 | note | Responsibility - SE/Site Supervisor
11407b73-1393-5c71-9321-df1248c9f500 | note | Verifying Documents - This ITP Signed Off
495249bc-6e84-57a9-a0c7-ef4f4c678650 | note | ○ Attach: Supplier Material Conformance Certificate, Delivery Dockets
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Weld Mesh Fences and Gates
0bfb3489-887a-52c2-9670-07333dbdbf10 | note | Reference - IFC Drawings AS4792
47d06fbe-1d52-5b49-b571-ea202b5896d0 | note | Acceptance Criteria - All weld mesh fences and gates to be galvanised steel with black powder coat unless nominated otherwise on fencing plans. Galvanised coating shall comply with AS/NZS 4792 with a coating class of HDG 300 mimum
85f4e2df-b2be-5295-9245-4316526cdf62 | note | Method - Document review, Visual and Measure
316d58ac-3a5c-5ffb-b7d9-2dc10c33603b | note | Frequency - All elements
fd355ccd-4c57-5c12-82f8-e429cd6c5e3b | note | Category - IP
699b4357-f849-5cc3-91e5-9e72edf671b8 | note | Responsibility - SE/Site Supervisor
67f2d693-50a6-5628-a243-e9b0c9f998e0 | note | Verifying Documents - This ITP Signed Off
6b173922-3cce-5e77-a92a-5c92b431aad1 | note | ○ Attach: Supplier Material Conformance Certificate, Delivery Dockets
| section | 3. Pre-construction / Pre-installation Activities
| checkpoint | 3.1 - Survey Set-out
2c19639a-eb66-5482-8666-b02cac82b553 | note | Reference - IFC Drawings
0951d8d1-c071-5e0f-bfab-e1dca35b9b78 | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays.
c1a564dd-dda9-50c7-99e9-7980a350cf95 | note | ○ Offset checked against the running edge prior to installation of posts.
73d16059-8aae-5bae-ac51-28587450fab1 | note | ○ Engineer to verify alignment of posts using string line or equivalent.
61568d14-90d4-5b5c-bf92-ba14abc93d10 | note | Method - Measure, Visual
2d63d5f0-c8bf-50ba-b306-fbecacbe86ab | note | Frequency - Each element
ad7b7468-33f1-5b70-aa94-2134b4fa086d | note | Category - IP
d30b4e72-8147-5a3d-b6be-0b027f9aba99 | note | Responsibility - Surveyor, SE/PE
dd94f09b-b2bc-5814-b635-8bbe32a78e6c | note | Verifying Documents - This ITP Signed Off
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Excavation works
1333b0e3-3469-5b37-856f-f6016849f220 | note | Reference - IFC Drawings VicTrack STD_C0031
26d04250-d18f-5d04-8934-b1cd3621858c | note | Acceptance Criteria - Excavation for post foundation must not undermine track, footing of existing structures and comply with the PTDT requirements.
0654f0b6-12f3-5870-b47c-e7105aa5af8b | note | ○ Follow asset owners guidelines for work around their service.
a84f16e6-1259-574d-bca1-e983d6152d96 | note | ○ Excavation must use Non Distructive Digging in the rail corridor
fcea1b97-28ea-55ca-95be-08a355b63a21 | note | Method - Measure, Visual
edf9c62f-d225-58f8-8ee1-09c025dc0c19 | note | Frequency - Each Post
238215a5-beaf-50c3-93cc-a498dfff0c74 | note | Category - IP
b6fccc62-dbfc-5aff-939a-5ea9a4bae0d5 | note | Responsibility - SE/Site Supervisor
90759db8-6c6b-58ea-a011-bc5f5b877f0e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Ground Conditions
77e2146e-f92c-5a17-bd4a-58ba2ab82e3b | note | Reference - IFC Drawings
e479bce2-3e64-5200-94ed-dfce50eb3ee7 | note | Acceptance Criteria - All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
6b74a14e-3c07-53f8-a32b-d0120740508e | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
b05b21a3-7fe1-586d-ae20-af0c44a35c49 | note | Method - Visual
212549c5-960e-578f-8075-c69e3bc03258 | note | Frequency - Each post
096fd146-6732-5880-9291-cc7479056af2 | note | Category - IP
f63b73a8-0861-5f36-a891-87250c43ccef | note | Responsibility - SE/Site Supervisor
8e967296-4434-51f9-a899-39527945fe61 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - MTM OHW Structures
1ed50e81-317d-5080-984a-44bbf83f6df6 | note | Reference - IFC Drawings VicTrack STD_C0031
6a6756e1-525e-5c3e-b8c0-ef31bc58f1cc | note | Acceptance Criteria - Fencing must be a minimum 2m away from OHW Structures.
35afd814-8d2f-5734-a63b-7ee78f2cde0d | note | ○ Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
23f9ee54-bedf-5330-a7a8-5a777a799afe | note | Method - Measure
1faaaba2-ae32-538d-8444-8bdb7f963fc2 | note | Frequency - Each Overhead
1f22a424-a07f-5291-b258-62096bce38a2 | note | Category - IP
ed558fc3-046b-5c01-8e11-ce4fb5206eee | note | Responsibility - SE/Site Supervisor
3443b690-5e5e-5504-9a3e-abc1702e860f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.4 - Fence Post Foundation
005bb2e6-68ae-5dfb-ab88-5f45a1e36e8d | note | Reference - IFC Drawings VicTrack STD_C0031
31c47802-3076-579f-b73d-6bbf94d1bd4e | note | Acceptance Criteria - Typical Footing: Footing dimension 600mm deep, 200mm diameter
30acd9b5-e40e-5624-b0e1-40a90d821a41 | note | ○ Gate Footing (3m to 5m gate opening)
8568ad40-ed31-50cf-9fcb-5cc25c94fe61 | note | – 300mm diameter by 1200mm depth
94c93b76-3e9f-5579-8c93-71873c9e448f | note | ○ Gate Footing (5m to 8m gate opening)
6540b884-9ef6-541c-a156-3e7bd0caee0c | note | – 450mm diameter by 1500mm depth
a5a1efb5-d75a-573e-bf76-8761d8364d03 | note | ○ Gate Footing (9m to 12m gate opening)
015d6158-a781-5d7f-9f2d-474f6f702ec3 | note | – 600mm diameter by 1600mm depth
1ff7bf12-c0dc-53cf-b61c-0fdd102ea370 | note | ○ Seperation Gap Footing
e2685df1-7a0a-5635-b97c-dc3132aee5b2 | note | – 450mm diameter by 1200mm depth.
e80b15c7-bc71-5567-acb4-1281db11e346 | note | Method - Measure
fce345ce-7dbe-5cc3-8a48-2c74cfa31f27 | note | Frequency - Each footing
775390f5-35a5-5554-8a74-d8e640973401 | note | Category - IP
bb7f63f1-9b50-51bf-8d1a-fbbf59b1bbd0 | note | Responsibility - SE/Site Supervisor
3f5b27a7-1518-506d-a855-c4cb619135ba | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.5 - Concrete Footing
1d5ac4bb-2db8-564e-ad6a-cc04274696fe | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
ef143cf0-b889-55ba-8d05-b476d79c8bfd | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
c4c16b7e-1247-5d0f-96c0-7d80f5ab29ba | note | ○ 0m³ to 10m³ = 1 sample
e56c634e-11df-5f96-978a-1d10253449fd | note | ○ 10m³ to 25m³ = 2 samples
d77f004e-1012-56c7-bb3c-19c9e875b906 | note | ○ 25m³ to 50m³ = 3 samples
bb99cde4-f5ec-564b-ba7d-566bbbbbd680 | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
db66b05d-946d-544f-b279-0e8ff0287142 | note | – For each additional 50m³ and additional sample shall be taken.
12bbc8f9-45f6-5fd1-a615-e1c57c82f2db | note | – Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
5e9618fe-244c-5070-9db4-e357158d93b6 | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
fc5841bd-5e7e-5665-9687-8ef1728a3553 | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
2b998c0d-728a-5ab0-9b2c-b62f4ae38cd7 | note | Method - Test
e532c716-1eb0-525b-b186-e1430cb47f59 | note | Frequency - Each element
43134551-ba9f-5667-b9d8-99cb1d103062 | note | Category - IP
5de9a188-acf2-592e-8cf1-c56d1eb60ad0 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
7e8ef7f6-17da-52fa-bdad-608fddaadaea | note | Verifying Documents - This ITP Signed Off, Concrete Pour Record
| checkpoint | 4.6 - Fence Post Installation
6e2b8f8c-4dcf-50b6-a666-a384a837589f | note | Reference - IFC Drawings
6c910918-c3b9-5782-8052-6862ebb6640e | note | Acceptance Criteria - Maximum post spacing to be 2.405m. Spacing may be locally decreased as required to avoid existing services
8bc9733d-0d9f-5e81-ba49-5e11d434e817 | note | ○ Max. post height 1800mm above ground level
17a6ef33-6967-5b15-8ae5-6683e6a3802a | note | ○ Vertical Tolerance: ±20mm from the design line.
dbf60356-2e71-59cb-8dc0-f4c87088003c | note | Method - Measure
4169822e-0a23-50f7-bce5-ea5c9119257c | note | Frequency - Each post
e9a4db49-3159-5082-8dcd-18dc543a87fd | note | Category - IP
3604e5e9-5151-5af7-8c77-6e8f34dd4cf2 | note | Responsibility - SE/Site Supervisor
53eb02fc-abb0-5a0b-be12-0dab70043a59 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.7 - Chain Wire Mesh Installation
5d556ebc-be96-5b12-a24f-210359d37cca | note | Reference - IFC Drawings VicTrack STD_C0031
96922693-bd1e-5f4a-9b13-4b0383108ec7 | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with Tek Screw and 25mm U-Clip
e1ebf08c-87d0-57d2-8568-e299ef36f189 | note | Method - Visual
94d3edda-2755-5928-9786-c4adcbe9fbe9 | note | Frequency - Each element
760ea1e2-774a-52c5-8bf5-4bd791f2c0cf | note | Category - IP
05ebb23e-b29c-5c40-bdb7-bbca75c448e5 | note | Responsibility - SE/Site Supervisor
2c07c968-d37d-54f9-84a0-5f31ccd0ee2e | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.8 - Bracing
8d2bd715-0b75-5da1-8e0f-c8f8a429c216 | note | Reference - IFC Drawings
8c0fff40-fa8f-57e0-a042-3634b1452a1e | note | Acceptance Criteria - 50 SHS x 2.5 Diagonal bracers to be installed at vehicle gate as per IFC Drawings
a30c5842-c18d-5c3d-9b22-76ccbd711ea5 | note | Method - Visual
79fe942f-4528-53cf-beac-ad43717f1dd2 | note | Frequency - Each element
85fa0433-1240-57a1-9ee5-51029112784e | note | Category - IP
d22502d4-c51b-5fad-82b5-7bd058d80326 | note | Responsibility - SE/Site Supervisor
b9997421-7da8-5fa9-8f62-84d217be3205 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.9 - Seperation Gap
b7ec6ba6-8b63-5975-8c69-2f7918581a8d | note | Reference - IFC Drawings
67236458-bdb1-5593-8363-d14f800b8ace | note | Acceptance Criteria - 100mm Seperation Gap between the existing fence and new fence to be installed.
4ba66d5c-f487-55c0-87a5-e06e6c6d942d | note | Method - Measure
924456ae-3016-54cb-9118-73cdc80a6ede | note | Frequency - Each element
e54eb5e0-ae21-596b-adcb-7be7aff3b204 | note | Category - IP
31673e24-188a-57f8-87f5-4babc75d9587 | note | Responsibility - SE/Site Supervisor
4e7de637-781a-5fe6-9f71-2dcf8458daa2 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.10 - Gate Installation - Gate
e0f8930a-aa0b-5763-9c22-2758c26bc57b | note | Reference - IFC Drawings
9130ebe5-d246-5545-952b-ba6af0a2f4a2 | note | Acceptance Criteria - Gates to be fabricated to the installed gate posts with equal spacing welded mesh.
0adee4a2-ee2a-5914-b89b-8d31707cf4a9 | note | ○ Braces and Verticals Mesh to be installed as per the IFC
294703ca-f8ec-50f1-ab55-90a3c2e86a46 | note | Method - Measure
f2ba769b-b267-5734-8115-437b98c0fa4c | note | Frequency - Each Gate
dd6730ec-af86-5a16-a296-e54b348ed5fc | note | Category - IP
99d86f1e-d127-5284-a1ec-d324748c32bb | note | Responsibility - SE/Site Supervisor
d139694e-4734-5e97-ace7-f7414a39001c | note | Verifying Documents - This ITP Signed Off
| section | 5. Post-construction / Post-installation Activities
| checkpoint | 5.1 - Fence Height and Track Clearance
f4d15bc5-fb01-5d43-899c-a1033b67ccd3 | note | Reference - IFC Drawings
06b44aec-0878-5f53-b706-8599e2c2bdfb | note | Acceptance Criteria - Vertical gaps between finished surface level and the bottom of the fence panel are to be 50mm minimum to 150mm maximum
141c372c-6233-504c-a3c7-4e2436482ef8 | note | Method - Measure
440b6a3a-7673-5dda-97b5-03c1eaa08005 | note | Frequency - Each lot
f6803116-aa5b-527a-be31-6cb57192f518 | note | Category - IP
0109a59e-ccf6-5f2a-a800-2e07a2991cba | note | Responsibility - SE/Site Supervisor
e754ee7e-bce7-5414-9b25-f31f3da58518 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
b4a423fb-9e8c-57c5-86c3-b38e72fb9239 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
b279f71f-d832-5366-bfcb-08aa370db0ea | textbox | Name:
d1797115-dcc8-5589-baa8-82990dec7919 | textbox | Position:
9cabf845-43f7-5185-b226-9a44dada08cd | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-170-CIV-BRUNT-Concrete Pavement Construction Rev 0 | itp | ITP-170-CIV-BRUNT-Concrete Pavement Construction Rev 0 | e6494dd3-71d3-4612-ac18-9dc724e397ad
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
0a1dd1aa-74c3-5c84-bbd0-c28e70c35da0 | note | Document Title: ITP-170-CIV-BRUNT-Concrete Pavement Construction
6a7facb1-397b-5dcf-9e7c-b4ca920da144 | note | ITP Description: Concrete Pavement Construction
4cdf22e1-56aa-5b14-8482-ecfefac5ccac | note | Discipline (e.g. CIV/STR/RAIL): CIV
2a823b99-2f0b-5b0e-9143-d267af8fa43f | note | Revision Number: 0
1f96d53b-b1e8-5d4e-acfa-05bd5812ad32 | note | Revision Date: 28/05/2024
932eb5c3-e1ea-596b-a838-dc48973ec2cc | note | ITP created by: Jon De Castro
f7ec6fc3-6e21-55a6-a1fa-0da016d17b4c | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
cd045a00-2f83-5b5e-b030-12699b754387 | note | Reference - VicRoads Section 304 August 2013
| checkpoint | 1.2 - Non Dependent
c8f0d91f-6485-5919-a6c2-bdb6dfc20e79 | note | Reference - VicRoads Section 703 April 2019
| checkpoint | 1.3 - Non Dependent
8b381c8b-f641-5f5f-83f4-b8d3600fc6de | note | Reference - Council EDCM 401
| checkpoint | 1.4 - Non Dependent
db77cada-1785-5726-acea-2d62070e09d2 | note | Reference - Council EDCM 501
| checkpoint | 1.5 - Non Dependent
d33a2c60-4596-5756-bfff-5ed5dc5eb509 | note | Reference - Council EDCM 502
| checkpoint | 1.6 - Non Dependent
e0a113fc-3e41-508b-a24c-a0f55ad20be9 | note | Reference - Council EDCM 503
| checkpoint | 1.7 - Non Dependent
9418ce41-3093-5227-901e-c8a2ba725f2c | note | Reference - AS 1379-2007
| checkpoint | 1.8 - Non Dependent
39653ae0-8306-547a-9384-d1cfb96615ca | note | Reference - VicRoads Section 812 July 2016
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Bedding Material Placement & Compaction
9d70a694-d691-5567-ba3b-f79bdfd5da5f | note | Reference - IFC Drawings: 812.04, 703.21
9a15eda6-f720-5022-8e51-a9eab21510dd | note | Acceptance Criteria - Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
4233f73f-0699-50d1-8552-5e49bf11f504 | note | ○ SUP: SIZE 20mm CLASS 3 CRUSHED ROCK
c09eb076-0b65-50a1-b094-1446bff14831 | note | ○ Driveways PT-08 and PT-08A: SIZE 20mm CLASS 3 CRUSHED ROCK
4828b640-e630-55a9-943c-092432690cb6 | note | ○ Material is registered with VicRoads in accordance with Code of Practice RC500.02.
ed70328c-0153-5450-9072-409f00794d16 | textbox | Enter: Teambinder Material Approval number
12ca4a1e-43bb-5e32-b149-43298bbdaf07 | note | Method - Document Review
ddbdcc33-40fa-522b-af77-82d4fcbe9922 | note | Frequency - Each Lot
6031f430-e903-593b-b866-40d852281235 | note | Category - HP
b01972ec-061c-5a22-bdb5-6be715d43f6e | note | Responsibility - Nominated Authority
5fc6054b-11f4-51ab-b7c0-b82fae5e23c7 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Concrete Mix
f50b83ae-4430-5f47-8d29-270f04d5cc11 | note | Reference - IFC Drawings: 703.05 (a), 703.07
6d04de31-6471-59b8-92f6-8fd148231994 | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
6d82564b-fcbe-582a-8b8a-cafad056f213 | note | – Footpaths: 25Mpa
f2dc787f-2570-5c9e-9db6-0de03e99a5c6 | note | – SUP: VR330/32
3476df60-5385-5fa6-b57d-85c299a9c8d5 | note | – Driveway PT-08: 25MPa
a60fdeba-8d85-518e-8fa9-76b08a0e1d7a | note | – Driveway PT-08A: 25MPa
f7a16607-a339-5203-ac5a-15baa5cf54d7 | note | ○ No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
0025b01c-9d95-5369-bc75-1752cb41b3dd | textbox | Enter: Teambinder Material Approval number
1a37231a-4cdf-586a-9fe7-145366e1ddbc | note | Method - Document Review
09f00e98-ac64-560b-b64a-b91ace288cf2 | note | Frequency - Each Lot
11b923fe-8863-5933-8798-d54ef6e655a3 | note | Category - HP
5fa64cee-1f34-5c91-ab35-f82f0137e053 | note | Responsibility - Nominated Authority
4e79931f-823c-5082-89c1-f7511a9a3431 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Reinforcement
9e5350db-4ee4-5215-a4fd-8bb1a829c742 | note | Reference - IFC Drawings: 703.16
7c109794-9903-5a68-8e9b-5e6fc0565710 | note | Acceptance Criteria - Reinforcement shall comply with AS4671.
6c3cd438-4cf7-5ec1-aa14-eba2a8db22a8 | note | ○ Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
1c39946c-2112-566d-bb67-e5a0e75b5121 | note | Following steel mesh requirements shall apply as per IFC Drawings:
d2bc934d-aaae-5f3d-bdd9-a402c22a6f73 | note | – Driveway PT-08: SL72 Continously Lapped
6109200b-7f93-50d5-a0e0-212a3e292075 | note | – Driveway PT-08A: SL82 Contniously Lapped
82ea848b-b8b8-547a-932a-74db2e3dc1b9 | note | – Footpaths, Residential driveways and Median islands infills: SL72
67b749c6-ee31-53d0-84bc-3af754641350 | note | – Industrial Crossovers: SL82
f1434acf-b029-54db-92c0-56d3c1f22033 | note | – Traffic Islands: SL72
2710998b-caf2-56ae-aa1f-02773f63ebcc | note | – SUP: SL82
5da4cfac-61ba-50bf-962c-f323fe9c87b0 | textbox | Enter: Teambinder Material Approval number
4c4c60a1-e931-5259-8282-430398c6a8ba | note | Method - Document Review
ebbd4cc5-7e2d-55fb-98e0-fbc32d587884 | note | Frequency - Each Lot
7e210870-fcc7-53f7-b031-e6449651350b | note | Category - HP
0dab344d-4866-593d-a92b-dce049d72aca | note | Responsibility - Nominated Authority
222024a3-d310-551f-94db-484bb51bc0ed | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
cabe0da3-44ca-51b2-8684-a3b3593e99a8 | note | Reference - 703.09, 610.17 (f)
ec0dcf82-c293-5845-b445-ad74ab045aad | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
0bddcd94-5909-5bb6-9c51-8ae916a133ac | textbox | Enter: Teambinder Material Approval number
192b7e77-7996-5368-a460-be2171711713 | note | Method - Document Review
59eab37b-856d-54a0-b057-e2edaad5a52c | note | Frequency - Once, for each product, prior to placement of concrete
9b7224e5-daf3-5ad7-9073-50a2b5e083c5 | note | Category - HP
8e1ee667-998e-5579-8356-d187f32b1878 | note | Responsibility - Nominated Authority
d2a45049-0930-5680-9545-a99db2bb24f7 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
adce7d7c-5a22-5567-91de-9c6002a4e9c6 | note | Reference - 703.10 (a), 610.23 (d)
f2a2f5af-f6e4-5379-9d3c-d75ed988448c | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
88c8d594-6046-5b59-a4b4-4e18cfd61eb6 | textbox | Enter: Teambinder Material Approval number
1a562d8f-567f-5aa9-a919-7716e3385d02 | note | Method - Document Review
ccac50da-ab94-5dfd-ab3a-24bef7158eeb | note | Frequency - Once, for each product, prior to placement of concrete
18cd2952-1583-5be2-b91a-b5ec1f7ce928 | note | Category - HP
871fa52f-0abf-5e98-8c64-fd524d765fd5 | note | Responsibility - Nominated Authority
dea0eec1-ce79-5a56-9f89-a4704d32ac98 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Survey Set-out
53a17a8b-91fd-5063-a598-6e5d60745364 | note | Reference - IFC Drawings 703.17
9fbf3ef3-2ec2-5ca9-aa99-c0da8814eebc | note | Acceptance Criteria - The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
eb67f936-35ef-5541-b2da-da730ee3da11 | note | ○ The Nominated Authority will review and confirm the set out.
2d757139-e6bd-56da-8e0c-588d10f440cf | note | Attach: Survey Report
3a4b18a9-2a4a-51dc-91da-e29d6d9944f7 | note | Method - Document Review, Measure, Visual
efa94041-8461-5649-930f-d2f4c94756a8 | note | Frequency - Each lot
305c9965-88d2-5426-adbc-4919bc09919e | note | Category - HP
4b2f7d38-5068-5638-927f-4a4f0f9ab7b9 | note | Responsibility - SE/PE, Surveyor
bfcf589d-9f54-51a5-90b4-a8628b2edecc | note | Verifying Documents - This ITP
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Lot Map
449bb60a-0a0c-5a6e-8fb8-73f12f316ebf | note | Reference - MRPA Lot Management Plan
4b95c8b3-5e47-5adc-9795-9875a207d530 | note | Acceptance Criteria - Attach Marked drawing indicating the location of this Lot
8faa6043-bdf7-587e-ae28-33eafadbbaa8 | note | Attach: Lot Map
64207803-8932-55a4-9c0d-4a2c15ad1592 | note | Method - Document
87b1ec5f-8009-5df3-b3d1-397da49fc2c3 | note | Frequency - Each Lot
c10e8e78-965a-5c87-8275-966ae1ba51e5 | note | Category - HP*
38f1f8dd-fafa-5480-8e70-91cdf67bcf26 | note | Responsibility - SE/PE
b8c897f0-564e-5749-9c8d-f8d8aee2d465 | note | Verifying Documents - This ITP
| section | 4. Pre-Construction Activities
| checkpoint | 4.1 - Site Clearing & Grubbing
e9fd1f5f-3194-5313-aa73-486336e75d93 | note | Reference - IFC Drawings
1cdddde5-9e23-546d-968e-be48baed29c1 | note | Acceptance Criteria - If not completed during the site establishment, the work area needs to be cleared and grubbed.
78aa99aa-672e-5282-a0ea-0b96ce7b4d11 | note | Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.
fc84629d-6492-547e-a277-e92f9dfdb6be | note | Method - Visual
70e8c683-354d-5098-aeb9-b2f553f0a229 | note | Frequency - Where applicable
893c0f11-3b05-5725-bb17-09ca943bac44 | note | Category - IP
a8377e52-bb5b-505f-9c74-b4f887d501fd | note | Responsibility - SE/PE/SPE
c35d6f34-8b3c-5add-9161-e0bfe2101d90 | note | Verifying Documents - This ITP
| checkpoint | 4.2 - IFC Drawings
58990205-1d4f-517c-8549-52c291dfe49d | note | Reference - MRPA Quality Management Plan
927e5636-b9c1-537d-a245-18d76dad2237 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
db6e835b-8e3b-5eb6-8f54-0738aed985ef | note | – Using the correct and complete set of drawings
a861fe2a-e270-57c1-b720-bd408446c62e | note | Method - Document Review
5e1b8a1f-b72a-5819-96ce-296992bd551b | note | Frequency - Prior to starting Works and at regular intervals
447badfa-478f-5c0c-9b41-3888cafcf65a | note | Category - HP*
f3d82e03-0629-59ed-89d1-1d3ea8443db2 | note | Responsibility - SE/PE/SPE
f18a6ad2-324f-57ff-a5ac-29c81673974e | note | Verifying Documents - This ITP
| section | 5. Construction Activities
| checkpoint | 5.1 - Excavation
f95a514c-916d-555b-ab3c-40688761f39d | note | Reference - 703.20 IFC Drawings
bf42bf9a-e604-584a-981b-9ca006d752c4 | note | Acceptance Criteria - Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
b27235e4-5dd9-5259-8cd7-4b8c57cf8320 | note | ○ Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
61cf5d57-1a8c-51bb-9f33-7be71a752717 | note | ○ Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
eb556e08-6b33-57e7-b678-27604015a21b | note | Method - Visual, Measure
e29a1c86-f648-5267-a73a-82a898aac16c | note | Frequency - Each lot
ef2bf7db-64e6-5e74-849e-8dbf6185ab5e | note | Category - IP
dfc5dc06-dcb9-5a2a-b105-48a17074b37e | note | Responsibility - SE/PE/SPE
d50d1bc8-0dcb-52a9-b629-9df18a0931c2 | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Excavation-Pavement Thickness Increases for Crossings
71644b24-8641-52c1-ae1a-f071fdb5c3b3 | note | Reference - IFC Drawings: Relevant Council Drawings
f770849b-aaad-5462-8254-1c2d9dfb26ff | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
366c2caa-1803-50f7-b197-06bf83481bf1 | note | ○ Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
2aa669c4-e428-580f-ba28-11915ddc38e2 | note | Method - Visual, Measure
c63f1bcc-184e-596d-96fa-f0cabde0ea3c | note | Frequency - Where applicable, each lot
2deeeef8-3618-5883-a723-7586544165e4 | note | Category - IP
1ec28c64-3da5-57e1-8246-bf05f4f84801 | note | Responsibility - SE/PE/SPE
45200c41-0fba-5472-932b-7946a097f751 | note | Verifying Documents - This ITP
| checkpoint | 5.3 - Bedding Material Placement & Compaction
c7e09415-e627-5ffa-ba0c-d52d42336684 | note | Reference - 703.21 IFC Drawings
f0432e21-e7d1-59f2-8572-18a1e35c5521 | note | Acceptance Criteria - Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
6cd92947-41f0-5bdd-b3ab-ea0faa900de2 | note | ○ Footpath: 100mm compacted thickness
bd214eb1-6ec4-5ba5-a06d-7dc709409187 | note | ○ SUP: 150 mm compacted thickness
60ee008a-b90f-5a21-a02f-9c0f351c1914 | note | ○ PAVEMENT TYPE PT08: DRIVEWAY (IN ACCORDANCE WITH EDCM 502): 50mm compacted thickness
641caafb-69b5-5000-aa7b-4dd8f1ffe293 | note | ○ PAVEMENT TYPE PT08A: COMMERCIAL DRIVEWAY (IN ACCORDANCE WITH EDCM 503): 100mm compacted thickness
0a283f6e-aba7-58a4-8c2c-40c0bc4e65d5 | note | ○ Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
f435c6c8-e762-51df-ab25-675c39fef01c | note | ○ The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
5dd222a3-c73d-563e-a536-6653cd3b0c68 | note | ○ All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
c3272f0c-5fa2-51ff-9209-78756eaf1c7b | note | Attach: Bedding Material Delivery Dockets
7e878ea3-54d3-59e9-a847-3f5221fc93ea | note | Method - Visual, Measure
0c249c4a-9fc2-5779-85ae-c80d04b1e1e9 | note | Frequency - Each lot
d439da89-277c-5f88-b342-1ce82c1bf779 | note | Category - IP
6cfa0e70-7ba9-5d31-822b-548ef5b12a50 | note | Responsibility - SE/PE/SPE
d14fc923-d75f-53a6-b1b2-5c2fec62708e | note | Verifying Documents - This ITP
| checkpoint | 5.4 - Compaction Testing
c7c8a42a-b06d-5f9b-a093-c8d35354ccfd | note | Reference - 703.21, 304.08 (a) & (b), 304.11 (a)
e28fb9f3-fa3b-5071-b2af-55451dc6738c | note | Acceptance Criteria - Compaction shall meet the following requirements:
dfc5f693-b4fd-513a-b691-c47fc6279785 | note | ○ Scale of Surface Level Measurement = Scale C
41c53b02-bacb-558e-8085-dc2761262e92 | note | ○ Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
4972168c-848e-5a49-a219-a4b5d19899df | note | ○ Mean Value of Density Ratio % (3 tests) not less than 100%
0efd3d0c-8b64-5bcf-b6a3-d60bd710243a | note | Attach: Moisture Content Test Results
91392357-b63b-5d3c-ba47-1746538d002d | note | Attach: Mean Value of Density Ratio
6d70ac30-5518-56be-98e7-a8f444f0e12a | note | Method - Document Review, Visual
09959da2-ecb4-5ac1-a282-79a791c6f361 | note | Frequency - Where applicable, each lot
06084254-ff89-51d9-9b97-2818852b18e5 | note | Category - IP
245c5c1f-0576-5ce5-a2a1-2fec2a260ba2 | note | Responsibility - SE/PE/SPE
b44db9dc-47e2-5ec7-8fd4-1f8734b0c91f | note | Verifying Documents - This ITP
| checkpoint | 5.5 - Proof-rolling
94326304-a18f-51d8-8015-41a00298d2e4 | note | Reference - 703.21, 304.08 (b)
91c7cf9b-a9e6-5e84-8100-1b5f19c2b72c | note | Acceptance Criteria - Bedding material to be compacted and proof rolled before any construction.
4fa7c20d-1f4e-57af-bcd8-a12a03ad8190 | note | ○ Withstands Test rolling without visible deformation or springing.
1bf9434a-bcaa-5b9a-9b38-8ba59c90fe9a | note | Method - Visual
91c3dfe7-e43a-5558-a61b-e2102bf64796 | note | Frequency - Where applicable, each lot
0024d461-a840-5c45-a3e7-65489f164f50 | note | Category - HP
01b070fd-6634-5b5d-827f-bb7bb10557ff | note | Responsibility - Nominated Authority
28656250-32b8-5362-934f-3758833b85e1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Formwork Construction & Placement
accca52a-458a-5f0d-b463-c7633ef9c6f2 | note | Reference - IFC Drawings 703.12
59ab3d3a-9e75-5d7a-bc8d-b8b82cdf2db4 | note | Acceptance Criteria - Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
c8ecd387-bc99-5cb1-b858-1af8ad00fde1 | note | ○ Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
5c9469e7-bf10-55e5-8de7-685ff8e46a01 | note | ○ Joints in formwork shall be constructed such that loss of mortar is prevented.
f7fdddbe-f8cf-56e4-af6f-ca9093cfb50f | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
1366696c-4b3b-55f0-947b-30a1e5b1938c | note | Method - Visual, Measure
3b451518-0321-5377-beb6-e76641c03861 | note | Frequency - Each lot
25235d0f-2df6-50ae-b0f5-7d455539f207 | note | Category - IP
6117185f-46bb-5aed-a4a8-dea70b6ddcc2 | note | Responsibility - SE/PE/SPE
f078f9fd-aaa6-585a-ae4c-c4ed1ac929db | note | Verifying Documents - This ITP
| checkpoint | 5.7 - Construction Joints & Matching Existing Surfaces
9f9bc5d6-9734-513d-a64e-eee4d0642b65 | note | Reference - IFC Drawings 703.24, Relevant Council Standard DrawingsRelevant Council drawings:
39eea0ba-ca71-5b8a-a597-5e4ee76d32cb | note | Acceptance Criteria - Where applicable, construction joints shall be placed where the new construction ties into existing structures.
bb5a9d0a-d437-5be7-8b7f-7b70587c3cec | note | Consult the relevant Council Standard drawings for the joint detail, these may require:
7d64cc02-432d-5448-8854-9acf4035b296 | note | i. Concrete cutting of a shear-key
7733eb85-f3a5-5d2a-aa5d-fa20b146dfb9 | note | ii. Surface roughening
d036d6de-93b7-52d4-af3d-ceb8d806dad9 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
4eab7937-0834-5988-9f00-6ca43eb8d395 | note | iv. Cutting a groove for sealant
47cb437f-02ec-597a-b556-eda340a467fb | note | ○ Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
96c93980-de6f-5f42-a50e-3de7bfdb222f | note | ○ Transitions between different profiles shall be made in accordance with the drawings.
f69b756a-56df-5ebe-819e-fc5df9749cd4 | note | ○ Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
bfec1140-9031-5c75-961f-4d0ccd07f92f | note | Method - Visual, Measure
3d478277-ccac-5a9c-b432-dc9e9d75643f | note | Frequency - Where applicable, each lot
bd4193fd-ff7a-527f-b828-e0390eec85f1 | note | Category - IP
a06bea59-7384-5280-aeeb-f9db3320b059 | note | Responsibility - SE/PE/SPE
7307db8f-92ff-50bc-9ba0-13cdf19d4b36 | note | Verifying Documents - This ITP
| checkpoint | 5.8 - Isolation Joints
bbae41f7-8cfb-545d-b918-e648f40ac172 | note | Reference - IFC Drawings 703.26 (c), Relevant Council Standard Drawings
8b69024e-c5e8-5f59-b365-ee7ccccf2b8d | note | Acceptance Criteria - Where applicable, isolation joints shall be placed:
687bff9a-eb3b-5b77-b917-cbbaf30c5038 | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
5623300c-dc39-5c52-b88b-7410d2181c50 | note | ii. at any location marked on the drawings
f613c143-f76b-55c5-acdd-991f1c3547ed | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
5a3c966a-0583-5c52-ad6f-b2b6d2d04589 | note | Method - Visual, Measure
c4875f6e-684b-5fe7-adda-e41e91ae945f | note | Frequency - Where applicable, each lot
70697f0d-8a12-5f79-897f-a719de127058 | note | Category - IP
eb2bf8ae-e27b-55fa-91e3-223f1ec0dbd9 | note | Responsibility - SE/PE/SPE
251b6194-9d2c-5bfc-8d7e-719f735c6b48 | note | Verifying Documents - This ITP
| checkpoint | 5.9 - Expansion Joints
91c46190-7e5d-507e-b335-fccbc4dc265e | note | Reference - IFC Drawings 703.26 (a) (ii) & (b) (i), Relevant Council Standard Drawings
9d036ecd-493b-597d-a2d5-eebeafcb3754 | note | Acceptance Criteria - Where applicable, expansion joints shall be placed:
cb93eafd-ea53-5d1a-b531-23605141ec04 | note | i. on either side of vehicle crossings
59932dea-230a-5ab8-8eb9-37f18eeae9d9 | note | ii. at junctions with existing footpaths and shared use paths
a4fe69c2-2c24-5bf6-8b1e-5a370a9e63e1 | note | iii. at junctions with bridges
3e043b7b-e299-5d8d-aa30-38ec25efdd6e | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
c12553e0-324b-591b-ba4b-ceafb8230fa2 | note | ○ The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
283150b0-a24e-5aac-b69e-93ef220f4232 | note | ○ Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
c6c7b24d-35d8-5b35-afa5-9a7d0a8798b0 | note | ○ Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
394b2f24-1fec-5151-82ec-8d33f304f6e9 | note | Method - Visual, Measure
2af9d3ac-f897-5ce1-97f6-09280de98266 | note | Frequency - Where applicable, each lot
5e7a767d-d9f8-52e2-a64e-ee06ef6a6027 | note | Category - IP
220225cb-9715-525f-8f1e-67d813ab8008 | note | Responsibility - SE/PE/SPE
e293660e-6521-5b33-bdb8-963588b848b8 | note | Verifying Documents - This ITP
| checkpoint | 5.10 - Reinforcement Placement
e19a2860-d9e4-5de2-9956-467109c9d077 | note | Reference - IFC Drawings 703.13
d7e6c58e-86af-5f57-96d7-53ea2b2a95c1 | note | Acceptance Criteria - The correct mesh type and location as shown on the IFC drawings.
459a1644-daf0-5654-ab56-2d4ccf28b6be | note | – Footpaths, Residential driveways and Median islands infills: SL72
f06813ea-394b-54d3-a30e-754a26975b4e | note | – Industrial Crossovers: SL82
5a8e049e-9364-5a28-ab79-266525371945 | note | – Traffic Islands: SL72
1a015fde-878e-5d27-a4a9-74309537b164 | note | – SUP: SL82
33760e75-a28e-5cb8-8a27-4194a5355a6c | note | ○ Minimum cover of 50mm at edges has been achieved (including tie wire locations).
46ccfe9e-7a4a-5f1f-b1c4-705b86613256 | note | ○ Any splice lengths achieve the minimum length and are in contact for this length.
45926603-d719-565f-938c-cd0eb2595c51 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
f2803149-3f17-52c6-b1cd-f9e9f987720c | note | ○ The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
9d6f5180-d7d5-50cf-82aa-4c90ced4fb27 | note | ○ Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
13492070-efed-5be5-abbe-effca6408c98 | note | Method - Measure, Visual
2780fa1f-cc57-55d0-8f08-e5877c4e7c71 | note | Frequency - Each element
76ef958a-d0d7-5f17-86dd-33919e044cae | note | Category - IP
5c10cf1a-77cc-55ea-b7d6-832e22ffa953 | note | Responsibility - Foreman, SE/PE/SPE
f2750907-76c4-5486-bd39-92a7cfa69a98 | note | Verifying Documents - This ITP
| checkpoint | 5.11 - Pre-pour Survey
45964c1c-98c4-59e9-89cb-1abc318b8e90 | note | Reference - IFC Drawings 703.15
14ed361f-be57-5814-964d-6068279598f8 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
b5412fb6-0b06-53b1-84a1-cad22515800a | note | Erected formwork and base layer within the tolerances below:
8789a89d-b6ff-51b2-b352-e269cd7aba1d | note | ○ Departure from RL = ±10mm
b0925755-91ea-5b93-ba09-2a82f3add819 | note | ○ Departure from alignment = ±10mm
5b50be87-3c69-5880-9462-5cd36a61856a | note | ○ Rate of change of deviation from RL or alignment = 10mm in 10m
390f60f3-4861-5945-9358-64b2a807d714 | note | ○ Irregularities in alignment = 5mm in 3m
9f71e2cd-547d-5de7-b490-840ba82e10ca | note | ○ Section dimensions = ±5mm
52a6f980-9c7c-5371-a941-3899b6933d8b | note | ○ Section dimensions (less than 25mm) = ±3mm
62f14c0a-4f18-5344-8b0a-0a4066ae77b5 | note | ○ Width of pavement = -5mm, +15mm
351fd78b-20e4-5128-b613-5a43b23ae601 | note | Attach: Survey Report
dc20e64f-4d25-5a72-a218-6eb1452ce7de | note | Method - Measure, Visual
cc8d28b3-ad82-52c8-acde-5b442c1de6e4 | note | Frequency - Each lot
ee682554-2fa6-5197-b5c5-9eb9c92e2952 | note | Category - HP*
b246759d-92da-5e99-8527-df1e71b325a2 | note | Responsibility - Surveyor, SE/PE/SPE
ca248feb-8575-5e7e-af77-2edd61d82209 | note | Verifying Documents - This ITP
| checkpoint | 5.12 - Pre-pour Inspection
c7471ad3-e39d-58e7-a18e-c22eb734608e | note | Reference - Section 703.09, Section 703.21 Section 610.17a), b) & c)
069b1b70-b4c5-5dea-a91f-54607cac600b | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
1a05b18c-2d87-5fb0-a86e-ec987e810cdf | note | ○ Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
6766b081-54df-52d4-8477-d844bc83c5b5 | note | Method - Measure, Visual
d5ff60e1-78fa-5284-a7c3-10b8b22c6167 | note | Frequency - Each lot
7e5b7394-e421-5541-9f16-b93f20e77e1f | note | Category - HP*
284693e3-2312-54c7-ba97-1cf54340ed8d | note | Responsibility - SE/PE/SPE
f963219c-f45a-5b21-ba8e-34c0d50a9627 | note | Verifying Documents - This ITP
| checkpoint | 5.13 - Weather Conditions & Evaporation Limits
42c18687-115d-56b2-a5d6-3639f2897584 | note | Reference - 703.09, 610.17 (a - f) Table 610.171
eb55a37b-3bf6-5888-9e2c-cfc6eb49948a | note | Acceptance Criteria - Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
95c2eb94-3a50-535d-a360-113da9b9b534 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
ff1bcfd3-2408-5d7c-b3d9-63e9358341ac | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
7af85eae-8721-5656-b870-60b29ddc2712 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
36c5903d-e9ac-516d-95e0-3d3a316ca1a9 | note | Record: Required information on the Concrete Pour Record.
b875e977-69ca-59a4-94f1-1e383e8d4fe0 | note | Method - Measure, Visual
8bbf7a6a-9fd8-55f0-8bcd-359ff9bf767d | note | Frequency - Each lot
6279b946-9e92-5e4c-90f1-97751959f1d0 | note | Category - IP
d9f41c1d-aff4-54db-a184-48f5893d8bb3 | note | Responsibility - Foreman, SE/PE/SPE
0411a08d-6269-567b-814a-67ee8faf3e8d | note | Verifying Documents - This ITP
| checkpoint | 5.14 - Concrete Testing - Sampling Frequencies-Footpath
3cb5cda1-542e-548a-bb72-c1125fb84b78 | note | Reference - 703.11, AS 1379-2007 Cluse 6.2
aa0d7970-ccce-566f-98f1-a18d4862e715 | note | Acceptance Criteria - The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
7825ced6-1615-5cd0-9609-ed71e3aa9ecd | note | ○ Correct quantity of cylinders manufactured per sample.
6661f3b1-5978-56a9-8d56-a7523ea4a4bc | note | Record: Required information on the Concrete Pour Record.
ec60e126-0ff5-5eee-8ed3-92e7fb3f2825 | note | Method - Test
d7475e45-967c-53c2-bd6f-f3db34e4b960 | note | Frequency - Each lot
1dca5cb6-f847-5f53-a4cd-1077e208c09e | note | Category - IP
91d85bd1-d2e4-5d0e-83bd-469e393bd127 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
410998ce-9dd1-51c3-899c-d72c28304925 | note | Verifying Documents - This ITP
| checkpoint | 5.15 - Concrete Testing - Sampling Frequencies
5e00e360-4f6d-5e6a-9c69-89d9a14c98e6 | note | Reference - 703.11, 610.16 (b)
d336e22c-cbfa-5178-b6ed-b54b67425914 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
2412cd79-ebed-5464-bee0-13aaae2abf2b | note | Shared User Path:
1aeba906-4db3-5bb3-98c3-83795978d937 | note | – 0m³ to 10m³ = 1 sample
ddaac6d1-f651-5f55-8efa-f019ba5c1f91 | note | – 10m³ to 25m³ = 2 samples
c2a93de0-aa3a-5685-9482-d54527c92fbb | note | – 25m³ to 50m³ = 3 samples
d16d773a-6851-5ce9-97e6-4102ff69f415 | note | – 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
ab58c641-fa83-5e18-a1fe-d83a5ee6fcf8 | note | ○ For each additional 50m³ and additional sample shall be taken.
92208792-1348-56ee-bfd6-56ac1ec0e747 | note | ○ Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
f7397f2e-8a37-59f4-88c7-2ddc8825db80 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
30be17fb-e387-5e28-8984-971d6432ebbd | note | Footpaths:
3f5954ca-95eb-5447-8ee1-a519217b4963 | note | – 0m³ to 50m³ = 1 sample
a0b608d8-3e7a-56db-b961-70f3a85d1e8d | note | ○ Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
8b0e5ab5-ec3f-5c20-86ea-dea385a77f3b | note | ○ Compressive strength cylinders = 2 no. 28 day strength.
8085cb92-9138-5374-9b6b-2ae4bf7a6c5f | note | ○ Correct quantity of cylinders manufactured per sample.
7c1234c0-298d-5259-87fc-707602cde871 | note | Record: Required information on the Concrete Pour Record.
c9f8a67d-5739-5c78-9ac3-09c191e26c5f | note | Method - Test
bd766f9a-f999-5c5b-889c-c0673430a681 | note | Frequency - Each lot
5a259e41-f69d-5b64-a000-15f0ae00624d | note | Category - IP
7b11ace8-c847-50ef-b0ef-dc24716d8a83 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
c6a1b508-b8be-5296-b0da-db7f7a811f05 | note | Verifying Documents - This ITP
| checkpoint | 5.16 - Concrete Testing - Slump
3491bb25-2058-507e-8c4b-f02a16e3db1e | note | Reference - 703.11, 610.16 (c)
48e02244-3c50-5fe3-8b18-c19b66f18514 | note | Acceptance Criteria - Slump testing tolerances =
fe37abae-5d87-5827-a3f7-47b7583f8591 | note | ○ <60mm = ±10mm
1ace7b0b-31d7-5835-9157-ccff7af53a47 | note | ○ ≥60mm to ≤80mm = ±15mm
e4577443-aeaf-58fb-aaa6-755005ed4d57 | note | ○ >80mm to ≤110mm = ±20mm
79c74d34-f408-50bf-a9cc-371695ac28f1 | note | ○ >110mm to ≤150mm = ±30mm
4fd8328c-15b9-59cb-a52c-734dfa9024a0 | note | ○ >150mm = ±40mm
ffe6650d-a792-5b7c-9d0e-dbaf5a34d6ec | note | Record: Required information on the Concrete Pour Record.
ad5f1494-972f-53e3-ba51-debc2fc48278 | note | Method - Test
cd1992b2-ad2a-5793-baf8-0050c7f9bcae | note | Frequency - Each sample
462a3eaf-7cb9-5d37-b0a1-b7514d77d442 | note | Category - IP
457caf92-079a-55b9-af07-0685e703cb28 | note | Responsibility - Concrete Tester
e2cebe64-9df9-50ef-bb92-c6f1de236fb8 | note | Verifying Documents - This ITP
| checkpoint | 5.17 - Placement & Compaction
5ce9c9ea-ad05-5cf9-a7cc-b9e17aea45b3 | note | Reference - 703.08
391d7c9d-1ab7-5986-8838-f111e9c113ca | note | Acceptance Criteria - All concrete batches are traceable.
fe5ef713-2bd6-56d4-ac4f-3bbd4aabdfb7 | note | Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
1ab68e97-9926-57da-b8fe-0632dfcd33e9 | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
b99cd49d-efe7-5dcc-a008-21adc192046d | note | Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
ba88fc11-4a92-5b2f-8e07-4fac51cfa483 | note | Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
66f6599c-760d-5e0e-9f24-c1c0378dafb2 | note | Vibration continued at each point until air bubbles cease to emerge from the concrete.
0860d1b8-1407-52b3-aecf-f0d1ad94d690 | note | Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
d3a21295-43a4-5f64-9378-18eff3ea5ef6 | note | Record: Required information on the Concrete Pour Record.
f8c44bea-3f31-5bf6-8cb9-2c27b36ce2bd | note | Attach: Concrete Pour Record
82d788c4-6e0d-58cc-a6bf-c7814e4adf6c | note | Attach: Concrete Dockets
6531a87f-f1b8-58f1-b1c0-00d2830a5e61 | note | Method - Visual
e06207f3-608b-5502-b871-685d170c9081 | note | Frequency - Each load
0257933c-75a3-54b3-9942-5a6e1b191d8e | note | Category - SP
3f020324-684e-5b8c-b59a-e18094d7ba8e | note | Responsibility - Foreman, SE/PE/SPE
31bdc4af-35ff-5a5f-ac04-9bf112efec42 | note | Verifying Documents - This ITP
| checkpoint | 5.18 - Surface Finishes
b57c57ea-3506-5daa-a11a-91aef5569245 | note | Reference - IFC Drawings, Relevant Council Drawings 703.25
c16b201b-34a3-5417-a228-8f713edbb7d1 | note | Acceptance Criteria - Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top. It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
d72a7b2a-a672-5b0d-b158-d12af210329e | note | ○ After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
c1b7a5fb-ba27-591b-9ee1-9f542fa9e176 | note | ○ Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
a4bd2269-a106-56ea-8cf6-dee15faeaa18 | note | ○ All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
54d30ed6-c554-5022-9f81-ba801257ec82 | note | Method - Visual
98d9b5aa-3ee3-58f2-bffe-33d9acee14e6 | note | Frequency - Each lot
eb2bfa14-3d85-56f6-9d75-79ffe17614d2 | note | Category - IP
1715c024-0755-50c2-9390-df49b7455178 | note | Responsibility - Foreman, SE/PE/SPE
9875fbda-fe86-513d-b341-e00acc083cb6 | note | Verifying Documents - This ITP
| checkpoint | 5.19 - Footpaths - Crack-control Joints / Weaken Plane Joints
c86ba7c1-75fe-5ea7-bd70-36c673a90d78 | note | Reference - IFC Drawings, Relevant Council Drawings 703.26 (b) (ii)
30d6dd1d-95cc-563e-8812-86cf8c1591e0 | note | Acceptance Criteria - Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
be03d189-60ec-57ba-a4e7-17f724bc1618 | note | Method - Visual
4c9e9088-f6b2-5ae4-9aa6-65e302ecbe2c | note | Frequency - Where applicable, each lot
204b26c5-123b-571b-a811-9361a8d5bbbd | note | Category - IP
156620f2-e482-57a3-a069-df7cbde79062 | note | Responsibility - Foreman, SE/PE/SPE
52e1ea12-1500-5a70-8df2-251a4d4adb44 | note | Verifying Documents - This ITP
| checkpoint | 5.2 - Curing
989bf558-ca19-55e2-bb1d-3de92896f123 | note | Reference - 703.1
1cf06055-ab74-5e3d-b11b-47297354bd91 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
50fbbe3a-217a-575d-a588-35cd9fcc5acf | note | ○ Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
ed0763dc-141d-52ec-bc8d-eacac2d51fca | note | ○ The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
df7eb7b5-e637-5fe0-87cb-0c19a0c66f0b | note | ○ Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
9356111a-484a-5444-b1e7-179eaec376fe | note | ○ Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
7c945e46-7edc-5639-9fbe-577d5d9dd8d5 | note | Method - Visual
2f8117f1-b768-5b77-a23a-0e2c2d63e433 | note | Frequency - Each lot
f6845d6e-f281-5c39-82a2-f2e0df4e3b38 | note | Category - IP
ebbdbfe2-c128-5aea-97b2-82fc2b33323e | note | Responsibility - Foreman, SE/PE/SPE
f9337905-b2cd-5cd0-a92e-73660fd0a523 | note | Verifying Documents - This ITP
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Crack-control Joints / Weaken Plane Joints
2a8e547e-084f-5742-84f8-04a4b3f93b4c | note | Reference - IFC Drawings, Relevant Council Drawings 703.26 (b) (ii)
63650a95-5be3-523f-9096-a3000ee2dfc2 | note | Acceptance Criteria - Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
420c7a39-eb75-5ac4-bb8e-574eda905632 | note | ○ <20°C = within 24 hours of finishing operations
080b3f78-f162-5f2d-a30a-1df2a0d41dee | note | ○ ≥20°C - 35°C = within 4 hours of finishing operations
2265a8fd-4199-5e96-b482-0a5957995c3e | note | Method - Visual
67bd7345-91d9-50b8-ace0-7a2ae75a2616 | note | Frequency - Where applicable, each lot
f39abd51-9cba-5b95-9bed-eec7b0b93df7 | note | Category - IP
2d45c371-8025-5abf-b7f7-dcbb67b350d6 | note | Responsibility - Foreman, SE/PE/SPE
5ac7afd9-d85d-5786-8eaf-002e9c00c015 | note | Verifying Documents - This ITP
| checkpoint | 6.2 - Protection of Newly Poured Concrete
efd83b6e-0688-5034-ae8d-45a385daf298 | note | Reference - 703.27
12453847-eb47-5ae2-b075-377391c5e2ff | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
1d94f906-eb6a-56cb-b07b-87c17130d542 | note | ○ Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
770144fb-79c7-5a81-8e06-e6f52b26cbca | note | Method - Visual
32a37c6d-c41b-5a61-acea-81ca2a7db22b | note | Frequency - Where applicable, each lot
9a3301cb-17b7-5942-b471-6340149fc288 | note | Category - IP
e2ece737-0c4c-57d8-aa70-be69a2f7712c | note | Responsibility - Foreman, SE/PE/SPE
7745f679-6313-5913-8f66-10aef0337b1a | note | Verifying Documents - This ITP
| checkpoint | 6.3 - Stripping Formwork
15499149-4d5d-5801-9327-fa6be562d248 | note | Reference - 703.12 AS3610 Table C2
2197f0ba-8fbd-5e2a-97a4-cf7990733695 | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
69ee14ab-3526-556d-8a83-8037c4b4f512 | note | i. 2 days for vertical formwork on external surfaces; and
b4dd2dca-7420-5292-9ddd-8497588f27d7 | note | ii. 1 day for vertical forms on permanently hidden surfaces
c61893ab-1052-5663-9a98-1efcd2d28b16 | note | Method - Visual
abf97707-e319-567e-aaba-d917c4cf2a75 | note | Frequency - Each lot
1265a3d0-257f-513a-b9ae-3f60ed959774 | note | Category - IP
04b8a545-7fa7-546f-9251-16563dc3b335 | note | Responsibility - Foreman, SE/PE/SPE
20d49944-5bb4-506f-8c4d-ed740b7f2f11 | note | Verifying Documents - This ITP
| checkpoint | 6.4 - Backfilling & Pavement Restoration
452ec146-bfeb-58b7-8026-9072a5a81936 | note | Reference - 703.29
4c5a3ac3-ea8a-5036-8f90-75156360844a | note | Acceptance Criteria - At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
25f1d47c-cc01-5883-b483-5a619daeab71 | note | Method - Visual, Measure
dedf2230-3518-5173-8be8-ae70a54a882c | note | Frequency - Each lot
42b8178e-e216-5da3-a857-7af398c42492 | note | Category - IP
bb646d0f-9baf-5664-99ed-9344386ec58a | note | Responsibility - Foreman, SE/PE/SPE
5ca2a20d-bd58-5385-b3ca-eb7f9f3483ca | note | Verifying Documents - This ITP
| checkpoint | 6.5 - Surface Inspection - Cracks
fb9962b0-2f3a-5de6-829e-a0c03ec44380 | note | Reference - 703.3
c833ae65-792f-5e19-9182-fd2e92cb3d2c | note | Acceptance Criteria - No cracks greater than 0.2mm.
8839e6ba-c9b4-5810-b6db-415f6cab60af | note | ○ If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
0d64f901-6ca8-5f5f-8dfd-fd6fdfb18ca6 | note | Method - Visual, Measure
fbcf4e23-0d03-5536-b3ff-53037159a9af | note | Frequency - Where applicable, each lot
b7ec207a-5804-5081-be81-076bda106db0 | note | Category - IP
78d7bca9-2198-5bce-a7d2-683a639d6b4f | note | Responsibility - SE/PE/SPE
5bc3f792-5a08-5806-8fc2-54330cade1b7 | note | Verifying Documents - This ITP
| checkpoint | 6.6 - Surface Inspection - Surface Finish
2bfd6725-da78-5c97-b11f-38f17dc97236 | note | Reference - IFC Drawings, Relevant Council Drawings 703.25, 703.10 (a) AS3610 Clause 3.2
185fd016-4f96-50dc-95fe-a1ac53942b24 | note | Acceptance Criteria - After finishing, all work shall present a consistently neat appearance of uniform colour.
a2414bd4-0a9f-572d-820f-a2261b6dca75 | note | ○ All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
e51f26dd-79c8-551d-9943-2620b6ccdbc5 | note | Class of finish:
0463341a-1569-5d69-810d-f9cafdf69ca4 | note | – Permanently hidden surfaces = Class 4
00a5a00f-1361-5621-8b79-1f3d7718c40c | note | – All other surfaces = Class 3
df867245-8ee7-5306-8825-464398aaaf06 | note | ○ At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface.
2c72f439-83ad-51e9-a114-a9f733b2be3f | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
53f4cdca-ec89-5de4-a287-0493e9734593 | note | Method - Visual
490795ab-66a0-5d28-b426-687de42a7943 | note | Frequency - Each lot
79c79a23-b229-57d9-a21d-2bb15c0f2497 | note | Category - IP
8345982e-0df7-5996-9e01-54b70e6ec0fe | note | Responsibility - SE/PE/SPE
98ad62b4-ed84-5057-9bce-06d839453881 | note | Verifying Documents - This ITP
| checkpoint | Final Inspection
756e8969-6307-522b-bef2-50ce793ce9c2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
959647ba-951f-53c4-ab1b-1b2b067a0414 | textbox | Name:
64cbf744-85fd-56da-a151-9396e615ced9 | textbox | Position:
1724fb15-65bf-568a-bbcc-8eef520a0911 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-172-CIV-BRUNT-Landscaping - Ground Preparation & Planting Rev 0 | itp | ITP-172-CIV-BRUNT-Landscaping - Ground Preparation & Planting Rev 0 | 79109cab-405b-4cb1-8867-6ad740d64004
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
67ceb0b0-8d3c-5bb6-be25-51a267836052 | note | Document Title: ITP-172-CIV-BRUNT-Landscaping-Ground Preparation & Planting
4433f08a-cfad-578e-966e-debc0c97210d | note | ITP Description: Landscaping-Ground Preparation & Planting
59e5469d-31b0-55d8-81cd-97b5521a6d4e | note | Discipline (e.g. CIV/STR/RAIL): CIV
b67644b2-d0dc-5e77-933c-9e7956026278 | note | Revision Number: 1
9fb16dad-6aaf-5aad-9f47-0c859f143135 | note | Revision Date: 28/05/2024
f240d2ea-818f-55a9-9422-6d5e286395e7 | note | ITP created by: Jason Lee
bb062458-3e56-5c0f-a8c6-83645f0c5ddb | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
518a1ea6-3849-50c5-b7bc-fd77c0f97e8f | note | Reference - VicRoads 720
| checkpoint | 1.2 - Non Dependent
3864a199-6185-535e-b3ca-a5dc3b6c4b62 | note | Reference - AS 4454
| checkpoint | 1.3 - Non Dependent
ae5ff4e8-aba8-5fd2-9814-49fb376b2314 | note | Reference - AS 4419
| checkpoint | 1.4 - Non Dependent
927aed95-9ace-5f52-901b-17475761bec6 | note | Reference - IFC Drawings
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Submission and records
1f76f13c-6fa6-54f2-a27f-f6a90d89860e | note | Reference - Section 720.03
8c12918b-80d9-545f-82d9-838801ef8ace | note | Acceptance Criteria - Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
2a811a3a-b772-54ed-9766-858a046526de | note | Following information shall be provided to the NA:
1b269a02-87f3-5e6f-b8c0-196208b79ada | note | Samples
e027130b-c195-5abb-9eb8-f64984a2da89 | note | – Mulch
4560d6d0-e115-5f26-b780-8f569c60df10 | note | – Imported topsoil
a72398e5-e463-5557-93a1-55e8b8f4c3d0 | note | Records
831c0d90-cce9-5002-806c-f761e9c98d6e | note | – Details of suppliers
c778ff31-c376-5cae-9880-5bfce3007e47 | note | – Soil tests on imported topsoil
4acff2ee-4f63-5255-a238-efaa4fd4b4ce | note | – Copies/Photos of fertiliser labels
49a29c79-21a2-5da7-aa83-798246f35504 | note | Attach: Records and Certs as Hold Point onto TeamBinder and write the Reference No.
8fa9f852-1338-50c4-9deb-a148790c6758 | note | Method - Document Review
8fb0716b-e71d-5219-a1f4-1035cac46222 | note | Frequency - Prior to Commencement of works
94950571-c581-511b-bebc-4836f5c87312 | note | Category - HP
1d37c552-32db-504d-908c-d1436d850fc0 | note | Responsibility - NA
96524a8b-e531-57da-b466-e71db2fda8ef | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Supply of topsoil
607f447c-014c-50e8-bf4e-784f725e877d | note | Reference - Section 720.04, Table 720.042 IFC Drawings
e8d54736-a154-5bbd-8080-2763a47d8002 | note | Acceptance Criteria - Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
cc3663ff-6b0f-53ca-8c03-3340f1b60565 | note | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings.
eaa590e9-eb1a-5bd5-a08f-a5790481cd5d | note | Attach: Material Conformance Docs / Test Reports as Material Approval onto TeamBinder and write the Reference No.
a4ab4b9f-b1aa-5134-8bed-e53ae331522a | note | Method - Verify, Doc. Review if applicable
9802003d-7413-51e7-8b63-d785d92562ad | note | Frequency - Prior to Commencement of works
9f3e76f3-3c74-5ae1-8258-0606ca1f547b | note | Category - HP
234cff29-d9d5-5cb5-ba5b-cd83515b23ad | note | Responsibility - NA
f3bf8a62-9efc-5791-8335-e6897c9fb77c | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Supply of Mulch
f7968c67-7a1f-5e46-a6a1-d127f915f86e | note | Reference - Section 720.04, Table 720.044, AS4454 IFC Drawings
735313af-c6cc-5d30-8d12-c289f48bd5d3 | note | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
b75253aa-2c0c-5024-a8ac-845bfdca462c | note | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
a9805343-68bb-51a5-90ef-6ea501ddbb98 | note | ○ Imported Wood Mulch shall comply with Table 720.044.
b5a37238-4da9-5ec4-b7c9-2bd9775d4fbe | note | Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
07d3fefc-7d98-5e23-a3bc-97b590de8c9a | note | Method - Verify, Doc. Review if applicable
07ff9875-71fb-5711-a4ee-36533fd6b657 | note | Frequency - Prior to Commencement of works
b0909cf4-1337-5fc6-a418-bd8afb4631d8 | note | Category - HP
78c328ea-4b82-52c7-8222-19e8dae0671d | note | Responsibility - NA
f62041f7-24aa-5d51-bc80-f3b9f55846cf | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Supply of Plant
5b4d2229-1b02-537d-9f47-b686287160e7 | note | Reference - Section 720.041
8450df08-9acb-554b-9ab6-0d86d53f0ece | note | Acceptance Criteria - All Plants have been inspected and comply with Sec 720.041
a4c66b5d-36ac-5f9b-bbae-6b65e6a9bb2f | note | Attach: Landscape Architect Approval
e4b34b7c-bc0c-52fc-abe8-9778828afe97 | note | Method - Verify
602edf29-7437-520e-9678-cf95cda4160d | note | Frequency - Each Lot
7a481136-788c-54bc-b585-93abb437b604 | note | Category - HP
af5b8846-8152-522f-b0ed-4a82cc63a2c5 | note | Responsibility - NA
36c912b5-6206-57ed-8df5-d442288ca7bb | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Supply of grass seed
7d7b5189-132e-55e6-982f-fe8805b55759 | note | Reference - VicRoads Spec.
eda080b8-d8ea-5313-aca7-eac1b766d942 | note | – Cl.720.04
28e50717-f698-56ca-bd21-a2accb9f722f | note | – Table 720.045
15af17f1-fd04-5ef8-a2c4-45d6da542d6d | note | Acceptance Criteria - Grass seed shall comply with Table 720.045
6487b7b2-a617-5742-99bc-926ede375399 | note | Attach: Material Conformance Docs / Test Reports as Material Approvasl onto TeamBinder and write the Reference No.
0e7def38-d590-518f-84cf-e74637e1e0c2 | note | Method - Verify
63cf2503-e7e2-55fe-abb6-c039430b3692 | note | Frequency - Prior to Commencing works
c4652c5b-8195-5932-ad6f-39fe54515e46 | note | Category - HP
56aa1cd7-faaf-5143-b31b-86faa23433d8 | note | Responsibility - NA
13e54c8f-d2e3-55b9-a845-2d85c338a284 | note | Verifying Documents - ConQA HP Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documents
| checkpoint | 3.1 - Check for correct documentation
d89529a9-c1b7-5685-8bff-4b442d3c3635 | note | Reference - Drawings and drawing registers
665b5335-31fe-5e75-85f0-57afb782732a | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
0a2e2979-ed2c-5c42-a20a-d7f60f715b01 | note | – Using the correct and complete set of IFC drawings
c33f6d05-4ab9-5756-a960-c29041c00a14 | note | – All drawings are the latest revision
ab3b72ce-9ed1-596c-95ad-240707eded52 | note | Method - Document Review
7f02d2ef-8667-5504-a87f-6898d43e2018 | note | Frequency - Prior to Commencement of works
6fa8a9e5-2c54-55b1-92ea-ad7bcc0ad3a9 | note | Category - IP
00003a19-c776-5022-9027-2570f4aea653 | note | Responsibility - SE/PE
73d538f5-7fb4-53e9-ac9d-9a78dcef6991 | note | Verifying Documents - ITP Signed Off
| checkpoint | 3.2 - Subcontractor ITP
1a4db1cb-4728-51d7-a29a-8d92dade9ae7 | note | Reference - Subcontractor ITP
dc7c782d-87ac-57ce-a82f-ce0cbb346adc | note | Acceptance Criteria - Subcontractor ITP to be reviewed and approved by MRPA.
349689c6-95d8-559b-b5a3-7733d9265a3c | note | Method - Document Review
ed5212df-a16c-5a91-8689-25ae8829c92a | note | Frequency - Each Lot
67e6e83c-e545-5bca-bdbc-81b76c926fcd | note | Category - WP
c5e572a0-78fe-5c2c-8fa1-7dae7344b990 | note | Responsibility - SE/PE
48d78e99-bc47-5223-9548-c2af503bb63f | note | Verifying Documents - ITP Signed Off
| section | 4. Ground Preparation
| checkpoint | 4.1 - Soil Additives
0779c064-ce9d-52f3-8992-54b7a704abc1 | note | Reference - Section 720.07 a) AS 4419
ac98cd02-9ee1-5bdf-8694-10709b3ff6af | note | Acceptance Criteria - Refer to Subcontractor ITP
8c62d3d0-fc2c-549f-b9f4-ac8471c7d0d1 | note | Method - Document Review
366ab38e-062d-516e-869f-dbd8dfd88541 | note | Frequency - Each Lot
c3c36fac-d2f4-5cdb-9e9f-9861c2993a6f | note | Category - IP
531ddb79-aa0f-5277-9ed2-aedb2562cb6d | note | Responsibility - SE/PE
06fce9c8-a75c-52c3-9f64-f490df4d60f3 | note | Verifying Documents - Sign ITP, Attach Test Report, Attached Delivery Docket (if applicable)
| checkpoint | 4.2 - Ripping of subsoil
120750c1-9e1f-5eb3-9b0f-bb622f8fe1a7 | note | Reference - Section 720.07 Table 720.071
2dc577fc-a165-565c-9a81-d2411f480d09 | note | Acceptance Criteria - Rip Subsoil to min 250mm at 500mm spacing
0eb86c7b-f320-5b37-9973-60672bd52f1a | note | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
ad916b54-42fc-57be-abd6-972af17fdfdf | note | Method - Verify
e6d0f0a8-4e97-5aaf-b8c4-d98366167cc6 | note | Frequency - Each Applicable Lot
e8db3e62-3db9-542d-bcd0-1a6a29696677 | note | Category - HP
77dbd235-5404-50b0-9eb2-8f0fa93a3768 | note | Responsibility - SE/NA
f52b83fb-8e8c-5fcb-8af0-6488f739582a | note | Verifying Documents - Sign ITP, Attach Lot Map/Marked Up Area Inspected
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Topsoil application
44235ac5-e212-5c79-8786-d7481de87d59 | note | Reference - Section 720.07
5f6a81a7-4098-5a08-abb7-d653ea211f17 | note | Acceptance Criteria - Topsoil to be installed at 150mm depth with no air pockets, weeds, rocks, and other debris. Finish surface should be smooth and uniform
1b454719-c617-549c-9fc1-40a0a1472f31 | note | Method - Verify
837cbe8d-4f67-50e4-9024-d2f86077e559 | note | Frequency - Each Applicable Lot
fc92c6c0-4e0a-5a02-aa2d-5843e10e19fc | note | Category - IP
7792dc00-9b1c-51d4-974c-27b929d3f9e2 | note | Responsibility - SE/Site Supervisor
f3faf0fc-c637-5ec3-b9de-e2695d75115f | note | Verifying Documents - Subcontractor ITP
| checkpoint | 4.4 - Mulching
be7ccfa5-e602-59b0-9621-af93ffc40170 | note | Reference - Section 720.08 a) IFC Drawings
d263ba93-4d97-56e5-a846-8dd4998b04ad | note | Acceptance Criteria - Mulch to be installed at 100mm and to finish 50mm below pavement.
e59ca615-9071-54b9-875a-9a81190a381f | note | Method - Verify
22b62223-b8f8-5f6e-a3f7-e52029df80e1 | note | Frequency - Each Applicable Lot
180538f0-0157-555e-bfb3-c99e946c9200 | note | Category - IP
1df691ca-96c1-5dce-ab96-d47cfd8e41b3 | note | Responsibility - SE/Site Supervisor
a49c817b-f2c5-5f51-9829-b53f950f5f34 | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
| checkpoint | 4.5 - Weed and Erosion Control Mat
3fd81d9b-9c23-5573-a339-0b62fb1a9af6 | note | Reference - Section 720.04 i) IFC Drawings
84068154-acee-5eb0-b154-cae6c8617f8f | note | Acceptance Criteria - Refer to Subcontractor ITP
50826e68-ca88-5bf5-8762-3ab276aba96d | note | Method - Verify
a6f719ef-65e8-5177-9390-6f759d67bbd5 | note | Frequency - Each Applicable Lot
1b133628-fec2-54ce-a4e0-b5658f8ba7ac | note | Category - IP
b0c845f3-c499-5b4a-a505-3b6f3ffe0162 | note | Responsibility - SE/Site Supervisor
4c6a116d-4012-5777-aaec-47ddd11374bc | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
| checkpoint | 4.6 - Jute Matting Installation
bdfe8dde-6ba9-57df-a9c1-e5c4897c7e75 | note | Reference - Section 720.071 IFC Drawings
71c3bce3-8646-5672-9796-47eec25d91f1 | note | Acceptance Criteria - Pre-slit Jute Matt installed as per specification
191ff8ed-8821-59ba-8961-cf667dd51fe5 | note | ○ Lay Matting into a trench of min 150mm wide and depth, pin and backfill
e5f810a8-867e-5acb-b97c-19cb5355bc16 | note | Method - Verify
2fcbe050-a9e5-5b56-ac4e-2d0cdda7b771 | note | Frequency - Each Applicable Lot
b5dbe4f4-392f-5bf5-a539-7fb5c006f8d1 | note | Category - IP
817d6983-cd17-5e26-b940-c15f4b9b0cc6 | note | Responsibility - SE/Site Supervisor
75a3097a-a757-51ba-9763-0267a056017b | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
| section | 5. Planting
| checkpoint | 5.1 - Plant Installation
14d9cec1-71be-5a61-8a46-46b96614869d | note | Reference - Section 720.041 IFC Drawings
6de1964a-7689-541d-bf92-722eee0d6fa0 | note | Acceptance Criteria - Plants to be removed from Pot and Roots Tickled
d3c9dc0e-606d-5e3c-9a60-5d32e355b072 | note | ○ Ensure Mulch does not overly cover stem of plant
d0f75e2e-9fa0-50fb-969e-6cf224445f51 | note | ○ Ensure plants to be watered within the same day
566f8229-b9d5-5c8a-8b02-49e5461bc658 | note | Method - Verify
df969c05-7b56-5fc9-9f8e-b9bb1a917d31 | note | Frequency - Each Applicable Lot
550b1eea-de6c-5bca-b0c7-7a03e28a1a02 | note | Category - IP
681e410f-0358-59f0-ab8b-f06d76a10d44 | note | Responsibility - SE, Site Supervisor
4d634496-2686-5500-b8b8-ec047a7cf039 | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
| checkpoint | 5.2 - Fertiliser Application
57525f02-bd7a-5f4c-9453-3b8d4fb9cb05 | note | Reference - Section 720.041 IFC Drawings
9e441af9-3d81-50c0-9b70-c28ab3055413 | note | Acceptance Criteria - Tubestock: 10gms (approx. 1 teaspoon) of fertiliser been added to base of plant
78437a92-4fbd-5a59-b8de-ae1dd34edce2 | note | ○ 15-30cm Pots: 40gms (approx. 4 teaspoons) of fertiliser been added to base of plant
fd373626-fa2b-5b53-99ed-1edcd2925a7b | note | ○ 45L Trees: 80gms (approx. 8 teaspoons) of fertiliser been added to top of root ball
350572dd-cd67-5b40-82ac-6ccec41ca922 | note | Method - Verify
72b89a9c-043a-557c-88f7-9e6412ad2a0b | note | Frequency - Each Applicable Lot
c26e3580-1c6c-57f3-aa43-b48a70091cb6 | note | Category - IP
ae0f2892-8abb-5d1e-ba65-4314b8a18c80 | note | Responsibility - SE, Site Supervisor
8290a716-4ea7-5373-923c-49064b44d55e | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
| checkpoint | 5.3 - Tree Installation
a565041e-849e-510d-8d29-bdeb6e658207 | note | Reference - Section 720.041 IFC Drawings
7c61fdf9-6e49-58d0-8710-15bf600e8955 | note | Acceptance Criteria - Installation on Grade:
1db2af8e-fcdc-5f49-8cd6-46a2f2208682 | note | – Hole to be 100mm deeper and 600mm wider than pot size
88731a35-2d4f-5804-a744-9528fffbbc9b | note | – Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
b6794887-f2b8-506b-86e9-39e698aa9104 | note | Installation on Garden Beds/Turf:
a3310e03-0103-5942-b5ac-016f3933aa14 | note | – Tree Pit Inspected and Minimum 3 times the root ball width
886122f5-ae62-51b9-954a-35b67d698216 | note | – Three 50mm x 50mm x 2400mm Hardwood Stakes driven min 600mm into ground outside rootball
3710f45c-2984-5919-ab57-50099bb7564a | note | Method - Verify
8623654d-60ae-546c-ad3b-e3341874a2b3 | note | Frequency - Each Applicable Lot
9ee8a2f4-87c8-55ec-b77d-ec16a55b87a4 | note | Category - IP
fa1889d7-922a-5bab-81ec-e864e89f002e | note | Responsibility - SE, Site Supervisor
07f1841d-ddfb-5c1a-9348-c00db8d91676 | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
| checkpoint | 5.4 - Soil Installation
2b775893-a3f2-59e3-abe9-a649b6ef8fae | note | Reference - IFC Drawings
336d6344-ab80-5786-b66a-e319cf44eb6e | note | Acceptance Criteria - 75mm depth topsoil & 100mm min in swales consolidated as approved
39b0b3d2-8064-5c37-8248-edf0108b818b | note | Method - Verify
ce7835e8-2064-5e6b-bc1f-680029678bb7 | note | Frequency - Each Applicable Lot
5edcbb32-bad6-5dcb-a510-e96bb071a07d | note | Category - IP
b286640d-8aa4-527b-9f57-5b3dcddc7091 | note | Responsibility - SE, Site Supervisor
b44bc31a-c989-5fed-bc7b-e6c5ddb044da | note | Verifying Documents - Subcontractor ITP, Attach Delivery Dockets
| section | 6. Post Construction
| checkpoint | 6.1 - NCR Closeout
1024f295-26bd-5e0f-8fb9-2a6801f594ed | note | Reference - MRPA Quality Management Plan
4a8224ce-ae0e-56b7-8ab2-b110c593d537 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot/element/Work Area that this ITP covers, have been closed
9c0053fe-23d2-59d2-b594-ede75bd6c576 | note | Method - Document Review
9bf514b6-1e62-5526-839c-b4c64f9732b6 | note | Frequency - Once, prior to closure of this lot/element/work area
ce35ef77-a7a4-539c-b544-625baaa6dd6a | note | Category - HP*
05da90ac-1a86-53d0-bf89-03b4fadf9264 | note | Responsibility - SE/PE/SPE
c344fac5-284f-5acc-8745-d522a35331b7 | note | Verifying Documents - ITP Signed Off
| checkpoint | Final Inspection
1ec275c0-3434-5ce0-9ab2-b20639c06ecb | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0ae39d96-fad4-5292-8253-e9e3b1c3c802 | textbox | Name:
457f0064-3532-5de8-8ae6-7ff0aa1c4a17 | textbox | Position:
c4eaa079-a074-52f7-87bb-b61e6acc3c6f | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-175-STR-BRUNT-Cast In-Situ Stairs Rev 0 | itp | ITP-175-STR-BRUNT-Cast In-Situ Stairs Rev 0 | d3285b70-250d-49c1-898e-99d0cdf2090e
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
a30258bb-a880-5620-846d-4260a30e6953 | note | Document Title: ITP-175-STR-BRUNT-Misc Structures Cast In-Situ Stairs
9467844d-742b-5604-b77d-45c6b23504d5 | note | ITP Description: Cast In-Situ Stairs
45f11d3c-0cda-55d9-bbe9-026f0003c26d | note | Discipline (e.g. CIV/STR/RAIL): STR
ca43ae60-6526-5e4e-99d4-43ab82ff4827 | note | Revision Number: 0
bc433d5f-f7fa-522e-afd7-f0db39d72520 | note | Revision Date: 27/05/2024
7f5ee4b3-c80e-5d67-aef7-765764241d1b | note | ITP created by: Derek Collins
88cb191d-f31f-5b00-b9e8-217aa9c58088 | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
81a723a8-3be2-51e4-be75-ce4d401a10c5 | note | Reference - VicRoads Section 602 October 2007
| checkpoint | 1.2 - Non Dependent
7a37f6d0-3608-5cae-a5b3-b14e635670d0 | note | Reference - VicRoads Section 610 February 2020
| checkpoint | 1.3 - Non Dependent
f0b678cb-7e87-56f6-bae4-37b7d953c4be | note | Reference - VicRoads Section 611 November 2018
| checkpoint | 1.4 - Non Dependent
9ea68b1c-4c7b-5f3a-9cf9-255f206792d8 | note | Reference - VicRoads Section 614 June 2017
| checkpoint | 1.5 - Non Dependent
fe73d2c2-b156-5085-82ad-297b94568345 | note | Reference - AS3810.1 2018
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
db3155bf-06aa-5f85-b113-4c35d68485cc | note | Reference - 610.07 Table 610.071 IFC Drawings
29a201f6-d5f2-5bb0-a6dd-f422784f58d0 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
1f8a7b95-940a-5055-b797-02091929ddb1 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
d641bb58-ee00-57b8-9f05-6d2be73e570b | textbox | Enter: Teambinder Material Approval number
ed9e4401-06d2-523e-a01b-f4538049cb50 | note | Method - Document Review
0b668e2e-6fa6-515b-b2d4-21a705cb0e84 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
e10a1032-566b-5191-af3e-c1fef201022b | note | Category - HP
ff0d0e90-85fa-50a4-9292-987e123e9d29 | note | Responsibility - Nominated Authority
3f14f8bb-fa30-57d4-9729-04ffa956c76b | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
c3b9648a-d8b7-5eab-97fd-de87c11cf4af | note | Reference - 611.05 (a)
8d419517-e43a-5291-b70b-e594de3220c9 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
8222b549-0053-5dfc-8bba-590e73f1ca89 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
16c67448-c2f7-5143-a4a5-549a7aa5beef | textbox | Enter: Teambinder Hold Point Ref Number
d8af7d23-bba0-5edd-965a-e5f20b9f91e0 | note | Method - Document Review
a1cf3e81-ba0e-5ce8-b6c6-634079de7959 | note | Frequency - Once for each supplier, 14 days of award of contract
a3876859-9c13-5653-80a0-f00686d671ad | note | Category - HP
fe8fd2c2-d890-5b4d-a1b7-493cceefeef2 | note | Responsibility - Nominated Authority
c56ddd1f-b773-5d0f-9a46-a0ee8e9cd417 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
e991ab02-a7f8-5507-8b66-9746857590d6 | note | Reference - 610.26 (a)
1e03a68f-d636-5a52-9720-8a8fbf80a524 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require testing to demonstrate suitability to prevent excessive deformation under loads.
5fa3897e-0ce8-53d5-a86a-556e339e369f | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
9dec13e0-b8a4-50a1-b1a0-261d42a26831 | note | ○ Concrete bar chairs and spacers shall have a maximum VPV value at 28 days of 12%. Bar chairs and spacers made of wood, metal, plastic coated metal and site made concrete shall not be used.
a4ee96c4-8463-5715-aec1-09cb15749dae | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
fbf3723c-8f87-5b79-a84d-dad019070978 | textbox | Enter: Teambinder Hold Point Ref Number
4d4f68d0-d246-5fa7-9c2a-ee575f6adb0e | note | Method - Document Review
f4c9c2bb-fa38-5ec2-ab5e-5a50a700b06c | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
fff3e816-3a7b-5568-9f66-027d390186f5 | note | Category - HP
79cd17cd-e839-58d6-aedf-12914feaff6c | note | Responsibility - Nominated Authority
820c3783-b0da-54d2-8643-31b5b2703459 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Evaporative Retardant
c3f9bbc3-7641-5bab-8ea7-7a96c8075324 | note | Reference - 610.17 (f)
2c8be4bc-ecc0-5897-a79f-2db6716f1f2f | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
cbd35692-b62b-5b84-9de4-c471dce75329 | textbox | Enter: Teambinder Hold Point Ref Number
f7ee7c63-21aa-5ecd-b7d6-72f67edfbbe0 | note | Method - Document Review
d1031bdc-1e14-59d5-8132-94a1cacd15f5 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
ac5def2c-c975-5393-bda4-44ded08c6d5d | note | Category - HP
59cf55c5-b85e-5f2e-8849-e224f7e630ed | note | Responsibility - Nominated Authority
7804b8d5-bc76-57f5-ab23-30af190eaa71 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Curing Compound
1c72a53e-4ec1-5a5f-b5d1-1dc02e0ad9e4 | note | Reference - 610.23 (d)
986b79e1-c1c4-5566-a52a-0fe287092caa | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
eee57fc5-b919-5693-b9e8-8ed6c43c8570 | textbox | Enter: Teambinder Hold Point Ref Number
61557a0e-10b9-5dc8-a6d7-7e438cf548bb | note | Method - Document Review
322c890d-a918-5c2d-98d2-e50f3196bfe3 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
cb1e0fe4-af6b-57e2-8ce4-e7ebfb2a6bac | note | Category - HP
861cadf2-fcf5-588d-ba10-ad29664e55ed | note | Responsibility - Nominated Authority
0e0aad67-17dc-52b7-9ecd-77f109bfab06 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
5d2fdfa8-efde-587a-8bb9-426c8495f68f | note | Reference - 610.18
9dace015-b4fb-57d6-9b2f-ffe2d3c3ba4d | note | Acceptance Criteria - Concrete placement and compaction to be in accordance with Section 610.18.
11168ffd-b0b3-5386-bc99-b90f2563fe5b | note | Method - Document Review
297949b7-8207-5110-bf3d-70647155a71e | note | Frequency - Each element
f8b0ef42-ac79-5df8-bef9-5a4fe9c31999 | note | Category - IP
5b2b96b0-2c0b-519b-9b4f-d3460820d1fd | note | Responsibility - SE/PE
5ffbc3cf-faaf-517c-8c8e-23501f546490 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
f6195f20-5faa-5c27-9796-3bb42c59d3f8 | note | Reference - 610.16
d1e420bf-3ed5-5a0f-be65-de492108d762 | note | Acceptance Criteria - Concrete sampling and testing to be in accordance with Section 610.16.
ce5b910f-53eb-50be-a453-7d892198062a | note | Method - Document Review
676af438-0944-5687-932c-7bedc0a53c95 | note | Frequency - Each element
eecb2d6d-b819-5a1e-8cd9-6c892bfc5787 | note | Category - IP
4a7464a0-5982-5271-9585-909e9e74a3cd | note | Responsibility - SE/PE
92687652-a13b-58cf-ae61-e903676fb09c | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.3 - Hot and/or Cold Weather Concreting Procedure
ec3efef1-ad35-5909-b681-502a56d3e561 | note | Reference - 610.17
6dc9d61b-33c8-5fcb-ac40-ff50ce3842c0 | note | Acceptance Criteria - Hot and/or cold weather concreting to be in accordance with Section 610.17.
5f59fe5d-7c94-56b1-929e-8316a51a644e | note | Method - Document Review
98b17412-d6d6-5e50-be5f-57d5465e698b | note | Frequency - Each element
d8bd360d-16e5-5e7c-bdd7-99c7b4c1e829 | note | Category - IP
0d0d097e-fda7-585c-82fd-2a248b6741c4 | note | Responsibility - SE/PE
d51c2ef6-f8e7-5b7c-9029-04ded79b9ec0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.4 - Curing Methodology (for Concrete and Grout)
41ff8148-ab2a-57c6-b6da-3db90c535191 | note | Reference - 610.23
a61d91c0-f334-5c7a-ad09-a64c915c474d | note | Acceptance Criteria - Curing methodology and procedure to be in accordance with Section 610.23.
75b0799c-506a-593e-bb7b-29b6809749fb | note | Method - Document Review
4eb06e42-eb37-5f03-b3ff-256c898ef194 | note | Frequency - Each element
bd3d1dea-59e0-5bc2-8ca7-390333b2f2e2 | note | Category - IP
0fe7b99c-6782-5877-92e5-b039d467eca9 | note | Responsibility - SE/PE
4b4d06d0-b07d-5bc2-b40b-e5360d977f31 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 3.5 - Concrete Drilling Procedure
5b351acb-4986-58a8-80ac-3bbcfb788135 | note | Reference - 610.46
eae0cf92-0a41-5ecf-aab1-460f3d10e14f | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services. Refer to Section 610.46
80215552-168e-524d-aee9-1a557bfae386 | note | Method - Document Review
6d7e7782-6c50-5ac8-b9cc-69ca278fe572 | note | Frequency - Each element
307233d3-5fe9-5717-b1f8-09f14d96a2d7 | note | Category - IP
d2631f5b-76e8-5f22-b421-412bc16cf1e8 | note | Responsibility - SE/PE
f36122f8-198c-575c-979b-f3e923e660d0 | note | Verifying Documents - This ITP Signed Off
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
a5e86a79-28a0-522c-9b09-6e680b991797 | note | Reference - MRPA Quality Management Plan
52061c3b-f3f7-591c-b1b6-589e7e748af0 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
1348e6fa-b760-501a-94da-82ef660a1971 | note | Method - Document Review
5b2be620-a638-5377-96f6-a35b8ba0fa4e | note | Frequency - Prior to starting Works and at regular intervals
76a5c383-5577-5778-a5a0-ad68bcb24663 | note | Category - HP*
454ffc60-2774-596d-8503-4f8535abcb40 | note | Responsibility - All
066c7fe1-28f9-5d82-8733-bb16062cea28 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Survey Set-out
fc66fb11-ed56-5d4d-8c76-96490e5386cc | note | Reference - IFC Drawings 610.47 (a) Table 610.472
c6ed8dfb-7378-5766-ba0c-941a4b2a7b5d | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
b1061199-973f-5333-a9fd-85e06db717c1 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
e42d925b-6437-5f6f-a32b-202a441ab52f | note | Method - Measure, Visual
8fc902e8-aff8-57cd-a5f4-1997137890e7 | note | Frequency - Each element
c3a53e24-7b70-562b-be36-532c99d31664 | note | Category - IP
884b3b27-8bdc-5627-85f9-a3f3f2061f8f | note | Responsibility - Surveyor, SE/PE
4dc52537-bcaf-5989-9428-fc3a5012fd18 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Concrete Blinding
f5c077e1-60bc-5e9f-83ea-8cc7625e2aef | note | Reference - IFC Drawings
037028ae-01e4-532a-b662-f020d0f0b941 | note | Acceptance Criteria - Blinding concrete shall be in accordance to IFC Drawings.
76cd28d6-6543-582a-80a5-415bdd8ad173 | note | Method - Visual
41c89815-cc8f-5dd8-96a4-04cfd03e50b7 | note | Frequency - Each element
77ba6793-4d8a-5ec1-ba37-b07a8bc1ae54 | note | Category - IP
e057714a-69da-54f7-a4f4-2e4e065712b8 | note | Responsibility - SE/PE
594dc656-5773-59e2-9c79-2daf260abf9e | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Formwork Design and Construction
bbe47f82-5c73-5bfe-82d2-195254f0a3a1 | note | Reference - IFC Drawings 614.04, 614.05, 614.06
7353b845-c279-56c0-b401-36485b876695 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
86c84f1a-ed9f-55e9-902f-63db69b11145 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
81b5acdc-604e-544a-b5e8-60f7231072c7 | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
b3180390-e493-5908-b7e6-66a6ca713d41 | note | Attach: Temp Works Design, Proof Engineer Approval
a877d085-463a-577f-b211-61928eaecb71 | note | Method - Document Review, Visual, Measure
920e9029-91e5-51f0-ba83-6ae3149d35f1 | note | Frequency - Each type of element
da88ba49-16d6-57c4-a122-07e13e993d62 | note | Category - HP*
703dee59-5b13-5d46-876c-32cec1f53312 | note | Responsibility - SE/PE/SPE
43bd93ee-c692-5f9e-a69c-0dafe1231c8b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
da784f43-8ac5-54e3-b3a6-9e9579b5de8a | note | Reference - 614.08
7a538327-89e6-5b6c-bb46-926d1d88b403 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
2c280491-b943-50e0-b1ca-9b628cf3b061 | note | Attach: Temp Works Design, Proof Engineer Approval
f265010b-989b-52ed-94e5-d474ba02b8bd | note | Method - Document Review, Visual, Measure
492436ff-9acd-5b71-8e15-376213d2e34c | note | Frequency - Each element (where greater than 2m)
b8b02acc-65d8-5501-a0d8-72660fcfeabf | note | Category - HP*
1aadbf17-c702-51e9-b5e7-cf6cef22b47a | note | Responsibility - SE/PE/SPE
adf3795d-e3f7-5be7-ba70-af1f0514ce1f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
de1e1bbf-c962-5e66-bf2e-66038468d339 | note | Reference - 614.08
e48949b7-4cfb-51fb-b058-d1adea20e6e6 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
bbda1d78-9d8d-5091-90d0-0e98059ae955 | note | Method - Document Review, Visual, Measure
fcc4065a-7de6-5106-bb91-2033cf897452 | note | Frequency - Each element (where 2m or less)
1741854e-bd1d-57bb-9829-47cd35b04903 | note | Category - HP*
dca05163-7238-53f5-a7dd-83ec6c51ea6d | note | Responsibility - SE/PE/SPE
03bc4527-1ba9-50c5-b380-d3a9bdfd608f | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.4 - Pre-pour Survey
3007c16f-3f74-5903-b5dc-f5bd2e50af29 | note | Reference - 610.47 (a) Table 610.472
c3b1a518-362c-5a82-b41c-2371cc18a3fa | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
c74ef2b9-ce0b-5ee1-b376-46fc59feb3cc | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
94dc2629-0371-5b51-abae-c88743551872 | note | Method - Measure, Visual
9c483b6e-0ce5-54e1-b1e5-37d91a8f46a4 | note | Frequency - Each element
89b1d424-0d6f-50e6-a06e-7f46db17b651 | note | Category - HP*
d177b299-40bd-526b-a417-00c04f6deca3 | note | Responsibility - Surveyor, SE/PE
d2878990-dfed-5ac4-b327-729c6e22617b | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.5 - Reinforcement Placement
f8b7f822-d041-5a57-a79e-199d32bd7cc4 | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
365960da-28d8-5e91-9167-aa889705c808 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
aa33effe-ca3b-5545-b714-a3403083f22b | note | ○ Projecting reinforcement is the correct length and location.
0762b934-c79e-5df4-af48-4434f4dab0b3 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
0ab697e2-c60d-5ba2-b9cb-12e7e65cfcf3 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
a4ea1906-9f3e-5b2c-928d-93eb7b318518 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
741f6f4f-f781-54a0-b729-53d3de73c327 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
9b77e89c-47b0-5e42-b06c-e5bb43e45c89 | note | Method - Measure, Visual
1e904b45-bb56-5e47-aa43-53ed26bdb137 | note | Frequency - Each element
8af45322-0607-5aef-bd55-71ba6dc6cacd | note | Category - IP
09682687-1a0a-5111-931e-5a4772c38cf8 | note | Responsibility - Foreman, SE/PE
5c04fd50-4c02-5891-9cd8-e67aae78117a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.6 - Cast-in Items
3743a1b4-8347-5472-8380-d369181d8271 | note | Reference - IFC Drawings 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
b5170bea-876d-5d96-9cb7-7958cc5ba888 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
407f3b3c-b377-554b-a382-36c2bc51161f | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
d4d5bb0b-c81b-5ae3-b89f-a2684d1d5f76 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
adf8e599-89f2-5546-9693-5c9bc86aad97 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
63e3a597-508b-5200-a932-f02cb9a8c42a | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
ba754344-7ea5-5fa5-acfc-ad72c676bca7 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
a14e093b-157e-5b7f-8805-198935269d9b | note | ii. Running dimensions of a group of the above = ±6mm
e8dbd57c-d43f-5247-b626-69834f83fe26 | note | iii. Ducts and conduit location = ±12mm
07ff3425-74f4-5767-b8ed-b8cc0ed6ef73 | note | iv. Diameter of ducts and conduits = ±3mm
baa1e087-9a6c-5f35-88f8-7a0cffd6bcac | note | Method - Measure, Visual
cb7b9dca-7e90-5bb7-8de8-c4407dba40fd | note | Frequency - Where applicable, each element
3b62efda-44ec-5307-a9c1-4c55210b587f | note | Category - IP
fc032f4c-2eab-562d-b059-c4e15eee25a5 | note | Responsibility - Foreman, SE/PE
173b387b-23b2-56d2-bac3-7ad50f8cac05 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.7 - Pre-pour Inspection
431081c0-ca56-5eb5-a51f-5ad324985b38 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
f95732c8-e129-593e-829c-f9f218dcf32b | note | Acceptance Criteria - Evidence that the forms, reinforcement, minimum cover, electrical continuity (if applicable) and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
16892336-916d-56be-8924-3ba240c7d63c | note | ○ All foreign material has been completely removed from the forms.
29f466cb-8353-569e-b9c4-66f96f76dc69 | note | Method - Measure, Visual
3d825049-b8f6-5d6b-9d66-08036b8ff2c1 | note | Frequency - Each element
66541927-7b45-5db6-9b82-c3f45d9ffe41 | note | Category - HP
f869d839-d50b-5320-9864-da2d4553c2af | note | Responsibility - Nominated Authority
9a9af691-0696-5ef9-9719-c4ac2b3f54b1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Weather Conditions & Evaporation Limits
3ccca869-a3d5-547d-b1ab-0b11229eebd7 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
4b7e8081-ec82-5968-b25f-c8ea59c3ce43 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
af461895-07a4-51b3-a986-d86a1886234f | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
580a9245-5716-5906-84c7-f501d08b64d7 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
6bb53a3e-c764-54ff-b071-b71200fea55e | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
021bf0f0-64a3-57ab-9946-b5b5968a1e1d | note | Record: Required information on the Concrete Pour Record.
85b5f693-0258-54eb-9cec-3fd3079f865c | note | Method - Measure, Visual
26bf308d-85aa-5f4e-be6f-12966c8f134d | note | Frequency - Each element
cd4fe68c-4e94-588e-9348-5a05a2929b25 | note | Category - IP
18364716-f46e-5401-8544-9c751662aacb | note | Responsibility - Foreman, SE/PE
e8db9736-ca67-508c-826c-3a646e175c76 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.9 - Concrete Testing - Sampling Frequency
7488ae28-8de3-5e11-8a48-63b02e8ceda3 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
ebb92103-b578-51b7-aa86-4284e5811b8f | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
267255c5-baaa-538f-be12-67eeb388774c | note | – 0m³ to 10m³ = 1 sample
679bfd19-ec95-5c8f-a756-1fa67821fa74 | note | – 10m³ to 25m³ = 2 samples
e16b1e93-a75f-5cfc-80b7-43fd01f884d7 | note | – 25m³ to 50m³ = 3 samples
7df10191-c74b-5f99-b537-4ad2bbd9997f | note | – 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
e3663ab1-58ca-556d-8385-f017dad6c020 | note | ○ For each additional 50m³ and additional sample shall be taken.
f0941ffd-57b6-5b49-b731-4fa96f10e88e | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
593b4c4b-83da-5aff-bd07-9af3c2be42a5 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
bdd4031f-291a-543a-aeae-8b05566387d2 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
6b132dbf-f52f-50d7-8809-23da414e2f0b | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
27521d20-18bf-5780-90ed-effd72cb6594 | note | Record: Required information on the Concrete Pour Record.
e627f533-b9c8-5636-8c72-5cc25ae0b19b | note | Method - Test
706be3b2-c1e9-59a5-bc52-e095dfad8d66 | note | Frequency - Each element
b0002d25-aa20-5d71-ad07-ff2382344cca | note | Category - IP
11a26c03-d1de-5451-9dfa-5732edb4d478 | note | Responsibility - Concrete Tester, Foreman, SE/PE
9a70f6f5-6241-5d84-ae68-2dc3b742d37a | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.10 - Concrete Testing - Slump
c5c1e58b-e7dd-5cc4-a977-097685a30ad6 | note | Reference - 610.16 (c)
c3237a91-97e2-5b60-b596-a460d0af3d28 | note | Acceptance Criteria - Slump testing tolerances =
ccc5c665-6147-5ae6-9deb-747302bb26f0 | note | ○ <60mm = ±10mm
5ad8cb94-b162-5f6f-9c02-9c5ffadf6234 | note | ○ ≥60mm to ≤80mm = ±15mm
a868c2c3-7f75-5407-9422-c9c861c10d93 | note | ○ >80mm to ≤110mm = ±20mm
c56d1004-08e2-5998-9c69-55a88e8cb98a | note | ○ >110mm to ≤150mm = ±30mm
e9e19b7a-9add-5eaa-810f-9984e1e3545d | note | ○ >150mm = ±40mm
f2dd72e5-031c-5278-bc9b-6790ce6461ce | note | Record: Required information on the Concrete Pour Record.
a42f34fb-9dcd-591a-840e-73316feaa860 | note | Method - Test
93987c70-06eb-5e42-a261-e9d62079e5f6 | note | Frequency - Each sample of Standard or Superplasticised Concrete
898c676d-c8df-5d46-b0c6-93bef80c8e60 | note | Category - IP
b4f523bd-5f10-5bee-968c-a5f2735b6e49 | note | Responsibility - Concrete Tester, SE/PE
8d661601-4e58-5fbe-b9c3-f8c96d156386 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
118978fb-7f27-52bc-9741-a4bd8b61d32f | note | Reference - Site Sampling & Testing Procedure
742ac300-6e17-5a9f-a0a2-ca36bb8b4ff3 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
e402963b-5241-5d65-aed0-dffd4b49aaba | note | Record: Required information on the Concrete Pour Record.
0f476574-18a1-598b-8ca3-84153524fa65 | note | Method - Test
5efc8816-03f1-5ef1-9d5b-0eb57af45639 | note | Frequency - Each sample
cade34da-4894-5faa-b059-166170312f06 | note | Category - IP
9842302c-3559-558c-83a4-7eef744f1dcf | note | Responsibility - Concrete Tester, SE/PE
14c0da17-874a-58e6-8104-ba53e79262fe | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.12 - Placement & Compaction
09958483-ae39-5cbb-a0d6-eaa9508f108e | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
7b3d85e3-cb7e-5746-b9d8-288dee14204c | note | Acceptance Criteria - All concrete batches are traceable.
b9bb8362-5397-5db1-aa6a-5656fe4c6efc | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
293a5fc5-6ba7-598e-ab7d-2293cd9fd346 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
271dcba7-65b4-5a44-a018-8191971a156b | note | ○ Concrete is not moved horizontally by use of vibrators.
80c171c5-073c-5d8f-a0c5-5edece584920 | note | ○ Adequate compaction is ensured
2e1e1765-be70-5b56-9f93-665912b1a846 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
9be35f56-049a-57d7-971f-eb48da875f5f | note | ○ Concrete layers are not more than 350mm
ef8bdbd1-9d14-5a21-8de0-f43b4228cbeb | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
870b6839-9885-57c8-9c49-76e22cc3f2fd | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
6bcaaa5e-e604-52e2-a3f0-c4fa372f2695 | note | Record: Required information on the Concrete Pour Record.
d6266a67-2e5a-5f92-b1d9-4049e3540e6b | note | Attach: Concrete Pour Record
4e876b90-d5db-525e-b774-d12ee0187e3b | note | Attach: Concrete Dockets
c5575ef2-85a3-5319-9019-07f8de6e356d | note | Method - Visual
b2a6bd46-f891-5216-9e94-cca11283f046 | note | Frequency - Each load
0c6c97a0-da7f-579c-98e9-910570253cdd | note | Category - SP
c52409d1-ecb0-5c38-aa16-ef04f49452f1 | note | Responsibility - Foreman, SE/PE
a70942c5-2662-51af-9e7c-64fbc6368f96 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.13 - Surface Finishes
dbb72036-3b9d-576f-afff-35ff38c07879 | note | Reference - IFC Drawings 610.31, 610.20
89f73c48-6981-5610-b95a-82686f3b82ec | note | Acceptance Criteria - Surface finish as per IFC drawings.
9b30d821-e5d1-591c-b304-907873bea24f | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
0932a6ae-5924-50a2-a323-3b9e2e970b2a | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
72bc4f43-a258-5820-a7f6-f0842f49ab24 | note | Method - Visual
d1d1d440-d3ea-53d9-9f02-71cd034e6422 | note | Frequency - Each element
dc6a5cad-cf4a-5676-9617-2056d45038bf | note | Category - IP
a4ea9a37-4ae3-5d69-9cf0-ac292a77977c | note | Responsibility - Foreman, SE/PE
c65fc091-dd38-5aab-8552-5e51c429e2ab | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.14 - Curing after formwork removal
21926576-a9a8-5e37-9af5-29a8682dfd48 | note | Reference - IFC Drawings
e67d7e79-2661-533d-a1d1-eaf9bfd5b93a | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
781f11c5-4054-521c-bb52-dc69e4aaf659 | note | Method - Visual
73aa409e-2587-5b68-875c-d207a339a39b | note | Frequency - Each element
a4c60103-ce96-51c8-b628-e9d539f6e049 | note | Category - IP
2ef74bfe-97fd-5d0d-a1d6-a267da19e4b2 | note | Responsibility - Foreman, SE/PE
617f287d-3873-5fab-a8d5-52291a1c0601 | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Early Age Compressive Strength Test Results - Removal of Formwork
da991a0d-d481-52ce-b63d-8ba56bcb2e6e | note | Reference - IFC Drawings
6454351d-9556-5e5f-9aa7-0a2b52c239ec | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
baf3cb62-0cdb-5ba1-8a73-102ed314a135 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
a5f16c97-cfe2-5392-94d6-06c2bde43d44 | note | Method - Document Review
8cbb8fac-b94a-5d77-a151-ae252ff43727 | note | Frequency - Where applicable, each element
326cedea-d749-525c-b777-4b89e5f97015 | note | Category - IP
c200c1e5-a752-5a26-a7f3-5c9c97f05748 | note | Responsibility - Foreman, SE/PE
a585beab-15ce-56f0-a209-9b4bd5851522 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Surface Inspection - Cracks
c1b746df-61e7-5bbc-aa1a-5b7c9cfea1e5 | note | Reference - 610.24
5e87b2ae-1068-530e-9863-79efec1cf8a7 | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
bbd82994-ea8f-5090-909d-2d8eabaadfef | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
896d4753-a49f-5759-97d5-3f58d73b53fe | note | Method - Visual, Measure
d63da043-62c8-53f0-8a64-7a7916106d20 | note | Frequency - Each element
1b2dac90-237b-5493-bcb4-99a444262786 | note | Category - IP
f608229a-4e97-508a-a7e7-4f8b8fed3ab6 | note | Responsibility - SE/PE
8c7a0809-38ef-502d-81d4-365e980c23f1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Surface Inspection - Surface Finish
caeaacb4-c8be-587c-8538-493982c4a59a | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
3d544955-660b-545b-9677-dd1b924fda43 | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
e0b45636-aa83-5559-805b-ef51b844df01 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
27197572-2830-575a-bef4-e7e3fb995f5c | note | Method - Visual
6ebd0f8f-1ca0-5619-bfe7-4b928b3d7a95 | note | Frequency - Each element
0e3ec7fd-3edc-505f-8e87-823d6302ad5b | note | Category - IP
3b4fa5be-e585-5e2f-9a1d-35b534f96de3 | note | Responsibility - SE/PE
755ec30e-862a-5aec-89c4-6ba2d34e81d6 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.4 - Measurement of Concrete Cover
ea599623-f354-570a-8024-7ae488aec584 | note | Reference - 610.34
442a547e-eef1-5d40-a7bb-3b48841e2db3 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
4d0e6c52-4f19-5420-b06b-9d8582fe538c | note | ○ Minimum 10 no. measurements recorded in each area.
bf90ad52-8c9e-5a8e-ae37-fd45900625c0 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
c478fdf0-2664-5b4a-a67a-a8032e7ff90c | note | Attach: Covermeter Check Record
baf4a54d-e961-5b42-b2e4-d106cd9280c3 | note | Method - Measure
2fe07426-321d-57f1-8cfa-bba9316737ac | note | Frequency - Each element
dfa88ba7-9b31-55dd-a582-c72416ceb741 | note | Category - IP
374ef38f-b407-5f1d-be81-d131196e8513 | note | Responsibility - SE/PE
392d461e-bf19-5fb4-8b9b-72e994da01f1 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.5 - Compressive Strength Test Results
616ab891-96c0-5474-9048-2047fcffb5c5 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
95cb13cf-ac8e-5883-ae97-e559d49cf251 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
da35924e-a089-52c6-992b-aa6d9d86a4b1 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
adcda721-5581-56b1-b360-657b88032b5c | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
2f3d077d-b011-5980-9fca-9b46caec56e4 | note | Attach: Compressive Strength Test Results
9bffe916-0db6-5e1a-b6e0-cf3c0a23c6b9 | note | Method - Document Review
9338c24d-e886-580f-be3c-911f523f5e8f | note | Frequency - Each cylinder
8277290d-4fa8-50c0-8bc2-40001779622f | note | Category - IP
752fb7c1-62eb-534d-9a99-a0a09e5f772c | note | Responsibility - SE/PE
e68d850b-8b77-51dc-80f1-1879997dde95 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.6 - As-built Survey
d754a7b7-04d4-5474-9ff7-258d5e9ee6bc | note | Reference - IFC Drawings 610.47 Table 610.472
4efbe0fa-5a57-5059-9bc1-ac7814527d93 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
3c44e359-976a-5602-bc39-0b8b8475c1d4 | note | Attach: Survey As-builts / Survey Report
0d6286f2-26b3-57b1-ac79-a7401521890f | note | Method - Document Review
9a3a2de0-9a9d-5da4-9033-1df7325f927a | note | Frequency - Each element
5880fac9-00ad-5aad-8ad4-915861fc5107 | note | Category - IP
f919bcff-0176-555e-b497-cf3f25599ea0 | note | Responsibility - Surveyor, SE/PE
588cbc83-6b00-5ccd-87cc-952685ae68ef | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.7 - Non-conformance Report (NCR) Closure
f436b393-d840-5887-932e-6041b4ea5b4c | note | Reference - MRPA Quality Management Plan
3d904f6d-5c48-5af4-a8c2-2cdc67aa9c88 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
09359364-a1aa-51ed-9e82-511f0e634c46 | note | Method - Document Review
8e5a4a2e-4022-50ed-ad57-00f8dfecff33 | note | Frequency - Once, prior to closure of this lot / element / Work area
b36f4ff9-5e7b-538d-a4b9-2a9d103b8bd9 | note | Category - HP*
87a4189d-ac3b-559f-bf77-35ee10306f8c | note | Responsibility - SE/PE
99954048-543c-5d09-902d-68a5f0a8bff0 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
32857496-29de-5243-b373-481f85b5ab00 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c1ef8caf-38bd-5661-b31c-9d78b5455f44 | textbox | Name:
aaeb7a42-5975-53aa-969b-f8f2602862bf | textbox | Position:
cd1185db-e490-5eea-8240-00443250f3d8 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-176-CIV-BRUNT-Line Marking Rev 0 | itp | ITP-176-CIV-BRUNT-Line Marking Rev 0 | ab24cfe2-d677-425a-b369-b0f7d96cad07
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
de62d85a-3634-5e23-870e-92aa52dfe296 | note | Document Title: ITP-176-CIV-BRUNT-Line Marking
e4fd6d91-08c4-5b0c-a7c3-c7e2031fda3d | note | ITP Description: Line Marking
aa383666-40f6-5d28-abd9-0e26d8838290 | note | Discipline (e.g. CIV/STR/RAIL): CIV
ca2763ce-1ae6-5194-bc9c-225eda4a85bd | note | Revision Number: 0
68a4d968-6864-5030-902d-a8bc95f1aab3 | note | Revision Date: 27/05/2024
8acff572-085d-5ba6-897a-5a762d066b7a | note | ITP created by: Jon De Castro
8b85500b-150f-52ea-bcd7-57c52f3e580e | note | ITP approved for use by: Jon De Castro
| checkpoint | 1.1 - Non Dependent
87be218d-3e30-52c3-ac78-b0c13205ea3a | note | Reference - VR Section 721
| checkpoint | 1.2 - Non Dependent
33c21c48-67bb-57dc-82a1-993e651a81a2 | note | Reference - VR Section 175
| checkpoint | 1.3 - Non Dependent
4208b2b3-d128-5d0d-9da7-ce035ef91ec7 | note | Reference - VR Section 853
| checkpoint | 1.4 - Non Dependent
95365e27-160f-5446-be91-c248ebfed308 | note | Reference - IFC Drawings
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Type of marking material as shown on design drawings and shall conform to the Standard
e9291945-996a-56cb-ad20-fd4aed909028 | note | Reference - Vicroads 721.A05
01fb1a40-d297-5163-b874-a042a48b3105 | note | Acceptance Criteria - Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
65b2a995-cc95-50cf-93c5-ba6854c60861 | note | ○ Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
e18a2480-20b7-5841-8aad-69015a25d638 | textbox | Enter: TeamBInder Material Approval Ref No.
d8b7263b-ccdd-5b90-8701-ee4217d88ef1 | note | Method - Document Review
e99a1dac-f4ac-5d02-ac63-a7e7b3077c76 | note | Frequency - Per Material
05a3022b-8910-5c80-955d-53d25e4319d4 | note | Category - HP
d82e8fb9-aabd-5052-98d6-ce34b4a3ec2b | note | Responsibility - Nominated Authority
d52b35db-1d19-5132-b0e6-d507954ff8d1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Raised Pavement Markers
08cab0f2-72cf-5b5a-adaf-6e2bd877e5e0 | note | Reference - Vicroads 721.A05
1feb7d4c-b4f7-5509-a0d5-b56fcc7738a0 | note | Acceptance Criteria - Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175.
feefd4bb-aec4-5139-9b24-239f8d9ad6d7 | note | (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material.
e1f17793-77d1-5126-82ae-b0aca32a29b6 | textbox | Enter: TeamBInder Material Approval Ref No.
fdac9e6f-14a4-504c-9c75-ced42739164b | note | Method - Document Review
b2261355-698e-51fb-8ecf-0f5f70305230 | note | Frequency - Per Material
895be3a5-87bb-548d-9bb0-47b500208692 | note | Category - HP
c31f5133-dd9e-545b-b723-4444ed789fbb | note | Responsibility - Nominated Authority
bc8edc39-832a-51f6-871e-e7f75fdfa35f | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Adhesive
c9dc4b9c-f75e-5584-9cd4-f8a3f4bb133d | note | Reference - Vicroads 721.A05
3e4b83c7-6676-5728-9ca0-63589ce35b44 | note | Acceptance Criteria - Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
bb53a0f8-8cdd-5a2d-9065-050ef7a53bfd | note | ○ Other types of adhesive materials shall only be used with the approval of the Superintendent
cd8a3fe1-75f9-54ab-9d49-75314ca49d86 | textbox | Enter: TeamBInder Material Approval Ref No.
507d83a8-91c8-5619-82d7-a6485c20d2e8 | note | Method - Document Review
d0e44b40-5ad0-5b57-8ee4-12e590c7333a | note | Frequency - Per Material
3eeec1eb-ee91-5da2-bb2f-fda3d7bc42e5 | note | Category - HP
8aa30fd2-1a79-5f8a-8733-5d97255fe81c | note | Responsibility - Nominated Authority
3b421ed0-0065-5813-8abd-dff93bc271c1 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Line marking and Road marking Paint
470214e2-34eb-5404-9f96-6200526e64d1 | note | Reference - Vicroads 721.A05
7f916f7f-b6b5-5f0b-b804-59a6e4fd0a83 | note | Acceptance Criteria - All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
c0a00ab1-a275-5735-b8f5-e373c3fc0022 | textbox | Enter: TeamBInder Material Approval Ref No.
dbda3049-72e8-5e35-a93f-51bd5e1ba00b | note | Method - Document Review
7405832d-b16e-568d-9cf5-9909be3cff4e | note | Frequency - Per Material
c5c259b3-fdda-5872-8841-f620599421fe | note | Category - HP
cfbdf62a-e86a-5e3a-8dde-e82317e4f406 | note | Responsibility - Nominated Authority
de3e2aed-0600-523b-8006-5bbc3cf7de1e | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Glass beads
dc59d2a5-bb4c-51ef-bb61-f1c825e8e099 | note | Reference - Vicroads 721.A05
ac38a6e6-8bd6-5d94-bc69-6be950d7c869 | note | Acceptance Criteria - Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
43aed708-c5b7-5b70-8cc1-65d655a90c0f | textbox | Enter: TeamBInder Material Approval Ref No.
8465acba-6fb0-5971-b513-010a278188d4 | note | Method - Document Review
cf59c17f-a4b8-5c47-91ed-37a467c482fe | note | Frequency - Per Material
0a3d26aa-4eb0-5315-a31b-3e92a6aa80fa | note | Category - HP
d9d1fa5a-0b54-504e-868f-75a03d0a60f7 | note | Responsibility - Nominated Authority
5fe55008-4091-5858-a499-b620d1877461 | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Pristine glass beads (Type B-HR)
da639177-c849-5bf7-8694-a880c0619bbb | note | Reference - Vicroads 721.A05
77b45d93-e5ce-5d67-85b4-047cb131acb9 | note | Acceptance Criteria - Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
a8b13308-c3d9-5feb-83fd-6e6e0d528d43 | note | ○ Pristine glass beads (Type B-HR)
48a73dcd-1642-5636-af61-8addc6bc73d0 | note | ○ Type B-HR glass beads shall comply with the properties of Type B (AS 2009:2006) drop-on glass beads, with an additional high performance retro reflectivity requirement, requiring the delivery of a minimum 450 mcd/lux.m², when tested in accordance with a modified Appendix M
a4527866-ff10-5207-85de-e650346ed85a | textbox | Enter: TeamBInder Material Approval Ref No.
863870aa-469d-55bb-9351-8b8938d2cd6b | note | Method - Document Review
84ce3fc4-3724-5102-9846-b2b7bdfa4b57 | note | Frequency - Per Material
edd8ff0c-e6a4-5baf-a03b-affc1bd0d088 | note | Category - HP
24807708-c2b3-52a4-b6c9-15a1222d3a64 | note | Responsibility - Nominated Authority
bdcb5321-babc-5920-8f33-3b41de9d68ad | note | Verifying Documents - ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Accreditation to Painting Contractors Certification Program
f3a33350-49a7-5407-8359-f21c58e2e989 | note | Reference - Vicroads 721.D01
d935d9cf-a110-5bde-8ae0-e20205e108ef | note | Acceptance Criteria - Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
a4bfd359-367b-52cf-9f1c-1aa6d39baf61 | textbox | Enter: Teambinder Approval number
8d92ad38-1959-509b-b1aa-9a3f2fd1a62b | note | Method - Document Review
04051865-a529-5293-8a90-ae78a56de228 | note | Frequency - Once
13da9dbc-7f49-5255-af5a-ea88dd2dfab0 | note | Category - HP
3b3bfd11-ec29-5df4-ab58-d733697b98bc | note | Responsibility - Nominated Authority
ce2e40c6-f0c1-5712-95aa-a2691421e783 | note | Verifying Documents - ConQA Hold Point Release
d4787950-8038-5c73-82a5-dfba90a240d4 | note | Attach: PCCP Accreditation
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - Surface preparation
eb55b6e3-bfe4-5b4f-94a7-38afbdd0bb05 | note | Reference - Vicroads 721.A06, Vicroads 721.A09
55501fea-36a0-5dbb-abb1-90dc5e757f20 | note | Acceptance Criteria - The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
af26b46b-dd86-5cff-bac5-53791abdf005 | note | ○ The area around making area is also clean to avoid tracking into the marking area
958b7557-d009-5237-b04d-f99ad31ab41d | note | ○ Removal of existing unsound, obsolete or redundant pavement markings
3ee9eae3-7448-5753-8ab4-337570cb5c50 | note | ○ Removal of any foreign materials and debris within reasonable limits.
e4e6b395-bcfd-5cd1-b889-58528e5276d5 | note | Method - Measure, Visual, Document Review
ab2e6d3b-229d-5358-8b24-2db1f5273966 | note | Frequency - Per Lot
f97d6e66-d62c-5017-a6f8-8d0688e65d9a | note | Category - IP
1138474e-1f6b-5340-9c5f-fa67fefb611d | note | Responsibility - SE/PE/SPE
33809e09-36b9-588e-9603-23b8d8cdd441 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.2 - Redundant pavement / unsuitable marking markers removal
917e3dc0-e505-5c27-bd7c-5687171dfa6e | note | Reference - Vicroads 721.A12, Vicroads 721.A06, Vicroads 721.A08
93e90615-1157-5519-95c0-dcce8fe1f126 | note | Acceptance Criteria - Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
290ef756-84d5-526c-bb21-5fb8d570bf5d | note | Method - Visual /Site Inspection & Document Review
9dc79bac-f465-5bfa-91b7-e2a3f97db164 | note | Frequency - Per Lot
0a60564c-c927-5002-b140-9602db2b2c04 | note | Category - HP*
1c4923d0-1767-5237-bf13-5205c7fce731 | note | Responsibility - SE/PE/SPE
f0ae8860-2e87-5511-acd7-c142aec04ddf | note | Verifying Documents - This ITP Signed Off
| checkpoint | 4.3 - Set out the works for installation of pavement markings / raised markers
d67516ad-5043-5bbd-8c06-81bbdd4ad2a8 | note | Reference - Vicroads 721.B05
d1da1449-7175-5f17-9414-ed5c2387fc5b | note | Acceptance Criteria - Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
8a3ebff9-6e25-57a7-9b2c-49586991fb82 | note | Method - Survey, Document Review
c854fc67-0685-560d-a0b3-8c89a321980c | note | Frequency - Per Lot
45e84188-f405-524c-9529-066008373990 | note | Category - HP*
86917541-7e7f-52de-8238-184206effb0f | note | Responsibility - SE/PE/SPE
52815660-bc1f-5fbc-9759-59c965b45223 | note | Verifying Documents - This ITP Signed Off
| section | 5. Construction Activities
| checkpoint | 5.1 - Application of pavement marking / markers
60c13f70-dad5-55b0-a0d7-607cd933e628 | note | Reference - Vicroads 721
0f6db314-ced0-57bf-87de-efd778f82d5e | note | Acceptance Criteria - Check conditions for application of marking paint & materials.
88772dfb-54ff-5ad7-a377-dab8560bc35f | note | (i) Paints and markers installed as per manufacturer’s recommendations.
898461f9-493c-5349-be2f-bdc1e047f6fc | note | (ii) The same materials used with those nominated in the certifications.
fa3d8ebe-5030-5ab6-bd5b-3cb5774b263c | note | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
5de33a6d-862b-50ee-b4c6-3c3e87afda09 | note | (iv) Verify markings are straight or with smooth, even curves where intended.
90989cb8-c343-5bc4-8ba6-879da616ac9d | note | (v) Edges are clean sharp cut off.
cd1b0d7f-53c3-59b0-a315-02fb1ef7bb37 | note | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
0857a420-fdf6-5d3d-b774-c1f82dbcc855 | note | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
a12c5f65-cf22-505a-9cb0-6bcc98b03984 | note | (viii) Markings are neat & free from traffic damage or other defects
4f14fe9e-3c4e-5910-a92f-44f001ff9f35 | note | (ix) Marking protected from traffic until hardened
073d630b-f7b7-5fd1-b4d4-828a43ea7d66 | note | Method - Visual /Site Inspection & Document Review
df4b35ce-4a9d-5daa-a9bb-816abbd610b3 | note | Frequency - Per Lot
3dd510e7-78aa-5b53-8423-66e0f2f018b7 | note | Category - IP
8dab781c-16a9-5101-b7eb-74c477ec9eed | note | Responsibility - SE/PE/SPE
bf7a9474-ee47-5eb2-bb55-58c0e51d8f31 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 5.2 - Tolerances for new marking/marker installations
08080474-10e9-57c5-bef4-0147a17bcf5e | note | Reference - Vicroads 721.A10 Table 721.A101
a87bb7c8-d4c7-546e-addd-ad541e38c42d | note | Acceptance Criteria - Pavement marking:
26b4eecf-2a13-5755-b2c2-38a2216d3eef | note | ○ Distance between the centreline of the marking and the centreline of the set out mark-<30 mm
63a64a41-2cb3-53e6-8169-af87803bbcb5 | note | ○ Distance between the centreline of the completed marking and the centreline of the previous marking-<15 mm
f812b7c2-ee7e-52cd-929a-f692a5793044 | note | ○ Width of completed painted markings-±10 mm of the specified dimensions
9bc5eb93-de4c-5ecb-b99c-b18a4d67f843 | note | ○ Width of completed markings for long life materials0 mm to +10 mm
ff1b89e9-e7d9-51e6-9361-460cf415532f | note | ○ Length of completed stripes and blocks-0% to +10% of the specified length
e6ec63c2-a0ad-5797-830e-852983d2dfe0 | note | ○ Gap between double lines--10 mm to +0 mm of the required 100 mm gap
233ea9ec-b127-5a11-898b-75b06dcbc7fd | note | Raised Pavement Markers:
ec9a4bd7-c6d3-5cb2-a238-b4eb00950a17 | note | (i) Markers in line with broken segments
6e5e0c50-b9a3-5a9c-8186-f7e0449dcf1e | note | – Transverse position-±25 mm of the centreline of segments
1496ece4-6002-538f-9ecb-e1138143ebb9 | note | – Longitudinal position-±0.5 m of the specified position
300418d4-6787-5799-8775-251862f61e23 | note | (ii) Markers in a longitudinal group
5fc7200c-50fe-5706-b965-4bab69fc8afe | note | – Transverse position-±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
1ff0ac69-f808-517c-8911-9e8fe4ac5615 | note | – Longitudinal position-±0.5 m
74c11814-7808-5b2d-a5d0-a231f94b7a89 | note | – Spacing of markers within the group-50 mm of specified spacing
d63604ad-b021-5ba3-b7f4-de6e2cd8289b | note | (iii) Markers adjacent to an unbroken line
b9f08478-d557-5576-8d1f-117f453b5aa0 | note | – Clearance to edge line-±5 mm of the specified dimensions
a16a7cc2-135e-57b7-99d2-74b740952a1e | note | – Longitudinal mismatch between markers in transverse pairs-<25 mm
9148dd10-13f5-5ca7-acd6-bf777aaf7d64 | note | – Longitudinal position-Lesser of: 0.5 m or 10%
41bc06d8-8790-55ac-b30c-e58c3f59bb35 | note | (iv) Orientation of reflective markers-Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
eb9fee3d-03eb-50db-ad99-d0b99f9140af | note | – Thermoplastic profiled lines
36b97465-b0d7-5366-b850-4735c248d881 | note | (i) Tolerances on dimension
a56d9ff6-ec86-5686-8492-c3258471633d | note | – Line width-+20 mm, -5 mm
4712de71-64f3-5828-b0a1-f21e91511d87 | note | – Line height-+2 mm, -0 mm
9a5da4f3-13cd-521d-8f58-ec02d99a3252 | note | – Extrusion breadth-+10 mm, -0 mm
334d4e82-93f3-55d4-acef-e38c59af8fb6 | note | – Extrusion spacing-±15 mm
0a73cef7-ee2f-5e54-8bb0-67adc6a563a3 | note | – Extrusion shape-±25 mm at any point from rectangular shape
ce9e6663-3db4-555f-af4e-1b6e5d6277c5 | note | (ii) Tolerances on position
452b2685-92f5-5c1a-969e-fb520a9e90df | note | – Distance between the centreline of the marking and the centreline of the set out-<30 mm
8b6dc76f-7d80-5df9-ad08-2a58bf909086 | note | – Length of the completed lines--0% to +5% of the specified length
99456b33-f032-53a6-af0f-6a6d1b6177e5 | note | – Longitudinal position of individual extrusions-±50 mm of any previously applied profiled lining
803b5c0a-bcc0-57c9-b372-e4fc84f6746a | note | Method - Visual /Site Inspection & Document Review
8a137bbc-1e22-54b1-a2a4-5e3fb4b34d41 | note | Frequency - Per Lot
04e6e29b-40e1-57ea-870a-944f8ac7f413 | note | Category - IP
1e4110b9-d0ea-52f1-83e9-d66edc3a2204 | note | Responsibility - SE/PE/SPE
df81f062-ffdd-5153-a9e2-b1d6351bacfa | note | Verifying Documents - This ITP Signed Off
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Retroreflectivity Report
18c5ac40-99ec-59b2-8e46-1d8b3f6ec534 | note | Reference - Vicroads 721.B06 (b)
137aa947-874b-5bd3-97d9-0c35f90a35b5 | note | Acceptance Criteria - Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
37613b44-7323-5498-a1f5-39b558560f8a | note | Method - Document Review
a3904436-2c92-51e5-86a7-d7c3e5cda31c | note | Frequency - Per lot
6299f705-7e2f-51e9-9e1f-8af68392b165 | note | Category - HP*
a661cca5-53cc-5ebc-be9b-0279bf4c8152 | note | Responsibility - SE/PE/SPE
c5419c2c-9259-5d46-ba7b-15b612107a69 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.2 - Job Completion Report
9501123d-ab5c-5300-bfe0-9da221871dab | note | Reference - Vicroads 721.B06 (a)
e59bc4ec-c8df-5645-8baa-7fc82a4095fd | note | Acceptance Criteria - For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings).
b99bc04c-b472-50ba-b7cd-f6db39f1d7e5 | note | Method - Document review
d198f15f-0a4d-5b6b-9a46-1d0e0d3ed1c0 | note | Frequency - Per lot When applicable
6d51cbd5-34d4-569f-b393-e979c4160d4e | note | Category - HP*
c57f6329-3bd7-52f5-a6bc-c206253412ef | note | Responsibility - SE/PE/SPE
b124d97f-73c9-5d0f-af22-b72d41c4f209 | note | Verifying Documents - This ITP Signed Off
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
17ffd294-73dc-53d6-8c1a-760da5a76207 | note | Reference - MRPA Quality Management Plan
282b117f-7688-59d7-9f06-d151ff89ce07 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
8e4ca5a8-1e70-506d-8d71-bc28eeecbfa6 | note | Method - Document Review
b2e5ea04-d529-5f6d-91a0-83641b672b7f | note | Frequency - Once, prior to closure of this lot / element / Work area
bed94a5e-3e2c-5105-a8b5-9b0211519efd | note | Category - HP*
b1922ae6-2f0f-5a12-b017-b56dda4798a6 | note | Responsibility - SE/PE
d4179b47-b4a2-5157-b7fc-e5daa07e5749 | note | Verifying Documents - This ITP Signed Off
| checkpoint | Final Inspection
3a043148-beae-59b2-8810-8a834e788bf6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
aed4bb06-44cd-5a59-b2cf-ba3ab1b0bee3 | textbox | Name:
7c949863-8c63-5aef-bb70-432f269919a5 | textbox | Position:
c347d841-34a9-56d0-ac42-d7c24d1df02a | date | Date Completed:
| signoff | Sign ITP