## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-192-CIV-Brunt-Handrails (Supply & Install) Rev 0 | itp |  |  |  |  | ITP-192-CIV-Brunt-Handrails (Supply & Install) Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-192-CIV-Brunt Rd - Handrails (Supply & Install)
label | ITP Description: Brunt Rd - Handrails (Supply & Install)
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 22/08/2024
label | ITP created by: Sandy Escalona/ Derek Collins
label | ITP approved for use by: Sandy Escalona
checkpoint | 1.1 - Non Dependent
label | Reference - IFC Drawings VicRoads Section 610 & 630, AS 1252, AS 5100.6, AS 5131:216
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Concrete Mix Design
label | Reference - VR Clause 610.07, VR Table 610.071
label | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on IFC drawings (32MPa)
textbox | Enter: Teambinder Material Approval number
label | Method - Verify, Document Review
label | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA/ TB Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Drawings
label | Reference - VR Clause 630.05
label | Acceptance Criteria - Subcontractor is responsible for preparation and verification of shop drawings. Prior fabrication, shop drawings are to be verified by a competent Structural Steel Engineer. Evidence of this review and competency of the reviewer shall be submitted to Nominated Authority.
label | Method - Verify, Document Review
label | Frequency - Prior fabrication
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA/ TB Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Material Certification
label | Reference - VR Clause 630.07
label | Acceptance Criteria - The Subcontractor shall submit to the Nominated Authority the steel manufacturer’s Certificate of Product Compliance and all related test certificates demonstrating compliance to the relevant steel product standards listed in Table 630.071, including all impact test values when appropriate.
label | ○ The test certificates shall be related to the steel by trademarks and heat number.
label | Method - Verify, Document Review
label | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA/ TB Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Check for correct documentation
label | Reference - IFC Drawings, Manufacture's Installation Guideline
label | Acceptance Criteria - Ensure that all employees and sub contractors are:
label | ○ Using the correct and complete set of IFC drawings (latest revision as per TeamBinder)
label | ○ Using approved shop drawings
label | ○ Follow Manufacturer's recommendations
label | Method - Document Review
label | Frequency - Once, prior to the commencement of activities
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
section | 4. Pre-construction Activities
checkpoint | 4.1 - Setting out
label | Reference - IFC Drawings
label | Acceptance Criteria - Set out work in accordance with IFC Drawings.
label | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings
label | ○ Attach: Lot Map-marked up drawing to indicate the location of the Lot
label | Method - Verify
label | Frequency - Prior to starting Works
label | Category - HP*
label | Responsibility - Surveyor/ Nominated Authority
label | Verifying Documents - This ITP
section | 5. Construction Activities
checkpoint | 5.1 - Footing Installation
label | Reference - IFC Drawings, Manufacturer's Installation Guideline
label | Acceptance Criteria - Footings to be constructed by Superintendent following IFC Drawings and Manufacturer's Installation Guidelines.
label | ○ Attach: subcontractors ITP signed off
label | Method - Visual, Site Survey
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Surveyor/ SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.2 - Installing Structures on site snug-tight Condition or tensioned using the Part-turn method if required
label | Reference - IFC Drawings AS 1252, AS 5100.6, Manufacturer's Installation Guideline
label | Acceptance Criteria - Bolts shall be installed as per AS 1252 & AS5100.6. All bolts to be supplied complete with nut, locknut (where specified) & washer.
label | ○ Attach: subcontractors ITP signed off
label | Method - Visual, Site Survey
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.3 - Grouting of Base Plate Posts
label | Reference - IFC Drawings AS 1252, AS 5100.6, Manufacturer's Installation Guideline
label | Acceptance Criteria - Superintendent to survey posts and confirm it is within tolerances prior to grouting base plates. Grout as per Engineering specifications.
label | ○ Attach: subcontractors ITP signed off
label | Method - Check level and alignments
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | 5.4 - Completion of Works
label | Reference - IFC Drawings, Approved shop drawings
label | Acceptance Criteria - Ensure that works were constructed as per IFC & approved shop drawings. Subcontractor and Superintendent must inspect works for damages and rectification of defects, including but not limited to protective coating and painting touch ups.
label | ○ Attach: subcontractors ITP signed off
label | Method - Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
section | 6. Post-construction Activities
checkpoint | 6.1 - DDA audit compliance
label | Reference - IFC Drawings AS 1428.1, AGRD 6A
label | Acceptance Criteria - Ensure compliance for railing heights and offsets from pathways
label | ○ Attach: DDA compliance report
label | Method - Document Review
label | Frequency - Completion of each lot
label | Category - WP
label | Responsibility - Surveyor/ SE/PE/SPE
label | Verifying Documents - DDA compliance report
checkpoint | 6.2 - Compressive Strength Test Results
label | Reference - IFC Drawings, Table VR Table 610.051, VR Clause 610.16
label | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each cylinder
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
checkpoint | 6.3 - NCR Close out (if applicable)
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot/ element/ work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP