## Structure
Id | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Checklist Template
fo:c8da2370-bb09-4227-80bf-49aa3871c647 | roof
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist |  |  |  |  | Quarterly Maintenance Checklist
fo:2c095aca-7eac-41e9-ab75-7e7aabc1569f | Chiller
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water |  |  |  |  | FCU Units Water
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 | Site Inspection - | [5 empty] | H&S - Site Inspection
fo:300f28ee-79d7-4986-8369-adf39f1b1919 | Plant room
fo:f5fb9f77-4cb0-4eb5-ada4-22b470617634 | Level 3
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist |  |  |  |  | Quarterly Maintenance Checklist
fo:6aee9124-dd76-4f37-a81f-a8680f986cd8 | Level2
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist |  |  |  |  | Quarterly Maintenance Checklist

## Checklists
Id | Location | Checklist Name | Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Not started | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | In progress | FCU Units Water | Chiller | FCU Units Water
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Failed | H&S - Site Inspection | Site Inspection -
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | In progress | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | In progress | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist

## Checkpoints
Checklist Id | Location | Checklist Name | Section Name | Checkpoint Name | Checkpoint Status | Signoff Status | Checklist Template | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Job Details | Job Details | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Indoor Units | Check unit operation | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Indoor Units | Check and clean filters | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Indoor Units | Check indoor air handler and report if cleaning is required | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Indoor Units | Check condensate drain line and test with 1 litre of water to ensure condensate is flowing freely | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Indoor Units | Check electrical wiring including thermostats and adjust where necessary. | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Indoor Units | Check flexible ducting for air leaks, retape and resupport where necessary. | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Indoor Units | Check if ducted system is fitted with passive fresh air | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Fans | Check fan current draw and damper operation | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Fans | Check and clean all grilles and filters | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Fans | Check sheet metal and flexible ducting for air leaks | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Fans | Check for excessive noise and vibration | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check and test stop and start sequence | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check condenser coils for obstruction | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check pipework and units for vibration | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check external pipework for evidence of any leaks | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check all electrical terminals for tightness | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check contactors, relays and compressor amp draw | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check condenser fan motors | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check refrigerant levels | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Outdoor Units | Check all covers are secure | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Timeclock | Check timeclock is displaying the correct time | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Timeclock | Check the "on-off" time settings making sure equipment is operating accoridngly and correct for customer's requirements | Not started |  | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:a5142dc9-91f9-4f41-9774-49685f447e99 | roof | Quarterly Maintenance Checklist | Summary | Comments of further work required | Not started | Open | Quarterly Maintenance Checklist | roof | Quarterly Maintenance Checklist
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Drawing number | Not started |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Attach highlighted drawing of unit getting q.a (can be a photo of drawing) | Not started |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Unit model correct. (photo) | Not started |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Unit labelled | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Hot water | N/A |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Chilled water | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Electric heat. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Pipe size right | N/A |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Valves installed as per schematic. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Control valves as per schedule. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Actuator installed. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Insulation Correct no gaps on chilled water. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Insulation as per spec. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Plenums installed as per drawing. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Plenums Sealed. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Spigots open | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Spigots sealed with Plastic wrap. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Seismic to design. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Filter fitted or note if is second fix i.e. in grill. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Condensate drain installed correctly. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Condensate checked for flow with water. | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | 2m of insulation on condensate line after unit. Check spec to confirm if more is needed. | N/A |  | FCU Units Water | Chiller | FCU Units Water
cl:adea6708-886d-471e-adc2-9e16f6eda105 | Chiller | FCU Units Water | Details | Site left tidy | Passed |  | FCU Units Water | Chiller | FCU Units Water
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Details | Details Complete (pass once relevant details are recorded below) | In progress |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Control | Hazard Board and signage up-to-date | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Control | Environmental plan - issues | In progress |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Control | Safety inductions for all on-site | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Control | Safety notice board current | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Facilities | Offices clean, adequate & good lighting | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Facilities | Smoko sheds - clean, portable water | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Facilities | Toilets - clean, washing water | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Site Facilities | Tool /equipment sheds adequate | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | General Site Tidiness and Access ways | Clear, safe access to work areas | N/A |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | General Site Tidiness and Access ways | Stairways and accessways clear | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | General Site Tidiness and Access ways | Hoardings /fence and gates secure | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | General Site Tidiness and Access ways | Loose materials secure from wind | N/A |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | General Site Tidiness and Access ways | House Keeping | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Personal Safety Equipment | Signage displayed and legible | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Personal Safety Equipment | Hardhats and boots being worn | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Personal Safety Equipment | Glasses /ear muffs /vests /masks used | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Personal Safety Equipment | Task specific PPE used | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | First Aid/Fire Prevention | First Aid Box Available | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | First Aid/Fire Prevention | Accident register | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | First Aid/Fire Prevention | Fire Extinguishers | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | First Aid/Fire Prevention | Evacuation | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Cranes/hoist/lifting equipment | Proper lift assessment plan done | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Cranes/hoist/lifting equipment | Crane certification current | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Cranes/hoist/lifting equipment | Slings/chains certified | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Cranes/hoist/lifting equipment | Operator procedures in place | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Cranes/hoist/lifting equipment | Inspections being done | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Cranes/hoist/lifting equipment | Man cage available | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Cranes/hoist/lifting equipment | Emergency plan in place | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Tools and equipment | In good condition | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Tools and equipment | Appropriate guards fitted | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Tools and equipment | Trained user | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Excavations | Correctly Shored/Benched/Battered | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Excavations | Access/Egress Installed | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Hot Works | Hot work permits being issued | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Hot Works | Fire extinguishers on hand | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Hot Works | Operators using PPE | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Main board lockable /weatherproof | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Current tagged and damage-free leads | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Current tagged plant | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Current tagged lifeguards | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Leads safely placed | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Equipment in good condition | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Appropriate guards on equipment | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Electrical Equipment | Adequate temporary lighting | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Chemicals | Correctly stored | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Chemicals | Safety Data Sheet (SDS) available | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Chemicals | Operators using PPE | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | P.A.T Tools | P.A.T tool WoF current and secure | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | P.A.T Tools | Staff trained in tool use (SWPS) | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | P.A.T Tools | PAT signage on site | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Ladders | Good condition | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Ladders | Access Ladders secured top and bottom | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Ladders | Stays and rungs undamaged | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Ladders | Working within weight limits | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Fall Hazards | Fall Hazards | Failed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Fall Hazards | Floor openings | N/A |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Fall Hazards | Lift shafts | N/A |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Fall Hazards | Stairs | Passed |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | EWP | Clean, Deck Clear | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | EWP | Log complete | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | EWP | Exclusion in place | Not started |  | H&S - Site Inspection | Site Inspection -
cl:22e09d49-b1fc-4c25-8a85-a58b8ae6b5f0 |  | Site Inspection - | Signoff | Required people sent signoff request | Not started | Open | H&S - Site Inspection | Site Inspection -
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Job Details | Job Details | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Indoor Units | Check unit operation | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Indoor Units | Check and clean filters | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Indoor Units | Check indoor air handler and report if cleaning is required | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Indoor Units | Check condensate drain line and test with 1 litre of water to ensure condensate is flowing freely | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Indoor Units | Check electrical wiring including thermostats and adjust where necessary. | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Indoor Units | Check flexible ducting for air leaks, retape and resupport where necessary. | In progress |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Indoor Units | Check if ducted system is fitted with passive fresh air | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Fans | Check fan current draw and damper operation | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Fans | Check and clean all grilles and filters | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Fans | Check sheet metal and flexible ducting for air leaks | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Fans | Check for excessive noise and vibration | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check and test stop and start sequence | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check condenser coils for obstruction | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check pipework and units for vibration | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check external pipework for evidence of any leaks | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check all electrical terminals for tightness | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check contactors, relays and compressor amp draw | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check condenser fan motors | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check refrigerant levels | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Outdoor Units | Check all covers are secure | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Timeclock | Check timeclock is displaying the correct time | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Timeclock | Check the "on-off" time settings making sure equipment is operating accoridngly and correct for customer's requirements | Not started |  | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:7398785c-6c94-4281-a7b3-eb8fa88d8b38 | Level 3 | Quarterly Maintenance Checklist | Summary | Comments of further work required | Not started | Open | Quarterly Maintenance Checklist | Level 3 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Job Details | Job Details | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Indoor Units | Check unit operation | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Indoor Units | Check and clean filters | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Indoor Units | Check indoor air handler and report if cleaning is required | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Indoor Units | Check condensate drain line and test with 1 litre of water to ensure condensate is flowing freely | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Indoor Units | Check electrical wiring including thermostats and adjust where necessary. | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Indoor Units | Check flexible ducting for air leaks, retape and resupport where necessary. | In progress |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Indoor Units | Check if ducted system is fitted with passive fresh air | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Fans | Check fan current draw and damper operation | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Fans | Check and clean all grilles and filters | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Fans | Check sheet metal and flexible ducting for air leaks | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Fans | Check for excessive noise and vibration | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check and test stop and start sequence | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check condenser coils for obstruction | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check pipework and units for vibration | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check external pipework for evidence of any leaks | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check all electrical terminals for tightness | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check contactors, relays and compressor amp draw | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check condenser fan motors | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check refrigerant levels | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Outdoor Units | Check all covers are secure | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Timeclock | Check timeclock is displaying the correct time | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Timeclock | Check the "on-off" time settings making sure equipment is operating accoridngly and correct for customer's requirements | Not started |  | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist
cl:cdab0cd5-bc6c-4908-8716-7b0a19f22418 | Level2 | Quarterly Maintenance Checklist | Summary | Comments of further work required | Not started | Open | Quarterly Maintenance Checklist | Level2 | Quarterly Maintenance Checklist

## Checklist Templates
Id | Type | Name | Values | Prompting Name | Usage Count | Resource Id
| checklist | Chilled Water Pipe Pre Pressure Test |  | Chilled Water Pipe Pre Pressure Test | 0 | e2d16ecb-9d5f-46a4-b1ca-277872e812cb
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of pipe getting q.a (can be a photo of drawing)
| checkpoint | Hangers installed with correct spacings.
| checkpoint | Pipe sizes correct to up to date planes
| checkpoint | Valves installed were shown.
| checkpoint | Air vents installed were needed.
| checkpoint | Drains installed were needed
| checkpoint | No valves handles on the bottom of pipe
| checkpoint | Valve sets as per up to date plans.
| checkpoint | Photos
| checkpoint | All joints complete
| checkpoint | Brazed or press fit
| checkpoint | Any pipe in walls provide photos.
| checkpoint | Pipe labelled.
| checkpoint | Site left tidy
| checklist | Close Out Documentation |  | Close Out Documentation | 0 | 9bd8d354-bf9a-4e30-8e6a-34492266ce20
| checkpoint | PS3
| checkpoint | COC
| checkpoint | AS built
| checkpoint | Manuals
| checkpoint | Commissioning results
| checklist | Commissioning |  | Commissioning | 0 | 514aaef4-3fcd-4847-8587-40b53f95b322
| section | Completion Status
| checkpoint | Electrical Complete
| checkpoint | Plumbing Complete
| checkpoint | System Ready for Commissioning
| section | System ID
| checkpoint | System identification
e2e7ba8d-7981-587e-8ddc-c94510d97622 | textbox | System identification as per Drawings
| checkpoint | Wall controller installed correctly
| checkpoint | Wall controller time and date set
| checkpoint | Wall controller operating correctly
| section | Drain
| checkpoint | Tundish Installed (photo)
| checkpoint | Tundish directional flow correct
| checkpoint | Drain terminated at tundish correctly (photo)
| checkpoint | Drain terminated at indoor unit correctly (photo)
| checkpoint | Access to test drain
| checkpoint | Drain tested
| section | Indoor Unit
| checkpoint | Take photo of model and serial number
| checkpoint | Unit installed correctly
| checkpoint | Pipes fully insulated
| checkpoint | Visible duct installed correctly and free of obstruction
| checkpoint | Fan operating and free of vibration
| section | Grilles
| checkpoint | Grilles installed correctly
| checkpoint | Grilles air-balanced to design airflows
| checkpoint | Strings removed from damper
| section | System Operation
| checkpoint | Correct Operating Temperatures and Pressures (provide 1 x temp read)
| section | Additional Comments
| checkpoint | Additional Comments and Notes
| section | Summary
| checkpoint | Apartment is Completed to ASC satisfaction and ready for handover
| checklist | Condensate Drainpipe |  | Condensate Drainpipe | 0 | c3b280c5-12e2-48c7-934b-c6088106b12c
| checkpoint | Size as per drawing if sized.
| checkpoint | Fall is achieved as required.
| checkpoint | Rod spacings are pipe specific.
| checkpoint | Insulation installed last 2m before units.
| checkpoint | Main pipe is terminated at tundish provided buy other.
| checkpoint | Units are connected.
| checkpoint | Traps installed were needed.
| checkpoint | All drains are water test for fall and leaks.
| checkpoint | Any pipe in walls provide photos
| checkpoint | Site left tidy
| checklist | Duct |  | Duct | 0 | ff592fba-6f65-4612-bc48-128aa47a6117
| checkpoint | Drawing number
| checkpoint | Attach highlighted drawing of duct getting q.a (can be a photo of drawing)
| checkpoint | System type.
| checkpoint | Installed as per latest drawings.
| checkpoint | Flange clamps installed.
| checkpoint | Adequate hangers
| checkpoint | Seismic to design. (Photo)
| checkpoint | Sealant applied to slip joints.
| checkpoint | Flange tape applied to flanged joints.
| checkpoint | Fire dampers installed. (not applicable to kitchen duct)
| checkpoint | Dampers all open.
| checkpoint | Open ends temporarily blanked of with plastic wrap.
| checkpoint | Duct Insulated external.
| checkpoint | Strapping installed.
| checkpoint | Taped up with no gapes.
| checkpoint | Site left tidy
| checklist | Electrical Fit Off |  | Electrical Fit Off | 0 | 0fcf7f04-3d45-4410-a93f-c4bc7cc4d046
| checkpoint | All control components are fit of
| checkpoint | Board complete
| checkpoint | Labelling complete
| checkpoint | Testing complete
| checkpoint | COC
| checkpoint | Site left tidy
| checklist | FCU Refrigeration |  | FCU Refrigeration | 0 | 7e953307-4624-4308-b3e3-e8e059fcd6bb
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of unit getting q.a (can be a photo of drawing)
| checkpoint | Fridge pipe terminated and tested.
| checkpoint | Fridge pipe insulated.
| checkpoint | Plenums installed as per drawing.
| checkpoint | Plenums Sealed.
| checkpoint | Spigots open
| checkpoint | Spigots sealed with Plastic wrap.
| checkpoint | Seismic to design.
| checkpoint | Condensate drain installed correctly.
| checkpoint | Condensate checked for flow with water.
| checkpoint | 2m of insulation on condensate line after unit. Check spec to confirm if more is needed.
| checkpoint | Site left tidy
| checklist | FCU Units Water |  | FCU Units Water | 1 | d4d39076-24ea-413c-b3b7-b0de87e42423
| checkpoint | Drawing number
| checkpoint | Attach highlighted drawing of unit getting q.a (can be a photo of drawing)
| checkpoint | Unit model correct. (photo)
| checkpoint | Unit labelled
| checkpoint | Hot water
| checkpoint | Chilled water
| checkpoint | Electric heat.
| checkpoint | Pipe size right
| checkpoint | Valves installed as per schematic.
| checkpoint | Control valves as per schedule.
| checkpoint | Actuator installed.
| checkpoint | Insulation Correct no gaps on chilled water.
| checkpoint | Insulation as per spec.
| checkpoint | Plenums installed as per drawing.
| checkpoint | Plenums Sealed.
| checkpoint | Spigots open
| checkpoint | Spigots sealed with Plastic wrap.
| checkpoint | Seismic to design.
| checkpoint | Filter fitted or note if is second fix i.e. in grill.
| checkpoint | Condensate drain installed correctly.
| checkpoint | Condensate checked for flow with water.
| checkpoint | 2m of insulation on condensate line after unit. Check spec to confirm if more is needed.
| checkpoint | Site left tidy
| checklist | Fire Damper # |  | Fire Damper # | 0 | d10a432f-7f3c-4436-8cec-897b51d0db2b
| checkpoint | Details
d73b23c8-1ce1-5fb4-9ece-b3fcb026964f | textbox | System Type
ba5d857d-90ca-5ce6-aebc-19cadc18fc75 | textbox | Damper Location
33428dc1-65f7-535c-b921-5bc39a6b330d | textbox | Damper Size
1f302373-0599-519e-ae9c-6fc61904e97b | textbox | Model Oreintation
| checkpoint | Installation Completed
87c63b24-ef81-581b-b4d8-410495b5550b | textbox | Name of Installer
36544955-4658-5332-ac96-15f5357d8b06 | note | Please click on the paperclip and add signature
| checkpoint | Testing Completed
d85cff68-fd45-5b48-8514-b9ff1230639e | textbox | Name of Tester
19cb855d-10f7-5443-be17-677678cdff53 | note | Please click on the paperclip and add signature
| checkpoint | Fire Damper Rating
68649309-67f1-54c8-a3ee-b7264c736384 | dropdown | FD Rating Required: | 30min,1hr, 2hrs, 3hrs, 4hrs
203b15b4-a3d2-5af7-a759-4cb3936fa248 | dropdown | Actual Rating | 30min,1hr, 2hrs, 3hrs, 4hrs
| checkpoint | Labelled
| checkpoint | Is fire rated certified material packed between Damper & building work
| checkpoint | Are Angles Fixed around damper both sides?
| checkpoint | Damper has been checked for flow direction, correct free operation and access
| checkpoint | Does the Wall/Floor comply with fire rating requirements?
| checkpoint | Does the Wall/Floor penetration comply with fire rating requirements?
| checkpoint | Site left tidy
| checklist | Grill Boxes and Flexible Duct |  | Grill Boxes and Flexible Duct | 0 | 76e520b1-282d-41a8-8b0e-a550c1f65317
| checkpoint | Drawing number
| checkpoint | Attach highlighted drawing of ceiling getting q.a if only a portion.
| checkpoint | Flexible is supported of the ceilings.
| checkpoint | Flexible is the right size
| checkpoint | Flexible is the right R value if insulated.
| checkpoint | No sharp bends on flexible
| checkpoint | Flexible ducts are not to long.
| checkpoint | Flexibles are taped of and cable tyed
| checkpoint | Insulation is pulled right over the spigots and taped
| checkpoint | Grill boxes are fixed to grills.
| checkpoint | No gaps for air to escape from grill box to grill joint
| checkpoint | Grill boxes are hung from ceiling as per design or as required.
| checkpoint | Site left tidy
| checklist | H&S - Accident & Incident Investigation |  | Accident & Incident Investigation Report | 0 | 209a7709-c33e-402f-9ccc-d08276411ab7
| section | Details
| checkpoint | Details Completed
744e1ac8-3773-579e-a0f5-792d59179d55 | textbox | Name of Investigator:
| section | Particulars of Incident
| checkpoint | Particulars of Incident Details Completed
f786f63e-cc35-5a80-8c2f-97569f4c1573 | dropdown | Day of Incident: | Monday,Tuesday,Wednesday,Thursday,Friday,Saturday,Sunday
1d31c2b3-8be7-5039-bc31-771e08f40adf | textbox | Time:
80b84a99-7898-5a80-8770-ed49e64130c3 | textbox | Project/Site:
bb11d683-b220-51fc-b11f-b70aa74bb839 | textbox | Date Reported:
| section | Injured Person Details
| checkpoint | Injured Person Details Completed
834d1cdd-2604-59c1-b312-2c06114245a3 | textbox | Name:
2f850aac-6e5b-541c-97d1-db81ee37021f | textbox | Age:
596a6fdd-7177-5fe8-aa7d-6cc56d1cd88b | textbox | Phone Number:
90de824a-14d2-56a3-8ad3-9360afdeeb2d | textbox | Address:
e496136c-ba58-5e43-ab52-007391c897eb | textbox | Reported date of incident:
84fe7300-e1c8-50c8-8884-4d96af987707 | textbox | Length of employment:
92136cb0-51cf-5fcd-a9cd-db051d78ae47 | textbox | Time on job:
| checkpoint | Type Of Injury:
b8be361b-87ad-5307-aeff-9fc44bd9868e | tickbox | Strain/sprain
af2c6e91-03d6-53c7-b572-4d5778c37dfb | tickbox | Fracture
8a111c52-edb1-596f-9a82-7a9836294d84 | tickbox | Laceration/cut
d047f39e-caa1-5409-9f11-031c745e49dc | tickbox | Bruising
ac2de79e-2574-59dc-bfb5-06322511182a | tickbox | Scratch/abrasion
938b3ca8-5e38-5e07-8345-b0bdc47ca056 | tickbox | Amputation
ef397f87-21c0-58a2-896c-2c8bc0550b44 | tickbox | Burn scald
11273c6a-ba56-5a78-8e14-86aa2f637637 | tickbox | Dislocation
69da1fc8-4e5a-5068-a688-374ba7906a76 | tickbox | Internal
fd7bd49b-a7f3-5fc1-b43f-56dfdf31c02a | tickbox | Foreign body
7fba2b82-957d-5255-a82f-7262ec96b050 | tickbox | Chemical reaction
a8f58e12-784a-54a5-9e7d-82d8ce795cf2 | tickbox | Other
1f3ff08c-a1f8-522d-8f5c-f577d304db94 | textbox | If other please specify:
dc79ca10-9877-5bf0-9a94-2388ef9ae825 | textbox | Injured Part of Body:
| section | Damaged Property
| checkpoint | Damaged Property Details Completed
f714bab7-572f-5dd7-a551-1c0634d8cb20 | textbox | Property/material damaged:
05b8f1be-0775-53b3-9445-60e4e556a713 | textbox | Nature of damage:
cec16146-7ec9-57b4-a2e3-38fb7cad6afa | textbox | Object/substance inflicting damage:
| section | Incident
| checkpoint | Incident Details Complete
a430e0c4-98fe-58d3-a203-e633dfb70184 | textbox | Describe what happened (space overleaf for diagram – essential for all vehicle incidents):
| section | Analysis
| checkpoint | Analysis Details Completed
86102e1a-9cab-5446-bf74-9beac947c7ed | textbox | What were the causes (root and contributing causes) of the incident?
2517bc3b-43a4-5d5a-8274-c678d198625b | textbox | Root causes – safety system failures:
b15acd75-7834-5515-967a-e2d7058062b6 | textbox | Contributing causes – unsafe acts and conditions:
| section | Prevention
| checkpoint | Prevention Details Completed
95e4526c-881c-596e-b225-8dfe1b5363fa | textbox | What action has or will be taken to prevent a recurrence? Tick items already actioned
811e7626-ddbd-5ead-b797-297293b45266 | tickbox | Completed
36967331-b535-5129-9cf5-05378c112c0a | textbox | By Whom:
e772ec0f-586c-5447-9d33-7b130a4f49bf | textbox | When:
| section | Treatment and Investigation of Incident
| checkpoint | Treatment and Investigation of Incident Details Completed
5667461d-e760-5451-a337-2b2e4273119c | textbox | Treatment and Investigation of Incident :
d79a6c9d-0efb-5bdc-96cb-84e4764f227e | textbox | Name of person giving First Aid:
05e9a0b9-bf6c-588c-958f-e5d7d2261885 | textbox | Doctor/Hospital:
6f45de04-3198-58ef-a963-c77c7f92eb5b | textbox | Incident investigated by:
29dd4390-8069-50a6-a8f9-c247bdfc5a7e | textbox | Date:
42ef6325-503a-5684-b6b7-778482bda5a7 | dropdown | Worksafe NZ advised | Yes,No
243f241b-77a9-59e9-87dc-dbddad68a65e | textbox | Date:
| section | Signoff
| checkpoint | Required people sent signoff request
| signoff | Signoff
| checklist | H&S - Daily Prestart |  | Date: | 0 | b5a8e840-f570-4688-b392-feec8630e8e1
| checkpoint | Person/s in charge of site operations
| checkpoint | Weather conditions
aa609aee-cc45-5bbd-8f79-7e21c1fb2b4d | dropdown | Conditions | Sunny, Overcast, Cloudy, Rainy
| checkpoint | Wind Conditions
c62d18a3-5bdc-5566-aa28-6b2337f03812 | dropdown | Conditions | Strong, Medium, Low, None
| checkpoint | Meeting minutes
| checkpoint | Safety minutes
| checkpoint | Main contractor supplied minutes
| checkpoint | Signatures of all attendees
| signoff | Send signoff to all attendees
| checklist | H&S - Safety Stand Down |  | Safety Stand Down | 0 | d1a77538-6e6b-4e2b-b8ce-39435617f4d7
| checkpoint | Who is running this meeting
| checkpoint | Cause of the stand down
| checkpoint | Trades affected
| checkpoint | Meeting minutes or updated TA
| checkpoint | Preventative measures put in place
| checkpoint | Signatures of all attendees
| checklist | H&S - Scaffolding |  | Scaffolding for Area: | 0 | 28683da3-2768-47ef-b7f3-af0f961b00ab
| checkpoint | Notifiable weekly Scafftag/current
| checkpoint | Handrails/mid-rails
| checkpoint | Toe boards
| checkpoint | Platforms
| checkpoint | Ladders/stairs
| checkpoint | Base sound
| checkpoint | Work platforms clear
| checkpoint | Platforms trip free
| checkpoint | Planks tied down
| checkpoint | Headroom clear
| checkpoint | Ties/bracing adequate
| checkpoint | Required people sent signoff request
| signoff | Signoff
| checklist | H&S - Site Inspection |  | Site Inspection - | 1 | 24c0540c-58e3-43ce-8032-608fa08cf96c
| section | Details
| checkpoint | Details Complete (pass once relevant details are recorded below)
6fb4bd70-a57c-5027-84b7-c79272aa7839 | textbox | Site/Location :
ef9c8925-ada5-58ec-aafe-2d3b56c7e257 | textbox | Name of Inspector :
| section | Site Control
| checkpoint | Hazard Board and signage up-to-date
887a1966-b33c-52b8-ae27-06dfbb8bbba6 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Environmental plan - issues
742032fd-ad06-5782-92e2-8a7c3bd5a4e1 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
f7f199b7-511b-5fee-a6b4-3a9026fdae4f | textbox | Toolbox talk last date:
| checkpoint | Safety inductions for all on-site
b2f314b6-4ace-5325-b81c-e9aa6fb6f004 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Safety notice board current
52740da5-673b-514c-8c91-cd969ace41b1 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Site Facilities
| checkpoint | Offices clean, adequate & good lighting
0a6e776e-ead5-5e2e-96d6-18e2c88d7da9 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Smoko sheds - clean, portable water
9468652a-0904-5edb-b91f-cb1f7bd3e3ac | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Toilets - clean, washing water
526262bd-caa5-50f0-a533-487f4c78b142 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Tool /equipment sheds adequate
b12f8c47-0ed2-5bb9-a3d5-d25c0e4b600e | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | General Site Tidiness and Access ways
| checkpoint | Clear, safe access to work areas
9831f16e-1513-5606-8031-1736dd44569c | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Stairways and accessways clear
a01ef015-0c2c-57a8-9515-9c6061886695 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Hoardings /fence and gates secure
39618b3e-d0c7-530e-8dd0-a0f3c0b3adae | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Loose materials secure from wind
baaa04de-fe0e-52aa-9c1c-2ba55f9e3144 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | House Keeping
f4619c11-d90e-57f6-a40b-3cce9a5e8678 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Personal Safety Equipment
| checkpoint | Signage displayed and legible
eabd5d90-d41e-500d-9482-4b4f94ebc433 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Hardhats and boots being worn
57b5359d-c77f-5a01-a96a-ae25011ce877 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Glasses /ear muffs /vests /masks used
a878aef2-1758-5bc7-b3b7-1123c9225462 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Task specific PPE used
42b5b147-57f9-50c4-919e-e3d6c566850c | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | First Aid/Fire Prevention
| checkpoint | First Aid Box Available
9af72e46-03a8-5812-9db3-27e3f968f250 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Accident register
17773d67-6245-5815-89ea-788eb78a8886 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Fire Extinguishers
3b9f451f-aa1a-5b21-9db8-4d66d73adf60 | tickbox | Available
756756d0-0471-5c21-b986-4873e3dfe39c | tickbox | Current (12mth)
115d2718-ed90-5945-9904-1afc8369b7c5 | tickbox | Sufficient number
8e59560f-d810-5ab6-ba0f-7f63dc165f43 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Evacuation
c0e72454-1f46-545c-accc-89a3876e526b | tickbox | Procedure current
7585c44c-c8c6-5b7d-832d-4f81e8fe1f3c | tickbox | All emergencies incl
64f4cdf9-5590-589d-8664-f8521de9af11 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Cranes/hoist/lifting equipment
| checkpoint | Proper lift assessment plan done
0b95a5e4-b456-5a2c-acc7-d2cb5d40f92a | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Crane certification current
bbf822a5-2481-5b0d-a1d2-18ff23b2f7cc | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Slings/chains certified
8438b0cd-1487-51ff-ad07-b0fafb555c1e | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Operator procedures in place
ed4ea859-1f77-52e7-9f4a-3de9c5cdf8a7 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Inspections being done
c5999857-2dcd-5260-b105-0456b59a4a9b | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Man cage available
2895d1b9-c6e0-56b7-9ca7-da3b9d62eccb | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Emergency plan in place
74c32a87-e8f4-5143-ab70-ae1130637990 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Tools and equipment
| checkpoint | In good condition
9274bf99-acf0-524c-b227-c5dd577a7211 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Appropriate guards fitted
94a7a05f-df24-5d4f-871d-896772392c41 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Trained user
0da896e2-7feb-579a-824c-7745f4c2bcb4 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Excavations
| checkpoint | Correctly Shored/Benched/Battered
14475989-6fc3-5673-a2d6-9ab7160d560b | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Access/Egress Installed
1092858d-1d9a-5175-bfbe-f14e0493bfa3 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Hot Works
| checkpoint | Hot work permits being issued
18d66f8a-1763-5b6e-b778-8a4e77c1409a | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Fire extinguishers on hand
4336e7b5-0216-5db4-b3d4-63b2de632d6a | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Operators using PPE
63ac5a2d-59e0-5a1f-92d0-dfc4adf28370 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Electrical Equipment
| checkpoint | Main board lockable /weatherproof
c4996885-2ff7-5bd9-9e3b-d4b93f871848 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Current tagged and damage-free leads
5c837abd-2fec-5f90-8680-beb69a3d721a | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Current tagged plant
ded7e71e-815c-59c6-bc83-87855572d50b | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Current tagged lifeguards
fa8ee01b-1afa-5cc3-8404-3c10aa465514 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Leads safely placed
f5f2f465-1c02-5d6d-9397-64bf9e1e1f70 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Equipment in good condition
ed777bd0-f201-5ef5-90bf-a2359aaf892f | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Appropriate guards on equipment
089ae119-aea6-5418-b699-58433d0ff9b6 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Adequate temporary lighting
0be06918-ba22-51f7-9c97-1e9012800fb9 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Chemicals
| checkpoint | Correctly stored
8d297ae6-29a8-5c7c-b409-f3f90a42801c | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Safety Data Sheet (SDS) available
c53d8a30-f106-5e63-8133-f58029eb9b8e | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Operators using PPE
18cae6d7-3b1e-5dc4-9d2a-0be9ce9f4609 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | P.A.T Tools
| checkpoint | P.A.T tool WoF current and secure
e41d9d87-5aaa-5faa-946c-4c3d7f647c58 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Staff trained in tool use (SWPS)
b308e51a-9b45-544c-9b87-cceccb754ed2 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | PAT signage on site
dc794dcd-45ec-5c56-9b56-a01f451e8094 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Ladders
| checkpoint | Good condition
d253feb0-3e54-5b7b-baf1-a8c97f72d805 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Access Ladders secured top and bottom
82bac5e2-b9f6-5df9-871f-2637739015bf | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Stays and rungs undamaged
4d81919a-008f-5a57-886f-6e9c51e9ed81 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Working within weight limits
cc317472-6603-5a0f-931e-d7032ec4bbd5 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Fall Hazards
| checkpoint | Fall Hazards
d2564b24-31dc-5ed3-a61b-e61da8777206 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Floor openings
a7140427-3b91-5c16-8094-3911e730b029 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Lift shafts
0254bdc9-1ae9-5db7-b20a-c0a01ac5a552 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Stairs
9662fdde-d58b-5c59-9cb9-9b3b41cba6b1 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | EWP
| checkpoint | Clean, Deck Clear
7c1297e8-7461-578d-8191-ccc0285d9757 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Log complete
5011af56-243d-5fa0-90fe-4196338f81c8 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| checkpoint | Exclusion in place
7ee25959-ab4e-59b5-a348-9e19ae0c9ee9 | dropdown | Priority | 1 - within 24 hours,2 - within 48 hours,3 - within 7 days,4 - no action required
| section | Signoff
| checkpoint | Required people sent signoff request
| signoff | Signoff
| checklist | H&S - Toolbox Meeting Minutes |  | Toolbox Meeting - | 0 | 1a3c6728-2e86-4270-a71a-4f87769fbfd2
| section | Details
| checkpoint | Details Complete (pass once all relevant details are inputted below)
d53229d0-5af1-539f-a027-6e308f09bb35 | textbox | Office location:
8a42238e-e663-5b36-89a0-28a253d2a4b0 | note | Who is running this meeting
cf2af2af-84fc-5bb9-887c-f992f70d2ee5 | textbox | Name:
3ead659d-0d7c-5eca-a73c-aa209c51df75 | textbox | Company:
579b2761-860f-5a34-8fe5-72569618a936 | textbox | Agenda items:
31b8b719-0ec6-586d-9a49-47951213016e | textbox | Theme of the week (topic for focus):
| section | Health and safety issues
| checkpoint | Relevant Issues recorded with appropriate actions and date
e23e9838-2435-55df-9221-92d48a9899e5 | textbox | Issue raised from site safety inspection:
00266ad7-198e-5f50-9a0d-d88b3176db8a | textbox | Actions:
83a2e6c8-2f2f-5b99-bf61-a7385018e545 | textbox | By who and when:
| checkpoint | Issues outstanding from previous briefings recorded with appropriate actions and date
33a0ad1f-dcbb-55a1-a22d-1f1d97156aaa | textbox | Issues outstanding from previous briefings:
e1664cce-39ae-5c17-8af4-d23e01d3cef5 | textbox | Actions:
28bfa81b-3880-59a8-821f-fd6dd0513136 | textbox | By who and when:
| checkpoint | 3. Employee-raised issues recorded with appropriate actions and date
691230f6-33a8-5ef5-bd76-de16c3dda469 | textbox | Employee-raised issues:
6819295b-ab43-54c8-ad3c-c2c31ab7e87e | textbox | Actions:
9b4efb57-5d97-5527-8eae-c16826e531da | textbox | By who and when:
| checkpoint | 4. Positive safe-action observations recorded with appropriate actions and date
257539e0-9170-5a78-a888-a9529a8ca217 | textbox | Positive safe-action observations:
2f72c5b8-6e3d-5c92-b044-f491dc33ab87 | textbox | Actions:
9cd0cb28-e4ff-5e8a-a99b-78db00e666e4 | textbox | By who and when:
| checkpoint | 5. Incidents or injuries recorded with appropriate actions and date
2875bae6-7ed3-5a07-996f-53f9205724c0 | textbox | Incidents or injuries:
278ae90e-d261-55df-af4e-bc7868cd2833 | textbox | Actions:
e9fe6b20-70a5-5be9-b54f-6965bc2da977 | textbox | By who and when:
| section | Job plans reviewed
| checkpoint | Job/Task plan(s) reviewed & Action(s) recorded below
d3d56c64-30d0-5140-8a1e-22e2c06c3540 | textbox | 1
2b690165-119e-5cf9-af03-3047434783cb | textbox | 2
b7508aab-73d2-5cbc-9752-b3332cab14d1 | textbox | 3
be311b3c-0665-5299-b7f0-e31362bf9c54 | textbox | 4
84c72f0d-9d91-5a53-a3c9-34f7128fbf20 | textbox | 5
7464b7ff-e4c6-502d-bf12-bc2b02ad9ea9 | textbox | 6
| section | Operational issues
| checkpoint | Operational Item(s) & Action(s) recorded below
56bb4fb4-f75b-5ee8-842d-3b83511e07ca | textbox | 1
7688e72b-c9fc-5ddd-bd79-ff62dd8c487d | textbox | 2
9ba99e61-199e-5718-bde5-167521d71ee5 | textbox | 3
d45e2bce-b582-5333-8976-efdd7a0e7f79 | textbox | 4
eefbda04-c338-502c-805b-b8ac6cf12b91 | textbox | 5
82795158-71a4-5b6c-af6e-4777bd04facd | textbox | 6
| section | Other business
| checkpoint | Other Business Item(s) & Action(s) recorded below
f4042683-0bfc-54ca-bb69-7e62497ff89d | textbox | 1
94219717-b8d8-5361-9c47-f50430da100d | textbox | 2
ddad65c2-7756-5f0c-aa5a-5bc5ad62f16a | textbox | 3
a8d544f9-d835-5222-919d-6a4c762c8630 | textbox | 4
| section | Attendees
| checkpoint | Add name and Photo of attendees (pass once all attendees are recorded)
| signoff | Send signoff request to all attendees
| section | Review by management
| checkpoint | Send to management to review?
| signoff | Reviewed and signed off by management
| checklist | Hot Water Pipe Pre Pressure Test |  | Hot Water Pipe Pre Pressure Test | 0 | 86597b68-2d2d-41c1-b98b-c10f1be6b015
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of pipe getting q.a (can be a photo of drawing)
| checkpoint | Hangers installed with correct spacings.
| checkpoint | Pipe sizes correct to up to date planes
| checkpoint | Valves installed were shown.
| checkpoint | Air vents installed were needed
| checkpoint | Drains installed were needed
| checkpoint | Valve sets as per up to date plans.
| checkpoint | Photos
| checkpoint | All joints complete
| checkpoint | Brazed or press fit
| checkpoint | Any pipe in walls provide photos
| checkpoint | Pipe labelled
| checkpoint | Site left tidy
| checklist | Insulation QA |  | Insulation QA | 0 | 2786ffb0-600b-45bb-94e5-964b4f8726f5
| section | Insulation First Fix QA
| checkpoint | QA requested, reviewed and approved from Trade
| signoff | Request QA
| checkpoint | Insulation details
5d43e116-49d2-5f4f-847c-b5ad6df392a9 | textbox | System type
ddd2a917-e5cd-535b-b4ce-a411ab71a917 | textbox | Insulation/ Cladding type
7ce5171a-3251-5ee9-a508-24110dc0f5b2 | textbox | R-Value
| checkpoint | Check that system to be insulated has been checked and tested
| checkpoint | Check specification/material type and work can start
| checkpoint | Insulation/cladding fitted to specification
| checkpoint | Check area is completed to specification and instructions
| checkpoint | Work completed and area left tidy
| signoff | Technical Alliance Approval
| checkpoint | Work completed and area left tidy
| signoff | Main Contractor Approval
| section | Insulation Second Fix QA
| checkpoint | QA requested, reviewed and approved from Trade
| signoff | Request QA
| checkpoint | Check for any areas that need completion for second fix
| checkpoint | Work completed and area left tidy
| signoff | Technical Alliance Approval
| checkpoint | Work completed and area left tidy
| signoff | Main Contractor Approval
| checkpoint | Site left tidy
| checklist | Kitchen Extract Duct |  | Kitchen Extract Duct | 0 | a950f0ae-280e-4b47-a03c-7812bc1031d6
| section | Details
| checkpoint | Drawing number
| checkpoint | Marked up drawing of duct getting Q.A. (Can be a photo of drawing)
| checkpoint | Duct is 18 gauge
| checkpoint | There are no terning veins installed in system
| checkpoint | No fire dampers installed
| checkpoint | Fire wrap were applicable
| checkpoint | All joints are tight and have duct clamps
| checkpoint | Cleaning access hatched provided
| checkpoint | Photos of duct
| checkpoint | Seismic as per design
| checkpoint | Good duct support
| checklist | Pre Commissioning Check |  | Pre Commissioning Check | 0 | b7399c54-5edf-406b-88c8-56d7bc1f0747
| checkpoint | Ductwork installation complete and QA records received
| checkpoint | Ductwork insulation complete and QA records received
| checkpoint | Ductwork fire rating complete and QA records received
| checkpoint | Pipework installation complete and QA records received
| checkpoint | Pipework insulation complete and QA records received
| checkpoint | Electrical installation complete and QA records received
| checkpoint | Controls installation complete and QA records received
| checkpoint | Latest drawings available
| checkpoint | Latest equipment technical schedules available
| checkpoint | Permanent power available
| checkpoint | Temporary filter media installed
| checkpoint | Permanent make-up water available
| checkpoint | Attach test sheets to this document
| checkpoint | Building works complete and areas cleaned
| signoff | Check Completed
| checklist | Pre Start |  | Pre Start | 0 | 985fcdb9-ba78-41f2-bb04-e4e98ff79549
| checkpoint | Is building advanced enough for first fix to start and achieve proper workflow. - Provide Photos
| checkpoint | Is building tidy enough. - Provide Photos
| checkpoint | Organise access.(Ladders,scaffold)
| checkpoint | Organise consumables.
| checkpoint | Organise material needed.
| checkpoint | Check drawings are approved.
| checkpoint | Site box required.
| checkpoint | Ladders?
| checkpoint | Organise other company tools that are needed.
| checkpoint | Site left tidy
| checklist | Pre Start Documentation |  | Pre Start Documentation | 0 | 98f567b1-fda5-4f3f-92b6-7f81ad4cc8c3
| checkpoint | SSSP
| checkpoint | Construction drawings
| checkpoint | Technical submissions
| checkpoint | Subbies signed up
| checklist | Pre start stage |  | Pre start stage | 0 | c9b4361f-36cd-4381-8770-f0a73da91324
| section | Drawings
| checkpoint | Drawings saved in job
| checkpoint | Unit/plant selections labelled on drawings
| checkpoint | AC pipe sizes shown on drawings
| checkpoint | Ducting sizes shown on drawings
| checkpoint | Penetrations to wall and roof are shown (with sizes)
| checkpoint | Condensate connection points marked on drawings
| checkpoint | Photos
| section | Purchasing
| checkpoint | All plant has been ordered for first fix
| checkpoint | All plant has been ordered for second fix (check Programme)
| checkpoint | Photos
| section | Health and Safety
| checkpoint | SSSP has been produced
| checkpoint | SSSP has been dropped to site office
| checklist | Pre Wire |  | Pre Wire | 0 | 869cbce8-8974-43db-ac7f-a25261bad986
| checkpoint | All terminations in the right place
| checkpoint | Correct cable run
| checkpoint | Correct separation from cables
| checkpoint | All cables run and label.
| checkpoint | Site left tidy
| checklist | Pressure Test Refrigerant |  | Pressure Test Refrigerant | 0 | 9a8fecc1-ac12-4472-b263-994747027211
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of pipe getting q.a (can be a photo of drawing) or reference to the system getting tested depending on if it is a section or a hole system.
| checkpoint | Pressure at start
| checkpoint | Pressure at end
| checkpoint | Photo at start of test
| checkpoint | Hold for 24 hours
| checkpoint | Photo at end of test.
| checkpoint | Site left tidy
| checklist | Pressure Test Water Pipe |  | Pressure Test Water Pipe | 0 | 6bfa7903-f6d3-4042-83e5-2dfd99e635a4
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of pipe getting q.a (can be a photo of drawing) or reference to the system getting tested depending on if it is a section or a hole system.
| checkpoint | Test to 1.5 working pressure or if specified otherwise buy supplier which is the authority on pressure test or on job spec.
| checkpoint | Pressure at start
| checkpoint | Pressure at end
| checkpoint | Photo at start of test
| checkpoint | Hold for 24 hours (unless specified)
| checkpoint | Photo at end of test.
| checkpoint | Note: there maybe a slight drop caused by atmospheric factors such as temperature. If so Head supervisor to confirm if this is a pass or not. (Test my need to be for longer)
| checkpoint | Site left tidy
| checklist | QA - Fit Off |  | QA - Fit Off | 0 | 22d433c9-6692-475a-9e42-162a65c8e6b6
| checkpoint | Area ready to start work
| checkpoint | Indoor unit fit off and installed correctly
| checkpoint | Grilles cut out completed
| checkpoint | Grilles fit off and installed correctly & B/fly dampers left open
| checkpoint | Access panels installed
| checkpoint | All drains fit off and tested
| checkpoint | Condenser unit fit off, pipes and wires sealed and capped where required
| checkpoint | Condenser labels Installed
| checkpoint | Builders works complete
| checkpoint | Ensure all rubbish and materials have been picked up and room is clean
| checkpoint | Site left tidy
| checklist | QA - Rough In |  | QA - Rough In | 0 | 9ee33d3b-5814-4b39-a253-afe7805163e3
| checkpoint | Area ready to start work
| checkpoint | Ducted AC unit installed c/w isolation mounts & filters
| checkpoint | Living & Bedroom cushion boxes & flex duct installed
| checkpoint | Access panels marked on floor
| checkpoint | Refrigeration pipes roughed in and installed to common riser
| checkpoint | Drain pipes roughed in and Terminated internal tundish
| checkpoint | Wall penetration Fire caulking completed and fire penetration labelled / documented.
| checkpoint | Pressure testing of Refrigeration pipework complete
| checkpoint | Site left tidy
| checklist | Quarterly Maintenance Checklist |  | Quarterly Maintenance Checklist | 3 | 089558c9-c1b3-4920-828d-5b68dff97a8b
| section | Job Details
| checkpoint-no-value | Job Details
00796531-9203-565a-8491-c9fbd93eb3a6 | date | Date:
b3aee00e-15a5-59f3-aa02-299dcff33069 | textbox | Client Name:
7b949008-8a1c-5c98-8a78-3c5c8d863fba | textbox | Address:
0e809424-1b4a-5a4e-a49b-4adeb978c1d0 | textbox | General Notes:
| section | Indoor Units
| checkpoint | Check unit operation
| checkpoint | Check and clean filters
| checkpoint | Check indoor air handler and report if cleaning is required
| checkpoint | Check condensate drain line and test with 1 litre of water to ensure condensate is flowing freely
| checkpoint | Check electrical wiring including thermostats and adjust where necessary.
271aa4bf-1efa-5817-a5bc-be275a2dd0b6 | note | Check pulleys and fan belts
| checkpoint | Check flexible ducting for air leaks, retape and resupport where necessary.
ae6dde96-3994-5d8d-ace0-6bba22d3ca46 | note | Check all supply and return air grilles
| checkpoint | Check if ducted system is fitted with passive fresh air
| section | Fans
| checkpoint | Check fan current draw and damper operation
| checkpoint | Check and clean all grilles and filters
| checkpoint | Check sheet metal and flexible ducting for air leaks
| checkpoint | Check for excessive noise and vibration
| section | Outdoor Units
| checkpoint | Check and test stop and start sequence
| checkpoint | Check condenser coils for obstruction
| checkpoint | Check pipework and units for vibration
| checkpoint | Check external pipework for evidence of any leaks
| checkpoint | Check all electrical terminals for tightness
| checkpoint | Check contactors, relays and compressor amp draw
| checkpoint | Check condenser fan motors
| checkpoint | Check refrigerant levels
| checkpoint | Check all covers are secure
| section | Timeclock
| checkpoint | Check timeclock is displaying the correct time
| checkpoint | Check the "on-off" time settings making sure equipment is operating accoridngly and correct for customer's requirements
| section | Summary
| checkpoint | Comments of further work required
| signoff | Signoff by Customer & Maintenance Technician
| checklist | Refrigerant Pipe Systems |  | Refrigerant Pipe Systems | 0 | a8271bf1-b3d5-435d-8b10-6f842d419439
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of pipe getting q.a (can be a photo of drawing)
| checkpoint | Hangers installed with correct spacings.
| checkpoint | Pipe sizes correct to up to date planes
| checkpoint | Valves installed were shown.
| checkpoint | Photos
| checkpoint | Pipe purged when brazed
| checkpoint | All brazing complete
| checkpoint | Any pipe in walls provide photos
| checkpoint | Pipe labelled
| checkpoint | Site left tidy
| checklist | Second Fix Grills |  | Second Fix Grills | 0 | aaaa096e-f056-4a9e-9d81-7154de1d1666
| checkpoint | Drawing number
| checkpoint | Attach highlighted drawing of ceiling getting q.a if only a portion.
| checkpoint | Grills installed to correct location.
| checkpoint | Grills installed as per up to date schedule.
| checkpoint | Site left tidy
| checklist | Split System - Ducted, Above Ceiling |  | Split System - Ducted, Above Ceiling | 0 | 2e13fabb-404b-4142-91f4-8912b50386dd
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of unit getting q.a (can be a photo of drawing)
| checkpoint | Pressure tested.
| checkpoint | Vacuumed to supplier’s requirement.( Please note vacuum)
| checkpoint | ODU fixed in place.
| checkpoint | Photo of indoor and outdoor unit
| checkpoint | If drain pump is provided test this.
| checkpoint | In-between cable run
| checkpoint | Wall control if required
| checkpoint | Any pipe in walls provide photos
| checkpoint | Commissioned and checked all operations.
| checkpoint | Plenums installed as per drawing.
| checkpoint | Plenums Sealed.
| checkpoint | Spigots open
| checkpoint | Spigots sealed with Plastic wrap.
| checkpoint | Seismic to design.
| checkpoint | Condensate drain installed correctly.
| checkpoint | Condensate checked for flow with water.
| checkpoint | 2m of insulation on condensate line after unit. Check spec to confirm if more is needed.
| checkpoint | Site left tidy
| checklist | Split System 1st Fix (Ducted) |  | Split System 1st Fix (Ducted) | 0 | 16194998-d407-4288-a078-432c88357dce
| section | Details
| checkpoint | Check location of indoor and out door unit are as per plan or confirmation from client
| checkpoint | Indoor installed with good support (photo)
| checkpoint | Plenums installed and sealed (photo)
| checkpoint | Flexibles installed correctly with no sharp bends and good connections to plenuims and grill boots
| checkpoint | All grill boots installed and in correct location.
| checkpoint | Drains terminated to indoor
| checkpoint | Fridge pipe terminated to indoor
| checkpoint | Pressure test fridge pipe if applicable
| checkpoint | Check location of were pipes come out of the wall
| checkpoint | Insulation to fridge pipe complete, photo
| checkpoint | Drains complete and tested with photo
| checkpoint | Fridge Pipe instilled with photos
| checkpoint | In-between run. Photo
| checkpoint | Wall control cable run. Photo
| checkpoint | Site left clean
| checklist | Split System 1st Fix (High wall, Casset, Under ceiling, Floor mounted) |  | Split System 1st Fix (High wall, Casset, Under ceiling, Floor mounted) | 0 | f395a9a2-9804-49ce-aaa8-1979ba08b035
| section | Details
| checkpoint | Check location of indoor and out door unit are as per plan or confirmation from client
| checkpoint | Check location of were pipes come out of the walls.
| checkpoint | Insulation to fridge pipe complete, photo
| checkpoint | Drains complete and tested with photo
| checkpoint | Fridge Pipe instilled with photos
| checkpoint | In-between run. Photo
| checkpoint | Wall control cable run. Photo
| checkpoint | Site left clean
| checklist | Split System 2nd Fix (Ducted) |  | Split System 2nd Fix (Ducted) | 0 | 3e048b60-e3f9-426a-86be-c3e72911b30e
| section | Details
| checkpoint | Terminations complete
| checkpoint | Grills installed
| checkpoint | Drain tested
| checkpoint | Capping installed photo
| checkpoint | Pressure test of fridge pipe. Photo
| checkpoint | Vacuumed to supplier requirements
| checkpoint | Checking of operation
| checkpoint | Photos of finished install
| checkpoint | Site left clean
| checklist | Split System 2nd Fix (High wall, Casset, Under ceiling, Floor mounted) |  | Split System 2nd Fix (High wall, Casset, Under ceiling, Floor mounted) | 0 | 747532cc-3b40-4368-9fc8-1c8da91bd3fd
| section | Details
| checkpoint | Terminations complete
| checkpoint | Drain tested
| checkpoint | Capping installed photo
| checkpoint | Pressure test of fridge pipe. Photo
| checkpoint | Vacumed to supplier requirements
| checkpoint | Checking of operation.
| checkpoint | Photos of finished install
| checkpoint | Site left clean
| checklist | Split Systems - High wall, Casset and Ceiling |  | Split Systems - High wall, Casset and Ceiling | 0 | 4a881a03-c973-4a0d-b9ac-8e5063e04bb8
| checkpoint | Drawing number
| checkpoint | attach highlighted drawing of unit getting q.a (can be a photo of drawing)
| checkpoint | Pressure tested.
| checkpoint | Drain checked with water.
| checkpoint | Vacuumed to supplier’s requirement.( Please note vacuum)
| checkpoint | ODU fixed in place.
| checkpoint | Photo of indoor and outdoor unit
| checkpoint | If drain pump is provided test this.
| checkpoint | In-between cable run
| checkpoint | Wall control if required
| checkpoint | Any pipe in walls provide photos
| checkpoint | Extra gas charge
| checkpoint | Commissioned and checked all operations.
| checkpoint | Site left tidy
| checklist | Variation Contract |  | Variation Contract - | 0 | fc4a7216-db1e-47c0-aad9-aec0f82f1416
| checkpoint | Job Details
02887922-3ae0-5e93-99c9-8919fc9cc5ff | textbox | Details of Work (Inc. Location):
d0e7f9f8-49e4-5c71-b78e-2a83de2dc0cc | textbox | Client:
6e771cb7-81bd-578b-95ab-a1fd746f023f | textbox | Reason for Variation:
d7e934af-03c0-5abe-a602-af4399eb6e89 | textbox | Project:
5ec5b8b8-fd9f-57f8-a2b8-8de2d76eeb82 | textbox | Job No:
aacf711d-8dae-52cf-8bdb-bbde9e6dc5b1 | textbox | Hours:
951e24f9-f45a-5bba-a3e8-360c3f3b3ff7 | textbox | Site Instruction No:
21f96f8b-5d38-52e7-b6db-80078fb48662 | textbox | Materials Equipment:
1b788ae7-2c49-54fd-931e-fd3fb465fb05 | textbox | Agreed Value:
| checkpoint | Work Details:
bd1d8149-784b-5aba-8ebd-04097625f4b5 | textbox | Details of Work (Inc. Location):
678d0c38-35d3-50be-a251-2ea4224c066c | textbox | Name:
225154f0-b0f1-58a6-b16e-e5ab23657cb7 | textbox | Reason for Variation:
cb516057-3a93-53ef-842f-573a90fb95d9 | textbox | Hours:
534f9c0a-20fc-507f-8a46-919e12f8241f | textbox | Materials Equipment:
b5a4d581-0cd4-5450-97b5-0dfa2f3f8a29 | textbox | Agreed Value:
| checkpoint | Foreman Sign Off
66d159cd-25b4-5470-a796-98959d81d3d1 | textbox | Name:
5092142c-347a-5d5c-874b-11c10996e448 | textbox | Name:
| checkpoint | Project Manager Sign Off
40b5321c-963d-5f24-907b-f0eb214b598f | textbox | Name:
0fd3dd9f-17d1-5dda-b9de-3d1243803cc7 | textbox | Name:
| checkpoint | Signature of Authorising Officer
a89079c9-77ff-59f8-8713-bdd4e6d69146 | textbox | Name: