## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Kitchen Extract Duct |  | Kitchen Extract Duct |  | a950f0ae-280e-4b47-a03c-7812bc1031d6
| section | Details
| checkpoint | Drawing number
| checkpoint | Marked up drawing of duct getting Q.A. (Can be a photo of drawing)
| checkpoint | Duct is 18 gauge
| checkpoint | There are no terning veins installed in system
| checkpoint | No fire dampers installed
| checkpoint | Fire wrap were applicable
| checkpoint | All joints are tight and have duct clamps
| checkpoint | Cleaning access hatched provided
| checkpoint | Photos of duct
| checkpoint | Seismic as per design
| checkpoint | Good duct support
| checklist | Split System 1st Fix (High wall, Casset, Under ceiling, Floor mounted) |  | Split System 1st Fix (High wall, Casset, Under ceiling, Floor mounted) |  | f395a9a2-9804-49ce-aaa8-1979ba08b035
| section | Details
| checkpoint | Check location of indoor and out door unit are as per plan or confirmation from client
| checkpoint | Check location of were pipes come out of the walls.
| checkpoint | Insulation to fridge pipe complete, photo
| checkpoint | Drains complete and tested with photo
| checkpoint | Fridge Pipe instilled with photos
| checkpoint | In-between run. Photo
| checkpoint | Wall control cable run. Photo
| checkpoint | Site left clean
| checklist | Split System 2nd Fix (High wall, Casset, Under ceiling, Floor mounted) |  | Split System 2nd Fix (High wall, Casset, Under ceiling, Floor mounted) |  | 747532cc-3b40-4368-9fc8-1c8da91bd3fd
| section | Details
| checkpoint | Terminations complete
| checkpoint | Drain tested
| checkpoint | Capping installed photo
| checkpoint | Pressure test of fridge pipe. Photo
| checkpoint | Vacumed to supplier requirements
| checkpoint | Checking of operation.
| checkpoint | Photos of finished install
| checkpoint | Site left clean
| checklist | Split System 1st Fix (Ducted) |  | Split System 1st Fix (Ducted) |  | 16194998-d407-4288-a078-432c88357dce
| section | Details
| checkpoint | Check location of indoor and out door unit are as per plan or confirmation from client
| checkpoint | Indoor installed with good support (photo)
| checkpoint | Plenums installed and sealed (photo)
| checkpoint | Flexibles installed correctly with no sharp bends and good connections to plenuims and grill boots
| checkpoint | All grill boots installed and in correct location.
| checkpoint | Drains terminated to indoor
| checkpoint | Fridge pipe terminated to indoor
| checkpoint | Pressure test fridge pipe if applicable
| checkpoint | Check location of were pipes come out of the wall
| checkpoint | Insulation to fridge pipe complete, photo
| checkpoint | Drains complete and tested with photo
| checkpoint | Fridge Pipe instilled with photos
| checkpoint | In-between run. Photo
| checkpoint | Wall control cable run. Photo
| checkpoint | Site left clean
| checklist | Split System 2nd Fix (Ducted) |  | Split System 2nd Fix (Ducted) |  | 3e048b60-e3f9-426a-86be-c3e72911b30e
| section | Details
| checkpoint | Terminations complete
| checkpoint | Grills installed
| checkpoint | Drain tested
| checkpoint | Capping installed photo
| checkpoint | Pressure test of fridge pipe. Photo
| checkpoint | Vacuumed to supplier requirements
| checkpoint | Checking of operation
| checkpoint | Photos of finished install
| checkpoint | Site left clean