## Breakdown
Kings Eectrical - 045 Kevin Hickman (Riccarton Park)
Stage 401 - Fire Kiosk
Valve Room
|  |  |  | Pre-populate | S - S - Electrical
Compliance Documents
|  | Stage 04 - Fire Kiosk | Pre-populate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist | S - S - Electrical
section | First Fix
checkpoint | Handover Accepted/Nogs Installed and area clean and tidy before starting
checkpoint | Check all drawings, plan symbols are identified and wired for, raise any anomalies
checkpoint | Check wall and ceiling outlets and fitting positions against Architectural/ Electrical drawings and acceptable
checkpoint | Check for any purchaser variations/ client extras
checkpoint | Check all power & light feeds present and acceptable
checkpoint | Check loop wires insatlled and acceptable
checkpoint | All joinery plans are followed and correct position of outlets installed and acceptable
checkpoint | Flush boxes straight and level and acceptable
checkpoint | Fire rated flush boxes where required + fire pads installed and acceptable
checkpoint | Lights are marked out on plans or floor ready for cut out
checkpoint | Electrical First Fix completed and acceptable and area clean and tidy for next trade
section | Second Fix
checkpoint | All cover plates in place & fitted correctly and striaght
checkpoint | All light fittings tight & secure and acceptable
checkpoint | All cables are tied up
checkpoint | Switch board fit off is completed and acceptable
checkpoint | Test sheet for insulation Resistance are completed and acceptable
checkpoint | Fixtures level & in place and acceptable
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff