## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | dba03565-ed03-4119-a7b6-790d38f3b13d |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 06abeb28-3098-4939-abba-43daf272aa19
checkpoint-status | 84ca1771-5083-4d64-a65e-cd9127dfe512 |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 1a785027-03ee-546b-a8de-a65a741a96ea | DataPoint is missing 'button' values | button | LBP Memorandum/ Record of works filled out, signed and attached
button | 7538fb00-8f06-5f1c-a98f-7d989fcc245d | DataPoint is missing 'button' values | button | Any Additional Compliance Documentation - Completed and Attached
label | b7835280-b55a-56f9-b743-210a581415ed |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 842fb68e-3f88-4c48-8253-df3bc3507629 |  | signoff | Request Signoff
checklist-flat | 53c0f536-5010-47cd-841e-5256503ab9e4 |  | checklist | Job Details |  |  |  |  | Yes | SYS - Job Details Checklist | 1af4ddc2-5469-4248-95e6-33d335b1dd0a
checkpoint-status | d7e905b6-7403-4c43-b19f-e5eec37719b0 |  | checkpoint | Site Information Recorded
label | f9dd9c5a-63f3-56ff-a722-3cb3795f4aa6 |  | note | Site Address - Riccarton Park - 25 Steadman Rd, Riccarton
label | dcbab177-4fb6-548e-a797-0bdabed581e7 |  | note | Main Contractor Details - Ryman Healthcare
text | bef64c69-f491-53b6-91bf-1946c2fb9673 |  | textbox | Project Managers Details - Andrew Inch - andrew.inch@rymanhealthcare.com
text | 47c4675e-9fc9-5959-882a-080e4003ac1a |  | textbox | Site Manager Details - Martin Collins - martin.collins@rymanhealthcare.com
label | f8d1fe83-596a-5f16-bae8-fcdb9bab3cf3 |  | note | QA Admin Details - Leshani Gunawardana - Leshani.Gunawardana@rymanhealthcare.com
checkpoint-status | 17dc874d-32e2-4c0b-9594-69a383a8f1ab |  | checkpoint | Scope of Works Attached
checkpoint-status | 7669fba9-8a5f-47e6-b3d4-caa3ec086dcf |  | checkpoint | Additional Pre Start Docs
checkpoint-status | e011ff45-f0f6-49c2-97d0-165119789569 |  | checkpoint | All relevant job details entered above
label | c5c437c0-28e1-55df-891e-1f20c5a24de6 |  | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or "N/A"
checklist-sectioned | 46b037be-5032-40e7-b5fe-1fc8c2cde8fb |  | checklist | POST - S - Data Installation |  |  |  |  | Yes | POST - S - Data Installation | 225c0c78-259c-48c7-81f0-83b58c340898
checkpoint-group | b0a0e947-483e-4c02-acb8-a188a52bde0b |  | section | Pre-wire
checkpoint-status | 02854063-0dd0-499c-b8b6-74cd77e6b02c |  | checkpoint | Area is left clean and tidy and approval to start work is obtained
checkpoint-status | 11eeb459-ef2d-4222-abe6-a7550878f14f |  | checkpoint | Internal cabling complete
checkpoint-status | 6152cbd5-eff7-450e-9229-9c3c2c6cdb7b |  | checkpoint | Main cabling complete (photos attached)
checkpoint-status | cd9cf2b7-7d93-486c-80ad-e1773dd0d8a6 |  | checkpoint | Flush boxes installed
holdpoint | 05f9ebc0-6859-4cae-93f8-1a0d282ff93c |  | signoff | Request sign off
checkpoint-group | db5cb415-56b0-4cae-93e6-d8fc9e729b02 |  | section | Termination & Testing
checkpoint-status | 35e268d5-6dba-4a93-a102-76d32453d897 |  | checkpoint | Install DB
checkpoint-status | c764e8b1-c740-42d6-ace5-6d086d749a48 |  | checkpoint | Fit off DB (photos attached)
checkpoint-status | 23a3ad85-54f9-4bbb-8dd8-af53dbfecbec |  | checkpoint | LAN test internals
holdpoint | 769bf138-c265-445f-a8c1-72da9cd88e55 |  | signoff | Request sign off
checkpoint-group | 841dbc69-9749-467e-9ec4-e1301536b9ce |  | section | Fit off
checkpoint-status | 14a8ab26-8e4a-47e9-9a5a-a172774866a4 |  | checkpoint | Area is left clean and tidy and approved to start work is obtained
checkpoint-status | 86c6deab-5f5e-42ce-b732-81edddcd0694 |  | checkpoint | TV/DATA fit off (photos attached)
checkpoint-status | a500d37b-3f49-4f0a-ac90-fabfe21624e2 |  | checkpoint | Nurse call fit off (photos attached)
checkpoint-status | ea3e7b57-f751-4082-a382-de7a5d06723b |  | checkpoint | Programming and commissioning
holdpoint | cfa33435-65f9-4a35-8e14-2d28a7c79ee5 |  | signoff | Request sign off
checklist-sectioned | 84470564-b680-41f9-b5e5-a7f79143cfed |  | checklist | QA - Common Area Sign Off |  |  |  |  | Yes | QA - Common Area Sign Off | 3170e45a-dfcf-469f-adc7-2a1159692ce2
checkpoint-group | ff7a03c6-87ea-432e-aeff-9c1ada952d18 |  | section | Pre wire
checkpoint-status | 53f2daf5-b3eb-412e-8efe-189386fae54a |  | checkpoint | Cabling complete
checkpoint-status | 7d1a0a72-68aa-40a6-a9aa-929d021fa857 |  | checkpoint | Flush box fire box installed (photos attached of fire box)
checkpoint-status | 71b9ee82-4320-4c84-9177-8836df6baffc |  | checkpoint | Attach photos of fire penetrations
checkpoint-group | 23a243d8-0458-4cbf-ab3b-293def391c72 |  | section | Terminated and tested
checkpoint-status | 3ecc7c4c-394a-474c-80d5-411823564357 |  | checkpoint | LAN test complete
holdpoint | 19fa2b71-63ef-4f75-9a5b-e6d0a9e3fbad |  | signoff | Request sign off
checkpoint-group | a8fde940-2ff3-489c-80d2-9eb4c8b3a24d |  | section | Fit off
checkpoint-status | dbe207bb-a333-4402-8913-d62192f0c208 |  | checkpoint | Nurse call fit off
checkpoint-status | 95258526-71c1-431a-9369-a4bc37647c3d |  | checkpoint | Camera fit off
checkpoint-status | 448074a3-6f06-49e2-9bcc-5c2e6bd476dc |  | checkpoint | Intercom fit off
checkpoint-status | a1ba6a62-b452-4963-9142-3ff47c45343f |  | checkpoint | AC-mags fit off
checkpoint-status | 56af5594-50d6-4176-9046-d78083785159 |  | checkpoint | AC fit off
holdpoint | d62e5ee8-5cb8-46df-a92c-5cb6fac7bcf0 |  | signoff | Request sign off
checklist-flat | bc002fcb-ecb4-4a25-b25c-38481f7d0ccb |  | checklist | POST - S - Second Fix - Nurse Call, Data & Communications & Security |  |  |  |  | Yes | POST - S - Second Fix - Nurse Call, Data & Communications & Security | 4860215d-b19d-46aa-bd47-9a12d35522b5
checkpoint-status | befddf8e-0053-4391-834a-c8dc70a0c236 |  | checkpoint | LAN test completed and acceptable
checkpoint-status | 98e19a68-efb5-4255-b390-7a8c77e8a850 |  | checkpoint | MATV terminated and acceptable
checkpoint-status | 2864bd88-b4c2-4e8c-907d-2b9da3ecb289 |  | checkpoint | Distribution Box terminated and acceptable
checkpoint-status | 241be2db-3350-4929-8529-e0788c863a48 |  | checkpoint | Nurse Call faceplates fitted off and acceptable
checkpoint-status | dd2c0f9e-913a-4bf7-9974-b2207435d306 |  | checkpoint | MATV/Data faceplates fitted off and acceptable
checkpoint-status | 30dae497-8f73-4863-8cd8-615be1b22b63 |  | checkpoint | Camera faceplates fitted off and acceptable
checkpoint-status | 73f21b48-cd4a-49ed-beff-93256ab08577 |  | checkpoint | Intercom faceplates fitted off and acceptable
checkpoint-status | 8982e624-0cf8-4b2d-8241-f8eead7fb3ce |  | checkpoint | AC-Mags faceplates fitted off and acceptable
checkpoint-status | 540539ae-3012-4b9b-8ffa-c046eb16ec16 |  | checkpoint | AC-Plates fitted off and acceptable
checkpoint-status | db740b4f-610f-4dd8-929e-2df9889c1a0d |  | checkpoint | Second Fix complete and acceptable and area clean and tidy for next trade
checklist-flat | 8a1dda7a-f1c8-4396-b4a9-b404cb5dd6a0 |  | checklist | QA - Floor Commissioning |  |  |  |  | Yes | QA - Floor Commissioning | 516293e9-3700-4453-bfb1-612116e7f069
checkpoint-status | 4457bd40-992e-4a64-bb20-86313312ce4b |  | checkpoint | Tone cables (attach photos)
checkpoint-status | 117b7580-acc6-4f10-8414-cbffbe16ad6d |  | checkpoint | Separate cables (attach photos)
checkpoint-status | 10f1ef19-5114-42af-b0a5-cb1f544148dd |  | checkpoint | Cable riser (attach photos)
holdpoint | 2b59a350-5baf-4545-82ca-46a42efecdf3 |  | signoff | Request sign off
checklist-sectioned | a6b6deaf-e17d-47b3-9f32-2b945d9b6145 |  | checklist | QA - Apartment Sign Off |  |  |  |  | Yes | QA - Apartment Sign Off | 8ae94b85-1dcd-4f64-a2b7-444cb17cdd4b
checkpoint-group | 12576376-ed30-40fe-bf93-897233843768 |  | section | Pre wire
checkpoint-status | 767fbb8f-713a-42da-9b7d-2aa4c3cb1ed1 |  | checkpoint | Internal cabling complete
checkpoint-status | 9fa56f2b-f95e-48f0-86b0-d38bc62111b1 |  | checkpoint | Main cabling complete (photos attached)
checkpoint-status | 50e79ca7-ba35-4438-8c93-8cbc4dddd8a2 |  | checkpoint | Flush boxes installed
checkpoint-status | 6db5f530-3ed0-4f93-83f9-7cd4756fbec8 |  | checkpoint | Fire boxes installed (photos attached)
checkpoint-status | dec85e88-1831-4c8b-83a8-ce32780a66c4 |  | checkpoint | Fire walls point of entry (photos attached)
holdpoint | 2ebed56c-1e27-472d-8ed7-517cf0d845d2 |  | signoff | Request sign off
checkpoint-group | e70cb496-a9f6-4c16-bd40-e899a7db6406 |  | section | Termination and testing
checkpoint-status | 43e5838a-0404-4d92-8a96-32f2f770c047 |  | checkpoint | Install DB
checkpoint-status | c8508af6-d7e3-4f89-81fb-a88303f9bf7f |  | checkpoint | Fit off DB (photo attached)
checkpoint-status | 6a61f6af-84ab-439a-9f98-137a74256f13 |  | checkpoint | LAN test internals (add signature)
holdpoint | 652a6867-7aa1-42c9-93fd-d397dc1cf841 |  | signoff | Request sign off
checkpoint-group | a099a5b6-4f7c-4056-8a2a-a0289422064a |  | section | Fit off
checkpoint-status | e08373ae-8ebc-4b88-8784-eb800f82decf |  | checkpoint | TV/DATA fit off (photos attached)
checkpoint-status | 6fc3e233-7b09-435d-a708-5cceb2efaa4d |  | checkpoint | Nurse call fit off (photos attached)
holdpoint | 42cec5dd-8794-45ca-ad13-a9d7fef66620 |  | signoff | Request sign off
checklist-flat | 3ad73f6f-a2b4-42f4-ba83-baf6fa38a829 |  | checklist | Completion Documents |  |  |  |  | Yes | SYS - Compliance / Completion Documentation | 8d931fa0-f378-4a71-9dfa-0c9a088849fe
checkpoint-status | 39fc234c-3931-4a7c-a3cb-2aee6545ca9c |  | checkpoint | All relevant Compliance Documentation completed and attached below
button | 3034ad46-d4a3-5e4d-b615-02474fbc0cd3 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | Yes, N/A
button | 64720b0e-e405-5428-96e4-30f7b59bdbd1 |  | button | As-built plans attached | Yes, N/A
button | 4c65252f-c68b-5d1f-bee9-0ea04594da26 |  | button | Any Additional Compliance Documentation - completed and attached | Yes, N/A
label | f5b70aa0-672b-5e03-86c5-bc781e67be05 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 22858ee7-91a1-4d1c-81a1-7dc37942451e |  | signoff | Request Signoff
checklist-sectioned | e4988e25-4c2f-4ac3-93cc-cd4e5cc935e7 |  | checklist | TH |  |  |  |  | Yes | QA - Townhouse Unit Installation | 970c04b9-6a76-4bc4-a2c9-d70d6a920547
checkpoint-group | 3cb540be-7721-40b9-a161-86a5374a876c |  | section | Pre-wire
checkpoint-status | 8597dcf5-1734-4757-8561-e80d1073ffab |  | checkpoint | Area is left clean and tidy and approval to start work is obtained
checkpoint-status | 6f64ae23-ceea-4eba-a4c5-704f58d2faa8 |  | checkpoint | Internal cabling complete
checkpoint-status | a3fce6e9-2d6e-4570-9eb2-6b491280f97a |  | checkpoint | Main cabling complete (photos attached)
checkpoint-status | 97740618-7ba3-4351-8e08-2338438a068a |  | checkpoint | Flush boxes installed
holdpoint | f24bdcee-2af4-4410-bccf-7434d9479d8e |  | signoff | Request sign off
checkpoint-group | 3c0ef49b-386f-421b-81e9-d6647962185c |  | section | Termination & Testing
checkpoint-status | 247ad636-64ee-45bc-a4bf-e38b0f2ce025 |  | checkpoint | Install DB
checkpoint-status | 5794722d-b25f-4e65-b70a-c860d2aa1cfe |  | checkpoint | Fit off DB (photos attached)
checkpoint-status | cbca486e-da23-447c-a19e-4542d13e8544 |  | checkpoint | LAN test internals
holdpoint | 55644acd-ce18-4d02-88f0-83b8f1ab2549 |  | signoff | Request sign off
checkpoint-group | a80c42a5-5040-41fd-ab92-0d5290f648f4 |  | section | Fit off
checkpoint-status | 7c827723-fce9-462d-8e4e-1f1b165ac6d7 |  | checkpoint | Area is left clean and tidy and approved to start work is obtained
checkpoint-status | a4134b44-71db-46c7-9f22-b672ab33ff21 |  | checkpoint | TV/DATA fit off (photos attached)
checkpoint-status | b092f795-264a-48b4-ba2a-0d20a1668277 |  | checkpoint | Nurse call fit off (photos attached)
holdpoint | eeffcdbd-1072-4d67-acfa-e24918405bc4 |  | signoff | Request sign off
checklist-flat | cb824c2c-0e9f-41e6-984b-477af5b38622 |  | checklist | PRE - S - First Fix - Nurse Call, Data & Communications & Security |  |  |  |  | Yes | PRE - S - First Fix - Nurse Call, Data & Communications & Security | b902cdaf-2283-43fc-a171-77126389d5ad
checkpoint-status | b8edcf42-a50d-4f57-83a4-b369d63b3ca3 |  | checkpoint | Framework available and acceptable
checkpoint-status | c9c59f68-c4a1-4a24-a160-0ab1458cca06 |  | checkpoint | Cabling completed and acceptable
checkpoint-status | 0a0de5c2-3a36-46b8-9aaf-4c461f917a9a |  | checkpoint | Nogs installed and acceptable
checkpoint-status | 0fbd20f5-1f72-4c63-a4c0-c4afcefcb855 |  | checkpoint | Flush/Fire boxes installed and acceptable
checkpoint-status | be06571d-05fb-47fe-ac80-78fcec4908fb |  | checkpoint | Fire Baffles installed and acceptable
checkpoint-status | 9e44625a-a702-4693-9a3e-511412e38cb6 |  | checkpoint | Fire penetrations completed, sealed and acceptable
checkpoint-status | e2977920-ad6e-4ca6-94f5-29c24f494a34 |  | checkpoint | First Fix complete and acceptable and area clean and tidy for next trade
checklist-flat | baceea71-98a4-4019-a7cb-56ad4f08d2d9 |  | checklist | Building Commissioning |  |  |  |  | Yes | QA - Building Commissioning | f2bcf6d2-c1ee-4420-a385-3527d6534451
checkpoint-status | a94af5aa-f32d-4f2d-9a7e-ad01eb442e4e |  | checkpoint | Separate cables
checkpoint-status | 18d0c2ad-2c65-4cca-bfbc-d68ee223aea8 |  | checkpoint | Separate security cables
checkpoint-status | 9eb8e3c1-6612-4e60-bf78-d5c54e83181e |  | checkpoint | Complete cable riser
checkpoint-status | 9db6add5-805c-4ad5-b08e-a73dc1ce8dc3 |  | checkpoint | Build patch panels (photos attached)
checkpoint-status | 7380ce4f-b2c4-41b4-ae8e-dd1983249716 |  | checkpoint | Build Nurce call system (photos attached)
checkpoint-status | ddd71ab8-0bc6-4302-a09c-2f79b54c33a7 |  | checkpoint | Build MATV system (photos attached)
checkpoint-status | 96edf86c-7ebf-4b84-9901-4f9ae445ed1d |  | checkpoint | Build security panels (photos attached)
checkpoint-status | 138ea7ab-cf9c-4acd-9deb-44cf771a4f65 |  | checkpoint | Program nurse call system
checkpoint-status | a85cd3fc-d19e-4efc-8da3-5539a01ee689 |  | checkpoint | Commission nurse call system (photos attached)
checkpoint-status | 91afd567-e759-41b4-a3b1-a7816f42c348 |  | checkpoint | Commission security system (photos attached)
checkpoint-status | e5601ab2-793a-4222-bd0c-1760b0486bca |  | checkpoint | Commission Fire interface (photos attached)
holdpoint | ca5eb271-2eb3-4559-a8d0-ff96ceef0863 |  | signoff | Request sign off