## Breakdown
South Pacific Fire Protection - 045 Kevin Hickman (Riccarton Park)
Stage 401 - Fire Kiosk
Valve Room
|  |  | Fire Alarm - Panel |  | Pre-populate | S - S - Fire Alarm
|  |  | Hydrant - Pipe/Valves |  | Pre-populate | S - S - Fire Hydrant
|  |  | Sprinklet - Main/Pipes Valves |  | Pre-populate | S - S - Fire Sprinkler
Compliance Documents
|  | Stage 04 - Fire Kiosk |  | Pre-populate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist | S - S - Fire Alarm
section | First Fix
checkpoint | Substrate acceptable
checkpoint | Area accessible
checkpoint | Flush boxes fitted
checkpoint | Ready to line walls
checkpoint | Ready to line ceiling
checkpoint | First fix completed and area cleared of waste
checkpoint | Main contractor sign off
section | Second Fix
checkpoint | Ceiling fitted off
checkpoint | Walls fitted off
checkpoint | Second fix completed in all aspects and area cleared of waste
Type | Name | Value
checklist-flat | S - S - Fire Hydrant
checkpoint | Substrate acceptable
checkpoint | Area accessible
checkpoint | First fix completed and area cleared of waste
checkpoint | Main contractor sign off
Type | Name | Value
checklist | S - S - Fire Sprinkler
section | First Fix
checkpoint | Substrate acceptable
checkpoint | Area accessible
checkpoint | First fix completed and area cleared of waste
checkpoint | Main contractor sign off
section | Second Fix
checkpoint | Second fix completed in all aspects and area cleared of waste
holdpoint | Main contractor sign off
section | Pressure Test
checkpoint | Pressure Test Info
checkpoint | System pressure test details
checkpoint | Installation conforms to accepted plans
checkpoint | Equipment used is approved
checkpoint | Test Results
checkpoint | Retest required
checkpoint | Installer review completed
checkpoint | Main contractor review completed
holdpoint | Main contractor sign off
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff