## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Basement 1st Fix |  |  |  |  | Yes | Basement 1st Fix | 09f1e57f-2e33-445e-b52d-270421434ab8
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Fan installed
checkpoint-status |  |  | checkpoint | Seismic bracing installed
checkpoint-status |  |  | checkpoint | Label applied
checkpoint-group |  |  | section | Split System Units
checkpoint-status |  |  | checkpoint | Indoor & outdoor units installed
checkpoint-status |  |  | checkpoint | Refrigeration pipework connected
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Condensate Pipework
checkpoint-status |  |  | checkpoint | Pipework installed to tundish by Hydraulics
checkpoint-status |  |  | checkpoint | Tested & witnessed
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework for 3 m from connection
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Outside air duct installed & covered
checkpoint-status |  |  | checkpoint | Extract air duct installed & covered
checkpoint-status |  |  | checkpoint | Flexible ducts installed
checkpoint-status |  |  | checkpoint | Fire dampers / fire sealants installed
checkpoint-status |  |  | checkpoint | Access panels installed
checkpoint-status |  |  | checkpoint | Balancing dampers installed & blade positions identifiable externally
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | CHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Isolating & isolating-regulating valves installed at floor take-offs
checkpoint-status |  |  | checkpoint | By-passes installed
checkpoint-status |  |  | checkpoint | Air vents & drains installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Flushed and chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | HHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Isolating & isolating-regulating valves installed at floor take-offs
checkpoint-status |  |  | checkpoint | By-passes installed
checkpoint-status |  |  | checkpoint | Air vents & drains installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Flushed and chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed, terminated and actuator fitted
checkpoint-status |  |  | checkpoint | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Ductwork Pre-Commissioning |  |  |  |  | Yes | Ductwork Pre-Commissioning | 0f5a4493-9145-432d-b493-644b052ac015
checkpoint-status |  |  | checkpoint | Covers removed
checkpoint-status |  |  | checkpoint | Balancing dampers fully open
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Roof - Level 13A Pre-Commissioning |  |  |  |  | Yes | Roof - Level 13A Pre-Commissioning | 108c82d8-7d84-4055-9fa8-991e1b22341b
checkpoint-status |  |  | checkpoint | Ductwork Covers removed
checkpoint-status |  |  | checkpoint | Balancing dampers fully open
checkpoint-status |  |  | checkpoint | Controls tested
checkpoint-status |  |  | checkpoint | Condensate Pipework Tested (again) & witnessed (again)
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Risers 2nd Fix |  |  |  |  | Yes | Risers 2nd Fix | 1c69d14b-916b-43dc-aa3e-3c4178b31ed1
checkpoint-status |  |  | checkpoint | Ductwork Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Roof 2nd Fix |  |  |  |  | Yes | Roof 2nd Fix | 1dc4b224-d690-426c-953a-4176e17b9107
checkpoint-status |  |  | checkpoint | Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Apartment Corridors 1st Fix |  |  |  |  | Yes | Apartment Corridors 1st Fix | 30fc3e6c-b0d0-4ecb-9b34-af6f4ecbee82
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Actuated Windows (By Icon)
checkpoint-status |  |  | checkpoint | Operable window installed with actuator
checkpoint-status |  |  | checkpoint | Window actuator power supply cabling complete (by Aseco)
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Outside air riser with fire damper installed
checkpoint-status |  |  | checkpoint | Outside air branch installed with fire damper
checkpoint-status |  |  | checkpoint | Rubbish room exhaust riser with fire damper installed
checkpoint-status |  |  | checkpoint | Rubbish room exhaust branch duct installed with balancing damper
checkpoint-status |  |  | checkpoint | Building C Cleaners room exhaust riser with fire damper installed
checkpoint-status |  |  | checkpoint | Building C Cleaners room exhaust branch duct installed with balancing damper (G/F, L1, L4, L7 & L10)
checkpoint-status |  |  | checkpoint | Access panels installed
checkpoint-status |  |  | checkpoint | Duct labels installed
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed and terminated
checkpoint-status |  |  | checkpoint | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Ductwork 2nd Fix |  |  |  |  | Yes | Ductwork 2nd Fix | 343b1e33-d60c-4529-b4df-09ea396f6a56
checkpoint-status |  |  | checkpoint | Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Apartment Corridors Pre-Commissioning |  |  |  |  | Yes | Apartment Corridors Pre-Commissioning | 345575a3-5515-40a1-81cc-6edc9b8b9bc6
checkpoint-status |  |  | checkpoint | Ductwork Covers removed
checkpoint-status |  |  | checkpoint | Power & Control - Window operation tested
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Main Plant 2nd Fix |  |  |  |  | Yes | Main Plant 2nd Fix | 38bc4fbf-36ea-44e0-9f6b-80021f1e8ee6
checkpoint-status |  |  | checkpoint | Ductwork Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Pipework 1st Fix |  |  |  |  | Yes | Pipework 1st Fix | 41785353-57d8-412b-9f92-a86ecd16fe5d
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Condensate Pipework
checkpoint-status |  |  | checkpoint | Pipework installed to tundish by Hydraulics
checkpoint-status |  |  | checkpoint | Tested & witnessed
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework for 3 m from connection
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | CHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Isolating & isolating-regulating valves installed at floor take-offs
checkpoint-status |  |  | checkpoint | By-passes installed
checkpoint-status |  |  | checkpoint | Air vents & drains installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Flushed and chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | HHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Isolating & isolating-regulating valves installed at floor take-offs
checkpoint-status |  |  | checkpoint | By-passes installed
checkpoint-status |  |  | checkpoint | Air vents & drains installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Flushed and chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Communal/Office 1st Fix |  |  |  |  | Yes | Communal/Office 1st Fix | 5288751b-07f2-415d-b0b0-495cc92145a8
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Fan Coil Units
checkpoint-status |  |  | checkpoint | Unit & plenums installed
checkpoint-status |  |  | checkpoint | FCU & plenums have rubber isolators installed
checkpoint-status |  |  | checkpoint | Seismic bracing installed if hanger rod is greater than 200 mm long
checkpoint-status |  |  | checkpoint | Label applied
checkpoint-group |  |  | section | Air Handling Units
checkpoint-status |  |  | checkpoint | Units installed
checkpoint-status |  |  | checkpoint | Spigots & by-pass dampers installed
checkpoint-status |  |  | checkpoint | Valve trains, air vents & drain valves installed
checkpoint-status |  |  | checkpoint | CHW & LTHW pipework connected
checkpoint-status |  |  | checkpoint | Condensate pipework connected
checkpoint-status |  |  | checkpoint | Gauges installed
checkpoint-status |  |  | checkpoint | Seismic bracings installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Heat Recovery Ventilation Units (HRU)
checkpoint-status |  |  | checkpoint | Unit installed with rubber isolators
checkpoint-status |  |  | checkpoint | Filter & HRU covered / protected from dust
checkpoint-status |  |  | checkpoint | Seismic bracing installed if hanger rod is greater than 200 mm long
checkpoint-status |  |  | checkpoint | Label applied
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Outside air duct installed
checkpoint-status |  |  | checkpoint | Extract air duct installed
checkpoint-status |  |  | checkpoint | Supply air duct installed
checkpoint-status |  |  | checkpoint | Kitchen exhaust air duct installed
checkpoint-status |  |  | checkpoint | Flexible ducts installed
checkpoint-status |  |  | checkpoint | Access panels installed
checkpoint-status |  |  | checkpoint | Balancing dampers installed & blade positions identifiable externally
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | CHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Valve trains installed
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | HHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Valve trains installed
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Condensate Pipework
checkpoint-status |  |  | checkpoint | Pipework installed to hydraulic interface
checkpoint-status |  |  | checkpoint | Tested & witnessed
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework for 3 m from connection
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed, terminated and actuator fitted
checkpoint-status |  |  | checkpoint | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Communal/Office 2nd Fix |  |  |  |  | Yes | Communal/Office 2nd Fix | 570600a4-cd39-401f-bd43-10e5e2a08607
checkpoint-status |  |  | checkpoint | Ductwork Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Roof - Level 13A 2nd Fix |  |  |  |  | Yes | Roof - Level 13A 2nd Fix | 58559a15-3fed-428f-aedf-605ec95ffda9
checkpoint-status |  |  | checkpoint | Ductwork Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Controller mounted on wall
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Basement Pre-Commissioning |  |  |  |  | Yes | Basement Pre-Commissioning | 5f62af61-37f3-475f-98f8-933e17811b81
checkpoint-status |  |  | checkpoint | Ductwork Covers removed
checkpoint-status |  |  | checkpoint | Balancing dampers fully open
checkpoint-status |  |  | checkpoint | Controller Tested
checkpoint-status |  |  | checkpoint | Condensate Pipework Tested (again) & witnessed (again)
checkpoint-status |  |  | checkpoint | Pipework Valves open
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Roof Pre-Commissioning |  |  |  |  | Yes | Roof Pre-Commissioning | 6ddc58d3-e7f6-4dc1-95ec-eab500538111
checkpoint-status |  |  | checkpoint | Ductwork Covers removed
checkpoint-status |  |  | checkpoint | Ductwork Balancing dampers fully open
checkpoint-status |  |  | checkpoint | Controls & actuators tested
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Roof 1st Fix |  |  |  |  | Yes | Roof 1st Fix | 73ad08b4-746f-4e00-ae9d-81ade623afad
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Fans or Cowls
checkpoint-status |  |  | checkpoint | Upstand with under flashing installed by Icon
checkpoint-status |  |  | checkpoint | Fans or cowls installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed
checkpoint-status |  |  | checkpoint | Cables terminated
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Apartment Pre-Commissioning |  |  |  |  | Yes | Apartments Pre-Commissioning | 765f0a54-d1bd-48e3-88d9-62c9ec74281a
checkpoint-status |  |  | checkpoint | Ductwork Covers removed
checkpoint-status |  |  | checkpoint | Controller Tested
checkpoint-status |  |  | checkpoint | Condensate Pipework Tested (again) & witnessed (again)
checkpoint-status |  |  | checkpoint | Drains and inline traps accessible from hatch
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Main Plantroom Pre-Commissioning |  |  |  |  | Yes | Main Plantroom Pre-Commissioning | 86f5b4ac-2886-4c80-9dc4-9c899f1bb9ab
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Covers removed
checkpoint-status |  |  | checkpoint | Balancing dampers fully open
checkpoint-group |  |  | section | CHW & HHW Pipework
checkpoint-status |  |  | checkpoint | Isolating & isolating-regulating valves open
checkpoint-status |  |  | checkpoint | Dosing pots isolated from system
checkpoint-status |  |  | checkpoint | Flushing by-passes closed
checkpoint-group |  |  | section | Condensate Pipework
checkpoint-status |  |  | checkpoint | Tested (again) & witnessed (again)
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls tested
checkpoint-status |  |  | checkpoint | Controls & actuators tested
checkpoint-group |  |  | section | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Apartments 1st Fix |  |  |  |  | Yes | Apartments 1st Fix | 9869e72d-e5c0-4e19-9485-7467d8c6a847
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Heat Recovery Ventilation Units (HRU)
checkpoint-status |  |  | checkpoint | Unit installed with rubber isolators
checkpoint-status |  |  | checkpoint | Filter & HRU covered / protected from dust
checkpoint-status |  |  | checkpoint | Seismic bracing installed if hanger rod is greater than 200 mm long
checkpoint-status |  |  | checkpoint | Label applied
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Outside air intake duct installed with balcony grille and plenum
checkpoint-status |  |  | checkpoint | Kitchen exhaust duct installed with balcony grille and plenum
checkpoint-status |  |  | checkpoint | Exhaust air duct installed with balcony grille and plenum
checkpoint-status |  |  | checkpoint | Toilet extract air duct installed
checkpoint-status |  |  | checkpoint | Supply air duct installed
checkpoint-status |  |  | checkpoint | Flexible ducts installed
checkpoint-status |  |  | checkpoint | Access panels installed
checkpoint-status |  |  | checkpoint | Duct labels installed
checkpoint-group |  |  | section | Condensate Pipework
checkpoint-status |  |  | checkpoint | Pipework installed to hydraulic interface
checkpoint-status |  |  | checkpoint | Tested & witnessed
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed and terminated
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | For Studio apartment clothes dryer kit supplied and discharge cowl fitted by Icon
checkpoint-status |  |  | checkpoint | For Studio apartments clothes dryer kit installed
checkpoint-status |  |  | checkpoint | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Pipework Pre-Commissioning |  |  |  |  | Yes | Pipework Pre-Commissioning | 9a72724f-c61c-49a0-bba8-087f3bc9555f
checkpoint-status |  |  | checkpoint | Ductwork Valves open
checkpoint-status |  |  | checkpoint | Condensate Pipework Tested (again) & witnessed (again)
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Apartment 2nd Fix |  |  |  |  | Yes | Apartments 2nd Fix | af2947f2-1ebd-4451-a502-540ea07fb3d4
checkpoint-status |  |  | checkpoint | Ductwork Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Controller mounted on wall
checkpoint-status |  |  | checkpoint | Filter removal via hatch ok
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Main Plant 1st Fix |  |  |  |  | Yes | Main Plant 1st Fix | b1a4e571-ce03-4c23-9b88-764cc7657ec0
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Chillers
checkpoint-status |  |  | checkpoint | Chiller installed
checkpoint-status |  |  | checkpoint | Valve trains, air vents & drain valves installed
checkpoint-status |  |  | checkpoint | Vibration/seismic isolators installed
checkpoint-status |  |  | checkpoint | CHW flow and return pipework connected
checkpoint-status |  |  | checkpoint | Temperature & flow sensors installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Boilers
checkpoint-status |  |  | checkpoint | Boilers installed
checkpoint-status |  |  | checkpoint | Pressure relief valves installed
checkpoint-status |  |  | checkpoint | Pipework reducers located immediately before the boiler connections
checkpoint-status |  |  | checkpoint | LTHW flow & return pipework connected
checkpoint-status |  |  | checkpoint | Gas pipework connected (incl. Appliance regulator, filter, IV, NRV, etc.)
checkpoint-status |  |  | checkpoint | Temperature sensors installed
checkpoint-status |  |  | checkpoint | Flow sensors installed
checkpoint-status |  |  | checkpoint | Flues installed
checkpoint-status |  |  | checkpoint | Seismic bracing installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Pumps
checkpoint-status |  |  | checkpoint | Pumps installed
checkpoint-status |  |  | checkpoint | Valve train installed (incl. Strainer, NRV, IVs, test points, etc.)
checkpoint-status |  |  | checkpoint | Vibration isolators installed
checkpoint-status |  |  | checkpoint | Pipework connected at inlet and outlet
checkpoint-status |  |  | checkpoint | Seismic bracings installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Expansion Vessels
checkpoint-status |  |  | checkpoint | Expansion vessels installed
checkpoint-status |  |  | checkpoint | Pressure relief valves installed
checkpoint-status |  |  | checkpoint | Pressure reducing valves installed
checkpoint-status |  |  | checkpoint | Pressure sensors installed
checkpoint-status |  |  | checkpoint | Seismic bracings installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-status |  |  | checkpoint | CHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed (incl. Headers with correct connection order)
checkpoint-status |  |  | checkpoint | Bypasses installed
checkpoint-status |  |  | checkpoint | Dosing pot installed
checkpoint-status |  |  | checkpoint | Air vents, isolation valves and drain valves installed
checkpoint-status |  |  | checkpoint | Temperature sensors & pressure gauges installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-status |  |  | checkpoint | LTHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed (incl. Header with correct connection order)
checkpoint-status |  |  | checkpoint | Bypasses installed
checkpoint-status |  |  | checkpoint | Dosing pot installed
checkpoint-status |  |  | checkpoint | Air vents, isolation valves and drain valves installed
checkpoint-status |  |  | checkpoint | Temperature sensors & pressure gauges installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Seismic bracings installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Condensate Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Tested & witnessed
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework for 3 m from connection
checkpoint-status |  |  | checkpoint | Seismic bracings installed
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed
checkpoint-status |  |  | checkpoint | Cables terminated
checkpoint-status |  |  | checkpoint | Actuators fitted
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Roof - Level 13A 1st Fix |  |  |  |  | Yes | Roof - Level 13A 1st Fix | baa8f96b-fd3a-4ab4-810d-e3b89ad28a55
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Fans
checkpoint-status |  |  | checkpoint | Fan installed
checkpoint-status |  |  | checkpoint | Seismic bracing installed
checkpoint-status |  |  | checkpoint | Label applied
checkpoint-group |  |  | section | Split System Units
checkpoint-status |  |  | checkpoint | Indoor & outdoor units installed
checkpoint-status |  |  | checkpoint | Refrigeration pipework connected
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Condensate Pipework
checkpoint-status |  |  | checkpoint | Pipework installed to tundish by Hydraulics
checkpoint-status |  |  | checkpoint | Tested & witnessed
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework for 3 m from connection
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Outside air duct installed & covered
checkpoint-status |  |  | checkpoint | Extract air duct installed & covered
checkpoint-status |  |  | checkpoint | Flexible ducts installed
checkpoint-status |  |  | checkpoint | Fire dampers / fire sealants installed
checkpoint-status |  |  | checkpoint | Access panels installed
checkpoint-status |  |  | checkpoint | Balancing dampers installed & blade positions identifiable externally
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed, terminated and actuator fitted
checkpoint-status |  |  | checkpoint | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Ducting 1st Fix |  |  |  |  | Yes | Ducting 1st Fix | d4b23633-a5ad-4174-ab70-bfe58110c6a2
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Outside air duct installed & covered
checkpoint-status |  |  | checkpoint | Extract air duct installed & covered
checkpoint-status |  |  | checkpoint | Flexible ducts installed
checkpoint-status |  |  | checkpoint | Fire dampers / fire sealants installed
checkpoint-status |  |  | checkpoint | Access panels installed
checkpoint-status |  |  | checkpoint | Balancing dampers installed & blade positions identifiable externally
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-sectioned |  |  | checklist | Risers 1st Fix |  |  |  |  | Yes | Risers 1st Fix | def28c2f-3fb0-4cab-a540-c3932594d657
checkpoint-group |  |  | section | Preinstall
checkpoint-status |  |  | checkpoint | Area accessible and ready to start work
checkpoint-group |  |  | section | Ductwork
checkpoint-status |  |  | checkpoint | Outside air duct installed & covered
checkpoint-status |  |  | checkpoint | Extract air duct installed & covered
checkpoint-status |  |  | checkpoint | Flexible ducts installed
checkpoint-status |  |  | checkpoint | Fire damper / fire sealant installed
checkpoint-status |  |  | checkpoint | 1M fire damper installation checks conducted
checkpoint-status |  |  | checkpoint | Access panels installed
checkpoint-status |  |  | checkpoint | Balancing damper installed & open
checkpoint-status |  |  | checkpoint | Balancing dampers installed & blade positions identifiable externally
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | CHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Isolating & isolating-regulating valves installed at floor take-offs
checkpoint-status |  |  | checkpoint | By-passes installed
checkpoint-status |  |  | checkpoint | Air vents & drains installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | HHW Pipework
checkpoint-status |  |  | checkpoint | Pipework installed
checkpoint-status |  |  | checkpoint | Isolating & isolating-regulating valves installed at floor take-offs
checkpoint-status |  |  | checkpoint | By-passes installed
checkpoint-status |  |  | checkpoint | Air vents & drains installed
checkpoint-status |  |  | checkpoint | Pressure tested & witnessed
checkpoint-status |  |  | checkpoint | Flushed and chemically treated
checkpoint-status |  |  | checkpoint | Insulation installed & fully encapsulates pipework
checkpoint-status |  |  | checkpoint | Labels applied
checkpoint-group |  |  | section | Power & Controls
checkpoint-status |  |  | checkpoint | Controls installed, terminated and actuator fitted
checkpoint-status |  |  | checkpoint | Area completion
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Basement 2nd Fix |  |  |  |  | Yes | Basement 2nd Fix | e4433512-03a4-40a1-a168-32f8e75ab0fe
checkpoint-status |  |  | checkpoint | Ductwork Grilles / diffusers & boxes installed
checkpoint-status |  |  | checkpoint | Controller mounted on wall
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Apartment Corridors 2nd Fix |  |  |  |  | Yes | Apartment Corridors 2nd Fix | f062d58a-24cc-49ea-a223-335bcfbda633
checkpoint-status |  |  | checkpoint | Ductwork grilles / diffusers installed
checkpoint-status |  |  | checkpoint | Group Control wiring complete for actuated windows
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Risers Pre-Commissioning |  |  |  |  | Yes | Risers Pre-Commissioning | f3a6809f-8262-47ce-8c89-fe9495ff43ce
checkpoint-status |  |  | checkpoint | Ductwork Covers removed
checkpoint-status |  |  | checkpoint | Balancing dampers fully open
checkpoint-status |  |  | checkpoint | CHW Pipework Isolating & isolating-regulating valves open; flushing bypass closed
checkpoint-status |  |  | checkpoint | HHW Pipework Isolating & isolating-regulating valves open; flushing bypass closed
checkpoint-status |  |  | checkpoint | Controls & actuators tested
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached
checklist-flat |  |  | checklist | Communal/Office Pre-Commissioning |  |  |  |  | Yes | Communal/Office Pre-Commissioning | f5c67d11-51d0-43fc-afd0-696b7cf66a70
checkpoint-status |  |  | checkpoint | Ductwork Covers removed
checkpoint-status |  |  | checkpoint | Balancing dampers fully open
checkpoint-status |  |  | checkpoint | CHW Pipework Isolating & isolating-regulating valves open; flushing bypass closed
checkpoint-status |  |  | checkpoint | HHW Pipework Isolating & isolating-regulating valves open; flushing bypass closed
checkpoint-status |  |  | checkpoint | Condensate Pipework Tested (again) & witnessed (again)
checkpoint-status |  |  | checkpoint | Controls & actuators tested
checkpoint-status |  |  | checkpoint | Any other items fixed/installed as necessary
checkpoint-status |  |  | checkpoint | Work completed and photos attached