## Sheet1
Keith Park (A.G.A)
QA
Building 7
Structure
Basement
Lift Pit & Manhole
[6 empty] | Lift Pit | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Manhole | pre-populate | ST - S - Concrete Pour - Without Reo
Concrete Pour
[6 empty] | Concrete Pour Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Concrete Pour Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Concrete Pour Area 3 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Concrete Pour Area 4 | pre-populate | ST - S - Concrete Pour - Without Reo
Precast Components
[6 empty] | Precast Wall Panel Installation | pre-populate | ST - S - Precast Wall Panel Installation
[6 empty] | Precast Wall Brackets Installation | pre-populate | ST - S - Precast Wall Bracket Installation
[6 empty] | Precast Spandrell panels Insallation | pre-populate | ST - S - Precast Spandrel Panel Installation
[6 empty] | Precast Flat Slab Installation | pre-populate | ST - S - Precast Flat Slab Installation
[6 empty] | Stair Installation | pre-populate | ST - S - Stair Installation
[5 empty] | Insitu Sitich Joints & Concrete Columns |  | ability to add | ST - S - Insitu Stitch Joints
Ground Floor
[5 empty] | Concrete Pour |  | ability to add | ST - S - Concrete Pour - Without Reo
[6 empty] | Insitu Beams Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Insitu Beams Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Insitu Beams Area 3 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 3 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
Precast Components
[6 empty] | Precast Wall Panel Installation | pre-populate | ST - S - Precast Wall Panel Installation
[6 empty] | Precast Wall Brackets Installation | pre-populate | ST - S - Precast Wall Bracket Installation
[6 empty] | Precast Spandrell panels Insallation | pre-populate | ST - S - Precast Spandrel Panel Installation
[6 empty] | Precast Flat Slab Installation | pre-populate | ST - S - Precast Flat Slab Installation
[6 empty] | Steel Deck | pre-populate | ST - S - Steel Deck Concrete Topping
[6 empty] | Stair Installation | pre-populate | ST - S - Stair Installation
[5 empty] | Insitu Sitich Joints |  | ability to add | ST - S - Concrete Pour - Without Reo
Level 1
[5 empty] | Concrete Pour |  | ability to add | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
Precast Components
[6 empty] | Precast Wall Panel Installation | pre-populate | ST - S - Precast Wall Panel Installation
[6 empty] | Precast Wall Brackets Installation | pre-populate | ST - S - Precast Wall Bracket Installation
[6 empty] | Precast Spandrell panels Insallation | pre-populate | ST - S - Precast Spandrel Panel Installation
[6 empty] | Precast Flat Slab Installation | pre-populate | ST - S - Precast Flat Slab Installation
[6 empty] | Steel Deck | pre-populate | ST - S - Steel Deck Concrete Topping
[6 empty] | Stair Installation | pre-populate | ST - S - Stair Installation
[5 empty] | Insitu Sitich Joints & Concrete Columns |  | ability to add | ST - S - Concrete Pour - Without Reo
Level 2
[5 empty] | Concrete Pour |  | ability to add | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
Precast Components
[6 empty] | Precast Wall Panel Installation | pre-populate | ST - S - Precast Wall Panel Installation
[6 empty] | Precast Wall Brackets Installation | pre-populate | ST - S - Precast Wall Bracket Installation
[6 empty] | Precast Spandrell panels Insallation | pre-populate | ST - S - Precast Spandrel Panel Installation
[6 empty] | Precast Flat Slab Installation | pre-populate | ST - S - Precast Flat Slab Installation
[6 empty] | Steel Deck | pre-populate | ST - S - Steel Deck Concrete Topping
[6 empty] | Stair Installation | pre-populate | ST - S - Stair Installation
[5 empty] | Insitu Sitich Joints & Concrete Columns |  | ability to add | ST - S - Concrete Pour - Without Reo
Level 3
[5 empty] | Concrete Pour |  | ability to add | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
Precast Components
[6 empty] | Precast Wall Panel Installation | pre-populate | ST - S - Precast Wall Panel Installation
[6 empty] | Precast Wall Brackets Installation | pre-populate | ST - S - Precast Wall Bracket Installation
[6 empty] | Precast Spandrell panels Insallation | pre-populate | ST - S - Precast Spandrel Panel Installation
[6 empty] | Precast Flat Slab Installation | pre-populate | ST - S - Precast Flat Slab Installation
[6 empty] | Steel Deck | pre-populate | ST - S - Steel Deck Concrete Topping
[6 empty] | Stair Installation | pre-populate | ST - S - Stair Installation
[5 empty] | Insitu Sitich Joints & Concrete Columns |  | ability to add | ST - S - Concrete Pour - Without Reo
Level 4
[5 empty] | Concrete Pour |  | ability to add | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Slab Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 1 | pre-populate | ST - S - Concrete Pour - Without Reo
[6 empty] | Balconies Area 2 | pre-populate | ST - S - Concrete Pour - Without Reo
Precast Components
[6 empty] | Precast Wall Panel Installation | pre-populate | ST - S - Precast Wall Panel Installation
[6 empty] | Precast Wall Brackets Installation | pre-populate | ST - S - Precast Wall Bracket Installation
[6 empty] | Precast Spandrell panels Insallation | pre-populate | ST - S - Precast Spandrel Panel Installation
[6 empty] | Precast Flat Slab Installation | pre-populate | ST - S - Precast Flat Slab Installation
[6 empty] | Steel Deck | pre-populate | ST - S - Steel Deck Concrete Topping
[6 empty] | Stair Installation | pre-populate | ST - S - Stair Installation
[5 empty] | Insitu Sitich Joints & Concrete Columns |  | ability to add | ST - S - Concrete Pour - Without Reo

## Sheet2
Type | Name
checklist | ST - S - Concrete Pour - Without Reo
section | Pour Details
checkpoint | Pour details entered
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork and Embedded Items
checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
checkpoint | Any control joints/ stop ends installed accurately and correctly braced
section | Pre-Pour Completion (Approval to pour)
checkpoint | Waterproofing elements have been correctly installed and checked
checkpoint | Relevant service requirements completed (locations checked and accurate)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
checkpoint | Ryman inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
checkpoint | Concrete Supplier details entered
text | Supplier Name:
text | Specified concrete strength:
text | Concrete strength ordered:
text | Concrete quantity ordered:
button | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
checkpoint | Concrete strength test reports attached and required concrete strength achieved
section | Placement Method
checkpoint | Placement methodology confirmed and necessary plant and equipment on site
checkpoint | Heights and falls checked/confirmed before placement
button | Is the cover correct to specification
checkpoint | Heights and falls checked/ confirmed after placement
checkpoint | Any curing compound applied correctly
checkpoint | Concrete placement completed - specified level of finish achieved
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
holdpoint | Raise remedial/ Request Signoff
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name
checklist-flat | ST - S - Precast Flat Slab Installation
checkpoint | Inspected on arrival and damage free
checkpoint | Installed in correct location
checkpoint | Adequately braced and braces are tagged
checkpoint | Precast Flat Slab Installation completed (checked location & level) and no damages
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name
checklist-flat | ST - S - Precast Spandrel Panel Installation
checkpoint | Inspected on arrival and damage free
checkpoint | Installed in correct location
checkpoint | Adequately braced and braces are tagged
checkpoint | Precast Spandrel Panel Installation completed (checked location & level) and no damages
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name
checklist-flat | ST - S - Precast Wall Bracket Installation
checkpoint | Bracket correct size as per drawing
checkpoint | Cast in weld plate in correct position
checkpoint | Adequately braced and braces to be tagged
checkpoint | Bracket installed in correct position, plumb and level
checkpoint | Welding inspected and correct as per drawing
checkpoint | Paint repair completed
checkpoint | Bracket installation completed correctly (checked location & level)
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name
checklist-flat | ST - S - Precast Wall Panel Installation
checkpoint | Inspected on arrival and damage free
checkpoint | Appointment with the engineers confirmed (Enter date & time of the appointment)
checkpoint | Installed in correct location
checkpoint | Adequately braced and Braces to be tagged
checkpoint | Grout sleeves correctly grouted
checkpoint | Precast Wall Panel Installation completed correctly (checked location & level) and damage free
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name
checklist-flat | ST - S - Stair Installation
checkpoint | Items inspected on arrival and correct (length, width, size/shape) as per design/shop drawings and damage free
checkpoint | Grid Set-out offset and level correct
checkpoint | Joints scabbled and acceptable
checkpoint | All setout completed correctly and approved
checkpoint | Temporary support installed and approved
checkpoint | Stairs placed, locations, heights and orientation approved. No damage during installation
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name
checklist | ST - S - Insitu Stitch Joints
section | Pour Details
checkpoint | Pour Details:
text | Area to be poured:
text | Date of pour:
checkpoint | Latest drawings available, checked and referenced
section | Formwork
checkpoint | Formwork braced & fixed correctly
checkpoint | All surfaces correctly prepared (e.g joints to exisiting concrete, release agent to formwork etc)
section | Reinforcing
checkpoint | Size and type correct to specification
section | Pre-Pour Completion (Approval to pour)
checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint | Raise remedial / Request Signoff
checkpoint | All relevant inspections completed and attached
checkpoint | Ryman inspection completed - Approval given to pour concrete
section | Concrete Supplier Specifics
checkpoint | Test blocks booked
checkpoint | All concrete dockets photographed/ attached
section | Post Pour Checks/Sign Off
checkpoint | Any remedial work completed
holdpoint | Raise remedial / Request Signoff
checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name
checklist-flat | ST - S - Steel Deck Concrete Topping
checkpoint | Area clean and accessible
checkpoint | Material and size are correct
checkpoint | Installed in the correct location and orientation
checkpoint | Firmly secured in the correct method
checkpoint | Area left tidy and accessible, and work signed off
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS