## Sheet1
type | name | values | prefix | postfix | Usage Count | User Addable | Template Name
checklist | Cell Comms V1 |  |  |  | 0 | Yes | Cell Comms V1
checkpoint | Communications cables fitted off
checkpoint | Communications cables labelled
checkpoint | Communications cables tested
checkpoint | WAP Installed
checkpoint | Cell complete
checklist | Comms BMS 2 |  |  |  | 0 | Yes | Comms BMS 2
checkpoint | Communications BMS copper cables roughed in
checkpoint | Terminated rack end
checkpoint | Terminated field end
checkpoint | Tested
checkpoint | Labelled
checkpoint | Outlets complete
checklist | OS2 - V1 |  |  |  | 0 | Yes | OS2 - V1
checkpoint | 12 Core OS2 cable roughed in
checkpoint | Terminated local end
checkpoint | Terminated remote end
checkpoint | Tested - OTDR
checkpoint | Tested - Power/Light Meter
checkpoint | Labelled
checkpoint | Fibre link complete
checklist | Drawings / Documents |  |  |  | 0 | Yes | Drawings / Documents
checkpoint | Attach Drawings / Docs
checklist | DJCS 2 |  |  |  | 0 | Yes | DJCS 2
checkpoint | 10 pair DJCS cable roughed in R1 Top
checkpoint | Terminated local end
checkpoint | Terminated remote end Administration Bldg PABX Rm
checkpoint | Tested
checkpoint | Labelled
checkpoint | Copper backbone links complete
checklist | Rough In & Fit Off With Floor box |  |  |  | 4 | Yes | Rough In & Fit Off With Floor box
checkpoint | In slab conduits and FB blockout installed for FB
checkpoint | Lighting roughed in
checkpoint | Power roughed in
checkpoint | Lighting control roughed in - KNX / DALI
checkpoint | Light feed installed CB #
checkpoint | Power feeds installed CB #
checkpoint | Lighting fit off
checkpoint | Power fit off
checkpoint | Room complete
checkpoint | Delays / Issues
checklist | OS2-V3 |  |  |  | 0 | Yes | OS2-V3
checkpoint | 24 Core OS2 DJCS cable roughed in R1 Top
checkpoint | 12 Core OS2 PIN/PEN cable roughed in R1 Bottom
checkpoint | Terminated local end
checkpoint | Terminated remote end
checkpoint | Tested - OTDR
checkpoint | Tested - Power/Light Meter
checkpoint | Labelled
checkpoint | Fibre links complete
checklist | Racks 2 |  |  |  | 0 | Yes | Racks 2
checkpoint | Install 15RU Wall Cabinet R4386
checkpoint | Cabinet secured
checkpoint | Cabinet fitted off
checkpoint | Cable management installed
checkpoint | PDU's Installed
checkpoint | Cabinet labelled
checkpoint | Cabinet cleaned
checkpoint | Cabinet complete
checklist | Comms BMS 1 |  |  |  | 0 | Yes | Comms BMS 1
checkpoint | Communications BMS copper cables roughed in
checkpoint | Communications Clock copper cables roughed in
checkpoint | Terminated rack end
checkpoint | Terminated field end
checkpoint | Tested
checkpoint | Labelled
checkpoint | Outlets complete
checklist | Floor Box / conduits in slab |  |  |  | 6 | Yes | Floor Box / conduits in slab
checkpoint | conduit installed, turned up in wall
checkpoint | Jet string installed
checkpoint | Tied off and secure
checkpoint | Floor Box blockout installed and secure
checkpoint | installation complete
checklist | Cable Tray |  |  |  | 0 | Yes | Cable Tray
checkpoint | Cable Tray Completed
checkpoint | Hold Ups
checklist | DB2 |  |  |  | 0 | Yes | DB2
checkpoint | DB installed
checkpoint | CB's installed
checkpoint | Mains roughed in
checkpoint | Power feeds roughed in
checkpoint | Mains fit off
checkpoint | Power fit off
checkpoint | Schedule completed
checkpoint | DB cleaned
checkpoint | Glands tight
checkpoint | Escutcheon secured
checkpoint | DB complete
checkpoint | Delays issues
checklist | Cell Comms V2 |  |  |  | 0 | Yes | Cell Comms V2
checkpoint | Communications cables installed from Rack
checkpoint | Communications cables fitted off
checkpoint | Communications cables labelled
checkpoint | Communications cables tested
checkpoint | WAP Installed
checkpoint | Cell complete
checklist | Comms 1 |  |  |  | 0 | Yes | Comms 1
checkpoint | Communications cables installed from Rack
checkpoint | Communications cables fitted off
checkpoint | Communications cables labelled
checkpoint | Communications cables tested
checkpoint | Area/Room complete
checklist | Rough In & Fit Off Body / Cardiac Protected Area |  |  |  | 74 | Yes | Rough In & Fit Off Body / Cardiac Protected Area
checkpoint | Lighting roughed in
checkpoint | Power roughed in
checkpoint | Lighting control roughed in - KNX / DALI
checkpoint | Earthing from all points to EPJ - Cardiac Areas
checkpoint | Medical Panel Installed, sealed, earthed
checkpoint | Light feed installed CB #
checkpoint | Power feeds installed CB #
checkpoint | Lighting fit off
checkpoint | Power fit off
checkpoint | Medical Panel fitted off
checkpoint | Photos attached
checkpoint | Testing completed
checkpoint | Prescribed Inspection completed
checkpoint | Room complete
checkpoint | Delays / Issues
checklist | Conduit, Pit, Pole Install |  |  |  | 5 | Yes | Conduit, Pit, Pole Install
checkpoint | Pit installed - please take a photo
checkpoint | Conduits installed to Pit
checkpoint | Ready for backfill
checkpoint | Danger tape installed
checkpoint | Trenching complete
checklist | Pole Light Install |  |  |  | 0 | Yes | Pole Light Install
checkpoint | Pole surveyed
checkpoint | Trench dug ready for conduit install
checkpoint | Footings dug out/bored
checkpoint | Rag bolts installed
checkpoint | Conduit 90's installed through rag bolts
checkpoint | Heights checked off RL's
checkpoint | Ready for concrete
checkpoint | Rough in complete
checkpoint | Light pole installed
checkpoint | Fit off complete
checkpoint | Light pole complete
checklist | OS2-V2 |  |  |  | 0 | Yes | OS2-V2
checkpoint | 24 Core OS2 DJCS cable roughed in R1 Top
checkpoint | 12 Core OS2 PIN/PEN cable roughed in R1 Bottom
checkpoint | 12 Core OS2 Arunta cable roughed in R2 Bottom
checkpoint | Terminated local end
checkpoint | Terminated remote end
checkpoint | Tested - OTDR
checkpoint | Tested - Power/Light Meter
checkpoint | Labelled
checkpoint | Fibre links complete
checklist | Rough In & Fit Off MEDICAL PANEL - Not BPA |  |  |  | 5 | Yes | Rough In & Fit Off MEDICAL PANEL - Not BPA
checkpoint | Lighting roughed in
checkpoint | Power roughed in
checkpoint | Lighting control roughed in - KNX / DALI
checkpoint | Medical Panel Installed, sealed, earthed
checkpoint | Light feed installed CB #
checkpoint | Power feeds installed CB #
checkpoint | Lighting fit off
checkpoint | Power fit off
checkpoint | Medical Panel fitted off
checkpoint | Photos attached
checkpoint | Testing completed
checkpoint | Prescribed Inspection completed
checkpoint | Room complete
checkpoint | Delays / Issues
checklist | Room ITP |  |  |  | 0 | Yes | Room ITP
checkpoint | Power feed roughed in CB #
checkpoint | Lighting roughed installed CB#
checkpoint | Lighting control / switching roughed in - KNX / DALI / 240V
checkpoint | Power fit-off
checkpoint | Lighting fit of
checkpoint | Lighting control / switching roughed in - KNX / DALI / 240V Fit off.
checkpoint | room complete
checkpoint | Delays / Issues
checklist | DB3 |  |  |  | 0 | Yes | DB3
checkpoint | DB installed
checkpoint | CB's installed
checkpoint | Mains roughed in
checkpoint | Power feeds roughed in
checkpoint | Mains fit off
checkpoint | Power fit off
checkpoint | Schedule completed
checkpoint | DB cleaned
checkpoint | Glands tight
checkpoint | Escutcheon secured
checkpoint | DB complete
checklist | Racks 1 |  |  |  | 0 | Yes | Racks 1
checkpoint | Install 45RU Standard Cabinet S2005
checkpoint | Install 45RU Class C Cabinet R4384
checkpoint | Cabinet secured
checkpoint | Cabinet fitted off
checkpoint | Cable management installed
checkpoint | PDU's Installed
checkpoint | Shelves Installed
checkpoint | Cabinet labelled
checkpoint | Cabinet cleaned
checkpoint | Cabinet complete
checklist | DB 1 |  |  |  | 21 | Yes | DB 1
checkpoint | DB installed
checkpoint | CB's installed
checkpoint | Mains roughed in
checkpoint | Lighting feeds roughed in
checkpoint | Power feeds roughed in
checkpoint | Lighting control feeds roughed in (CBUS & DALI)
checkpoint | Mains fit off
checkpoint | Lighting fit off
checkpoint | Power fit off
checkpoint | Lighting control fit off (CBUS & DALI)
checkpoint | Schedule completed (attached to door)
checkpoint | DB cleaned
checkpoint | Glands tight / Fire sealed
checkpoint | Escutcheon secured
checkpoint | DB live, tested and commissioned - photo of results
checkpoint | Delays issues
checklist | DJCS 1 |  |  |  | 0 | Yes | DJCS 1
checkpoint | 10 pair DJCS cable roughed in R1 Top
checkpoint | 30 pair Arunta cable roughed in R2 Bottom
checkpoint | 1 x C6A UG Arunta cable roughed in R2 Bottom
checkpoint | Terminated local end
checkpoint | Terminated remote end Administration Bldg PABX Rm
checkpoint | Tested
checkpoint | Labelled
checkpoint | Copper backbone links complete
checklist | Rough In & Fit Off 2 |  |  |  | 0 | Yes | Rough In & Fit Off 2
checkpoint | In slab conduits installed
checkpoint | Floor box installed and complete
checkpoint | Lighting roughed in
checkpoint | Power roughed in
checkpoint | Lighting control roughed in (CBUS and DALI)
checkpoint | Light feed installed
checkpoint | Power feeds installed
checkpoint | Lighting fit off
checkpoint | Power fit off
checkpoint | Room complete
checklist |  |  |  |  | 130 | No
checkpoint | Power feed roughed in CB #
checkpoint | Lighting roughed installed CB#
checkpoint | Lighting control / switching roughed in - KNX / DALI / 240V
checkpoint | Power fit-off
checkpoint | Lighting fit of
checkpoint | Lighting control / switching roughed in - KNX / DALI / 240V Fit off.
checkpoint | Room complete
checkpoint | Delays / Issues