## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Ceiling Diffusers |  |  |  |  | Yes | Ceiling Diffusers | 0c0b2d11-10fa-4da0-9e72-0b6c0c507e2a
checkpoint-status |  |  | checkpoint | Egg-crate grille diffuser, round, half chevrons, 4-way diffusers etc. cut into ceiling with adequate support around frame
checklist-flat |  |  | checklist | AHU Installation |  |  |  |  | Yes | AHU Installation | 22b937e1-6393-4e05-ad4c-d03778d68aa3
checkpoint-status |  |  | checkpoint | Ensure that the AHU’s are not damaged after delivery.
checkpoint-status |  |  | checkpoint | Are drawings on site the latest issue
checkpoint-status |  |  | checkpoint | Identify and install the AHU in the right location.
checkpoint-status |  |  | checkpoint | Label the AHU clearly.
checkpoint-status |  |  | checkpoint | Install anti-vibration mounts
checkpoint-status |  |  | checkpoint | Ensure that the AHU is securely installed.
checkpoint-status |  |  | checkpoint | Is the impeller free to move
checkpoint-status |  |  | checkpoint | Install VSD if required
checkpoint-status |  |  | checkpoint | Follow the manufacturer’s installation instructions.
checkpoint-status |  |  | checkpoint | Fix all the screws, nuts and bolts.
checkpoint-status |  |  | checkpoint | Have access panels been provided
checkpoint-status |  |  | checkpoint | Has ductwork been completed
checkpoint-status |  |  | checkpoint | Make sure that the pipe is clean inside and free of debris.
checkpoint-status |  |  | checkpoint | Remove all rubbish.
checkpoint-status |  |  | checkpoint | Store all materials not being used.
checkpoint-status |  |  | checkpoint | Mark alterations and sizes on final locations for records.
checkpoint-status |  |  | checkpoint | Mechanical Services Consultant Inspection
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | Inspection upon Rough ins
checkpoint-status |  |  | checkpoint | Inspection prior to sheeting
checkpoint-status |  |  | checkpoint | Inspection upon progression of every 3 levels or subject to site progression
checkpoint-status |  |  | checkpoint | Inspection of Equipment operation – testing and witness
checkpoint-status |  |  | checkpoint | Installation and Manufacturers Certification provided
checkpoint-status |  |  | checkpoint | Obtain certificate of compliance for installation from appropriate authority.
checkpoint-status |  |  | checkpoint | Fire trip witness test
checkpoint-status |  |  | checkpoint | Operation of essential services
checkpoint-status |  |  | checkpoint | Car-park ventilation via FIP
checkpoint-status |  |  | checkpoint | Shut down of equipment via smoke detector
checkpoint-status |  |  | checkpoint | Witness air flow test for random bade building systems including apartment air conditioning and ventilation
checkpoint-status |  |  | checkpoint | Marking and Labelling
checklist-flat |  |  | checklist | Scope of Works |  |  |  |  | Yes | Scope of Works | 30c6ed8d-24ec-40a3-a8dc-1668c6e7ef9e
checkpoint-status |  |  | checkpoint | Check scope of works & ensure all documents are current revision
checkpoint-status |  |  | checkpoint | Cooling/heating capacity established
checkpoint-status |  |  | checkpoint | Work by others
checkpoint-status |  |  | checkpoint | Check for 3 phase requirements
checkpoint-status |  |  | checkpoint | Coordination with other trades
checklist-flat |  |  | checklist | Ductwork |  |  |  |  | Yes | Ductwork | 331a6320-27b7-4f60-91f1-bea9c5430aae
checkpoint-status |  |  | checkpoint | Ductwork is made to as per design drawings
checkpoint-status |  |  | checkpoint | Duct hangers as per specification
checkpoint-status |  |  | checkpoint | Ductwork installed as per design drawings:
label | 4dbbfd5e-2019-52e0-bd50-72082d9cdb9a |  | note | – check size
label | d1aaaf7b-376d-5be7-bef9-72a49f1c7679 |  | note | – check height
label | d25bc7e2-0605-5bf9-b507-bbbd3b26e93c |  | note | – check position
checkpoint-status |  |  | checkpoint | No physical damage to ductwork
checkpoint-status |  |  | checkpoint | Volume dampers accessible and operative, where required
checkpoint-status |  |  | checkpoint | Access panels fitted where required and of enough size.
checklist-flat |  |  | checklist | Access Panel |  |  |  |  | Yes | Access Panel | 34d3d046-dd30-450a-b8ed-e43bd29621d3
checkpoint-status |  |  | checkpoint | A/P available
checkpoint-status |  |  | checkpoint | A/P located close to equipment
checklist-flat |  |  | checklist | Fan Coil Unit |  |  |  |  | Yes | Fan Coil Unit | 37360c8a-2526-4487-8456-75d96f301b76
checkpoint-status |  |  | checkpoint | Unit model number in accordance with design specification & correctly labelled
checkpoint-status |  |  | checkpoint | Unit installed in accordance with design specifications
checkpoint-status |  |  | checkpoint | Control cable installed in wall and back to FCU
checkpoint-status |  |  | checkpoint | Drain installed in wall and back to FCU
checkpoint-status |  |  | checkpoint | Controller fitted off
checkpoint-status |  |  | checkpoint | Adequate access to unit access panels.
checklist-flat |  |  | checklist | Site Induction |  |  |  |  | Yes | Site Induction | 3c518a2a-f5f1-4904-a946-ac61361bd79b
checkpoint-status |  |  | checkpoint | All works related personnel to be site inducted prior to commencing on site
checklist-flat |  |  | checklist | Suspension and Fixings |  |  |  |  | Yes | Suspension and Fixings | 4082de8f-d252-41c7-8374-138893bd79fc
checkpoint-status |  |  | checkpoint | Hangers to be fixed to the vertical section of the purlin / C section not drilled through bottom
checkpoint-status |  |  | checkpoint | Where hangers to be fixed to the suspended slab:
label | 89095412-0081-59d8-9fee-5e0b60bda41c |  | note | - Check for services location, prior to drilling/fixing
label | 0d31cc94-3dde-5aca-8aca-f29032b18149 |  | note | - Check for post tension cables/ducting location, prior to drilling/fixing
checklist-flat |  |  | checklist | Flexible Duct |  |  |  |  | Yes | Flexible Duct | 42c82a91-72cf-448e-b645-504529d0eaac
checkpoint-status |  |  | checkpoint | Flexible duct spigot damper quadrants accessible and operative
checkpoint-status |  |  | checkpoint | Flexible duct damper left open when installed
checkpoint-status |  |  | checkpoint | Flexible duct installed in accordance with design documentation
checkpoint-status |  |  | checkpoint | Check flexible duct supports
checkpoint-status |  |  | checkpoint | Check flexible duct is not kinked, not squashed, excessive lengths reduced, not over stretched etc.
checklist-flat | 377529b0-de71-4816-a80b-0379c390d4a6 |  | checklist | Defect ITP |  |  |  |  | Yes | Defect ITP | 5664e298-ab61-44eb-b1fd-061605aee174
checkpoint-status | 6c508e36-f560-407f-9c7d-fef4659617e8 |  | checkpoint | Take photos of defect & comment where applicable
text | 0f49d769-4984-5a52-9b7f-28d83238ddb3 |  | textbox | Ceiling Access Panel
text | 17dda71f-1369-51f4-8903-c52c5417ce01 |  | textbox | Duct Access Panel
text | c5145b5f-aea9-5a39-800a-434d45fcad63 |  | textbox | Damper Type
text | d5363b41-9a53-52f5-8578-5c596ec5a83e |  | textbox | Wall type
text | 1b284fc8-d134-5d44-b886-3c2be3dfd39b |  | textbox | Shape
text | fcca32a7-54ef-5800-9d7e-f86848228401 |  | textbox | Angle System
text | 8e259145-4fbc-52a5-8c9b-11bb9c50db0a |  | textbox | Angle Installation
text | 078c27a1-bc8a-5625-ab7e-39f4ed83f3b9 |  | textbox | Mastic
text | a1838033-ff22-5d65-8c3a-c06c2b3906c4 |  | textbox | Breakaway joint
text | 33eea49d-681c-5216-85bf-786c41cfb274 |  | textbox | Ventilation Damper
text | 987be4cf-7c0e-5824-810f-39c8eac017ce |  | textbox | Airflow reading
checklist-flat |  |  | checklist | Louvres, Grilles & Diffusers |  |  |  |  | Yes | Louvres, Grilles & Diffusers | 69b36039-863d-456e-80b6-2e355655b804
checkpoint-status |  |  | checkpoint | Check louvres & grilles have been manufactured to correct opening size and colour
checkpoint-status |  |  | checkpoint | Door grilles to be anodised aluminium finish
checkpoint-status |  |  | checkpoint | Brickwork grilles to be anodised aluminium finish
checkpoint-status |  |  | checkpoint | Grilles and louvres plumb with adequate fixings
checkpoint-status |  |  | checkpoint | Outlets delivered to site in individual protective wrapping Outlets labelled.
checkpoint-status |  |  | checkpoint | Outlets constructed in a neat and tidy manner, no sharp edges, misaligned blades etc.
checkpoint-status |  |  | checkpoint | Outlets as per spec, color as per spec
checkpoint-status |  |  | checkpoint | Outlets same to sample submitted.
checkpoint-status |  |  | checkpoint | Outlet mounted with fully concealed fixings & installation not askew with surroundings
checkpoint-status |  |  | checkpoint | Opposed blade damper fitted to outlet, where specified.
checkpoint-status |  |  | checkpoint | Outlet flanges sufficiently covering penetration and irregularities in surrounds.
checkpoint-status |  |  | checkpoint | Air cushion box fitted.
checkpoint-status |  |  | checkpoint | Internal finishes painted matt black if visible.
checkpoint-status |  |  | checkpoint | Outlet not damaged.
checkpoint-status |  |  | checkpoint | Air cushion box supported as per Specification.
checkpoint-status |  |  | checkpoint | Louvres to be anodised aluminium finish in brickwork
checkpoint-status |  |  | checkpoint | Grilles to match finished colour where installed in wall cladding
checkpoint-status |  |  | checkpoint | Door grilles to be anodised aluminium finish
checklist-flat |  |  | checklist | Building Penetrations |  |  |  |  | Yes | Building Penetrations | 6c8a8e32-8c40-421f-b245-51ac07a8329a
checkpoint-status |  |  | checkpoint | Building penetrations are flashed or sealed as per specification:
checkpoint-status |  |  | checkpoint | Acoustic treatment
checkpoint-status |  |  | checkpoint | Maintaining fire integrity
checkpoint-status |  |  | checkpoint | Airtight sealing of all penetrations
checkpoint-status |  |  | checkpoint | Trimming where required
checklist-flat |  |  | checklist | Site Risk Assessment |  |  |  |  | Yes | Site Risk Assessment | 6ca6c4c9-d3e9-4b7b-973e-bfcfd40f80bb
checkpoint-status |  |  | checkpoint | Assess all risks relating to the site and document accordingly e.g. gas location, power lines, access and the like
checklist-flat |  |  | checklist | Electrical Wiring |  |  |  |  | Yes | Electrical Wiring | 6d90ede2-46fc-4647-8a24-e2d4969c26d7
checkpoint-status |  |  | checkpoint | Installed in accordance with design documentation
checkpoint-status |  |  | checkpoint | Termination of cables in accordance with design specification
checkpoint-status |  |  | checkpoint | Cable sizes & routes confirmed
checkpoint-status |  |  | checkpoint | Fire rating requirements confirmed (MIMS cable)
checkpoint-status |  |  | checkpoint | Adequate cable support confirmed (trays if necessary)
checkpoint-status |  |  | checkpoint | Cable separation confirmed
checkpoint-status |  |  | checkpoint | Cables isolated from sharp edges, pipes and the like.
checkpoint-status |  |  | checkpoint | Conduits used in exposed cable locations.
checkpoint-status |  |  | checkpoint | Location of termination points confirmed
checklist-flat |  |  | checklist | Pipework |  |  |  |  | Yes | Pipework | 6e17acc6-438f-430b-b1f8-68c2fc841ca4
checkpoint-status |  |  | checkpoint | Pipework material as per design specifications
checkpoint-status |  |  | checkpoint | Pipework bends, fittings & supports as per specification
checkpoint-status |  |  | checkpoint | Carry out testing
checkpoint-status |  |  | checkpoint | Check expansion and contraction joints have been fitted
checkpoint-status |  |  | checkpoint | Confirm valves and other fittings supplied and installed in accordance with design documentation
checkpoint-status |  |  | checkpoint | Confirm general maintenance access is available to valve locations.
checklist-flat |  |  | checklist | SWMS |  |  |  |  | Yes | SWMS | 71f9c64e-c216-40f9-9823-ae9a9a02d1a3
checkpoint-status |  |  | checkpoint | All works related personnel have contributed to, read and signed the relevant SWMS prior to commencing on site.
checklist-flat |  |  | checklist | Undercut Doors |  |  |  |  | Yes | Undercut Doors | 78acdadd-9aa9-4c0e-8dca-a097986e54d7
checkpoint-status |  |  | checkpoint | Check doors nominated on workshop drawings have been undercut
checklist-flat |  |  | checklist | Volume Dampers |  |  |  |  | Yes | Volume Dampers | 85697196-24da-4c7d-8d4a-859730e20e6a
checkpoint-status |  |  | checkpoint | Volume dampers fitted in accordance with design documentation & labelled
checkpoint-status |  |  | checkpoint | Damper complete and operational.
checkpoint-status |  |  | checkpoint | Damper construction as per Specification.
checkpoint-status |  |  | checkpoint | Damper of a neat and tidy appearance.
checkpoint-status |  |  | checkpoint | Damper blade seals fitted.
checkpoint-status |  |  | checkpoint | Rattles, fluttering or slack movement.
checkpoint-status |  |  | checkpoint | Linkage connected to all blades.
checkpoint-status |  |  | checkpoint | Open and closed positions clearly and permanently marked on quadrant.
checkpoint-status |  |  | checkpoint | Once installed, damper suitably supported.
checkpoint-status |  |  | checkpoint | Quadrant located in accessible position.
checkpoint-status |  |  | checkpoint | Motorised Dampers, damper motor located in accessible position.
checkpoint-status |  |  | checkpoint | Damper motor rigidly mounted so as to prevent flexing or distortion of ductwork during operation.
checkpoint-status |  |  | checkpoint | Where one damper motor is used for two dampers, use linkages which allow either damper to be adjusted independently.
checklist-flat |  |  | checklist | Condenser |  |  |  |  | Yes | Condenser | 88dcd0cd-2ed4-41ea-b326-313cbb9a3d71
checkpoint-status |  |  | checkpoint | Equipment Schedules verifying qty, make & model
checkpoint-status |  |  | checkpoint | Layout and locations confirmed
checkpoint-status |  |  | checkpoint | Power capacity verified
checklist-flat |  |  | checklist | Work Delays |  |  |  |  | Yes | Work Delays | 89ea4a60-4de7-495c-8682-9dae612296c3
checkpoint-status |  |  | checkpoint | Area accessible and ready for work - Any delays please comment and add photos
checklist-flat |  |  | checklist | SOU - Rough-in |  |  |  |  | Yes | SOU - Rough-in | 9172967e-65e2-4c17-8b7a-7268b35346c0
checkpoint-status |  |  | checkpoint | Pipework rough-in complete
checkpoint-status |  |  | checkpoint | Interconnect control cable rough-in complete
checkpoint-status |  |  | checkpoint | Wall Controller cable rough-in complete
checkpoint-status |  |  | checkpoint | Drain rough-in back to tundish location
checkpoint-status |  |  | checkpoint | Plenum sheetmetal box installed on façade louvre
checkpoint-status |  |  | checkpoint | Plastic ductwork installed, sealed & supported, as per drawings
checkpoint-status |  |  | checkpoint | Exhaust fan installed as per drawings
checkpoint-status |  |  | checkpoint | Exhaust fan flexible duct connected to ductwork
checkpoint-status |  |  | checkpoint | Power cable for FCU rough-in
checkpoint-status |  |  | checkpoint | Power cable for Fan rough-in
checklist-flat |  |  | checklist | Switchboards Installed |  |  |  |  | Yes | Switchboards Installed | 9afca910-7bca-4ad0-aab3-4e0998da45a4
checkpoint-status |  |  | checkpoint | No loose or untidy wiring
checkpoint-status |  |  | checkpoint | Cable covers & control covers are fitted
checkpoint-status |  |  | checkpoint | Interior light is operational & interior is clean
checkpoint-status |  |  | checkpoint | Circuits are identified.
checkpoint-status |  |  | checkpoint | Fuse sizes correspond with design requirements.
checkpoint-status |  |  | checkpoint | Correct labelling including wire numbers.
checklist-flat |  |  | checklist | PAC Unit |  |  |  |  | Yes | PAC Unit | a1489fbe-5c68-4381-8137-00ee48416750
checkpoint-status |  |  | checkpoint | Equipment Schedules verifying qty, make & model
checkpoint-status |  |  | checkpoint | Layout and locations confirmed
checkpoint-status |  |  | checkpoint | Power capacity verified
checklist-flat |  |  | checklist | Turning Vanes |  |  |  |  | Yes | Turning Vanes | a293956b-99fa-416d-a7e4-742908f75831
checkpoint-status |  |  | checkpoint | Turning vanes fitted in accordance with design documentation
checklist-flat |  |  | checklist | Internal Equipment Fit off |  |  |  |  | Yes | Internal Equipment Fit off | aa8525e4-0262-408c-a2de-edf5b40cdce4
checkpoint-status |  |  | checkpoint | Samples of fittings & equipment submitted and approved
checkpoint-status |  |  | checkpoint | Layout and locations confirmed
checkpoint-status |  |  | checkpoint | Pre-construction finishes completed
checkpoint-status |  |  | checkpoint | Power supply termination points available
checklist-flat |  |  | checklist | Fire Dampers |  |  |  |  | Yes | Fire Dampers | bbd31b11-f10c-4be6-bcfc-ccb5eb3d460e
checkpoint-status |  |  | checkpoint | Check rating, location and positioning of dampers
checkpoint-status |  |  | checkpoint | Vessels have correct passes.
checkpoint-status |  |  | checkpoint | Insulation and sheathing in accordance with Specification.
checkpoint-status |  |  | checkpoint | Factory inspection tests and Certificates provided.
checkpoint-status |  |  | checkpoint | Spring mounts supplied, as selected by manufacturer in accordance with Specification.
checkpoint-status |  |  | checkpoint | Electrical Schematic provided and checked by electrical/controls Subcontractors.
checkpoint-status |  |  | checkpoint | Cables installed in a manner that will not obstruct future removal of compressors, motors, etc.
checklist-flat |  |  | checklist | Filters |  |  |  |  | Yes | Filters | c8529aed-e894-4162-89d9-0c842a18276e
checkpoint-status |  |  | checkpoint | Filter frames and channel slides sealed airtight to airflow
checklist-flat |  |  | checklist | Ventilation Equipment |  |  |  |  | Yes | Ventilation Equipment | cb8279a2-3490-4b90-9ce7-bcf784bdac08
checkpoint-status |  |  | checkpoint | Samples of fittings & equipment data approved
checkpoint-status |  |  | checkpoint | Layout and locations confirmed
checkpoint-status |  |  | checkpoint | Insulation & Acoustic criteria determined
checklist-flat |  |  | checklist | Documentation |  |  |  |  | Yes | Documentation | cc15dad2-6a8b-48f6-9081-60dfbe859c67
checkpoint-status |  |  | checkpoint | Ensure current revision of design drawings and specifications
checklist-flat |  |  | checklist | Timer |  |  |  |  | Yes | Timer | cd37a883-398f-4e88-9c7c-a803677ee1fa
checkpoint-status |  |  | checkpoint | Supply and install timer in accordance with design documentation
checkpoint-status |  |  | checkpoint | Position in accordance with design requirements
checklist-flat |  |  | checklist | Fan Installation |  |  |  |  | Yes | Fan Installation | e1dda43f-5908-4f16-b270-f8ed8d549b3d
checkpoint-status |  |  | checkpoint | Ensure equipment is not damaged.
checkpoint-status |  |  | checkpoint | Are drawings on site the latest issue
checkpoint-status |  |  | checkpoint | Identify and install the fan in the right location.
checkpoint-status |  |  | checkpoint | Is the fan labelled
checkpoint-status |  |  | checkpoint | Have anti-vibration mounts been installed
checkpoint-status |  |  | checkpoint | Is the fan securely installed
checkpoint-status |  |  | checkpoint | Is the impeller free to move
checkpoint-status |  |  | checkpoint | Has VSD been installed if required
checkpoint-status |  |  | checkpoint | Have the manufacturer’s installation instructions been followed
checkpoint-status |  |  | checkpoint | Are screws, nuts and bolts fixed
checkpoint-status |  |  | checkpoint | Are access panels provided
checkpoint-status |  |  | checkpoint | Is ductwork including spigots complete
checkpoint-status |  |  | checkpoint | Are ducts clean and free of debris on the inside
checkpoint-status |  |  | checkpoint | Has rubbish been removed
checkpoint-status |  |  | checkpoint | Store all materials that are not being used.
checkpoint-status |  |  | checkpoint | Mark alterations and sizes on final locations for records.
checklist-flat |  |  | checklist | Testing & Commission |  |  |  |  | Yes | Testing & Commission | e3a9093f-c2f8-429b-a489-0c19ac812b1a
checkpoint-status |  |  | checkpoint | Equipment installed and fitted off
checkpoint-status |  |  | checkpoint | All equipment tested & commissioned
checkpoint-status |  |  | checkpoint | Consultant sign off of installation
checklist-flat |  |  | checklist | Insulation |  |  |  |  | Yes | Insulation | e6a3ec35-610b-4036-887c-d5fe95c7d927
checkpoint-status |  |  | checkpoint | Insulation of all pipe work is complete
checkpoint-status |  |  | checkpoint | No internal damage or tear on insulation etc.
checklist-flat |  |  | checklist | SOU - Fit Off |  |  |  |  | Yes | SOU - Fit Off | eb067046-f1bc-46bc-8cb0-019b21c02665
checkpoint-status |  |  | checkpoint | Ductwork connected to range-hood complete
checkpoint-status |  |  | checkpoint | FCU fitted off and in correct position
checkpoint-status |  |  | checkpoint | Pipework, drain and control cables terminated at FCU
checkpoint-status |  |  | checkpoint | Wall controller fitted off as per drawings
checkpoint-status |  |  | checkpoint | Drain terminated into tundish, as per drawings
checkpoint-status |  |  | checkpoint | Exhaust grille installed, as per drawings
checkpoint-status |  |  | checkpoint | Access Panels marked and in correct location.
checklist-flat |  |  | checklist | Amenities Extraction Fans |  |  |  |  | Yes | Amenities Extraction Fans | ed5d92f8-e220-44c1-bf10-1461e96a0608
checkpoint-status |  |  | checkpoint | Disabled fan runs on light sensor and remains on for 10 minutes after light turns off
checklist-flat |  |  | checklist | Final Inspection |  |  |  |  | Yes | Final Inspection | f4547a3f-ae6f-472f-a681-554432147708
checkpoint-status |  |  | checkpoint | Installation and Manufacturers Certification provided
checkpoint-status |  |  | checkpoint | Obtain certificate of compliance for installation from appropriate authority.
checkpoint-status |  |  | checkpoint | Fire trip witness test
checkpoint-status |  |  | checkpoint | Operation of essential services
checkpoint-status |  |  | checkpoint | Car-park ventilation via FIP
checkpoint-status |  |  | checkpoint | Shut down of equipment via smoke detector
checkpoint-status |  |  | checkpoint | Witness air flow test for random bade building systems including apartment air conditioning and ventilation
checklist-flat |  |  | checklist | Shop Drawings |  |  |  |  | Yes | Shop Drawings | f6bdb3a3-f61d-4713-8944-b54769ae47d0
checkpoint-status |  |  | checkpoint | Mechanical Shop drawing submitted and approved
checklist-flat |  |  | checklist | Mech Switchboard Installation |  |  |  |  | Yes | Mech Switchboard Installation | f86fc110-3b7e-4f1d-9e26-ccf86cf9628e
checkpoint-status |  |  | checkpoint | Submains provided
checkpoint-status |  |  | checkpoint | Service cabling installed and ready for termination