## res_ITC 0XX - B80 Concrete Stru
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Concrete Structures | [5 empty] | ITC 0XX - B80 Concrete Structures
checkpoint | 1 - Mix Design
note | REQUIREMENTS / REFERENCE: B80 Cl 3.9.1, B80 Cl 3.9.3
note | ACCEPTANCE CRITERIA:
note | • HP: Concrete mix design submitted at least 4 weeks prior to its use – submit either mix design details as per B80 Cl 3.9.3, or nominate a mix design from the Register of TfNSW Concrete Mixes
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 2 - Formwork Certification (1)
note | REQUIREMENTS / REFERENCE:
note | • B80 Cl 5.2.3
note | • Table B80.11
note | • B80 Cl 5.3
note | ACCEPTANCE CRITERIA:
note | • HP: Formwork documentation and design certification submitted for category B and C formwork components as per below:
note | ○ Category A – Low risk, heights less than 3m (Hold Point not required)
note | ○ Category B – Moderate risk, 3m < heights < 6m (Submit Hold Point prior to placement of reinforcement)
note | ○ Category C – High risk, heights >6m (Submit Hold Point prior to erection of formwork)
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 2 - Formwork Certification (2)
note | ACCEPTANCE CRITERIA:
note | • WP: Production of a test member to demonstrate the suitability of a concrete mix for the works, where required under Clause 3.7, or if specified in Annexure B80/A4 or on the project drawings (if applicable)
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 3 - Formwork Erection
note | REQUIREMENTS / REFERENCE: B80 Cl 7.4
note | ACCEPTANCE CRITERIA:
note | • All foreign matter e.g. dirt, wood chips, concrete, tie wire etc removed prior to placement
note | • Formwork within tolerances specified in Table B80.18
textbox | INSPECTION:
checkpoint | 4 - Reinforcement
note | REQUIREMENTS / REFERENCE:
note | • B80 Cl 6.7.3
note | • B80 Cl 6.4.2
note | • B80 Cl 6.5
note | ACCEPTANCE CRITERIA:
note | • WP: Assembly, lifting and transport of prefabricated reinforcement cages (if applicable)
note | • Lapped bar splices not shown on drawings conform to B80 Clause 6.4.2
note | • Mesh splices must be made so that the two outermost transverse wires of one sheet of fabric overlap the two outermost wires of the sheet being lapped.
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 5 - Delivery (1)
note | REQUIREMENTS / REFERENCE:
note | • B80 Cl 7.5.1
note | • B80 Cl 7.5.2
note | • B80 Cl 4.4.2
note | • B80 Cl 4.4.4
note | • B80 Cl 4.4
note | • B80 Cl 4.6
note | ACCEPTANCE CRITERIA:
note | • HP: Submission of checklists for verifying conformity of the nominated concrete mix, formwork, reinforcement and embedments for precast concrete members cast off site (if applicable)
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 5 - Delivery (2)
note | ACCEPTANCE CRITERIA:
note | • HP: Concrete pour details and pre pour checklist submitted to principal and approved prior to concrete pour taking place (if applicable)
note | • Prior to discharge, concrete agitated on site for a minimum 3min in mixer
note | • Unless a hydration admixture is added, concrete placed & compacted within 1.5 hours from the time of batching
note | • Do not add water to mix 45 min after batching, total quantity of water added does not exceed 9kg/m3
note | • Slump tested and recorded immediately prior to discharge
note | • Concrete temperature at discharge between 5°C and 35°C
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 6 - Placement (1)
note | REQUIREMENTS / REFERENCE: B80 Cl 7.2.3, B80 Cl 7.3
note | ACCEPTANCE CRITERIA:
note | • HP: At least two weeks prior to the first concrete pour, submit to the principal the names of the personnel who will be involved in the concreting works, which of these persons hold a TfNSW Bridgeworks Concreting Grey Card, and corresponding evidence of this.
note | • At least four hours prior to pouring concrete, submit a statement stating that at least half of the involved concreting personnel hold a Grey Card
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 6 - Placement (2)
note | ACCEPTANCE CRITERIA:
note | • Vibration applied to full depth of each layer, extending 100mm into previous layer
note | • Number of vibrators not less than one for each 10m³ placed per hour, with a min of 2. One spare vibrator per 4 vibrators
note | • Vibrator left in place until air bubbles cease breaking the surface
note | • Concrete placed in air temperature range 5°C-38°C
note | • All batches slump tested
note | • Compressive strength tests, 1 set per each 25m3
textbox | INSPECTION:
note | COMMENTS / ATTACHMENTS:
note | • Concrete Pour Docket
note | • Concrete Test
note | • Survey Report (if applicable)
checkpoint | 7 - Formwork Removal and Early Trafficking
note | REQUIREMENTS / REFERENCE:
note | • B80 Cl 9.9
note | • B80 Cl 5.9.2
note | • Table B80.12
note | • B80 Cl 5.10
note | • B80 Cl 8.4.1
note | ACCEPTANCE CRITERIA:
note | • HP: Early trafficking of concrete bridge deck prior to curing (if applicable)
note | • Remove formwork in such a way and such a time as to achieve the specified characteristics:
note | I) Vertical surfaces 15MPa
note | II) Underside of horizontal surfaces 80% of Fc.min(s)
note | • if formwork is stripped prior to curing is complete, apply a curing compound or wet cure the area for the remainder of the curing period
textbox | INSPECTION:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
textbox | Name:
textbox | Date:
note | Signature