## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Concrete Structures |  |  |  |  | Yes | ITC 10 - B80 Concrete Structures | 064a3893-cf60-4535-8053-ed948e7ae7fe
checkpoint-status |  |  | checkpoint | 1 - Mix Design
label | 833423fb-1bc0-568e-bf75-b300717ebb0e |  | note | REQUIREMENTS / REFERENCE: B80 Cl 3.9.1, B80 Cl 3.9.3
label | 1e932faa-fc10-5341-94fb-b95b7b8e17cb |  | note | ACCEPTANCE CRITERIA:
label | 6dec9fb4-8885-5638-8376-04842b5b5ece |  | note | • HP: Concrete mix design submitted at least 4 weeks prior to its use – submit either mix design details as per B80 Cl 3.9.3, or nominate a mix design from the Register of TfNSW Concrete Mixes
text | 10dfaa88-b34e-5634-906f-345f57c56544 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Formwork Certification (1)
label | 9467ca76-21b9-561b-866b-069144b66935 |  | note | REQUIREMENTS / REFERENCE:
label | 95b1d375-8fe0-573a-bb3e-965f54a6709d |  | note | • B80 Cl 5.2.3
label | c357c7cd-b841-543e-adf3-556de4338426 |  | note | • Table B80.11
label | d4f2d4e8-1843-53c3-84da-fc6c4bf149ca |  | note | • B80 Cl 5.3
label | 4a1cf78f-3a2c-58a4-bc1b-b53b27f0d8b1 |  | note | ACCEPTANCE CRITERIA:
label | 1a3f23c5-1f1c-5109-b97c-88b69da51d22 |  | note | • HP: Formwork documentation and design certification submitted for category B and C formwork components as per below:
label | ba829de8-eb8b-514d-955a-3610940d6c22 |  | note | ○ Category A – Low risk, heights less than 3m (Hold Point not required)
label | b0c5bd33-51d3-5698-a7b4-81d37edbafb6 |  | note | ○ Category B – Moderate risk, 3m < heights < 6m (Submit Hold Point prior to placement of reinforcement)
label | 470b0cf2-5e2f-5c93-b021-d2598fe2a16e |  | note | ○ Category C – High risk, heights >6m (Submit Hold Point prior to erection of formwork)
text | ea133fa8-cd16-5d2a-be77-23487921e94e |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Formwork Certification (2)
label | 7046d1d4-829d-56eb-8f08-997e6eaee203 |  | note | ACCEPTANCE CRITERIA:
label | 47438357-a38c-59f6-b37c-be53c29c0bd7 |  | note | • WP: Production of a test member to demonstrate the suitability of a concrete mix for the works, where required under Clause 3.7, or if specified in Annexure B80/A4 or on the project drawings (if applicable)
text | 53ff92ff-961e-510a-a66d-eb1c6bd1a0d7 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Formwork Erection
label | b3ba4f05-1804-568b-beb3-ae606267a5cf |  | note | REQUIREMENTS / REFERENCE: B80 Cl 7.4
label | 2d2873fa-4106-58e4-a732-c724259ca2a9 |  | note | ACCEPTANCE CRITERIA:
label | 982251c6-dfe9-5b19-8818-c967a62b8aae |  | note | • All foreign matter e.g. dirt, wood chips, concrete, tie wire etc removed prior to placement
label | a95a769e-5c5d-5dc5-9537-12478b2434ea |  | note | • Formwork within tolerances specified in Table B80.18
text | 9d97a8f8-98cd-5755-96b9-42cec7527968 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 4 - Reinforcement
label | 9246d9bd-0a02-5a0d-9e91-9c9628d03eef |  | note | REQUIREMENTS / REFERENCE:
label | 046f45a4-42ab-5cb9-b296-8f0e6c1a6fd2 |  | note | • B80 Cl 6.7.3
label | 37b48c7d-4fea-5443-ad96-c772a2e8b2d5 |  | note | • B80 Cl 6.4.2
label | cc62d886-88f9-5ee9-a26a-115facdd40fb |  | note | • B80 Cl 6.5
label | 1e4a34fc-a035-50cd-a514-7606063eea8b |  | note | ACCEPTANCE CRITERIA:
label | df03dbf9-19a8-521e-a858-e52ae8080256 |  | note | • WP: Assembly, lifting and transport of prefabricated reinforcement cages (if applicable)
label | f70a45a8-7e9a-5cf4-94eb-12ac52c9807d |  | note | • Lapped bar splices not shown on drawings conform to B80 Clause 6.4.2
label | 7bc3f06e-9c31-52ea-b615-f01a6ebd071a |  | note | • Mesh splices must be made so that the two outermost transverse wires of one sheet of fabric overlap the two outermost wires of the sheet being lapped.
text | bec662cd-2be8-503c-bd3e-823f38674d40 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Delivery (1)
label | 32f84c20-ae53-5ba0-a3fe-647706a8055e |  | note | REQUIREMENTS / REFERENCE:
label | 9a0faa52-56a9-5e17-979a-463257801bc3 |  | note | • B80 Cl 7.5.1
label | 6e6def9b-4851-5f82-9752-29e4ed0fdf5a |  | note | • B80 Cl 7.5.2
label | 50086772-78fe-5328-b7ae-ef0d5517f2b1 |  | note | • B80 Cl 4.4.2
label | 0fd127fa-101d-50b9-94b8-8902ffa9b8ee |  | note | • B80 Cl 4.4.4
label | 993b493d-73a1-5e14-bb50-1e6975993f94 |  | note | • B80 Cl 4.4
label | bf233944-0aa2-525c-80f8-d8a23fbc3592 |  | note | • B80 Cl 4.6
label | 1fc95b95-5042-54d6-a074-4eceedf99124 |  | note | ACCEPTANCE CRITERIA:
label | c7cb1ec1-660a-5f3e-a138-24bb95a0fd7e |  | note | • HP: Submission of checklists for verifying conformity of the nominated concrete mix, formwork, reinforcement and embedments for precast concrete members cast off site (if applicable)
text | 0c98adae-056b-5bc3-92e8-40f8d225716f |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Delivery (2)
label | d4035557-0420-53f6-ae06-b307572e51a3 |  | note | ACCEPTANCE CRITERIA:
label | df26ed6b-2bb6-511a-b47e-8bd781f8b3ca |  | note | • HP: Concrete pour details and pre pour checklist submitted to principal and approved prior to concrete pour taking place (if applicable)
label | 53126083-5e68-582f-ba3a-e435ec6ee287 |  | note | • Prior to discharge, concrete agitated on site for a minimum 3min in mixer
label | efdd3df0-3613-5023-a1f2-e51475774df3 |  | note | • Unless a hydration admixture is added, concrete placed & compacted within 1.5 hours from the time of batching
label | 0be7a891-f794-525e-af09-74ee58038aaf |  | note | • Do not add water to mix 45 min after batching, total quantity of water added does not exceed 9kg/m3
label | 3380f53b-508d-5458-8a79-73ee925852bd |  | note | • Slump tested and recorded immediately prior to discharge
label | aacf5a61-d179-5222-89c9-8876a244a3a5 |  | note | • Concrete temperature at discharge between 5°C and 35°C
text | ab51f7c7-a89d-504d-b2c9-2be2545e001a |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 - Placement (1)
label | 925f4468-f394-5689-8d8d-7099ceb9b09e |  | note | REQUIREMENTS / REFERENCE: B80 Cl 7.2.3, B80 Cl 7.3
label | 2a74b8b8-e1aa-5408-bcdf-33230909ae44 |  | note | ACCEPTANCE CRITERIA:
label | 85ebbe78-d539-579a-957a-d2c5c7580bd3 |  | note | • HP: At least two weeks prior to the first concrete pour, submit to the principal the names of the personnel who will be involved in the concreting works, which of these persons hold a TfNSW Bridgeworks Concreting Grey Card, and corresponding evidence of this.
label | 1ad7d2e0-0726-5c6b-8052-7a708339b037 |  | note | • At least four hours prior to pouring concrete, submit a statement stating that at least half of the involved concreting personnel hold a Grey Card
text | 5657fc77-cae1-59c2-8d8c-b498163610b2 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 - Placement (2)
label | a8616888-2621-53bf-b9ba-ba28a6a2f1d4 |  | note | ACCEPTANCE CRITERIA:
label | 4e2de0e1-a50d-5680-be83-6781dbf72f6e |  | note | • Vibration applied to full depth of each layer, extending 100mm into previous layer
label | 23f159a5-878e-5a01-ba17-7a5080d1c07a |  | note | • Number of vibrators not less than one for each 10m³ placed per hour, with a min of 2. One spare vibrator per 4 vibrators
label | e7c2c698-7c75-573f-a448-6dbbe76ff52b |  | note | • Vibrator left in place until air bubbles cease breaking the surface
label | aa14cc0b-ba30-55cc-8305-feaebae4174d |  | note | • Concrete placed in air temperature range 5°C-38°C
label | 748b3057-43a5-5624-a956-f2fa82fa2e03 |  | note | • All batches slump tested
label | 592c179a-4604-5eae-8bec-e3457ca8b176 |  | note | • Compressive strength tests, 1 set per each 25m3
text | e6f9c2ed-ae31-523f-a73a-c5c1e7e28f2b |  | textbox | INSPECTION:
label | e196325b-d66d-5092-be8e-bf2a3d1f7248 |  | note | COMMENTS / ATTACHMENTS:
label | 3fa3140d-e5e3-5a18-bb9e-453568e1b426 |  | note | • Concrete Pour Docket
label | 81f80b0c-c4ea-5610-a783-18d2bcf63110 |  | note | • Concrete Test
label | 6006fcd4-8d3e-5b06-a2bd-5d330ce7de60 |  | note | • Survey Report (if applicable)
checkpoint-status |  |  | checkpoint | 7 - Formwork Removal and Early Trafficking
label | b43207d7-dade-55ff-9763-1ce138498b49 |  | note | REQUIREMENTS / REFERENCE:
label | c4e56ae4-3cf0-513e-9c4d-8a46abe1542e |  | note | • B80 Cl 9.9
label | 06ba3989-9251-5f17-ac88-c88bd9512567 |  | note | • B80 Cl 5.9.2
label | 2ff1a79a-b5f8-58bf-8463-bb3f29968ea9 |  | note | • Table B80.12
label | e3b1a137-acbc-529a-9c5a-3c88d7ad7c95 |  | note | • B80 Cl 5.10
label | a6dcf712-973d-561f-9303-b350583b38d2 |  | note | • B80 Cl 8.4.1
label | fa624813-b490-5438-a6cf-b8de5ba732a4 |  | note | ACCEPTANCE CRITERIA:
label | d13d2695-1fe4-5903-87d6-ad068976d1d5 |  | note | • HP: Early trafficking of concrete bridge deck prior to curing (if applicable)
label | 30d259dd-e941-5814-bf7c-2c66f4d1d514 |  | note | • Remove formwork in such a way and such a time as to achieve the specified characteristics:
label | c145a73e-dd6c-5991-a172-8e0f7f5c20e0 |  | note | I) Vertical surfaces 15MPa
label | da6da6fe-301c-5a0a-b40f-01c625484a1e |  | note | II) Underside of horizontal surfaces 80% of Fc.min(s)
label | 2c3840a6-2c2d-59a2-b7a4-9600fb1efa10 |  | note | • if formwork is stripped prior to curing is complete, apply a curing compound or wet cure the area for the remainder of the curing period
text | f7315d80-417e-565e-a0fc-6aa978e2c6af |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | cd36818e-be21-5d27-8d27-edeb2c1754ec |  | textbox | Name:
text | 2a565706-22f0-52aa-b9b0-e5c4503f7e78 |  | textbox | Date:
label | 1e703364-0afa-50b4-bb4d-d940174f6406 |  | note | Signature
checklist-flat |  |  | checklist | Heavy Duty Dense Graded Asphalt (AC20 and AC14) |  |  |  |  | Yes | ITC 07 - R116 Heavy Duty Dense Graded Asphalt (AC20 and AC14) | 09b15138-22fc-4c87-b6e6-b32c9c9b0e97
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | 607a6ff9-acfe-5554-82c3-f1076a6c5346 |  | note | REQUIREMENTS / REFERENCE: R116 Cl 3
label | 95fae24d-4d5f-50ff-b6ed-7e9adce0577c |  | note | ACCEPTANCE CRITERIA:
label | 9a5f8537-5528-5d50-8426-4aad7c1780c7 |  | note | • Existing surface has been cleaned ahead of asphalting works taking place
label | bcc87ba0-5c38-5416-89ed-ec0463b06150 |  | note | • Existing surface has tack coat / spray seal prepared as per Project Drawings and as agreed with Client
text | b02d7eb3-541a-517c-8b5b-da9ef876d969 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Materials (1)
label | 865920fe-9e65-5d02-a424-b7282b2483a4 |  | note | REQUIREMENTS / REFERENCE: R116 Cl 2.3.5, 3.5.1
label | 4f8bdd71-e239-521a-98df-4db72869d04b |  | note | ACCEPTANCE CRITERIA:
label | c70103cd-c6ca-5738-b7d6-8e74370dcee9 |  | note | • HP: Submission of nominated mix design details for consideration by the Client, at least 7 working days before the nominated mix(es) is (are) proposed to be placed
text | 0ddf6537-4f2c-5cd7-8a06-037c2b267c53 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Materials (2)
label | f94c166b-5e8e-5684-b8a1-9630444e892a |  | note | REQUIREMENTS / REFERENCE: R116 Cl 2.3.5, 3.5.1
label | 6d96ab5f-afa3-5102-9f0b-fdec6110f706 |  | note | ACCEPTANCE CRITERIA:
label | 283de8c4-795a-544d-a61e-0ff8a73e1c9a |  | note | • HP: Commencement of paving using the nominated mix(es) including trial section. Submit details of min. temperature asphalt will be delivered to the paver, min. temperature initial compaction of the asphalt can still commence, and method of temperature measurement
text | 35497b69-1e6b-5b79-afa7-9285bdebe453 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Pre-planning and initial works (1)
label | 0bfac480-3b8f-5d05-ac9c-2478f9df9d23 |  | note | REQUIREMENTS / REFERENCE: R116 Cl 3.6.3, Cl 3.8.6
label | a14c09e9-2962-5a22-8bb1-b2e9a6e3e90c |  | note | ACCEPTANCE CRITERIA:
label | 69c8576f-2f45-5d7c-8b4f-5884de3430d3 |  | note | • HP: Placing of asphalt in nonconforming layer thicknesses, for corrective courses and tie-ins to an existing pavement (if applicable)
text | 88f8f4ee-7e8f-53d8-84d2-316dcc7b534e |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Pre-planning and initial works (2)
label | 46540fc9-bcf4-543b-9114-8f03a732b7ff |  | note | REQUIREMENTS / REFERENCE: R116 Cl 3.6.3, Cl 3.8.6
label | 66626a64-3c8b-5344-ae95-372807fa7d61 |  | note | ACCEPTANCE CRITERIA:
label | 53e4df12-fdef-5bff-a98d-3f39f22609a3 |  | note | • HP: Submission of verification checklists and test results from trial section
text | d7ef62ec-60f7-5a25-8aba-abd06bedd4ff |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Non-conformances (1)
label | 2592f32f-a28b-50e0-9a46-253680b373d2 |  | note | REQUIREMENTS / REFERENCE: R116 Cl 5.8.5, Annexure B2.3
label | 43b4f88a-c807-588c-b0a9-51e68b84419a |  | note | ACCEPTANCE CRITERIA:
label | 907f8c07-81be-5adb-aa2e-c1fbe809d680 |  | note | • HP: Rectification or replacement of a nonconforming lot. Submission of Nonconformity Report and details of proposal for rectification or replacement of the Lot (if applicable)
text | 2f29c30f-3dd3-500d-a4c3-12b09bb60d92 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Non-conformances (2)
label | 5d2b9b62-4c1c-507a-a5b0-822301432437 |  | note | REQUIREMENTS / REFERENCE: R116 Cl 5.8.5, Annexure B2.3
label | 0c6e5056-3e7f-5b62-b3f8-926bf9729eff |  | note | ACCEPTANCE CRITERIA:
label | 7e0d7d71-b6b3-5299-b93f-fdb18a3c0bc7 |  | note | • HP: Where Tensile Strength Ratio (TSR) has been found to be < 70% and air voids in the laboratory compacted mix nonconforming, HP for further production of the nominated mix (if applicable)
text | b1965777-c423-53c9-a76c-c767e3279ddb |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Changes to approved mix
label | 1c615dc0-f7ca-525f-a0d5-cf74e505ae2b |  | note | REQUIREMENTS / REFERENCE: R116 Annexure F
label | 661d35b5-a227-5c8a-9550-15b34506ec47 |  | note | ACCEPTANCE CRITERIA:
label | e433bd3f-9aba-53c5-b139-9209f01b30e6 |  | note | • HP: Progression to a higher RAP Approval Level (if applicable)
text | 17707e17-af4e-5632-89db-41f7e9a85f40 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 - Conformance of works
label | 130689cb-ac2b-502c-9571-3d6ec5496e21 |  | note | REQUIREMENTS / REFERENCE: R116 Annexure A, Cl 5.5.1
label | f4d977ca-a40e-574c-b12c-8e8cb9ff3720 |  | note | ACCEPTANCE CRITERIA:
label | c5b94a73-6955-5679-8282-a7772c641ec3 |  | note | • Survey Report: Conformance heights as per below requirements (Table R116.11)
label | 8e77b4d0-bf32-5f42-ae86-4b22906ba526 |  | note | – o Wearing course: -0mm / +10mm
label | e88aedd9-4374-570c-a18c-b51d54097415 |  | note | – o Top Intermediate course: -5mm / +10mm
label | 56e3e188-636d-5a0c-9ffb-5217d2b3c79a |  | note | – o Other Intermediate courses: -10mm / +10mm
label | 00f18aef-3baa-5a80-ab4f-46e92c46a6d0 |  | note | – o Corrective course: -15mm / +10mm
label | a565d71d-59a1-5119-9cee-a43ac08bfa4e |  | note | – o Note: Minus (-) is below design level and plus (+) is above design level.
label | c19ae6e1-f88f-547a-8484-a743cdf4083a |  | note | • Test Reports: Testing for Resilient Modulus and Wheel Tracking Depth (as measure of deformation resistance) for each asphalt mix
label | 15cfcebf-9e2e-5d77-bb99-470e6cf66621 |  | note | • Test Reports: Testing for Ride Quality for finished pavement / wearing course only
label | 9ab9247c-04a1-5baf-a7d5-19edd85293d6 |  | note | • Lot Package: Submission of Lot Package provided by asphalt subcontractor
text | 2fd67b49-2d42-5ef6-a346-a65808911132 |  | textbox | INSPECTION:
label | 16eef36c-6905-5390-9774-8262b3391d9e |  | note | COMMENTS / ATTACHMENTS:
label | 257abe0a-2486-5aef-af5b-8f4291e20aac |  | note | • Survey Report(s)
label | 36d06407-1313-5e6d-8f17-71c7cff0214c |  | note | • Test Report(s)
label | b336884e-965e-57f6-b106-e1fcd998fce1 |  | note | • Lot Package
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | b4f8811c-f900-535c-90ae-3f357188b975 |  | textbox | Name:
text | 7d39cd2b-31f9-5e09-8f76-ebe0a15224fb |  | textbox | Date:
label | 3ee6e4c0-152d-5293-9bbe-ddda48a495b0 |  | note | Signature
checklist-flat |  |  | checklist | G040 – Clearing and Grubbing |  |  |  |  | Yes | G040 – Clearing and Grubbing | 149b9ee5-f76f-4297-b4d2-434a077aac90
checkpoint-status |  |  | checkpoint | Clause 2.4 - Clearing any area of work
label | 64f5ff7e-3e14-58a2-bfbb-618aea725b0e |  | note | Submit Clearing and Grubbing Plan (Annexure G40/D) and report on the presence of weeds and unsound trees together with written notice that limits of clearing and areas of weed infestation identified in the ecologist report (Clause 2.4(a)) are marked, at least 7 days before starting any clearing
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | G010 – Traffic Management |  |  |  |  | Yes | G010 – Traffic Management | 22347f46-351e-42f6-acf1-cf9212c9992f
checkpoint-status |  |  | checkpoint | Clause 1.7.4 - Any work controlling and directing traffic on the site
label | 0d7fd83f-0ce1-5c77-a96f-d5e4067180ef |  | note | Submit names of proposed Traffic Controllers and their qualification details such as registration numbers and expiry dates
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 2.2.1 - Submission of application for ROL
label | dc3a9960-df6a-5355-9f43-a20a188984c1 |  | note | At least 20 working days prior to the proposed date of submission of application for the ROL (on any shorter period as agreed) submit your Traffic Management Plan
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 2.4.1 - Any activities which will affect traffic conditions for a particular section of the site
label | 724a1e09-fc39-5a59-9042-2ed27f2ce0c6 |  | note | If not previously submitted as part of the TMP or where a TMP is not required, at least 3 working days prior to its proposed use, submit your Traffic Control Plan. Include the VMP and PMP, and copies of any associated ROL and SZA obtained and any associated Road Safety / Traffic Control Plan Audit report
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.4.2 - Implementation of traffic switch or opening of temporary roadway and detour of traffic
label | 20d7633e-d430-50a1-97e0-05847281506b |  | note | At least 1 day prior of the intended opening date, notify the principal in writing that the traffic control measures are conforming and ready for their inspection
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | Fencing (R201) |  |  |  |  | Yes | ITC 11 - R201 Fencing | 23b51527-f7ac-40b7-8926-1c58da15041d
checkpoint-status |  |  | checkpoint | 1 - Material approvals and preparation works
label | 47839c3d-2229-5f3d-94f7-fe9ed946cd23 |  | note | REQUIREMENTS / REFERENCE:
label | 8dbaa4f5-1ffe-5413-a056-c8272a1bf85c |  | note | – WHSMP
label | 64f604e2-f0f7-5c51-9ed0-1e9f3e800529 |  | note | – Design DWGs
label | 73d841f7-5f54-5e6b-9dc2-be3451077c57 |  | note | – R201 Cl 3.11
label | f9c45eef-7fdc-5c80-b4f2-2b49fdc01522 |  | note | ACCEPTANCE CRITERIA:
label | 86cd7de1-887d-55cc-80f9-8064c91fd6f7 |  | note | • Materials approved for use by the Client
label | 66a9dd17-4f5b-5bdd-921f-9fb2816be01d |  | note | • Locations of fence and fenceposts set out by surveyor and as per drawing
label | b9416eef-e882-5368-943a-620b6fa44bfa |  | note | • HP: Submission of Certificate of Compliance for materials and components
text | e6fda2ec-2b43-5bc5-808e-420cfaaa2edd |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Pre-planning of works
label | 92ba0299-c8d7-5dc1-83e5-f3ebdf0379fe |  | note | REQUIREMENTS / REFERENCE: R201 Cl 4.1
label | b2c7fbae-ac2d-5449-bec5-9edb5652318f |  | note | ACCEPTANCE CRITERIA:
label | 3417fc49-5939-5aa8-ab4d-c1f2af795abb |  | note | • HP: Submission of proposed connection arrangement of new fencing to existing fencing
text | bf933176-0cee-51eb-b380-8f0cb6efe869 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Construction works
label | 755f0a77-4c85-5203-a30e-a1b402c1ff53 |  | note | REQUIREMENTS / REFERENCE: R201 Cl 4.4.2
label | 5ba059f3-cfdf-598c-ac62-dde5038f02de |  | note | ACCEPTANCE CRITERIA:
label | 002c065a-ad14-53bb-9dfa-e537bf6290e5 |  | note | • HP: Removal of trees with trunk diameter exceeding 100mm (if required)
label | 44089054-fb05-50b5-bcb1-3308c5855f4a |  | note | • Fenceposts, panels and connections installed as per drawings and as agreed on site
text | 8ed6da09-240b-58cb-b828-579ee8205d4d |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | ce399267-4bb9-53a9-b859-e099393eca34 |  | textbox | Name:
text | 72b7423a-c234-5b71-aca8-106a5ae5ef0a |  | textbox | Date:
label | de044c3c-b186-54e7-bc61-e6b391c6a324 |  | note | Signature
checklist-flat |  |  | checklist | Linemarking / Pavement Marking (R145) |  |  |  |  | Yes | ITC 09.2 - R145 Linemarking | 31baf3dc-9159-45d3-9208-19f77d1bfea5
checkpoint-status |  |  | checkpoint | 1 - Material approvals and preparation works
label | e392c6b2-05d7-5c06-b393-7036185a695b |  | note | REQUIREMENTS / REFERENCE:
label | 1029f140-184c-5a52-9fdd-d886d9c70c2c |  | note | – WHSMP
label | 6401831d-240c-51b6-ae75-38a00ed65f97 |  | note | – Design DWGs
label | 9dfb1f78-597c-59c2-b60b-044f2b95fdd1 |  | note | – R145 Cl 3.2.4
label | 7d66c51b-76a5-56b0-b63e-9227d15d825b |  | note | ACCEPTANCE CRITERIA:
label | b83afcd6-d86c-5e27-ba56-ccba4768af56 |  | note | • Materials approved for use by the Client
label | 38f45bd4-8ebd-5ee7-ab84-92122b8ebc13 |  | note | • Locations of linemarking set out by surveyor and as per drawing
label | 6eba2a5b-84ea-52ab-a992-578f33c99a7a |  | note | • HP: Application of pavement markings – Notify the Client that set out of the pavement markings is complete ahead of the works taking place
text | 99b594ee-dff9-504b-9a87-3b82601664b3 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Construction works
label | 73e42528-21ac-545d-a9e2-b3e572fd8f6f |  | note | REQUIREMENTS / REFERENCE: R145 Cl 3.1.2, R145 Cl 7
label | f576fdbe-5517-5be5-9c75-2abebfadedda |  | note | ACCEPTANCE CRITERIA:
label | bd17476e-8200-5c3c-bf90-a4d87798fcc9 |  | note | • Surface and surrounding area is dry and free of dirt, gravel and other loose or foreign material
label | ba16b9b1-4980-5af1-be71-40b33cbf5d28 |  | note | • Pavement markings placed as per construction drawings and as per conformity requirements in R145 Clause 7.
text | 8e074d4b-ce64-5cd9-819c-33ae3075c605 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | e12d2a6e-f638-513c-8950-f9b488c5ff90 |  | textbox | Name:
text | 65658faf-9cd3-5116-82b0-cbb332bd0049 |  | textbox | Date:
label | 5458330a-f1e0-526c-9400-4d20a9cc61b7 |  | note | Signature
checklist-flat |  |  | checklist | Subgrade (R44) |  |  |  |  | Yes | ITC 08 - R44 Subgrade | 34204115-fad0-4e10-8af3-6e3b0320aa38
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | 4a131b63-26ed-57f2-a6a4-a4bd6090be51 |  | note | REQUIREMENTS / REFERENCE: WHSMP, Design DWGs
label | 375285f1-2fc6-50e6-b93b-d46148646e7d |  | note | ACCEPTANCE CRITERIA:
label | aaa94960-30df-50ee-ba47-595f61172b39 |  | note | • Contact DBYD and complete excavation permit
label | 8b0a0ed3-43be-5087-a047-dc9c70d5996b |  | note | • Extent of works set out with survey pegs
text | 161af989-918d-5426-b707-7cdbf0c247e8 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Initial works (1)
label | ab938a4f-1d9a-59df-a12a-bac481637349 |  | note | REQUIREMENTS / REFERENCE:
label | 2737b367-e721-5717-82fd-2848eb0b003d |  | note | • R44 Cl 2.4
label | 95847e84-4534-582c-bf89-751db2b9fa28 |  | note | • R44 Cl 3.2
label | 7d8a63c4-f67c-5600-a005-b1df7776c31d |  | note | • R44 Cl 3.4
label | 3303f05c-6379-5fc6-a21b-69b1165f9fcb |  | note | ACCEPTANCE CRITERIA:
label | 05778440-da65-5bf6-b27b-122afb9c1da4 |  | note | • HP: Inspection after removal of unsuitable material and prior to backfilling (if applicable)
text | 14238537-d8c8-594e-b233-d217fa3a2c7c |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Initial works (2)
label | ca9f4818-5019-531e-a46c-d87c6fdf8131 |  | note | REQUIREMENTS / REFERENCE:
label | 391c1433-e055-50e3-94fe-ad7e465967aa |  | note | • R44 Cl 2.4
label | 3d983ab0-55d4-54da-8c7c-83455f8688f0 |  | note | • R44 Cl 3.2
label | 6571b50f-30a6-50e2-9b8e-dd8a9a3ee777 |  | note | • R44 Cl 3.4
label | 4c7f5941-7350-547e-8e19-8ac578bb4976 |  | note | ACCEPTANCE CRITERIA:
label | f6c4b55b-b8e7-5e20-b8bf-58ed5860057c |  | note | • HP (Filling): Presentation of each Lot of embankment foundation and submission of survey, notification of completion of clearing and topsoil removal, and CBR and PI results if required (if applicable)
text | cc76537d-904e-54c8-a3e6-11afd952d8e3 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Initial works (3)
label | 5bc62ad5-57de-54be-8f6f-a323e81cb80a |  | note | REQUIREMENTS / REFERENCE:
label | a11a3596-3144-5c74-9273-8597a4e8dc00 |  | note | • R44 Cl 2.4
label | b1456f70-cbf3-5a2e-a60b-d1bb5f08efea |  | note | • R44 Cl 3.2
label | 525aeb1f-1d37-5069-a309-078f51c152ae |  | note | • R44 Cl 3.4
label | 99f519a9-0ead-5a2c-bfdc-d5b0f216678e |  | note | ACCEPTANCE CRITERIA:
label | f5c91e07-a116-5eaa-be71-fef6e6f8f1f0 |  | note | • HP (Cutting): Presentation of each Lot of floor of cuttings and notification of completion of excavation, and CBR and PI results of material in floor of cutting (if applicable)
text | 5dce45cf-4456-57ea-8c00-565a6f74ed56 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Materials
label | edc95322-7496-557b-9cb0-a1b23eeca954 |  | note | REQUIREMENTS / REFERENCE: R44 Cl 6.1.1
label | 4aafd424-9164-5c27-be37-29d4e73e5350 |  | note | ACCEPTANCE CRITERIA:
label | d207c9b8-adcd-5193-8125-429c5fcba6a3 |  | note | • HP: Submission of details of location, quantities, type and verification of conformity of Upper Zone Material (including selected Material). If imported, verification that all possible onsite sources of material have been exhausted (if applicable)
text | 3c5bb55f-119b-5470-9965-04681d9f9842 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Construction works (1)
label | 03d567f7-c45d-587f-862d-7d5e3234b9ab |  | note | REQUIREMENTS / REFERENCE:
label | 3021e2f1-ea53-57d7-aceb-8f7b855e325f |  | note | • R44 Cl 7.6.1, R44 Cl 7.6.2
label | 7b495218-5e2e-5618-9dac-f4814f3c826f |  | note | • R44 Annexure A2.2, R44 Cl 7.3.6, Table R44.10, Table R44.11
label | d002ac13-d9ad-595a-a47c-bc2910558852 |  | note | ACCEPTANCE CRITERIA:
label | be54d4fd-c3d0-552b-afcb-51573162a1f5 |  | note | • T117, T109 Test Results: CBR ≥ 8 and PI ≤ 25 respectively
label | cac973d7-5beb-5c37-860c-55e0822eb120 |  | note | • T166 Test Result: Relative compaction ≥ 98%
label | 9be75b4a-5e6b-558f-a9dc-4fa785e70de9 |  | note | • T162 Test Result: 60% ≤ Moisture content ≤ 90%
label | 7a68e4da-5d1e-5059-8a00-6eeffe195268 |  | note | • Survey Report: Finished surface within tolerance of +0mm to -40mm of design
text | f6b14b9a-207d-543d-9325-f513dd699a77 |  | textbox | INSPECTION:
label | 1d5dbf9a-6bec-5c18-9665-6d888be6231f |  | note | COMMENTS / ATTACHMENTS:
label | 3e9c8c34-28e0-5c8f-bab1-e8c81f545b50 |  | note | • Test Reports
label | fcebd316-42f0-592e-afa3-20a10d25b0f4 |  | note | • Survey Report
checkpoint-status |  |  | checkpoint | 4 - Construction works (2)
label | a6fbdf50-b21e-5174-8249-658a63a2bfef |  | note | ACCEPTANCE CRITERIA:
label | ce9618f6-5a36-5232-a6b0-66c6de782e9b |  | note | • WP: Proof rolling of embankment layers and other surfaces within 1.5m of the underside of the Selected Material Zone
text | 61aee842-114b-5536-bc00-cd7c1f1186ca |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Construction works (3)
label | 366ced98-1fba-5ddc-a8e2-fd516cf94f22 |  | note | ACCEPTANCE CRITERIA:
label | d478cb55-d44f-5173-a306-cc23df575048 |  | note | • WP: Benkelman Beam testing of Selected Material Zone (top and underside of SMZ layer)
text | 2af8fb69-ed6a-5ce9-a733-1928a4cc9be0 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Conformity of Completed Works
label | fa799d84-fe11-537f-9a01-1f5e5dda939a |  | note | REQUIREMENTS / REFERENCE: R44 Cl 7.6.2
label | 2aeeb737-ad79-571c-9b87-f9bc43f5081b |  | note | ACCEPTANCE CRITERIA:
label | 2fd3cd76-5995-5a24-a860-878a1997c4cc |  | note | • HP: Submission of deflection test results, finished surface levels and verification of conformity of each lot of Subgrade placed (submission of lot package with beam test, proof roll, test and survey as required)
text | d9af939c-ae55-583a-9c47-97d51c6cedb0 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | 53148c3b-a3e0-57be-84a8-aadf9c2c93f6 |  | textbox | Name:
text | 23c1bdd0-61c6-55f5-b308-9886bf084311 |  | textbox | Date:
label | 4afc3a4b-8128-56bf-954a-d50aa03838c0 |  | note | Signature
checklist-flat |  |  | checklist | G036 – Environmental Protection |  |  |  |  | Yes | G036 – Environmental Protection | 4aa61759-2cbc-4e45-9f01-210b2439237a
checkpoint-status |  |  | checkpoint | Clause 3.1 - Commencement of work not previously addressed by CEMS and CEMP documents and authorised by earlier Hold Point release
label | 0d615322-ff72-572d-a546-e5e515877a93 |  | note | Submission of CEMP and selected CEMS documents
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.2.2 - Commencement of any activity requiring an approval, licence and/or permit from an appropriate authority
label | a79054d1-a0da-5e0d-9a88-d9df813a29f5 |  | note | At least 15 working days prior to the activity, provide to the principal evidence of receipt of the environmental approval, licence and/or permit from the relevant authority
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.2.4 - Commencement of activities requiring an EWMS
label | 0f042793-a437-5959-b86b-2c10369f37c0 |  | note | Submission of an EWMS at least 15 working days prior to the proposed commencement of the activities requiring it
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.7.4.4 - Commencement of work not previously addressed by CSES documents and authorised by earlier Hold Point release
label | 2e68cbb2-1808-5154-a47a-4313ecc5e8a7 |  | note | At least 20 working days prior to the proposed commencement of the stage of work, submit the CCS (Community Communications Strategy) and associated sub-plans
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.7.4.4 - Commencement of work not previously addressed by engagement documents and authorised by earlier Hold Point release
label | 5c815578-7318-5d7b-b540-ba462d0788c7 |  | note | At least 20 working days plus (refer table) prior to the proposed commencement of the stage of work, submit the CCS (Community Communications Strategy) and associated sub-plans
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.10 - Verification that the failure has been rectified, and details of the measures implemented to prevent recurrence
label | c2cafc76-71de-5803-b6b0-64480e3f6f5d |  | note | In the event of any environmental nonconformities, verify that the failure has been rectified, and provide details of the measures implemented to prevent recurrence
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.2.4 - Activities within the vicinity of actual or suspected contaminated land
label | bc9bf005-24b1-5129-8d9f-5a9f73178da9 |  | note | Where the Remediation Action Plan is to be prepared by the contractor, at least 5 working days prior, submit your Remediation Action Plan and relevant procedures
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.6 - Commencement of work outside of normal working hours
label | b3b71100-abb4-5bf4-ad1e-6bcd14de7c1e |  | note | At least 5 working days prior, provide the principal with a copy of the Out of Hours Work Assessment
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.7 - Commencement of blasting, pile driving, excavation by hammering or ripping, dynamic compaction, demolition operations, or any other activity which may cause damage through vibration or airblast
label | 4ee56c59-b156-5727-9a38-06ba0706be07 |  | note | Building Condition Inspection Reports and Vibration and Airblast Management Sub Plan
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.7.1 - Commencement of building condition inspections
label | d685d1be-1966-578e-9f0b-6417334c9d47 |  | note | At least 10 working days prior, provide to the principal a copy of the Vibration Risk Assessment, undertaken by a suitably qualified person, identifying the properties which contain buildings that require a building condition inspection
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.9 - Recommencement of construction at location of identified Aboriginal heritage item
label | b8e5c825-9faa-5a37-b227-79d94a143651 |  | note | Submit details of the Aboriginal heritage item and its location
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.11.4 - Transport of waste generate under the contract to the "waste site" outside the identified project boundaries
label | 1f6465e1-ec23-5cb0-9519-ba6233e79ba7 |  | note | Submit completed and signed copy of "approved notice" and supporting documents, as listed under items (a) to (g) in Clause 4.11.4 (S143 form)
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.13 - Working in or near environmentally sensitive areas
label | daa314a8-7267-5ffc-8ddc-61e3248cf776 |  | note | At least 15 working days prior, provide the principal with a copy of the EWMS for working in these location(s) and written notice that the area(s) are clearly delineated with locations and boundaries signposted
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.15.2 - Taking possession of any land nominated or authorised by the principal for use for the contractor's site facilities
label | dab3b0d5-538e-548f-88fa-a4c086e8c466 |  | note | Submit a pre-construction land condition assessment report for each area you intend to use for the contractor's site facilities, and evidence of any required statutory and environmental approvals
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | Topsoil Stripping (R44) |  |  |  |  | Yes | ITC 03 - R44 Topsoil Stripping | 4ec8673c-ab40-4c69-91b5-d4c9a0f3392a
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | 6e33a208-df3a-53eb-81cf-ce45a789334f |  | note | REQUIREMENTS / REFERENCE: R44 Cl 2.3.1
label | 7f39422f-4113-5b58-8595-d762cfa90161 |  | note | ACCEPTANCE CRITERIA:
label | bc657bfc-b16d-5e73-92da-b778f6646a89 |  | note | • Erosion and sediment controls implemented prior to starting works
label | ee4d3dae-c0de-5dc2-94d9-6a4a7b22a03e |  | note | • Clearing and grubbing completed in area of works ahead of time
text | d6f1f86c-b987-5e3c-8b67-2333e973187e |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Unsuitable material
label | 5d07fd9d-330d-56b8-bd76-16d692bc2323 |  | note | REQUIREMENTS / REFERENCE: R44 Cl 2.4.1
label | 34d22a73-1862-5b87-b7c5-03a953f54500 |  | note | ACCEPTANCE CRITERIA:
label | 95f03c6d-7b98-575d-8344-ab1bac95c28d |  | note | • Notify the Principal at least 24 hours prior to excavation or removal of contaminated material
label | 6cc1ec04-6f94-57b3-8609-3b84bff8ba9e |  | note | • HP: Inspection after removal of unsuitable material and prior to backfilling (if applicable)
text | 1200cf45-7500-5ebf-97b8-59d960d718aa |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Joint survey following removal of topsoil
label | 30b39919-692c-5325-9531-c0171c2cb2ec |  | note | REQUIREMENTS / REFERENCE: R44 Cl 2.3.3
label | 27d5a0f9-2acc-5515-b12d-019336789b03 |  | note | ACCEPTANCE CRITERIA:
label | 1b3fda04-771c-5893-928c-9977383a07df |  | note | • HP: At least three working days prior to the proposed date for altering the ground surfaces, complete a Joint Survey and submit a survey report of the existing surface levels, following removal of the topsoil
text | 86ba6ac6-6aed-5880-a300-f80a6798631a |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | c8c0de44-5801-5e63-a030-fe0e05006d82 |  | textbox | Name:
text | 9f3d987d-1e9b-5a47-afa9-d6265603ea90 |  | textbox | Date:
label | 3dc98437-f515-5074-a318-cadc13f95aa5 |  | note | Signature
checklist-flat |  |  | checklist | Stormwater (R11) |  |  |  |  | Yes | ITC 02 - R11 Stormwater | 5054cc6d-b36f-4969-99dc-bdc05180c90b
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | f7cf66a1-035c-5660-a785-098c46eb8744 |  | note | REQUIREMENTS / REFERENCE: WHSMP, Design DWGs
label | a46f0879-82c5-5a74-84a1-651b41b3c54e |  | note | ACCEPTANCE CRITERIA:
label | 9230bb97-c2e6-5e3c-950d-e3ecf81b0986 |  | note | • Contact DBYD and complete excavation permit
label | f3490c68-5524-5d55-877c-81c3c27277f8 |  | note | • Extent of works set out with survey pegs
text | 4a05e9ec-8d5c-5d41-9b64-337e851f1aa9 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Supply of Precast Concrete Members
label | cdf5b216-8451-5a63-8977-a3ff277a1584 |  | note | REQUIREMENTS / REFERENCE: R11 Cl 2.4.1
label | 863cf0da-aa49-53d3-aced-da1cc840c285 |  | note | ACCEPTANCE CRITERIA:
label | c4ea9d46-4eb8-56f2-b0d2-798ab781e4c1 |  | note | HP: Submission of certified product drawings and details of methods for manufacture, testing and installation, prior to the supply of precast concrete members subject to traffic and/or earth pressure loading, or water retaining structures with capacity greater than 25 000 litres
text | ed1fda05-df3a-576d-9a5c-17852faf844e |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Certificates of Conformity (1)
label | 016b8421-05a1-59f1-b8be-a3b1268d1b91 |  | note | REQUIREMENTS / REFERENCE: R11 Cl 2.6
label | 42268428-8577-59a5-ae1b-5a4a6623b162 |  | note | ACCEPTANCE CRITERIA:
label | cbd27967-8ef7-5862-9004-50afa6222ebf |  | note | • HP: Certificate of Conformity (Pit / Headwall)
label | 312427f7-39b2-5f89-869d-49432447956e |  | note | Submission of certificate of conformity prior to incorporation in the works of any supplied manufactured drainage product
text | 85b65ad0-b868-55f5-aa02-29b4e1614d4d |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Certificates of Conformity (2)
label | 88c40c1b-de7d-55e6-bda8-3141291a587c |  | note | REQUIREMENTS / REFERENCE: R11 Cl 2.6
label | fc531f24-4b21-558b-9eb5-9af7d330f8ce |  | note | ACCEPTANCE CRITERIA:
label | 84147fea-01b3-53eb-9053-e14d01aa0d77 |  | note | • HP: Certificate of Conformity (Box Culverts)
label | 8a32b690-0143-525d-9010-6fbc4fa8a25f |  | note | Submission of certificate of conformity prior to incorporation in the works of any supplied manufactured drainage product
text | 2667ca5c-c4c2-5b1f-8907-14db593edfe8 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Survey Set Out
label | 0e303462-89b6-5b4c-b9df-63e62465de07 |  | note | REQUIREMENTS / REFERENCE: R11 Cl 4.1.1
label | 911b1f7c-46c5-556a-8033-2289133240ef |  | note | ACCEPTANCE CRITERIA:
label | 8b03fd26-3399-50c2-afb2-c1831fc99f7e |  | note | HP: Notification of set out of drainage system and any proposed design changes in locations and levels
text | 19c3b84f-2e0d-53a4-9c98-e8c964f166f6 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Unable to meet Min. Grade
label | feeb1f7d-bb86-5419-90ab-2572e317ebae |  | note | REQUIREMENTS / REFERENCE: R11 Cl 4.2.1
label | fb211368-e457-5b88-b96c-895dc91aab71 |  | note | ACCEPTANCE CRITERIA:
label | c8bb234c-a933-5122-b452-4e55fb976f4f |  | note | HP: Notification that 0.5% minimum grade cannot be achieved for section(s) of open drains (if applicable)
text | 6a51bf80-bedf-514c-aca2-27f87fe2e48b |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 - Excavation
label | 4e35fc2d-cbbe-5a86-af34-1fe9be40828b |  | note | REQUIREMENTS / REFERENCE: R11 Cl 4.3
label | 4a046f03-0379-5b8c-b2e8-ecaee9298a20 |  | note | ACCEPTANCE CRITERIA:
label | 2ea9ffa7-27aa-5510-b4c8-bd6910571323 |  | note | WP: Excavation for Box Culvert installation and other drainage structures
holdpoint |  | Data not allowed on signoff: INSPECTION:(e9a646e2-a356-5525-b50f-756d5731deb4) | signoff | Hold Point
checkpoint-status |  |  | checkpoint | 7 - Unsuitable Foundation
label | beda10dc-047d-50f2-a0ae-a6bb58d95b53 |  | note | REQUIREMENTS / REFERENCE:
label | 45170e27-ecb4-59ca-8242-b646c94f02dd |  | note | R11 Cl 4.3.3
label | 454be684-7a76-5f8c-9ec0-f5ec5cc33bde |  | note | Table R11.2
label | 8ca067ef-7842-5d5a-8018-e486b4e7d3fa |  | note | ACCEPTANCE CRITERIA:
label | 47e46e26-d89d-5959-850a-6a4d6e1c4c6c |  | note | • HP: Replacement of inadequate foundation material (if applicable)
label | 4c462d09-8448-5151-b09a-dfd54b0a6b91 |  | note | • Notify the principal of any unsuitable foundation material on the base of the trench, or poor quality material on the sides of the trench. Replace and compact material in consultation with principal
text | 655e1df9-d192-59dd-8ef7-6f9d846de88d |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8 - Installation of Drainage
label | 143de1f1-cd96-53a0-9e44-7fc49c1bbdd2 |  | note | REQUIREMENTS / REFERENCE: R11 Cl 4.4.1, Table R11.2
label | 47e83fd3-8ac6-5f16-a7ea-2701c54ddd62 |  | note | ACCEPTANCE CRITERIA:
label | 01a7f073-c4b5-533d-8115-9e00ecf1a120 |  | note | • 95% compaction requirement for base of trench and layers around pipe
label | 7c04fb18-5fe9-54b5-bc98-10f8e07899bf |  | note | • Material for pipe bedding and haunch zones is Type BH Select Fill
label | c7598889-fad2-58c6-b5ec-1125977642c2 |  | note | • Material for pipe side and overlay zones is Type SO Select Fill
text | 4cafa9bd-a4b1-5c40-8ec4-2cb61aac2c9f |  | textbox | INSPECTION:
label | ef2b58e5-f2c8-52e9-b66f-899c73c80a15 |  | note | COMMENTS / ATTACHMENTS: T166 / T173 Test Report
checkpoint-status |  |  | checkpoint | 9 - Construction
label | 16902d7d-1ac2-5fbf-9219-fb8b3fb5ff24 |  | note | REQUIREMENTS / REFERENCE: R11 Cl. 4.7
label | c7923252-6b72-54a8-bb42-b508313095c8 |  | note | ACCEPTANCE CRITERIA:
label | 58db3d24-86d5-53fe-846e-af28bfe1e3fe |  | note | WP: Construction of drainage structures other than box culverts
holdpoint |  | Data not allowed on signoff: INSPECTION:(5c671af2-a3ad-551c-9263-441f62378c8d) | signoff | Hold Point
checkpoint-status |  |  | checkpoint | 10 - Protective Measures
label | 4906ead1-7538-5ff7-bbde-38ec6b2c04dd |  | note | REQUIREMENTS / REFERENCE:
label | 138fc9e4-54e9-55e4-9df2-c9bd7b6c03e9 |  | note | R11 Cl. 4.10
label | 2a0e0d55-3f6b-57c2-816f-ae0c0a77fa86 |  | note | TfNSW G2
label | 520c4188-393c-5d4d-a89e-e9c906022e82 |  | note | ACCEPTANCE CRITERIA:
label | 63af335f-0282-59c1-8ab8-012a6333e3f0 |  | note | • HP: Protective measures for pipes and box culvert structures from heavy construction plant or vehicles
label | fb6d7263-d795-5b78-b8e6-9889e1b462e4 |  | note | • If structures will be subject to heavy construction loading prior to completion, submit protective measures to principal for approval
text | a40951c0-2c1f-575e-b9d1-ef2bcd410f24 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 11 - Backfill and Compaction
label | d0292fbc-320c-52f1-836c-832249ceb7f0 |  | note | REQUIREMENTS / REFERENCE: R11 Cl. 4.9, R44
label | eea4c70b-5552-5e22-889d-ee5f4495b6e0 |  | note | ACCEPTANCE CRITERIA:
label | cfa8ecd9-8cbc-57f7-a9fe-78f704824397 |  | note | • Above the pipe overlay, backfill with general fill material or other material accepted by principal
label | 27f794f0-3055-529e-8005-51aaec3ec872 |  | note | • Backfill in 150mm layers unless directed otherwise by the principal
label | 2e7561b9-85bd-5879-a6bf-36284a957080 |  | note | • 95% compaction for general backfill, 102% compaction required if adjoining SMZ layer (R44)
text | 6deba54a-74fc-5a01-9d0d-95386f932af1 |  | textbox | INSPECTION:
label | 34fbf663-d87c-5564-b885-fb63a9eb2f11 |  | note | COMMENTS / ATTACHMENTS: T173 Test Report
checkpoint-status |  |  | checkpoint | 12 - Completion
label | 29161bdf-611c-5e7c-8b67-ae8a491d670a |  | note | REQUIREMENTS / REFERENCE: R11 Cl. 5.2
label | 6fa34cb2-46b8-5e62-ba96-c43058d4020f |  | note | ACCEPTANCE CRITERIA:
label | b90d5f17-ad98-5cd6-b24e-59efe658a526 |  | note | Survey pickup of asbuilt pit inverts (downstream and upstream) and pit locations. Survey report provided and any NCRs raised, changes picked up on WAE drawings
text | 1af78d6a-dcb2-59ae-8180-083dac0f1c38 |  | textbox | INSPECTION:
label | b3e10cc3-3569-557a-9191-7820be3b3fb8 |  | note | COMMENTS / ATTACHMENTS: Survey Conformance Report
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | ca7b76ff-c23d-5134-be91-e937ea6f7486 |  | textbox | Name:
text | 0db7d438-44d2-5b09-b892-95aa95bb61c4 |  | textbox | Date:
label | 559c0292-e298-5e25-938f-0e2dbc5d6ef2 |  | note | Signature
checklist-flat |  |  | checklist | Trench Drains |  |  |  |  | Yes | ITC 13 - R33 Trench Drains | 5553f362-feab-4433-8bbd-22a8441a8bd4
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | c23fb9d6-6711-590e-9674-51e62660aa2d |  | note | REQUIREMENTS / REFERENCE: WHSMP, Design DWGs
label | cc4af1e2-13ec-5f4e-9b08-0438c799fc48 |  | note | ACCEPTANCE CRITERIA:
label | 7b91478b-9dc2-5b4e-9ad9-2587febfa1e0 |  | note | • Contact DBYD and complete excavation permit
label | 1cc5fd7f-941d-5b38-974a-381773c23aee |  | note | • Extent of works set out with survey pegs
text | 1df3f603-ba48-5413-9366-006d8f47b1b8 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Materials
label | 2b130030-3b77-5bb5-9921-559682e9568f |  | note | REQUIREMENTS / REFERENCE:
label | 7eecddf2-c3df-5680-93be-f4133bdd7799 |  | note | • R33 Cl 2.1
label | 181fe2ef-8db8-510a-b029-20173b0286a0 |  | note | • TfNSW 3552
label | 7b1fca54-17a8-5fe9-b377-61a991927954 |  | note | • AS2439.1
label | 63dfd51a-1613-5a95-be75-011e96047560 |  | note | • TfNSW 3556
label | c984170b-79ee-5f1f-84e8-97d1a038ff58 |  | note | • R33 Cl. 2.2 R63/E
label | ce5b171c-a04d-56e7-9358-26ef699d73cb |  | note | • R33 Cl. 2.3
label | 3e575cdd-7f43-5acf-ac30-8db83bc26931 |  | note | • TfNSW 3222
label | fc08534c-2fc5-5b9b-acc6-584974454b5d |  | note | • R44
label | 6b87323a-84c3-5d60-98c1-7e9c88d9816c |  | note | • R33 Cl. 2.4
label | ee55eb29-5408-57e7-87d3-b7cfbaedb1c2 |  | note | ACCEPTANCE CRITERIA:
label | f0f6123e-b292-5d75-9e75-724c9ce050f8 |  | note | • Supplier certificate showing TfNSW 3552 / 3556 conformance and dated within last 6 months
label | 6faddb70-75a9-51f7-ba16-59dfd502cc09 |  | note | • Geotextile strength Class A and meets R63/E
label | b475a321-c64a-5f71-86a7-3c708171886e |  | note | • No fines concrete (NFC) mix is approved and is grade NFC SD, complies with TfNSW 3222
label | 526fd3ec-ba97-55a9-8ede-597498241458 |  | note | • Selected fill conforms to R44
label | 383cb3d5-edcf-5ff5-8ffa-b5893fcd5f6f |  | note | • All materials have been submitted to the principal including type of material, supplier name and compliance records
text | 944b907d-981d-5a16-b0e1-32955f1350e8 |  | textbox | INSPECTION:
label | 544393f1-a132-5b4b-9c44-74ea4270024e |  | note | COMMENTS / ATTACHMENTS:
label | 85e19286-0bc9-5300-b92c-a09c4600481c |  | note | • Certificates and Test Reports
label | dbde8ea7-808a-5535-ba5f-d0d88bbf1b74 |  | note | • Email(s)
checkpoint-status |  |  | checkpoint | 3 - Excavation and Installation
label | 52d41b44-3222-5190-9b29-cedf449a8450 |  | note | REQUIREMENTS / REFERENCE:
label | a0b82c9a-0361-5a2e-82e7-bf2c77e0ccd0 |  | note | • R33 Cl. 3.2
label | 3f455b30-7d4c-5a57-a4d0-32cf2e219ec9 |  | note | • R33 Cl. 3.3
label | f5530e70-bec2-5bc1-a5b9-bff1ce0d1685 |  | note | • R33 Cl. 3.4
label | 2723c94a-b391-5efb-a27b-606fc5a1e966 |  | note | ACCEPTANCE CRITERIA:
label | afd26982-38b7-5ec1-9009-d9c2efbce099 |  | note | • Excavate trench as per location and dimensions shown on the design drawings
label | 1058aff2-29cf-541c-a339-84e650ba751d |  | note | • Bottom of trenches have a minimum fall grade of 0.5% towards outlet, trench floor is compacted
label | 468a747c-cc5c-5b93-afb6-f042a49760df |  | note | • Pipe laid in centre of trench, 100mm bedding of filter material underneath. Buried end is capped
text | 7278f553-fe71-54ac-8a19-e9896c21fa85 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 4 - Backfill
label | 1d073622-6794-51a7-b240-374c2913da30 |  | note | REQUIREMENTS / REFERENCE:
label | 1d60de86-ee93-5989-826f-9759e467df8f |  | note | • R33 Cl. 3.5
label | e077ae05-c0c1-506c-b812-0b5a8943a7b2 |  | note | • R37 Cl. 3.2
label | 22ee6740-b1b1-5cfb-9297-ac76f6535d89 |  | note | • R33 Cl. 3.5
label | f5c4373d-2854-5859-b7da-9831c4344799 |  | note | • R33 Cl. 3.6
label | 95a8631e-db4a-5ffa-9d53-bea8938fb447 |  | note | • R37 Cl. 3.3
label | f07f8e93-1188-5aa5-b565-099b6a973fb3 |  | note | ACCEPTANCE CRITERIA:
label | 5e9acd85-5251-5f3a-8901-17a468d796ee |  | note | • HP: Verification that pipe laying, jointing and bedding are complete and conforming, prior to backfilling over the drainage pipe in the trench with filter material
label | 8de2f929-fb02-51ea-9fd3-d2d5ac8564ab |  | note | • Backfill with no fines concrete only as per Project Drawings. NFC placed to allow the free flow of water and has not segregated
text | bf207d5a-af86-54a6-ab75-236d48583efd |  | textbox | INSPECTION:
label | 667e6a82-1e39-5d55-ad4d-280accd0e3a6 |  | note | COMMENTS / ATTACHMENTS:
label | 492df8d8-7495-5f24-9d15-724dc4980c57 |  | note | • Concrete pour docket(s)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Completion
label | 4655c4fb-0ce5-5c15-bdfa-c86250d718a1 |  | note | REQUIREMENTS / REFERENCE: R33 Cl. 6
label | 71f5bd4d-8b36-5fb9-a102-373ef923cd4b |  | note | ACCEPTANCE CRITERIA:
label | 71b30059-c21d-5774-a40c-aebdcf91bf62 |  | note | • Record all trench drain inlets and outlets using GPS for inclusion in WAE drawing
text | 9a285d61-59c6-5232-af8b-77988ddad420 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | c5067e7e-67ee-532b-a6b8-0566792ca03f |  | textbox | Name:
text | 60d11a23-c188-563d-b6a1-a0f555fea0e0 |  | textbox | Date:
label | 58cf28b3-8465-5f3e-9240-cbccfab31feb |  | note | Signature
checklist-flat |  |  | checklist | Select Material Zone (SMZ Layers) |  |  |  |  | Yes | ITC 06 - R44 Select Material Zone (SMZ) | 635447ce-cde7-4fd8-aa86-4caa27c154a3
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | 6cccfa4a-5993-58cb-8fe5-34083f0f19df |  | note | REQUIREMENTS / REFERENCE:
label | 4e41fc01-6572-51e3-b8fa-c639a5aa9eac |  | note | ACCEPTANCE CRITERIA:
label | 0e2405bc-603b-56f0-85c3-97543a027d30 |  | note | • Underlying surface is homogenous and free of loose material, all data has been collected prior to covering (survey / test / proof roll / beam test)
text | 1afbf344-d675-5800-a6a3-851865d13983 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Materials (1)
label | abfe6b21-6756-5247-9bf5-f703e2f03318 |  | note | REQUIREMENTS / REFERENCE: R44 Cl 6.1.1, R44 Cl 6.1.2
label | ef3e2925-4ca0-5a0d-9687-dcbd7ae064f8 |  | note | ACCEPTANCE CRITERIA:
label | 465a8409-84b3-51a7-a8b7-d7da61b058a1 |  | note | • HP: Submission of details of location, quantities, type and verification of conformity of Selected Material. If imported, verification that all possible onsite sources of material have been exhausted (if applicable)
text | d877e2b1-7c43-5acb-86e2-6f315ce63c66 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Materials (2)
label | 1a250cd5-07fb-5428-83bb-8f3612a2b7c7 |  | note | REQUIREMENTS / REFERENCE: R44 Cl 6.1.1, R44 Cl 6.1.2
label | 6e42f0d5-de3c-5585-80a6-71e15ee7a8e6 |  | note | ACCEPTANCE CRITERIA:
label | 17a51931-1770-5d1e-92d8-60ba56bb62f1 |  | note | • HP: Verification of conformity of stockpiled Selected Material, with test results showing conformance to project requirements (Particle Size Distribution, CBR and PI) and that the material is free from contaminants and foreign materials.
text | 8fdaeac5-f37a-59d6-b05a-b59fdeeaf6fc |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Deflection Testing and Verification of Works (1)
label | cb8b8726-758f-557d-afb1-646cecd2e049 |  | note | REQUIREMENTS / REFERENCE:
label | e855f61c-cca0-5ac5-a136-9f23f9feaba5 |  | note | – R44 Cl 7.6.2
label | b0f04d9b-3446-5003-a761-67c9e340e8ca |  | note | – R44 Cl 7.6.1
label | e892c54a-0111-5a6a-b00e-cb03861ea372 |  | note | – R44 Cl 7.4
label | 1a43a798-d15a-5602-b17e-7d1e393eab55 |  | note | – R44 Cl 7.7.1
label | 12602439-5a06-57ea-be31-82c95f228951 |  | note | ACCEPTANCE CRITERIA:
label | b208e5f6-959b-5b57-9183-56a428286743 |  | note | • Note: Proof rolling not required for Selected Material Zone as per R44 Cl 7.6.1. Proof roll required if Benkelman Beam testing is not feasible.
label | a7b09e1a-e083-5e3c-a73d-cf697de0d5ac |  | note | • T166 Test Result: Relative compaction ? 102%
label | 60d0d2a0-7af5-56da-a911-2d9bc256d63b |  | note | • T162 Test Result: 60% ? Moisture content ? 90%
label | 8653e5a4-be1e-5f0b-a5bd-12e90eb44402 |  | note | • Survey Report: Finished surface level within tolerance of +10mm to -40mm of design (for top of lower layer), surface level within tolerance of +0mm to -20mm of design (for top of upper layer)
text | 264b9385-9e32-5c55-a191-364ac1ea2821 |  | textbox | INSPECTION:
text | a8edcf3f-8007-5f76-bb3d-084ea018a0fc |  | textbox | WITNESS POINT:
label | 11cacc22-59b4-5bf1-9ef0-06655ab1e5d1 |  | note | COMMENTS / ATTACHMENTS:
label | ec989d6a-3385-5139-8345-f760a448f9b1 |  | note | • Test Reports
label | 74c2f495-386a-5bb4-aef3-458e7d4f008e |  | note | • Survey Report
checkpoint-status |  |  | checkpoint | Benkelman Beam testing of Selected Material Zone (top of SMZ layer)
label | 6f94ca96-0d17-4fac-afc5-44d4e41e2919 |  | note | Proof rolling not required for Selected Material Zone as per R44 Cl 7.6.1. Proof roll required if Benkelman Beam testing is not feasible.
holdpoint |  |  | signoff | Hold Point
checkpoint-status |  |  | checkpoint | 4 - Conformity of Completed Works (1)
label | deadab22-42c5-5c7f-8a06-3b2495fc83f9 |  | note | REQUIREMENTS / REFERENCE: R44 Cl 6.1.2, R44 Cl 7.6.2
label | ebbaa0e2-8e75-58b6-93d0-3417ccf0270b |  | note | ACCEPTANCE CRITERIA:
label | e7e85802-6ef3-5ae3-b1ac-eb83424d13e4 |  | note | • HP: Verification of conformity of each lot of Selected Material Zone placed, provided with conforming test and survey reports
text | 90608647-36f3-534f-9e72-ca2b6c3fd6f2 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Conformity of Completed Works (2)
label | 815b5c75-91f7-571d-a001-995ff584c026 |  | note | REQUIREMENTS / REFERENCE: R44 Cl 6.1.2, R44 Cl 7.6.2
label | 24b79146-b7d2-5ce3-9975-a9dd563a770b |  | note | ACCEPTANCE CRITERIA:
label | 4a13e486-88fb-5798-871c-d1b141c94b2b |  | note | • HP: Submission of deflection test results, finished surface levels and verification of conformity of each lot of Selected Material Zone placed (submission of lot package with beam test, test and survey)
text | 6bc92b88-cf73-52f7-a4e7-975957db4d10 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | 04d90180-0039-5d05-baf3-e9cd046129fe |  | textbox | Name:
text | ff057175-2953-5cd3-b1c4-2d1a28a86313 |  | textbox | Date:
label | 87f58403-15db-5e97-90ca-120973fe9221 |  | note | Signature
checklist-flat |  |  | checklist | G022 – Work Health & Safety (Construction Work) |  |  |  |  | Yes | G022 – Work Health & Safety (Construction Work) | 6785a239-0930-4bb6-bc5b-607a653e270e
checkpoint-status |  |  | checkpoint | Clause 3.8.3 - Commencement of work on the site
label | 77bd5846-bf95-54c3-b999-96cd7c5db18c |  | note | At least 10 working days prior, submit the WHS Management Plan and any supporting documents
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.3.2 - Commencement of work on the site
label | 924c6e5c-17cd-5f8e-be8f-985887efbdf2 |  | note | At least 10 working days prior, submit the Heavy Vehicle CoR Management Plan and any supporting documents
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6.3.1 - Work process which the principal considers is not being carried out safely
label | accba62b-5070-5f9d-9667-dc0a5d68bbe4 |  | note | Intervention by the principal / issue of corrective action request by the principal
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | Clearing and Grubbing (G40) |  |  |  |  | Yes | ITC 01 - G40 Clearing and Grubbing | 92527d25-768c-4cc9-bde9-3d751baa90e9
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | 0e638d4c-eec7-5ceb-ade7-1e60962d5995 |  | note | REQUIREMENTS / REFERENCE: G40 Cl 2.4
label | a3468930-a1a2-5432-851a-390d31be3c66 |  | note | ACCEPTANCE CRITERIA:
label | a4e28a2b-2320-567d-a70e-033a2d683b62 |  | note | • Confirm clearing limits with Principal and project arborist via site walk
label | 5ac8a736-c8ab-5263-8f8d-6923450ec68d |  | note | • Identify limits of clearing by clearly visible markers
label | d9ff4838-6ab9-5182-8813-d52dc0fccd00 |  | note | • Install all soil erosion and sedimentation controls required for the initial stage of construction
label | 9b5c22f3-7e42-5faf-8121-a83c62ccc90a |  | note | • Complete pre-clearing survey and survey report for flora and fauna prior to starting
text | d68394e2-e16c-5918-9c07-5b520c8a2558 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Clearing and Grubbing Plan
label | 118efad9-f75f-58e7-b863-d2fc67cb93a8 |  | note | REQUIREMENTS / REFERENCE: G40 Cl 2.4
label | 250cc7f8-5592-505b-aedf-f144c4597aa8 |  | note | ACCEPTANCE CRITERIA:
label | 717f0f5d-f712-54b0-a99e-1fad06d6bca9 |  | note | HP: Prior to clearing any area of work, submit Clearing and Grubbing Plan (Annexure G40/D) and report on the presence of weeds and unsound trees together with written notice that limits of clearing and areas of weed infestation identified in the ecological report (Clause 2.4(a)) are marked, at least seven days prior to starting clearing
text | e7cf1754-df1c-544d-9f68-ca7f6490df92 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | 10c6e597-b82a-56b6-9560-c5d315de4c99 |  | textbox | Name:
text | 6c649e9e-79a1-5db6-9560-ef527a21a637 |  | textbox | Date:
label | f20c589b-335f-51ed-84f7-e981c013c06e |  | note | Signature
checklist-flat |  |  | checklist | G002 – General Requirements |  |  |  |  | Yes | G002 – General Requirements | 937b274d-0508-4f01-9cc5-949bbddbd1f4
checkpoint-status |  |  | checkpoint | Clause 14.2 - Commencement of work on site
label | dbb44dbe-fe05-523b-b382-dfa00231729a |  | note | Provide a copy of the transferred environmental protection licence to the principal at least 7 days prior to the proposed commencement of work
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 37.3.2 - Inviting tenders for the Primary Testing subcontract
label | 26de775e-73c5-59d3-9608-fe65d877cd57 |  | note | Submit proposed subcontract documents and proposed invitation to tender including schedule of rates and list of tenderers to be invited and a list of supplementary information that will be provided to the tenderers. Submit the procedure required by TfNSW Q Clause 7.4 for the management of subcontract work
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 37.3.3 - Accepting tenders for the Primary Testing subcontact
label | 79188755-8f1c-5803-95e9-b4673825ea45 |  | note | Submit all tenders received, including the tendered schedule of rates, the assessment and recommendation with reasons for recommending the successful tenderer, at least 7 days prior to the proposed acceptance of the tender. Submit any changes to the procedure required by TfNSW Q Clause 7.4 for the management of the subcontract work
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | Signposting (R143) |  |  |  |  | Yes | ITC 09.1 - R143 Signposting | a492b5d1-34eb-48e5-aaf8-6ee847c3db99
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | cd733435-0957-5c24-8957-4d6b30e40e81 |  | note | REQUIREMENTS / REFERENCE:
label | df6e9cea-3b4e-5a85-84bf-b2d253d164b8 |  | note | – WHSMP
label | 09555057-5cfb-5187-9b7f-0ad36728f930 |  | note | – Design DWGs
label | 6423d553-f392-5ffb-8286-e8c45d7c8566 |  | note | – R143 Cl 3.2
label | f91fbba0-52df-59bd-ad00-1b1471a46ef8 |  | note | ACCEPTANCE CRITERIA:
label | 6c1c7249-214f-56db-a357-0ebc7efbfe43 |  | note | • Contact DBYD and complete excavation permit
label | 657d6c01-d03c-577a-afe7-3dcf7373b011 |  | note | • Locations of signs set out by surveyor
label | 9e0616bc-0631-5627-8c20-b54b5cc9d2c5 |  | note | • HP: Construction of sign support structure foundations – Submit to the Client the proposed location and orientation of each sign support structure
label | 10b948b9-235d-535a-97ac-aff3c0275213 |  | note | • Hold points for placement of concrete apply as per B80 and R53 as required
text | b5696b0f-4c05-5a07-b9dd-9c0c889ee927 |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Construction works
label | 36fb4f12-10b0-52c6-9b04-61874fb1e481 |  | note | REQUIREMENTS / REFERENCE: R143 Cl 3
label | 7fc62168-64fd-5e05-af1f-ac1c536383db |  | note | ACCEPTANCE CRITERIA:
label | 2134a626-baa0-55ae-88fc-246cc88fcfd6 |  | note | • Sign foundation structure completed as per construction drawings
label | 7f8f7570-59c2-5a37-9424-f138c0be9ae1 |  | note | • Sign face(s) installed as per construction drawings
text | b1a6f1bf-a102-524b-92bb-4d0307205795 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | cfdf7d57-8e4d-5a09-aa45-c00748bcad18 |  | textbox | Name:
text | ce1523d5-e8f8-515a-b578-0efd460366db |  | textbox | Date:
label | 6158bad4-db8a-5f21-9cf0-fce0210f39ec |  | note | Signature
checklist-flat |  |  | checklist | G001 – Job Specific Requirements |  |  |  |  | Yes | G001 – Job Specific Requirements | ac54c9d9-ed30-4f53-aaab-7427337ef61e
checkpoint-status |  |  | checkpoint | Clause 6 - Environmental Protection Plan (CEMP)
label | 0dc04ee3-031b-5c7b-94d0-317d92b1c037 |  | note | Start of works
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6 - Quality Assurance Plan
label | 5440e32f-392c-5aa9-ad04-dc4ebf4dee72 |  | note | Start of works
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6 - Clearing and Grubbing Plan
label | 03e584ee-b273-522b-89e7-09d0cf342b61 |  | note | Start of works
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6 - Traffic Management Plan
label | 68e4f212-d64c-5038-9b43-583a957fae31 |  | note | Start of works
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6 - Work Health and Safety Plan
label | cf9e18de-705c-5340-85dc-e89168a3a111 |  | note | Start of works
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6 - Chain of Responsibility Plan
label | 7e6d0f44-7012-5303-9dc3-068ab9c26bf7 |  | note | Start of works
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 8.1 - Construction staging drawings submitted at least 2 weeks prior to the commencement of work in the relevant area
label | 608baa31-76fd-50e7-b4d2-2ab987470145 |  | note | Commencement of construction
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 8.1 - Revised construction staging drawings submitted at least 4 weeks prior to commencing work using the revised staging plan
label | e86718ee-cb29-50e8-a1ce-25cdb70e397f |  | note | Commencement of construction in accordance with the revised construction staging plan
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 11 - Contractor's compound - documented location, size and relevant approvals
label | 36175146-9680-5804-911d-16df9b6634b7 |  | note | On-site establishment of Contractor's compound
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 11 - Contractor's stockpile sites - documented location, size and relevant approvals
label | b1d1f8a9-ff37-54ee-8bf5-1b9ea4572968 |  | note | On-site establishment of Contractor's stockpile sites
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 12 - Dilapidation survey / Pre-Construction Condition Survey Report
label | 593da8f9-22d8-5c04-95f9-696c07c7fab5 |  | note | On-site establishment of Contractor's compound
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 15 - In case of contaminated material, submit EPA waste classification reports and clearance certificates, if applicable
label | 4d27d6e4-84aa-5725-8d8e-e8c408ecfd4e |  | note | Commencement of excavation in the potential contaminated areas
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 22 - Submit temporary works design including certified drawings and design report (including methodology if applicable) for proposed temporary works including certification
label | 905c8139-c129-5267-bb8e-e2420fcf403b |  | note | Construction of temporary works
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | Select Fill + Upper Zone Formation (R44) |  |  |  |  | Yes | ITC 05 - R44 Select Fill + Upper Zone Formation | b3a57aaa-34d7-46be-af6f-24d0f11e4a1e
checkpoint-status |  |  | checkpoint | 1 - Preparation works
label | a4cee82a-e473-5209-88da-cf98b9a739ac |  | note | REQUIREMENTS / REFERENCE: WHSMP, Design DWGs
label | b1206317-4870-5b2a-90d4-ea3dbfb01685 |  | note | ACCEPTANCE CRITERIA:
label | 50d96aeb-23c4-5bdb-92cf-911e4c88850a |  | note | • Contact DBYD and complete excavation permit
label | 56845b05-b978-570e-a70c-6f5eac968be7 |  | note | • Extent of works set out with survey pegs
text | d8a0eeed-ff2b-5ae3-97a6-657d932aff74 |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Initial works
label | 6a8700f0-9280-5b18-81d4-879fef5b7b81 |  | note | REQUIREMENTS / REFERENCE:
label | 095604e1-c9bd-5962-9c84-d1ff64beaf1d |  | note | – R44 Cl 2.4
label | 8e9e0ab8-463b-5457-8877-2cb086e70558 |  | note | – R44 Cl 3.2
label | 737abeaf-0cb0-56e7-aad3-2e6304354d3b |  | note | – R44 Cl 3.4
label | 95dd6730-a393-5efd-998f-5caf77a194a1 |  | note | ACCEPTANCE CRITERIA:
label | 39cd8243-5f40-587c-8c86-387912d4e7ee |  | note | • Foundation inspection and removal of unsuitable material covered as part of Subgrade ITC and relevant Subgrade Lot
text | ce4ef1ff-3197-558a-9db7-0bc809a89b6c |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 3 - Materials
label | ad31c51b-bf09-52c4-88de-9d472cfcf934 |  | note | REQUIREMENTS / REFERENCE:
label | bd45a0fe-5b8f-55e7-8189-b0567f3eadcf |  | note | – R44 Cl 6.1.1
label | 57075256-98d5-50db-9818-484819cec9f7 |  | note | – R44 Annexure A2.2
label | 739ef832-1e65-51dd-bb37-aadea95cbb5d |  | note | ACCEPTANCE CRITERIA:
label | 445ccdca-a2df-5647-a2da-8642f027a449 |  | note | • Material conformity covered as part of Subgrade ITC and relevant Subgrade Lot
text | 4ab61a3d-0734-552a-b37c-25c462e1cafc |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 4 - Construction works
label | 3c0bc146-08df-52d8-b2f1-f52afeba2a75 |  | note | REQUIREMENTS / REFERENCE:
label | f1512405-7ccb-5039-83ad-35c8b872ae5c |  | note | – R44 Cl 7.6.1
label | 90507f54-bca7-510c-bf7d-c3dec201d91b |  | note | – R44 Cl 7.6.2
label | 652ba44f-f4bc-5bc2-b76d-c68601029f73 |  | note | – Table R44.11
label | da8e48f5-f155-55b2-b6a3-6f75751f7340 |  | note | – R44 Cl 7.3.6
label | f00784d2-1eae-523e-add3-08d90a4b1a8d |  | note | – Table R44.10
label | 5a1df505-8bbb-554b-8cc7-2becc9e38168 |  | note | ACCEPTANCE CRITERIA:
label | d3e56670-cf84-5ddb-aa36-44eab97085d8 |  | note | • Constructed surface is free from debris and loose material, placed in conforming layers of maximum 300mm each.
label | ebaf124d-b695-583a-85ad-1bcfdaaeb092 |  | note | • Proof rolls, Benkelman Beam and survey conformance results covered as part of Subgrade ITC and relevant Subgrade Lot
label | 9b37d5bd-01eb-55c9-9955-ebd77733d70f |  | note | • T166 Test Result: Relative compaction ? 98%, test results for each 300mm layer.
label | ab9dc2dd-b90c-5328-917b-ed0f34ac878a |  | note | • T162 Test Result: 60% ? Moisture content ? 90%, test results for each 300mm layer.
label | ea213ecc-482a-5434-a70e-2a0ae5580059 |  | note | • Lot map included alongside ITC
text | 3999aa4d-a407-589e-92c3-a7bb59ffe0bd |  | textbox | INSPECTION:
label | 9b911af4-b4d5-59db-a21c-e7ecd67744d3 |  | note | COMMENTS / ATTACHMENTS:
label | c0427290-b46a-5800-b0f5-7c17b11df8a1 |  | note | • Test Reports
label | 7e987c63-07d9-5838-b7d9-9f2a2066c144 |  | note | • Lot map
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | 0e80c406-cdec-51bc-be7a-a81cd73375a7 |  | textbox | Name:
text | 376e8dd0-342e-5d1e-bb75-4730561b6cd3 |  | textbox | Date:
label | 9a3842de-713f-5474-b498-96723df04279 |  | note | Signature
checklist-flat |  |  | checklist | G004 – Principal’s Project Accommodation |  |  |  |  | Yes | G004 – Principal’s Project Accommodation | cec04626-debd-46f1-aac0-1f71f82d8c22
checkpoint-status |  |  | checkpoint | Clause 1.3 - Work to provide the principal's project accommodation
label | ca1799f1-e18a-5e0f-8688-ebc4c00eed81 |  | note | Submit location and layout of site office compound, arrangement of individual buildings, car parking area, access road, security measures, internal layout of buildings, furniture, appliances and fixtures, pre-construction land conditions assessment report (as per G36 Cl 4.15.2), program for construction and fit-out of accommodation
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 1.3 - Work to provide the relocated principal's project accommodation
label | bec71a5c-dff0-5127-a39f-740881a7670c |  | note | Submit location and layout of relocated site office compound, arrangement of individual buildings, car parking area, access road, security measures, internal layout of buildings, furniture, appliances and fixtures, pre-construction land conditions assessment report (as per G36 Cl 4.15.2), program for construction and fit-out of accommodation
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | G071 – Construction Survey |  |  |  |  | Yes | G071 – Construction Survey | da891686-9dbb-4abf-a2fd-ad34c0ce6840
checkpoint-status |  |  | checkpoint | Clause 2.3.3 - Commencement of any work at the site
label | 4d5ef30f-643c-5c68-9194-cc8212279ca4 |  | note | Submit Project Quality Plan for Survey, including survey procedures and evidence that they are capable of achieving the specified Orders of Accuracy, and strategy for the replacement of survey control marks and cadastral reference marks
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 2.9 - Commencement of survey field work
label | 79e64a60-32ee-549f-8f60-9c932380145f |  | note | Documents listed under items (a) to (e) in Clause 2.9, at least 5 working days before commencement
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 2.10.1 - Commencement of each survey specified to be a joint survey
label | 77e1bae7-9116-593f-b5ff-43cec1d20dd7 |  | note | Survey date and location, surveyor's name, description of methods and equipment to be used, at least 3 working days before commencement
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 2.10.2 - Disturbing or covering up area of joint survey
label | 3ae4cd53-27b9-50ff-9ff4-780f34025381 |  | note | Survey report, including any calculations made to determine quantities, at least 1 working day before disturbing or covering up area of joint survey
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.1.2 - Commencement of construction activities near Survey Infrastructure
label | 1fe69b20-3edf-5bf5-b163-e82a6b0b4b23 |  | note | Application for authorisation to remove Permanent Survey Marks, Cadastral Reference Marks and Bench Marks, together with Items (a) and (b) in Clause 3.1.2 at least 30 working days prior to commencement of construction activities near survey infrastructure (POSI)
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.1.4 - Any activities that may cause removal, damage, destruction etc of a permanent control or cadastral mark
label | 3fd8490b-1c2a-562c-a03d-761c3edc5b1f |  | note | Receive Surveyor General's approval under the Surveying Regulation, at least 2 days before disturbing the mark (POSI)
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.2.1 - Use of survey control marks forming part of the Survey Control Network
label | c20b81aa-c198-52c3-9434-5652722361ce |  | note | Submit survey report verifying coordinates and level values of the survey control marks, at least 10 working days before use of the marks. Where requested, submit the procedure for replacing the affected Primary Survey Control Marks
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.6.2 - Use of Machine Guidance, for purpose of guiding work
label | c67c91ca-ee2a-5689-8981-7bbbcd3a4b70 |  | note | Submit the survey report detailing the site localisation used and the survey report detailing the machine specific Test Sites at least 5 working days before the use of Machine Guidance
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 4.6.3 - Use of Design Model within Machine Guidance System
label | 292ea6cf-d8d5-5a35-8c91-ca15e3bda5ee |  | note | Submit machine specific files and where applicable, instructions for uploading this information into the Machine Guidance System. Submit any quality assurance documents utilised in the process of generating these files
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 5.4.2 - Use of the Bridge Survey Control for setting out the bridge works
label | cc31a12f-e767-54f2-8616-0650fe86f6b4 |  | note | Submit the plan of the Bridge Survey Control including coordinates, and the measurements and calculations used to determine the coordinates
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 5.6.6 - Covering up of work subject to a conformity verification survey
label | af9d173a-f082-562e-a01e-d112a313ebde |  | note | Survey Report verifying conformity
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | G038 – Soil and Water Management |  |  |  |  | Yes | G038 – Soil and Water Management | ee27527d-ca07-45c8-ace6-5a5ab0828251
checkpoint-status |  |  | checkpoint | Clause 3.1 - Commencement of work requiring the installation of erosion control and sediment capture measures not previously addressed by ESCP and authorised by an earlier HP release
label | f42fc429-8816-531b-b783-0c8e9b303dbd |  | note | Submission of an ESCP (Erosion & Sediment Control Plan) and where required, WQMP (Water Quality Management Program), for a section of the work under the contract
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.1 - Disturbance of the existing surface on a section of the site, other than for the installation of erosion and sediment capture measures (WP)
label | f3794f3b-123b-5fdb-a340-213c781bfae6 |  | note | Submission of written notice that measures set out in the ESCP for a section of the work have been installed
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.4.2 - Commencement of dewatering activities
label | 30ff46c1-1b51-55e6-aa63-b3101f6cbfb3 |  | note | Submission of the dewatering procedure prior to the commencement of dewatering activities
holdpoint |  |  | signoff | Holdpoint
checklist-flat |  |  | checklist | Sprayed Bituminous Surfacing (R106) |  |  |  |  | Yes | ITC 04 - R106 - Sprayed Bituminous Surfacing | f1ccfb62-0178-4037-8443-de6e7fa9dba0
checkpoint-status |  |  | checkpoint | 1 - Preparation Of Pavement Surface
label | 9004bd2f-05ba-546e-ba01-c81e069efaa3 |  | note | REQUIREMENTS / REFERENCE: R106 Cl 5.2
label | 03b87f6c-6a30-5644-ae2a-5f15c36ccbaa |  | note | ACCEPTANCE CRITERIA:
label | 20af9565-9999-56f8-9953-715be72da748 |  | note | • Sweep the pavement surface by the use of a rotary road broom or suction broom to provide a uniformly clean surface.
label | db74e492-93c4-555e-be1e-62e9b408d371 |  | note | • Sweeping must extend at least 300 mm beyond each edge of the area to be sprayed.
text | aa1aebe3-d27f-5913-9964-7389f8addafb |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 2 - Pavement Temperature And Weather Conditions
label | f1994375-836a-5f1b-a112-c298f51a3129 |  | note | REQUIREMENTS / REFERENCE: R106 Cl 5.3
label | 3f03a78f-5ac3-5fc2-aa92-3a0bc0d6dc04 |  | note | ACCEPTANCE CRITERIA:
label | 37e1b4ba-4e4c-5fd9-a9ce-028783098c9e |  | note | • Measure and record pavement temperatures at regular intervals during the course of work. Commence spray only if pavement is at or above 10ºC for at least one hour before commencement
label | 303ea6ef-2446-5394-a6b3-26eab0f70e2d |  | note | • Do not spray wet pavement or while rain appears imminent or during strong winds or dust storms.
text | a070d567-76e3-587d-89e7-20374eeeb59e |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | 3 - Endorsement of Materials and Spray Seal Design
label | fc84568f-84d5-5cca-bb1d-a49382450214 |  | note | REQUIREMENTS / REFERENCE:
label | 972e12c0-7a31-5323-9a31-d7ce033c756e |  | note | – R106 Cl 3.3.3
label | 3fe8cf84-899f-5df6-b87d-f551d18bd082 |  | note | – R106 Cl 2
label | a4e4524c-ff29-50b6-98e0-2def9739ebed |  | note | – R106 Cl 3
label | 208cf867-e163-5925-aad1-aa3882b37b66 |  | note | – R106 Annexure D
label | 5ea34140-6f89-5d51-a805-bf0cb75c89ab |  | note | ACCEPTANCE CRITERIA:
label | 4c7ee71f-17e3-5f6c-9f2c-00cec80ae835 |  | note | • HP: Submit a signed statement stating that each spray seal design and its constituent materials meet the requirements of R106 Clauses 2 and 3. The statement must include NATA endorsed test results for all specified tests. Submit documents as required in Clause 1.2.4 and Annexure R106/D at least 7 days prior to the commencement of spray seal works on the site
text | 7e8fdb55-df91-5787-94f2-f47eef2c806a |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Review of Nominated Application Rates
label | 1f2f1c0a-c975-5d63-9f74-11b5d08d085c |  | note | REQUIREMENTS / REFERENCE: R106 Cl 3.4
label | 2c07ab36-9222-5eb6-bb09-1e67e892ee5a |  | note | ACCEPTANCE CRITERIA:
label | 7bfd539a-ccd1-5e97-abf0-201c73319477 |  | note | • HP: Submit spray seal sheet with aggregate lot details and target application rates
text | dca83510-ab94-5732-9490-d13af64b86bf |  | textbox | INSPECTION:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Application Of Primer, Primerbinder And Binder
label | 90615be6-d026-593f-bf1a-112c6fcfbcf8 |  | note | REQUIREMENTS / REFERENCE: R106 Cl 7
label | af140d32-9196-54c8-a139-07fe5ed65484 |  | note | ACCEPTANCE CRITERIA:
label | 670be367-d8f6-5d30-ba1c-73062b0dd825 |  | note | • Limit the area to be sprayed with primerbinder to the area that can be covered with aggregate at the target application rate within fifteen minutes of spraying bitumen or cutback bitumen.
label | 495f4c8a-672a-5919-b875-dfa90480fa21 |  | note | • The class and grade of primer and primerbinder must be as specified
label | e756fe01-bfa8-57f8-a79e-d141af4cc9c7 |  | note | • Apply nominated and target application rates and quantities of primer and primerbinder to the whole material, including cutter oil, measured at 15ºC.
text | 4db4a72b-da5c-5c82-9024-b98b52917b6a |  | textbox | INSPECTION:
checkpoint-status |  |  | checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | 449c0eab-541f-5f78-b107-492486bf38d6 |  | textbox | Name:
text | 2aea923d-dc8d-54d1-9c63-59d1fd61f018 |  | textbox | Date:
label | ed95c009-4942-529a-acd5-d8049d6aacc0 |  | note | Signature
checklist-flat |  |  | checklist | G007 – Utility Adjustment |  |  |  |  | Yes | G007 – Utility Adjustment | f77d39c6-6622-45ab-9f3c-7524f9292243
checkpoint-status |  |  | checkpoint | Commencement of utility investigation works (Locating existing utilities)
label | dd6ae990-d541-53ac-ba90-77c76f6282cf |  | note | Clause 2.3.1 - Submit Potholing Investigation Plan at least 5 days prior to proposed commencement of investigation works
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Construction commencement
label | f1f0369e-fd9a-5936-b1e7-e6626c21446d |  | note | Clause 2.3.2 - Submit details of the utility conflict including any associated survey results and your proposals for resolving the conflict to the principal for their direction, at least 10 days prior to proposed commencement of construction
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.1 - Commencement of excavation for utility adjustment work
label | bf1969ee-6882-5827-8fae-49643e0e6664 |  | note | Notification that all existing (including private property connections) utilities have been identified, their locations, elevations and set out locations for proposed utilities have been marked on the ground, and submit associated plans (including in MX and 12D format) showing their locations, including potholing and survey results, at least 20 working days prior
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 3.1 - Commencement of utility adjustment work other than excavation (for utility adjustment work not managed directly by the utility owner)
label | 5981b6cc-913a-5616-9478-c89321316047 |  | note | Submit the name of the contractor carrying out the utility adjustment work and evidence of accreditation, detailed construction work plan and program, and evidence of approval for the works, at least 5 working days prior
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6.1.4 - Award of Telstra Works Subcontract
label | 11bd62d8-12d7-5aea-bc60-48a8aff93af3 |  | note | Submit subcontract documentation, quotes received from Telstra approved Industry Specialists and advice from Telstra substantiating its selection of the preferred Telstra approved Industry Specialist
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6.1.5 - Completion of civil works (WP)
label | a1ff6d11-8520-59a3-8c6e-1782a0814f52 |  | note | Submit a copy of the civil work completion certificate issued by Telstra
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 6.1.5 - Completion of cable works (WP)
label | 56d818e7-3344-59c8-a41f-890c4f026ade |  | note | Submit a copy of the cable work completion certificate issued by Telstra
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 7.1.1 - Commencement of work within or adjacent to Jemena's Pipeline Land
label | ea0e7d85-c4ec-59de-8c16-94b9557c1080 |  | note | Copy of Permit to Work, evidence that Permit Issuing Officer has been notified and will attend the site works (if required)
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 8.1.2 - Relocation of traffic signals or modifications of the signal phasing
label | 1c796f77-d117-5fd2-8cf1-657383450bc2 |  | note | Details of the TCS modification required
holdpoint |  |  | signoff | Holdpoint
checkpoint-status |  |  | checkpoint | Clause 10.4.1 - Commencement of concrete encasement work
label | 1c93c499-a6b2-5e49-932a-e259c2689196 |  | note | Submit associated survey in MX and 12D format showing the locations of utilities to be concrete encased
holdpoint |  |  | signoff | Holdpoint