## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Stormwater and Culvert works (R11 and R16) | [5 empty] | ITC 12 - R11 and R16 Stormwater and Culvert works
checkpoint | 1 - Preparation works
label | REQUIREMENTS / REFERENCE: WHSMP, Design DWGs
label | ACCEPTANCE CRITERIA:
label | • Contact DBYD and complete excavation permit
label | • Extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Delivery of Box Culvert
label | REQUIREMENTS / REFERENCE:
label | • R16 Cl2
label | • AS1597.2
label | ACCEPTANCE CRITERIA:
label | • HP: Design requirements and procedures of AS 1597.2 submission
label | • Include in the design records, the calculations produced during both the design and verification processes.
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 3 - Delivery of Box Culvert
label | REQUIREMENTS / REFERENCE:
label | • R16 Cl3
label | • AS1597.2
label | ACCEPTANCE CRITERIA:
label | • HP:Design based on load testing, provide certification, supported by testing and calculation records, demonstrating that the design complies with the requirements of AS 1597.2 for each different culvert / load combination.
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 4 - Crack Serviceability Test for Box Culvert
label | REQUIREMENTS / REFERENCE:
label | • R16 Cl5
label | • AS1597.2
label | • B80
label | ACCEPTANCE CRITERIA:
label | • WP: Sample and test for concrete strength in accordance with TfNSW B80.
label | • Certificate of compliance in respect of test loads and other relevant details supported by verification checklists.
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 5 - Supply of Precast Concrete Members
label | REQUIREMENTS / REFERENCE: R11 Cl 2.4.1
label | ACCEPTANCE CRITERIA:
label | • HP: Submission of certified product drawings and details of methods for manufacture, testing and installation, prior to the supply of precast concrete members subject to traffic and/or earth pressure loading, or water retaining structures with capacity greater than 25 000 litres
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 6 - Certificates of Conformity (1)
label | REQUIREMENTS / REFERENCE: R11 Cl 2.6
label | ACCEPTANCE CRITERIA:
label | • HP: Certificate of Conformity (Pit / Headwall)
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 6 - Certificates of Conformity (2)
label | ACCEPTANCE CRITERIA:
label | • HP: Certificate of Conformity (Box Culverts)
label | • Submission of certificate of conformity prior to incorporation in the works of any supplied manufactured drainage product
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 7 - Supply of Rip Rap material
label | REQUIREMENTS / REFERENCE:
label | • R11 Cl 3.4.4
label | ACCEPTANCE CRITERIA:
label | • HP: Details regarding the properties and source of the rock rip rap as per R11 Cl 3.4.4.
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 8 - Survey Set Out
label | REQUIREMENTS / REFERENCE: R11 Cl 4.1.1
label | ACCEPTANCE CRITERIA:
label | • HP: Notification of set out of drainage system and any proposed design changes in locations and levels
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 9 - Unable to meet Min. Grade
label | REQUIREMENTS / REFERENCE: R11 Cl 4.2.1
label | ACCEPTANCE CRITERIA:
label | • HP: Notification that 0.5% minimum grade cannot be achieved for section(s) of open drains (if applicable)
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 10 - Excavation
label | REQUIREMENTS / REFERENCE: R11 Cl 4.3
label | ACCEPTANCE CRITERIA:
label | • WP: Excavation for Box Culvert installation and other drainage structures
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 11 - Unsuitable Foundation
label | REQUIREMENTS / REFERENCE:
label | • R11 Cl 4.3.3
label | • Table R11.2
label | ACCEPTANCE CRITERIA:
label | • HP: Replacement of inadequate foundation material (if applicable)
label | • Notify the principal of any unsuitable foundation material on the base of the trench, or poor quality material on the sides of the trench. Replace and compact material in consultation with principal
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 12 - Installation of Drainage
label | REQUIREMENTS / REFERENCE:
label | • R11 Cl 4.4.1
label | • Table R11.2
label | ACCEPTANCE CRITERIA:
label | • 95% compaction requirement for base of trench and layers around pipe
label | • Material for pipe bedding and haunch zones is Type BH Select Fill
label | • Material for pipe side and overlay zones is Type SO Select Fill
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: T166 / T173 Test Report
checkpoint | 13 - Construction
label | REQUIREMENTS / REFERENCE: R11 Cl. 4.7
label | ACCEPTANCE CRITERIA:
label | • WP: Construction of drainage structures other than box culverts
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 14 - Protective Measures
label | REQUIREMENTS / REFERENCE:
label | • R11 Cl. 4.10
label | • TfNSW G2
label | ACCEPTANCE CRITERIA:
label | • HP: Protective measures for pipes and box culvert structures from heavy construction plant or vehicles
label | • If structures will be subject to heavy construction loading prior to completion, submit protective measures to principal for approval
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 15 - Backfill and Compaction
label | REQUIREMENTS / REFERENCE:
label | • R11 Cl. 4.9
label | • R44
label | ACCEPTANCE CRITERIA:
label | • Above the pipe overlay, backfill with general fill material or other material accepted by principal
label | • Backfill in 150mm layers unless directed otherwise by the principal
label | • 95% compaction for general backfill, 102% compaction required if adjoining SMZ layer (R44)
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: T173 Test Report
checkpoint | 16 - Completion
label | REQUIREMENTS / REFERENCE: R11 Cl. 5.2
label | ACCEPTANCE CRITERIA:
label | • Survey pickup of asbuilt pit inverts (downstream and upstream) and pit locations. Survey report provided and any NCRs raised, changes picked up on WAE drawings
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Survey Conformance Report
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature