## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Geotextiles (R63) | [5 empty] | ITC 14 - R63 Geotextiles
checkpoint | 1 - Preparation works
label | REQUIREMENTS / REFERENCE: WHSMP, Design DWGs
label | ACCEPTANCE CRITERIA:
label | • Contact DBYD and complete excavation permit
label | • Extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Materials (1)
label | REQUIREMENTS / REFERENCE: R63 Cl 2.4
label | ACCEPTANCE CRITERIA:
label | • Carry out control testing on each batch of geotextile delivered to site to ensure conformity for the properties specified in Tables R63/E.1 and R63/E.2. Testing must include the mean weight of the geotextile, determined as per AS 3706.1 and AS 2001.2.13
label | • Frequency of sampling and testing as per Table R63.1
label | • WITNESS POINT: Sampling of geotextile on site. Submit to the Client: Location, date and time of sampling and person sampling
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 3 - Materials (2)
label | REQUIREMENTS / REFERENCE: R63 Cl 2.5
label | ACCEPTANCE CRITERIA:
label | • Provide a Certificate of Compliance that the geotextile complies with all the requirements of this specification for its specified usage, together with test results reported on NATA-endorsed test documents. The certificate must not be more than 12 months old.
label | • The Client may accept test certificates for tests carried out for other projects from the same batch samples taken at site for the Client.
label | • HOLD POINT: Supply of geotextile. Submit to the Client: Certificate of Compliance from the supplier, and nomination of where each strength and filtration class will be used
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | 4 - Storage, Packing, Identification and Delivery
label | REQUIREMENTS / REFERENCE: R63 Cl 3
label | ACCEPTANCE CRITERIA:
label | • Geotextiles must be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
label | • Do not store materials directly on the ground or where they may be affected by heat, dirt or damage.
text | INSPECTION:
checkpoint | 5 - Installation
label | REQUIREMENTS / REFERENCE: R63 Cl 4
label | ACCEPTANCE CRITERIA:
label | • Place the geotextiles in accordance with the Specifications and as shown on the Drawings.
label | • Unless specified otherwise, select geotextiles of the appropriate strength and filtration class in accordance with Table R63/A.1 and Table R63/E.1
label | • HOLD POINT: Placement of geotextile. Submit to the Client: Site sampling test results referred to in Clause 2.4 prior to placement of geotextile
text | INSPECTION:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature