## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 003 - R15 Kerb and Gutter | [5 empty] | A173 - Appin - ITC 003 - R15 Kerb and Gutter
checkpoint | 1 - Preparation and preliminary works
label | REQUIREMENTS / REFERENCE: Project Safety Plan, Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Works completed in accordance with Project Safety and Environment Plans
text | INSPECTION:
checkpoint | 2 - Survey set out
label | REQUIREMENTS / REFERENCE: Survey model
label | ACCEPTANCE CRITERIA:
label | • Survey set out pegs (or equivalent) to identify alignment, levels, transitions as per design
text | INSPECTION:
checkpoint | 3 - Subbase
label | REQUIREMENTS / REFERENCE: R15 Cl. 3.3, AS 2876
label | ACCEPTANCE CRITERIA:
label | • Prepare bedding layer as per drawings – SMZ
label | • Foundation layer is compacted, free of loose material and homogenous throughout
label | • Levels are within +5mm to -10mm tolerances and have been picked up by surveyor every 10m
label | • Do not undercut batters of cuttings for the purpose of kerb and gutter construction
text | INSPECTION:
checkpoint | 4 - Materials
label | REQUIREMENTS / REFERENCE: R15 Cl 2.2, R53 Cl 2.4.3
label | ACCEPTANCE CRITERIA:
label | • R53 HP: Concrete mix design submitted at least 5 days prior to works and accepted by principal
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Profiles and dimensions
label | REQUIREMENTS / REFERENCE:
label | • R15 CL 3.6
label | • Project Drawing MP-99300-FS-CIV-DWG-10
label | ACCEPTANCE CRITERIA:
label | • Profiles and dimensions must be as nominated on the Drawings
label | • Refer to Kerb Control Details drawings for kerb style and set out
label | • For kerb shapes and dimensions refer to TFNSW R0300-01 Standard Kerb and Gutter shapes
text | INSPECTION:
checkpoint | 6 - Concrete Placement
label | REQUIREMENTS / REFERENCE:
label | • R15 CL 3.7
label | • R53.3.3.1
label | • R53.3.3.2
label | ACCEPTANCE CRITERIA:
label | • R53 HP: Submit concrete pour details to principal at least 2 days prior
label | • Pour as per R53 Specification
label | • Concrete temperature is between 10-35ºC
label | • Air temperature is between 5-35ºC
label | • Clear weather, no imminent rain
label | • Concrete placed to limit segregation, compacted with internal vibrator
label | • Min. 25MPa concrete design strength adj. flexible pavement. Max 10mm nominated aggregate size for extrusion and slipform, 20mm otherwise
label | • Min. 32MPa concrete design strength adj. concrete pavement. Max 20mm nominated aggregate size
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 7 - Joints
label | REQUIREMENTS / REFERENCE: R15 Cl 3.8, R15 Cl 2.6
label | ACCEPTANCE CRITERIA:
label | • Form and prepare joints in conformity to AS 2876
label | • Provide joints in K&C of the type and at the locations shown on the Drawings or as specified in Annexure R15/A
label | • Where K&C is to be constructed alongside an existing flexible pavement, conform to the requirements shown on the Drawings or specified in Annexure R15/A1
label | • For longitudinal joints with rigid pavement base the longitudinal joint must be continuous and not deviate from 3m straight edge by +20mm for curvature.
label | • Align joints at an angle of 90° ± 6° to the line of the kerb
label | • Seal joints with sealant conforming to R83 (TfNSW 3204).
text | INSPECTION:
checkpoint | 8 - Concrete Finish
label | REQUIREMENTS / REFERENCE: R54 Cl 3.9
label | ACCEPTANCE CRITERIA:
label | • Finish concrete surface with:
label | • Steel float on face of kerb
label | • provide a broomed finish to the tops of kerbs
text | INSPECTION:
checkpoint | 9 - Stripping
label | REQUIREMENTS / REFERENCE: R53 Cl 3.3.7, AS 3610.1
label | ACCEPTANCE CRITERIA:
label | • Formwork not stripped earlier than 2 days (for external surfaces) or 1 day (for permanently hidden surfaces)
text | INSPECTION:
checkpoint | 10 - Conformity
label | REQUIREMENTS / REFERENCE: R15 Cl 4, AS 2876
label | ACCEPTANCE CRITERIA:
label | • Completed kerb and gutter conforms to design profiles and alignments
label | • Finished surfaces are uniform except at grade changes and bends, passes a straight edge test
label | • Surfaces are homogenous and free of dags
label | • Level of gutter lip does not deviate between +0mm and -10mm below the adjoining pavement surface at any point
label | • Horizontal alignment is within 20mm left / right of control line setout
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Survey Conformance Report
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature