## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 005 - R44 Foundation Treat. Loosen and Compact | [5 empty] | A173 - Appin - ITC 005 - R44 Foundation Treat. Loosen and Compact
checkpoint | 1 - Preparation works
label | REQUIREMENTS / REFERENCE: WHSMP, Design DWGs
label | ACCEPTANCE CRITERIA:
label | • Contact DBYD and complete excavation permit
label | • Extent of works set out with survey pegs
text | INSPECTION:
checkpoint | 2 - Initial works (1)
label | REQUIREMENTS / REFERENCE:
label | • R44 Cl 2.4
label | • R44 Cl 3.2
label | • R44 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • HP: Inspection after removal of unsuitable material and prior to backfilling (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Initial works (2)
label | ACCEPTANCE CRITERIA:
label | • HP (Filling): Presentation of each Lot of embankment foundation and submission of survey, notification of completion of clearing and topsoil removal, and CBR and PI results if required (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Initial works (3)
label | ACCEPTANCE CRITERIA:
label | • HP (Cutting): Presentation of each Lot of floor of cuttings and notification of completion of excavation, and CBR and PI results of material in floor of cutting (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Construction works (Type E1 & C1)
label | REQUIREMENTS / REFERENCE:
label | • R44 Cl 7.6.1
label | • R44 Cl 7.6.2
label | • R44 Annexure A2.2
label | • R44 Cl 7.3.6
label | • Table R44.10
label | • Table R44.11
label | ACCEPTANCE CRITERIA:
label | • T117, T109 Test Results: CBR ≥ 3 and PI ≤ 25 respectively
label | • T166 Test Result: Relative compaction ≥ 98% for Type C1
label | • T166 Test Result: Relative compaction ≥ 95% for Type E1
label | • T162 Test Result: 60% ≤ Moisture content ≤ 90% for type C1
label | • T162 Test Result: -2% (dry) to +2% (wet) of standard optimum for type E1
label | • Survey Report: Finished surface within tolerance of +10 mm / –40 mm of design for Type C1
label | • Survey Report: Finished surface within tolerance of +50 mm / –150 mm for Type E1
label | • Proof rolls and survey conformance results covered as part of Subgrade ITC and relevant Subgrade Lot
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Test Reports, Survey Report
checkpoint | 5 - Conformity of Completed Works
label | REQUIREMENTS / REFERENCE: R44 Cl 7.6.2
label | ACCEPTANCE CRITERIA:
label | • HP: Submission of finished surface levels and verification of conformity of each lot of Subgrade placed (test and survey as required)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature