## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 008 - R54 Medians & Traffic Island | [5 empty] | A173 - Appin - ITC 008 - R54 Medians & Traffic Island
checkpoint | 1 - Preparation
label | REQUIREMENTS / REFERENCE:
label | • Project Safety Plan
label | • Project Environment Plan
label | ACCEPTANCE CRITERIA:
label | • Works completed in accordance with Project Safety and Environment Plans
text | INSPECTION:
checkpoint | 2 - Unsuitable Material
label | REQUIREMENTS / REFERENCE: R54 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • Notify the Principal of the foundation that contain material that is unsuitable to support the proposed pavement
label | • Principal may direct the removal and replacement of this unsuitable material or some other foundation treatment in accordance with TfNSW R44.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Placing of Concrete
label | REQUIREMENTS / REFERENCE:
label | • R54 Cl 4.3
label | • R53 Cl 3.3
label | ACCEPTANCE CRITERIA:
label | • HP: Concrete mix design submitted at least 5 days prior to works and accepted by principal
label | • Min. 100 DGS20 compacted to 95% MMDD
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Proposed joints layout and reinforcement details
label | REQUIREMENTS / REFERENCE: R54 Cl 4.4
label | ACCEPTANCE CRITERIA:
label | • HP: If not shown on the drawings, markup submitted to principal showing proposed joint and reinforcement details, approved prior to concreting (if applicable)
label | • Contraction joints each 1.5m, expansion joints at max 6m and in line with adjacent kerbs
label | • Isolation joints where abutting concrete
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Concrete Placement
label | REQUIREMENTS / REFERENCE: R54 Cl 5.2.1
label | ACCEPTANCE CRITERIA:
label | • HP: Details of pattern, colour, class of finish and experience of personnel in producing patterns on concrete paving, at least 5 working days prior.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Testing
label | REQUIREMENTS / REFERENCE:
label | • R54 Cl 2.1.1
label | • R54 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • PI of Select Fill Type U as per T109 for a minimum testing of one per 200 m3 prior to placement
label | • Compaction as per TfNSW R44 submitted to principal showing proposed joint and reinforcement details, approved prior to concreting (if applicable)
text | INSPECTION:
checkpoint | 6 - Concrete Finishing and Curing
label | REQUIREMENTS / REFERENCE:
label | • R54 Cl 5
label | • R53 Cl 3.3
label | • R53 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • Broomed surface finish
label | • Concrete cured for 7 days minimum, curing process completed as agreed with principal
text | INSPECTION:
checkpoint | 8 - Conformity
label | REQUIREMENTS / REFERENCE: R54 Cl 5.3
label | ACCEPTANCE CRITERIA:
label | • Finished surface conforms to design, within a tolerance of +10mm and -5mm
label | • Any vertical step across the joint must not exceed 5 mm unless shown otherwise on the Drawings
label | • Finished surface must not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 5 mm, except at grade changes
text | INSPECTION:
label | COMMENTS / ATTACHMENTS: Survey Conformance Report
checkpoint | Tactile Indicators
label | REQUIREMENTS / REFERENCE: R54 Cl 6
label | ACCEPTANCE CRITERIA:
label | • HP: Details of proposed tactile indicator tiles, associated materials (such as adhesive), and installation method.
label | • Install tactile indicators at the locations shown on the Drawings
label | • Concrete slab clean of dust by using water jets, and any contamination using where necessary high-pressure hydro-blasting, sand/grit blasting or mechanical scabbling
label | • Install the tiles, without any voids beneath the tiles
label | • Remove any excess grout, grout film or haze
label | • Do not allow traffic over freshly grouted joints for at least 7 days, unless recommended otherwise by the manufacturer.
label | • The finished surface level of the tiled surface must comply with the requirements of Clause 5.3.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature