## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 009 - R71 Unbound Pavement Course | [5 empty] | A173 - Appin - ITC 009 - R71 Unbound Pavement Course
checkpoint | 1 - Safety Review
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • Required traffic control plans and documentation submitted & approved
text | INSPECTION:
checkpoint | 2 - Erosion and Sediment Control
label | REQUIREMENTS / REFERENCE:
label | • R71 Cl2.3
label | • G38
label | ACCEPTANCE CRITERIA:
label | • Appropriate erosion and sedimentation controls
text | INSPECTION:
checkpoint | 3 - Certified stockpiles
label | REQUIREMENTS / REFERENCE: R71 Cl 2.2
label | ACCEPTANCE CRITERIA:
label | • Statement signed by ACPL rep submitted to Principal
label | • NATA endorsed test results
label | • delivery docket
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Submission of nominated mix design
label | REQUIREMENTS / REFERENCE: R71 Cl 4.2
label | ACCEPTANCE CRITERIA:
label | • <10 days submit nominated mix design to the Principal
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Alternative Construction Method
label | REQUIREMENTS / REFERENCE: R71 Cl 5.2.2
label | ACCEPTANCE CRITERIA:
label | • Procedures, and inspection and test plan (spreading and mixing of binder)
label | • Documents verifying calibration of the spread rate at a demonstration
text | INSPECTION:
checkpoint | 6 - Design and field target spread rates
label | REQUIREMENTS / REFERENCE: R71 Cl 5.2.3
label | ACCEPTANCE CRITERIA:
label | • Determine the Design Target Spread Rate of binder in kg/m2 ( Add a minimum tolerance of 0.2 kg/m2 to the Design Target Spread Rate)
label | • Submission 14 days prior to the commencement of spreading of binder
text | INSPECTION:
checkpoint | 7 - Survey
label | REQUIREMENTS / REFERENCE: R71 Cl 7.2
label | ACCEPTANCE CRITERIA:
label | • Schedule of levels of the underlying surface
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 8 - Treatment of nonconforming lots
label | REQUIREMENTS / REFERENCE: R71 Cl 8.12
label | ACCEPTANCE CRITERIA:
label | • Submit a nonconformity report and details of your proposal to rectify or replace the lot.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 9 - Conformance of works
label | REQUIREMENTS / REFERENCE:
label | • Table G71.9
label | • R71 Cl 8.5
label | • R71 Cl 8.6
label | • R71 Cl 8.7
label | ACCEPTANCE CRITERIA:
label | • Tolerances submission for Sub-base and base layers
label | • Submission of test and survey reports
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature