## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 010 - R101 Cold milling of road | [5 empty] | A173 - Appin - ITC 010 - R101 Cold milling of road
checkpoint | 1 - Safety Review
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • Required traffic control plans and documentation submitted & approved
text | INSPECTION:
checkpoint | 2 - Erosion and Sediment Control
label | REQUIREMENTS / REFERENCE:
label | • Project Environment Plan
label | • G36 G38
label | • R44 cl 1.7
label | ACCEPTANCE CRITERIA:
label | • All erosion and sediment controls in place to protect environment and prevent contamination.
checkpoint | 3 - Permits
label | REQUIREMENTS / REFERENCE: Project Safety Plan
label | ACCEPTANCE CRITERIA:
label | • Excavation Permit approved.
text | INSPECTION:
checkpoint | 4 - Survey of Hidden Objects
label | REQUIREMENTS / REFERENCE:
label | • HP
label | • R101 Cl 3
label | ACCEPTANCE CRITERIA:
label | • HP: All hidden objects located by means of surveying, speaking to authority. Verification document marking all hidden objects and milling depths submitted to Principal.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Milling to specified cut
label | REQUIREMENTS / REFERENCE:
label | • HP
label | • R101 Cl 4.2
label | ACCEPTANCE CRITERIA:
label | • HP: Cover milled work area and the remove cold milling machine and cleaning plant from the site after milling ready for inspection by Principal.
label | • Principal notified 24 hours in advance of completion to inspect.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Temporary ramps – Opening traffic to milled roads
label | REQUIREMENTS / REFERENCE: R101 4.9
label | ACCEPTANCE CRITERIA:
label | • The dimensions of ramps must be as follows:
label | – Transverse Joints - Minimum taper of 2.5m for each 50mm variation in level
label | – Longitudinal Joints - Provide a ramp of minimum 1.0 m length for each 50 mm variation in levels
label | – Interface with structures - Ramps must have a minimum taper length of 1.5 metres for each 50 mm depth of cut
text | INSPECTION:
checkpoint | 7 - Tolerances
label | REQUIREMENTS / REFERENCE: R101 Cl 4.1
label | ACCEPTANCE CRITERIA:
label | • As per R101 Cl 4.1 table
text | INSPECTION:
checkpoint | 8 - Clean up and disposal
label | REQUIREMENTS / REFERENCE:
label | WP
label | R101
label | Cl4.10
label | ACCEPTANCE CRITERIA:
label | • WP: Final Sweeping and loose aggregate measurement completed prior to opening road to traffic. Number of loose material does not exceed 20 particles per square meter.
label | • Principal notified of time and location prior to commencement of cleaning.
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature