## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 012 - R116 HDD Graded Asphalt (AC20, AC14) | [5 empty] | A173 - Appin - ITC 012 - R116 HDD Graded Asphalt (AC20, AC14)
checkpoint | 1 - Preparation works
label | REQUIREMENTS / REFERENCE: R116 Cl 3
label | ACCEPTANCE CRITERIA:
label | • Existing surface has been cleaned ahead of asphalting works taking place
label | • Existing surface has tack coat / spray seal prepared as per Project Drawings and as agreed with Client
text | INSPECTION:
checkpoint | 2 - Materials (1)
label | REQUIREMENTS / REFERENCE: R116 Cl 2.3.5, 3.5.1
label | ACCEPTANCE CRITERIA:
label | • HP: Submission of nominated mix design details for consideration by the Client, at least 7 working days before the nominated mix(es) is (are) proposed to be placed
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Materials (2)
label | ACCEPTANCE CRITERIA:
label | • HP: Commencement of paving using the nominated mix(es) including trial section. Submit details of min. temperature asphalt will be delivered to the paver, min. temperature initial compaction of the asphalt can still commence, and method of temperature measurement
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Pre-planning and initial works (1)
label | REQUIREMENTS / REFERENCE: R116 Cl 3.6.3, Cl 3.8.6
label | ACCEPTANCE CRITERIA:
label | • HP: Placing of asphalt in nonconforming layer thicknesses, for corrective courses and tie-ins to an existing pavement (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Pre-planning and initial works (2)
label | ACCEPTANCE CRITERIA:
label | • HP: Submission of verification checklists and test results from trial section
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Non-conformances (1)
label | REQUIREMENTS / REFERENCE: R116 Cl 5.8.5, Annexure B2.3
label | ACCEPTANCE CRITERIA:
label | • HP: Rectification or replacement of a nonconforming lot. Submission of Nonconformity Report and details of proposal for rectification or replacement of the Lot (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Non-conformances (1)
label | ACCEPTANCE CRITERIA:
label | • HP: Where Tensile Strength Ratio (TSR) has been found to be < 70% and air voids in the laboratory compacted mix nonconforming, HP for further production of the nominated mix (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 5 - Changes to approved mix
label | REQUIREMENTS / REFERENCE: R116 Annexure F
label | ACCEPTANCE CRITERIA:
label | • HP: Progression to a higher RAP Approval Level (if applicable)
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 6 - Conformance of works
label | REQUIREMENTS / REFERENCE: R116 Annexure A, Cl 5.5.1
label | ACCEPTANCE CRITERIA:
label | • Survey Report: Conformance heights as per below requirements
label | Table R116.11 - Course Surface Level Tolerances
label | –– Course –– ¦¦ –– Tolerances (mm) ––
label | Wearing Course ¦¦ -0 / +10
label | Top Intermediate course ¦¦ -5 / +10
label | Other Intermediate Courses ¦¦ -10 / +10
label | Corrective course ¦¦ -15 / +10
label | • Test Reports: Testing for Resilient Modulus and Wheel Tracking Depth (as measure of deformation resistance) for each asphalt mix
label | • Test Reports: Testing for Ride Quality for finished pavement / wearing course only
label | • Lot Package: Submission of Lot Package provided by asphalt subcontractor
text | INSPECTION:
label | COMMENTS / ATTACHMENTS:
label | • Survey Report(s)
label | • Test Report(s)
label | • Lot Package
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature