## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 013 - R131 Installation of Guide Posts | [5 empty] | A173 - Appin - ITC 013 - R131 Installation of Guide Posts
checkpoint | 1 - Materials
label | REQUIREMENTS / REFERENCE:
label | • TfNSW 3411
label | • R131 Cl 2
label | ACCEPTANCE CRITERIA:
label | • Conform to TfNSW 3411
label | • Backfill – use excavated material. If not, imported material with same characteristic
text | INSPECTION:
checkpoint | 2 - Install
label | REQUIREMENTS / REFERENCE:
label | • TfNSW 3411
label | • R131 Cl 3.1
label | • R131 Cl 3.2
label | • AS 1742.2
label | • R131 Cl3.4
label | ACCEPTANCE CRITERIA:
label | • Uniform distance away from the pavement edge
label | • Adjacent to an embankment or at the surrounding natural surface level, install the guide posts inside edge is in line with the outside edge of the shoulder
label | • Located within a cutting, install the guide posts on the pavement side of the table drain such that the flow of water in the drain is not impeded.
label | • Embedment depth of 500 mm for rigid and timber guide posts, and a minimum embedment depth of 350 mm for flexible guide posts
text | INSPECTION:
checkpoint | 3 - Orientation
label | REQUIREMENTS / REFERENCE: R131 Cl3.3
label | ACCEPTANCE CRITERIA:
label | • Wide face = 100 mm (right angle to the centre line of the roadway)
label | • Height = 100 mm wide face (facing traffic in the near lane)
label | • Delineators – Retroreflective delineators facing the traffic is as follows
label | – o Red Delineator = driver’s left hand side
label | – o White Delineator = driver’s right hand side for undivided (two way) carriageways
label | – o Yellow Delineator = driver’s right hand side on medians separating traffic travelling in opposite directions for divided (one way) carriageways
label | • Undivided (two way) carriageways will be fitted with two delineators: red on the face displayed to drivers in the lane nearest and one white delineator on the opposite face.
text | INSPECTION:
checkpoint | 4 - Tolerances
label | REQUIREMENTS / REFERENCE:
label | • R131 Cl 3.6
label | • Table R131.2
label | ACCEPTANCE CRITERIA:
label | • Plan – 200mm longitudinally and 100mm transversely of the plan position (control line ref)
label | • Height - <25mm of uniform height (nominally 1,000mm)
label | • Vertically – Within 3 from the true vertical position
text | INSPECTION:
checkpoint | 5 - Removal and Disposal
label | REQUIREMENTS / REFERENCE:
label | • R131 Cl 4
label | • TfNSW G36
label | ACCEPTANCE CRITERIA:
label | • Removal guide post, any part or component that is in-ground
label | • Backfill all holes and compact (150mm layers)
label | • Dispose of all guide posts that have been removed off site.
label | • If practical, recycle any unwanted guide posts
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature