## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 015 - R142 Reflective RPMs | [5 empty] | A173 - Appin - ITC 015 - R142 Reflective RPMs
checkpoint | 1 - Retroreflective raised pavement markers
label | REQUIREMENTS / REFERENCE:
label | ACCEPTANCE CRITERIA:
label | • Comply with the requirements of AS/NZS 1906.3.
label | • Use only retroreflective raised pavement markers prequalified by the Principal
label | • All markers must be identifiable for at least 12 months after the initial installation
text | INSPECTION: | Prior to installation
checkpoint | 2 - Materials certification
label | REQUIREMENTS / REFERENCE: R142 Cl 2.2
label | ACCEPTANCE CRITERIA:
label | • Submit a statement, signed by you (or your suppler if you are purchasing markers from a manufacturer), stating that materials meet the respective requirements of Clause 2
label | • Includes test results from a laboratory registered by NATA for the specified tests or by a laboratory approved by the Principal. Such certificates must be valid for tests conducted no more than 36 months previously.
text | INSPECTION: | At least 7 days prior to the proposed use of materials
checkpoint | 3 - Setting out
label | REQUIREMENTS / REFERENCE: R142 Cl 3.1
label | ACCEPTANCE CRITERIA:
label | • Ensure that all retroreflective raised pavement markers are placed in accordance with the nominated drawings, RMS referenced documents, and to the tolerances required by this Specification.
label | • Provide notification to the principal that the set out is complete
text | INSPECTION: | Prior to application
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 4 - Performance criteria of retroreflective pavement marker
label | REQUIREMENTS / REFERENCE: R142 Cl 4
label | ACCEPTANCE CRITERIA:
label | (a) > 80% of the total number of markers installed for 12months after the initial installation under the Contract; and
label | (b) not fall below this level at any time during this period; and
label | (c) the maximum number of consecutive ineffective retroreflective raised pavement markers installed under the contract must not exceed three retroreflective raised pavement markers..
label | • Defined as effective if it is retained on the pavement surface and the retroreflective element is functional, in accordance with Cl 4.1.
label | • Installed must be 100% within 30 calendar days after Completion or otherwise advised.
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature