## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 016 - R143 Signposting | [5 empty] | A173 - Appin - ITC 016 - R143 Signposting
checkpoint | 1 - Preparation works
label | REQUIREMENTS / REFERENCE:
label | • WHSMP
label | • Design DWGs
label | • R143 Cl 3.2
label | ACCEPTANCE CRITERIA:
label | • Contact DBYD and complete excavation permit
label | • Locations of signs set out by surveyor
label | • HP: Construction of sign support structure foundations – Submit to the Client the proposed location and orientation of each sign support structure
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Removal, Modification and Relocation of Existing Signs
label | REQUIREMENTS / REFERENCE: R143 Cl 4
label | ACCEPTANCE CRITERIA:
label | • Carry out removal, modification, or relocation as per drawings or principal direction
text | INSPECTION:
checkpoint | 3 - Construction works
label | REQUIREMENTS / REFERENCE: R143 Cl 3
label | ACCEPTANCE CRITERIA:
label | • Sign foundation structure completed as per construction drawings
label | • Sign face(s) installed as per construction drawings
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature