## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 017 - R145 Linemarking | [5 empty] | A173 - Appin - ITC 017 - R145 Linemarking
checkpoint | 1 - Proposed Materials
label | REQUIREMENTS / REFERENCE: R145 Cl 2.1.4
label | ACCEPTANCE CRITERIA:
label | • Using Waterborne Paint, as Specified
text | INSPECTION:
checkpoint | 2 - Marking position set-out
label | REQUIREMENTS / REFERENCE: R145 Cl 3.2.4
label | ACCEPTANCE CRITERIA:
label | • Notify that set-out is complete, principal may inspect set out prior to authorising release of HP.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Surface Preparation
label | REQUIREMENTS / REFERENCE: R145 Cl 3.1
label | ACCEPTANCE CRITERIA:
label | • If other preparation is required
label | • Surface Area and around it to be dry and free of dirt
label | • Existing markings material is flaking or chipping, proposed surface prep method agreement to be obtained from Principal
label | • Prepare the marking or surface suitably before applying the pavement marking material when material to be applied may be incompatible
text | INSPECTION:
checkpoint | 4 - Application of Pavement Marking
label | REQUIREMENTS / REFERENCE: R145 Cl 3.4
label | ACCEPTANCE CRITERIA:
label | • Where practical apply permanent pavement marking on asphalt wearing course surfaces only after 7 days. It is not intended that we can comply as linemarking must be replaced same shift for safety.
label | • Strictly in accordance with the manufacturers’ instructions and guidelines
label | • Apply all longitudinal lines using a self propelled machine, unless otherwise approved by the Principal.
text | INSPECTION:
checkpoint | 5 - Reinstatement of linemarking after road works
label | REQUIREMENTS / REFERENCE: R145 cl 3.5
label | ACCEPTANCE CRITERIA:
label | • Reinstate as soon as practical.
label | • Temporary RPMs can be used for up to 10 days after opening to traffic after which permanent pavement markings must be reinstated.
text | INSPECTION:
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature