## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 018 - R178 Vegetation | [5 empty] | A173 - Appin - ITC 018 - R178 Vegetation
checkpoint | 1 - Delivery of imported general purpose topsoil
label | REQUIREMENTS / REFERENCE: R178 CL2.1.3
label | ACCEPTANCE CRITERIA:
label | • HP: At least 7 days prior to delivery, a statement signed by you verifying that the topsoil complies with specified requirements.
label | • The Principal will consider the submitted documents and may inspect the test records prior to authorising the release of the Hold Point.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Application of Fertiliser
label | REQUIREMENTS / REFERENCE: R178 CL2.4
label | ACCEPTANCE CRITERIA:
label | • WP: Notify Principal, not less than 2 working days prior to the intended time of applying fertiliser, that the unopened bags or containers of fertiliser are available for inspection on Site.
text | INSPECTION:
text | WITNESS POINT NUMBER:
holdpoint | WITNESS POINT
checkpoint | 3 - Use of seed pre-treated off site
label | REQUIREMENTS / REFERENCE: R178 CL3.3
label | ACCEPTANCE CRITERIA:
label | • HP: At least 3 working days prior to delivery, submit the accompanying certificate showing the species, variety, weight and place of pre-treatment.
label | • The Principal will consider the submitted documents and may inspect the seed prior to authorising the release of the Hold Point.
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature