## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | A173 - Appin - ITC 019 - R201 Fencing | [5 empty] | A173 - Appin - ITC 019 - R201 Fencing
checkpoint | 1 - Material approvals and preparation works
label | REQUIREMENTS / REFERENCE:
label | • WHSMP
label | • Design DWGs
label | • R201 Cl 3.11
label | ACCEPTANCE CRITERIA:
label | • Materials approved for use by the Client
label | • Locations of fence and fenceposts set out by surveyor and as per drawing
label | • HP: Submission of Certificate of Compliance for materials and components
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 2 - Pre-planning of works
label | REQUIREMENTS / REFERENCE: R201 Cl 4.1
label | ACCEPTANCE CRITERIA:
label | • HP: Submission of proposed connection arrangement of new fencing to existing fencing
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | 3 - Construction works
label | REQUIREMENTS / REFERENCE: R201 Cl 4.4.2
label | ACCEPTANCE CRITERIA:
label | • HP: Removal of trees with trunk diameter exceeding 100mm (if required)
label | • Fenceposts, panels and connections installed as per drawings and as agreed on site
text | INSPECTION:
text | HOLD POINT NUMBER:
holdpoint | HOLD POINT
checkpoint | QA ENGINEER / SPE / PE SIGN OFF
text | Name:
text | Date:
label | Signature