## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | b6d06063-c647-4901-bd28-622d6a3c37ca |  | checklist | FIXING OF PANEL |  |  |  |  | Yes | FIXING OF PANEL | 0d736da1-c027-4fa3-91a8-8c78f2fd2453
checkpoint-status | 46c2073c-aff1-4bd6-9fd9-f65e04a25099 |  | checkpoint | Silicon seal on bolt/screw head installed during installation.
checkpoint-status | e700ec3b-6227-41da-b0c6-c3db7fdfed3d |  | checkpoint | Sub-gutter has not been damaged short or missing gasket.
checkpoint-status | f1192c7f-7da9-47aa-bd33-25c1936f5a68 |  | checkpoint | The foam block at the base of the mullion is on
checkpoint-status | 708f9e42-90a9-457f-9878-2db7b2c3a8af |  | checkpoint | The correct type of sealant used (DC-791 Silicone)
checkpoint-status | bbf68a35-d44d-4613-ba08-fc97a1bc65ee |  | checkpoint | The panel within tolerance in Hor, Vert, and Plumb Plane (H,V,P)
checkpoint-status | dfb3b758-90ef-465c-b8dd-363a95a11331 |  | checkpoint | RL to top of panel correct, refer set-out tag drawings
checkpoint-status | 24696e0d-e93c-4d57-baac-25ba6fc0c71b |  | checkpoint | Correct panel installed in the location
checkpoint-status | 133567c6-2625-44c0-a1b6-822fbac614aa |  | checkpoint | Head mullion bracket installed bead seal and silicone seal on a head screw.
checkpoint-status | ee3436cd-7bf7-40cb-8e54-42e7bf2d2430 |  | checkpoint | The mullion joint at the back of the panel is within tolerance
checkpoint-status | 98fdf011-9a96-4e22-8c06-a4096ab8eb1e |  | checkpoint | Mullion gaskets not missing, cut, or damaged
checkpoint-status | a871bc48-6c77-4af1-b9ce-06885057ae8f |  | checkpoint | No damage to Backpan/insulation
checkpoint-status | 076c501c-7832-469a-965a-bf57fd61c0f2 |  | checkpoint | No damage to aluminium
checkpoint-status | 8e4bb530-03a2-4733-8b4f-fb6ac4650619 |  | checkpoint | No damage to the Glass
checklist-flat | c7cd8cbc-520e-4ee8-b528-9690c5b5355c |  | checklist | Structural Opening Handover Checklist |  |  |  |  | Yes | Structural Opening Handover Checklist | 0dbc899a-0064-4c20-b13b-6ddda874d336
checkpoint-status | 2716304b-b166-48ef-adb6-44ab3ead12d2 |  | checkpoint | Access to the floor/s?
checkpoint-status | 66b94fc4-499e-42aa-819d-de623588c859 |  | checkpoint | Handrails / Edge Protection/s?
checkpoint-status | 86951eea-6bcf-4b56-b2c9-7bc5c96c45e5 |  | checkpoint | Safety Line?
checkpoint-status | 116e9631-3aa7-48d5-86d9-1c57b5f5b758 |  | checkpoint | Are concrete/opening surfaces clear for work?
checkpoint-status | a68ec291-a8a6-4b8e-be21-cf4c7fef553c |  | checkpoint | Surface Preparation (Inc. Vapor Shield and Waterproofing)?
checkpoint-status | ef3f5cf5-d004-4f02-a2f9-6d5d76012aee |  | checkpoint | Electricity/Power Supply / Lights (1-Phase and/or 3-Phase)?
checkpoint-status | 702947b2-f0df-4483-9169-e412a5881456 |  | checkpoint | Access provided?
checkpoint-status | f2262186-4552-438f-ab07-c10078134ad2 |  | checkpoint | Are gridlines visible and accessible (datum marked and confirmed)?
checkpoint-status | dd103984-cf20-4ba4-a9d4-d4fd58c76c2f |  | checkpoint | Structure complete and built as per approved Shop Drawing?
checkpoint-status | 7c84dcdf-4289-4a7a-a5a5-4cecfd080829 |  | checkpoint | Structural fagade opening within tolerance (+/- 10mm total in each direction)?
checkpoint-status | 60dc84b6-5043-4199-83c6-2f7f96fb94f6 |  | checkpoint | Floor slabs pan tolerance max. +/- 20mm over the height of the building?
checkpoint-status | 46c383d1-732c-4543-88ec-9b6304bcf13c |  | checkpoint | Has there been any opening not handover at this level/elevation?
checkpoint-status | fdd0b5ca-a623-4ec3-a924-3f3c39ff93cb |  | checkpoint | Handover
text | 188b99e8-5f04-51c4-8cd5-8574ba77d5cd |  | text | Structure Handed-over by:
checklist-flat | d1f0ed9a-7066-4f34-b82d-f3a9045e0f12 |  | checklist | Project Details |  |  |  |  | Yes | Project Details | 1f01ad77-eae1-4b98-ac73-1c55a015bb7a
checkpoint-status | b9347d64-3485-435b-a108-448fc9f7d0f8 |  | checkpoint | Details
text | edceb43d-f245-5b81-8d96-8cf0deae4160 |  | text | Site Address:
text | 495f0aa6-4834-5327-8b4f-57ab1e9887b0 |  | text | Main Contractor Detail:
text | e96d7fe3-19f9-5800-9c95-3393968f3aa1 |  | text | Project Manager Details
text | 16c4718e-c008-5c84-8e46-968263e4f8be |  | text | Site Manager:
text | 8fef4737-a856-5b22-9cbf-58595432ffcc |  | text | Sub Contractor:
checkpoint-status | c39f3e3d-fdae-4db4-8dd1-2e264df54827 |  | checkpoint | Latest for Construction Drawing (attachment)
checkpoint-status | d0b50de9-c9eb-4010-ac0f-763b924e9348 |  | checkpoint | Scope of Work (attachment)
checkpoint-status | cd9f69f7-a20d-4d05-8155-0361f9d1637d |  | checkpoint | Additional Pre Start Doc
checklist-flat | 6dc9928a-83b1-4cf2-9215-13f21531ab78 |  | checklist | SILL FLASHING, SILL TRAY, & SEISMIC HEAD |  |  |  |  | Yes | SILL FLASHING, SILL TRAY, & SEISMIC HEAD | 48270490-38ce-49e8-a84e-c488649dd342
checkpoint-status | 0a839527-9b4d-430c-90d2-5fbf1a6389e3 |  | checkpoint | Sill flashing install.
checkpoint-status | 08856106-0daf-4aa8-b6e9-21ce033c8c87 |  | checkpoint | Sill tray install in the correct RL & GL
checkpoint-status | feb004cf-dc93-425f-b40b-f20277851792 |  | checkpoint | Drainage slots / Weep holes do not block, clear, and correct.
checkpoint-status | 9dbe9cd8-09ae-4039-b869-34a27da11a04 |  | checkpoint | Aluminum surface cleaned and applied with primer prior to sealant works.
checkpoint-status | 80647b5a-c4da-4263-8efe-ffe6dc42fffd |  | checkpoint | The number of rear splices installed correctly, seal complete, bed sealed to the gutter, and fillet sealed at the end
checkpoint-status | b272ae26-faf2-4ab3-a232-90974569e6fd |  | checkpoint | Front splice installed, seal complete, bed sealed to the gutter, and fillet sealed at the end.
checkpoint-status | 1b4cffe0-c34b-4427-a553-33be136e7651 |  | checkpoint | The correct type of sealant used (DC 791)
checkpoint-status | c344e36c-1566-47bc-8c79-523b79990448 |  | checkpoint | Site water test on the gutter, performed
checkpoint-status | 85890605-0aae-4555-9e30-aa0ccf3042ab |  | checkpoint | Seismic Head installed in the correct RL & GL.
checkpoint-status | 6b06e96d-3a0c-4634-b30b-a5b5a5c96ed7 |  | checkpoint | Hed splice installed correctly, seal complete, bed sealed to the seismic Head, and fillet sealed at the end.
checkpoint-status | e6055263-1222-465e-80c8-6aa172eaa45e |  | checkpoint | Drilling, cleaning, fixing screws, applying sealant in the hole, and cap sealing the heads of fixings.
checkpoint-status | 32610d30-9ca5-4610-9fc1-daff768499a0 |  | checkpoint | Complete sealant on all perimeters including air seal.
checklist-flat | 70b9ee35-e69c-46c3-996a-a22f2f3989c4 |  | checklist | Aluminum Cladding |  |  |  |  | Yes | Aluminum Cladding | d4794c4e-7fb9-488a-b995-3c11b3ba2b7e
checkpoint-status | aa7076c3-4420-42e4-ba46-1c16f5b3a50e |  | checkpoint | Silicone seal on the Head installed during installation
checkpoint-status | eb4ba32a-a191-4af7-a112-93c6cd9767a4 |  | checkpoint | Angle bracket/subframe to fit
checkpoint-status | 4f72e2df-2440-4d7e-a84b-b5810d8dcf75 |  | checkpoint | Alum cladding installed in the correct level and plumb.
checkpoint-status | 8991186c-ca9e-455d-b100-59f9dc38f0b1 |  | checkpoint | The drain hole is not blocked
checkpoint-status | 5784f6a0-16bd-4115-8d41-a137c0d33fe6 |  | checkpoint | Sealant complete
checkpoint-status | 31402429-9b97-4a44-b20d-ce6dd931813b |  | checkpoint | Scratches to aluminum
checkpoint-status | 2aee6078-bdf1-4db1-ad99-d56188fbac18 |  | checkpoint | Protecting tape not removed
text | efed525c-53ee-5166-9d17-d05474e204c3 |  | text | Other: