## Sheet1
Management of Site Fire Risk as part of CPU (Checklist)
Folder Setup
Existing Folders | Existing Folders | New Folder Setup | New Sub Folder Setup | Existing Folders |  | 2 Same Checklist every SUB Folder (Rename different) | Area | Check Required
|  |  |  | New Folder Setup |  |  |  |  | Pass
|  |  |  | New Sub Folder Setup | 1 Checklist Name | Management of Site Fire Risk as part of CPU (Morning) | Carpark Stairs | Check fire doors are closed on Levels : | Fail
[7 empty] | Amenities End |  | Comment
INVERCARGILL CENTRAL | Management of Site Fire Risk as part of CPU | 2022-07-01 | 2022-07-19 |  | 2 Checklist Name | Management of Site Fire Risk as part of CPU (Evening) |  | L1 & L2
2022-07-20
2022-07-21
2022-07-22
|  |  | 2022-07-23 |  |  |  | Area | Check Required
2022-07-24
|  |  | 2022-07-25 |  |  |  | Carpark Stairs | No combustible material within 5m of doors on levels : | Pass
|  |  | 2022-07-26 |  |  |  | Amenities End |  | Fail
|  |  | 2022-07-27 |  |  |  |  | L3 & L4 | Comment
2022-07-28
2022-07-29
2022-07-30
|  |  | 2022-07-31 |  |  |  | Area | Check Required
|  | 2022-08-01 | 2022-08-01 |  |  |  | Carpark Level 3 Plant Deck | Plant Deck Level 3 – | Pass
|  |  | 2022-08-02 | [5 empty] | Fail
|  |  | 2022-08-03 |  |  |  |  | No fuel within 5m | Comment
2022-08-04
2022-08-05
2022-08-06
|  |  | 2022-08-07 |  |  |  | Area | Check Required
2022-08-08
|  |  | 2022-08-09 |  |  |  |  | Bulkheads by Carpark Stairways – | Pass
|  |  | 2022-08-10 |  |  |  | Bulkheads Farmers Carpark Stairwell |  | Fail
|  |  | 2022-08-11 |  |  |  |  | No combustibles or Hot works within 5m | Comment
2022-08-12
2022-08-13
2022-08-14
|  |  | 2022-08-15 |  |  |  | Area | Check Required
|  |  | 2022-08-16 |  |  |  |  | Farmers Carpark Stairwell –
|  |  | 2022-08-17 |  |  |  |  | No combustible material within 5m | Pass
|  |  | 2022-08-18 |  |  |  | Farmers Carpark Stairwell |  | Fail
|  |  | 2022-08-19 |  |  |  |  | L3 & L4 | Comment
2022-08-20
2022-08-21
2022-08-22
|  |  | 2022-08-23 |  |  |  | Area | Check Required
2022-08-24
|  |  | 2022-08-25 |  |  |  | Carpark |  | Pass
|  |  | 2022-08-26 |  |  |  | Tay St Stairway | No combustible material within 5m of stairway | Fail
|  |  | 2022-08-27 | [5 empty] | Comment
2022-08-28
2022-08-29
2022-08-30
|  |  | 2022-08-31 |  |  |  | Area | Check Required
|  | 2022-09-01 | 2022-09-01
|  |  | 2022-09-02 |  |  |  | Emergency Egress Ground Floor | No combustibles within 5m of emergency egress exterior. | Pass
|  |  | 2022-09-03 | [5 empty] | Fail
|  |  | 2022-09-04 | [5 empty] | Comment
2022-09-05
2022-09-06
2022-09-07
|  |  | 2022-09-08 |  |  |  | Area | Check Required
|  |  | 2022-09-09 |  |  |  | Bike Store Beside Ramp | Bike store is clear of combustibles within 5m | Pass
|  |  | 2022-09-10 | [5 empty] | Fail
|  |  | 2022-09-11 | [5 empty] | Comment
|  |  | 2022-09-12 |  |  |  | Area | Check Required
2022-09-13
|  |  | 2022-09-14 |  |  |  | Sprinkler Tank | Checked sprinkler tank level
|  |  | 2022-09-15 |  |  |  |  | (Red arrow down is full) | Pass
|  |  | 2022-09-16 | [5 empty] | Fail
|  |  | 2022-09-17 | [5 empty] | Comment
2022-09-18
2022-09-19
|  |  | 2022-09-20 |  |  |  | Mall Toilet Corridor Gate | Gate in toilet hallway is not in use | Pass
|  |  | 2022-09-21 | [5 empty] | Fail
|  |  | 2022-09-22 | [5 empty] | Comment
|  |  | 2022-09-23 |  |  |  | Area of carpark with no sprinkler coverage - range pipes in but no heads | Road cones and frog system to make carparks effected as being blocked off. A map to be prepared and ABL Management to check twice daily | Pass
|  |  | 2022-09-24 | [5 empty] | Fail
|  |  | 2022-09-25 | [5 empty] | Comment
|  |  | 2022-09-26 |  |  |  | Level 1 offices area - sprinkler coverage - defeciant due to the gib ceiling | ABL Management instructed to remove the content under the bulkhead
|  |  | 2022-09-27 | [5 empty] | Pass
|  |  | 2022-09-28 | [5 empty] | Fail
|  |  | 2022-09-29 | [5 empty] | Comment
2022-09-30
|  | 2022-10-01 | 2022-10-01
2022-10-02
2022-10-03
2022-10-04
2022-10-05
2022-10-06
2022-10-07
2022-10-08
2022-10-09
2022-10-10
2022-10-11
2022-10-12
2022-10-13
2022-10-14
2022-10-15
2022-10-16
2022-10-17
2022-10-18
2022-10-19
2022-10-20
2022-10-21
2022-10-22
2022-10-23
2022-10-24
2022-10-25
2022-10-26
2022-10-27
2022-10-28
2022-10-29
2022-10-30
2022-10-31
|  | 2022-11-01 | 2022-11-01
2022-11-02
2022-11-03
2022-11-04
2022-11-05
2022-11-06
2022-11-07
2022-11-08
2022-11-09
2022-11-10
2022-11-11
2022-11-12
2022-11-13
2022-11-14
2022-11-15
2022-11-16
2022-11-17
2022-11-18
2022-11-19
2022-11-20
2022-11-21
2022-11-22
2022-11-23
2022-11-24
2022-11-25
2022-11-26
2022-11-27
2022-11-28
2022-11-29
2022-11-30
|  | 2022-12-01 | 2022-12-01
2022-12-02
2022-12-03
2022-12-04
2022-12-05
2022-12-06
2022-12-07
2022-12-08
2022-12-09
2022-12-10
2022-12-11
2022-12-12
2022-12-13
2022-12-14
2022-12-15
2022-12-16
2022-12-17
2022-12-18
2022-12-19
2022-12-20
2022-12-21
2022-12-22
2022-12-23
2022-12-24
2022-12-25
2022-12-26
2022-12-27
2022-12-28
2022-12-29
2022-12-30
2022-12-31
|  | 2023-01-01 | 2023-01-01
2023-01-02
2023-01-03
2023-01-04
2023-01-05
2023-01-06
2023-01-07
2023-01-08
2023-01-09
2023-01-10
2023-01-11
2023-01-12
2023-01-13
2023-01-14
2023-01-15
2023-01-16
2023-01-17
2023-01-18
2023-01-19
2023-01-20
2023-01-21
2023-01-22
2023-01-23
2023-01-24
2023-01-25
2023-01-26
2023-01-27
2023-01-28
2023-01-29
2023-01-30
2023-01-31