## Breakdown
Aquacraft Plumbing Limited (Kevin Hickman - Riccarton Park)
Project Build QA
Stage 3 - THB11, THB13
Underslab
THB11 (TH33,34,35,36)
[5 empty] | Underslab Drainage | Pre-populate | F - S - Underslab plumbing
THB13 (TH37,38, 39)
[5 empty] | Underslab Drainage | Pre-populate | F - S - Underslab plumbing
First Fix
THB11 (TH33,34,35,36)
[5 empty] | TH33 | Pre-populate | Pre - S - Plumbing First Fix
[5 empty] | TH34 | Pre-populate | Pre - S - Plumbing First Fix
[5 empty] | TH35 | Pre-populate | Pre - S - Plumbing First Fix
[5 empty] | TH36 | Pre-populate | Pre - S - Plumbing First Fix
THB13 (TH37,38, 39)
[5 empty] | TH37 | Pre-populate | Pre - S - Plumbing First Fix
[5 empty] | TH38 | Pre-populate | Pre - S - Plumbing First Fix
[5 empty] | TH39 | Pre-populate | Pre - S - Plumbing First Fix
Second Fix
THB11 (TH33,34,35,36)
[5 empty] | TH33 | Pre-populate | Post - S - Plumbing Second Fix
[5 empty] | TH34 | Pre-populate | Post - S - Plumbing Second Fix
[5 empty] | TH35 | Pre-populate | Post - S - Plumbing Second Fix
[5 empty] | TH36 | Pre-populate | Post - S - Plumbing Second Fix
THB13 (TH37,38, 39)
[5 empty] | TH37 | Pre-populate | Pre - S - Plumbing First Fix
[5 empty] | TH38 | Pre-populate | Pre - S - Plumbing First Fix
[5 empty] | TH39 | Pre-populate | Pre - S - Plumbing First Fix
Compliance Documentation
|  | Stage 3 - THB11, THB13 |  |  |  | Pre-populate | Cst - S - Completion Documents

## Checklist
Type | Name | Value
checklist | F - S - Underslab plumbing
checkpoint | Correct gradiant of the pipework achieved
checkpoint | Pipe wrapped/protected and acceptable
checkpoint | Flood test completed and acceptable
checkpoint | Pipe capped and acceptable
checkpoint | All undefloor plumbing works installed as per specifications
Type | Name | Value
checklist | Pre - S - Plumbing First Fix
section | Preinstall QA
checkpoint | Permission to begin work obtained
checkpoint | Drawings correct issue and construction set
Checkpoint | Area is left clean and tidy and work can begin
holdpoint | Raise remedial/Request signoff
section | First fix QA
Checkpoint | Materials supplied as per specification
Checkpoint | Heights and locations checked
Checkpoint | Hot water supply lines run over shortest distance
Checkpoint | Any required brackets or reinforcements supplied
Checkpoint | Pipes fixed and supported appropriately to specification
Checkpoint | Penetrations are trade sealed
Checkpoint | All pipework neatly clipped and tidy
Checkpoint | All pipework secured/siliconed
Checkpoint | FWG Flange is recessed into floor
Checkpoint | Water pressure testing completed and passed
Checkpoint | Checked for drips on water and waste lines
Checkpoint | Left over materials tidied up and removed
Checkpoint | Gauge removed from pipe system
Checkpoint | Area is left clean and tidy
Checkpoint | Work is 100% competed to required specifications
holdpoint | Raise remedial/Request signoff
Type | Name | Value
checklist | Post - S - Plumbing Second Fix
section | Preinstall QA
checkpoint | Permission to begin work obtained
checkpoint | Drawings correct issue and construction set
Checkpoint | Area is left clean and tidy and work can begin
section | Second fix QA
Checkpoint | Fit-off materials match schedule or drawings
Checkpoint | Setouts/min clearances as per specification
Checkpoint | Water pipework maintained test throughout
Checkpoint | No debris in floor wastes or subs
Checkpoint | Hot water cylinder tempered to required outlet temp
Checkpoint | Flanges installed on all pipework to vermin proof
Checkpoint | All soil pipes are connected to sanitary sewer
Checkpoint | No crossovers, hot on left and cold on right
Checkpoint | All fixtures are siliconed down and splash sealed
Checkpoint | Shower hoses are fitted with non returns
Checkpoint | Area is left clean and tidy
Checkpoint | Work is 100% competed to required specifications
holdpoint | Raise remedial/Request signoff