## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 9ee98997-72ae-4726-87cd-dba76f040888 |  | checklist | Apartment - Second Fix |  |  |  |  | Yes | QA - Apartment - Second Fix | 00cd63e3-7325-4fd2-b4dd-f87e55c4e152
checkpoint-status | da569708-743d-495f-86af-17d7627ed512 |  | checkpoint | Emergency lights installed (Battery plugged in)?
checkpoint-status | 8f7d690a-dbb6-4d24-9f9a-570589d1aea0 |  | checkpoint | General lights installed?
checkpoint-status | b425b358-0e51-4573-8d29-0d51ebed68c4 |  | checkpoint | Light switches installed?
checkpoint-status | 5362ead5-dc51-4955-ac0e-bf5032ebc7c8 |  | checkpoint | Power points installed?
checkpoint-status | 66e4955d-4fc3-4072-ba23-60f239da1edf |  | checkpoint | Hub powerpoint installed?
checkpoint-status | 0a4b3bac-c9c6-4038-989a-67a5975dd487 |  | checkpoint | Hot Water Cylinder installed?
checkpoint-status | 2b5c65a8-aa1f-496a-9384-8a7c61f15820 |  | checkpoint | Mechanical Fan interface fit off?
checkpoint-status | db2d07d1-d1eb-480a-a147-d578d8227ce8 |  | checkpoint | Wall heaters installed (Bath and Rooms)?
checkpoint-status | 4914520f-da2f-49ba-a76e-8b11fe90b32d |  | checkpoint | Switchboard completed (inc. all covers)?
checkpoint-status | 3b4f67de-efc5-4f7a-b1bc-1a131692fd06 |  | checkpoint | Tested & Commissioned?
checklist-flat | d4318133-a90c-4275-9668-b12754580bbb |  | checklist | [5 empty] | Yes | SYS - QA - Second Fix Electrical - Common Area | 04423e01-5d06-4a39-9813-e305580a965c
checkpoint-status | 0bcd8413-13b4-4cea-a184-8944f19a5fd1 |  | checkpoint | Emergency lights installed (Battery plugged in)?
checkpoint-status | ae748c94-e7f0-4f18-b154-8883a7a9e4e0 |  | checkpoint | General lights installed?
checkpoint-status | 526d257e-86b3-4dce-915b-60d28205fe61 |  | checkpoint | Light switches/panels installed?
checkpoint-status | 847b26df-13bb-4ed1-9e17-fa8b174343f7 |  | checkpoint | Motion sensor installed?
checkpoint-status | 8057d595-8b54-455e-aa57-43589199850d |  | checkpoint | Tested & Commissioned?
checklist-flat | 50b0769a-e3bf-455c-9f5d-9d99ebf9983f |  | checklist | Common Area - Second Fix |  |  |  |  | Yes | QA - Common Area - Second Fix | 04929db1-4887-4890-97e9-b13186a980f5
checkpoint-status | df1c9c22-085c-4c35-ab1a-43aab1deac45 |  | checkpoint | Emergency lights installed (Battery plugged in)?
checkpoint-status | 298dddea-80ea-410d-b52b-92eadaec141d |  | checkpoint | General lights installed?
checkpoint-status | 6ef96bfe-eacd-4736-bd39-ac79535035cc |  | checkpoint | Light switches/panels installed?
checkpoint-status | 1198896a-b6b5-485f-bd90-d29b8609a9d2 |  | checkpoint | Power points installed?
checkpoint-status | 30331eb6-f85c-4785-95c0-c7b13300a5e7 |  | checkpoint | Motion sensor installed?
checkpoint-status | 53c62500-26a1-4752-a323-39dabd33c855 |  | checkpoint | Tested & Commissioned?
checklist-sectioned | fa6b1d00-4502-47e1-b80d-862ca596269b |  | checklist | Exterior Lights Power First Fix Checklist |  |  |  |  | Yes | QA - Exterior Lights Power First Fix Checklist | 0e68f461-838d-47fa-b5cb-cb30902c5ca9
checkpoint-group | cf1580be-db75-47c2-9dd8-5c0515545e7e |  | section | Cabling
checkpoint-status | abc0d7d4-4f01-4849-8679-bd341c2c7369 |  | checkpoint | Lighting circuit/s cable installed?
checkpoint-status | f101780c-59ee-4672-ae67-6e427e2b1531 |  | checkpoint | DALI + KNX Cables installed?
checkpoint-status | 31f6c28c-1756-48cb-b0a5-e307f208bea7 |  | checkpoint | Emergency lighting circuit/s cable installed?
checkpoint-status | f0047acb-6852-47eb-af0b-bd146ce5f12a |  | checkpoint | Power circuit/s cable installed?
checkpoint-status | 44275206-95aa-4ac1-b3d5-591ed60998e2 |  | checkpoint | Photocell cable installed? {LIGHTING CONTROL CABLE}
checkpoint-status | 979310e3-168a-412e-ad91-55b4db1e68aa |  | checkpoint | DB Chart checked - All circuits installed?
checkpoint-status | e5eb661a-2415-4469-8dbe-feca39891f2a |  | checkpoint | Lighting controls plans checked - all DALI & Relay channels installed.
checkpoint-group | 1edf792d-a143-4c85-a84f-2028abaf09ab |  | section | Wall
checkpoint-status | 02d82dd9-146d-4582-9b50-3ad95bf0b021 |  | checkpoint | Wall lights penetrating in final location. Check weatherproofing with ICON
checkpoint-status | 6514b122-952f-4fd4-8eb5-03dba1c5116e |  | checkpoint | Powerpoints penetrating in final location. Check weatherproofing with ICON
checkpoint-status | 2ce19d30-9fcd-48df-8a98-0303bf64b84d |  | checkpoint | Photocell cable penetrating in final location. Check weatherproofing with ICON
checkpoint-group | 961db2cb-9ac5-4bb6-bd0c-349ff6306220 |  | section | Ceiling
checkpoint-status | f686097d-ba53-4b51-ae2a-935047b65e70 |  | checkpoint | Cables to lights in final location & fixed in place?
checkpoint-status | 909f7a34-2af1-4b79-88e0-06a3e7e097d6 |  | checkpoint | Conduit or Catenary wire installed tidy and fixed?
checklist-flat | 0733910a-0251-43d3-8641-febf181674ea |  | checklist | Stairwell Second Fix Checklist |  |  |  |  | Yes | QA - Stairwell Second Fix Checklist | 765b8ada-0f83-42c4-958f-3873783bf7b6
checkpoint-status | f1a83ea9-55da-4ff3-ae89-d05de7c10b7e |  | checkpoint | Emergency lights installed (Battery plugged in)?
checkpoint-status | b846b1d5-351f-4757-bfce-04c5c1b2bb2d |  | checkpoint | Surface lights installed?
checkpoint-status | 81740aea-1059-4e35-ab7a-848b8c5cd92b |  | checkpoint | Motion sensor installed?
checkpoint-status | f69cb1a8-c5ea-48f7-a3d8-615ba309d1c2 |  | checkpoint | Conduit fixed and lids installed?
checkpoint-status | fc6975bd-ed68-400c-a151-6fcfda3a3c04 |  | checkpoint | 2nd fix complete & area left tidy?
checkpoint-status | 12293729-8278-4a43-a562-92905e07c400 |  | checkpoint | Tested & Commissioned?
checklist-flat | 0cd3fff3-b1aa-4cd7-903b-3a5897772709 |  | checklist | SYS - QA - Second Fix Electrical - Apartments |  |  |  |  | Yes | SYS - QA - Second Fix Electrical - Apartments | 77ece8df-1c18-4226-aff3-b2068e994a6c
checkpoint-status | af10aed1-0b94-4cdc-ab90-85dd1fb6451a |  | checkpoint | Emergency lights installed (Battery plugged in)?
checkpoint-status | 65ecbfaf-a5d6-4bb3-be0c-23dfa4300856 |  | checkpoint | General lights installed?
checkpoint-status | d41a14b9-b93c-4923-af3d-dbe1ddc15c04 |  | checkpoint | Light switches installed?
checkpoint-status | f6e4eb7a-3266-48cf-8775-a397e865afef |  | checkpoint | Power points installed?
checkpoint-status | 358208d4-8417-4686-98d3-b1d20c2b6cd7 |  | checkpoint | Hub powerpoint installed?
checkpoint-status | 86363b41-60ce-4525-83d1-122e282a5196 |  | checkpoint | Tested & Commissioned?
checklist-flat | de6b0586-12e1-475f-80f2-2426d1ab61a3 |  | checklist | SYS - QA - Second Fix Electrical |  |  |  |  | Yes | SYS - QA - Second Fix Electrical | 7a6b9973-6c8d-4082-a324-5cc671890a88
checkpoint-status | 86c16b06-7af8-4bc0-a4c5-2ddb3879352f |  | checkpoint | General lights installed?
checkpoint-status | 91e4ef9a-fd3e-4684-b07b-457065d160de |  | checkpoint | Light switches/panels installed?
checkpoint-status | 86190264-d402-423c-8b68-97c9492639d7 |  | checkpoint | Power points installed?
checkpoint-status | cf6da29b-e446-4384-80d4-5bf2bf35f2f3 |  | checkpoint | Motion sensor installed?
checkpoint-status | 807a9649-40d3-49ae-996a-c74de156f61b |  | checkpoint | Tested & Commissioned?
checklist-sectioned | 56272451-1b68-449a-9a04-f2886443a15e |  | checklist | Common Area - First Fix |  |  |  |  | Yes | QA - Common Area - First Fix | 7d2d5974-506f-483c-84b2-45141b9eaea1
checkpoint-group | 801d8989-1b0e-402f-8e88-5635f1833bab |  | section | Cabling
checkpoint-status | 18602ac8-4d3d-477d-b6e2-71cd9228aa3e |  | checkpoint | Lighting circuit/s cable installed?
checkpoint-status | 72b7ff6b-081a-4340-afd1-67a68e609b44 |  | checkpoint | DALI + KNX Cables installed?
checkpoint-status | 6670c743-d5d9-4e06-912a-bd8f199f41e4 |  | checkpoint | Emergency lighting circuit/s cable installed?
checkpoint-status | 5bd458d4-47bd-4ddd-a9dd-fcdc8e92313a |  | checkpoint | Power circuit/s cable installed?
checkpoint-status | 00b5982f-5031-4083-bdff-bb7bcf7dd0a1 |  | checkpoint | DB Chart checked - All circuits installed?
checkpoint-status | 6d159cd0-57d9-45f6-8311-1d89a6047392 |  | checkpoint | Lighting controls plans checked - all DALI & Relay channels installed.
checkpoint-group | 3633f848-adc5-4d3b-b801-6fe2ee7b7109 |  | section | Wall
checkpoint-status | 238d83e9-5b52-4f1e-a36a-b31a559abc45 |  | checkpoint | Light switch cables in flush box in final location?
checkpoint-status | 554c533c-c1d9-4899-8c35-3882a6b7a322 |  | checkpoint | Power cables in flush box in final location?
checkpoint-status | 05e35b99-4697-4ee7-a74d-bc9120451656 |  | checkpoint | Firepads installed and recorded if applicable?
checkpoint-group | 69238c0d-c766-4846-b4a3-dad3a83e7e8e |  | section | Ceilings
checkpoint-status | 829c6af9-d60f-451c-ae64-1af00aae7e66 |  | checkpoint | Cables to motion sensors fixed in place?
checkpoint-status | cd0ed12b-0786-4012-ad28-37db78633639 |  | checkpoint | Cables to lights in final location & fixed in place?
checkpoint-status | 407117b6-cc3e-4703-afe0-66505057ef53 |  | checkpoint | Conduit or Catenary wire installed tidy and fixed?
checkpoint-status | 74398bbc-3b14-4aa5-84ed-93e9894de531 |  | checkpoint | Cables fixed to catenary with cable ties?
checklist-flat | 91e20b78-333d-43dc-9f43-3c541084f459 |  | checklist | First Fix - Switchboard |  |  |  |  | Yes | QA - First Fix - Switchboard | 84cae616-5cec-43ad-8560-c9ca04827cf6
checkpoint-status | a2465db3-dc9b-4e0a-88f9-36225adcd28e |  | checkpoint | Check board is built correctly to shop drawings.
checkpoint-status | 4fdc6d07-9b42-4652-9b9c-9c18cd43b75c |  | checkpoint | Check all labelling correct.
checkpoint-status | 47177af6-fe95-40e1-be77-80f2e177c285 |  | checkpoint | All lighting controls installed?
checkpoint-status | c3bb4c2c-1573-455c-9021-23a619cbfd7d |  | checkpoint | All MCBs and RCDS installed?
checklist-flat | 3030bbba-cf7f-413e-989d-e2ed4457185c |  | checklist | Exterior Lights Power Second Fix Checklist |  |  |  |  | Yes | QA - Exterior Lights Power Second Fix Checklist | 87caa49d-ba07-4dbe-a036-6aeddeb3cc32
checkpoint-status | 3cd4a76c-d35e-4fca-b84f-006fd27a4a67 |  | checkpoint | Emergency lights installed (Battery plugged in)?
checkpoint-status | 0e8228f4-755e-4f2a-925b-cff58f8a8f9a |  | checkpoint | General lights installed?
checkpoint-status | 68dbc408-630a-458c-8129-04cab7689ab4 |  | checkpoint | Powerpoints installed?
checkpoint-status | 976b0e71-014e-4fbf-a31f-bd27291ac512 |  | checkpoint | Tested & Commissioned?
checklist-flat | 0d244ba0-ed58-4d30-944f-e9ecfcd71e04 |  | checklist | Cable Trays |  |  |  |  | Yes | QA - Cable Trays Checklist | 9c48a216-7b2b-4abf-a2b0-3588c7a1df17
checkpoint-status | b4071c20-32a4-4f51-9176-531173fe4ed3 |  | checkpoint | All tray installed in zone complete?
checkpoint-status | 18dec6b4-191d-490f-8330-f8deb70d7cc5 |  | checkpoint | Seismic completed?
checkpoint-status | 44e4ea25-e170-4c95-8b8c-52e794fa0d26 |  | checkpoint | Record any changes include photos
checklist-flat | a8287677-9351-4fd0-b770-1fd3ec47f868 |  | checklist | Second Fix - Switchboard |  |  |  |  | Yes | QA - Second Fix - Switchboard | 9e04db9b-97ec-41c5-9a2a-f170b81cbdb7
checkpoint-status | 5a3d59e2-77cd-46ed-8394-cff948c3473a |  | checkpoint | Board fixed in place?
checkpoint-status | 8e30be25-8b67-4849-bdb9-509513d91e1b |  | checkpoint | Submains fit off?
checkpoint-status | 4bb3310c-8aa5-4260-9fd4-f57854f66145 |  | checkpoint | Sub circuits fit off?
checkpoint-status | 8d60efc4-039a-46cd-a409-240de2d76102 |  | checkpoint | All circuit changes recorded, include photos
checkpoint-status | 696b17b1-ae46-4578-9aaa-9bfc07f04332 |  | checkpoint | Switchboard live tested? - Separate Document
checkpoint-status | bff8a26a-3d9c-4c2e-bf94-c53911120c0a |  | checkpoint | Subcircuits live tested? Separate Document
checklist-sectioned | 2f6324f2-bbf4-4450-9f37-a670fe2ae2fe |  | checklist | Stairwells First Fix Checklist |  |  |  |  | Yes | QA - Stairwells First Fix Checklist | c5452f12-00d0-48ba-b5ee-c2dc592edb53
checkpoint-group | 9ca123f6-1a86-4c8d-8144-e82b9eda8ee6 |  | section | Cabling
checkpoint-status | edee749a-0701-407c-bca3-a29596d45c7f |  | checkpoint | Light circuit/s run + labelled?
checkpoint-status | 406633e8-3f31-493f-bec6-d9108c21e8ce |  | checkpoint | DALI + KNX Cables installed?
checkpoint-status | 16b81189-c989-4573-9678-c200e5f02cad |  | checkpoint | Power circuit/s run + labelled?
checkpoint-status | 0632f0bc-147a-4a53-af67-9e475c2ba6ff |  | checkpoint | Emergency light circuit run + labelled?
checkpoint-status | 78fae610-b2bf-413d-945f-334697ded9e4 |  | checkpoint | DB Chart checked - All circuits installed?
checkpoint-status | f5613672-53f6-4f9f-b47d-1090fe92d759 |  | checkpoint | Lighting controls plans checked - all DALI & Relay channels installed.
checkpoint-group | f2a21279-8e8c-46d4-accf-a98c05823bda |  | section | Wall
checkpoint-status | 03e8ff35-dfe4-4649-a89a-fde8cac2efe6 |  | checkpoint | Light switch and Power point flush boxes & cables installed?
checkpoint-status | 63a9637b-5fca-45b2-9755-bd72294600ec |  | checkpoint | Wall light nogs and cable in place?
checkpoint-group | 87c5ae52-45da-4503-a3de-154a217a0802 |  | section | Ceiling
checkpoint-status | daa2545f-9eb1-4153-9124-a56889b9abeb |  | checkpoint | Cables to motion sensors fixed in place?
checkpoint-status | 73fef139-1044-49ce-b48b-be1da56024c3 |  | checkpoint | Cables to lights in final location & fixed in place?
checklist-sectioned | 028aa9db-bd17-4539-8ee9-17ffc0809914 |  | checklist | Apartment - First Fix |  |  |  |  | Yes | QA - Apartment - First Fix | da2172a9-efe3-43a6-9c9d-fbfde489e752
checkpoint-group | b959763a-580f-4bbf-b676-d5754b0fc053 |  | section | Cabling
checkpoint-status | 357209fd-927e-419e-9edc-debfff7586de |  | checkpoint | Lighting circuit/s cable installed?
checkpoint-status | 8ef258a2-7422-4c37-943f-07e0e1a18821 |  | checkpoint | Emergency lighting circuit/s cable installed?
checkpoint-status | c84ed98c-de45-45dc-9298-7c36ab3782ff |  | checkpoint | General power circuits installed?
checkpoint-status | 8d24f856-af69-4c7a-acad-369067a3ee92 |  | checkpoint | HWC circuit installed?
checkpoint-status | fe760626-fd86-45f8-b586-4945eae1b708 |  | checkpoint | Kitchen power circuits installed?
checkpoint-status | bb51d920-92be-49cf-af29-a0ceb26b0fc1 |  | checkpoint | Kitchen Earth cable installed?
checkpoint-status | 5aff75b7-c14c-409d-a21e-cf7b411280a0 |  | checkpoint | Fan Control cabling installed?
checkpoint-status | cd65a2e0-87c3-4416-b967-6a5f49482f47 |  | checkpoint | Laundry circuit installed?
checkpoint-status | 66f75dce-5995-4310-8f21-ba4c60623cb1 |  | checkpoint | Heater/s circuits installed?
checkpoint-status | 52e60b85-7e5a-444a-8e40-e03acd5e9e81 |  | checkpoint | Submain Installed?
checkpoint-status | 5ca48b81-657b-4417-80bd-506883d775fa |  | checkpoint | Oven circuit installed?
checkpoint-status | 3cd0af19-9e22-4180-a971-55d258481c95 |  | checkpoint | Hob circuit installed?
checkpoint-status | 59194375-6789-4852-96db-672d14132c62 |  | checkpoint | Data Hub circuit installed?
checkpoint-status | d7cd4088-bc54-46a6-97b4-08e8c0e49d98 |  | checkpoint | DB Chart checked - All circuits installed?
checkpoint-group | 7e7ee022-6d56-4ba3-919f-7d7265ab4bfe |  | section | Wall
checkpoint-status | 15499569-cd04-4e0a-b073-f27c9dcfd6e5 |  | checkpoint | DB installed?
checkpoint-status | a9993af3-d9b9-4257-bd8b-4afe983f442d |  | checkpoint | Light switch cables in flush box in final location?
checkpoint-status | bcb8543e-9dc0-4908-9999-8d63f4094995 |  | checkpoint | Power cables in flush box in final location?
checkpoint-status | 54ce05e1-f40c-434b-8a9d-f9e6cc834862 |  | checkpoint | Data hub cable inside box?
checkpoint-status | 87d9b09a-08f0-493b-8b12-08ada9ee8367 |  | checkpoint | Kitchen Flush Boxes in correct locations?
checkpoint-status | 5a287e92-2c00-44f7-bab9-b99e9d1b7de7 |  | checkpoint | Bathroom heater nog and cable in place?
checkpoint-status | 8885619b-1936-4ab1-957c-479bc01eb5ce |  | checkpoint | Bathroom mirror light nog and cable in place?
checkpoint-status | d685f041-a210-4700-8934-8af8caacf759 |  | checkpoint | Firepads installed and recorded if applicable?
checkpoint-group | 1adb95df-cbc9-4e74-9ab3-7205018da725 |  | section | Ceilings
checkpoint-status | ec9089ec-3113-461a-a191-2da30552101f |  | checkpoint | Surface Lighting nogs and cable in place?
checkpoint-status | 9a936e56-7380-43d3-98e7-e696e921c4da |  | checkpoint | Cables to lights in final location & fixed in place?
checkpoint-status | c6e6a478-1fe4-4c95-b3fa-dfc4d506776e |  | checkpoint | Conduit or Catenary wire installed tidy and fixed?
checkpoint-status | 1a04c72a-3e09-4c8e-b59f-4f1e76b51815 |  | checkpoint | Cables fixed to catenary with cable ties?
checklist-flat | a44d9dcc-09fc-4425-b6e3-16d7a94fc1ad |  | checklist | Exterior Ducts Pits Checklist |  |  |  |  | Yes | QA - Exterior Ducts Pits Checklist | e20fb2a0-2bae-4cfb-9791-fe9643c3abc4
checkpoint-status | 2f7edf5c-723b-49bc-9177-1616f9ea0636 |  | checkpoint | Ducts Installed include photos
checkpoint-status | a02688aa-9047-4b4d-821b-6e33d9e2d021 |  | checkpoint | Pits installed include photos
checkpoint-status | e1ffe636-6b1b-4a56-9853-062803fb7a1d |  | checkpoint | Record measurements and dims for asbuilt
checklist-sectioned | a2e540ba-8439-43e4-a8f2-0039ceb12364 |  | checklist | SYS - First Fix Electrical |  |  |  |  | Yes | SYS - First Fix Electrical | eff8f0b1-25a4-40cb-9e31-203ccda04c08
checkpoint-group | 171e9769-6784-43c1-84af-b2d590281e75 |  | section | Cabling
checkpoint-status | c2ae068b-fe1b-44b0-b066-154ba87f0307 |  | checkpoint | Lighting circuit/s cable installed?
checkpoint-status | 94b00bfd-a76b-45ed-a934-171201aa3adc |  | checkpoint | Emergency lighting circuit/s cable installed?
checkpoint-status | 798c96d8-1f8f-4b4e-b509-38f257154507 |  | checkpoint | General power circuits installed?
checkpoint-status | 184a8f95-0d5a-456d-9010-2d9416ccfc39 |  | checkpoint | HWC circuit installed?
checkpoint-status | 80b26171-971e-4506-a36b-7f6a12bc1c79 |  | checkpoint | Kitchen power circuits installed?
checkpoint-status | 6c4d1168-98a2-48b7-917c-22c03c8a2be5 |  | checkpoint | Fan Control cabling installed?
checkpoint-status | 47a25797-5133-4250-aa1d-3c4f48a8acd4 |  | checkpoint | Laundry circuit installed?
checkpoint-status | 43fbbf03-373b-4933-8670-373d98ac6722 |  | checkpoint | Heater/s circuits installed?
checkpoint-status | c7a5dcb8-8465-4568-81b4-791f21402503 |  | checkpoint | Oven circuit installed?
checkpoint-status | 97fa2348-2c47-4352-82fe-c413fd5080e6 |  | checkpoint | Hob circuit installed?
checkpoint-status | 7acbcc8a-bbc6-4cd4-80da-bc6b43c5923c |  | checkpoint | Data Hub circuit installed?
checkpoint-status | 165acf19-1cfb-4d2a-8d01-614598ec52e8 |  | checkpoint | DB Chart checked - All circuits installed?
checkpoint-group | 95f814c7-d6b6-4c2a-8f1f-e097c946dd64 |  | section | Wall
checkpoint-status | a2000e4c-58e2-48b3-9d4f-fc2f4bc2f518 |  | checkpoint | DB installed?
checkpoint-status | 9f59edfa-e9bb-46af-a5bc-1666462e47c7 |  | checkpoint | Light switch cables in flush box in final location?
checkpoint-status | 8dc73661-94c1-4bb2-8d16-4a852fb8adfb |  | checkpoint | Power cables in flush box in final location?
checkpoint-status | ed2ad4a0-919f-4402-991f-a35e40fe65e1 |  | checkpoint | Data hub cable inside box?
checkpoint-status | 22fa5525-c18d-4bfd-ada9-ccd9a5866745 |  | checkpoint | Kitchen Flush Boxes in correct locations?
checkpoint-status | d405ac61-3bf6-4352-b193-4f1844e35961 |  | checkpoint | Bathroom mirror light nog and cable in place?
checkpoint-status | 8e7e74fa-7a9a-4bfe-959f-e9d233665dca |  | checkpoint | Firepads installed and recorded if applicable?
checkpoint-group | 5e9f86b8-8ece-42ba-a84d-151c2497ccb5 |  | section | Ceilings
checkpoint-status | 866b2d9a-a940-4456-adb9-f6c4050dd815 |  | checkpoint | Surface Lighting nogs and cable in place?
checkpoint-status | b0aed460-6606-4151-a1af-d8f60da0481f |  | checkpoint | Cables to lights in final location & fixed in place?
checkpoint-status | 7300147c-ca68-4ab8-8066-06ceb375d40d |  | checkpoint | Conduit or Catenary wire installed tidy and fixed?
checkpoint-status | 6542121e-0c87-4388-9a24-beaba9e812a1 |  | checkpoint | Cables fixed to catenary with cable ties?
checklist-sectioned | 01c2f4d8-e438-4139-a21c-123dcbbd5cf4 |  | checklist | SYS - First Fix Electrical - Building C - 105-C |  |  |  |  | Yes | SYS - First Fix Electrical - Building C - 105-C | feaa48d6-f91e-4d80-a27c-6388a0208ee9
checkpoint-group | 86feff18-bb19-42d1-8239-db16feb2c3c9 |  | section | Wall
checkpoint-status | ab671bf6-e661-4101-aa1d-20ad19afb9bf |  | checkpoint | DB installed?
checkpoint-status | 84857366-5f3e-4a56-8d50-983f71943c94 |  | checkpoint | Light switch cables in flush box in final location?
checkpoint-status | 8e583656-32fe-4307-8767-8458d652a2c4 |  | checkpoint | Power cables in flush box in final location?
checkpoint-status | 4383a1f4-d81a-4ca1-ad8b-f251adf5587f |  | checkpoint | Data hub cable inside box?
checkpoint-status | 1e141fd9-3d88-4b5c-be70-e50e6dd896dc |  | checkpoint | Kitchen Flush Boxes in correct locations?
checkpoint-status | 1a4fcca5-d9c9-4cd9-863c-d062785657bd |  | checkpoint | Bathroom mirror light nog and cable in place?
checkpoint-status | 99b72e8f-6e01-4593-986c-cd77e790d675 |  | checkpoint | Firepads installed and recorded if applicable?
checkpoint-group | 85f43f52-12cd-48cd-af26-2138cb2d4629 |  | section | Ceilings
checkpoint-status | 301c4d62-8029-4f58-ba9a-9c07cadaa784 |  | checkpoint | Surface Lighting nogs and cable in place?
checkpoint-status | 601320c4-1ecf-4bac-985e-4024493c5f06 |  | checkpoint | Cables to lights in final location & fixed in place?
checkpoint-status | 1ac05163-e772-4533-9a55-2598847012ac |  | checkpoint | Conduit or Catenary wire installed tidy and fixed?
checkpoint-status | 139e7b4c-1d6e-439c-8374-7679e637dcd5 |  | checkpoint | Cables fixed to catenary with cable ties?