## Sheet1
type | name
checklist | Basement 5 Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Grilles and OBD’s installed
checkpoint | Volume control dampers installed
checkpoint | Fire dampers installed and tested
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | Lobby A/C correctly installed
checkpoint | A/C drain installed and tested
checkpoint | Linear grilles installed with foam on boxes to avoid leakage
checkpoint | Builders works completed
checkpoint | Builders works completed
checkpoint | Check approved drawings for approved conduit sizes, order correct conduit sizes and components.
checkpoint | Check conduits and components for any damage prior to installation.
checkpoint | Check approved drawings for approved conduit runs and locations
checkpoint | Install required junction boxes at required/approved locations.
checkpoint | Install conduit by securing to metal frame work to avoid conduit sitting on concrete frame work. Ensure there is some distance between the conduits.
checkpoint | Use adhesive that is used for joining PVC conduit. Ensure all joins are sealed correctly.
checkpoint | Where possible check conduits prior to concrete poor to check for any accidental damage by other trades
checklist | Basement 2 Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Grilles and OBD’s installed
checkpoint | Volume control dampers installed
checkpoint | Fire dampers installed and tested
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | Lobby A/C correctly installed
checkpoint | A/C drain installed and tested
checkpoint | Linear grilles installed with foam on boxes to avoid leakage
checkpoint | Fans installed correctly
checkpoint | Fan direction is correct
checkpoint | Builders works completed
checkpoint | Builders works completed
checkpoint | Check approved drawings for approved conduit sizes, order correct conduit sizes and components.
checkpoint | Check conduits and components for any damage prior to installation.
checkpoint | Check approved drawings for approved conduit runs and locations
checkpoint | Install required junction boxes at required/approved locations.
checkpoint | Install conduit by securing to metal frame work to avoid conduit sitting on concrete frame work. Ensure there is some distance between the conduits.
checkpoint | Use adhesive that is used for joining PVC conduit. Ensure all joins are sealed correctly.
checkpoint | Where possible check conduits prior to concrete poor to check for any accidental damage by other trades
checklist | Roof Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Duct capped and sealed from weather
checkpoint | Over flashings on all roof penetrations correctly installed and sealed
checkpoint | Cooling towers installed correctly
checkpoint | Chemical dosing piped up and tested
checkpoint | Heat pump boilers installed correctly
checkpoint | Pumps installed and levelled up correctly
checkpoint | Condenser water pipes installed, labelled and pressure tested
checkpoint | Fan installed correctly
checkpoint | Check fan direction is correct
checkpoint | Volume control and non-return dampers installed
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | MSSB’s installed
checkpoint | Roof cleaned
checkpoint | Builders works completed
checklist | Ground Floor Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Grilles and OBD’s installed
checkpoint | Volume control dampers installed
checkpoint | Fire dampers installed and tested
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | All A/C correctly installed
checkpoint | A/C drains installed and tested
checkpoint | Condenser water pipes installed, and pressure tested
checkpoint | Linear grilles installed with foam on boxes to avoid leakage
checkpoint | Fans installed correctly
checkpoint | Fan direction is correct
checkpoint | MSSB installed
checkpoint | Builders works completed
checkpoint | Builders works completed
checkpoint | Check approved drawings for approved conduit sizes, order correct conduit sizes and components.
checkpoint | Check conduits and components for any damage prior to installation.
checkpoint | Check approved drawings for approved conduit runs and locations
checkpoint | Install required junction boxes at required/approved locations.
checkpoint | Install conduit by securing to metal frame work to avoid conduit sitting on concrete frame work. Ensure there is some distance between the conduits.
checkpoint | Use adhesive that is used for joining PVC conduit. Ensure all joins are sealed correctly.
checkpoint | Where possible check conduits prior to concrete poor to check for any accidental damage by other trades
checklist | Basement 4 Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Grilles and OBD’s installed
checkpoint | Volume control dampers installed
checkpoint | Fire dampers installed and tested
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | Lobby A/C correctly installed
checkpoint | A/C drain installed and tested
checkpoint | Linear grilles installed with foam on boxes to avoid leakage
checkpoint | Fans installed correctly
checkpoint | Fan direction is correct
checkpoint | MSSB installed
checkpoint | Builders works completed
checkpoint | Builders works completed
checkpoint | Check approved drawings for approved conduit sizes, order correct conduit sizes and components.
checkpoint | Check conduits and components for any damage prior to installation.
checkpoint | Check approved drawings for approved conduit runs and locations
checkpoint | Install required junction boxes at required/approved locations.
checkpoint | Install conduit by securing to metal frame work to avoid conduit sitting on concrete frame work. Ensure there is some distance between the conduits.
checkpoint | Use adhesive that is used for joining PVC conduit. Ensure all joins are sealed correctly.
checkpoint | Where possible check conduits prior to concrete poor to check for any accidental damage by other trades
checklist | Basement 3 Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Grilles and OBD’s installed
checkpoint | Volume control dampers installed
checkpoint | Fire dampers installed and tested
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | Lobby A/C correctly installed
checkpoint | A/C drain installed and tested
checkpoint | Linear grilles installed with foam on boxes to avoid leakage
checkpoint | Fans installed correctly
checkpoint | Fan direction is correct
checkpoint | Builders works completed
checkpoint | Builders works completed
checkpoint | Check approved drawings for approved conduit sizes, order correct conduit sizes and components.
checkpoint | Check conduits and components for any damage prior to installation.
checkpoint | Check approved drawings for approved conduit runs and locations
checkpoint | Install required junction boxes at required/approved locations.
checkpoint | Install conduit by securing to metal frame work to avoid conduit sitting on concrete frame work. Ensure there is some distance between the conduits.
checkpoint | Use adhesive that is used for joining PVC conduit. Ensure all joins are sealed correctly.
checkpoint | Where possible check conduits prior to concrete poor to check for any accidental damage by other trades
checklist | Level 1-20 Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Grilles and OBD’s installed
checkpoint | Volume control dampers installed
checkpoint | Fire dampers installed and tested
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | Lobby A/C correctly installed
checkpoint | Lobby A/C drains installed and tested
checkpoint | Linear grilles installed with foam on boxes to avoid leakage
checkpoint | Condenser water pipes installed, and pressure tested
checkpoint | Builders works completed
checklist | Basement 1 Checklist
checkpoint | Duct installed, sealed up and levelled
checkpoint | Grilles and OBD’s installed
checkpoint | Volume control dampers installed
checkpoint | Fire dampers installed and tested
checkpoint | Fire penetrations and fire caulking completed
checkpoint | Fire penetrations labelled and documented
checkpoint | Lobby A/C correctly installed
checkpoint | A/C drain installed and tested
checkpoint | Linear grilles installed with foam on boxes to avoid leakage
checkpoint | Fans installed correctly
checkpoint | Fan direction is correct
checkpoint | Builders works completed
checkpoint | Check approved drawings for approved conduit sizes, order correct conduit sizes and components.
checkpoint | Check conduits and components for any damage prior to installation.
checkpoint | Check approved drawings for approved conduit runs and locations
checkpoint | Install required junction boxes at required/approved locations.
checkpoint | Install conduit by securing to metal frame work to avoid conduit sitting on concrete frame work. Ensure there is some distance between the conduits.
checkpoint | Use adhesive that is used for joining PVC conduit. Ensure all joins are sealed correctly.
checkpoint | Where possible check conduits prior to concrete poor to check for any accidental damage by other trades