## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 200d244d-0c47-48a8-accf-666077390601 |  | checklist | Water Pump Commissioning |  |  |  |  | Yes | Water Pump Commissioning | 03f75588-1ecd-43ae-abb2-542838710aaa
checkpoint-group | b1d4c5df-7fc9-4cef-9d50-26697d9d9d0e |  | section | Pump setup
checkpoint-status | 66baba65-6e08-47d1-964d-3cbe1efecce9 |  | checkpoint | Connections welded correctly
checkpoint-status | 7f5deb54-bf46-4087-8963-dfa5ce8197b4 |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | b29f3076-7bb3-4705-ac0a-802340f3dd89 |  | checkpoint | Valves fitted correctly
checkpoint-group | 089f58c5-7be2-4a5f-8b9d-06b00a111dcd |  | section | Pumps
checkpoint-status | 069d3f59-595e-416f-847c-3048478e8ad0 |  | checkpoint | Pump 1 Startup level
checkpoint-status | f385f80b-1717-413d-befa-695a3552bdcd |  | checkpoint | Pump 2 Startup level
checkpoint-status | 18deea4c-abfd-4ed5-b9d5-3e459a47b449 |  | checkpoint | Pump 1 kick out level
checkpoint-status | c9e2a36a-6e7d-476f-8d8f-0b01c3ba5ceb |  | checkpoint | Pump 2 kick out level
checkpoint-group | 4dc974ef-b151-41e7-982b-672d0a3f5031 |  | section | General
checkpoint-status | fd09fd48-a69b-40c9-a16d-783204346bff |  | checkpoint | low level alarm test
checkpoint-status | 66b93d00-03a0-4b52-b3a7-e7d554750088 |  | checkpoint | Tanks clear of debris
checkpoint-status | 4f93f51f-af05-452b-bb61-d2caedb1c18d |  | checkpoint | Low level pump shut off
checkpoint-status | a11cf1ee-6f86-4505-adb1-bb1cc0d47596 |  | checkpoint | Impeller clear and free
checkpoint-status | 38da2a7b-dd5d-4d0e-915c-34ec833c7839 |  | checkpoint | Installers name & date works completed
text | d6f985e9-51e7-5bb0-89a2-acb8846cca06 |  | text | Installers name
text | d29b4da1-bc65-55aa-a04c-61703b9427c6 |  | text | Date:
checkpoint-status | baebfa71-eb90-4e67-9782-b71fef4d4429 |  | checkpoint | Tested by & date
text | 093f5104-26d1-50f4-9af7-66aa8f7098b7 |  | text | Tested by:
text | 0f3890a7-5b25-5b05-8083-34047cf9388c |  | text | Date tested:
checkpoint-status | 270864fb-a9ee-4622-88c6-d21103b8d3bc |  | checkpoint | Council inspector sign off and date
checklist-flat | 89f4be47-d838-4948-9c6b-616e62a7ba05 |  | checklist | Core waste & Stormwater |  |  |  |  | Yes | Core waste & Stormwater | 06546616-88d3-451a-8413-6e81f8c702b0
checkpoint-status | d744f26e-6054-4c8a-9201-d71085f1b690 |  | checkpoint | Waste Pipeout
checkpoint-status | f19ed068-4cd7-4b45-a83a-cbaa2da5cffc |  | checkpoint | Vent installed
checkpoint-status | d0ae4462-9c41-4abd-ba1d-0842a6540aa1 |  | checkpoint | Check sewer hasn't been connected to stormwater.
checkpoint-status | 42353607-d72a-4820-ae2a-36d66912126c |  | checkpoint | Correct or exceeded minimum fall
checkpoint-status | c3f1bb18-a81c-4b57-ae38-687b982d618f |  | checkpoint | Correct Clipping
checkpoint-status | 9f6efcf1-df9c-4813-8cbf-600794fb3806 |  | checkpoint | Flood Test in accordance with ASNZ 3500
checkpoint-status | f4d72486-35ec-4878-8877-f05dd18a2c49 |  | checkpoint | Hydrostatic test Plug Removed By
checkpoint-status | b7cee96f-64ab-4d83-8071-e32c22d392c6 |  | checkpoint | Inspection Cover Replaced By
checkpoint-status | 591c2cdd-7a94-4514-8c95-6747831b791d |  | checkpoint | Seismic bracing for pipework, longitude & lateral
checkpoint-status | f7b09e62-f44c-4424-a876-145e373f2b1f |  | checkpoint | Pipe labeling
checkpoint-status | aafb6d05-bdad-45b3-a009-05907fd6f427 |  | checkpoint | Access points for cleaning
checkpoint-status | f78a048c-a80d-48bf-9bb2-b9590bea56cc |  | checkpoint | Acoustic lagging
checkpoint-status | 3153154e-0a6f-4e15-a63f-7f16c08a1716 |  | checkpoint | All pipe stubs covered or capped
checkpoint-status | 0a5ea546-15ef-4a13-b938-302867881b30 |  | checkpoint | Installers name & date works completed
text | 84a5a98f-d1e0-5479-84d5-17380c48652b |  | text | Installers name
text | dfa5e370-047b-556d-9bc9-5e822133a61e |  | text | Date:
checkpoint-status | c4c1c5b1-ab65-448c-a211-615756b77726 |  | checkpoint | Tested by & date
text | f30aafaf-b8ab-5433-b7f3-879e2c21df52 |  | text | Tested by:
text | dc43ff74-8014-53b1-b88f-d76a585c4f58 |  | text | Date tested:
checkpoint-status | ed8c0eae-d763-4d65-9c60-5b165e7e4d05 |  | checkpoint | Council inspector sign off and date
checklist-flat | 77870e48-31fb-4507-a42d-3322e7a80dc0 |  | checklist | Roof |  |  |  |  | Yes | Roof | 0a38e48b-ae5e-4b68-b60a-68ae6a5a7a87
checkpoint-status | f9105b9a-1547-4e8f-a307-ee9b84ff06ad |  | checkpoint | All vents installed
checkpoint-status | 25bf53f7-4a03-4a9b-bd8c-f16745518f26 |  | checkpoint | All vermin proofing fitted
checkpoint-status | fa87d67f-1dc2-4b7c-babc-7ecd78c27eac |  | checkpoint | Hose taps installed
checkpoint-status | f75985ab-19ee-47b6-904c-ed891b7f4f49 |  | checkpoint | Dektites fitted to vents
checkpoint-status | 474b7b4d-3213-41b1-9374-95213413f0f0 |  | checkpoint | All overflows finished
checkpoint-status | 3373fbae-27d7-4bd5-8131-25e0a140405c |  | checkpoint | All downpipes connected and working
checkpoint-status | 0b6eb290-7654-47fb-a583-69e8f888f9c5 |  | checkpoint | All outlet covers fitted/correct screws
checkpoint-status | 6f3d24d4-ca65-44eb-ab09-e9837b8a4ace |  | checkpoint | All rubbish removed
checkpoint-status | 6326543b-3ad4-4cd3-822a-8f7ab4fbfd6a |  | checkpoint | Check plastic outlets for cracks
checkpoint-status | 1981f07b-9ec8-4fa0-baed-9a71bfb50987 |  | checkpoint | All downpipes clipped
checkpoint-status | 16fe58b0-0a5b-4fd9-b887-da37733ec272 |  | checkpoint | Tested by & date
text | 64a56952-ede2-5bd6-b412-640f854a97e3 |  | text | Tested by:
text | a7a148a1-800d-5c7d-8212-9b2c37a8d858 |  | text | Date tested:
checkpoint-status | 0a5020a7-5816-40fe-8450-3bf95cc21a3f |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 3d29974d-6fba-459c-8396-a539a074f30b |  | checklist | Core Water & Gas |  |  |  |  | Yes | Core Water & Gas | 0c48bea4-5954-4372-8f20-2a8b89c8116a
checkpoint-group | 3228afb2-0162-49a7-a3ae-af7c44eec8d7 |  | section | Gas Mains
checkpoint-status | b185508a-352a-44be-9203-228ec41b76a5 |  | checkpoint | Connection brazed correctly
checkpoint-status | 061c3f84-e8f4-4c7c-a80d-8736094691e1 |  | checkpoint | horizontal/vertical
checkpoint-status | cc0db36a-7277-4302-a036-4e1b73f144c9 |  | checkpoint | values fitted correctly
checkpoint-status | 6800c957-1499-43b4-a6ff-83a96153fc0b |  | checkpoint | Drop test complete
checkpoint-group | 7cae5fe5-71a3-4c60-98da-c38f8a40333b |  | section | Cold water main
checkpoint-status | bb5aba21-641b-467a-bd95-bd3f3582d2c4 |  | checkpoint | Connections brazed correctly
checkpoint-status | 66705d82-733b-47c1-8c53-2d29608c7add |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 29f9db36-3156-4bbf-ade5-89f8ad38abe2 |  | checkpoint | Valves fitted correctly
checkpoint-group | 81a8107e-8224-4c40-9d0c-9acfd1b64b4b |  | section | Hot water main
checkpoint-status | 53b24d8a-edbb-4f57-99e2-166ebdde19db |  | checkpoint | Connections welded correctly
checkpoint-status | 4415d37e-5935-4a89-8bb1-9634965125a2 |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 54a6f202-bc2f-4986-a28a-dfe1fe38f9bd |  | checkpoint | Expansion allowed for
checkpoint-status | b91f0531-a425-4108-aab8-e283e98be2f4 |  | checkpoint | Lagging installed and neat
checkpoint-status | c720c1b9-5d5f-4b6e-92f5-93b50fa07476 |  | checkpoint | Valves fitted correctly
checkpoint-group | f9ed5fc3-6f0b-4fa4-9164-1ced1c8f69a9 |  | section | General
checkpoint-status | c34692d3-89e3-455f-83de-eff0241c76c6 |  | checkpoint | Open ends of riser capped for testing
checkpoint-status | f37d2bdd-11ae-4237-97ba-a944ccf6df43 |  | checkpoint | Checked for crossovers
checkpoint-status | ee592074-434c-4d29-8ae1-e4f5066e4a97 |  | checkpoint | Tidy work areas
checkpoint-status | f18675f3-2554-4f52-a5d7-5a1c8513ea85 |  | checkpoint | Pressure test to 1500kpa for 30mins
checkpoint-status | 4bd7ae52-b6bc-42ec-a432-6b15cb017736 |  | checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
checkpoint-status | b656e02d-b317-4a8c-9fec-f200572d2415 |  | checkpoint | Seismic bracing for pipework longitude and latitude
checkpoint-status | 67a267ed-3368-415a-967f-b3eac016e290 |  | checkpoint | Lateral labelling of pipework backflow devices fitted
checkpoint-status | cdb4b969-3b2e-48ae-96f1-9cec6a95fae5 |  | checkpoint | Pre Line Inspection Passed
checkpoint-status | 0d03270d-6aad-46df-9487-17ac97d79c85 |  | checkpoint | Installers name & date works completed
text | c0d1dd4d-f622-56ca-b59f-d8e1bff3e9b2 |  | text | Installers name
text | 93c40a08-2428-5312-bb47-4531fa69ed18 |  | text | Date:
checkpoint-status | 9a5203bc-5a93-4c96-a4eb-d44c1a821efe |  | checkpoint | Tested by & date
text | f6713723-3e69-5803-8dc7-d799bb5ca0f7 |  | text | Tested by:
text | 363a58ad-0139-5e62-adca-c2fa3c53635f |  | text | Date tested:
checkpoint-status | f468a711-7cc9-4372-a8de-4c979e79d58b |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 66e785b3-6d0b-423b-b6a8-4313b52ea305 |  | checklist | First Fix Plumbing - Including HWC - no balcony |  |  |  |  | Yes | First Fix Plumbing - Including HWC - no balcony | 100a3ee5-8c6b-469e-bd7a-ed5514420247
checkpoint-group | ebf7ea65-9f90-470e-90f0-ff1057ab69df |  | section | Bathroom
checkpoint-status | 06ef5dd2-2b2d-4dc6-97b7-38fe62baf994 |  | checkpoint | W.C Supply
checkpoint-status | 2762626a-0521-4a79-8bf2-bd98d0b2ba9d |  | checkpoint | Shower waste
checkpoint-status | 8dacb45a-1f12-4f7f-959d-404e1670f070 |  | checkpoint | Shower mixer/check depth
checkpoint-status | f0e9745e-f875-4442-bf7d-1d24d090cad1 |  | checkpoint | Toilet waste
checkpoint-status | 3a564b71-fcf9-4fe0-bba0-5bcabc32d1a6 |  | checkpoint | Vanity Waste
checkpoint-status | 49d02036-afad-4da3-8efa-67f65809ffdd |  | checkpoint | Vanity Wingbacks
checkpoint-status | 15098b7d-cb58-4776-b294-33242be352e3 |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-status | 35b40957-92f9-4c94-880f-81a694a3858e |  | checkpoint | Bath mixer where applicable
checkpoint-group | 3e6b15aa-9c86-49fc-b92d-243e86d21380 |  | section | Laundry
checkpoint-status | f3adc551-a0b6-49d9-8118-929c58551b86 |  | checkpoint | Hot and cold water
checkpoint-status | 1b23984f-a6b1-45bd-97a4-5dcab5c29f0f |  | checkpoint | Waste pipe
checkpoint-group | 410c026b-274c-4a94-88de-4a9480f6de5b |  | section | Kitchen
checkpoint-status | bbd8ade2-631e-4b48-ac8c-094d3cd2f7f5 |  | checkpoint | Hot and cold water
checkpoint-status | c4e3c9dc-d756-439c-8981-6b4d820b0973 |  | checkpoint | Waste pipe
checkpoint-group | e1f452bc-d164-4ff5-b49e-367783349974 |  | section | General
checkpoint-status | 80ba4547-5856-4a45-bcf3-5b9601fb4bae |  | checkpoint | Pipe Work Clipped
checkpoint-status | 61c6711c-7aae-4cda-a50b-a0f7e5345457 |  | checkpoint | HWC water feeds
checkpoint-status | d73ad09e-345a-4633-9c49-0af43c413298 |  | checkpoint | HWC waste
checkpoint-status | cae1f3f9-7a82-4793-be4a-ed456452bea4 |  | checkpoint | HWC nogs for strapping
checkpoint-status | 5cecc6d0-4bf2-4c29-bfe4-a106f7bcb7bc |  | checkpoint | Pipe Work Siliconed
checkpoint-status | e873f437-8cd9-488e-a63b-8eb44c717f9e |  | checkpoint | Capped Off
checkpoint-status | 8cc587a6-b64c-44d7-8c8a-3529d5c45a60 |  | checkpoint | Check for Crossovers
checkpoint-status | 965a9a39-b618-4266-87d5-c5a20817bb95 |  | checkpoint | Double check all sefont of fixtures
checkpoint-status | 6505f5ab-c34d-4f40-9d07-9f9119c51245 |  | checkpoint | Acoustic lagging where required
checkpoint-status | 8088196e-2c37-4369-b4f1-b773d1eb3221 |  | checkpoint | Thermal lagging to hotpipes where required
checkpoint-status | 36bfd7f2-1c2d-4903-8c60-c920013a9773 |  | checkpoint | Floor waste flange fitted
checkpoint-status | 334bf1ed-6e09-4f92-b83c-10d3bdcd7f93 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | 9fb4c4a7-d6fd-46bd-80a9-650e274947fb |  | checkpoint | Installers name & date works completed
text | e53d59d3-68ae-5488-a841-60ccb1af3bbb |  | text | Installers name
text | c939c8c7-583d-5f4d-a765-f220d434ee45 |  | text | Date:
checkpoint-status | 7f76153e-2938-4693-a96b-8bb0668baa82 |  | checkpoint | Tested by & date
text | eb22c62d-1a59-516b-b6ab-de00aa88dbd2 |  | text | Tested by:
text | 9fa490d5-d722-50ca-9c38-f90d532a3494 |  | text | Date tested:
checkpoint-status | fc179317-4d5c-4e7b-a447-e1fd16380e5b |  | checkpoint | Council inspector sign off and date
checklist-flat | 34fb241e-70ec-4e12-bd94-d45c11e1f91f |  | checklist | Classroom 2nd fix |  |  |  |  | Yes | Classroom 2nd fix | 1946b76d-504f-41db-b4f2-d6cf8d639521
checkpoint-status | b9e8244e-6fbe-4468-aa18-136a980eb16c |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 5093fcf1-b44b-48e7-a9eb-7f40911c8d5d |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 4c91dc72-1ab5-4055-af95-cbb2cc1e4c71 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | ba873300-e802-4efe-aec7-f9881ddcee9d |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | b3a84aa2-97b9-478c-bd26-dac7c1d86841 |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 0d1fe230-a044-4807-a061-f1aa4991aa46 |  | checkpoint | Check Traps For Leaks
checkpoint-status | 43a2f172-be72-44c4-a35d-59ff239b6415 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 25cd888c-98b0-4e68-a385-121aa692e6d5 |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | 267b3232-c827-459b-86c4-85f87d47035f |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | 0e20a4de-29c5-4c3f-9aa6-c759e6e0c08e |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | f49cb93a-56f6-480b-a216-2dfc78ec56f2 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | fd2787b5-8a08-4b3b-a69d-05f9d1e590f9 |  | checkpoint | Check FWG are clean & clear
checkpoint-status | 54d6e23e-cb15-4e20-ab5b-6c264dd7628f |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | c4bc50bf-51d0-4b04-b70b-d5b2a91f77c5 |  | checkpoint | Check All Soil Pipe Connections Are Connected To Drain
checkpoint-status | 0061a177-f340-42b1-8635-2c4e889de72e |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | 36a67d26-2cb7-4c88-b82f-8fe3329d6fc6 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | 7656c142-8ea2-422e-a5ad-19af4e9af339 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 1a4a6383-8af3-482c-b7a5-740231047dc3 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | e8f48083-7889-4c86-8ce6-e5e160a18bbc |  | checkpoint | Temperature set point
checkpoint-status | 2a9fcc6f-aab8-42b1-826e-8cde647069cd |  | checkpoint | Installers name & date works completed
text | 9d73cc4b-eb73-5313-b328-d88523768cce |  | text | Installers name
text | a3c0ed39-a1d7-54e7-af92-e5df5ebf3836 |  | text | Date:
checkpoint-status | 0dbf6dc7-be3c-4fc7-8d6c-7f9d8b21892f |  | checkpoint | Tested by & date
text | f4285850-0f68-5e27-89dc-c095e709cf2a |  | text | Tested by:
text | 76a0211f-163b-55bb-916f-e3c14b4ab38c |  | text | Date tested:
checkpoint-status | 9039b885-24a2-4694-aedb-886e2bf7c5cd |  | checkpoint | Council inspector sign off and date
checklist-flat | d12fb04e-156c-4f57-96e1-ea55e08c6e47 |  | checklist | Hotwater Plant, Pumps & Tempering Valves |  |  |  |  | Yes | Hotwater Plant, Pumps & Tempering Valves | 2e562e6b-3128-4c00-9e92-92e8aced62ff
checkpoint-status | 9c7f0bf9-9cba-41a2-83a6-08626fe654bd |  | checkpoint | Flush all lines and strainer including rinnais
checkpoint-status | 22766f8c-da30-486b-a8e8-fc110ee80627 |  | checkpoint | All safety valves installed
checkpoint-status | f9f411fb-792b-409f-a5cb-a1b8bb6bdb29 |  | checkpoint | Seismic restraint fitted
checkpoint-status | 5e6b3242-38b1-4d88-a48d-41002a6b9345 |  | checkpoint | Check condensate drains from Rennais
checkpoint-status | ac4606b7-a053-456a-aa89-04411f29ff0c |  | checkpoint | Check All Connectors For Leaks
checkpoint-status | 08e4ab54-78a4-4666-b1c8-80dd4a59237f |  | checkpoint | Check all valves and connections for leaks
checkpoint-status | a3d0887c-0bd8-4a4c-b014-ece7e2daff1c |  | checkpoint | Operate cold water expansion valves / check operation
checkpoint-status | 0b6378b1-830a-42b3-bc2f-942b86159454 |  | checkpoint | Set limiting valve
checkpoint-status | 82da5d3a-c170-45d1-a9f5-ee4841315761 |  | checkpoint | Test TPR valve
checkpoint-status | 961cd21c-e4af-4bb2-892f-b420d8324b43 |  | checkpoint | Check for crossovers
checkpoint-status | 8836a987-719d-4fd3-9c44-c61a6265d2b5 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | 312dd205-812a-4d38-ae94-dcf8b7777790 |  | checkpoint | Lagging completed
checkpoint-status | 5c567bca-723c-4f01-8560-ee024e8b0420 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 1f1172c9-803d-4d88-b695-7ad2117a0cbd |  | checkpoint | Set tempering valve temperature
checkpoint-status | 2d2659f6-6c9f-457f-af61-60cdf2e25e92 |  | checkpoint | Set Rinnai gas water heaters
checkpoint-status | f1a82ef4-693a-4537-897c-f7138a3a134b |  | checkpoint | Set thermostat temperature
checkpoint-status | fe070203-8c9a-4330-b824-01283f7a0efb |  | checkpoint | Set Bleed air from primary pumps
checkpoint-status | c58aef7b-a9ee-438a-b789-f63854bfb14e |  | checkpoint | Bleed air from circulating pump
checkpoint-status | fc2b9d61-c154-4445-9ff0-0ea4b71f8077 |  | checkpoint | Set all return thermostatic balancing valves
checkpoint-status | 89bfcc4a-07cc-4f9b-b7b8-8aa89d76ca8a |  | checkpoint | Test gas for soundness & check working pressure
checkpoint-status | 814f784f-c914-4070-a5cb-f3b38123f859 |  | checkpoint | Water temperature in Hot water cylinders
checkpoint-status | c247190a-fc03-4427-85f1-38b65a1fd5f9 |  | checkpoint | Installers name & date works completed
text | 3adaa422-3656-5be1-a0d2-65563873401b |  | text | Installers name
text | 8ed004db-1a9e-5141-a974-fa6b07d39754 |  | text | Date:
checkpoint-status | f6995b47-405d-4902-a52c-81bdf659a98f |  | checkpoint | Tested by & date
text | b8965633-9814-57cc-9050-8d7ca413a635 |  | text | Tested by:
text | d29b5046-f1bb-5fe8-9b76-1500b4d11a97 |  | text | Date tested:
checkpoint-status | e0dafeac-764a-43c7-8916-0151c13663f7 |  | checkpoint | Council inspector sign off and date
checklist-flat | 60fb185e-4ba8-4299-b6e8-405399049ece |  | checklist | Bathroom Second Fix Plumbing |  |  |  |  | Yes | Bathroom Second Fix Plumbing | 35f3ecf9-eeda-42cb-b7c9-5012428f6948
checkpoint-status | b3fa709a-d14e-4abd-87f3-8267ab1d4704 |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 071eb7cb-aa30-4ee1-9ba5-c2957d701edd |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 716a8254-ee5e-45e4-be82-e9ae6d56d9aa |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | d00e94c5-ef3a-4dee-add7-8638cdb28a9b |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 925b98ea-6a5c-4652-89d9-6a2fd6a14078 |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 127be3c4-fc0e-4a98-a639-6caaa97e063e |  | checkpoint | Check Traps For Leaks
checkpoint-status | c9752ff1-0932-45ef-b3d4-77a88c3cadb7 |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | 7287c33b-94a7-40c0-9b0d-7d4d5cea7a49 |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | f3101ec2-3d2f-4d92-b2ed-d5717f74a8a0 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | f2d8d01a-3c09-4352-8b2b-0e2f169745db |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | 82c02c2d-abf5-41fc-8a63-4b6816c5b2b5 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | 0a22f64d-af23-4531-a112-47a290b61df0 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | 691a3a3c-b41e-494b-8961-7e64210a1347 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | 5391d5e1-2736-42ed-842d-3fb999dc87f7 |  | checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint-status | 1ff97bba-46a0-426d-aef4-9a7c57e0c66b |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | ecdbc97b-ed9a-4293-ad4f-f5e8eff15440 |  | checkpoint | Check All Soil Pipe Connections Are Connected To Drain
checkpoint-status | 1a1565b1-6dc2-4242-a7a9-f0b781f83298 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | a9ad4047-d77e-4247-9840-a18831422354 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | d449f111-be4b-4f51-96af-4a3335622f20 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | fd3259bc-4760-4ab4-989b-e49bfea48c4f |  | checkpoint | Temperature set point
checkpoint-status | ae80c287-d3e8-49fc-9f6f-63ba993d00d2 |  | checkpoint | Installers name & date works completed
text | 6dd28630-57b9-5d2b-92e2-a072255ecb49 |  | text | Installers name
text | deb2150a-2277-5a68-9f27-e31abace6027 |  | text | Date:
checkpoint-status | 8b2086c9-bacb-461b-9c2b-a95b8831b2a9 |  | checkpoint | Tested by & date
text | 9c3c521a-55b8-5992-b593-1dc05c545364 |  | text | Tested by:
text | 4676c40f-1ffb-50a1-a5c4-e3c9788c392e |  | text | Date tested:
checkpoint-status | 62b89217-f2cc-4192-880b-3a244cf5fd22 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 7cbadf00-78fd-4ae8-b152-5561d051aa9f |  | checklist | Stormwater- Pipeline Installation Checklist |  |  |  |  | Yes | Stormwater- Pipeline Installation Checklist | 38729541-15b0-4f8c-98b4-94f594760c26
checkpoint-group | 7f830e75-e33d-44af-b13b-1debd8881e2c |  | section | Pipe Laying
checkpoint-status | 43082800-0089-465a-aebf-24a8c93d1008 |  | checkpoint | Latest consented drawings
text | 8cb1d2e9-8736-5bfe-82c3-4e6468bb62f5 |  | text | Drawing Ref No.
checkpoint-status | 8bffb162-454d-433e-be28-d8a26584afa9 |  | checkpoint | Setout completed checked and accurate
checkpoint-status | e628996c-7920-4c70-a993-36693a908e46 |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | c3a72c70-b4e4-4adb-a8ef-0815329ef6c7 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 8d967776-77e9-4287-92d4-4892cf3f10c9 |  | checkpoint | Bedding depth and material correct
checkpoint-status | c6333b2d-7952-48d4-b889-a352cd6117eb |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | d9edc338-7094-5b86-ad52-9fbc9bb78522 |  | text | Grade of Pre-Line %
text | dd444f8e-e587-5c02-8b87-4825bdbe00ae |  | text | Product Type
checkpoint-status | 709bcf2c-96e0-4c11-a1f5-88b4a31ce31f |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | 28f05c45-6b8d-43a1-9fcc-22c3e314eeb7 |  | checkpoint | All Downpipes have been checked, installed and approved
text | 747be77a-eee4-53e2-9dce-de60c652f04d |  | text | How many installed?
boolean | 460be2bc-731e-5eeb-ab07-0644478908c2 |  | bool | Location confirmed
boolean | 5bedf117-6154-5de2-9f03-11dc0aaa97ae |  | bool | Heights are correct
boolean | 4e24a4ef-fcaa-5399-9d1a-53fdaefd7959 |  | bool | Caps are secure
checkpoint-status | b00359d9-6a18-4382-87c1-ee064c182281 |  | checkpoint | All Cess Pits have been checked, installed and approved
text | 7d84f501-b436-531f-bbca-80865b955f65 |  | text | How many installed?
boolean | 2a4e0a14-39f5-5ed2-8cac-0b3aaf60e1a1 |  | bool | Location confirmed
boolean | db516fb1-9e78-5046-98dc-fe5c09da67a7 |  | bool | Heights are correct
boolean | ad53570c-56bb-54e5-aec4-df30387e136a |  | bool | Caps are secure
checkpoint-status | 1e112cc2-af30-4d17-b56b-441bc1e61e69 |  | checkpoint | Pipe Laying Completed
text | a0380621-e563-503c-870c-891331ba51e9 |  | text | Laid by
boolean | 1ca21224-5114-5ac5-8724-58893389df68 |  | bool | Bedding Sound
boolean | 3a48590e-8faa-5056-a2a7-5a17529e120b |  | bool | Soil Removed
boolean | 59ac5c2a-62ec-5ea5-befa-c2282f8ab95e |  | bool | Trench Compacted
boolean | df008a7e-1530-5e33-8e31-f2c313c08fd7 |  | bool | Hard Filled
checkpoint-status | 49ed81d7-b54c-4c5f-80ff-953a8ee664a3 |  | checkpoint | Install Tests completed, reviewed & approved
text | 80a45fc2-3116-5d14-8e04-22fcea291c25 |  | text | Local Authority Inspection Passed
text | 9e8b4df8-5dc7-572a-b01d-f9084ec6472a |  | text | Name of inspector
text | 196bbdb1-e50e-5341-bd04-30cc14873bd7 |  | text | Date
checkpoint-status | 2f2807a4-69fd-47d6-8a9b-fea363b59cf3 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | b09f7b6b-c566-5327-a28f-d83ca242abae |  | text | Sign Off By
text | e50a2c15-020c-54f3-b397-acef097c7aea |  | text | Acknowledgement of checklist by
text | 8e067aec-8257-5b64-a7d5-b05f80f8de64 |  | text | Foreman
checkpoint-group | 7a9f7ffe-914a-485d-bc2d-bfca4d62c703 |  | section | Backfill
checkpoint-status | 84dcfbcf-f228-4eab-8e38-d3f9d956648e |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 2d0ac9e1-2bb5-4204-a979-647152bc9edd |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | a8a7ccb8-a79c-40a8-80c1-05ae3cd46ad0 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | ff83b4b3-6635-4d1b-8198-3e600b7fd6d9 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | 138fd143-f466-48ca-a1f2-fab11176a68a |  | checkpoint | General photos and observations during backfill
checkpoint-status | 89c6cadd-84fb-4157-94d2-8542069052b2 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat | b664167c-d7a2-4b75-a349-ce26429631fc |  | checklist | First Fix - No HWC |  |  |  |  | Yes | First Fix - No HWC | 38a842ae-efa2-40b6-9c10-d6af974f665f
checkpoint-status | ffa58e06-9ea9-4f33-bab8-1f9cd052750e |  | checkpoint | Underslab complete
checkpoint-status | f12b59ba-0bef-46dc-8d14-af13b422934b |  | checkpoint | Toilet, shower and basin waste installed and in correct position
checkpoint-status | 4298e485-9600-4943-96d0-7e4d186ccca6 |  | checkpoint | A/C drain connected
checkpoint-status | 50a07173-54cd-4860-bcc5-fb4c2bb634e1 |  | checkpoint | Shower flange installed
checkpoint-status | 31d9b734-482f-48d0-938d-8efaa5f25e4a |  | checkpoint | Water to toilet
checkpoint-status | e124bfe4-2c3c-4129-93cd-6d09a382a224 |  | checkpoint | Water run to basin and basin taps installed
checkpoint-status | f22969cf-507f-4a8b-a240-d3e646447621 |  | checkpoint | Water run to shower and shower mixer installed
checkpoint-status | 55bb2273-a1c6-431d-b1c1-61f1acbc8463 |  | checkpoint | water supply run to shower rose
checkpoint-status | c08f6b2e-03ea-43b2-b8ab-7f5f0ee2ade1 |  | checkpoint | All pipework clipped and siliconed where it runs through walls
checkpoint-status | 3377bebf-df7a-40bd-b9e1-d8d5d4378f5c |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | f956fa36-6e45-4a7c-a5ae-72c8c12cacae |  | checkpoint | Thermal lagging to hot pipes where required
checkpoint-status | d86122de-65ae-4a3b-9982-4ed1252ce672 |  | checkpoint | Tempering valve installed
checkpoint-status | ad9808a0-b218-486a-bed8-308dc7d4bea1 |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | e35b8af8-e299-46e3-bed7-76952d76003e |  | checkpoint | Check no 1st fix clashes with 2nd fix fixing screws
checkpoint-status | 5358004b-03ab-420c-b5ed-9eb3328e1b63 |  | checkpoint | Check all nogs are installed
checkpoint-status | c91926f5-cdba-4a67-ac77-04030e8de00e |  | checkpoint | Double check all setouts and heights.
checkpoint-status | 7997cfa7-0049-4398-99cc-09da23fe540a |  | checkpoint | Installers name & date works completed
text | ac5f4a18-62e2-5773-85d5-979c248954d3 |  | text | Installers name
text | 7bca42b4-d4b2-5460-adc0-5b6b87ae7d4b |  | text | Date:
checkpoint-status | 1a3380a7-d3fe-4bd9-af31-e4f0dd244715 |  | checkpoint | Tested by & date
text | bb779583-8a18-570b-9819-b3ee32d46ba6 |  | text | Tested by:
text | f144827e-2fc8-54be-a3f3-01a01ce4ba4f |  | text | Date tested:
checkpoint-status | f159f1b2-1970-42c4-9a73-86e25ed706d3 |  | checkpoint | Council inspector sign off and date
checklist-flat | 43b296e2-9fcf-4f04-96b2-d2d01fb2b48e |  | checklist | Commercial Kitchen 2nd fix |  |  |  |  | Yes | Commercial Kitchen 2nd fix | 3ba4fa3f-077c-4f6b-b25a-5eb8eb1b9b17
checkpoint-status | e2eb7f1e-f41e-4087-bbde-36c616e44c7f |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 88c29803-9bf8-48a6-bc60-2583d4af9cf2 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | a72a8588-2310-445a-8ccb-e292ed7b28e8 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | a13f9f2d-a039-49a5-9978-d2cc12d92307 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 1810bea1-9836-41dc-99a9-1d0111cf1a8f |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 71d6e0d8-3283-4ec7-8a55-fe8cd029b7cb |  | checkpoint | Check Traps For Leaks
checkpoint-status | 0eb8ed24-7656-4bc9-8810-19a8944d18d2 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 6f62f641-c0dc-45bc-a5c9-f8a9033f5809 |  | checkpoint | High temp wastes installed
checkpoint-status | 3c132489-7ff3-4c04-9e75-bdb54c427da6 |  | checkpoint | Gas appliances tested
checkpoint-status | d3d7642f-968e-40e7-83da-557d24ef3185 |  | checkpoint | Check FWG are clean & clear
checkpoint-status | 7b0aea56-df07-463e-b847-ecbd41a306d4 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 9cc0f30a-ddf7-4379-93d8-3e1352aae657 |  | checkpoint | Check All Soil Pipe Connections Are Connected To Drain
checkpoint-status | 0fef433a-6aad-4f85-80f9-76e6f2a3e330 |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | 81841629-13ee-49ad-9dea-8f4ea22cf4a4 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | cd1f7365-8b3b-4f66-9670-8bda829df16c |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | a3381189-e625-48ce-a90a-b7b2cce1e4af |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 0d09f14c-0068-4e2e-81a0-5a431e62368e |  | checkpoint | Temperature set point
checkpoint-status | 2e8dc13b-1c6f-45d1-a314-953894cc2e46 |  | checkpoint | Installers name & date works completed
text | 2d1eae07-38c4-5c61-960e-8d7c7c0a39e7 |  | text | Installers name
text | 70eb52d2-432d-521d-9a94-9d841c6a2f7f |  | text | Date:
checkpoint-status | 0e54fdba-90d7-425d-99a1-c098a7f06dbe |  | checkpoint | Tested by & date
text | 659d8af5-00d0-51e4-b2ac-6f4774ac03c8 |  | text | Tested by:
text | deaba142-307e-5d52-a47e-6a2f7f3d0f6c |  | text | Date tested:
checkpoint-status | 6998bc0d-12c5-4683-87a7-de3b62875ad6 |  | checkpoint | Council inspector sign off and date
checklist-flat | 72f6e4df-cc79-4e39-a01d-4cf8bd1f2fe7 |  | checklist | Second Fix - No Hot water cylinder |  |  |  |  | Yes | Second Fix - No Hot water cylinder | 3d1cdd21-3377-475a-a7cf-bf5fca81f5c9
checkpoint-status | 7fa0641c-fef2-4768-810b-8eac932ae784 |  | checkpoint | Flush all pipework before fitting taps & fittings
checkpoint-status | 4fdb9514-0075-48a8-9cb2-5d07d0464e80 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 53d5f63f-86fa-41a7-afe1-bbac3d7e55e5 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | 7d529433-9eb8-45c4-8ad4-92d3323bf7b6 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 981fd46a-b598-4b30-9d43-0849b3253388 |  | checkpoint | Check Traps For Leaks
checkpoint-status | 87fa94b8-3826-4977-8b8b-ba6c0ba0c2ff |  | checkpoint | Check Cisterns are flushing correctly
checkpoint-status | 4fa9d1ed-1a23-497a-a9a3-e8604fb88fc2 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | b66f6ada-e11d-4a31-972d-287393895f9a |  | checkpoint | Check shower waste is clear
checkpoint-status | 68f90d50-8a36-46e9-934c-591ddc19fda6 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 4e943fef-cd90-47a5-82f7-f114f76c4f77 |  | checkpoint | All Your Rubbish Removed Or In Bins Provided
checkpoint-status | 0fc837d8-1644-44d2-9290-7e10f2088edc |  | checkpoint | Check no fixing screws have fit pipes
checkpoint-status | d376165d-5ca6-43a9-b2e7-987f2e925da9 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 43718100-f675-46ee-9314-29d989b8832a |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | 0f371436-ee84-4c62-bada-7f18e9ee1803 |  | checkpoint | Temperature set point degree 55degC
checkpoint-status | fa109e2e-01b7-497d-945a-36df000e039b |  | checkpoint | Installers name & date works completed
text | 38e0044f-1835-5450-8c8d-d83119d19b0d |  | text | Installers name
text | 5ad0f30b-d8a6-5dcc-a5dc-d57e9c5de440 |  | text | Date:
checkpoint-status | 152663e8-7244-4587-94bc-d95573f381f6 |  | checkpoint | Tested by & date
text | 4882d2ed-5b20-56eb-bb02-bcb37fbc8fb8 |  | text | Tested by:
text | 3903a290-ef19-5181-9398-acd514a622db |  | text | Date tested:
checkpoint-status | 7dc751aa-652a-4841-9ba3-9914cc364069 |  | checkpoint | Council inspector sign off and date
checklist-flat | 7dca679b-c985-4a21-bd57-eaba975f45b1 |  | checklist | Classroom 1st fix |  |  |  |  | Yes | Classroom 1st fix | 4d4ae3a7-38e3-4fb7-8994-5ee502e6dc0d
checkpoint-status | 3d3e49d5-4773-40b7-8827-a88bf4f8d350 |  | checkpoint | Cold water pipework installed
checkpoint-status | 14379488-fc5c-4373-a125-112831bd8b38 |  | checkpoint | Hot water pipework installed
checkpoint-status | 8119a37c-81f0-4a03-819c-c1fc81b08ab6 |  | checkpoint | Thermal lagging complete
checkpoint-status | 624d4e16-9f26-4758-9118-05dd8dca1093 |  | checkpoint | Wingback and waste correct setout
checkpoint-status | 883b10d1-890c-4c1a-b794-7b354946737e |  | checkpoint | Gas pipework installed
checkpoint-status | 783728ff-fc29-46f2-a7ed-a0c7d4ac1d8c |  | checkpoint | Gas Guards installed
checkpoint-status | e2a07723-d443-450d-8eb2-3f95ddb61788 |  | checkpoint | All pipework clipped and siliconed where it runs through walls
checkpoint-status | d3e25bf2-fe07-461c-a0e3-2099add6d31a |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 8978fa00-bd28-423d-9ace-cd7c51711b59 |  | checkpoint | Tempering valve installed
checkpoint-status | 9585eae8-4fe0-4b6d-8ef5-ceb0d7b0d421 |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | 73c5fe51-ec72-4962-b340-d84673778f7d |  | checkpoint | All pipework pressure tested
checkpoint-status | 6060c704-7244-4973-9c5e-1097d3648d97 |  | checkpoint | Check no 1st fix clashes with 2nd fix fixing screws
checkpoint-status | 45252139-198c-43ce-bf20-79dce9f1581d |  | checkpoint | Check all nogs are installed
checkpoint-status | 197165cf-3932-4ca6-8c67-9e11efdb7aa0 |  | checkpoint | Installers name & date works completed
text | d5f08ed9-1ccf-53b5-8743-86b9cdb364a6 |  | text | Installers name
text | 6c454d26-fb6d-509d-ac26-f409a5848836 |  | text | Date:
checkpoint-status | 337c5683-8aff-4092-8033-f021be699927 |  | checkpoint | Tested by & date
text | 35c4c658-ca51-517a-a7d7-ada0fa57f9c1 |  | text | Tested by:
text | aa916de5-5ff8-593d-bb33-76bad133615a |  | text | Date tested:
checkpoint-status | 2edd3676-697e-47af-9ef1-93a99868dcc2 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 87aa7796-5fb5-4d01-90e3-f3542425dc82 |  | checklist | Sewer- Pipeline Installation Checklist |  |  |  |  | Yes | Sewer- Pipeline Installation Checklist | 555c2b2e-a785-458a-9322-d248511496a7
checkpoint-group | 0505ebb5-04aa-4bc0-98d5-cdf344b4af35 |  | section | Pipe Laying
checkpoint-status | b195c12a-ac0a-49ce-af2d-5866beecd88f |  | checkpoint | Latest consented drawings
text | bd6f592f-b53a-537f-be4c-de276767594e |  | text | Drawing Ref No.
checkpoint-status | f3a636a6-a8c4-43f6-b76f-005ba4946aab |  | checkpoint | Setout completed checked and accurate
checkpoint-status | 4118872c-46cd-4eb1-a8ea-ec699c4eae1b |  | checkpoint | Excavation Accurate - Location & Depth
checkpoint-status | 5d938102-926f-41b4-84f6-73548879b728 |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status | 2c395284-8199-48f2-93f2-9d26581c5d27 |  | checkpoint | Bedding depth and material correct
checkpoint-status | 1bc2307c-82a9-45b9-81ad-410215a1f049 |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | ea5e8e91-af13-5452-b2ec-ccc446c8dc44 |  | text | Start Invert
text | bde3a23e-f965-5e48-a4e0-43dd8576ac68 |  | text | Finish Invert
text | 9a0f5db5-ab00-5fdd-a1e2-305d34250473 |  | text | Grade of Pre-Line %
text | 1dcbe523-7c55-5ee8-b6c6-6e0a8c9c1d60 |  | text | Product Type
checkpoint-status | a8e1701f-e429-4f4e-b29f-2e6e6a0df1fa |  | checkpoint | Install Tests completed, reviewed & approved
text | 0e327be8-2969-50ca-b96d-43479621b690 |  | text | Local Authority Inspection Passed
text | 972d634a-5a6b-5cda-8d95-2df77be8ce0c |  | text | Name of inspector
text | 1225ba94-7344-5e66-9802-c89a111e3b38 |  | text | Date
checkpoint-status | 88223a16-578c-42a9-8add-e2d1fad1623c |  | checkpoint | Pipe Laying Completed
text | fdb42d4f-5eeb-5759-a4fd-02df81d8b2db |  | text | Laid by
boolean | b5b68e32-6aa5-5682-9007-67d6c6d103e6 |  | bool | Bedding Sound
boolean | b9cb1270-972f-5d27-b0a5-010dfa403290 |  | bool | Soil Removed
boolean | 36caebe7-cf9a-55c3-903a-3fc7bdb5307f |  | bool | Trench Compacted
boolean | 1840fc8f-7256-52de-9e1f-309fba554b86 |  | bool | Hard Filled
checkpoint-status | e29a7334-3704-4b70-8124-39f0238015b9 |  | checkpoint | Connections to manholes complete and approved
checkpoint-status | a0a5f46e-b923-4713-b2fa-f9b731f1c428 |  | checkpoint | Air Test Complete
checkpoint-status | 607424a4-ff0b-424d-b024-76fb325856c9 |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 3f0dbe99-c8b1-5a0a-8c82-7a0744f74fb7 |  | text | Sign Off By
text | ac095ed4-7df5-54be-8471-9eca6ff2ea1f |  | text | Acknowledgement of checklist by
text | 3de5128b-9208-5d11-bcfe-bf60ea22e650 |  | text | Foreman
checkpoint-group | 526bf8a6-909f-4363-9aa9-b4d44d38f81d |  | section | Backfill
checkpoint-status | deb2855d-4fa3-40dd-a5bd-7aa6abbe1354 |  | checkpoint | Backfill methodology and material confirmed
checkpoint-status | 17d9ea21-8461-4a9c-be90-3a5c8f9a645b |  | checkpoint | Any formwork/ debris removed from area
checkpoint-status | 4a502391-d9da-4c5e-a83d-99295d31dc68 |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
checkpoint-status | fbb25736-9313-4042-ab25-9cbd0efcb176 |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closed out
checkpoint-status | 4bf2e3b2-e6ae-4a0c-818e-0c167c4239d5 |  | checkpoint | General photos and observations during backfill
checkpoint-status | c96eecc4-4c1c-4414-a34b-5816487609f3 |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-sectioned | e704d931-cf8f-4971-a9c1-2ef80892ff89 |  | checklist | Core Water |  |  |  |  | Yes | Core Water | 5b7011a0-5a39-43c4-ab33-60148517d4de
checkpoint-group | 64a87d3f-20c8-421e-8833-a192a37c8614 |  | section | Cold water main
checkpoint-status | 6a0e00bc-33c4-4dc4-8e9a-539a047912bf |  | checkpoint | Connections brazed correctly
checkpoint-status | 4cd23867-2da4-491e-9078-cfd21d72d19d |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 747b4169-3cf6-4c93-ba56-bc837780a164 |  | checkpoint | Valves fitted correctly
checkpoint-group | 9848bb33-f4df-49f5-9077-96e7382824f5 |  | section | Hot water main
checkpoint-status | de1f823d-a51b-48e5-a95d-8f7b8adab9b5 |  | checkpoint | Connections welded correctly
checkpoint-status | 475f5890-1070-47ea-b592-f36e7238fd16 |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 28203903-bfe5-4d98-860c-0a611d4ea6fb |  | checkpoint | Expansion allowed for
checkpoint-status | 0f2c0f63-fabc-44cf-a810-44ff768ed731 |  | checkpoint | Lagging installed and neat
checkpoint-status | 411dffe2-86c3-4ef6-803d-545fdc11a029 |  | checkpoint | Valves fitted correctly
checkpoint-group | f32c13c7-a8c0-4e22-b3d9-d17bcac6739b |  | section | General
checkpoint-status | b162acd8-7e86-4e9a-a872-40f80af110e3 |  | checkpoint | Open ends of riser capped for testing
checkpoint-status | ba01e4c2-d498-4272-b31d-bd16ed2ca504 |  | checkpoint | Checked for crossovers
checkpoint-status | 810d34dc-ffc5-4424-a9a3-6fcbe71a68b2 |  | checkpoint | Tidy work areas
checkpoint-status | ba603b94-4d46-4074-8b3d-3dd80ca6fe85 |  | checkpoint | Allowance for expansion
checkpoint-status | 0888a23f-ba82-4c62-9c4a-cb7298147584 |  | checkpoint | Pressure test to 1500kpa for 30mins
checkpoint-status | 2d9872a2-798f-40ac-bc67-e2d38dca7f0d |  | checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
checkpoint-status | ef3188dd-310c-423e-ae09-d847259a4721 |  | checkpoint | Seismic bracing for pipework longitude and latitude
checkpoint-status | d97eb7e4-82eb-4d6c-a2b4-86fade5eadbf |  | checkpoint | Lateral labelling of pipework backflow devices fitted
checkpoint-status | b6b86143-575d-40c7-8f21-8ebd8e797692 |  | checkpoint | Pre Line Inspection Passed
checkpoint-status | 3855c4dc-defe-4643-8e88-85246f603ebb |  | checkpoint | Installers name & date works completed
text | bd5e8d76-f1a6-5ef7-9a7e-944ae12cd117 |  | text | Installers name
text | addbee51-38a9-5c02-919b-19212ec37076 |  | text | Date:
checkpoint-status | 3713c0d5-358e-45c0-869d-c2c6c166dd73 |  | checkpoint | Tested by & date
text | c945b2f8-ce5f-5304-804d-5186b5afad76 |  | text | Tested by:
text | a42678e4-6abe-5a76-836b-e3e3f3136991 |  | text | Date tested:
checkpoint-status | c0fa3075-9739-4d35-a75c-d6bc8f299f48 |  | checkpoint | Council inspector sign off and date
checklist-flat | f99c4dce-7b30-4130-a326-8090912541c1 |  | checklist | Underslab |  |  |  |  | Yes | Underslab | 60e65c64-a2f4-4469-967f-be9784ab5422
checkpoint-status | 5ae4f3df-5466-405c-a9f6-a0ebedd6388e |  | checkpoint | Area ready for works
checkpoint-status | 99173294-3115-4908-8247-183a05b8bf48 |  | checkpoint | Dimensioned Slab Set Out Drawings
checkpoint-status | 47b5b5a9-d643-4f89-aba9-02a92d3c1acd |  | checkpoint | Minimum Or More Fall Achieved on Slab Piping
checkpoint-status | 50247a41-af14-4e9f-a553-95ebdd4b0f16 |  | checkpoint | Under Slab Piping In Slab
checkpoint-status | 23645028-069b-483d-acdb-a2857f0eb3ee |  | checkpoint | Called For Underslab Inspection To Be Booked
checkpoint-status | f92e8702-e895-45eb-8f26-f8856cfee3e5 |  | checkpoint | Mains Water Supply In Slab
checkpoint-status | 0b37ffe9-b1f6-468c-b602-db236a1039d1 |  | checkpoint | Water Supplies installed incoming / island bench
checkpoint-status | 4055823d-d2e4-496d-9fed-bfa9b16a3fef |  | checkpoint | Gas supply
checkpoint-status | 1ebc44aa-09a6-4dfc-becc-fd2063fd9c37 |  | checkpoint | Test Plug Removed From Pipe System by:
checkpoint-status | 50509871-71bd-4781-8103-584eb56258bb |  | checkpoint | As-Built Drawings
checkpoint-status | 0de1e65b-ba36-427a-9521-2a367183e36c |  | checkpoint | 25mm Protection Around Pipes Penetrating Slab
checkpoint-status | 0ce5d057-cec3-4d26-834b-ae4af7c106d2 |  | checkpoint | All Measurements Double Checked
checkpoint-status | cf15ef97-28a0-4137-811b-9a62ec8ff3cc |  | checkpoint | Boxing For Shower Wastes
checkpoint-status | ef74ddde-7c6e-4bac-b172-4df850414a39 |  | checkpoint | Lagging and trace wire to greasy wastes
checkpoint-status | 787bfdc8-a5ce-44bd-9f39-5c61bf9c608d |  | checkpoint | Haunching & Bedding
checkpoint-status | e5b75762-f339-4525-bf56-c4250c2a969a |  | checkpoint | Concrete Under Gully
checkpoint-status | 2168b22a-a78d-4a78-9fca-e3691812d738 |  | checkpoint | Drawing Number And Revision
checkpoint-status | a4a231bb-cc00-464b-9338-e45c95184caa |  | checkpoint | As built drawing complete
checkpoint-status | fc5865ec-b27f-4d82-bd05-661761a7ab19 |  | checkpoint | All upstands capped
checkpoint-status | 49c8f260-aca6-419d-a49a-a12e081fd00e |  | checkpoint | Installers name & date works completed
text | 49bfeeb6-f829-5691-9d80-6d3ab14d0ad3 |  | text | Installers name
text | e0acffd0-83ff-549c-b053-15bd5858568a |  | text | Date:
checkpoint-status | 553b2547-d77b-47a1-b7ba-f839cdaa27f3 |  | checkpoint | Tested by & date
text | 6673ad80-1793-5d81-9c11-0f7610c4766a |  | text | Tested by:
text | e5e420f5-f148-51f0-9d91-bf56fd18c4d0 |  | text | Date tested:
checkpoint-status | e95b9bb8-91ac-46c6-ae52-e4d206448b58 |  | checkpoint | Council inspector sign off and date
checklist-flat | 68511e8e-bacd-426a-a09d-e3ec045bd557 |  | checklist | Second Fix Plumbing - Including HWC no balcony |  |  |  |  | Yes | Second Fix Plumbing - Including HWC no balcony | 653585c2-7aaf-4654-829f-d1236e392439
checkpoint-status | 9b78a9a2-360b-4b78-919e-fcfe8b04e8e4 |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 79a4ea26-1331-445a-a4b1-4ae4f4048df7 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 03601a4c-4432-4f61-aa43-5aced8173da4 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | e4f5e819-a380-4b99-9f27-e647e7ffa947 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 81f4cc3c-bab4-4954-b698-d51a64d6d6be |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | f6b93829-cccf-4c87-bdb3-6d88dddf1ad6 |  | checkpoint | Check Traps For Leaks
checkpoint-status | 7aeaeb84-bea8-489e-b2eb-64830fefc9d1 |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | 03da690a-971c-4ad0-ac3c-55a62c888cf8 |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | f882dfc5-1d27-4a4c-9e0b-ebc3d3b3c892 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 21a694b6-f27c-4f71-a858-049eb70c2323 |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | 2d260e49-a110-4408-93d4-300c716b43e6 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | b09b708b-8df7-4527-ad2a-0b8ebd70d997 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | 6ce7b962-a150-463b-9a3d-c3c486753594 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | 60b5b5c8-a6d6-4ba4-b704-4a976a1d82e6 |  | checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint-status | c792b341-53eb-4305-823c-802cdde28b80 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 92a32674-5c05-4672-b192-5ffbb4cb6694 |  | checkpoint | Check All Soil Pipe Connections Are Connected To Drain
checkpoint-status | 429d214d-9d07-478b-955d-40f13781034e |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | c3263c0c-f7b8-412a-8486-e83027570abf |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | 9a4ef7c6-c1c2-43fc-a234-04c4c25e720d |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 71a105d0-0f69-4e4d-9cf4-838376512d8d |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | e7d3a222-02d4-48ba-9259-0149fb41146b |  | checkpoint | Temperature set point
checkpoint-status | 940f97c3-3538-4720-a747-6a1a614785a9 |  | checkpoint | Installers name & date works completed
text | 314e876c-1b3b-5b75-9083-fb940f731e9f |  | text | Installers name
text | 40ef9dce-d80f-520f-b298-e774bc3372e1 |  | text | Date:
checkpoint-status | 52ae3708-4363-4c6c-89d6-d4dfb18b96dc |  | checkpoint | Tested by & date
text | dd2a2dee-5f54-53ef-820f-624eb45ce6ed |  | text | Tested by:
text | 874705e6-b1b0-541d-8453-7dcc05b68422 |  | text | Date tested:
checkpoint-status | 63bef7e2-c860-437b-a41c-6a69ef2e8fd9 |  | checkpoint | Council inspector sign off and date
checklist-flat | cca6fe2a-859a-4be9-9233-cc8b0030a4cc |  | checklist | Kitchen 1st fix |  |  |  |  | Yes | Kitchen 1st fix | 69d387f5-12e2-4b89-8123-84081ba52ffc
checkpoint-status | f5800ec5-03b8-4e07-8ac4-bc13f22c9377 |  | checkpoint | Cold water pipework installed
checkpoint-status | 68a0cc93-8955-443b-96c6-d03393dcf662 |  | checkpoint | Hot water pipework installed
checkpoint-status | 4a990457-0b77-4d2f-a25a-f9fdf902a678 |  | checkpoint | Thermal lagging complete
checkpoint-status | 5d350215-2321-4342-8c7e-db93f8921692 |  | checkpoint | Wingback and waste correct setout
checkpoint-status | cbc593ef-3dd5-4a7c-84ea-5d6daa0cee26 |  | checkpoint | HWC waste installed
checkpoint-status | a0369c45-c99f-4a53-a895-31a9c7a63515 |  | checkpoint | Floor waste installed
checkpoint-status | 8fe7fc08-1d5a-4b5e-b073-06e3100e2869 |  | checkpoint | Waste pipes installed
checkpoint-status | f73d81ef-4513-467d-b503-7c2a2b53d1fa |  | checkpoint | All pipework clipped and siliconed where it runs through walls
checkpoint-status | dc9fa573-91ba-42ec-adb9-6541a0e4c502 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 8d4c5fe5-5d80-4c89-8e0d-6a105f5cc164 |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | 5bcb2282-aae5-4d69-b390-b4a7cf4a4ae9 |  | checkpoint | All pipework pressure tested
checkpoint-status | c900917a-53cc-4afb-ad07-8da6a8178802 |  | checkpoint | Check no 1st fix clashes with 2nd fix fixing screws
checkpoint-status | 219fd526-f756-4f77-9e78-44b9a8163510 |  | checkpoint | Check all nogs are installed
checkpoint-status | 326bc80a-2185-4e88-b5a1-83b7a3babb53 |  | checkpoint | Installers name & date works completed
text | 9076f721-9ae0-5d30-a0a4-8a7e48b66672 |  | text | Installers name
text | 12fd19d7-b14f-5010-909f-ac4332f08534 |  | text | Date:
checkpoint-status | 9d7e690c-1eab-4606-95f7-d95e0dd26420 |  | checkpoint | Tested by & date
text | 23e52d7d-ce80-5cbd-90c3-25096787dcc4 |  | text | Tested by:
text | d76673b4-70c3-5fb4-adea-a32dcfb842b1 |  | text | Date tested:
checkpoint-status | df8994db-81ee-4b91-a268-0bd1b2fa00d1 |  | checkpoint | Council inspector sign off and date
checklist-flat | 55254dad-1ba7-4fd4-9bda-4861822d0f6e |  | checklist | Second Fix Plumbing -Apartment no HWC |  |  |  |  | Yes | Second Fix Plumbing -Apartment no HWC | 6bccc7c0-bd6d-40e8-b8ee-8e1dd83cbc48
checkpoint-status | a58dc4e4-cb03-4f04-847d-ccd68a861f60 |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 626292a0-b44b-45f3-94ad-3c836183c10c |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 9757639f-046a-4a19-bf1f-e2c2f73f7702 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | 761dd866-ddd7-4057-9af3-e10daa368871 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 27dba455-ab40-4b0b-bd3b-7d15442be54f |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 9975b67f-ca95-42a5-9611-51edd76b7977 |  | checkpoint | Check Traps For Leaks
checkpoint-status | c5457981-852e-409d-bc86-0259bfd9a03b |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | 393f8742-736f-4756-bc56-2e3a4cc41c5c |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | 3eb6f976-851b-4012-8001-5ef57cb766c5 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 9cf87a2d-5b3d-4510-8a79-eaf961478740 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | 4eabfb5a-0a65-4d83-affd-83eda3cffc63 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | b03b4d2e-b169-4ac1-add3-bafa3c2a4099 |  | checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint-status | dd2c13cc-25d4-4bb1-a3f4-4bb4b2c3678e |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 70433cfc-bfe9-49c6-b393-699f673f46e1 |  | checkpoint | Check All Soil Pipe Connections Are Connected To Drain
checkpoint-status | 3bdc99d4-e337-4657-920f-ece8152f886d |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | eb1cf47a-d111-4174-b715-6578d605457b |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | 8c12b730-0003-4dd0-89f6-7797b44a96df |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 4a565b61-250c-41de-b28d-d3acf96566d6 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 30dcb47e-5754-498b-838b-e5d477ded22d |  | checkpoint | Temperature set point
checkpoint-status | de399123-f102-4597-8a45-fa165ec3f60a |  | checkpoint | Downpipe & overflow cover installed on balcony
checkpoint-status | 7b507e20-03d1-4c76-9a39-a58fdfb82ae6 |  | checkpoint | Correct screws on balcony drain
checkpoint-status | f8613d6f-88b6-46f9-9da4-2e5dec234fc4 |  | checkpoint | Installers name & date works completed
text | 257e0c60-c5f9-534c-9fc7-8df4ba465205 |  | text | Installers name
text | e38dce97-5e60-54b0-9df5-9d9138a72da9 |  | text | Date:
checkpoint-status | c5d0515f-b943-4c5c-9c01-0288fa00c1f2 |  | checkpoint | Tested by & date
text | 316e1ae2-c069-56aa-9cee-8935aaa8a118 |  | text | Tested by:
text | 720d10d4-5064-5659-b9d2-076200293cad |  | text | Date tested:
checkpoint-status | 47948479-5bfc-4e9f-9d92-92a317770672 |  | checkpoint | Council inspector sign off and date
checklist-flat | b4ed00e8-4e54-41f7-be34-247e8f9cfa59 |  | checklist | Kitchen 2nd fix |  |  |  |  | Yes | Kitchen 2nd fix | 735b203b-3991-4a9b-be94-b78ded03fb30
checkpoint-status | 058e4586-5b48-4122-83c8-442168daa13b |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 892ee7cf-c4a3-4db6-9cd1-e2f7da53d844 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | f21720ea-04e1-4abc-9146-aaec379f013a |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | cbf2802e-377a-4044-b343-632a675bc5d9 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | e07956d5-a8d1-4854-84c2-b3e0e7525a2a |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 65a695f4-e21b-4130-b936-50c41a92a3b4 |  | checkpoint | Check Traps For Leaks
checkpoint-status | 002c6d51-d5b3-444e-a4c3-f3c55b9e6b32 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | bbb54b2c-d4bb-4454-96bb-04e8ad40f653 |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | ef9364df-4950-4670-84bc-769b83e3ef84 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | 0de472a1-498e-43bf-adee-662a95249514 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | f642b285-f2ed-401c-96b2-5f5799878161 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | c31c83a3-32fd-45c3-891c-d187da98e59f |  | checkpoint | Check FWG are clean & clear
checkpoint-status | df1af34e-169f-4203-9d7a-0a520d6b591d |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 61807b95-cbe4-4ffc-9491-badabe32eefd |  | checkpoint | Check All Soil Pipe Connections Are Connected To Drain
checkpoint-status | 7a27ce51-df28-4c43-b735-8453f21ed006 |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | cc8061cd-9b4b-4960-83bc-7792f2c17b03 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | facbe1c4-7c74-4955-bdb3-1e197cf038cd |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | f288b182-f375-4dc7-b474-8d3c5cd15450 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | a2943918-64fe-44c0-aa42-5df3f196ca25 |  | checkpoint | Temperature set point
checkpoint-status | 760b6044-1f71-4c98-97d4-b9b689546d2f |  | checkpoint | Installers name & date works completed
text | bf95d275-f902-5ff3-b34c-4d224b345289 |  | text | Installers name
text | 2d19a6a0-92fb-5a74-b642-f4e403309406 |  | text | Date:
checkpoint-status | a7935609-e461-4d9d-a857-587a7d6428d0 |  | checkpoint | Tested by & date
text | 48fc9dd7-00e2-52a5-9d2e-9d9b48bb5f75 |  | text | Tested by:
text | aa62f103-5155-5828-91d1-fa7037b2a091 |  | text | Date tested:
checkpoint-status | 1ccbc83a-8afe-47e9-965a-ba9d38455233 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 495122ad-5c73-4c7e-9c27-a9cebb5a40e9 |  | checklist | Bathroom First Fix Plumbing |  |  |  |  | Yes | Bathroom First Fix Plumbing | 78a673a0-80a5-4b95-9cdf-fcbf4eed376b
checkpoint-group | d1104ea9-c4cd-4470-9006-50aec2287475 |  | section | Bathroom
checkpoint-status | eab00afc-911b-4e3e-b945-2669a235ccb6 |  | checkpoint | W.C Supply
checkpoint-status | 4d3fb103-6c59-497a-83ec-84f45c3badc5 |  | checkpoint | Shower waste
checkpoint-status | d30fe81a-6532-46ac-9a83-ed101aeef266 |  | checkpoint | Shower mixer/check depth
checkpoint-status | 79c9bc4c-d048-4ccb-a2d5-8452862b0601 |  | checkpoint | Toilet waste
checkpoint-status | 1689e0b5-e1f9-4711-b61f-3e9e162a4e86 |  | checkpoint | Vanity Waste
checkpoint-status | fdbefedd-5f2a-4b80-8e92-57ed32ef030c |  | checkpoint | Vanity Wingbacks
checkpoint-status | 1ed871d4-9092-40ce-bfaf-7c767e42fbcc |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-group | a25befc9-f777-45e6-a652-1214835017b6 |  | section | Cleaner sink
checkpoint-status | d9848040-6211-40e7-b09e-6ca5023e8960 |  | checkpoint | Hot and cold water
checkpoint-status | 7b5c00ac-ef48-413d-85ea-634096ba6225 |  | checkpoint | Waste pipe
checkpoint-group | dfdb0478-09f5-46f9-956d-74e8d721e3ac |  | section | General
checkpoint-status | 04747b76-b6b6-405d-a208-1b374465e2df |  | checkpoint | Pipe Work Clipped
checkpoint-status | f8a32af2-625a-413c-b90b-987264b2e41c |  | checkpoint | HWC water feeds
checkpoint-status | 70143056-8b15-4cf1-ba4b-e518752e12ec |  | checkpoint | HWC waste
checkpoint-status | 78ef302c-223a-4e50-99e0-b976cbb3e1c9 |  | checkpoint | HWC nogs for strapping
checkpoint-status | e0408f0a-be2f-449f-8fc6-380952978db1 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 8622c118-eff7-4a4a-80dc-beb737f783cf |  | checkpoint | Capped Off
checkpoint-status | f18a4d9d-590d-41b8-8797-1f125b87ee43 |  | checkpoint | Check for Crossovers
checkpoint-status | e3a9b87f-7553-4afb-bf19-33cb8376c52f |  | checkpoint | Double check all sefont of fixtures
checkpoint-status | 0bbf2f7e-2bc1-492c-8c85-dedfa199571b |  | checkpoint | Acoustic lagging where required
checkpoint-status | 1aebc658-c005-4eda-a0e6-2e974c0f1570 |  | checkpoint | Thermal lagging to hotpipes where required
checkpoint-status | cc9cf746-1026-4729-9193-26274c8221b4 |  | checkpoint | Floor waste flange fitted
checkpoint-status | 6ee1c95f-9915-4208-8dc6-634faf7e3f26 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | 5caa834d-b5fa-4828-8a15-1ffdbee06997 |  | checkpoint | Installers name & date works completed
text | 74732413-622e-5431-a462-bfddfacc4379 |  | text | Installers name
text | bf4fc612-8191-5ece-b9ab-7dc5ebf7467d |  | text | Date:
checkpoint-status | c6a72624-70c2-4096-a203-34fc145b3711 |  | checkpoint | Tested by & date
text | 18f05bb9-225f-5476-8726-2363faa3a179 |  | text | Tested by:
text | 2bf336dd-695a-5be6-8c1c-e7140848a811 |  | text | Date tested:
checkpoint-status | 5478233b-1fc2-43b4-b323-02c1da01f590 |  | checkpoint | Council inspector sign off and date
checklist-flat | b1cf46a0-dfdb-45eb-988e-34bdd7e361b3 |  | checklist | 2nd fix Plumbing - Including HWC |  |  |  |  | Yes | 2nd fix Plumbing - Including HWC | 9af9b02d-26ae-4fc1-8ec2-98ba92866b4d
checkpoint-status | 9929ad11-7367-4920-b78c-6f78ad15fd07 |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | d003d1ff-9801-46b6-991c-5b6037e77b40 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | e2f8e56f-d1d9-41f8-954b-0bf3b461a45d |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | 70aeffa9-4e3a-4acd-a668-af3eb5c8ac89 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 5854bd3e-045a-4bec-921b-f69145049033 |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 9480ab4f-ea90-4d15-9d42-4bb84ebc8053 |  | checkpoint | Check Traps For Leaks
checkpoint-status | 299bb677-f1ea-4e97-9c91-599e461ccf19 |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | 5110da74-6d98-4b74-a99e-8ecee12bb786 |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | 08fb40c9-9686-49be-ac89-1cd069a30a55 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 9cfd2064-32fc-41e7-8fbc-372ac46366b8 |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | c99b16d6-9afa-40f6-9b8d-e5f9a3c57346 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | 424062f2-2397-4fd2-bb13-6e597b7e8cb0 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | 143de381-ad18-4fd5-bdbc-67d372f4547b |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | 32bd0b83-9324-4809-ac1c-3b1d3fbb92cf |  | checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint-status | a5c760cc-8666-4042-b7a5-6bc7583d9c80 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 2e694086-0082-44e8-bbe0-817e44e25294 |  | checkpoint | Check All Soil Pipe Connections Are Connected To Drain
checkpoint-status | 512ad669-80ad-4d71-9e5c-f90b66962942 |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | 570ad6c5-3127-41cf-a9c9-6308f47f8290 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | dd3ee563-9691-4e50-801b-562aa1c04d5f |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 02187dbb-4563-462c-8ddc-68868851c592 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 997fafcd-7b44-481c-b6ef-db3b50abdbbd |  | checkpoint | Temperature set point
checkpoint-status | 82617139-1573-4c0f-9360-a95515feb0d8 |  | checkpoint | Downpipe & overflow cover installed on balcony
checkpoint-status | 0d442f4f-f50f-4e35-bf28-3475a4a1d79e |  | checkpoint | Correct screws on balcony drain
checkpoint-status | 228ffda4-9bcb-4533-bdf0-0fe0dfc5917d |  | checkpoint | Installers name & date works completed
text | 66afbf1d-434a-50a9-8805-7a8b2904794e |  | text | Installers name
text | 96a6903f-b892-584c-aafa-cbb4203283a5 |  | text | Date:
checkpoint-status | 410e0af0-9ca4-4240-b128-30f758344167 |  | checkpoint | Tested by & date
text | 8ffa8697-5875-5169-ac96-a663d7a860e4 |  | text | Tested by:
text | a59ee28c-54e9-5594-925f-6a8a6be9d02f |  | text | Date tested:
checkpoint-status | 4b5206ff-b84d-484b-b9c0-d2c5f4b73ecf |  | checkpoint | Council inspector sign off and date
checklist-flat | 2a6d9034-1248-4df1-b5d9-1ab67c79f84b |  | checklist | Cleaners cupboard |  |  |  |  | Yes | Cleaners cupboard | ab3a58b5-7f6b-4777-ad39-992c50204b7f
checkpoint-status | e21bddca-4416-4883-8d54-6eb4ca1cf945 |  | checkpoint | Hot and cold water
checkpoint-status | 3541bcd3-2a1a-4702-ab88-87ed93849865 |  | checkpoint | Waste pipe
checkpoint-status | da3b45df-23dc-41dd-aef0-713b3f9afa21 |  | checkpoint | Pipe Work Clipped
checkpoint-status | a490eafc-0c81-47f2-a7ff-39f2e088cfce |  | checkpoint | HWC water feeds
checkpoint-status | 58384a2e-c64f-4113-834c-43dbf126ec85 |  | checkpoint | HWC waste
checkpoint-status | 05b2eb68-c385-4c6e-a38b-a34d17c033ed |  | checkpoint | HWC nogs for strapping
checkpoint-status | 24bc44d1-b098-4720-9529-ef5d24e8d934 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 7a0a2507-2bce-4240-8713-908b3f3d0fbd |  | checkpoint | Capped Off
checkpoint-status | 362832a7-ef5c-4a5c-a2a5-f23e59a16df9 |  | checkpoint | Check for Crossovers
checkpoint-status | 891d1dd2-ef71-4294-a4d6-f7cefb734a0f |  | checkpoint | Double check all set out of fixtures
checkpoint-status | a15e29ef-24b8-42b1-8d77-933dfeb8bf88 |  | checkpoint | Acoustic lagging where required
checkpoint-status | 0b39247a-5569-4b29-b1b6-ce149bfbaa17 |  | checkpoint | Thermal lagging to hot pipes where required
checkpoint-status | 6191813a-3032-4424-8e89-6b4aab5a5949 |  | checkpoint | Floor waste flange fitted
checkpoint-status | 760f56cd-8cdc-4feb-965a-186f336de180 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | ae91b354-0312-46d5-b6cd-dc878c9b037f |  | checkpoint | Installers name & date works completed
text | 065a66e0-2cbc-5cd3-9e49-c65ee71c6cf8 |  | text | Installers name
text | 596f3f68-5806-57e7-a074-c5d9d9fcfdd5 |  | text | Date:
checkpoint-status | f4bddca3-1cf9-4561-8bfd-574d075af5df |  | checkpoint | Tested by & date
text | ea071b4e-25f2-527d-8250-85c13765c3b4 |  | text | Tested by:
text | c8724cb3-1bfc-523e-a1e8-724da21ab0d9 |  | text | Date tested:
checkpoint-status | 065527b7-25e0-4b33-8ac3-4f77484b9fed |  | checkpoint | Council inspector sign off and date
checklist-sectioned | f65d4c4c-5eea-4dfc-8cb4-1f283980ac02 |  | checklist | In ground Watermains |  |  |  |  | Yes | In ground Watermains | ac529ad5-03f5-42b7-983b-b1b3bf71312e
checkpoint-group | 7b8e79e8-f1ea-4354-949a-83f9d02a208e |  | section | Water mains
checkpoint-status | 28e2b0cc-2408-499e-8c81-b440f76522bd |  | checkpoint | All fittings scrapped correctly
checkpoint-status | c722ded2-72c9-4801-a24f-accc55afb4a5 |  | checkpoint | Iso used on fittings
checkpoint-status | 3039a0d9-922f-434e-abfe-22f63d053145 |  | checkpoint | Valves fitted correctly
checkpoint-status | 2b0eccc0-d80b-4696-a40a-1d70cbdc3e83 |  | checkpoint | Fittings welded & weld indicator has popped out
checkpoint-status | e4511377-6cc6-44c9-90db-3b62f243150f |  | checkpoint | Trace wire and ID tape installed
checkpoint-status | 517b5335-ccad-49aa-ae57-32bc978855a1 |  | checkpoint | All open ends capped
checkpoint-status | 9d45edc9-3de2-43dc-b422-3ea0e9813ac0 |  | checkpoint | Pipework bedded correctly
checkpoint-status | cb8426bd-0004-4c19-8d6e-f4b29ef3342a |  | checkpoint | Tidy work areas
checkpoint-status | f589b039-2fb5-46e5-878e-fe7ecc1bac3e |  | checkpoint | Pressure test pipework
checkpoint-status | 64baf2de-95a8-48dc-b388-d18a1484cea9 |  | checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
checkpoint-status | ca92e12f-ee44-4052-8cc7-54e9b6ff82f4 |  | checkpoint | Backfill around pipework with fines
checkpoint-status | b308242c-85c8-4f15-8d21-5236b5580a73 |  | checkpoint | as-built completed and photo
checkpoint-status | 716f9075-e51e-4df4-ba6e-466142ec65bb |  | checkpoint | Installers name & date works completed
text | a569f184-8c4c-538c-8829-bd76e6585113 |  | text | Installers name
text | 84994663-95fe-5bed-a0c3-0ef0b61d3f09 |  | text | Date:
checkpoint-status | 778f926f-9a2e-47ef-bf33-bf5376a83296 |  | checkpoint | Tested by & date
text | 25c70f6e-2f68-5303-b9db-3b950f8dff67 |  | text | Tested by:
text | 3b5381aa-9794-5490-a59d-e4494139d83e |  | text | Date tested:
checkpoint-status | 8c2c8c3a-db8f-4fe8-a0e5-508cf2b8fc4d |  | checkpoint | Council inspector sign off and date
checklist-flat | 93df911b-54c8-4e80-9a87-b6dad07551ca |  | checklist | 1st fix Plumbing - Including HWC |  |  |  |  | Yes | 1st fix Plumbing - Including HWC | ae560a31-35df-4bea-9402-ed0c038c96a9
checkpoint-status | fa89ba69-2996-4cd2-94e3-057b4493058b |  | checkpoint | Toilet water supply
checkpoint-status | b287fc87-4439-4f1b-8fa9-c7c93b551ac0 |  | checkpoint | Toilet waste
checkpoint-status | e88dc360-f630-4fff-8119-ddd5e97ef42c |  | checkpoint | Vanity Waste
checkpoint-status | 3f691773-ba35-4b2e-a2b1-d981e177defa |  | checkpoint | Vanity Wingbacks
checkpoint-status | 0b3e4682-c7c6-48fd-8a6b-a92792f6b115 |  | checkpoint | Vanity toilet nogs
checkpoint-status | c28d607c-6486-41b7-ad09-f2215570354c |  | checkpoint | sink water & waste
checkpoint-status | 1766aa30-b2ea-4451-bbd3-4526d72ae348 |  | checkpoint | Pipe Work Clipped
checkpoint-status | c85d17f3-65da-4233-b257-7bebc75e75ba |  | checkpoint | HWC water feeds
checkpoint-status | 8758de6e-1618-4349-9b28-85fd4bbeeec6 |  | checkpoint | HWC waste
checkpoint-status | 38338b1e-ccc4-4c1d-a151-c1073bc80160 |  | checkpoint | HWC nogs for strapping
checkpoint-status | 4a420cfc-aeda-4d3e-a397-cbb4f6c0feb9 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | dfc30a3d-d5d9-4f24-befa-de7f5d9d8736 |  | checkpoint | Capped Off
checkpoint-status | 95df7911-2429-4057-bbcf-e2410046d48b |  | checkpoint | Check for Crossovers
checkpoint-status | 9dcbbea9-9087-4a96-b0de-32527ad35e61 |  | checkpoint | Double check all set out of fixtures
checkpoint-status | 866b0755-1111-44f0-8691-4b687d639e10 |  | checkpoint | Sanitary vent
checkpoint-status | 41d83c87-9d39-489c-a729-0ec8e6ea1410 |  | checkpoint | Thermal lagging to hotpipes where required
checkpoint-status | 64199a57-7b8f-4f38-a509-508a9e0ac38d |  | checkpoint | Floor waste flange fitted
checkpoint-status | f567b33d-31c4-442c-ba39-86ab3c1cf5f6 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | 64cde069-41ea-42d0-bcc7-1842ceb97b5b |  | checkpoint | Installers name & date works completed
text | 46f831ba-e10d-52f7-bbfa-a5613dd420b4 |  | text | Installers name
text | ab676138-21c5-5f06-90e2-54b77ca6285c |  | text | Date:
checkpoint-status | 55e28de1-8d1f-4fb5-8a30-045c0597b1c7 |  | checkpoint | Tested by & date
text | f4754983-cac5-5b4f-8b96-543748c26583 |  | text | Tested by:
text | 17d01080-8dba-5ff9-8e48-a8c359690b08 |  | text | Date tested:
checkpoint-status | 031e8be3-245d-430e-b580-3c2fdbdeb130 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | cda8ffa8-be90-4cac-be7c-69ed34ba83a1 |  | checklist | First Fix Plumbing - Apartment no HWC |  |  |  |  | Yes | First Fix Plumbing - Apartment no HWC | b21b12d5-afdc-4fd7-8bd2-4bb55c73da65
checkpoint-group | 25a96817-ea3d-4876-9410-acd01302ca8e |  | section | Bathroom
checkpoint-status | 0efc74cc-9a42-442c-a5ab-61760aeb3b2b |  | checkpoint | W.C Supply
checkpoint-status | d83c7da4-7211-4514-88c3-4562a7e1c1f0 |  | checkpoint | Shower waste
checkpoint-status | 50d5e8dd-251b-4994-a609-53dede92b36a |  | checkpoint | Shower mixer/check depth
checkpoint-status | 8f511bb5-f9fc-4e7d-a5be-56749b39da99 |  | checkpoint | Toilet waste
checkpoint-status | d6b336b1-ee3a-43c6-a395-75d1c90401ef |  | checkpoint | Vanity Waste
checkpoint-status | 5ee405b8-1795-4331-8b1b-759e03eefb99 |  | checkpoint | Vanity Wingbacks
checkpoint-status | 11e15ba1-c476-46cc-8cc9-c1bcd9bcae34 |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-status | 70ebc1ca-e09f-4ef8-96da-e5c20e833369 |  | checkpoint | Bath mixer where applicable
checkpoint-group | 854f0ca5-5044-401f-948b-b38bb87d0467 |  | section | Laundry
checkpoint-status | 92e2f337-4ed3-41c8-845f-c8fc0947af80 |  | checkpoint | Hot and cold water
checkpoint-status | 6ec05deb-d2cd-4ccb-bcee-c13c0c67eeac |  | checkpoint | Waste pipe
checkpoint-group | c1e5ff74-7ab0-4ddc-86bc-0d3534857cec |  | section | Kitchen
checkpoint-status | 37138ee3-94ec-4332-8223-ff3542486873 |  | checkpoint | Hot and cold water
checkpoint-status | f53f49bb-d453-4565-a684-96841844cc0f |  | checkpoint | Waste pipe
checkpoint-group | 10019e68-db18-4664-80c8-2e046a627817 |  | section | Balcony
checkpoint-status | c3c1cdd1-62cb-40be-9a97-da466d532715 |  | checkpoint | Balcony drains & pipework installed/correct screws in flange
checkpoint-status | 681de9c2-4735-492a-8196-95ab2965f810 |  | checkpoint | Correct screws in flange
checkpoint-group | 221256bd-a2be-4c7b-ac10-a6f298bf8306 |  | section | General
checkpoint-status | e88bf852-16f4-4881-a093-d15e2fe376b2 |  | checkpoint | Pipe Work Clipped
checkpoint-status | 84a0cbdd-2475-432e-8758-9d8e6b36a19c |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 7364b274-48c1-4abc-be0c-5f721fd6f2b6 |  | checkpoint | Capped Off
checkpoint-status | fe74c86f-e967-4c5a-8bd6-e0e5e60d9b2f |  | checkpoint | Check for Crossovers
checkpoint-status | 26e59ce9-c09f-4023-9e0d-ec04aae40be5 |  | checkpoint | Double check all setont of fixtures
checkpoint-status | 6022668b-53d8-4772-8e66-ed320555991d |  | checkpoint | PRV & water meters installed
checkpoint-status | 7a867b97-77cc-42fe-ae4b-19245993eb4d |  | checkpoint | Acoustic lagging where required
checkpoint-status | f64e75e3-231d-40fc-8344-ac74c28a6e1a |  | checkpoint | Thermal lagging to hotpipes where required
checkpoint-status | 228437e6-11f9-4e91-be97-87f37466cfeb |  | checkpoint | Floor waste flange fitted
checkpoint-status | 39c0bf9e-c18b-47ea-99cb-79874c9f1ba7 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | 9cac8457-68e6-4b9e-8ab4-5fe817149b53 |  | checkpoint | Installers name & date works completed
text | 4653a5a6-2d17-5ad6-aa02-63504f727ca7 |  | text | Installers name
text | 381c8dd8-3242-55f3-9ce0-00c4a66a51bc |  | text | Date:
checkpoint-status | 8bfde875-6021-4b53-a561-6bba04a9114b |  | checkpoint | Tested by & date
text | 8cd80e99-dc41-5bba-9518-81ed7c69bf90 |  | text | Tested by:
text | 320183b9-8cfa-5b04-9e61-2984b559f842 |  | text | Date tested:
checkpoint-status | 31e83c0c-eedf-4a7b-962d-0f289a48bb4f |  | checkpoint | Council inspector sign off and date
checklist-flat | 5ee3ffc5-b068-446b-bd0d-c74310eda1bf |  | checklist | Commercial Kitchen 1st fix |  |  |  |  | Yes | Commercial Kitchen 1st fix | bc4c2ce2-725a-4902-b7b2-d08871e42852
checkpoint-status | ccabe075-7908-4560-b873-174f0babbb8f |  | checkpoint | Cold water pipework installed
checkpoint-status | e8705c3a-8249-42d2-a2c0-7b21b1082482 |  | checkpoint | Hot water pipework installed
checkpoint-status | 478f4a42-60f6-4324-b455-e0841d42988a |  | checkpoint | Thermal lagging complete
checkpoint-status | b332df39-dde0-454f-8928-90638ebbde81 |  | checkpoint | Wingback and waste correct setout
checkpoint-status | 9461ca30-b397-4179-a664-6a5056b44247 |  | checkpoint | Gas pipework install
checkpoint-status | 2621fc8c-2358-4f9c-9ff6-5444d236d0cc |  | checkpoint | Gas solenoid & Emergency stop
checkpoint-status | 97c66676-f697-4b15-89be-7142aaf878a0 |  | checkpoint | Waste pipes installed / High Temp wastes.
checkpoint-status | 36df7eea-31d9-44d4-9c29-83772420142f |  | checkpoint | All pipework clipped and siliconed where it runs through walls
checkpoint-status | 94bbb548-e5ea-4e79-bf72-4289a4315583 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 487c159d-8a90-4ec6-b05e-8fd54a119011 |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | d0cf3654-b914-4aef-a2bd-8c5037724151 |  | checkpoint | All pipework pressure tested
checkpoint-status | 7e2c6562-ff6b-44f3-8a80-c2bdf5ff03e4 |  | checkpoint | Check no 1st fix clashes with 2nd fix fixing screws
checkpoint-status | 24df31ce-84c3-4425-bec5-c28a47e094f1 |  | checkpoint | Check all nogs are installed
checkpoint-status | 8b0af48c-bf0a-44c9-9c23-ce1bde953aee |  | checkpoint | Installers name & date works completed
text | 9282eb84-f16c-5a10-af25-1ed6b9b5e9f2 |  | text | Installers name
text | 337b0b06-fde3-5b5c-a936-be39a05e10c9 |  | text | Date:
checkpoint-status | 815e121f-5e18-416e-a9d8-0f2fb4aac853 |  | checkpoint | Tested by & date
text | f0cfe5d4-a75e-5db3-9446-1b786444c052 |  | text | Tested by:
text | 6ae941c6-37b1-55ca-8043-ebb55990a9be |  | text | Date tested:
checkpoint-status | 40ec6a74-60b1-4ca9-b07e-e113716f6974 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 7d5e98e3-bb8a-4101-902d-7e5618086fd0 |  | checklist | SS or SW pump QA |  |  |  |  | Yes | SS or SW pump QA | c2e2153b-4519-4ad9-bfe2-eced04d2ebe8
checkpoint-group | 1a8eb7a8-d110-48e1-806b-238bde691c43 |  | section | Pumpset manifold
checkpoint-status | 59726cad-56d7-4b27-aa12-87433bad7491 |  | checkpoint | Connections welded correctly
checkpoint-status | a84d7cf9-31d8-498b-a326-40c32a9b81b4 |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | e53c5a80-ac8f-4c87-b1f1-58e9ba580172 |  | checkpoint | Valves fitted correctly
checkpoint-status | 87d07640-7fd7-4ce6-ad15-59f9a1915b2d |  | checkpoint | Line strainer fitted between pump & tank
checkpoint-group | 5d61a632-1573-4015-8211-34bf77bc5d06 |  | section | Pumps
checkpoint-status | eece8a33-d415-4a9b-a69a-d004fdebc967 |  | checkpoint | Pump 1 Startup KPA
checkpoint-status | 2f11fabe-f10d-436e-82f5-fc94cba237b6 |  | checkpoint | Pump 1 kick out pressure KPA
checkpoint-status | 0f3a9684-f01b-4416-932b-b3af01d40a8a |  | checkpoint | Pump 2 Startup KPA
checkpoint-status | 0ae94de4-898d-44da-a94a-2f261dc19920 |  | checkpoint | Pump 2 kick out pressure KPA
checkpoint-status | ea64aff3-a1f3-49aa-944e-738c72c5247e |  | checkpoint | Pressure vessel pressure
checkpoint-group | d7ffff05-5f1e-4b39-9cee-31962018ee85 |  | section | General
checkpoint-status | 6f1ea831-224a-402c-88ed-686d2e6fa37b |  | checkpoint | Mains water change over
checkpoint-status | c719fa5f-b1e4-4712-9999-9148a3f2a291 |  | checkpoint | Flow test pump
checkpoint-status | 08889b6c-52b3-4ca6-a3b6-300c4da89166 |  | checkpoint | Pressure tests pipework
checkpoint-status | aea257f1-0a32-40d2-b1f0-d7d470d106be |  | checkpoint | Visual check (for leaks from valves, tees, saddles, etc)
checkpoint-status | 888c0746-644d-4225-ae64-1a624f509b59 |  | checkpoint | Non return valves fitted
checkpoint-status | caa02638-dca4-4cfa-88c2-6efebfb193db |  | checkpoint | Installers name & date works completed
text | 7a5a3630-398c-5cdb-ae80-416ad703e280 |  | text | Installers name
text | 4e084e22-89b7-59e4-bad9-fe911b804109 |  | text | Date:
checkpoint-status | 446db509-7a19-4051-b4f0-d093969d7a71 |  | checkpoint | Tested by & date
text | 8a8a0674-afae-51f6-b36f-4c408e7760de |  | text | Tested by:
text | 4d9864e4-d351-554e-a44e-c161bca2e5e7 |  | text | Date tested:
checkpoint-status | ba1efec6-43b9-4050-9cfe-2fe35b7a3ce7 |  | checkpoint | Council inspector sign off and date
checklist-flat | 17ef5100-9945-476c-aa7f-8a1db8065d92 |  | checklist | Factory room |  |  |  |  | Yes | Factory room | e4995390-ff17-461d-ac0c-c8e1b91c87c5
checkpoint-status | 7090829f-d5b6-4945-ab6d-24bca1a6a80f |  | checkpoint | Waste pipe
checkpoint-status | 09004187-b5dc-485d-abe3-3cf2168d9889 |  | checkpoint | Floor drain installed to correct height
checkpoint-status | 06076f69-d9ca-4b6e-9239-7e07c5e41cf3 |  | checkpoint | Floor drain level and bedded correctly
checkpoint-status | 4bbef5a8-d8fc-4922-a316-c5016416798d |  | checkpoint | Floor drain strainer and grate installed
checkpoint-status | afa3c152-142a-4ba7-a236-7bc33114951f |  | checkpoint | Floor drain trapped clean and clear
checkpoint-status | 88d23775-f222-474b-9f15-cbef59670550 |  | checkpoint | Channel drain installed at the correct height
checkpoint-status | b6c71181-08f4-4f9a-91c6-42a5027493dc |  | checkpoint | Channel drain installed level and bedded in place
checkpoint-status | d08b0a89-da0c-4d56-996a-9f26f53a89cf |  | checkpoint | Channel drain strainer and grate installed
checkpoint-status | f2e551a8-a235-40eb-8379-0d36e1c88784 |  | checkpoint | Channel drain trap clean and clear
checkpoint-status | 99b63d0c-adc0-495a-ac71-2b32a1e7c910 |  | checkpoint | Channel drain and floor drain protected for floor coating
checkpoint-status | 8ff53f50-87b8-42d5-b26a-05a18373b1bb |  | checkpoint | Final inspection of floor drain
checkpoint-status | 341332b7-6ce5-4b7a-adcd-1e6a91d523d7 |  | checkpoint | Final inspection of channel drain
checkpoint-status | bbde2506-33bc-40ef-819c-d88284c716d4 |  | checkpoint | Tundish points in installed
checkpoint-status | 8cf6dd87-6cc2-4a1b-8189-7bbab23e4633 |  | checkpoint | Vents installed
text | 302dea3f-22d2-555a-8f0c-3e37a995bd88 |  | text | Installers name
text | 6ef84e06-67b9-582a-9d63-c57d03a3f330 |  | text | Date:
checkpoint-status | 1121b995-3068-4e86-974e-6db1d52d558b |  | checkpoint | Tested by & date
text | bde8bacc-5eb4-5510-9b26-092bd4d91b49 |  | text | Tested by:
text | 1cbf0dea-c14f-5e8a-b64e-546f3fc7ee71 |  | text | Date tested:
checkpoint-status | f9441a22-2a18-49e5-a2d6-9dad5cd5fb58 |  | checkpoint | Council inspector sign off and date
checklist-flat | fec286ae-a8f8-406e-afa3-c3c9ce802df3 |  | checklist | Syphonic Stromwater |  |  |  |  | Yes | Syphonic Stromwater | fa74e348-3ce0-46cb-97a7-c136064931e5
checkpoint-status | 53821cfc-e9f1-4aea-ac5c-873195f18c75 |  | checkpoint | All pipework installed as per design drawings
checkpoint-status | 6841e542-439a-4141-ac0a-ee166c1143f4 |  | checkpoint | Fittings scrapped and ISO before welding
checkpoint-status | f38cd05f-fb5c-45a8-86e0-c824cec460d0 |  | checkpoint | Correct fittings used
checkpoint-status | edb12178-f7db-4706-a695-8ca17a2d50fb |  | checkpoint | Brackets and clips installed as per design
checkpoint-status | 6c93d48d-6c04-45a2-a227-59a4664b4b50 |  | checkpoint | Seismic braces installed as per design
checkpoint-status | 78c6365d-0a70-469e-8a26-8475bdfc763b |  | checkpoint | Outlets installed and syphonic grates installed
checkpoint-status | 31f6010c-1417-49f1-97ca-86177d2e526c |  | checkpoint | Overflow outlets fitted with riser fittings
checkpoint-status | 1e1fbdef-4f13-4581-adac-0e3201c3552c |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | 5c752259-d8b4-4081-8c61-a1c723f279c8 |  | checkpoint | All pipework flood tested
checkpoint-status | c7e9ebc2-6700-4040-96d4-6d4d96619b87 |  | checkpoint | Installers name & date works completed
text | 537d59a8-6f69-5f79-acdb-3b0792dbacfb |  | text | Installers name
text | 297d27df-efb8-52d9-b394-4d773014adf7 |  | text | Date:
checkpoint-status | a02a8e5f-43a4-4c79-9fc2-16fb181eb958 |  | checkpoint | Tested by & date
text | 8fe2770e-de7b-50d6-affa-84ea997c0881 |  | text | Tested by:
text | 3c9d08f6-4daf-5621-a828-eb9738ee7565 |  | text | Date tested:
checkpoint-status | ee27754d-22ed-4a26-abeb-18c8b5f1b37d |  | checkpoint | Council inspector sign off and date