## Structure
Project Name | 42 Favona Rd Warehouses | Checklists
Drainage Installation
1.Stormwater | 1. 150mm upvc SN16 Building Downpipe Connection | SWMH D1-1 - SWMH D1-2
Stormwater- Pipeline Installation Checklist
| 2. 300mm Upvc | SWMHB1-3-1 Grated Lid
Stormwater- Pipeline Installation Checklist
| 3.150mm upvc SN16 Building Downpipe Connection | SWMH B 2-1
Stormwater- Pipeline Installation Checklist
| 4.150mm upvc SN16 Building Downpipe Connection | SWMH B2-2
Stormwater- Pipeline Installation Checklist
| 5.150mm upvc SN16 Building Downpipe Connection | SWMH B2-3B
Stormwater- Pipeline Installation Checklist
| 6. 150mm ，200mm，225mm, 300mm upvc SN16 Building Downpipe Connection | SW Downpipes along side B2-3B to Holding tank
Stormwater- Pipeline Installation Checklist
| 7. 150mm upvc SN16 Building Downpipe Connection | SWMH B1-9
Stormwater- Pipeline Installation Checklist
| 8..2 x 175mm upvc SN16 Building Downpipe Connection | SWMH B1-6-2
Stormwater- Pipeline Installation Checklist
| 9..2 x 175mm upvc SN16 Building Downpipe Connection | SWMH B1-6-3
Stormwater- Pipeline Installation Checklist
| 10. 3 x 175mm upvc SN16 Building Downpipe Connection | SWMH B1-6-4
Stormwater- Pipeline Installation Checklist
| 11. 1 x 175mm upvc SN16 Building Downpipe Connection | SWMH B1-6-5
Stormwater- Pipeline Installation Checklist
| 12. 3 x 150mm upvc SN16 Building Downpipe Connection &100mm Channel | SW Chamber
Stormwater- Pipeline Installation Checklist
| 13. 1 x 100mm upvc SN16 Building Downpipe Connection | SW Chamber
Stormwater- Pipeline Installation Checklist
| 14. 3 x 175mm upvc SN16 Building Downpipe Connection | SWMH D1-4
Stormwater- Pipeline Installation Checklist
| 15. 175mm Downpipe Connection | SWMH D1-4 to D1-2
Stormwater- Pipeline Installation Checklist
2.SEWER | I Will Send to you later

## Checklist
name
Cesspit Installation
Setout & position checked and confirmed
Cesspit installed as per standards
Setout & position checked and confirmed
All cut pipes epoxied
Confirm Levels Correct
Cesspit cleaned of all Debris
Concrete Apron installed (if required)
Frame & Grate alignment checked
Minimum sump depth checked
Captive Grates installed (if required)
Cesspit complete & ready for sign off
name
Drainage Installation
Setout and position checked and confirmed
Trench width and lid level (attach photos)
Gap 10 & 65 measured and ordered
Stockpiles & cart out confirmed
Pipework installed as per specification
Pipe test booked and test ready
CCTV complete
As built plans complete
Clegg test on hardfill (results recorded)
RON & CAR signed off
Pipework complete & ready for sign off
name
Pressure Test
Test Media(Water/Gas/Fire)
Working Pressure
Test Pressure(PSI/Kpa)
Duration of Test (mins)
The above systems have been installed and pressure tested
Witness Name & Company
Bassett Representative
name
Drainage As Built Details
As built Pipework complete and ready for sign off
Pipe Diam (mm)
Pipe Length from MH Centres(mm)
Pipe Type
Pipe Supplier
name
Below Ground Services Checklist
Pre-Installation
Pre-Installation checks complete
Drawing Red No:
Starting Point:
Finishing Point Established
Grade of Pre-Line%
Level Obtained
Installation
Pipe Work Tested
Air
Water
Visual
Backfill Material
Local Authority Inspection Passed
Name of Inspector:
Stormwater- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Connections to manholes complete and approved
All Downpipes have been checked, installed and approved
How many installed?
Location confirmed
Heights are correct
Caps are secure
All Cess Pitts have been checked, installed and approved
How many installed?
Location confirmed
Heights are correct
Caps are secure
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Sewer- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Drainage - Manhole Install Checklist
Manhole Install
Latest consented drawings
Drawing Ref No.
Setout Completed checked and accurate
Excavation Accurate - Location & Depth
Ground conditions checked & acceptable
Bedding depth and material correct & compacted
Correct manhole installed to specified height and sitting level
Manhole Risers Installed (if applicable)
Joints & connections correctly sealed as specified
Manhole benching completed and acceptable
Concrete Lid Installed and sitting appropriately
Cast Iron Lid Installed and sitting flush
Signoff on Completed Work (Council etc)
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Services Trench Checklist
Trench Excavation
Latest consented drawings
Drawing Ref No.
Trench type
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Services laid as per detaill - attach relevant cross section
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Connection Checklist
Approval given to connect
Heights confirmed - Invert level
General comments & photos during installation
Connection completed
Watermain- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Gasmain- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Firemain- Pipeline Installation Checklist
Pipe Laying
Latest consented drawings
Drawing Ref No.
Setout completed checked and accurate
Excavation Accurate - Location & Depth
Ground Conditions Checked & Acceptable
Bedding depth and material correct
Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
Start Invert
Finish Invert
Grade of Pre-Line %
Product Type
Install Tests completed, reviewed & approved
Local Authority Inspection Passed
Name of inspector
Date
Pipe Laying Completed
Laid by
Bedding Sound
Soil Removed
Trench Compacted
Hard Filled
Connections to manholes complete and approved
Air Test Complete
Area of Work Inspection Completed & Sign Off
Sign Off By
Acknowledgement of checklist by
Foreman
Backfill
Backfill methodology and material confirmed
Any formwork/ debris removed from area
Any waterproofing/ drainage / service requirements completed and inspected
Approval given to commence backfill - attach any other relevant inspections and observations closedout
General photos and observations during backfill
Backfill completed correctly and heights checked/ correct
Civil Install Checklist
Foundation Set out
Confirm Levels Correct
As Built
As built Pipework complete and ready for sign off

## Weekly Checklist
type | name | value
checklist | Weekly Safety Inspection
section | Site Control
checkpoint | Hazard board and signage up-to-date
checkpoint | Environmental plan - issues
text | Toolbox meeting last date
checkpoint | Safety inductions for all on site
checkpoint | Safety notice board current
section | Site Facilities
checkpoint | Offices-Clean, adequate and good lighting
checkpoint | Smoko sheds-clean portable water
checkpoint | Toilets-Clean, Washing water
checkpoint | Tool/equipment sheds adequate
section | General Site Tidiness and Access ways
checkpoint | Clear access to work areas
checkpoint | Stairways and access ways clear
checkpoint | Hoardings/fence and gates secure
checkpoint | Loose materials secure from wind
section | Personal Safety Equipment
checkpoint | Signage displayed and legible
checkpoint | Hardhats being worn
checkpoint | Correct footwear being worn
checkpoint | Glasses/ear muffs/vests/ masks used
section | First Aid/Fire Prevention
checkpoint | First Aid Box available and current
checkpoint | Accident Register
checkpoint | Fire Extinguishers
label | Available
label | Current(12mth)
label | Sufficient
checkpoint | Evacuation
label | Procedure Current
label | All emergencies Incl.
section | Cranes/Hoist/Lifting equipment
checkpoint | Proper lift assessment plan done
checkpoint | Crane Certification current
checkpoint | Slings/Chains Certified
checkpoint | Operator procedures in place
checkpoint | Inspections being done
checkpoint | Man cage availiable
checkpoint | Emergency plan in place
section | Compressed Air Equipment
checkpoint | In good condition
checkpoint | Appropriate guards fitted
checkpoint | Trained User
checkpoint | Excavations Correctly shored
section | Welding/Gas Cutting
checkpoint | Hot works permits being issued
checkpoint | Fire extinguishers on hand
checkpoint | Operators using PPE
section | Electrical Equipment
checkpoint | Main board lockable/weatherproof
checkpoint | Current tagged and damage free leads
checkpoint | Current tagged plant
checkpoint | Current tagged Lifeguards
checkpoint | Leads safely placed
checkpoint | Equipment in good condition
checkpoint | Appropriate guards on equipment
checkpoint | Adequate temporary lighting
section | Chemicals
checkpoint | Correctly Stored
checkpoint | MSDS available
checkpoint | Operators using PPE
section | Tools
checkpoint | PAT tool WOF current and secure
checkpoint | Staff trained in tool use (SWPS)
checkpoint | PAT signage on site
section | Scaffolding
checkpoint | Notifiable weekly Scaftag/current
checkpoint | Handrails/mid-rails
checkpoint | Toe boards
checkpoint | Platforms
checkpoint | Ladders/stairs
checkpoint | Base sound
checkpoint | Work platforms clear
checkpoint | Platforms trip free
checkpoint | Planks tied down
checkpoint | Headroom clear
checkpoint | Ties/bracing adequate
section | Ladders
checkpoint | Good Condition
checkpoint | Secured top and bottom
checkpoint | Stays to step ladders
checkpoint | Working 2 Steps down
section | Fall Hazards
checkpoint | Floor edges
checkpoint | Floor openings
checkpoint | Lift shafts
checkpoint | Stairs