## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 1b7407b2-b3c9-426b-9dfb-ebf07337e78c |  | checklist | Second Fix Plumbing -Apartment no HWC |  |  |  |  | Yes | Second Fix Plumbing -Apartment no HWC | 0eb42fe4-2d5a-4aa4-9dd5-acfd4508088d
checkpoint-status | 875d6181-b03f-4bd4-96f5-4e844fd80d71 |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 644a68c9-f2ea-4288-b1be-e8ae528e966b |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 4196acfb-c5f8-4d3d-b492-691567d3e839 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | fb7a93b5-1f0d-4c86-995c-8f6255c8ed59 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 51418e23-ff8e-4edd-beda-aa6bba992dec |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | d65af899-1f3a-4d0c-b927-fa3d291822b6 |  | checkpoint | Check Traps For Leaks
checkpoint-status | 9650633a-8247-485f-83c0-8bda3090df4f |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | 39fc06e6-b4b8-44de-acb3-7eddf8b1d4bb |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | eca33be0-53f9-4e5d-b4b9-d67090353f01 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 8bfbb9aa-bd73-4baa-917a-65f36872c8e6 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | 6b56463c-d83b-4250-90d9-3554866c26c2 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | ff61b754-c2d6-49ad-a0a7-ac003afe2439 |  | checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint-status | df34b3d4-a219-4036-afaf-00c161608c4b |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 4aa60192-61f7-48d2-8e55-b2a2c489931f |  | checkpoint | Check All Soll Pipe Connections Are Connected To Drain
checkpoint-status | d387fb87-bb64-4f62-8022-21b65323a068 |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | e2e03af6-607c-4e69-86b5-64247cd9be64 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | 1149faa3-493c-4505-b76e-04593f612439 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 8c4a6056-e747-4628-8cbe-adbd1d3a68dc |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 2fed0e2f-9bb6-442a-87c8-58af674815e3 |  | checkpoint | Temperature set point
checkpoint-status | a58c6897-bb55-4d49-85a3-25a19f17a1f5 |  | checkpoint | Downpipe & overflow cover installed on balcony
checkpoint-status | 8577fdc0-59d8-42e9-a100-a943b8f82139 |  | checkpoint | Correct screws on balcony drain
checkpoint-status | 45c63ead-6780-4ba4-8a1c-8b22fbcb6f8f |  | checkpoint | Installers name & date works completed
text | 08aebe59-6e24-5723-a659-e08aca7a7eb7 |  | textbox | Installers name
text | 05911a21-fbe9-528d-b837-1dc1766fbf56 |  | textbox | Date:
checkpoint-status | 06466aa7-fd6c-4ad2-a18a-fc9b138d34d9 |  | checkpoint | Tested by & date
text | 959bde7b-f600-514c-bf11-68e1e15ed285 |  | textbox | Tested by:
text | cb115775-44b1-5ac7-a0e5-ba77db6e07ec |  | textbox | Date tested:
checkpoint-status | a6f7cc7b-7a81-4026-8842-0ebe50883833 |  | checkpoint | Council inspector sign off and date
checklist-flat | a0f01fa4-c350-4e0e-b315-f0606bfb2ff5 |  | checklist | Second Fix - No Hot water cylinder |  |  |  |  | Yes | Second Fix - No Hot water cylinder | 1dc46eb9-72ed-4a31-908d-8884325181d3
checkpoint-status | bc16af83-9c3a-4d84-841e-b6917c21d409 |  | checkpoint | Flush all pipework before fitting taps & fittings
checkpoint-status | a43a5715-32aa-4131-a5e7-bd6d1feb116e |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 24ac28c0-b6af-428e-b857-c35461420d9c |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | 84ff5a24-c068-4668-8a20-405834cf48a9 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | bca4b781-1e18-4269-893e-9b041b005cd3 |  | checkpoint | Check Traps For Leaks
checkpoint-status | e16d300b-c4b9-40cd-947d-88a8157a43ba |  | checkpoint | Check Cisterns are flushing correctly
checkpoint-status | d7d8dcc6-029f-4a1f-a09b-417b634c3852 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | e3c98a26-236f-4118-aad8-f2b9f28f71f3 |  | checkpoint | Check shower waste is clear
checkpoint-status | f6f60520-7b00-4408-85ec-b3919a670432 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | c646b990-481a-4604-b8f6-beccd1d1f04b |  | checkpoint | All Your Rubbish Removed Or In Bins Provided
checkpoint-status | 46eb9f4d-6a3b-4e48-bad4-0a4683c46d4e |  | checkpoint | Check no fixing screws have fit pipes
checkpoint-status | c1691cea-9e8a-4bac-82ef-de280616de3e |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 249f999c-a132-4674-a140-75efad1df71e |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | 35f113c7-63c7-4b13-8882-1b827b144a69 |  | checkpoint | Temperature set point degree 55degC
checkpoint-status | fe063f6d-ef4b-433f-a8ef-04fa9213438f |  | checkpoint | Installers name & date works completed
text | c4cc8b1f-c427-5ad5-b9ee-5721d2e7b84c |  | textbox | Installers name
text | 6737b5f3-974a-5994-87ef-e1c9327ba05e |  | textbox | Date:
checkpoint-status | 922fcb25-a9d8-4231-ad12-9b9efacdbec6 |  | checkpoint | Tested by & date
text | 1c3fe2ec-1e79-5e4a-9a42-af0ae2fe9924 |  | textbox | Tested by:
text | 25811d02-0ef2-5b56-89d7-20a824ae631c |  | textbox | Date tested:
checkpoint-status | 0c676e97-d929-4476-b66c-560ffacfa32a |  | checkpoint | Council inspector sign off and date
checklist-flat |  |  | checklist | Seismic Checklist |  |  |  |  | Yes | Add Seismic Checklist | 2b937435-1834-4ab6-866b-0ffa091d0ccc
checkpoint-status |  |  | checkpoint | Latest Seismic drawing details provided
holdpoint |  | Data not allowed on signoff: Rev(223abcb2-6044-4e32-bb0b-81f46bc924a0) | signoff | Raise Remedial / Request Sign Off
checkpoint-status |  |  | checkpoint | All seismic bracing requirements have been completed in accordance with deisgn and specification
holdpoint |  |  | signoff | Raise Remedial / Request Sign Off
checklist-sectioned |  |  | checklist | Area: |  |  |  |  | Yes | Add Services Trench Checklist | 337db184-4708-4487-948e-05c5b6a15632
checkpoint-group |  |  | section | Services Trench Excavation
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | 82f552eb-596c-4c18-ae82-f56245c3b8a1 |  | textbox | Drawing Ref No.
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Setout completed checked and accurate
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Excavation Accurate - Location & Depth
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Services laid as per detaill - attach relevant cross section
boolean | fbed20ac-d487-42c4-b8c4-cd594e8c349f |  | tickbox | Bedding Sound
boolean | b4e338ef-1962-4908-9d51-7f8b98fc91c0 |  | tickbox | Soil Removed
boolean | e24d910b-24ae-41ca-9176-502d616ddba2 |  | tickbox | Trench Compacted
boolean | be320b04-bd61-4104-82b4-4c3d4f55bf0b |  | tickbox | Hard Filled
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | bc91a210-7eda-4289-a86d-5f70f2b7d791 |  | textbox | Sign Off By
text | 8b66f5dd-9275-47fa-85eb-dd1048b84ed5 |  | textbox | Acknowledgement of checklist by
text | df22312c-cbd2-493f-ae37-0c939962242c |  | textbox | Foreman
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-group |  |  | section | Backfill
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
holdpoint |  |  | signoff | Raise remedial / Request signoff
checklist-flat | a4fa9925-5a62-496d-a13b-9b567a0486d8 |  | checklist | Factory 2nd Fix |  |  |  |  | Yes | Factory 2nd Fix | 4d87e292-e91f-454a-b108-3495aca0b73c
checkpoint-status | 96ef1a2b-af2b-4b3a-8bc3-e5a15a75d21b |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 2bf59b73-a39f-4494-ac0c-21a57f3a71b5 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 6f1dfbcf-cf17-4846-b5c4-a3ae6d651814 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | 25762efe-00d9-4d08-b1de-16b45a7c32c3 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 06b4f2ad-b184-47f0-b293-f9d215fdd276 |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | d02cd86a-3e27-462f-a6b3-670e14c4d90c |  | checkpoint | Check Traps For Leaks
checkpoint-status | 7cba1469-a906-4dd1-8e4d-4366b08545cd |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | 69a9e769-a092-45e7-a9b3-b01cf7f4a791 |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | f9e351b1-db20-4915-bde8-e5214e81869a |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 00505c17-a923-4af0-b42d-a33ac8d7949e |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | 3f1e92ea-bace-4993-a6bb-f8b5909014d9 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | b4528013-e9fc-4415-a3ed-aa5e8eb98e3c |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | a8d277c2-38ff-41bb-b751-bc84cbb22c67 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | 1df4846e-804c-446a-9488-a4ec6cd86128 |  | checkpoint | Any future waste stubs capped
checkpoint-status | aa00b56e-154a-4b85-953c-f349f8ee27a9 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | da115099-40f8-4cdf-b986-59a539dadddd |  | checkpoint | Check All Soll Pipe Connections Are Connected To Drain
checkpoint-status | 0fe5bce7-ef9c-4726-8a8a-206c7fa66d9f |  | checkpoint | Picked Up All Left Over Material & Retumed to Office
checkpoint-status | e12cce48-1bbf-4b7e-a63b-c63b3285b4a0 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 61b8d1af-adf3-4218-9f37-95223c22b53f |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 7e79a84c-c7d7-4643-8fdb-76864b95778c |  | checkpoint | Temperature set point
checkpoint-status | f467b5e6-c718-477f-a5e6-e592addb1e67 |  | checkpoint | Installers name & date works completed
text | 226a5e59-31fe-539f-a862-873dccbc8e56 |  | textbox | Installers name
text | c9cd6fbd-940d-574e-82a8-0564b4bca759 |  | textbox | Date:
checkpoint-status | 2b6bb1ce-4c9c-4584-9f08-1e7991695cb1 |  | checkpoint | Tested by & date
text | 2a029991-2779-5b07-845b-b36d581c79d3 |  | textbox | Tested by:
text | f22cc2e4-835f-5b43-b782-becfc7944fde |  | textbox | Date tested:
checkpoint-status | 83e9fe92-f4e9-49d9-9950-b3a54ea4492d |  | checkpoint | Council inspector sign off and date
checklist-flat | 0f5befd4-4028-4ea9-8a55-a4e36ef96ec9 |  | checklist | Classroom 2nd fix |  |  |  |  | Yes | Classroom 2nd fix | 51c23b74-3688-4424-8f72-ba0f67e41ce6
checkpoint-status | 57143c25-0c9e-4b89-83cf-1367a5176e1c |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | ae56a2b0-6f7d-443d-a260-7e9b0519f676 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 45ab3f54-89af-4528-98c6-36e62f29a7e9 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | 148340e4-c94c-4821-8cda-500ce159b22a |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 96a9d165-a608-4af2-9ab8-61dd575027eb |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | a813f45f-c832-4368-a94d-572d4d954a4f |  | checkpoint | Check Traps For Leaks
checkpoint-status | f262baf3-193a-4d63-b29c-54acde50f55d |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 231d11b3-0401-4be9-85ad-eb2883a1f39e |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | c9d1286a-8a35-496c-ae53-fd1b87f58074 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | 47dae718-8679-4bba-afd7-c778231843e0 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | bc6b9bba-2373-459c-8dae-54c5489803bc |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | f0263505-9182-452e-87fb-afe8a5857ebb |  | checkpoint | Check FWG are clean & clear
checkpoint-status | 7e8c5972-7022-43a9-8a63-e8e50d2953e3 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 24847ac4-a2ae-4615-bff7-5063e7a5e1bc |  | checkpoint | Check All Soll Pipe Connections Are Connected To Drain
checkpoint-status | 8fd28df7-a947-40e6-9c1f-8faf75254052 |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | 7fa0e3e8-6112-4a89-bd77-d040ceace8d9 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | 6aa5ee91-d0ef-41db-b72c-586110686930 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 27712dd1-907d-483d-9f66-6433f3593bd2 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | ff331fd7-2826-4c86-9d1b-71e953becd75 |  | checkpoint | Temperature set point
checkpoint-status | e8a259d7-cff2-436c-83b1-10e6c10b881b |  | checkpoint | Installers name & date works completed
text | e1cbc396-bd71-509f-842c-1e337590617a |  | textbox | Installers name
text | 567962c3-62ff-5844-9e6c-d2014665204a |  | textbox | Date:
checkpoint-status | ffd0569c-e289-4263-955e-bf6919cea462 |  | checkpoint | Tested by & date
text | 9cfe9c07-efef-58ec-b05e-6c49e7cfbccf |  | textbox | Tested by:
text | ee255da5-db23-5882-9aaf-2d91acaa2ac7 |  | textbox | Date tested:
checkpoint-status | 5f967f26-3d69-44de-95d4-b4dd624ccda4 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 48815a05-d4a3-4ab1-bb0d-0b8f8506417f |  | checklist | First Fix Plumbing - Apartment no HWC |  |  |  |  | Yes | First Fix Plumbing - Apartment no HWC | 56cb6d64-dfad-4971-bde4-b8e374b5a480
checkpoint-group | 1976db18-bc95-4c63-b9f5-b7f77ea50065 |  | section | Bathroom
checkpoint-status | 75913242-a0de-487c-a6d5-9f609922e63a |  | checkpoint | W.C Supply
checkpoint-status | 7f6d09d3-2098-4bb8-b821-ce1f1f4fb666 |  | checkpoint | Shower waste
checkpoint-status | c90a569f-a6cf-401e-8c82-2942e28a24ef |  | checkpoint | Shower mixer/check depth
checkpoint-status | d7ba9e8c-9b48-42dc-aeff-5c3fe1862601 |  | checkpoint | Toilet waste
checkpoint-status | f3af4790-5c4b-4907-8c41-3a366f5abdde |  | checkpoint | Vanity Waste
checkpoint-status | 826af620-ce39-49ca-aed1-e2efc5a4bae0 |  | checkpoint | Vanity Wingbacks
checkpoint-status | 63f21ae6-96a0-49f4-8338-6e5465fef31b |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-status | 6cb3dd0e-aed2-4fb5-b5a2-60258645e16f |  | checkpoint | Bath mixer where applicable
checkpoint-group | dedbe063-66dc-43a6-836e-55d2316e7d37 |  | section | Laundry
checkpoint-status | 971a0879-951a-4551-a311-6b3bf3c1ec1e |  | checkpoint | Hot and cold water
checkpoint-status | 6622c70d-a0ed-48f5-b303-def6ed876432 |  | checkpoint | Waste pipe
checkpoint-group | 48655e34-1837-4efd-8574-2b2aaef3af7e |  | section | Kitchen
checkpoint-status | 723eb851-6ea6-4a53-8cee-d7e640b33f2a |  | checkpoint | Hot and cold water
checkpoint-status | 38ebf9e7-16bc-4cff-8b58-6b251d266aee |  | checkpoint | Waste pipe
checkpoint-group | 70804cb6-2163-4886-b1c2-d980f7ef828c |  | section | Balcony
checkpoint-status | 6ca9cee6-035c-4ce1-9a9a-c33fb652e83a |  | checkpoint | Balcony drains & pipework installed/correct screws in flange
checkpoint-status | 31abcfd0-6f83-4479-92bf-6959fdc900d2 |  | checkpoint | Correct screws in flange
checkpoint-group | 74554482-c27b-49de-94dd-206c75f4d4a8 |  | section | General
checkpoint-status | c99c66ec-2630-4218-a007-19e208e8f28f |  | checkpoint | Pipe Work Clipped
checkpoint-status | 95030567-7c6b-430d-b1c2-d4933b508a9e |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 65b06543-f6ea-49ca-86c4-24a7cf246c23 |  | checkpoint | Capped Off
checkpoint-status | 23cfe0a1-09f8-4918-bfb4-5db221d42be6 |  | checkpoint | Check for Crossovers
checkpoint-status | 3deb9c9a-f245-4389-9967-5a3e3d35b45c |  | checkpoint | Double check all setont of fixtures
checkpoint-status | 71cbb1ed-11dc-4e35-8f4b-118c7bff8476 |  | checkpoint | PRV & water meters installed
checkpoint-status | 14d0e83e-5072-41d8-88ce-268fc1584fbd |  | checkpoint | Acoustic lagging where required
checkpoint-status | 0915f5e4-dbdb-4a9d-ba17-864c1a149752 |  | checkpoint | Thermal lagging to hotpipes where required
checkpoint-status | c8ef318e-9be1-493a-8322-fa1fb5b47ed0 |  | checkpoint | Floor waste flange fitted
checkpoint-status | d1bfd25c-4039-4046-9bd9-5c40971e0e4c |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | 0941fd2c-c349-4e0e-90d8-f5be552b3613 |  | checkpoint | Installers name & date works completed
text | ac762496-da8a-5427-90fd-edf0c57a9d1c |  | textbox | Installers name
text | 12555da3-990c-5401-bfc5-80952e289a62 |  | textbox | Date:
checkpoint-status | 21cf9bca-c637-4073-974f-e9c1e729bb6c |  | checkpoint | Tested by & date
text | 5b2a3555-39f3-59dd-9e55-00d2379970b2 |  | textbox | Tested by:
text | 50b88345-1452-5ab4-bf05-f518ee3263dd |  | textbox | Date tested:
checkpoint-status | cb11185a-d2e0-44a9-befb-36f92ded65b7 |  | checkpoint | Council inspector sign off and date
checklist-flat |  |  | checklist | Connection to Existing Manhole |  |  |  |  | Yes | Add Connection checklist | 56eb7908-8866-4cee-8c56-6ad457991ba1
checkpoint-status |  |  | checkpoint | Approval given to connect
checkpoint-status |  |  | checkpoint | Heights confirmed - Invert level
checkpoint-status |  |  | checkpoint | General comments & photos during installation
checkpoint-status |  |  | checkpoint | Connection completed
checklist-sectioned | ec26aee4-690c-41c2-be55-a4ede0c78f40 |  | checklist | Water Pump Commissioning |  |  |  |  | Yes | Water Pump Commissioning | 5ed03eca-d101-4d25-b9c0-e561cec686b0
checkpoint-group | c168f18a-84f8-45dd-84c9-b6a139b69019 |  | section | Pump setup
checkpoint-status | 526e602d-6802-4b1c-ab44-d663bd658100 |  | checkpoint | Connections welded correctly
checkpoint-status | b7e38dc7-7374-4d59-958f-045f59b78994 |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | a52fb29a-d84e-41b0-adb3-e22268d877b6 |  | checkpoint | Valves fitted correctly
checkpoint-group | f33e8ac4-969b-4111-ad97-7b6b8698fff1 |  | section | Pumps
checkpoint-status | 9f73d4ff-10f6-49b8-93d5-8fa590fb3054 |  | checkpoint | Pump 1 Startup level
checkpoint-status | 96e4a9f3-b8ca-4fc0-9ca4-cff3ef894bbe |  | checkpoint | Pump 2 Startup level
checkpoint-status | aded6f2f-6191-4f0f-ae8a-30fadfa2a3aa |  | checkpoint | Pump 1 kick out level
checkpoint-status | cdd3a451-a778-4c30-ab78-d57dbf2e1eaa |  | checkpoint | Pump 2 kick out level
checkpoint-group | a84d6be0-ab84-4885-a0be-6c1cc34043a6 |  | section | General
checkpoint-status | aa172f6d-5b66-4562-87d3-b6dcbaaa944d |  | checkpoint | low level alarm test
checkpoint-status | 816dd1f0-3263-4e85-a1a8-6070842c05a6 |  | checkpoint | Chamber clear of debris
checkpoint-status | 84a7c6df-48df-44a9-92e7-872f06a3fe25 |  | checkpoint | Low level pump shut off
checkpoint-status | 4cdffcb2-a78f-43bd-b3fe-e684b50ff787 |  | checkpoint | Impeller clear and free
checkpoint-status | a8661761-0194-4005-83ec-5d03150f0ade |  | checkpoint | Installers name & date works completed
text | 277e36b1-30b3-5c6c-a2d0-1e8bf9b81bc0 |  | textbox | Installers name
text | 813cbb81-fc68-5805-a9c0-eabdb23de6e7 |  | textbox | Date:
checkpoint-status | 62280272-0141-47c3-9d1b-221ec308e117 |  | checkpoint | Tested by & date
text | 8aac10bc-5444-520c-a01d-c1136ed4b625 |  | textbox | Tested by:
text | 78a210db-316c-5f12-839a-7dce329a1ea6 |  | textbox | Date tested:
checkpoint-status | ef9aa90b-3efd-47f7-b141-858634e9089a |  | checkpoint | Council inspector sign off and date
checklist-sectioned |  |  | checklist | Stormwater- |  |  |  |  | Yes | Add Stormwater Pipe Laying Checklist | 60201f18-20aa-45fd-93fe-428538127ea4
checkpoint-group |  |  | section | Pipe Laying
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | a477132b-57e8-4d99-9fb9-261bd3bb8774 |  | textbox | Drawing Ref No.
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Setout completed checked and accurate
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Excavation Accurate - Location & Depth
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 506b4b75-a588-4bab-acdf-5042eac17a26 |  | textbox | Start Invert
text | 4500ec0a-af8d-46b7-b9b6-3d477e0d1913 |  | textbox | Finish Invert
text | 36a4c5ce-c227-4f66-9465-7b8bcd17a68f |  | textbox | Grade of Pre-Line %
text | afb3e5ba-cbab-4d0b-88b7-45161603806c |  | textbox | Product Type
checkpoint-status |  |  | checkpoint | Connections to manholes complete and approved
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | All Downpipes have been checked, installed and approved
text | 92e08a02-a791-4998-be41-995b52e8ccad |  | textbox | How many installed?
boolean | 0df858e7-a459-49c1-bd39-5a401effe272 |  | tickbox | Location confirmed
boolean | 951f7e9c-2d71-44e0-b67e-6b11ecc5df42 |  | tickbox | Heights are correct
boolean | 2f8856c0-3907-4a0e-8ff3-59be164abc71 |  | tickbox | Caps are secure
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | All Cess Pitts have been checked, installed and approved
text | 86ccf72d-8d14-4ae5-bb9d-29b9a0e0a4c0 |  | textbox | How many installed?
boolean | 67ea2f19-8da7-4044-8733-fd4c414cec6c |  | tickbox | Location confirmed
boolean | f63bed26-448c-457b-94ef-77921e05c2fd |  | tickbox | Heights are correct
boolean | 3e05821a-234a-4dfb-ad14-f145adb86e86 |  | tickbox | Caps are secure
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Pipe Laying Completed
boolean | 703a8824-d911-4557-938f-dfaaf57d67ec |  | tickbox | Bedding Sound
boolean | 3ae4a801-fd15-448b-aef2-a1ebd497283f |  | tickbox | Soil Removed
boolean | 79bdfbda-b56a-4a89-9b3f-6279540966e8 |  | tickbox | Trench Compacted
boolean | 8b4419d0-f74e-4c78-96d3-fc5dedbdc517 |  | tickbox | Hard Filled
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Install Tests completed, reviewed & approved
text | a86c6f04-76d7-43a3-8967-0985d34b51c4 |  | textbox | Local Authority Inspection Passed
text | 4a9ee53a-c281-435c-af91-a41a99ad205a |  | textbox | Name of inspector
text | 0f80ae94-c1a2-4c4d-8c29-9fff806a2d21 |  | textbox | Date
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 0cf59902-0ae3-4c91-8036-6dae554458c2 |  | textbox | Sign Off By
text | cec1e1b7-97a8-4976-b4a1-b431e46a890c |  | textbox | Acknowledgement of checklist by
text | 275e36a1-e17c-4a12-bb7b-843fc985f97e |  | textbox | Foreman
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-group |  |  | section | Backfill
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
holdpoint |  |  | signoff | Raise remedial / Request signoff
checklist-flat | 238c0b7d-9386-4592-b055-de2352266a02 |  | checklist | Bathroom Second Fix Plumbing |  |  |  |  | Yes | Bathroom Second Fix Plumbing | 61decd58-2e29-43eb-b0b7-41b0db6f2e82
checkpoint-status | fba8b2da-e986-43b0-9f25-c17f72de3fc4 |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 4ac52b8e-37fe-4889-95b3-4f1f0ddb037f |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | a7f2f87f-e5c1-46e1-aa0c-c92527b85f2b |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | b7b78948-b0a8-4b03-a886-e6342fcc2db0 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 3f0cd363-6ea5-4983-bff0-0973109cb3af |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 6ebe0497-efb0-4207-838b-699b4344fc8f |  | checkpoint | Check Traps For Leaks
checkpoint-status | 5054440e-116e-470d-801f-8c6c15c7c2fd |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | ce84643c-16e9-4358-a10a-6fab1728f262 |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | cb840ea9-98f7-4006-8214-ff3c1b3ddd15 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 7a5ecd2e-97f3-433d-a6ae-58bd39e35383 |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | 2b6ca729-e846-4206-9957-6c4a2cb9c6d7 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | d500b7c7-7d14-4b72-9901-a95415d442f4 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | f9cc82a8-9bc6-4cb4-b2b0-99385d0418bb |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | b771818d-4a91-4b70-b51b-389746bd11ef |  | checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint-status | 88350530-5e6c-4b91-98d9-c062c45f0e44 |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | c803469c-f123-4e36-85b5-749e5091774a |  | checkpoint | Check All Soll Pipe Connections Are Connected To Drain
checkpoint-status | 89f85670-7f82-40be-bf4b-ee6429209c8c |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | 123f7047-e5eb-4075-bc33-c8b86fef45c3 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 69b9247b-6cf7-4a8a-b1ef-50b1672752af |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | fce503e7-fba0-41e2-b5eb-a048851c985f |  | checkpoint | Temperature set point
checkpoint-status | 2fb9d4d0-8900-4751-a7be-6d7dcb7152bd |  | checkpoint | Installers name & date works completed
text | 6cc28f75-c83d-5136-8058-f163dd04367a |  | textbox | Installers name
text | 563dda3b-2642-58b4-9e3a-5a039aa231e4 |  | textbox | Date:
checkpoint-status | d4cf42e3-ccf9-4031-a164-8a4def062cb5 |  | checkpoint | Tested by & date
text | b7a0fdfb-a527-5c80-8fe6-e36750d2305b |  | textbox | Tested by:
text | fd24a8c3-703e-57d3-a794-4535632fde4f |  | textbox | Date tested:
checkpoint-status | dbb11bfd-7dfd-4891-aa59-654606cad1a5 |  | checkpoint | Council inspector sign off and date
checklist-flat | 9c22841e-4df6-43c7-996e-551b4dcb8194 |  | checklist | Kitchen 1st fix |  |  |  |  | Yes | Kitchen 1st fix | 67eab57c-555e-45f6-aa90-cb92691c35f3
checkpoint-status | 7289ec66-9df9-4e6b-8589-6599b1e31b22 |  | checkpoint | Cold water pipework installed
checkpoint-status | 4734c674-6317-4a11-8217-08bcb04372f8 |  | checkpoint | Hot water pipework installed
checkpoint-status | 5427ae96-522d-4c3b-bbd7-ae27f8404414 |  | checkpoint | Thermal lagging complete
checkpoint-status | 2324b190-8c2f-4b59-a93e-9df5d5ede2b0 |  | checkpoint | Wingback and waste correct setout
checkpoint-status | f57a065c-ef7a-4273-80c9-eff5e46b35aa |  | checkpoint | HWC waste installed
checkpoint-status | cdea6f18-e2f2-43d9-889b-3f55b39c0f3a |  | checkpoint | Floor waste installed
checkpoint-status | c7a5bea6-9168-40a2-91a3-0e1257a73316 |  | checkpoint | Waste pipes installed
checkpoint-status | 49b77fac-d12a-40f0-9202-24ce6321300e |  | checkpoint | All pipework clipped and siliconed where it runs through walls
checkpoint-status | b3824535-d68c-4e59-957e-46505a4db916 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | a84b8afe-e719-45aa-a710-c35f52636877 |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | be48cb52-7189-4dfd-be04-9881fdd68680 |  | checkpoint | All pipework pressure tested
checkpoint-status | f41e63c0-6b7e-4052-9cdb-2dae5a01ecfc |  | checkpoint | Check no 1st fix clashes with 2nd fix fixing screws
checkpoint-status | 24b18211-c77c-4bd9-a1cc-6d84c95664fb |  | checkpoint | Check all nogs are installed
checkpoint-status | 14527668-6195-4bec-b1d7-27572e084a85 |  | checkpoint | Installers name & date works completed
text | 4b6b65b8-24ea-51c2-aad0-52a6ef04f39f |  | textbox | Installers name
text | 703d7a62-ef7f-5460-8d2a-d40ae34f3186 |  | textbox | Date:
checkpoint-status | 74e069e0-7fb1-47e6-880f-a25a5d8c88de |  | checkpoint | Tested by & date
text | eb435d6b-7f78-5b23-bba7-1986af6a2b8c |  | textbox | Tested by:
text | 870e4051-8ecf-5c5c-a170-8cba7f8a0ac2 |  | textbox | Date tested:
checkpoint-status | 3f12db13-f98b-4f6d-88bc-23a3e6bd542a |  | checkpoint | Council inspector sign off and date
checklist-flat | eae4ddb6-f511-495c-bbe1-d1be08fd18fe |  | checklist | Second Fix Plumbing - Including HWC |  |  |  |  | Yes | Second Fix Plumbing - Including HWC | 81267ba7-3bad-42ce-a3b4-131ac334d318
checkpoint-status | dba20df7-0074-4fb7-84b0-276eb8c29986 |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | c6ca89cb-fc24-4c7d-895f-55de7defd652 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | c5dd80b9-aa24-4577-ba7c-e2d98e960a6f |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | a1e3a181-d041-49a2-8ff1-e511fa1ee99d |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 6529234f-deb0-412a-9079-de74a1be1c59 |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | c90de6e2-8281-4d49-9827-5eb9248e8eaa |  | checkpoint | Check Traps For Leaks
checkpoint-status | c2f10cd1-3733-4218-bdc6-03c3190f7d8c |  | checkpoint | Check Cisterns For Leaks
checkpoint-status | f90a9df4-c9f9-4ba5-92e9-d0949a18f329 |  | checkpoint | Check cisterns flushing correctly
checkpoint-status | 2cd97a4c-08ee-453f-8196-03b94904b75f |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | a0ce0ceb-10c5-4cca-bdaf-35e5dc72b176 |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | 42ecfc9a-3203-4844-9743-1af9faba2d1b |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | c29004c3-99bc-4a54-bd87-85e3fd99c737 |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | 9c1050c7-5fb8-47b4-918d-01e71eb7b39f |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | 8737c725-c437-48c4-ad7d-df1ee2baddc6 |  | checkpoint | Check FWG & Shower wastes are clean & clear
checkpoint-status | 9f757e83-49bf-4e2a-8df8-2c934d9b2bbc |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 410329e5-1e3f-4743-ab37-26cb9c859098 |  | checkpoint | Check All Soll Pipe Connections Are Connected To Drain
checkpoint-status | f23ccfd2-4877-4faa-8169-4de75e490ceb |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | b924ea66-95ca-4d75-8892-7021de9c4b74 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | bd971630-3b27-4d09-a038-e8cbf8407fb7 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 3d87801c-aaa7-4a2e-b001-7226d1f6eeb4 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 3888144d-33e3-4c19-86ba-cd331c66996d |  | checkpoint | Temperature set point
checkpoint-status | d27fe0d4-6c78-466b-8bed-861ac1213e2f |  | checkpoint | Downpipe & overflow cover installed on balcony
checkpoint-status | 191a7776-70c1-4ad5-8655-65bb2d6a7a6a |  | checkpoint | Correct screws on balcony drain
checkpoint-status | eec5dc80-74d2-4fc0-b716-9f6d53dcf35a |  | checkpoint | Installers name & date works completed
text | e02c6ef2-2b6b-5765-89b2-a16631a65aea |  | textbox | Installers name
text | 549a1407-d742-53d1-ba0a-68a3939e4f18 |  | textbox | Date:
checkpoint-status | a53a3179-8aeb-4b33-be6a-d8c66bad86a8 |  | checkpoint | Tested by & date
text | bd53aeed-2f81-5edf-a7fc-b67b8cf0d642 |  | textbox | Tested by:
text | 1b8ea146-56f5-55ff-a455-bee2fc2fe637 |  | textbox | Date tested:
checkpoint-status | c3703b9d-ae80-4189-880f-640ab6b86093 |  | checkpoint | Council inspector sign off and date
checklist-flat | ced45b6f-abf9-4e0c-a8f5-2c0a22c2ac12 |  | checklist | Kitchen 2nd fix |  |  |  |  | Yes | Kitchen 2nd fix | 8256048d-49b3-4bbe-845b-867eb787170b
checkpoint-status | 6409c702-866d-4c92-8237-99f932fbddfb |  | checkpoint | Flush all water pipes before connecting fittings
checkpoint-status | 27b1a89e-5f12-424a-8921-b6d36b0d2277 |  | checkpoint | Correct Taps And Fittings Provided
checkpoint-status | 410b990c-4f19-465b-9150-004fc05740a3 |  | checkpoint | Silicone Applied To Fixtures Where Required
checkpoint-status | c3d333aa-ae08-4b87-a759-85b56a362010 |  | checkpoint | Check All Tap Connectors For Leaks
checkpoint-status | 3dfa56d6-59ef-4f81-8a0a-7b08aafc0d34 |  | checkpoint | Check Screwed Nippling In Walls For Leaks
checkpoint-status | 506a5e0d-d686-4987-890e-d004f6c8970c |  | checkpoint | Check Traps For Leaks
checkpoint-status | 9611adcb-f296-4d51-8a33-28856b4ddfc3 |  | checkpoint | Check All Fixtures Function Correctly
checkpoint-status | 55bb8d27-9a78-4cec-af1d-950d146e7c63 |  | checkpoint | Test TPR on HWC and safetray drains away & airgap
checkpoint-status | 5b3b585a-4d3e-4e3f-84fe-f8a24e37facd |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | aadac729-30f9-4d8a-82b4-d0dd272ec76c |  | checkpoint | Check Restraints & Timber chooks are installed on HWC
checkpoint-status | 9e4795e1-eb90-4947-a05b-4d8868e71501 |  | checkpoint | Element Position on HWC Is In A Serviceable Position
checkpoint-status | 5efdfc5a-3793-4f79-ba36-49db81e0efe0 |  | checkpoint | Check FWG are clean & clear
checkpoint-status | 5f6fa43c-f260-496b-b077-70683b899c8f |  | checkpoint | Check Flanges Have Been Installed Where Required
checkpoint-status | 62cbe0ad-095f-4327-8699-9ebf888555a4 |  | checkpoint | Check All Soll Pipe Connections Are Connected To Drain
checkpoint-status | 661668ff-4d57-415e-9d05-9b5b6ee73d32 |  | checkpoint | Kitchen overflow working and no leaks
checkpoint-status | 038cd4ae-6fe0-42a8-b4e6-01fbeb884880 |  | checkpoint | Picked Up All Left Over Material & Returned to Office
checkpoint-status | b4c4a2ae-2ed2-4eaa-bdb4-e164b4d0cc07 |  | checkpoint | All your rubbish removed or in bins provided
checkpoint-status | 085c15a9-86e3-4286-8b55-0a46e269feb5 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | c4ec1e8d-dadd-4a52-a1e5-5d1f9797493a |  | checkpoint | Temperature set point
checkpoint-status | 7b9569d2-48da-49ba-b3a5-91a4d28f4f35 |  | checkpoint | Installers name & date works completed
text | 9c8e3ff4-d217-5f27-8a06-0417288e811f |  | textbox | Installers name
text | 2dea4fd8-9ad8-5e62-92f9-3b583c1f5266 |  | textbox | Date:
checkpoint-status | 22b50ae8-4623-43a2-b85f-82b5d7194bc0 |  | checkpoint | Tested by & date
text | 91ae3c75-8dad-5ad8-b9c1-332ee3c5b690 |  | textbox | Tested by:
text | 83192683-d962-51cd-a71c-b7e122e1a362 |  | textbox | Date tested:
checkpoint-status | 1d840f3f-dc66-459d-8af5-03cf931117c0 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 5f8a462b-cbe4-4fb0-b59b-ebe241a25313 |  | checklist | Core Water & Gas |  |  |  |  | Yes | Core Water & Gas | 8849f9d1-fb93-4f7f-94ca-8dd3ce33a89d
checkpoint-group | a1f7cc95-5d37-478d-b43b-460aa9c6e8a8 |  | section | Gas Mains
checkpoint-status | fc81b2dc-bc2f-4c58-8c4e-a0e09cb7e936 |  | checkpoint | Connection brazed correctly
checkpoint-status | 886d90ac-b15e-425b-be2f-c91e5cebfb7f |  | checkpoint | horizontal/vertical
checkpoint-status | 58f40ff1-910b-4233-9fe2-a3f2800dd7e9 |  | checkpoint | values fitted correctly
checkpoint-status | a3b9fa4d-04e1-4d93-9ea7-0c27cd652acf |  | checkpoint | Drop test complete
checkpoint-group | c2ffae2a-d511-4f82-8399-1ed0bf0dd679 |  | section | Cold water main
checkpoint-status | 2d3bab15-8dda-4119-b742-805dc37a1f1a |  | checkpoint | Connections brazed correctly
checkpoint-status | fa339a3b-2de6-43b2-b055-e034130d8567 |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | fc5692b2-3e68-43a9-86d0-89a5d8ca8579 |  | checkpoint | Valves fitted correctly
checkpoint-group | ffda8520-8fda-46aa-b073-ea85ff2de5b7 |  | section | Hot water main
checkpoint-status | afd856ee-1ccb-49a3-b661-cb398cae8f62 |  | checkpoint | Connections welded correctly
checkpoint-status | 7c28f245-5736-4189-8965-c7b0e42f27c1 |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | d61916de-1858-4dc4-acf4-baeb0f0a0d64 |  | checkpoint | Expansion allowed for
checkpoint-status | 17682f73-0146-4764-aae9-15a158a442a4 |  | checkpoint | Lagging installed and neat
checkpoint-status | b0d0d937-103f-4596-b169-a3d2cab32e2c |  | checkpoint | Valves fitted correctly
checkpoint-group | 36a7f197-fd61-45c3-9d19-f2e8cdd932e1 |  | section | General
checkpoint-status | 383be813-8557-4db1-b6ac-d2514b25a527 |  | checkpoint | Open ends of riser capped for testing
checkpoint-status | b54c7ffd-0830-4165-959f-983bff8ade03 |  | checkpoint | Checked for cross over's
checkpoint-status | 58eaf49a-f661-481c-bf2b-d509a42ee6cd |  | checkpoint | Tidy work areas
checkpoint-status | 926dc600-a52a-4307-88fc-86b309c67b9e |  | checkpoint | Pressure test to 1500kpa for 30mins
checkpoint-status | a97daa3b-c758-4a0a-b536-b3ede4f904c6 |  | checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint-status | 9287507a-55dd-4139-99b6-f0672f0095d5 |  | checkpoint | Seismic bracing for pipework longitude and latitude
checkpoint-status | b68b575d-a87f-439b-9e0a-e00ef685df14 |  | checkpoint | Lateral labelling of pipework backflow devices fitted
checkpoint-status | e543eb5f-a198-453b-a346-d1ee709a871f |  | checkpoint | Pre Line Inspection Passed
checkpoint-status | 0f5077c9-bba7-48ee-b848-9d3deaeab4aa |  | checkpoint | Installers name & date works completed
text | e2e4a213-af2f-5ba8-96d8-fc0e3d99082b |  | textbox | Installers name
text | 2e41a5e8-5a00-5529-9271-303c0bf4ecb6 |  | textbox | Date:
checkpoint-status | 4be3c34d-e5f3-4e7f-a5f8-85085309d952 |  | checkpoint | Tested by & date
text | ca7eb1d6-75cf-54da-8dcc-a15fccd390a3 |  | textbox | Tested by:
text | 0ae15289-3232-5dbc-b9c0-1ed024078d8b |  | textbox | Date tested:
checkpoint-status | dcb704ad-8c74-4e20-a6af-0f09c346bfb8 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | ebcc0a55-e112-4e99-9b6a-ccebfd2fb736 |  | checklist | In ground Water & Gas mains |  |  |  |  | Yes | In ground Water & Gas mains | 8f9ce17c-5c98-43bc-b012-2294dfadfec0
checkpoint-group | 7d097ce9-2fe1-47d4-b6e1-a01e4f318166 |  | section | Water mains
checkpoint-status | 4846d7a2-2a48-4be4-a554-e99bd57a0f97 |  | checkpoint | All fittings scrapped correctly
checkpoint-status | b5e31cbe-1a78-4e9d-b9b7-545b4cc1459d |  | checkpoint | Iso used on fittings
checkpoint-status | b3efebc9-ba15-4138-bba7-bef06b0abbcc |  | checkpoint | Valves fitted correctly
checkpoint-status | d6729ef5-d921-4a47-b300-4c6bc7b19e9e |  | checkpoint | Fittings welded & weld indicator has popped out
checkpoint-status | e0d60dfe-fad8-4122-8080-b592dfdf4e3f |  | checkpoint | Trace wire and ID tape installed
checkpoint-group | 944628bf-5cad-427f-9f9b-e7868069acd3 |  | section | Gas main
checkpoint-status | 13e268f9-ea93-4ca8-8faf-b5afd4182e62 |  | checkpoint | All fittings scrapped correctly
checkpoint-status | 4bc8b977-163a-4f5e-a911-3c5885ca0a4f |  | checkpoint | Iso used on fittings
checkpoint-status | 4b56a569-23d6-48a3-9ff6-d428b9729c58 |  | checkpoint | Valves fitted correctly
checkpoint-status | cc542b3f-a57b-4810-90fa-a73815cad2f8 |  | checkpoint | Fittings welded & weld indicator has popped out
checkpoint-status | 6ea2cba7-e7c9-48eb-bea2-fb1ea8d54b62 |  | checkpoint | Trace wire and ID tape installed
checkpoint-group | 44db02f7-cf53-456c-bd5c-da1b0bed5eca |  | section | General
checkpoint-status | ae8b244e-aa8a-41ef-a540-bf6a4842cd53 |  | checkpoint | All open ends capped
checkpoint-status | 0627f3ac-15ef-4431-a727-636283d6c366 |  | checkpoint | Pipework bedded correctly
checkpoint-status | 1ef21cd4-8487-4054-beb2-b9d52db37c3a |  | checkpoint | Tidy work areas
checkpoint-status | 9e4a1073-e06c-4456-aade-67728fcf1d36 |  | checkpoint | Pressure test pipework
checkpoint-status | 4ca5e949-7eb6-4a99-94ff-a0081136907b |  | checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint-status | b01b3c5a-f776-4677-9c4b-135bdfb8fccc |  | checkpoint | Backfill around pipework with fines
checkpoint-status | 949f42d4-a3d7-4017-931c-2ff7e2960b00 |  | checkpoint | as-built completed and photo
checkpoint-status | 490604af-3634-4956-8605-e63e001f3c33 |  | checkpoint | Installers name & date works completed
text | bb05fb08-af91-5a58-a16f-08fb5fb63519 |  | textbox | Installers name
text | 38b43b80-e360-52e1-a195-1ede2726c260 |  | textbox | Date:
checkpoint-status | c1b892da-b8fe-44ea-b723-0f6b70effda6 |  | checkpoint | Tested by & date
text | 18655d9c-5cab-50a6-86e5-e1a82d5cdea1 |  | textbox | Tested by:
text | d50415df-e12c-5157-a706-cf0c582d5846 |  | textbox | Date tested:
checkpoint-status | 2b696654-23eb-40f6-807e-5c6880a6bbbc |  | checkpoint | Council inspector sign off and date
checklist-sectioned |  |  | checklist | Sewer- Pipeline Installation Checklist |  |  |  |  | Yes | Add Sewer Pipe Laying Checklist | a81cb2c6-72ea-4894-998a-07669ded27c8
checkpoint-group |  |  | section | Pipe Laying
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | d517dc95-c108-4fbb-a9d2-650233272911 |  | textbox | Drawing Ref No.
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Setout completed checked and accurate
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Excavation Accurate - Location & Depth
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | a69b6674-f30b-45bf-bdfb-78386060c9b5 |  | textbox | Start Invert
text | 7a909b46-b877-4bca-8dad-93651ad00436 |  | textbox | Finish Invert
text | 94d1cbc9-fe00-4cb1-aa2c-1b6552a5e914 |  | textbox | Grade of Pre-Line %
text | 1d0809d2-0f49-4c95-b589-2b40c021c674 |  | textbox | Product Type
checkpoint-status |  |  | checkpoint | Install Tests completed, reviewed & approved
text | 1b25573f-a944-45b8-ad85-ea308c5ff04e |  | textbox | Local Authority Inspection Passed
text | dc1ddf60-0c43-4e82-b60b-82c931e3ae1f |  | textbox | Name of inspector
text | 787ecc0a-32e2-403a-a2c5-f5bf04a1ddd1 |  | textbox | Date
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Pipe Laying Completed
boolean | bc1a645f-f6c8-45f9-a557-f9089fe6ca97 |  | tickbox | Bedding Sound
boolean | 76133791-d13e-43b7-b2d8-f39355cb162d |  | tickbox | Soil Removed
boolean | 3295bab5-7609-48ef-a5d5-644a3a04d845 |  | tickbox | Trench Compacted
boolean | 1822e4d9-f894-4c87-be28-8b4c790129d5 |  | tickbox | Hard Filled
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Connections to manholes complete and approved
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Air Test Complete
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Area of Work Inspection Completed & Sign Off
text | 0f353b68-3847-4459-b3d7-751bb1246f30 |  | textbox | Sign Off By
text | 50d481a4-cbdd-4d80-a009-9fc3eb4a4aee |  | textbox | Acknowledgement of checklist by
text | 2af19e98-900a-4f52-b6ad-282378ccd0df |  | textbox | Foreman
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-group |  |  | section | Backfill
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
holdpoint |  |  | signoff | Raise remedial / Request signoff
checklist-sectioned | c49642eb-002e-4a1a-887c-76bcd9bed245 |  | checklist | SS or SW pump QA |  |  |  |  | Yes | SS or SW pump QA | af839da9-7c5c-4cd9-9841-205b7fbc8b82
checkpoint-group | 605afd5b-848c-45d1-8cdb-321a7452040b |  | section | Pumpset mainfold
checkpoint-status | e9e02e92-5324-4b59-b879-fc8c564514cc |  | checkpoint | Connections welded correctly
checkpoint-status | 9aff4666-fbfe-4187-b2ea-769ecb2aa1b6 |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 44382a7a-01b2-4f9b-a76f-c2ea25e7a45b |  | checkpoint | Valves fitted correctly
checkpoint-status | bf450cf1-b718-47eb-8f58-6b70510d81e3 |  | checkpoint | Line strainer fitted between pump & tank
checkpoint-group | a91d4544-7422-42b6-83d0-e51aafef66bb |  | section | Pumps
checkpoint-status | fb20ec46-4806-42f5-9b18-48dce9f6b367 |  | checkpoint | Pump 1 Startup KPA
checkpoint-status | a33fc124-ca51-4865-8c00-83f85f82a2a9 |  | checkpoint | Pump 1 kick out pressure KPA
checkpoint-status | 51f99e68-a355-43e8-a8e2-51cf1f272ca1 |  | checkpoint | Pump 2 Startup KPA
checkpoint-status | b2adfc8d-47a1-4217-a368-aa151d774ada |  | checkpoint | Pump 2 kick out pressure KPA
checkpoint-status | 9e1eb5f4-10f7-48ce-9bb5-095ba7e0a5b2 |  | checkpoint | Pressure vessel pressure
checkpoint-group | 6f1049e3-7f82-459c-868c-d1fe2ba4d9d9 |  | section | General
checkpoint-status | 794d4aa1-0885-4b13-9d4c-fa7bdc2af01a |  | checkpoint | Mains water change over
checkpoint-status | cbea165b-d0fa-49a6-9137-ec4d5662b356 |  | checkpoint | Flow test pump
checkpoint-status | 2cbfaacf-915f-4468-8c59-c736e5736848 |  | checkpoint | Pressure tests pipework
checkpoint-status | be044dc9-9ea7-4366-8a24-7e366736473f |  | checkpoint | Visual check (for leaks from valves, tees, saddles, etc)
checkpoint-status | a2eea961-f208-4d65-87bd-1afcdaf9ad57 |  | checkpoint | Non return valves fitted
checkpoint-status | c6360f14-e83e-4fe9-b72c-33052f21656b |  | checkpoint | Installers name & date works completed
text | f661c5b6-1575-565d-8533-48835af11bd9 |  | textbox | Installers name
text | 8684b730-a10c-5d7a-bc5c-54cbbf9d81cf |  | textbox | Date:
checkpoint-status | 37ac30ee-f932-44fe-bfab-7b9e8c757e49 |  | checkpoint | Tested by & date
text | 4c119dfd-321e-566c-8dfc-7c66577c152a |  | textbox | Tested by:
text | d49219f5-3638-5dbc-9eb3-a38a44474d91 |  | textbox | Date tested:
checkpoint-status | 81cc07b0-5263-4525-8dad-84910e50e0cb |  | checkpoint | Council inspector sign off and date
checklist-flat | 6798b1c1-2d1a-4e20-a0d4-191dc210d13a |  | checklist | Hotwater Plant, Pumps & Tempering Valves |  |  |  |  | Yes | Hotwater Plant, Pumps & Tempering Valves | b20f255c-284d-40af-b702-cacbe1c0e3c4
checkpoint-status | 07207788-a2f0-4b10-9834-1cccf1660d64 |  | checkpoint | Flush all lines and strainer including rinnais
checkpoint-status | 0813770e-97a4-4dcf-9acc-110bf29e7053 |  | checkpoint | All safety valves installed
checkpoint-status | 452239b8-d502-4f43-88b5-1ee2cd885902 |  | checkpoint | Seismic restraint fitted
checkpoint-status | b112ef45-368c-4ca8-9629-b2da01378fb2 |  | checkpoint | Check condensate drains from Rennais
checkpoint-status | bc8dc9fc-908e-4a75-aeda-5d9ba133e238 |  | checkpoint | Check All Connectors For Leaks
checkpoint-status | 92b16a36-6620-475e-be8d-8b569fe3f4bc |  | checkpoint | Check all valves and connections for leaks
checkpoint-status | 0e5a7f4a-c323-4eec-9ab0-b9dfe97e051b |  | checkpoint | Operate cold water expansion valves / check operation
checkpoint-status | 76d84f95-fdb0-4ebd-a86e-3d1fb1e20dce |  | checkpoint | Set limiting valve
checkpoint-status | 81adf210-fa6b-4f61-bc2d-8249a78beba2 |  | checkpoint | Test TPR valve
checkpoint-status | c27989a4-a454-4510-b82a-648578f760a4 |  | checkpoint | Check for crossovers
checkpoint-status | 32260abd-9ee8-4ef7-904f-93a6095e48d3 |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | f8fd2b75-76da-4912-b165-2085e03b4175 |  | checkpoint | Lagging completed
checkpoint-status | ae1db242-b71c-4a2c-9108-e9f0e6527dc3 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 7f116609-f786-48a0-9d1e-9b0566166561 |  | checkpoint | Set tempering valve temperature
checkpoint-status | d3280ea2-8b65-4f66-8dc5-f93cb795befc |  | checkpoint | Set Rinnai gas water heaters
checkpoint-status | 76482e5e-f191-4772-ab34-0eb3b4bc7433 |  | checkpoint | Set thermostat temperature
checkpoint-status | 44266c44-7ed4-445f-9f58-8bfbf4818f19 |  | checkpoint | Set Bleed air from primary pumps
checkpoint-status | 23bafd9b-0a31-4f65-885b-bb79b07ad1b7 |  | checkpoint | Bleed air from circulating pump
checkpoint-status | 281082fc-16ee-4484-9f82-4da5878f666d |  | checkpoint | Set all return thermostatic balancing valves
checkpoint-status | f1c113cd-a325-425a-93bf-bc1a7a72e100 |  | checkpoint | Test gas for soundness & check working pressure
checkpoint-status | a125bd03-7591-4862-8559-c840f835ea99 |  | checkpoint | Water temperature in Hot water cylinders
checkpoint-status | 7642bf3b-ebae-4716-a5b7-2a0fc92bb92e |  | checkpoint | Installers name & date works completed
text | e76d1990-f24f-55db-a33d-f14779cf7a21 |  | textbox | Installers name
text | 2faf3790-82db-5606-87ec-f0ff25eead89 |  | textbox | Date:
checkpoint-status | f4a116a3-c62d-44f1-aeaa-8e1b31c9ee67 |  | checkpoint | Tested by & date
text | 478da1b1-dfc5-51eb-ab78-3c8d9ec40a2a |  | textbox | Tested by:
text | 440d9784-6cdd-5d25-bbc5-8404249d15ed |  | textbox | Date tested:
checkpoint-status | 63c96674-81c0-4d09-80ef-9fa72c9374ee |  | checkpoint | Council inspector sign off and date
checklist-flat | 2493777f-5db5-49f0-a434-8eed288021e9 |  | checklist | Cleaners cupboard |  |  |  |  | Yes | Cleaners cupboard | b6fda357-0641-4221-9af8-3a3d4981197d
checkpoint-status | bda9f52c-196a-4a5a-9700-61e21052b85f |  | checkpoint | Hot and cold water
checkpoint-status | 4faefcb4-2497-4d30-bac0-7cee991c0395 |  | checkpoint | Waste pipe
checkpoint-status | 9e45d27c-09fe-4044-8b2d-d5a788b110d1 |  | checkpoint | Pipe Work Clipped
checkpoint-status | c1746da8-539f-4e9a-883d-1dbaf6e61985 |  | checkpoint | HWC water feeds
checkpoint-status | f507fba1-1199-4933-8f2e-e507aad02c56 |  | checkpoint | HWC waste
checkpoint-status | 8ef3b813-6109-4642-ac2f-f52d0225c368 |  | checkpoint | HWC nogs for strapping
checkpoint-status | 65669a67-7d05-4f34-862d-2af235dcf08f |  | checkpoint | Pipe Work Siliconed
checkpoint-status | be6824c2-3bce-44cd-94fd-43087d6332ac |  | checkpoint | Capped Off
checkpoint-status | 948d195c-6e5a-4b18-afa6-eed1bcef8289 |  | checkpoint | Check for Crossovers
checkpoint-status | bc1f6c2e-1d31-4a9f-ae30-77ba968d900b |  | checkpoint | Double check all set out of fixtures
checkpoint-status | f37d88c3-90c4-4e30-9331-a8dfa93ec5cd |  | checkpoint | Acoustic lagging where required
checkpoint-status | 0d325f17-e987-4bb3-b1b5-ef98291b968b |  | checkpoint | Thermal lagging to hot pipes where required
checkpoint-status | 7dd198bb-7c9f-4017-b69f-8ddbae97eb80 |  | checkpoint | Floor waste flange fitted
checkpoint-status | e247b405-1a47-4d90-8a1d-444ff82a703a |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | c390fb69-8e76-4416-bb01-d40f736505bf |  | checkpoint | Installers name & date works completed
text | 838d7bf1-12bc-5260-bbd0-c511951ac6e7 |  | textbox | Installers name
text | 8e8643de-715f-54c5-8011-df33fc40646b |  | textbox | Date:
checkpoint-status | 862654f4-1bcc-4c98-bec7-753730d66f0f |  | checkpoint | Tested by & date
text | 99de0e35-645c-53d7-9378-01515095b4d6 |  | textbox | Tested by:
text | 593bc4fe-953b-5ec6-a7b3-0d8a6be60256 |  | textbox | Date tested:
checkpoint-status | d3226551-bb79-4cb2-ab0d-8cd165ab80a9 |  | checkpoint | Council inspector sign off and date
checklist-sectioned |  |  | checklist | Manhole: |  |  |  |  | Yes | Add New Manhole Checklist | c0cff711-468c-4f2b-b48e-4fc2b4cc03a9
checkpoint-group |  |  | section | Manhole Install
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | 68395be9-4fdc-4dd7-98a8-699ce4470422 |  | textbox | Drawing Ref No.
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Setout Completed checked and accurate
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Excavation Accurate - Location & Depth
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Bedding depth and material correct & compacted
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Correct manhole installed to specified height and sitting level
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Manhole Risers Installed (if applicable)
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Joints & connections correctly sealed as specified
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Manhole benching completed and acceptable
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Concrete Lid Installed and sitting appropriately
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Cast Iron Lid Installed and sitting flush
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Signoff on Completed Work (Council etc)
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-group |  |  | section | Backfill
checkpoint-status |  |  | checkpoint | Backfill methodology and material confirmed
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any formwork/ debris removed from area
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closedout
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | General photos and observations during backfill
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
holdpoint |  |  | signoff | Raise remedial / Request signoff
checklist-flat | 495f5214-3381-4082-a6a8-088eaeaf359c |  | checklist | First Fix - No HWC |  |  |  |  | Yes | First Fix - No HWC | c78ca32b-b78b-4cac-b2d4-33c5d63b4de3
checkpoint-status | f92bed84-06d2-41b4-a9f7-e92feadf29b7 |  | checkpoint | Underslab complete
checkpoint-status | 6094acd6-4b0f-415e-82d9-b81a48fd8869 |  | checkpoint | Toilet, shower and basin waste installed and in correct position
checkpoint-status | 9cd8dbb4-a838-4fd0-a085-892c034ee295 |  | checkpoint | A/C drain connected
checkpoint-status | 6c153daf-322a-48b1-83d4-5c967bfe53f3 |  | checkpoint | Shower flange installed
checkpoint-status | fdf95159-adca-4b01-a566-f5f19a9ce80d |  | checkpoint | Water to toilet
checkpoint-status | 47c5b132-bb5c-4fa3-a0cc-e9b4be578620 |  | checkpoint | Water run to basin and basin taps installed
checkpoint-status | b033dfe1-b4c5-4a3e-b3d3-51100328009b |  | checkpoint | Water run to shower and shower mixer installed
checkpoint-status | a23a6b32-583e-41a7-a94d-3f3301b5e620 |  | checkpoint | water supply run to shower rose
checkpoint-status | 4391bfa6-509c-4da3-8572-1d379ea8147b |  | checkpoint | All pipework clipped and siliconed where it runs through walls
checkpoint-status | 16b87f92-88c5-4bad-bcb6-0a01c82a2a42 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 56607e39-aced-4f3d-bd95-a06d750e6417 |  | checkpoint | Thermal lagging to hot pipes where required
checkpoint-status | b84c2e83-ee30-47a3-8cf3-1e8e2ca55462 |  | checkpoint | Tempering valve installed
checkpoint-status | 50d9190e-7985-43e3-a9bc-137fae2efc26 |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | 2788c846-f79e-495e-b362-71f31aac98fc |  | checkpoint | Check no 1st fix clashes with 2nd fix fixing screws
checkpoint-status | 2df42095-350a-4aef-9227-ff0bd0a792af |  | checkpoint | Check all nogs are installed
checkpoint-status | aba9f20e-db3d-4823-846e-ece522c61c70 |  | checkpoint | Double check all setouts and heights.
checkpoint-status | c19867e5-4ce5-47af-85ba-91f9252dbdc7 |  | checkpoint | Installers name & date works completed
text | 918049a7-330d-521b-830a-259bfb600b43 |  | textbox | Installers name
text | 8a589b6f-0fbf-53b2-9621-9c6ffc9c8d50 |  | textbox | Date:
checkpoint-status | 61482e42-68d3-4651-afa5-8608b59ca0b3 |  | checkpoint | Tested by & date
text | 074ab39d-0865-564f-a79f-85734855e95f |  | textbox | Tested by:
text | 7003c20f-64ad-5602-982c-03c54a1806b2 |  | textbox | Date tested:
checkpoint-status | 770e26bb-4ad4-48b0-94df-cf8ed9d0c707 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 020732d1-2de1-4f9a-adbc-2a47d0621fca |  | checklist | First Fix Plumbing - Including HWC |  |  |  |  | Yes | First Fix Plumbing - Including HWC | cfd536db-777f-48f5-836a-3e201d7304f8
checkpoint-group | 9811d8a5-8d9a-4df0-8f0c-36cb666e43c0 |  | section | Bathroom
checkpoint-status | 03fec11c-4428-4415-bd55-5add23cfc196 |  | checkpoint | W.C Supply
checkpoint-status | 7ca6a84e-572a-41ae-9738-c38dd1a4b4c8 |  | checkpoint | Shower waste
checkpoint-status | 9634224a-9568-4686-bc13-52be885f927a |  | checkpoint | Shower mixer/check depth
checkpoint-status | aab5df74-7ef1-44e7-9b7e-8565cf3dd9c1 |  | checkpoint | Toilet waste
checkpoint-status | 34ab0964-b4b3-4e88-919f-96a7f2636cf6 |  | checkpoint | Vanity Waste
checkpoint-status | d6a98066-63af-4aa6-913a-7f1aa8d81c5a |  | checkpoint | Vanity Wingbacks
checkpoint-status | 8d2c272e-0f7a-4ff4-9e45-0dd4ac000998 |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-status | 4dd445c6-3035-466f-bed4-87fb12147401 |  | checkpoint | Bath mixer where applicable
checkpoint-group | 09cf7bef-728d-4804-9049-11be9980311b |  | section | Laundry
checkpoint-status | 7933d776-4abb-412e-a085-4e37346d6b08 |  | checkpoint | Hot and cold water
checkpoint-status | 3bb4ef4a-1b73-4d10-ab6d-1cb0aa0b3d70 |  | checkpoint | Waste pipe
checkpoint-group | 8eadc8fb-a808-4bf0-b770-2d6d067d771f |  | section | Kitchen
checkpoint-status | be87cc8a-b650-4641-b41c-5f200de0023a |  | checkpoint | Hot and cold water
checkpoint-status | e50e1d15-a450-493e-80b2-9b8fe737f766 |  | checkpoint | Waste pipe
checkpoint-group | dd6e9a71-b944-4f5a-a377-e2046cc7badc |  | section | Balcony
checkpoint-status | f056d5bf-28b7-4156-8fa4-b25ea28c6585 |  | checkpoint | Balcony drains & pipework installed/correct screws in flange
checkpoint-status | c30ac893-da73-473a-ab44-4900d07894a1 |  | checkpoint | Correct screws in flange
checkpoint-group | 7b803c12-796c-4a83-b9a0-ebf61262c23f |  | section | General
checkpoint-status | e0e0b3cc-8e18-4757-8121-7d6794f4af0a |  | checkpoint | Pipe Work Clipped
checkpoint-status | 6d58d341-91c8-4b2e-b66f-904bf9f7dbff |  | checkpoint | HWC water feeds
checkpoint-status | 1c7738c7-ab4f-470d-9fb8-89974679c179 |  | checkpoint | HWC waste
checkpoint-status | e4aaee71-3f24-43a7-8491-abbe7880e739 |  | checkpoint | HWC nogs for strapping
checkpoint-status | eb6e5f54-944c-413f-aaac-5d87df5ad546 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 51505884-24a3-4272-803e-2ae21c9d292e |  | checkpoint | Capped Off
checkpoint-status | 99f67950-eaee-4160-8252-7769529f745c |  | checkpoint | Check for Crossovers
checkpoint-status | 5dd92da6-49c8-49f6-9c0e-b17bfa236a36 |  | checkpoint | Double check all sefont of fixtures
checkpoint-status | ebeaacf5-64b8-4170-9897-913ef1339312 |  | checkpoint | Acoustic lagging where required
checkpoint-status | 03ef9f27-11cd-41c4-9249-a68ac68e98b3 |  | checkpoint | Thermal lagging to hotpipes where required
checkpoint-status | d2aedecd-b2bc-44c2-8c2b-b8f100b6ff0d |  | checkpoint | Floor waste flange fitted
checkpoint-status | d9430a75-9222-4204-a812-50094505f164 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | a5c7110e-69ac-4395-b163-c4444e1eff1f |  | checkpoint | Installers name & date works completed
text | 4aa4b840-297d-5386-8fbb-69a8e9b172a7 |  | textbox | Installers name
text | 918ca811-d0b8-524b-830f-98f024a4e093 |  | textbox | Date:
checkpoint-status | 95befecc-f4a5-402d-867c-c6482f6c8949 |  | checkpoint | Tested by & date
text | b0fc632e-37a8-52d3-9422-a1b82c03ff10 |  | textbox | Tested by:
text | 7a18a381-0bbe-53c4-902b-763be618f6f6 |  | textbox | Date tested:
checkpoint-status | a1a9f5c1-abe7-4e6b-bae2-0fc446f861d2 |  | checkpoint | Council inspector sign off and date
checklist-flat | d885afa8-89b2-4990-84a8-066a8e50e810 |  | checklist | Factory 1st Fix |  |  |  |  | Yes | Factory 1st Fix | da34e884-184c-4b0c-9887-3bc634a043de
checkpoint-status | 39dd5464-b700-455b-87c1-764e5c7d9750 |  | checkpoint | W.C Supply
checkpoint-status | 87cb9c21-7700-45e8-ac29-a5041af33278 |  | checkpoint | Shower waste
checkpoint-status | 7fae522e-369c-4eaa-b408-bbab16b64206 |  | checkpoint | Shower mixer/check depth
checkpoint-status | 7ff59b07-56e3-4143-99dc-fb58539b58ba |  | checkpoint | Toilet waste
checkpoint-status | 5b875e89-b8d1-4896-b904-da9e7e85ef28 |  | checkpoint | Vanity Waste
checkpoint-status | 17aa24ed-8beb-4840-a4d5-1afb2b652c85 |  | checkpoint | Vanity Wingbacks
checkpoint-status | 539ff642-bdc2-48d1-b3a0-2e70a0509f7b |  | checkpoint | Vanity & toilet nogs
checkpoint-status | 4c06da67-cd8a-4709-bc23-6ff3347cfaff |  | checkpoint | Hot and cold water pipes installed
checkpoint-status | 1d3a806b-0642-4c59-ab25-82881ef3cd64 |  | checkpoint | Pipe Work Clipped
checkpoint-status | 96df317e-ac27-4bb2-ae9c-913eeca99c9e |  | checkpoint | HWC water feeds
checkpoint-status | 236aa8c3-c808-4d18-b769-089600a84e0c |  | checkpoint | HWC waste
checkpoint-status | 4e4b2754-f770-48a7-8dd1-0c878802a4b1 |  | checkpoint | HWC nogs for strapping
checkpoint-status | fd41faf6-109b-4796-8716-030bc14b8d1b |  | checkpoint | Hose tap installed
checkpoint-status | 48256a25-7449-4181-bc0a-7528ada7a5f8 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 8c54c25d-ad2d-4dbc-8ac1-f9695ff19c37 |  | checkpoint | All water pipes and waste pipes capped
checkpoint-status | bd604fbc-02af-4e3a-8f0e-47fc07ca0792 |  | checkpoint | Check for Crossovers
checkpoint-status | 01253176-97b9-4b5d-bb43-6d3ebd302951 |  | checkpoint | Double check all setout of fixtures
checkpoint-status | c12af3fe-a473-4257-9ebf-6a923617d5fd |  | checkpoint | As built drawing complete, attach copy
checkpoint-status | 76883c4f-2d25-44e2-9435-dc8940659d62 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | 40bf6194-84ef-4306-bcfc-50ce4b88e029 |  | checkpoint | Installers name & date works completed
text | 4b6218ab-dbd8-53c8-bf86-b7d6b337633d |  | textbox | Installers name
text | 2064cb87-2df5-5e9b-a3d0-1d7c70ee0002 |  | textbox | Date:
checkpoint-status | 2e9d7f74-bd17-485e-ad91-1d51931d41d9 |  | checkpoint | Tested by & date
text | 8446b504-c821-529f-a6a0-ee255c36ec0e |  | textbox | Tested by:
text | 285a9cb7-32cd-5fcd-a110-6df104d73d2d |  | textbox | Date tested:
checkpoint-status | bbe7aba1-8f8f-4164-9ed8-f7a7cc45e20b |  | checkpoint | Council inspector sign off and date
checklist-sectioned | e815324f-f4b2-4d83-a65d-20a6f7cefa4e |  | checklist | Core Water |  |  |  |  | Yes | Core Water | df79a4ed-3f26-4126-88b7-50087e394454
checkpoint-group | 0dad7e3f-d80c-41e1-b5ed-ae835549194d |  | section | Cold water main
checkpoint-status | c6e42967-8170-421b-8d48-8e5494c657aa |  | checkpoint | Connections brazed correctly
checkpoint-status | b5c5e503-5fc7-44e5-a245-c06973574904 |  | checkpoint | Clip Spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 5e79e75d-21ad-4873-a83a-aa10f864759b |  | checkpoint | Valves fitted correctly
checkpoint-group | 528b2b84-4db2-40d3-9602-3ff4df811c77 |  | section | Hot water main
checkpoint-status | dbe4ecd4-d08f-42e1-a309-f3067980b2ec |  | checkpoint | Connections welded correctly
checkpoint-status | 10f06e95-f304-4d83-b92a-6cb32f6864ea |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 64918de4-2c0e-4519-8736-d2140d088632 |  | checkpoint | Expansion allowed for
checkpoint-status | 31d968c9-60a5-4eb8-8078-9e903bf4cecf |  | checkpoint | Lagging installed and neat
checkpoint-status | f8a8f3db-ff29-47d9-9043-8a39d20e346e |  | checkpoint | Valves fitted correctly
checkpoint-group | cfe13cb1-fac2-4520-a4e6-8e03c076c43e |  | section | General
checkpoint-status | f77fdff7-9fc1-4310-a21b-f7d22651cf33 |  | checkpoint | Open ends of riser capped for testing
checkpoint-status | dd3ec3ac-a044-4a6c-a4e1-276380c32202 |  | checkpoint | Checked for cross over's
checkpoint-status | 04f6aa77-28c2-47c3-b299-eb0ee4252138 |  | checkpoint | Tidy work areas
checkpoint-status | 54645d98-03fd-447b-a5d6-7641e2734d91 |  | checkpoint | Allowance for expansion
checkpoint-status | 308abd89-7078-487f-a21b-e1b82cd42cc7 |  | checkpoint | Pressure test to 1500kpa for 30mins
checkpoint-status | 29ebe807-f5f3-4ae0-b4bb-74a90dfb730a |  | checkpoint | Visual check (for leeks from valves, tees, saddles, etc)
checkpoint-status | 0b30cf86-00b0-4b9a-ba98-baf6edc91378 |  | checkpoint | Seismic bracing for pipework longitude and latitude
checkpoint-status | ff2892b7-b21c-4dad-9a1b-6afe1bce4953 |  | checkpoint | Lateral labelling of pipework backflow devices fitted
checkpoint-status | 1d994c32-d5aa-40c1-8cd5-67a4506e2170 |  | checkpoint | Pre Line Inspection Passed
checkpoint-status | 9f389436-067a-48cd-b847-8dcdbf64738c |  | checkpoint | Installers name & date works completed
text | 1f43e7e3-6bdb-555d-adec-f710c5481486 |  | textbox | Installers name
text | 499511d2-baf6-5d78-bef8-4b221b1a8c75 |  | textbox | Date:
checkpoint-status | c3b96b51-a385-4532-b0f2-23bacebf0b9c |  | checkpoint | Tested by & date
text | 390754ce-c8e2-51bf-b546-177436db5c0f |  | textbox | Tested by:
text | c41d8bbd-2915-5c5c-b78d-58703154bf34 |  | textbox | Date tested:
checkpoint-status | a2f01175-2e45-4488-8800-0d57db68f70b |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 97992fe9-17e7-4d50-9d4f-693f97f1de95 |  | checklist | Bathroom First Fix Plumbing |  |  |  |  | Yes | Bathroom First Fix Plumbing | e2187f6f-6b3a-48aa-ae17-7c6484a139d5
checkpoint-group | 5f71cafa-5a36-416f-be7c-58c7a0ae5d83 |  | section | Bathroom
checkpoint-status | 9bfd78ad-33a4-4b9d-a09c-131c4cd9a824 |  | checkpoint | W.C Supply
checkpoint-status | 71d4c6bf-1869-44c0-b9f5-e2c337338385 |  | checkpoint | Shower waste
checkpoint-status | 196792ac-1f0b-4b39-96fa-1eeb4fd7c5f5 |  | checkpoint | Shower mixer/check depth
checkpoint-status | 6517f3f5-7a36-4272-9cae-c4ca07bed557 |  | checkpoint | Toilet waste
checkpoint-status | 0a2db277-d5f6-4071-95bd-ffc6d2432462 |  | checkpoint | Vanity Waste
checkpoint-status | 41ec91e0-037f-47e8-87e9-53a6161b9a5f |  | checkpoint | Vanity Wingbacks
checkpoint-status | 6c793588-56d1-457f-94c3-c3661f469049 |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-group | 935f8b37-c06e-4147-a359-ede67acf7612 |  | section | Cleaner sink
checkpoint-status | 0019f0a5-3a80-48a5-bea8-7c7df30b2589 |  | checkpoint | Hot and cold water
checkpoint-status | f5ef2bc8-9179-4267-9f29-ba2f9eb2bb2e |  | checkpoint | Waste pipe
checkpoint-group | 61917aa9-29d4-491a-8b51-cd5e80962e69 |  | section | General
checkpoint-status | 99bcf607-e767-4fe1-ad94-ad7316e142f1 |  | checkpoint | Pipe Work Clipped
checkpoint-status | 11384843-c769-4437-9aa7-ca93943de81b |  | checkpoint | HWC water feeds
checkpoint-status | 71c4b77f-c339-40af-a73b-0b728027c5bf |  | checkpoint | HWC waste
checkpoint-status | 1f05dc45-494f-4e2b-b874-a9d9b582a8ab |  | checkpoint | HWC nogs for strapping
checkpoint-status | bf32a4d7-d653-4c7b-86f1-386c19c30058 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 12590bb7-384a-470c-9ed9-9761904f8136 |  | checkpoint | Capped Off
checkpoint-status | c81ecea5-dcc6-4494-a830-d006e8276a7a |  | checkpoint | Check for Crossovers
checkpoint-status | 335b136f-bddb-48f2-8165-937b639481d9 |  | checkpoint | Double check all sefont of fixtures
checkpoint-status | 1e6edd59-2695-43dc-9e3b-16f2b6706598 |  | checkpoint | Acoustic lagging where required
checkpoint-status | b0d3b6fd-72fa-4461-90d6-c91803c07b8b |  | checkpoint | Thermal lagging to hotpipes where required
checkpoint-status | e9daa2a9-0bb3-4394-9a05-9e0a15a7a058 |  | checkpoint | Floor waste flange fitted
checkpoint-status | 5f950d7d-53bf-452f-8901-050b4a2cd928 |  | checkpoint | Pressure Test 1500 KPA
checkpoint-status | c521ced3-305f-4167-b766-ccbb93e91a0f |  | checkpoint | Installers name & date works completed
text | dc90adb4-39c5-5e0a-84e7-b8789dd668f2 |  | textbox | Installers name
text | 524eecf8-6066-5cd5-9fe1-c16ab366800f |  | textbox | Date:
checkpoint-status | 49c7e93b-6bcc-4747-88ee-4d4d74cfb605 |  | checkpoint | Tested by & date
text | 2ce3aa8d-e72f-5716-8c63-d74f27f1982f |  | textbox | Tested by:
text | 355a4f00-e1e7-5da7-ad6a-7b3c7ce11e5f |  | textbox | Date tested:
checkpoint-status | 1759e0c2-eab3-4d79-96a2-60f1ec80c1e5 |  | checkpoint | Council inspector sign off and date
checklist-flat | 6711de4f-88f4-4a84-a5fb-d35e2168721c |  | checklist | Classroom 1st fix |  |  |  |  | Yes | Classroom 1st fix | e54d5300-4af1-427c-ab2f-131fc84d004f
checkpoint-status | 775309c6-8197-41f5-a94b-004140af3426 |  | checkpoint | Cold water pipework installed
checkpoint-status | a89be1fa-84d2-4245-a060-fc54044d23d2 |  | checkpoint | Hot water pipework installed
checkpoint-status | 1c759839-960f-4b9f-955b-23a3f1264576 |  | checkpoint | Thermal lagging complete
checkpoint-status | 896086bf-3d55-4772-8fbc-52a0efca755d |  | checkpoint | Wingback and waste correct setout
checkpoint-status | 9269ff73-c657-4fa5-8f27-1949a7fb9754 |  | checkpoint | Gas pipework installed
checkpoint-status | 1dd5258a-256a-4785-8ba0-a35bf195081a |  | checkpoint | Gas Guards installed
checkpoint-status | 8f1490b9-5002-42dc-8886-97519e21a042 |  | checkpoint | All pipework clipped and siliconed where it runs through walls
checkpoint-status | 3969635b-087b-47ce-92c8-2fedaac7dc15 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 8718ca6b-6051-4c28-945f-7225bb634465 |  | checkpoint | Tempering valve installed
checkpoint-status | e634a1d7-d643-4297-9fbf-f8831d8a3fe8 |  | checkpoint | All rubbish removed and materials back in storage
checkpoint-status | 7c3d599d-ad2b-4735-8f02-c45032bbf1be |  | checkpoint | All pipework pressure tested
checkpoint-status | e9d1db14-7f2f-4689-81cc-99da8427519a |  | checkpoint | Check no 1st fix clashes with 2nd fix fixing screws
checkpoint-status | 3e03af06-e5d5-4cc9-b13b-64b64f8605a9 |  | checkpoint | Check all nogs are installed
checkpoint-status | 99babd63-5d32-479e-8940-ea424a119029 |  | checkpoint | Installers name & date works completed
text | 637e3445-dd35-5bf1-b566-9068dc6215ac |  | textbox | Installers name
text | 9327418b-5781-51f8-a707-408090141706 |  | textbox | Date:
checkpoint-status | d5391bf0-2a61-4fe9-ac54-2957ff030a2c |  | checkpoint | Tested by & date
text | f7c14cba-946d-5ef0-9047-311208e73af7 |  | textbox | Tested by:
text | c3cd26a7-229e-540c-b20e-76dfa8ad5658 |  | textbox | Date tested:
checkpoint-status | a2e3e546-084f-490a-9567-da5969241f15 |  | checkpoint | Council inspector sign off and date
checklist-flat | 9147fd25-c000-45ce-bc47-0fd0478bdb2c |  | checklist | Roof |  |  |  |  | Yes | Roof | e5e8de52-06b4-4d02-8f18-c87c0a5aed2f
checkpoint-status | d3133207-07b5-4fa0-b7ba-e764dd8f6eca |  | checkpoint | All vents installed
checkpoint-status | 6e679110-f421-4065-8dac-ad3f70f7482b |  | checkpoint | All vermin proofing fitted
checkpoint-status | 12e4f14d-5d89-4e3e-bc80-a40a7d127a99 |  | checkpoint | Hose taps installed
checkpoint-status | fbcc7ef2-9e78-4db2-b211-35e05404e53a |  | checkpoint | Decktites fitted to vents
checkpoint-status | 9de55228-eb30-4d64-9662-802ac6dd7cf7 |  | checkpoint | All overflows finished
checkpoint-status | b7d77336-d4da-4449-87c5-34ed1a540987 |  | checkpoint | All downpipes connected and working
checkpoint-status | 151d5cb2-bc33-4831-bda2-885f040b9599 |  | checkpoint | All outlet covers fitted/correct screws
checkpoint-status | 9bdff6da-c176-4726-82bf-4471de0e3fe0 |  | checkpoint | All rubbish removed
checkpoint-status | f89dec65-a663-4d7e-867e-1cd7c277eb6d |  | checkpoint | Check plastic outlets for cracks
checkpoint-status | a976cada-058e-4f84-9692-e8527e46d887 |  | checkpoint | All downpipes clipped
checkpoint-status | 482242e2-e40b-4682-b99a-14f746dec92e |  | checkpoint | Tested by & date
text | 899c8dfa-643f-5cb9-964d-e1d08f8b44fc |  | textbox | Tested by:
text | 7cec4283-f53e-5593-b7cf-5edfde083c25 |  | textbox | Date tested:
checkpoint-status | e36a827a-d9dc-44e2-b11d-f5db21904301 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | ca607e6c-6e13-4d0f-971d-3d2a65805e11 |  | checklist | Solar system |  |  |  |  | Yes | Solar system | f94c576b-b2df-4124-ad11-9bbac5a3bb00
checkpoint-group | 2076dd16-5839-4a4b-87ab-f4b05d7825b1 |  | section | System Check
checkpoint-status | f07a9940-c11c-4981-9a91-b2c4c873ee3c |  | checkpoint | Air test solar collector loop to within 0.5bar of pressure relief valve for 2 hours
checkpoint-status | 8dc44b6f-e6f6-45ba-b02b-46c280ca81b7 |  | checkpoint | Flush piping with clean water before filling
checkpoint-status | 414d06e2-5f21-4ef4-bce9-e14e23f7aa04 |  | checkpoint | Ensure system holds fluid pressure with no leaks
checkpoint-status | c2a77212-47ae-4de5-8dac-cd3d41889798 |  | checkpoint | Operate pump manually and check flow
checkpoint-status | 46b7f7c7-75e3-45ec-bf59-3d574f8a9b7c |  | checkpoint | Check that all collector banks have balance flow
checkpoint-status | d194308f-7574-4402-bbf3-958fb6f617e7 |  | checkpoint | Exposed piping is insulated, jacketed and labeled
checkpoint-status | 8c7bd455-5359-44e6-a5c9-ae86eeaa2df2 |  | checkpoint | Interior piping is insulated and labeled
checkpoint-status | ae7a262a-4634-45d5-9ae5-5b425097ceec |  | checkpoint | Temperature sensors are installed in proper location and providing accurate readings
checkpoint-status | c06ddaa2-228b-41ce-986a-9c2d01160cb4 |  | checkpoint | Temperature gauges are installed on the solar thermal flow and return lines
checkpoint-status | a2c10397-2b36-4f4a-8c79-01c1637bea25 |  | checkpoint | Visual flow gauge is installed on the solar thermal loop
checkpoint-status | bed202d6-6406-4dfa-b2e2-e0b4ad0cdb44 |  | checkpoint | Pressure gauge is installed on solar thermal loop (for closed loop systems)
checkpoint-status | 59b6a0ac-9df2-439c-83e9-d58d83b07c26 |  | checkpoint | Motorised ball valve/s correctly orientated for default flow path
checkpoint-group | 5c340d76-ce5b-42f4-bfda-77fb42f30ca7 |  | section | Evacuated Tube Installation
checkpoint-status | 57b2075a-7e00-4d6d-bc28-fa47c8390e84 |  | checkpoint | All heat pipe bulbs coated in heat transfer paste
checkpoint-status | 52a9a2b1-f157-4ced-87e5-423a7ad7a59b |  | checkpoint | No tubes have vacuum loss
checkpoint-status | d8543b91-3232-4796-8df3-a39c9b873cc9 |  | checkpoint | All evacuated tubes are installed
checkpoint-status | 5e1d03f3-a3a8-4116-adcf-fef81d081587 |  | checkpoint | All tubes have rubber caps and clips are neatly aligned
checkpoint-group | 7f13b151-b1cc-491e-ac50-b3ab627af8e1 |  | section | Operation & Performance Check
checkpoint-status | 4f3e2ca1-1a2f-4e2e-8747-cbab9125eeb1 |  | checkpoint | Collectors generate heat when pump is not running
checkpoint-status | c55ea73c-e80d-484b-b036-08d7a8bb01d3 |  | checkpoint | Controller operates properly switching pumps and relays on/off as expected
checkpoint-group | e3c1ff0a-c844-4eff-b898-e8cc7f7a1586 |  | section | Cleaning
checkpoint-status | 0f1a89d8-73a3-4a24-8b6e-4afb628e6f3b |  | checkpoint | Solar collector manifold and evacuated tubes have been cleaned
checkpoint-status | cdfe3198-e122-4ac5-aad5-c34a966a3fba |  | checkpoint | All rubbish has been removed from the roof and equipment rooms
checkpoint-group | 59be7a20-3fef-4275-8d45-dd5ccb95c402 |  | section | Handover to Owner
checkpoint-status | ab2af13d-d1b9-41e3-a33b-572b1a6f80e0 |  | checkpoint | Provided operation and maintenance documentation set
checkpoint-status | babf449e-9547-43a3-85d6-0b2d6a6e803c |  | checkpoint | Completed explanation of the basic system operation
checkpoint-status | ac2a71bc-d158-400c-a36d-bff7cefa36c8 |  | checkpoint | Completed training on how to safely turn off the system
checkpoint-status | 666c6ec0-3139-4268-b5db-7a0ead2ab35d |  | checkpoint | Complete training on which valves must not be tampered with
checkpoint-status | 93f5fad7-8c67-4d76-8e19-69933002c734 |  | checkpoint | Completed training on the basic operation of the controller to read system settings
checkpoint-status | c854f780-7811-4b58-aa80-6d960f81720f |  | checkpoint | Completed training on the maintenance tasks, and frequency at which to be conducted
checklist-flat | 85e9babd-bb8a-4e84-9d8d-56559298db17 |  | checklist | Underslab |  |  |  |  | Yes | Underslab | fd097781-7525-4623-813c-ec5de88c97f4
checkpoint-status | 11b2f827-b802-42e5-be02-c860c797819d |  | checkpoint | Area ready for works
checkpoint-status | e5c325a4-0b4c-4ed9-9f00-8d715a86a9c3 |  | checkpoint | Dimensioned Slab Set Out Drawings
checkpoint-status | f9f56158-d81c-4c7d-a39d-b596c3dd612b |  | checkpoint | Minimum Or More Fall Achieved on Slab Piping
checkpoint-status | c72ccddc-1a6a-48bc-a605-bfa2fda7e0f6 |  | checkpoint | Under Slab Piping In Slab
checkpoint-status | 1610bcec-17aa-4f86-bd57-074157f730ed |  | checkpoint | Called For Underslab Inspection To Be Booked
checkpoint-status | b6a6f2a9-4aa7-4b5f-b35c-56b293b51540 |  | checkpoint | Mains Incoming Water Supply Installed and tested
checkpoint-status | 5d510a00-8acc-43cd-b248-117d529a8762 |  | checkpoint | Test Plug Removed From Pipe System or capped for drainlayer to remove?
checkpoint-status | 7827c587-8239-4c18-9202-29b310420004 |  | checkpoint | 25mm Protection Around Pipes Penetrating Slab
checkpoint-status | 42d040ad-2e4a-4a6e-bbba-4c19a0fec3f3 |  | checkpoint | All Measurements Double Checked
checkpoint-status | 39f789dd-6149-48e2-982f-23827b1fcc3b |  | checkpoint | Haunching & Bedding
checkpoint-status | 3b2c964d-9a5a-49fe-9c98-f1c11a6543de |  | checkpoint | Concrete Under Gully
checkpoint-status | 58da5701-2a94-4f4e-bd5b-1c4954969939 |  | checkpoint | Drawing Number And Revision
checkpoint-status | 1b3d3737-6777-41ed-9645-fa918d451e02 |  | checkpoint | As built drawing complete, attach copy
checkpoint-status | 6cff1088-2e84-4889-836a-dc577f406cc4 |  | checkpoint | All upstands capped
checkpoint-status | b9049550-1fd7-4f19-a1d3-27ba755216c1 |  | checkpoint | Installers name & date works completed
text | 8686357e-9a83-529d-8f74-bbb31bff45bb |  | textbox | Installers name
text | 99b9edfc-f5f7-5768-96e4-61330d336007 |  | textbox | Date:
checkpoint-status | 47abb185-262f-4be4-8e83-4e63d5b95647 |  | checkpoint | Tested by & date
text | 5bf40d48-8ed7-5a46-ab99-84b0e1f68327 |  | textbox | Tested by:
text | 5d36e5b7-73e7-5045-b3f1-77b1393283a9 |  | textbox | Date tested:
checkpoint-status | 5da0cb52-a970-4463-a3ff-a272df86fb70 |  | checkpoint | Council inspector sign off and date
checklist-flat | 723228b4-6127-491c-9c70-bf3a230cf2b2 |  | checklist | PVC |  |  |  |  | Yes | PVC | fd27351e-b05e-4db1-a800-47d092b1dd16
checkpoint-status | 362e8afe-a3e8-4278-84e0-edad5c6c55ea |  | checkpoint | Waste Pipeout
checkpoint-status | 8f271f04-0fba-419d-bac3-65d637291fa3 |  | checkpoint | Vent installed
checkpoint-status | 4b22162f-fdcc-4906-a420-83417ff18368 |  | checkpoint | Check sewer hasn't been connected to stormwater.
checkpoint-status | 18cf47a2-e8c3-44a1-998c-4d2f9e6b6080 |  | checkpoint | Correct or exceded minimum fall
checkpoint-status | 8faecdf4-2a8c-43ea-9098-057f255cf451 |  | checkpoint | Correct Clipping
checkpoint-status | 36af5610-9f57-49c1-86a4-7d6c3d4afdd5 |  | checkpoint | Flood Test in accordance with ASNZ 3500
checkpoint-status | 703148bf-004b-4922-9724-8247492bd8fc |  | checkpoint | Hydrostatic test Plug Removed By
checkpoint-status | 8a1974af-def4-4c2b-94f1-db41d5cd0e47 |  | checkpoint | Inspection Cover Replaced By
checkpoint-status | e5f4c159-1564-42d4-a504-2bdea8d5bae6 |  | checkpoint | Seismic bracing for pipework, longitude & lateral
checkpoint-status | 320e47e0-5c89-417b-b42b-df2c48bea41c |  | checkpoint | Pipe labeling
checkpoint-status | 19b4555b-ca71-45e6-bcfb-b4dd3969ee59 |  | checkpoint | Access points for cleaning
checkpoint-status | 148822e9-bf82-4c6b-8a8d-58019e50014a |  | checkpoint | Acoustic lagging
checkpoint-status | 3d154495-0000-4b99-b0bf-60c5de32f0c9 |  | checkpoint | All pipe stubs covered or capped
checkpoint-status | 5b572f1e-2731-4ab3-aadd-fae414de35de |  | checkpoint | Installers name & date works completed
text | 96430c8d-3d1c-5734-905f-d5af16fe12d4 |  | textbox | Installers name
text | 5a38b042-d19d-5ee3-8f70-09a0eef380f2 |  | textbox | Date:
checkpoint-status | f3278ef9-a9e0-4630-bef0-7d71f1df552c |  | checkpoint | Tested by & date
text | 95de2f17-3a5e-5bd9-abdc-469bbdf3e6cc |  | textbox | Tested by:
text | 9673c539-ef88-54ac-bec2-431a3ce7a78f |  | textbox | Date tested:
checkpoint-status | f302d066-97cf-4cfb-8d51-b1b5c46caa28 |  | checkpoint | Council inspector sign off and date