## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 48f7e878-7fe6-4bc4-866f-8cf6305e51ed |  | checklist | Basement - Gym |  |  |  |  | Yes | Basement - Gym | 0a45ae39-e857-4796-9e09-b8e5ac2449a7
checkpoint-status | 0b1853a3-b408-4fc2-8551-ecd3f30b7492 |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 1753a40e-b222-4eb3-a371-e4c3a879564b |  | checkpoint | Gym area ready for tiling work
checkpoint-status | 9ddf199f-aecf-4ae9-9b3b-d04f4dcaf1d0 |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | 09a7bf49-922d-4611-8baa-9872bef2fdaa |  | checkpoint | Seq # 2 - Screeding
checkpoint-status | 0631a841-d1df-43de-89a4-629e9f402142 |  | checkpoint | Seq # 3 - Regupol 4515 Acoustic Under Lay
checkpoint-status | 234c0b1e-8666-44a7-acd1-2b18e79be410 |  | checkpoint | Seq # 4 - Floor Tiling
checkpoint-status | eb53f624-09a4-4c9c-89bd-cf9367b45aa2 |  | checkpoint | Seq # 5 - Wall Tiling
checkpoint-status | d56e3b0f-d7d8-4a34-a675-f40df5a614f4 |  | checkpoint | Seq # 6 - Standard Grout
checkpoint-status | abad4d82-0d5d-48fd-ac70-e0d023552ed8 |  | checkpoint | Seq # 7 - Floor cover Trim. L angle Trim
checkpoint-status | 91d198cd-1b72-4447-95bb-fa7d8cdd1550 |  | checkpoint | Seq # 8 - Silicon
checkpoint-status | 2f232d9e-745d-4daf-95f5-600de21f368e |  | checkpoint | Seq # 9 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | 6715f129-2ec7-4374-8d19-b2b03f3985ec |  | checkpoint | Seq # 10 - Floor Finish Protection / Ramboard
checkpoint-status | 2a39b668-2670-490b-aca2-7f5578938748 |  | checkpoint | Seq # 11 - Handover
checklist-flat | 539303a9-e945-47a1-8614-501e5efb0bfc |  | checklist | WC |  |  |  |  | Yes | WC | 0fb91a41-cf61-4667-a0c9-c46a70877ef2
checkpoint-status | 3722f7ce-f148-422a-8112-6ecac2ea032d |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 792cb39b-450a-4cd7-9eb9-08048f45731b |  | checkpoint | WC ready for tiling work
checkpoint-status | a179589c-e352-424e-bc4b-934ca322dcc1 |  | checkpoint | Seq # 1 - Screeding
checkpoint-status | b292ab85-8cb0-41d6-a1ce-71e0e4500cae |  | checkpoint | Seq # 2 - Levelling
checkpoint-status | 920fce78-faab-4a5c-9c5f-5ff6ea1ef66c |  | checkpoint | Seq # 3 - Waterproofing
checkpoint-status | 56f0bea8-08c8-4016-9aa7-634b85c7ed7e |  | checkpoint | Seq # 4 - Floor Tiling
checkpoint-status | d029a736-5dbc-4f06-bbb0-307aa72d23ac |  | checkpoint | Seq # 5 - Wall Tiling
checkpoint-status | da547f8b-03ee-402f-8420-44708db09aab |  | checkpoint | Seq # 6 - Epoxy Grout
checkpoint-status | 9478d70d-20cc-495f-a6c3-703d554ffd6c |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | da5328a8-b828-4714-8137-c8d745424a8c |  | checkpoint | Seq # 8 - Floor Trim
checkpoint-status | 905fdbf1-9c2f-4a32-bbfa-64b37165d70a |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | 10dc5aee-5f67-4b5e-96b3-69657f1be03d |  | checkpoint | Seq # 10 - Final Finish / Cleaning
checkpoint-status | 2dfe60a7-ccb9-4c03-89cf-6af1c002e4e9 |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | baded8d5-00b3-4793-bf25-e5e12a75ab1d |  | checkpoint | Seq # 12 - Handover
checklist-flat | 2b25ec44-d14b-4414-afb1-518a7d1eac82 |  | checklist | Laundry |  |  |  |  | Yes | Laundry | 108adac7-5378-4045-8dd5-16768e509f67
checkpoint-status | 7d205dae-134b-4baa-bc24-9db2c2a3fc3c |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 7bfcb726-1df8-4827-95ac-00eb9c2b5e64 |  | checkpoint | Laundry ready for tiling work
checkpoint-status | 5ae026d1-0cea-4249-b313-5dbe003b45ed |  | checkpoint | Seq # 1 - Screeding
checkpoint-status | c3eb921e-fad9-46bd-a8c7-899471c15d17 |  | checkpoint | Seq # 2 - Levelling
checkpoint-status | f948b88a-6ba2-4fb5-a433-6d8ab79c1851 |  | checkpoint | Seq # 3 Regupol 4515 Acoustic Under Lay Installation
checkpoint-status | 1676bba5-7db8-4e67-8a00-672712fa47f5 |  | checkpoint | Seq # 4 - Waterproofing
checkpoint-status | 02a97e07-7c3b-46c3-a27f-ff7907cb30b1 |  | checkpoint | Seq # 4 - Floor Tiling
checkpoint-status | 96e12a3b-9e0d-415f-ad03-57796976c7f7 |  | checkpoint | Seq # 5 -Splashback
checkpoint-status | e64b6ea5-8df4-4541-a4b9-176d4f0028d6 |  | checkpoint | Seq # 6 - Epoxy Grout
checkpoint-status | 62aa587c-0b73-45c0-affd-3e463b7ac937 |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | 44479fad-379d-413d-ab15-29ec8a4bf583 |  | checkpoint | Seq # 8 - Floor Trim
checkpoint-status | a763ed8e-c376-4e5f-9e26-29d784428e78 |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | 2f067e22-81bd-4b95-8ce5-05f9ddde02ff |  | checkpoint | Seq # 10 - Final Finish / Cleaning
checkpoint-status | 4e36ca20-dee9-4f6d-a5f7-ad7ca8583dd3 |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | 0e1e4bd9-827f-4cda-a19e-1a62e7d9c553 |  | checkpoint | Seq # 12 - Handover
checklist-flat | 54106af1-109a-47be-8fe0-15ba5e9d9ceb |  | checklist | Logia / Patio |  |  |  |  | Yes | Logia / Patio | 309a999e-5bc2-45ef-a05e-c36a28b6e6d9
checkpoint-status | 29e87ac4-fb1e-4a3f-891e-cd757accbeb5 |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 4a42934c-22d4-4c96-9224-327d6ef00f1e |  | checkpoint | Logia / Patio ready for tiling work
checkpoint-status | ee16d05d-2e61-4b58-8664-d83efa170abd |  | checkpoint | Seq # 1 - Screeding
checkpoint-status | 442a7225-30fb-4b0f-b795-61f2632bbc39 |  | checkpoint | Seq # 2 - Levelling
checkpoint-status | 4fad231b-2c35-49ce-8289-77623b6fa21c |  | checkpoint | Seq # 3 Regupol 4515 Acoustic Under Lay Installation
checkpoint-status | aa2231e4-c9b3-471a-9cde-81909bf8663c |  | checkpoint | Seq # 3 - Waterproofing
checkpoint-status | 8d1ebfa6-b0e6-4e65-a5a3-54d11be4f93d |  | checkpoint | Seq # 4 - Floor Tiling / Floor tiles over Deckjacks for L1 Patio
checkpoint-status | 2b6022b5-377a-4059-a84c-38b24180dab0 |  | checkpoint | Seq # 5 - Wall Tiling
checkpoint-status | 01df81b7-3b91-46f3-bd71-d5fd14e7b8f7 |  | checkpoint | Seq # 6 - Epoxy Grout
checkpoint-status | 9f9299a0-f2cb-4e1e-8e27-32d6808a3ee3 |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | c0eb088c-a031-46be-9422-77fcf63376ae |  | checkpoint | Seq # 8 - Floor Trim
checkpoint-status | 66d5f387-88be-44d8-abb6-346cf8dd3cee |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | b3c1e9f4-7311-4566-a866-39e5427d43c5 |  | checkpoint | Seq # 10 - Final Finish / Cleaning
checkpoint-status | ed5f5e1f-d41f-42a1-a1b4-2ef819278b44 |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | dca30c0a-8d9c-4493-a313-e9d7ce98d487 |  | checkpoint | Seq # 12 - Handover
checklist-flat | 5e4c5952-6331-45c1-b79a-2963408bd4eb |  | checklist | Kitchen / Scullery |  |  |  |  | Yes | Kitchen / Scullery | 3758858d-e97f-4da3-b98c-7c49a6316917
checkpoint-status | 7e57404b-2aac-4e09-94ee-ba746471140a |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 85c61f3c-aae1-45d7-a8d5-bfab30d58c47 |  | checkpoint | Kitchen / Scullery ready for tiling work
checkpoint-status | 473bb578-00d4-4e1f-a38a-05244072aec9 |  | checkpoint | Seq # 1 - Screeding
checkpoint-status | 9989b6e1-c9d6-48fd-81fa-36ef5e033a02 |  | checkpoint | Seq # 2 - Levelling
checkpoint-status | 6d5fb0db-172c-4596-88cb-0e8ef6df0de1 |  | checkpoint | Seq # 3 - Waterproofing
checkpoint-status | 3c61a29d-98af-4192-a06b-53b6b85df01a |  | checkpoint | Seq # 4 - Floor Tiling
checkpoint-status | 46780cec-ace4-4fbf-afd2-a052a801fa27 |  | checkpoint | Seq # 5 -Splashback
checkpoint-status | e5752f6c-4b2e-41f2-a473-b2d4b4288d17 |  | checkpoint | Seq # 6 - Epoxy Grout
checkpoint-status | 7ed89ad3-664f-414f-875d-f0c89158802b |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | 1300dd31-b9cf-48fc-aca0-e743d1ad00a2 |  | checkpoint | Seq # 8 - Floor Trim
checkpoint-status | 2c196e57-d04c-46fd-8efe-e68fedb9d585 |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | cf106eed-6c6d-4987-a968-1e722cf05229 |  | checkpoint | Seq # 10 - Final Finish / Cleaning
checkpoint-status | eb4034a8-6daf-428b-a49a-ece7b7e6f2ab |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | 2b100463-edff-4c29-aed6-6f5b1c3912df |  | checkpoint | Seq # 12 - Handover
checklist-flat | 6fe70565-fe64-45b5-9135-46bbb69b9bc8 |  | checklist | Lift Lobby |  |  |  |  | Yes | Lift Lobby | 380275fb-9261-437e-83af-d687ed4cef23
checkpoint-status | 0133eeed-23eb-4bf5-8b2b-b388feabfdec |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | e3f5e371-e7f2-4260-80db-f03568ac692b |  | checkpoint | Lift Lobby ready for tiling work
checkpoint-status | 9911467e-fe28-4c53-80e6-68fb9b9d7fdd |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | 3a13a96d-9cc7-4c77-be17-cc1253871bc8 |  | checkpoint | Seq # 2 - Screeding
checkpoint-status | 6f477af0-c77b-44ad-b150-c391a480a484 |  | checkpoint | Seq # 3 - Levelling
checkpoint-status | 5fb0ef6b-a82f-45eb-95e7-50f0ee47f503 |  | checkpoint | Seq # 4 - Regupol 4515 Acoustic Under Lay
checkpoint-status | d75a406e-cb7f-42d3-87c4-092c8cdd8cca |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | f8782306-9a6c-4eb4-b007-453ec597da2b |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | fd224e95-8acb-4414-b249-c7901fdde726 |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | f28f65a0-be69-4778-a7f9-cac3b76bc1c4 |  | checkpoint | Seq # 8 - Floor cover Trim. L angle Trim
checkpoint-status | 390702f5-ca8c-4a44-a2e1-778119200bc3 |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | 09ed00f2-d354-4c30-8bc7-69b996ec6860 |  | checkpoint | Seq # 10 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | f2827537-7fea-493d-b8d6-4a1294c83d87 |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | 8d42eb28-97b5-48b5-a603-98305e8e0999 |  | checkpoint | Seq # 12 - Handover
checklist-flat | 2070b0dc-a944-44be-a671-200a49c8f760 |  | checklist | Basement - Storage |  |  |  |  | Yes | Basement - Storage | 3a70dfac-81db-434c-ad2c-8157da742380
checkpoint-status | 731daf06-9252-4811-b09f-f2144cddadb7 |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 30130545-39b8-466b-a6c2-32e3d581c534 |  | checkpoint | Storage area ready for tiling work
checkpoint-status | c7156851-4a8b-4d37-a0a7-0e0718ff8b30 |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | 98ae118c-520a-4499-97d2-6d90bf876ac9 |  | checkpoint | Seq # 2 - Screeding
checkpoint-status | d5bea86d-34b1-4fb9-ba89-ea8301bb250f |  | checkpoint | Seq # 3 - Levelling
checkpoint-status | 98271813-5c95-4e5e-bd35-6efeeb1a3ab5 |  | checkpoint | Seq # 4 - Regupol 4515 Acoustic Under Lay
checkpoint-status | 2566a32a-f690-44ea-aed2-97037a6c818e |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | 3248c610-9eea-4d50-ad84-ee4c07296333 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | 6f843bc2-aa52-4d07-85bd-dde7c2ed551d |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | 2ec09039-f9c7-4bdd-bb44-c412331793c8 |  | checkpoint | Seq # 8 - Floor cover Trim. L angle Trim
checkpoint-status | 0ecaf7c3-ab5d-4901-a278-93730ea03340 |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | b9509858-ccdb-4369-8da8-fbed419763fe |  | checkpoint | Seq # 10 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | 564c2c30-0e33-45a2-b5f0-ebcb29aabce5 |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | 1ade2d51-d541-4bd0-943b-8efd080fe006 |  | checkpoint | Seq # 12 - Handover
checklist-flat | 4b9970ed-5014-4d22-86a9-32ba4f3b5d98 |  | checklist | Basement - Corridor |  |  |  |  | Yes | Basement - Corridor | 3dbcdd7d-e172-424a-a928-93b8ab7a0e0a
checkpoint-status | a372b5d2-8089-4ebb-8ef6-862dbfd9dc18 |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 9743a10b-6268-470a-b683-7444ea4fe0cf |  | checkpoint | Corridar ready for tiling work
checkpoint-status | c2b96241-0278-4d1b-9907-21adf8ec31e8 |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | 1406ef8a-3cdc-47fa-81c9-ea2096801a51 |  | checkpoint | Seq # 2 - Screeding
checkpoint-status | 0839cd9d-3989-46c8-b833-429eba5617f6 |  | checkpoint | Seq # 3 - Levelling
checkpoint-status | 9244cdef-b630-4045-9957-45088b7c00a7 |  | checkpoint | Seq # 4 - Regupol 4515 Acoustic Under Lay
checkpoint-status | 39a59569-c546-447e-808a-e7b05f9f40be |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | 1aa3b5e4-9f95-4df7-b4c3-76965816daa5 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | 4e672386-f0e1-4b16-813c-f627fcd5c6c5 |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | d843bc10-0353-4359-b76c-c1747c4b5148 |  | checkpoint | Seq # 8 - Floor cover Trim. L angle Trim
checkpoint-status | e497c324-8fb7-4055-adcc-efd115cdad5d |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | bc165153-277e-44dc-8659-94a4535f2356 |  | checkpoint | Seq # 10 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | 297082f9-d275-4884-9ffe-1e2fbf2856b5 |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | b9f71e8b-78aa-47a2-8beb-9d253216340d |  | checkpoint | Seq # 12 - Handover
checklist-flat | df241b45-4962-4951-9dbf-89f1c869ecc1 |  | checklist | Basement - Toilets |  |  |  |  | Yes | Basement - Toilets | 8f71e1e9-ff41-4dd8-af58-89d3169446c4
checkpoint-status | 31d0a366-6e0f-47d3-b7e4-839b833fe79b |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | f40aa238-345b-4f28-adee-03560a427b82 |  | checkpoint | Toilets ready for tiling work
checkpoint-status | dc613f91-9ec4-4076-a2c7-a76ba58b515e |  | checkpoint | Seq # 1 - Screeding
checkpoint-status | f560e70c-11b2-4b6d-9fa5-dd27091710be |  | checkpoint | Seq # 3 Regupol 4515 Acoustic Under Lay
checkpoint-status | 2bd57bf4-a00a-4302-894a-e35cbdbe51e0 |  | checkpoint | Seq # 4 - Waterproofing for toiler floor and shower wall
checkpoint-status | cf7933a2-c3ae-4789-b7d7-fccf4569e11e |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | 28d3bc7d-73e4-437c-8ea5-30c36429eb31 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | 9fea0984-e9aa-463b-8eca-8fad02d2057e |  | checkpoint | Seq # 7 - Epoxy Grout
checkpoint-status | 0b9d8687-c8a2-427b-ae93-61a48977522f |  | checkpoint | Seq # 8 - Standard Grout
checkpoint-status | c7a9ad0a-2362-4036-bc92-312ca36dc8f2 |  | checkpoint | Seq # 9 - Floor Trim
checkpoint-status | 6d4a30d7-0d07-4bc1-9eb7-c6a24ce5b6af |  | checkpoint | Seq # 10 - Silicon
checkpoint-status | 514fac82-628b-4dc5-98fa-b12353eb060c |  | checkpoint | Seq # 11 - Final Finish / Cleaning
checkpoint-status | 8b97a8be-9460-4eda-860f-82ff9b390141 |  | checkpoint | Seq # 12 - Floor Finish Protection / Ramboard
checkpoint-status | c2de2648-c5bf-40d6-9843-760415b699cc |  | checkpoint | Seq # 13 - Handover
checklist-flat | 4d6a6149-a8d5-455a-9e45-62601f534d6d |  | checklist | Main Lobby |  |  |  |  | Yes | Main Lobby | 91a324dd-2bd9-4cb1-9b9a-b6c3a6b021bb
checkpoint-status | ce8c8d3f-840a-492d-902c-d2e995afcb60 |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | e4033323-f32f-462c-89d9-8fd449c62e21 |  | checkpoint | Main lobby ready for tiling work
checkpoint-status | c62065a1-c674-4613-a076-7751b974b45a |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | ae35cb7e-351b-4371-a503-2df71920457b |  | checkpoint | Seq # 2 - Screeding
checkpoint-status | 960bee8d-b1b0-4dc4-9c8b-d20c9c436e98 |  | checkpoint | Seq # 3 - Levelling
checkpoint-status | d3cd1363-cb3d-4e20-9e61-cf01def4a97f |  | checkpoint | Seq # 4 - Regupol 4515 Acoustic Under Lay
checkpoint-status | 82ba179d-2612-4859-9515-43b216dca30b |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | e7419812-b14f-4082-a7bf-6660d2869878 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | f1630aeb-4cba-4439-9027-75ed28a99ffd |  | checkpoint | Seq # 7 - Stair tread and riser tiling
checkpoint-status | f58ccb04-4057-4d2d-9da0-8bfe229933ad |  | checkpoint | Seq # 8 - Standard Grout
checkpoint-status | dee9c3a0-8db9-4114-b843-68fb8e34357d |  | checkpoint | Seq # 9 - Floor cover Trim. L angle Trim
checkpoint-status | dea759b7-cffa-4e15-87b8-8d2d17647035 |  | checkpoint | Seq # 10 - Silicon
checkpoint-status | ddf1fa77-3eca-4826-9f30-8b0566e2f972 |  | checkpoint | Seq # 11 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | 2b507e4f-6246-442e-9e2e-3146c106016d |  | checkpoint | Seq # 12 - Floor Finish Protection / Ramboard
checkpoint-status | 966d6f05-e5cd-4c14-9709-3dd66ef93f80 |  | checkpoint | Seq # 13 - Handover
checklist-flat | 3c89e097-62cf-4217-af30-4d8b89b908e2 |  | checklist | Dining |  |  |  |  | Yes | Dining | b0eb5aae-7a38-429e-9673-54de433dc1f2
checkpoint-status | 3435ce95-e996-4891-a909-d871e8857b2f |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | e5a10d3c-7c73-48af-a9bb-c9f2e8280de8 |  | checkpoint | Dining ready for tiling work
checkpoint-status | f7dbf9a7-861b-4a7e-b31c-44dac94c819c |  | checkpoint | Seq # 1 - Screeding
checkpoint-status | d8ac815f-92ca-48b1-8b7d-efbf6b7a6c19 |  | checkpoint | Seq # 2 - Levelling
checkpoint-status | 173b7dd9-f8c9-44a4-9260-527a2b86ae9e |  | checkpoint | Seq # 3 - Waterproofing
checkpoint-status | 04577b82-69f4-4fc3-8d0a-436cc794e89a |  | checkpoint | Seq # 4 - Floor Tiling
checkpoint-status | fe794c65-7f64-4b43-980e-ef31181dd469 |  | checkpoint | Seq # 5 - Wall Tiling
checkpoint-status | 139d5784-9b2a-4dd3-84e5-a2b113cceee1 |  | checkpoint | Seq # 6 - Epoxy Grout
checkpoint-status | 8337af05-4e4b-4c4a-b529-6161af18eda2 |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | d0045616-a954-42f3-b281-e4028ab29dd7 |  | checkpoint | Seq # 8 - Floor Trim
checkpoint-status | 6a7010ac-f48e-4032-bd95-cef633f276d7 |  | checkpoint | Seq # 9 - Silicon
checkpoint-status | aa1858d3-40c6-4927-a5d5-12bbe2f609ef |  | checkpoint | Seq # 10 - Final Finish / Cleaning
checkpoint-status | fa807c2c-9486-4297-8a38-f8d4c3e5a5b2 |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | 044b2de0-4b82-42db-9185-89d28b04712c |  | checkpoint | Seq # 12 - Handover
checklist-flat | 32b00e2d-8a27-49f5-bad3-35eadbfc3a13 |  | checklist | Stair Case |  |  |  |  | Yes | Stair Case | befa8be6-595d-4f70-8ad4-988392b10255
checkpoint-status | b7bf8d1d-22b2-4a4b-9bff-96114a272d07 |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | d08aa172-bf0e-4f7b-9868-3beba43d6687 |  | checkpoint | Main Entrance ready for tiling work
checkpoint-status | 2af990de-c152-4536-a0a2-c3e5a22a697b |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | da4d2474-bb48-4986-8577-d66930f626fd |  | checkpoint | Seq # 2 - Screeding
checkpoint-status | 77c9331f-d0d2-449e-8991-4227f3bd6158 |  | checkpoint | Seq # 3 - Levelling
checkpoint-status | 740e5bd9-d2ae-4e03-bb08-ddf7201c9a1f |  | checkpoint | Seq # 4 - Regupol 4515 Acoustic Under Lay
checkpoint-status | 67ef56e8-e1c9-4c9b-95d6-56a7b0f4ee26 |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | 64bad1b7-af8f-44f2-883b-1682a7d9ad98 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | c1282d99-e212-4f39-a4d4-4ea3d496a2ba |  | checkpoint | Seq # 7 - Stair tread and riser tiling
checkpoint-status | 856b6331-5375-4790-b2eb-342b60d6ef09 |  | checkpoint | Seq # 8 - Cut the groove and Install Store Nosing (Brass)
checkpoint-status | 15fad2bd-1610-4fd4-9138-7d74f17f354f |  | checkpoint | Seq # 9 - Standard Grout
checkpoint-status | 390ff54c-021f-4598-8db3-3ec0e847decf |  | checkpoint | Seq # 10 - Floor cover Trim. L angle Trim
checkpoint-status | 6e01e6e7-af44-4435-a6ba-9e13c3fa0910 |  | checkpoint | Seq # 11 - Silicon
checkpoint-status | 470f0efe-c1ce-44ec-adf7-1c27f827fd46 |  | checkpoint | Seq # 12 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | c05f4926-4b22-409d-a7c4-e0cedaa0b680 |  | checkpoint | Seq # 13 - Floor Finish Protection / Ramboard
checkpoint-status | af99af50-f259-4c73-9e09-1b6a07e4691c |  | checkpoint | Seq # 14 - Handover
checklist-flat | c4c8dcbe-eb6f-4d53-b918-589f2133fb19 |  | checklist | Bathroom |  |  |  |  | Yes | Bathroom | c915b211-7873-4916-a4c1-dddad59a6383
checkpoint-status | 98a6f09a-975f-43a4-be9e-2e8430a1ecaf |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 9f33c475-0fea-4550-bdf7-ac405fac07aa |  | checkpoint | Bathroom ready for tiling work
checkpoint-status | 745d3098-a03a-4715-8a18-ad1a9956290c |  | checkpoint | Seq # 1 - Screeding
checkpoint-status | 95599fc4-e2a6-4963-8b81-d51fbe766ec2 |  | checkpoint | Seq # 2 - Levelling
checkpoint-status | 56a13e6c-8867-4496-8573-053ad70a4e92 |  | checkpoint | Seq # 3 Regupol 4515 Acoustic Under Lay
checkpoint-status | 79ebeb92-932b-4c93-900e-f5746e9fdeff |  | checkpoint | Seq # 4 - Waterproofing
checkpoint-status | 2aa797d5-42d6-4836-bb48-8f384cfcbaf5 |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | 64766755-006a-4fa4-847a-73b195792600 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | 3d5aad43-4908-4683-b8a4-471926f67083 |  | checkpoint | Seq # 7 - Epoxy Grout
checkpoint-status | 5d787ac1-8c2e-46a5-81ef-278179b39f65 |  | checkpoint | Seq # 8 - Standard Grout
checkpoint-status | 087794af-0daa-402e-88aa-13741924671b |  | checkpoint | Seq # 9 - Floor Trim
checkpoint-status | 07877cce-75a6-4a69-b9a0-e61991a24bae |  | checkpoint | Seq # 10 - Silicon
checkpoint-status | cc1d67ad-dea7-4336-a23d-89e49b83daba |  | checkpoint | Seq # 11 - Final Finish / Cleaning
checkpoint-status | c11b684d-35ff-4660-839b-6d9aa5bd2c0e |  | checkpoint | Seq # 12 - Floor Finish Protection / Ramboard
checkpoint-status | 8baac93b-4908-4889-92cc-a965287e09f3 |  | checkpoint | Seq # 13 - Handover
checklist-flat | 0be4e77d-8cb1-4ed7-b07e-6b3fbd166abc |  | checklist | Basement - Lift Lobby |  |  |  |  | Yes | Basement - Lift Lobby | f190d0e7-31ac-451d-a87a-fca8b4f59ca0
checkpoint-status | 167d6f40-1654-470c-a5fa-3490f314e22c |  | checkpoint | Pre-Start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | 36327baa-1ff4-424c-a34a-9c812ac410db |  | checkpoint | Lift Lobby ready for tiling work
checkpoint-status | 65e9b040-b342-44ed-ab4e-438a2e7f549d |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | a45d935d-434a-4e47-b7d8-fe6bed56daf8 |  | checkpoint | Seq # 2 - Screeding to Ramp
checkpoint-status | 0374fbcd-2474-4fb3-94d8-8f376261ee37 |  | checkpoint | Seq # 3 - Levelling
checkpoint-status | 64352420-5b1d-4f6a-b0df-fe7dedb1a6d1 |  | checkpoint | Seq # 4 - Regupol 4515 Acoustic Under Lay
checkpoint-status | 21aee211-55a2-442e-8f23-933e9dedfb98 |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | 62efc500-afa2-4e6e-9cae-77c35c84d8f0 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | a4d73677-0539-477f-b6fb-b13c25394f74 |  | checkpoint | Seq # 7 - Standard Grout
checkpoint-status | 2120b468-8fc6-4e79-8290-39edf260e00a |  | checkpoint | Seq # 8 - Floor cover Trim. L angle Trim and expansion joints
checkpoint-status | 23c14652-bb32-4356-bc54-c1cdc503bd42 |  | checkpoint | Seq # 9 - Silicone
checkpoint-status | e59b2bfb-0b94-4214-9ac0-0b219bf9c5df |  | checkpoint | Seq # 10 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | f7cd2671-263c-4d39-b5e2-7a195fdca77c |  | checkpoint | Seq # 11 - Floor Finish Protection / Ramboard
checkpoint-status | 82a61af2-8079-4af8-a280-09f495e8db43 |  | checkpoint | Seq # 12 - Handover
checklist-flat | 8b2456ec-7cef-4087-abae-fc4b539a22bc |  | checklist | Basement - Pool Area |  |  |  |  | Yes | Basement - Pool Area | fb3f5496-07a9-437a-8f80-3a45e784fb5c
checkpoint-status | 9f3bf116-0b97-4dcc-9573-7a9d2953706e |  | checkpoint | Pre start - Area tidy and Accessable- Free from any foreign objects
checkpoint-status | d3e83210-978f-4f85-8867-69816da48ac8 |  | checkpoint | Pool Area ready for tiling work
checkpoint-status | f03c6fb1-0596-4f6b-baf9-6f90f0fefd2a |  | checkpoint | Seq # 1 - Substrate Prepration
checkpoint-status | c248018d-9b76-4182-94fc-ad6c8b4ea0a0 |  | checkpoint | Seq # 2 - Screeding
checkpoint-status | a960d800-f6f2-47e8-aeee-c4c1934900e8 |  | checkpoint | Seq # 3 - Levelling
checkpoint-status | 23e43daf-fba6-4235-9520-2b74cd342a6f |  | checkpoint | Seq # 4 - Regupol 4515 Acoustic Under Lay
checkpoint-status | b7519332-7d79-4d6f-a9ca-8988a8b387c8 |  | checkpoint | Seq # 5 - Floor Tiling
checkpoint-status | 369969fb-13d0-4b05-b3a2-db4c8c035af8 |  | checkpoint | Seq # 6 - Wall Tiling
checkpoint-status | ae82ed68-f2e6-4d33-a3cc-a66a86c7443f |  | checkpoint | Seq # 7 tile install to Skimmers
checkpoint-status | e431d774-32ba-451b-b7a2-a3a13a2a9926 |  | checkpoint | Seq # 8 - Stair tread and riser tiling
checkpoint-status | 54c3a02f-7e05-4a77-90c1-69904c443ab3 |  | checkpoint | Seq# 9 - Pool Coping
checkpoint-status | ae2957d8-5799-4383-bfd4-c9fa8084f5e9 |  | checkpoint | Seq # 10 - Epoxy Grout
checkpoint-status | 5dc0d0ed-8aa8-4700-ac4a-1fdfc6695a42 |  | checkpoint | Seq # 11 - Floor cover Trim. L angle Trim
checkpoint-status | b84da8da-7d31-4ffe-8759-010d01a85480 |  | checkpoint | Seq # 12 - Silicon
checkpoint-status | 18bfb74f-c758-4718-9afe-0d2f408d2589 |  | checkpoint | Seq # 13 - Final Finish / Cleaning / All tools and equipment packup
checkpoint-status | 3222ec3f-1c59-4047-a1af-dddc5fa6977d |  | checkpoint | Seq # 14 - Floor Finish Protection / Ramboard
checkpoint-status | fadadb7b-0fde-4470-8a49-6e3e870b0a69 |  | checkpoint | Seq # 15 - Handover