## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Window Checklist |  |  |  |  | Yes | Window Checklist | 1204beb3-7bf6-470f-98f5-334bde8730ef
checkpoint-group |  |  | section | Subframe installation
checkpoint-status |  |  | checkpoint | subframe material delivered to site free of defects
checkpoint-status |  |  | checkpoint | Check Grid references, setouts etc for correct installation location
checkpoint-status |  |  | checkpoint | Opening accepted as "ready for subframe installation" i.e. waterproofed, water stop angles, plinths etc
checkpoint-status |  |  | checkpoint | Reference shop drawings for correct sub framing material, fixing type & spacings and FFLs where there is zero clearance to sliding doors.
checkpoint-status |  |  | checkpoint | Overseal sill fixings, install end dams and carry out flood test
checkpoint-group |  |  | section | Frame Installation
checkpoint-status |  |  | checkpoint | Frames are free of defects with protection tape applied
checkpoint-status |  |  | checkpoint | Handing's of Unit are correct as per shop drawing
checkpoint-status |  |  | checkpoint | Drainage weep holes are free of any debris
checkpoint-status |  |  | checkpoint | Ensure frames to be assembled onsite are square, sealed and all components are installed.
checkpoint-group |  |  | section | Glass
checkpoint-status |  |  | checkpoint | Ensure Glass is correct type, thickness etc and free from defects( report glass defects to the PM immediately)
checkpoint-status |  |  | checkpoint | Ensure glass and frame components are free from contaminating material/substances
checkpoint-status |  |  | checkpoint | Setting blocks installed to support full weight of glass
checkpoint-status |  |  | checkpoint | Gaskets and seals are installed where needed
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | General inspection to ensure Units are clean, operational and free from defects.
checkpoint-status |  |  | checkpoint | Flyscreens, flydoors, security doors installed where applicable
checkpoint-status |  |  | checkpoint | Decals installed where applicable
checklist-flat |  |  | checklist | Floor Plan |  |  |  |  | Yes | Floor Plan | a6997690-9a6e-474a-8c43-7cdfd95d7c02
checkpoint-status |  |  | checkpoint | Floor Plan attached