## Structure
Project Name | Onehunga Mall Club (OMC)
Checklists
Site QA
| Underslab |  |  | Underslab QA
First Fix
Ground Floor
|  |  | Ground Floor Part A | Plumbing Preline QA
|  |  | Ground Floor Part B | Plumbing Preline QA
|  |  | Ground Floor Part C | Plumbing Preline QA
|  |  | Ground Floor Part D | Plumbing Preline QA
First Floor
|  |  | Ground Floor Part A | Plumbing Preline QA
|  |  | Ground Floor Part B | Plumbing Preline QA
|  |  | Ground Floor Part C | Plumbing Preline QA
|  |  | Ground Floor Part D | Plumbing Preline QA
Second Floor
|  |  | Corridor / | Plumbing Preline QA
|  |  | Unit 2.1 | Plumbing Preline QA
|  |  | Unit 2.2 | Plumbing Preline QA
|  |  | Unit 2.3 | Plumbing Preline QA
|  |  | Unit 2.4 | Plumbing Preline QA
|  |  | Unit 2.5 | Plumbing Preline QA
|  |  | Unit 2.6 | Plumbing Preline QA
|  |  | Unit 2.7 | Plumbing Preline QA
|  |  | Unit 2.8 | Plumbing Preline QA
|  |  | Unit 2.9 | Plumbing Preline QA
|  |  | Unit 2.10 | Plumbing Preline QA
|  |  | Unit 2.11 | Plumbing Preline QA
|  |  | Unit 2.12 | Plumbing Preline QA
|  |  | Unit 2.13 | Plumbing Preline QA
|  |  | Unit 2.14 | Plumbing Preline QA
|  |  | Unit 2.15 | Plumbing Preline QA
|  |  | Unit 2.16 | Plumbing Preline QA
|  |  | Unit 2.17 | Plumbing Preline QA
Third Floor
|  |  | Corridor | Plumbing Preline QA
Unit 3.1
|  |  | Unit 3.2 | Plumbing Preline QA
|  |  | Unit 3.3 | Plumbing Preline QA
|  |  | Unit 3.4 | Plumbing Preline QA
|  |  | Unit 3.5 | Plumbing Preline QA
|  |  | Unit 3.6 | Plumbing Preline QA
|  |  | Unit 3.7 | Plumbing Preline QA
|  |  | Unit 3.8 | Plumbing Preline QA
|  |  | Unit 3.9 | Plumbing Preline QA
|  |  | Unit 3.10 | Plumbing Preline QA
|  |  | Unit 3.11 | Plumbing Preline QA
|  |  | Unit 3.12 | Plumbing Preline QA
|  |  | Unit 3.13 | Plumbing Preline QA
|  |  | Unit 3.14 | Plumbing Preline QA
|  |  | Unit 3.15 | Plumbing Preline QA
|  |  | Unit 3.16 | Plumbing Preline QA
|  |  | Unit 3.17 | Plumbing Preline QA
Fourth Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 4.1 | Plumbing Preline QA
|  |  | Unit 4.2 | Plumbing Preline QA
|  |  | Unit 4.3 | Plumbing Preline QA
|  |  | Unit 4.4 | Plumbing Preline QA
|  |  | Unit 4.5 | Plumbing Preline QA
|  |  | Unit 4.6 | Plumbing Preline QA
|  |  | Unit 4.7 | Plumbing Preline QA
|  |  | Unit 4.8 | Plumbing Preline QA
|  |  | Unit 4.9 | Plumbing Preline QA
|  |  | Unit 4.10 | Plumbing Preline QA
|  |  | Unit 4.11 | Plumbing Preline QA
|  |  | Unit 4.12 | Plumbing Preline QA
|  |  | Unit 4.13 | Plumbing Preline QA
|  |  | Unit 4.14 | Plumbing Preline QA
|  |  | Unit 4.15 | Plumbing Preline QA
|  |  | Unit 4.16 | Plumbing Preline QA
|  |  | Unit 4.17 | Plumbing Preline QA
Fifth Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 5.1 | Plumbing Preline QA
|  |  | Unit 5.2 | Plumbing Preline QA
|  |  | Unit 5.3 | Plumbing Preline QA
|  |  | Unit 5.4 | Plumbing Preline QA
|  |  | Unit 5.5 | Plumbing Preline QA
|  |  | Unit 5.6 | Plumbing Preline QA
|  |  | Unit 5.7 | Plumbing Preline QA
|  |  | Unit 5.8 | Plumbing Preline QA
|  |  | Unit 5.9 | Plumbing Preline QA
|  |  | Unit 5.10 | Plumbing Preline QA
|  |  | Unit 5.11 | Plumbing Preline QA
|  |  | Unit 5.12 | Plumbing Preline QA
|  |  | Unit 5.13 | Plumbing Preline QA
|  |  | Unit 5.14 | Plumbing Preline QA
|  |  | Unit 5.15 | Plumbing Preline QA
|  |  | Unit 5.16 | Plumbing Preline QA
|  |  | Unit 5.17 | Plumbing Preline QA
Sixth Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 6.1 | Plumbing Preline QA
|  |  | Unit 6.2 | Plumbing Preline QA
|  |  | Unit 6.3 | Plumbing Preline QA
|  |  | Unit 6.4 | Plumbing Preline QA
|  |  | Unit 6.5 | Plumbing Preline QA
|  |  | Unit 6.6 | Plumbing Preline QA
|  |  | Unit 6.7 | Plumbing Preline QA
|  |  | Unit 6.8 | Plumbing Preline QA
|  |  | Unit 6.9 | Plumbing Preline QA
|  |  | Unit 6.10 | Plumbing Preline QA
|  |  | Unit 6.11 | Plumbing Preline QA
|  |  | Unit 6.12 | Plumbing Preline QA
|  |  | Unit 6.13 | Plumbing Preline QA
|  |  | Unit 6.14 | Plumbing Preline QA
|  |  | Unit 6.15 | Plumbing Preline QA
|  |  | Unit 6.16 | Plumbing Preline QA
|  |  | Unit 6.17 | Plumbing Preline QA
Seventh Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 7.1 | Plumbing Preline QA
|  |  | Unit 7.2 | Plumbing Preline QA
|  |  | Unit 7.3 | Plumbing Preline QA
|  |  | Unit 7.4 | Plumbing Preline QA
|  |  | Unit 7.5 | Plumbing Preline QA
|  |  | Unit 7.6 | Plumbing Preline QA
|  |  | Unit 7.7 | Plumbing Preline QA
|  |  | Unit 7.8 | Plumbing Preline QA
|  |  | Unit 7.9 | Plumbing Preline QA
|  |  | Unit 7.10 | Plumbing Preline QA
|  |  | Unit 7.11 | Plumbing Preline QA
|  |  | Unit 7.12 | Plumbing Preline QA
|  |  | Unit 7.13 | Plumbing Preline QA
|  |  | Unit 7.14 | Plumbing Preline QA
|  |  | Unit 7.15 | Plumbing Preline QA
|  |  | Unit 7.16 | Plumbing Preline QA
|  |  | Unit 7.17 | Plumbing Preline QA
Second Fix
Ground Floor
|  |  | Ground Floor Part A | Plumbing Preline QA
|  |  | Ground Floor Part B | Plumbing Preline QA
|  |  | Ground Floor Part C | Plumbing Preline QA
|  |  | Ground Floor Part D | Plumbing Preline QA
First Floor
|  |  | Ground Floor Part A | Plumbing Preline QA
|  |  | Ground Floor Part B | Plumbing Preline QA
|  |  | Ground Floor Part C | Plumbing Preline QA
|  |  | Ground Floor Part D | Plumbing Preline QA
Second Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 2.1 | Plumbing Preline QA
|  |  | Unit 2.2 | Plumbing Preline QA
|  |  | Unit 2.3 | Plumbing Preline QA
|  |  | Unit 2.4 | Plumbing Preline QA
|  |  | Unit 2.5 | Plumbing Preline QA
|  |  | Unit 2.6 | Plumbing Preline QA
|  |  | Unit 2.7 | Plumbing Preline QA
|  |  | Unit 2.8 | Plumbing Preline QA
|  |  | Unit 2.9 | Plumbing Preline QA
|  |  | Unit 2.10 | Plumbing Preline QA
|  |  | Unit 2.11 | Plumbing Preline QA
|  |  | Unit 2.12 | Plumbing Preline QA
|  |  | Unit 2.13 | Plumbing Preline QA
|  |  | Unit 2.14 | Plumbing Preline QA
|  |  | Unit 2.15 | Plumbing Preline QA
|  |  | Unit 2.16 | Plumbing Preline QA
|  |  | Unit 2.17 | Plumbing Preline QA
Third Floor
|  |  | Corridor | Plumbing Preline QA
Unit 3.1
|  |  | Unit 3.2 | Plumbing Preline QA
|  |  | Unit 3.3 | Plumbing Preline QA
|  |  | Unit 3.4 | Plumbing Preline QA
|  |  | Unit 3.5 | Plumbing Preline QA
|  |  | Unit 3.6 | Plumbing Preline QA
|  |  | Unit 3.7 | Plumbing Preline QA
|  |  | Unit 3.8 | Plumbing Preline QA
|  |  | Unit 3.9 | Plumbing Preline QA
|  |  | Unit 3.10 | Plumbing Preline QA
|  |  | Unit 3.11 | Plumbing Preline QA
|  |  | Unit 3.12 | Plumbing Preline QA
|  |  | Unit 3.13 | Plumbing Preline QA
|  |  | Unit 3.14 | Plumbing Preline QA
|  |  | Unit 3.15 | Plumbing Preline QA
|  |  | Unit 3.16 | Plumbing Preline QA
|  |  | Unit 3.17 | Plumbing Preline QA
Fourth Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 4.1 | Plumbing Preline QA
|  |  | Unit 4.2 | Plumbing Preline QA
|  |  | Unit 4.3 | Plumbing Preline QA
|  |  | Unit 4.4 | Plumbing Preline QA
|  |  | Unit 4.5 | Plumbing Preline QA
|  |  | Unit 4.6 | Plumbing Preline QA
|  |  | Unit 4.7 | Plumbing Preline QA
|  |  | Unit 4.8 | Plumbing Preline QA
|  |  | Unit 4.9 | Plumbing Preline QA
|  |  | Unit 4.10 | Plumbing Preline QA
|  |  | Unit 4.11 | Plumbing Preline QA
|  |  | Unit 4.12 | Plumbing Preline QA
|  |  | Unit 4.13 | Plumbing Preline QA
|  |  | Unit 4.14 | Plumbing Preline QA
|  |  | Unit 4.15 | Plumbing Preline QA
|  |  | Unit 4.16 | Plumbing Preline QA
|  |  | Unit 4.17 | Plumbing Preline QA
Fifth Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 5.1 | Plumbing Preline QA
|  |  | Unit 5.2 | Plumbing Preline QA
|  |  | Unit 5.3 | Plumbing Preline QA
|  |  | Unit 5.4 | Plumbing Preline QA
|  |  | Unit 5.5 | Plumbing Preline QA
|  |  | Unit 5.6 | Plumbing Preline QA
|  |  | Unit 5.7 | Plumbing Preline QA
|  |  | Unit 5.8 | Plumbing Preline QA
|  |  | Unit 5.9 | Plumbing Preline QA
|  |  | Unit 5.10 | Plumbing Preline QA
|  |  | Unit 5.11 | Plumbing Preline QA
|  |  | Unit 5.12 | Plumbing Preline QA
|  |  | Unit 5.13 | Plumbing Preline QA
|  |  | Unit 5.14 | Plumbing Preline QA
|  |  | Unit 5.15 | Plumbing Preline QA
|  |  | Unit 5.16 | Plumbing Preline QA
|  |  | Unit 5.17 | Plumbing Preline QA
Sixth Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 6.1 | Plumbing Preline QA
|  |  | Unit 6.2 | Plumbing Preline QA
|  |  | Unit 6.3 | Plumbing Preline QA
|  |  | Unit 6.4 | Plumbing Preline QA
|  |  | Unit 6.5 | Plumbing Preline QA
|  |  | Unit 6.6 | Plumbing Preline QA
|  |  | Unit 6.7 | Plumbing Preline QA
|  |  | Unit 6.8 | Plumbing Preline QA
|  |  | Unit 6.9 | Plumbing Preline QA
|  |  | Unit 6.10 | Plumbing Preline QA
|  |  | Unit 6.11 | Plumbing Preline QA
|  |  | Unit 6.12 | Plumbing Preline QA
|  |  | Unit 6.13 | Plumbing Preline QA
|  |  | Unit 6.14 | Plumbing Preline QA
|  |  | Unit 6.15 | Plumbing Preline QA
|  |  | Unit 6.16 | Plumbing Preline QA
|  |  | Unit 6.17 | Plumbing Preline QA
Seventh Floor
|  |  | Corridor | Plumbing Preline QA
|  |  | Unit 7.1 | Plumbing Preline QA
|  |  | Unit 7.2 | Plumbing Preline QA
|  |  | Unit 7.3 | Plumbing Preline QA
|  |  | Unit 7.4 | Plumbing Preline QA
|  |  | Unit 7.5 | Plumbing Preline QA
|  |  | Unit 7.6 | Plumbing Preline QA
|  |  | Unit 7.7 | Plumbing Preline QA
|  |  | Unit 7.8 | Plumbing Preline QA
|  |  | Unit 7.9 | Plumbing Preline QA
|  |  | Unit 7.10 | Plumbing Preline QA
|  |  | Unit 7.11 | Plumbing Preline QA
|  |  | Unit 7.12 | Plumbing Preline QA
|  |  | Unit 7.13 | Plumbing Preline QA
|  |  | Unit 7.14 | Plumbing Preline QA
|  |  | Unit 7.15 | Plumbing Preline QA
|  |  | Unit 7.16 | Plumbing Preline QA
|  |  | Unit 7.17 | Plumbing Preline QA

## Checklists
type | name | values
checklist | Plumbing Preline QA
section | Preline QA
checkpoint | Area Accessible
checkpoint | Service
select | type | Hot Water, Gas Service, Vent, Condensate, Cold Water, Flushing Water, Soil/Waste, Other
text | If others
checkpoint | Pipework securely clipped
checkpoint | Lagging installed
checkpoint | Seismic restraints installed
checkpoint | Fire collars fitted
checkpoint | Penetrations sealed through floors
checkpoint | Outlet positions checked for
bool | Location
bool | Height
checkpoint | Heights – Finished floor height verified with Main Contractor
text | mm
checkpoint | Projection of valves, shower mixers and the like correct for second fix
checkpoint | Nogs installed for second fix installation
checkpoint | Pipework identification installed if required
section | Testing
checkpoint | Hot Water
text | Specified to | Kpa
text | Test Pressure | Kpa
text | Duration
checkpoint | Cold Water
text | Specified to | Kpa
text | Test Pressure | Kpa
text | Duration
checkpoint | Soil/Waste Pipes
text | Specified to | Kpa
text | Test Pressure | Kpa
text | Duration
checkpoint | Vent Pipes
text | Specified to | Kpa
text | Test Pressure | Kpa
text | Duration
checkpoint | Gas Services
text | Specified to | Kpa
text | Test Pressure | Kpa
text | Duration
checkpoint | Other
text | specify other
text | Specified to | Kpa
text | Test Pressure | Kpa
text | Duration
section | Handover
checkpoint | Area left clean and tidy
checkpoint | Local Authority Verification
holdpoint | Plumbing inspection complete and passed as satisfactory
checkpoint | DL Good Verification
holdpoint | Plumbing Complete and ready for lining
checkpoint | Main Contractor verification
holdpoint | Plumbing Complete and ready for lining
checklist | Plumbing Fitoff QA
section | Wash Hand Basin
checkpoint | Basin level and secure
checkpoint | Waste connection watertight, plug supplied
checkpoint | Water connection watertight, tap secure
checkpoint | Hot & Cold waterflow satisfactory, no water hammer
section | Toilet
checkpoint | Securely fixed, silicone at floor
checkpoint | Flush and cistern fill operation checked
checkpoint | Water connection watertight – cold water
section | Shower
checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint | Waste clear
checkpoint | Cover plate fixed securely
section | Bath/Shower
checkpoint | Waste clear, plug installed
checkpoint | Divertor operation working (where applicable)
checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint | Cover plate/spout fixed securely
checkpoint | FWG
checkpoint | Grate flush with floor or slightly below
checkpoint | Waste clear of debris
section | Amenity Areas / Kitchens etc
checkpoint | Hot & Cold waterflow satisfactory, no water hammer
checkpoint | Water connection watertight, tap secure
checkpoint | Waste connection watertight
checkpoint | Dishwasher connection watertight
checkpoint | Wastemaster connection watertight
checkpoint | Overflow connection watertight
checkpoint | Waste clear, plug installed
section | HWC
checkpoint | Seismic Restraints installed
checkpoint | Expansion valves operation checked
checkpoint | Pipework securely fixed
checkpoint | Waste connection watertight
checkpoint | Tempering valve set correctly – water temperature checked
section | Handover
checkpoint | Area left clean and tidy
checkpoint | DL Good Verification
holdpoint | Plumbing Complete and ready for lining
checkpoint | Main Contractor verification
holdpoint | Plumbing Complete and ready for lining
checklist | Underslab QA
section | Pipework
checkpoint | Service
select | Service being checked | Stormwater, Waste Water, Gas, Water supply, others
text | If others
checkpoint | Pipework Material as specified/scheduled/drawn
checkpoint | Grid lines and fitting dimensions confirmed
checkpoint | Drain invert checked
checkpoint | Gully position checked
checkpoint | Floor levels established
checkpoint | Falls checked
checkpoint | Drainlayer/Plumber interface Points established
checkpoint | Penetrations co-ordinated with main contractor
checkpoint | Pipework backfilled correctly
checkpoint | Identification strip installed if required
checkpoint | Open ends of pipework capped off to prevent dirt ingress
checkpoint | Work completed and photos attached
section | Testing
checkpoint | Cold Water
text | Specified to
text | Test Pressure
text | Duration
checkpoint | Waste water
text | Specified to
text | Test Pressure
text | Duration
checkpoint | Gas Services
text | Specified to
text | Test Pressure
text | Duration
checkpoint | Others
text | Specified to
text | Test Pressure
text | Duration
section | Handover
checkpoint | Area left clean and tidy
checkpoint | Local Authority Verification
label | Plumbing inspection complete and passed as satisfactory
checkpoint | DL Good Verification
label | Plumbing Complete and ready for backfill/ concrete pour
checkpoint | Main Contractor verification