## Sheet1
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Strip Out Works checklist
checkpoint | Services Isolation Complete for this section of works
checkpoint | Protection of remaining items
checkpoint | Non-friable Asbestos Removal Complete
checkpoint | Friable Asbestos Removal Complete
checkpoint | Defit Tenancy - Removal of all joinery, doors, furniture, partitions
button | Is there reason to believe there are load bearing elements? | Yes,No
checkpoint | Walls - Remove to correct height as outlined by scope/BuildCorp
checkpoint | Ceilings - Greencap to mark out extent of mould. Confirm removed by Delta with before and after photos.
button | Walls - Are the studs timber or steel? | Timber,Steel
checkpoint | Only if timber - Take photo, inform BuildCorp, gain approval to remove - attach BuildCorp signature below
checkpoint | Shopfront - Greencap/BuildCorp to confirm extent of demolition. Take photo to confirm marking of extent - attach BuildCorp signature below
button | Flooring - Are the floors timber or tiles? Timber flooring can be removed with a photo taken upon completion - attach BuildCorp signature below | Timber,Tiles
checkpoint | Only if tiles - Take photo, inform BuildCorp, gain approval to remove/leave.
checkpoint | Removal of subfloor services. Concrete scanning to be completed before sawcutting - attach Delta signature below
checkpoint | Service in Floor - Greencap to confirm if conduit is to be removed - attach Greencap signature below
checkpoint | Builders Clean complete
checkpoint | Is all of Delta's scope complete and ready to handover for decontamination? Attach BuildCorp signature below
checklist-flat | Decontamination Works checklist
checkpoint | Containment of work complete
checkpoint | Corvex have installed mould remediation plant - HEPA Filtration
checkpoint | Remediation process - Non-porous materials should be cleaned using the 'sandwich technique'. Confirm completed
checkpoint | Remediation process - Semi-porous and porous materials should be removed at least 300mm beyond visibly affected sections. Confirm completed
checkpoint | Is waste material being suitably bagged and removed from the work area as per Greencap Scope of Works - attach Greencap signature below
checkpoint | Inspection - Interim evaluations (PRE) to be completed by Greencap - attach Greencap signature below
checkpoint | Inspection - Post-Remediation Verification to be completed by Greencap. Greencap to confirm results have passed - attach Greencap signature below
button | Are antimicrobial treatment required in these works?
checkpoint | If required, antimicrobial treatment complete
checkpoint | Have Delta completed their decontamination works in the area highlighted by this ITP? - attach Greencap signature below
checklist-flat | Pre-construction Works checklist
checkpoint | Delta Management Plans submitted and approved
checkpoint | Delta SWMS submitted and approved
checkpoint | BuildCorp and Delta inductions completed for all personnel
checkpoint | Paper based ITP uploaded - attach below
checkpoint | Delta is approved to begin construction - BuildCorp and Delta signatures required - attach below

## Sheet2
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Strip Out Works checklist
checkpoint | Services Isolation Complete for this section of works
checkpoint | Protection of remaining items
checkpoint | Non-friable Asbestos Removal Complete
checkpoint | Friable Asbestos Removal Complete
checkpoint | Defit Tenancy - Removal of all joinery, doors, furniture, partitions
button | Is there reason to believe there are load bearing elements? | Yes,No
checkpoint | Walls - Remove to correct height as outlined by scope/BuildCorp
checkpoint | Ceilings - Greencap to mark out extent of mould. Confirm removed by Delta with before and after photos.
button | Walls - Are the studs timber or steel? | Timber,Steel
checkpoint | Only if timber - Take photo, inform BuildCorp, gain approval to remove - attach BuildCorp signature below
checkpoint | Shopfront - Greencap/BuildCorp to confirm extent of demolition. Take photo to confirm marking of extent - attach BuildCorp signature below
button | Flooring - Are the floors timber or tiles? Timber flooring can be removed with a photo taken upon completion - attach BuildCorp signature below | Timber,Tiles
checkpoint | Only if tiles - Take photo, inform BuildCorp, gain approval to remove/leave.
checkpoint | Removal of subfloor services. Concrete scanning to be completed before sawcutting - attach Delta signature below
checkpoint | Service in Floor - Greencap to confirm if conduit is to be removed - attach Greencap signature below
checkpoint | Builders Clean complete
checkpoint | Is all of Delta's scope complete and ready to handover for decontamination? Attach BuildCorp signature below

## Sheet3
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Decontamination Works checklist
checkpoint | Containment of work complete
checkpoint | Corvex have installed mould remediation plant - HEPA Filtration
checkpoint | Remediation process - Non-porous materials should be cleaned using the 'sandwich technique'. Confirm completed
checkpoint | Remediation process - Semi-porous and porous materials should be removed at least 300mm beyond visibly affected sections. Confirm completed
checkpoint | Is waste material being suitably bagged and removed from the work area as per Greencap Scope of Works - attach Greencap signature below
checkpoint | Inspection - Interim evaluations (PRE) to be completed by Greencap - attach Greencap signature below
checkpoint | Inspection - Post-Remediation Verification to be completed by Greencap. Greencap to confirm results have passed - attach Greencap signature below
button | Are antimicrobial treatment required in these works?
checkpoint | If required, antimicrobial treatment complete
checkpoint | Have Delta completed their decontamination works in the area highlighted by this ITP? - attach Greencap signature below

## Sheet4
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Pre-construction Works checklist
checkpoint | Delta Management Plans submitted and approved
checkpoint | Delta SWMS submitted and approved
checkpoint | BuildCorp and Delta inductions completed for all personnel
checkpoint | Paper based ITP uploaded - attach below
checkpoint | Delta is approved to begin construction - BuildCorp and Delta signatures required - attach below