## Sheet1
Item | Basic Job Step | Acceptance Criteria | Applicable Standard | Method | Frequency | Verifying Records
1 | Pre-construction
1.1 | JSA signed off | Written Notification from Downer |  |  | Once | This ITP
1.2 | PIP, Piling Installation Plan Signed off | Written Notification from Downer |  |  | Once | This ITP
1.3 | Shop Drawings: Steel Detail Sheets | Written Notification from Downer | AS/NZS 1554.3, |  | Once, before fixing cages | This ITP
1.4 | Mix Designed signed off | Written Notification from Downer | Waka Kotahi Technical Specifications, BBO Specifications, Construction Drawing Set |  | Once | This ITP
2 | Construction of Piles
2.1 | Traffic Management | As shown in the Traffic Management Plan | Contract Documents | As per the TMP | Before mobilising piling equipment | This ITP
2.2 | Water and Power supply | 2 phase power, tab suitable for hose connections | Contract Documents | Visual | Before mobilising piling equipment | This ITP
2.3 | Working platform | Working Platform Certificate | Construction Drawings and PIP |  | Before moving piling equipment into position over pile location | This ITP or Working Platform Certificate
2.4 | Proof Bores | Engineer`s review and comment | Drawing 4001 rev.2 | Machine Drilling | Before drilling commences | Borehole Records
2.5 | Surveying Pile Centres | Placing the survey peg on the pile centre | Surveying industry standards | Survey | Before drilling commences | This ITP
2.6 | Sediment Ponds | Close to the piling locations, big enough to accommodate water coming from pile holes | Resource Content, PIP, |  | Before drilling commences | This ITP
2.7 | Reinforcing Cage | As per approved details sheet (item 1.3 of this ITP) For example lap length is minimum 1.8m for RB32, Grade 500 steel | Waka Kotahi Specifications, BBO, Specifications, Construction Drawings | Visual | Every Pile Cage | This ITP and Site Inspection Record Documents
2.8 | Drilling borehole and Pile socket length | Engineer`s Acceptance, sockets lengths as per approved drawing | Waka Kotahi Specifications, BBO Specifications, Construction Drawings, PIP, Drawing 4010 rev.2 | Visual | Every Pile | This ITP and Site Inspection Record Documents, Pile Card
2.9 | Placing pile cage and concreting | Pile cage identification tag matches with pile number. Downer confirms that cage orientation and position are under tolerances. | Waka Kotahi Specifications, BBO Specifications, Construction Drawings, PIP | Survey | Every pile | This ITP and Pile Card
2.10 | On site concrete testing | As per approved mix design (item 1.4 of this ITP) | PIP, Waka Kotahi Specifications, BBO | In-situ test | Each delivery | Concrete docket
2.11 | Removal of permanent casing | As per tolerances | Construction drawing 4010 Rev.2, Waka Kotahi Specifications, BBO | Survey | Every pile | Pile Card
2.12 | Concrete crush test | Minimum 40 MPa for 28 days samples (3 samples for 28 days and 1 sample for 7 days) | Waka Kotahi Specifications, BBO | Laboratory Crush Test | Each pouring day | Concrete test results
2.13 | Integrity testing | No major defects or flows | Drawing 4001 rev.2, PIT Specifications | Pile Integrity Testing | 50% of piles | Test results