## Table 1
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | TASK TIMING OR TASK FREQUNECY & MINIMUM REQUIREMENTS |  | TASK ASSIGNED TO | MEASURING DEVICES OR METHOD | ACCEPTANCE CRITERIA | QUALITY DOCUMENTATION | DOCUMENTATION RECEIVED |  | FREQUENCY ACHIEVED |  | ACCEPTANCE CRITERIA ACHIEVED
PRECONSTRUCTION HOLD POINTS | [8 empty] | Signature | Date | Signature | Date | Signature | Date
Agree QA Requirements | ITP | Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing | Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
Confirm Pricing for Additional Items | NTP | Pricing for additional items to be submitted to Design Project Manager and approved | Prior to construction handover meeting. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
Construction Handover Meeting | NTP | Meeting | Minimum 2 weeks prior to commencement of physical works. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
Physical works Programme | NTP | Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Bryan Crean and start and end dates to by updated in RAMM Contractor prior to physical works. | Minimum 10 working days prior to commencement of physical works. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
Quantity Review | NTP | Confirm construction set-out and drawings align with quantities provided in schedule of quantities | After construction set-out, prior to commencement of physical works. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
Existing Pavement Walkover | NTP | Visual Inspection of existing pavement | Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength. Min 24hr notice to be given prior to inspection. |  | Construction Project Manager | Eye, spray paint, mark-up on drawings | Confirmation received by Delivery Manager by scheduled task timing | Mark-up on drawings
MILLED SURFACE CONSTRUCTION (IN TIE IN AREAS)
Finished Level | TNZ F/1 11.2.2 | String line or equivalent | 20m centres each side, min 3 measurements across lane = 147 Measurements |  | Pavement subcontractor quality representative | Stringline, tape measure | +0mm / -30mm | Inspection checklist
Finished Level (post milled) |  | Visual inspection of milled surface | Site walkover between WestLink Delivery Manager and Construction Project Manager to ensure milled surface acceptability and compliance. Min 24hr notice to be given prior to |  | Construction Project Manager | Visual inspection | Confirmation received by Delivery Manager | Inspection checklist and photographs supplied
Compaction | TNZ F/1 10.5.1 | Proof Roll | 100% coverage |  | Pavement subcontractor quality representative | Smooth wheel roller with min loading 6259 kg/m width or large miller | ≤ 5mm | Inspection checklist
BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
Crushing Strength | TNZ M/4 3.3.1 | Crushing Resistance Test | 1 test per 10,000m3 (min 1 per source) - 1 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.10 | <10% fines passing 2.36mm under 130 KN load | IANZ Report
Weathering Quality | TNZ M/4 3.3.2 | Weathering Quality Index Test | 1 test per 10,000m3 (min 1 per source) - 1 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.11 | AA, AB, AC, BA, BB or CA | IANZ Report
Soaked CBR | TNZ M/4 3.3.3 | Remoulded soaked CBR | 1 test per 10,000m3 (min 1 per source) - 1 tests |  | IANZ accredited laboratory | Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15 | ≥ 80% | IANZ Report
Sand equivalent | TNZ M/4 4.2.1.1 | Sand equivalent | 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3 | 3 Tests | IANZ accredited laboratory | NZS4407 : 1991, Test 3.6 | ≥ 40 | IANZ Report
Broken Faces Content | TNZ M/4 4.2.2 | Broken face content |  | 3 Tests. n.b. not required if sourced from 100% crushed rock quarry | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.14 | ≥ 70% | IANZ Report
Particle size distribution | Design | Wet sieving test |  | 3 Tests (1 test must be from same sample as MDD/OMC test) | IANZ accredited laboratory | NZS4407 4407 : 1991, Test 3.8.1 | 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600µm 3 - 14 passing 300µm 0 - 10 passing 150µm 0 - 7 passing 75µm | IANZ Report
Solid Density | TNZ B/2 7.5 | Solid Density | 1 test per 5000m2 - 2 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.7 | report value only | IANZ Report
Determination of MDD & OWC | TNZ B/2 7.5 | 5 point compaction curve | 1 test per 5000m2 - 2 tests |  | IANZ accredited laboratory | NZS 4402 : 1986, Test 4.1.3 | report value only | IANZ Report
BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40 | [8 empty] | Signature | Date | Signature | Date | Signature | Date
Formation | TNZ B/2 7.7 | 3m straight edge or approved equivalent | 20m centres each side - 28 Tests |  | Pavement subcontractor quality representative | 3m straight edge, tape measure | +/- 10mm | Inspection checklist
Finished Level | TNZ B/2 5.1 | String line or equivalent | 20m centres each side - 28 Tests |  | Pavement subcontractor quality representative | Stringline, tape measure | +15mm / -5mm | Inspection checklist
Plateau Density Test | TNZ B/2 7.5 (b) | Plateau Density Test | 1 test minimum |  | IANZ accredited laboratory | NDM | report value only | IANZ Report
Compaction | TNZ B/2 7.6 | NDM | min 5 tests per lot (max lot size = 1,000m2) - 10 tests |  | IANZ accredited laboratory | NDM | Mean ≥ 98% MDD, Min ≥ 95%, Total voids ≤ 20% | IANZ Report
Degree of Saturation | TNZ B/2 12 | NDM | min 5 tests per lot (max lot size = 1,000m2) - 10 tests |  | IANZ accredited laboratory | NDM | < 60% (or 80% on consultation with the pavement designer) | IANZ Report
Surface Finish | TNZ B/2 7.8 | Visual Inspection | 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. Min 24hr notice to be given prior to inspection. |  | Pavement subcontractor quality representative | Stiff bristled broom, camera, eye | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which; • The large aggregate is • exposed to the surface; • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material; • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter. | Inspection checklist and photographs supplied electronically.
Ride Quality | Internal measure | Ride quality test to AG:AM/T002 | Within 12 months of first coat seal |  | Either by pavement subcontractor or by Westlink Asset Management team from latest HSD survey | inertial laser profiler or response-type roughness meter | no 100m moving average > 60 counts | Certified test report
BITUMEN - TO GAIN APPROVAL
Penetration | TNZ M/1 Table 1 | Penetration at 25°C, 100g, five seconds | 1 test |  | IANZ accredited laboratory | ASTM D5 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
Viscosity | TNZ M/1 Table 1 | Viscosity PaS at 60°C | 1 test |  | IANZ accredited laboratory | AS 2341.2 or ASM D2171 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
| TNZ M/1 Table 1 | Viscosity mm2/s at 135°C | 1 test |  | IANZ accredited laboratory | AS 2341.3 or ASM D2170 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
Flash Point | TNZ M/1 Table 1 | Flash point (Cleveland open cup), °C | 1 test |  | IANZ accredited laboratory | ASTM D92 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
Solubility | TNZ M/1 Table 1 | Solubility in Trichloroethylene, % or Solubility in Toluene, % | 1 test |  | IANZ accredited laboratory | ASTM D2042, AS 2341.8 | Complies with requirements for penetration grade as per TNZ M/01 Table 1 | Letter of compliance from NZTA
Rolling Thin Film | TNZ M/1 Table 1 | Rolling Thin Film Oven Test | 1 test |  | IANZ accredited laboratory | ASTM D2872 or AS 2341.10
Penetration | TNZ M/1 Table 1 | Penetration of residue, at 25°C, 100g, five seconds, % of original | 1 test |  | IANZ accredited laboratory | ASTM D5 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
Ductility | TNZ M/1 Table 1 | Ductility of residue, at 25°C, (metres) | 1 test |  | IANZ accredited laboratory | ASTM D113 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
SEALING CHIP MATERIAL TESTING
Crushing Strength | TNZ M/6 3.2 | Crushing Resistance Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.10 | <10% fines passing 2.36mm under 230 KN load | IANZ Test report
Weak Particles Test | TNZ M/6 3.4 | Australian Weak Particles Test | Only undertaken in cases of dispute |  | IANZ accredited laboratory | AS 1141.32-1995 | Maximum of 1% | IANZ Test report
Polished Stone Value | TNZ M/6 3.5 | Polished Stone Value Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality |  | Accredited PSV Testing Agency | BS 812: Part 114 | PSV Required = 43 | IANZ Test report
Cleanliness | TNZ M/6 4.1.1 | Cleanliness Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.9 | Grade 2 - 89 min Grade 3 - 87 min Grade 4 - 85 min | IANZ Test report
Size & Shape | TNZ M/6 4.1.2 | Size & Shape | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.13 | Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm | IANZ Test report
Broken Faces | TNZ M/6 4.1.2 | Broken Faces Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.14 | 98% with minimum two broken faces | IANZ Test report
Grading | TNZ M/6 4.2.2 | Grading | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.8 | Grade 5 100% passing 13.2mm 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm Grade 6 100% passing 9.5mm 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm | IANZ Test report
SEAL DESIGN
Seal design | TNZ P/3 | Seal design | 2 weeks Prior to sealing |  | Contractor's Quality Manager | report only | report only | Seal design
Seal design approval | Internal measure | Internal verification | 2 weeks Prior to sealing |  | Downer Surfacing Expert | report only | report only | Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
Surface Finish | TNZ B/2 7.8 | Visual Inspection | 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. |  | Sealing subcontractor quality representative | Stiff bristled broom, camera, eye | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which; • The large aggregate is • exposed to the surface; • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material; • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter. | Inspection checklist and photographs supplied electronically.
SEALING RECORDS
Blend sheet | Client request |  | On day of seal |  | Bitumen blending facility |  | Report value only | Blend sheet
Spray sheets | Client request |  | On day of seal |  | Sealing Manager |  | Report value only | Spray sheets