## HGS ITP
Inspection and Test Plan
ITP Nº : 1 | Kopaki Bridge Slope Reinforcement | Project No. 210021NZ01 |  |  | ITP Prepared By : | Andrew King | Site Engineer
[5 empty] | ITP Reviewed By : | Charles Sweeney | Design Manager
[5 empty] | ITP Approved By : | Adam Chapman | General Manager
[5 empty] | Revision : | 0
Title / Description : |  | Soil Nails, Tecco Mesh
Quality Objective to be met : |  | All inspections and tests required by the contract, codes and regulations are planned and carried out.
How will meeting the objective be demonstrated? |  | Checking and signing off against relevant items as the project progresses
Distribution : | Project Manager, Project Engineer, Site Supervisor, Designer, Client | Records Coordinator : | Shannon Greenfield - Site Supervisor
ITP Prepared By : | Andrew King | Attachments :
List of Inspections and Tests
A. Preliminary | [6 empty] | Sign and Date When Action Complete
Item Nº | Description | Frequency | Specification Reference | Responsible Person | Record Required | Notes | Signature | Date
A1 | Ensure design is complete and "Issued For Construction" (IFC) drawings are accurate, complete, and approved by GSI Engineer & GSI Management | Before issue to site | Job pack | GSI Project Manager | Job Pack | Hard copies on site
A2 | Confirm all material intended for use in the works comply with design specification, have been ordered, and will be available on site when required | Before site establishment | Job pack | GSI Construction Manager / Site Engineer | Job pack
A3 | Load test schedule, test locations and test sheets are reviewed and approved by GSI Engineer and Engineer to contract | Prior to start on site | NZTA 2226 TS | GSI Project Engineer | Engineer to contract agreement in writing | Hard copy of standard held on site
A4 | Ensure load testing equipment is calibrated and calibration certificates supplied to Engineer to contract for review. | Prior to start on site | NZTA 2226 TS | GSI Project Engineer | Engineer to contract receipt | Hard copy of standard held on site
A5 | Slope assessment completed and reviewed by GSI Project Manager | Prior to start on site | N/A | GSI Project Engineer | Slope assessment checksheet | Hard copy on site
A6 | Confirm site extents agreed with Engineer and aligns with general intent of the design | Prior to start on site | N/A | GSI Project Engineer | Written confirmation to design team
A7 | Sacrificial test nail number and locations agreed and approved by GSI PDE / BBO / Earthtec | Prior to start on site | N/A | GSI Project Manager | Engineer to contract agreement in writing
A8 | Pre-construction sign off - Subcontract agreement signed, TMP approved, all staff and subcontractors inducted , CMP reveiwed and in place . | Prior to start on site | N/A | GSI General Manager | Job pack signed | Document reviewed and signed off by site staff and required management .
A9 | Permit to Work/Excavate - Confirm location and extent of works, notify service authorities, locate underground services where applicable, notify Worksafe of notifiable works | Before commencing work | N/A | GSI Project Manager | Job pack signed
A10 | Plant - Ensure plant suitable for use on site and calibration up to date. Rig capable of reaching all anchor locations, sufficient wire rope and rig anchoring equipment. | Before commencing work | N/A | Site supervisor | Job pack signed
A11 | HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
B. Site Establishment | [6 empty] | Sign and Date When Action Complete
Item Nº | Description | Frequency | Specification Reference | Responsible Person | Record Required | Notes | Signature | Date
B1 | Check Erosion & Sediment Controls are in place and adequate | Before commencing work | Job pack | Site supervisor | Photos / drawings | Visual inspection
B2 | Establish lay down area and suitable protection of property (ply wood, tarps etc) and bunding around grout unit/refuelling areas as required. | At time of establishment | N/A | Site Supervisor | Photos. Note on Pre-Start form | Consider delivery of materials
B3 | Check slope stability, area is safe to work in for slope remediation crews (WAH permit in place) | Daily prior to accessing lower levels | N/A | Site Supervisor | Photos. Note on Pre-Start form | Install offset pegs
B4 | Notify tenants / land users below work site of intended work and likely duration. | At time of establishment | N/A | Site Supervisor | Note on Pre-Start form | Door knock and face to face discussion required.
B5 | Completed installation of approved rope access anchor points as required | At time of establishment | N/A | Site supervisor | Photos. Note on Pre-Start form
B6 | Before You Dig completed. Identify and mark location of any existing services including probing, potholing and survey as required. | At time of establishment | N/A | Project Engineer and Site supervisor | Written confirmation to client | Install offset pegs, mark on drawings
B7 | Site markout - GSI Engineer, GSI PDE and Engineer to contract to agree on nail and test nail set out plan. | Before commencing work | N/A | GSI Project Engineer & GSI PDE | Engineer to contract agreement in writing | Install offset pegs, mark on drawings
B8 | HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE | Before commencing work
C. Excavations/Slope trimming | [6 empty] | Sign and Date When Action Complete
Item Nº | Description | Frequency | Specification Reference | Responsible Person | Record Required | Notes | Signature | Date
C1 | Valid Permit to Dig/SWMS | Daily | N/A | Project Engineer | Permit signed and valid
C2 | Pre-start check on equipment | Daily | N/A | Site Supervisor | Daily Equipment Pre-start form completed by operator
C3 | Safety audit completed when trimming/scaling slope - not to impact people or property below slope | Daily | N/A | Site Supervisor | Aduit results sent to PM
C4 | Levels and extents of devegatation and slope trimming marked and checked. | Prior to excavating | Drawings | Project engineer and site supervisor | Photo
C5 | GSI Engineer / GSI PM to sign off on completed vegatation and slope trimming. | At completion of earthworks | N/A | GSI PDE and GSI PM | Confirm with client
C6 | HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE | Before commencing work
D. Soil Nails and Grouting | [6 empty] | Sign and Date When Action Complete
Item Nº | Description | Frequency | Specification Reference | Responsible Person | Record Required | Notes | Signature | Date
D1 | Pre-start check on equipment | Daily | N/A | Site Supervisor | Daily Equipment Pre-start form completed by operator
D2 | Valid Permit to Dig/SWMS | Daily | N/A | Site Supervisor | Permit signed by operator and Site Superivisor and valid
D3 | Confirm cement/water mix ratio including number bags cement needed versus water capacity of mixer | Prior to drilling | Confirm ratio / IFC drawings / Specification | Site Supervisor | Grout log | Engineer to contract to confirm in writing
D4 | Drill methodology approved by GSI PDE/GSI Engineer and Engineer to contract confirmed following review of proof test results | Prior to production nail installation | Engineer to contract | Project Engineer | Written confirmation designer | Engineer to contract to confirm in writing
D5 | HOLD POINT - Ensure soil nail setout is in accordance with the drawings and approved by BBO / Earthtec | Prior to drilling | Drawings | Project Manager / GSI PDE | Written confirmation to client
D6 | Confirm drill depth, angle and orientation of soil nails - per IFC drawings | Each nail | Drawings | Site Supervisor | Drill log | Mark on as-built drawings
D7 | Ensure grout sample cubes or cylinders are available and ready for use (4 per day of grouting) | Prior to drilling | GSI grout sampling procedure | Site Supervisor | Grout log | All GSI staff to review updated Grout Samplign SOP prior to start of works
D8 | Install sacrifical anchors: 1 x 9m anchor and 1 x 6m anchor with Grouted Bond Length of 4m ONLY. Anchors to be installed with 16mm tremmie line, with centralizers every 1.5m. Locations to be confirmed by GSI Engineer and Engineer to contract (per B7). | During drilling | NZTA 2226 TS (181220) | Project Engineer | Photo Test result sheet | Results to be reviewed by GSI Engineer and Engineer to contract
D9 | Drill logs (fully) complete, including hole ID, diameter and length of hole drilled - as well as geology i.e. colour, type (rock/soil), moisture (i.e. dry, slightly moist, wet). Esnure to stipulate which holes are to be used for test anchors - based on B7. | During drilling | NZTA 2226 TS (181220) | Project Engineer | Photo Test result sheet | Results to be reviewed by GSI Engineer and Engineer to contract
D10 | Anchor testing to follow NZTA 2226 TS test schedule at min 7 days after install. For both 6m and 9m anchors. Pullout Creep test per NZTA 2226 TS test schedule i.e. 60 min creep test at 110kN. If pullout has not occurred at 150kN, proceed to next load. Do not exceed 250kN. | During drilling | NZTA 2226 TS (181220) | Project Engineer | Photo Test result sheet | Results to be reviewed by GSI Engineer and Engineer to contract
D11 | HOLD POINT - NO WORK TO COMMENCE UNTIL SACRIFICAL TEST RESULTS REVIEWED BY ENGINEER | Before commencing work
D12 | Install 78 no Anchors, in a top down methodology, 18 x 9m RB32 (top row) Anchors, 58 x 6m RB32 anchors. Anchors to be installed with 16mm tremmie line, with centralizers every 1.5m. Suitability testing on 5% of installed nails to 150% design working load. 2 x 9m and 3 x 6m suitability anchors to have 1m temporary debonded length for suitability testing. Locations to be confirmed by GSI Engineer and Engineer to contract (per B7). | During drilling | Drawings/NZTA 2226 TS | Project Engineer | Photo Test result sheet | Results to be reviewed by GSI Engineer and Engineer to contract
D13 | HOLD POINT - NO WORK TO COMMENCE UNTIL SUITABILITY TEST RESULTS REVIEWED BY ENGINEER | Before commencing work
D14 | Acceptance testing on 25% of installed nails to 100% design working load | After Drilling | NZTA 2226 TS (181220) | Project Engineer | Photo Test result sheet | Results to be reviewed by Engineer to the contract and GSI Engineer
D15 | Grout sampling to follow relevant SOP i.e. tamping down in 1/3 lifts, and stored in supplied chilly bin after initial 12 hours of curing. Temperature in chilly bin is to remain as constant as practicable (avoid uneccesarily opening lid). | During drilling | GSI grout sampling procedures | Site Supervisor | Grout log
D16 | Grout samples to be delivered to the lab within 2 days of sampling, where practicable, or as soon as possible thereafter. | During drilling | GSI grout sampling procedures | Site Supervisor | Grout log
D17 | Grout mud balance testing - per relevant SOP | Per hour during grouting session | GSI grout sampling procedures | Site Supervisor | Grout log
D18 | Grout logs i.e. number of grout bags per hole and total. Volumes to be recorded for each sol nail anchor. Ensure nails are appropriately numbered with relevant ID. | Each grout session | N/A | Batching Operator and Project Engineer | Grout log
D19 | Grout top-up complete. Where necessary, dry pack grout behind plates where grout not in contact with plate. Ensure temporary debonded sections of acceptance test nails are topped up. Update grout logs with those test nails that have been topped up. | Each grout session | N/A | Site Supervisor | Photo
D20 | Soil nail sacrifical, suitability and acceptance tests complete (as above) - per IFC drawings/NZTA 2226 specification | 2 nails, 5% of nails (or min. 5), and 25% of nails | Drawings | Project Engineer | Test result sheets
D21 | HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE | Before commencing work
E. TECCO Mesh, Spider Plate and Bio Coir | [6 empty] | Sign and Date When Action Complete
Item Nº | Description | Frequency | Specification Reference | Responsible Person | Record Required | Notes | Signature | Date
E1 | Confirm extents of mesh to be installed | Prior to commencement | Drawing | GSI Project Engineer and Site Supervisor | Email to PM
E2 | Confirm that depressions for spike plates have been SUITABLY excavated around nail collars. | Daily | Manufacturers Guidelines | Site Supervisor | Photo
E3 | TECCO mesh installed as per manufacturers guidelines. Ensure wire ropes are installed on top and bottom edges of mesh and tensioned appropriately. | Daily | Manufacturers Guidelines | Site Supervisor | Photo
E4 | Cirtex Bio-Core installed as per manufacturers guidelines. | Daily | Manufacturers Guidelines | Site Supervisor | Photo
E5 | HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE | Before commencing work
F. Mesh Installation | [6 empty] | Sign and Date When Action Complete
Item Nº | Description | Frequency | Specification Reference | Responsible Person | Record Required | Notes | Signature | Date
F1 | Erosion control mat and slope protection mesh installed correctly | Each session | Drawings | Supervisor | Photo | Tecco mesh
F2 | Products fixed and connected in accordance with manufacturers requirements | Each session | Drawings | Supervisor | Photo | Photos
G. Sign-Off and QA deliverables | [6 empty] | Sign and Date When Action Complete
Item Nº | Description | Frequency | Specification Reference | Responsible Person | Record Required | Notes | Signature | Date
G1 | Drill and Grout logs | Daily | N/A | Site Supervisor | Drill and grout logs
G2 | Sacrificial, Suitability and Acceptance test nails | Per IFC drawings/NZTA 2226 TS | NZTA 2226 TS | Project Engineer | Test log sheets
G3 | Grout crushing test | 7, 14 and 28 day results | 30MPa at 28 days | Project Engineer | Test reults | 7 and 14 day results are indicative only
G4 | Photo records | Daily | N/A | Site Supervisor and Project Engineer | Photos
G5 | As-Built Drawings | Project Completion | N/A | Project Engineer | Updated Drawings
Close out | Sign and Date When Action Complete
Date | Position: Name: | Signature: | Date: | Notes
Project Engineer:
Project Manager:
Client:
Supervisor:
Construction Manager: