## 100 General Contract
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 100 - General |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
100 | General for Project
100.1 | Physically located all utility locations | Permit to work around services (Gas, Power, Fibre, etc.) | H | as required per section of works | Document Review | All services physically located | Permit attached or permit number noted | Contractor | Overhead power will be relocated by The Lines Company prior to possession of the Site for Separable Portion 2.
100.2 | Contract Document Signed | Ensure Contract is signed | H | at the Contract kickoff meeting | Document Issue | N/A | Issued with a NTC | Downer / BBO's Rep.
100.3 | "For Construction" Drawings Isssued | Ensure "For Construction" drawings are issued | H | at the Contract kickoff meeting | Document Issue | N/A | Issued with a NTC | Downer/BBO's Rep.
100.4 | Traffic Management Plan | Ensure TMP is approved and check that the requirements are fully understood by the STMS | H | every morning and/or when the TMP changes | Document and Physical works review | COPTTM | TMP from contractor | Contractor
100.5 | Design | Ensure that Design is approved and Drawings are the latest version | H | Prior to commencement | TNZ M/20; TNZ M/7; TNZ M/24 |  | Check Drawing register | Contractor | Drawing register maintained by BBO and e-mailed to contractor when revised drawings are issued
100.6 | Approved Consents | Is a copy of approved consent(s) available on site | H | Prior to commencement | Visual Inspection |  | This ITP | BBO's Rep.
100.7 | Pre-start meeting | Pre-start meeting to confirm work strategy and safety measures | H | Before commencing work each day | N/A | 100% attendance | Pre-start sign on register / site diary | BBO
100.8 | Contractor's methodology | Approval of Contractor's methodology | H | Prior to commencement | Document review | Methodology conforms with all relevant specifications | Methodology submitted via NTE | BBO's Rep. | Methodology submitted min. 7 working days and approval min. 3 working days prior to commencement
100.9 | Laydown area / stockpile sites | Site inspection | M | Prior to commencement | Visual Inspection | Approved by NZTA | Request for approval (RFA) via NTE | BBO's Rep. | RFA submitted min. 7 working days and approval min. 3 working days prior to commencement
100.10 | Weather | Assessment of forecast | H | Daily prior to and during works | Check local and national weather forcast services | No imminent rain or adverse weather conditions. Consideration of wind and project location/environment | Contractor's site diary | Contractor
100.11 | Environmental Protection | Site evaluation | M | Prior to commencement | Inspection | Supervisor assessment of conformance | Contractor's site diary | Contractor
100.12 | Precondition Surevy | Examine extent of the site | M | Prior to commencement | Inspection | Supervisor assessment of conformance | Contractor's site diary | Contractor | A precondition survey and report is to include, but is not limited to structures, road, rail, services, paved area, vegetation including weeds, fences, gates and farm paddocks condition generally within 10 metres of the extent of excavations, structural works or any laydown areas carried out by the Contractor on the Site and is specifically to include a survey of the State Highway 30 pavement, culverts and other structures and assets.
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 200 Earthworks
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - 12/08/2021
|  |  |  | Project: Kopaki Bridge Replacement |  |  |  |  | Date submitted: 12/08/2021
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 200 - Earthworks |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
200 | Setout, Materials and Preparation
200.1 | Earthworks methodology (prior to commencing site works) | Prepare earthworks construction methodology suitable for site (eg access, working areas, proximity to slopes, traffic and other site hazards, construction stages proposed) | H | NA | NA | N/A | Methodology | Contractor | Methodology to be provided to Engineer for review prior to commencing excavation on site.
200.2 | Material suitability (prior to bringing fill to site) | Confirm imported fill material suitability | H | As per Drawings and Specification | As per Drawings and Specification | As per Drawings and Specification | IANZ Report | Contractor | Results to be provided to Engineers Geotechnical Representative for review prior to commencing excavation on site.
200.3 | Mark out and approve | Set out and mark up of extent of earthworks | H | All earthworks areas | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
200.4 | Excavation to formation level (prior to fill placement) | Confirm excavations are suitably trimmed and benched. | H | All earthworks areas | TNZ F/1:1997 | Formation materials in accordance with design assumptions. | Contactor's Site Diary | Contractor | Joint walkover with Contractor and Engineers Geotechincal Representative.
200.5 | Suitability of excavation formation for compaction | Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill. | H | Test on a on a 10m grid / maximum lineal distance between tests is 10m | Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil and shear vane test for cohesive soil. | For approval by Engineer. Where forms Subgrade as per Pavement Design Drawings and ITP | Contractor's site diary | Contractor | Results to be provided to Engineers Geotechnical Representative for review prior to filling.
200.6 | Suitability of excavation formation for compaction | Confirm the excavated soils are adequate to support construction plant and allow compaction of engineered fill. | H | All earthworks areas | Proof roll or as agreed with Engineer | Formation soils do not heave and no significant visual deformation under wheel load | Contractor's site diary | Contractor | Where the excavation formation soils are not adequate a working platform (SIL Layer) or undercut of unsuitable soils may be required.
200.7 | Sediment Controls are in place for the particular section |  | M | once per section | Asbuilts completed | NA | Asbuilts | Contractor | Forward asbuilts to Taranaki Regional Council
Construction and Finshing (Granular Fill)
200.8 | Testing of placed material | Density of placed material | W | Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid | Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer | Minimum field density of 90% of maximum dry density (MDD) obtained by static compaction for the first 500mm above thestripped and prepared ground surface. | IANZ Report & Contractors Report | Contractor | Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
200.8 |  | Density of placed material | W | Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid | Nuclear Density Meter (NZS 4402:4.2.2 Heavy Compaction) or alternative agreed with Engineer | Minimum field density of 98% of maximum dry density (MDD) obtained by vibrating compaction from 500mm above thestripped and prepared ground surface. | IANZ Report | Contractor | Test results to be provided to the Engineers Geotechnical Representative for review. Prelim tests in conjunction with IANZ Lab, compared to Contractors NDM Results, provided results are consistently within 1% of IANZ, acceptance for Contractor to Report NDM's thereafter on mutual agreement. On request by ER
200.9 |  | Density of placed material | W | All Engineered Fill at 300mm lifts, 1 Test per 50m2/lift. | Scala Penetrometer (NZS 4402.6.5.2) for cohesionless soil. | Minimum CBR 10 as correlated against NDM's | Contractor's site diary | Contractor | Correlated against NDM's by "in field testing" Witnessed by Engineers Representative and signed off in daily diary
200.10. | Surface Finishing | Check geometry of the placed fill is in accordance with the design. | H | All earthworks area | Survey, TNZ F/1 1997 | Geometry is in accordance with design drawings (fill surface and batter slope profile, removal of any excess fill). All points within 30mm of a 3m straight edge with no points above design level. No ponding of water. | Suvey, Stringline dips @5 points across carriageway @ 20m spacings | Contractor | Joint walkover between Contractor and Engineers Representative.
Construction and Finshing (GAP Hardfill)
200.11 | Confirm GAP Hardfill Material | Hardfill Aggregates | M | 3 per source stockpile | PSD, Weathering Resistance, CBR, MDD OMC | NZTA Project Spec 2.2.10 | Certificate in contractor's site folder | Contractor | Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Produiction properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3
200.12 |  | Density of placed material | M | Unless otherwise in Specification or on Drawings, test every 300mm fill height on a 10m grid | Nuclear Density Meter (NZS 4407:2015 4.3) or alternative agreed with Engineer | Average field density of 92% of maximum dry density (MDD)with no readings below 90%. | IANZ Report | Contractor | By IANZ accredited lab
200.13 | Surface Finishing | Check geometry of the placed fill is in accordance with the design. | H | All earthworks area | Suvey, Stringline dips @5 points across carriageway @ 20m spacings | Geometry is in accordance with design drawings (fill surface and batter slope profile, removal of any excess fill). All points within 30mm of a 3m straight edge with no points above design level. No ponding of water. | Stringline Report | Contractor | Joint walkover between Contractor and Engineers Representative.
Construction and Finshing (Surcharge)
200.12 | Confirm Kopaki Cut to Waste Material | Density of placed material | M | Unless otherwise in Specification or on Drawings, test every 500mm fill height on a 10m grid | Nuclear Density Meter (NZS 4407:2015 4.3) or alternative agreed with Engineer | Average field (wet) density recorded of each layer and used to calculate surcharge depth. | Contractors Report | Contractor | By Contractor
200.13 | Confirm Acceptance of Surcharge | Check denisty and depth of surcharge fill is in accordance with the design (40 Kpa) | H | Field Density (wet) multiplied by depth of surcharge | Suvey, Stringline dips @3 points across carriageway @ 20m spacings | 40Kpa (minimum) of exerted force from surcharge at each chainage and in place for 3 months | Stringline Report | Contractor | Contractor to supply spreadsheet of surcharge depths and densities at 3 points for each 20m chainage.
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 300 Stormwater Drainage
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 300- Stormwater Drainage |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
300 | Setout, Materials and Preparation
300.1 | Mark out works | Set out and mark up proposed drainage features by surveyor | H | All drainage features | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
300.2 | Underground services | Identify and positively locate services | H | All drainage features | Hydoexcavation | N/A | Drawings | Contractor
300.3 | Precast Concrete Pipes | Contract to provide manufacturer dwgs of the proposed design for approval | H | 1 per culvert size/type | Supplier Producer Statement | NZS 4058:2007 | NTC / Site instruction | Contractor
300.4 | Precast headwall/wingwall units | Contract to provide manufacturer dwgs of the proposed sturcture design for approval | H | 1 per wingwall type | N/A | Engineer to review and approve proposed design | NTC / Site instruction | Contractor | This requirement acknowledges minor variances in manufacturer design details for precast wingwalls
Construction and Finshing
Stormwater Line 1- Ch 225m Kopaki Rd; 750mm Dia
300.5 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.6 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.7 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.8 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.9 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.10 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.11 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
Inlet 1-1 1400mmDia Standpipe with Scruffy Dome - Ch 220m Kopaki Rd
300.12 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.13 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.14 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.15 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Outlet 1-2 Precast Headwall- Ch 230m Kopaki Rd
300.16 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No target - Engineer to advise undercut requirements prior to installation | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.17 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.18 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.19 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Stormwater Line 2- Inlet 2.1 to SD 2.2 @ CH65 Kopaki Road - Bradcock Access Track ( Ø900mm)
300.20 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.21 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.22 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.23 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.24 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.25 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.26 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
Inlet 2-1 : Precast Headwall Bradcock Access Track ( Ø900mm)
300.27 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.28 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.29 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.30 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
SD2.2 Manhole/Standpipe with Scruffy Dome Bradcock Access Track ( Ø1650mm)
300.31 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No target - Engineer to advise undercut requirements prior to installation | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.32 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.33 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.34 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Stormwater Line 2 - SD 2-2 to Outlet 2-3 Kopaki Road (Ø900mm)
300.35 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.36 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.37 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.38 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.39 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.40 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.41 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
Outlet 2-3 : Precast Headwall Kopaki Road ( Ø900mm)
300.42 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.43 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.44 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.45 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Inlet 2-4 : Precast headwall/wingwall - CH 290 State Highway 30 (Ø1050mm)
300.46 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.47 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.48 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.49 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Stormwater Line 2 - Inlet 2-4 to Outlet 2-5 : Statehighway 30 (Ø1050mm)
300.50 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.51 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.52 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.53 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.54 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.55 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.56 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
Outlet 2-5 Precast headwall/wingwall : Statehighway 30 (Ø1050mm)
300.57 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.58 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.59 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.60 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Stormwater Line 3 : Inlet 3-1 to SD 3 -2 @ CH 410 Statehighway 30 (Ø750mm)
300.61 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.62 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.63 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.64 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.66 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.65 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.67 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
Inlet 3-1 : Precast headwall/wingwall - Statehiway 30 (Ø750mm)
300.68 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.69 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.70 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.71 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Outlet 3-2 Precast headwall/wingwall : Statehighway 30 (Ø750mm)
300.72 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.73 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.74 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.75 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Stormwater Line 4 : SD 4-1 to Outlet 4-2 - Culvert to Wetland Access Track (Ø750mm)
300.76 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.77 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.78 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.79 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.80 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.81 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.82 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
SD 4-1 Manhole/Standpipe with Scruffy Dome ( Ø1400mm)
300.83 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No target - Engineer to advise undercut requirements prior to installation | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.84 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.85 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.86 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Outlet 4-2 Precast headwall/wingwall : Access Track (Ø750mm)
300.87 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.88 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.89 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.90 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Stormwater Line 5 : SD 5-1 to Outlet 5-2 Culvet to SW Treatment Wetland (Ø600mm)
300.91 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.92 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.92 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.94 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.95 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.96 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.97 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
SD 5-1 Manhole/Standpipe with Scruffy Dome ( Ø1400mm)
300.98 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No target - Engineer to advise undercut requirements prior to installation | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.99 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.100 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >15 (CBR = 20). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.101 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Outlet 5-2 Precast headwall/wingwall : Swale line 1 (Ø600mm)
300.102 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.103 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.104 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.105 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Peers Adams /Kiwirail Access Culvert : (Ø450mm)
300.106 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.107 | Pipe bedding | Bedding | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.108 | Jointing of pipes | Jointing | M | Every Pipe Joint | Visual Inspection | In Accordance with section 5.2 of the Project Technical Spec. | Contractor's site diary | Contractor | Rubber rings to be mounted evenly and lined up truly concentric with pipe. Gap between spigot and shoulder to of pipes to be even and between 5mm and 10mm.
300.109 | Pipe haunching | Haunching | M | 1 per 5m trench | NZS 3725:2007 | In Accordance with HS2, Minumum haunching depth of 0.3D, CIV Value on compacted haunching >25 (CBR = 30). | Contractor's site diary | Contractor | PAP 7 material to be used.
300.110 | Trench backfill | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
300.111 | Visual Structural Inspection | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and spiggots | Contractor's site diary/Photo's | Contractor
300.112 | CCTV Inspection | Visual record of Existing works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction prior to Practicle Completion
Intet : Precast headwall/wingwall unit for Ø450mm.
300.113 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.114 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.115 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.116 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Outlet : Precast headwall/wingwall unit for Ø450mm.
300.117 | Determine Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or 1 per drainage structure | Scala Penetrometer (NZS 4402.6.5.2). | No Specific target - Suggest Engineer to advise undercut requirements prior to installation for any scala readings less than 3 blows per 100mm. | Contractor's site diary | Contractor | Seek design subgrade strength prior to commencement so expected subgrade strength is known.
300.118 | Structures (manholes, head walls etc.) | Visual inspection of concrete components | W | 1 per structure | Visual Inspection | No visible damage, especially around collars and joints | Contractor's site diary/Photo's | Contractor
300.119 | Structures (manholes, head walls etc.) | Bedding | M | 1 per 5m trench per 1m lift | NZS 3725:2007 | In Accordance with HS2, Minumum bedding depth of 150mm, CIV Value on top of compacted bedding >12 (CBR = 15). | Contractor's site diary | Contractor | GAP 65 to be used with a leveling coarse of PAP 7.
300.120 | Structures (manholes, head walls etc.) | Backfilling | M | 1 per 5m trench per 1m lift | Scala Penetrometer (NZS 4402.6.5.2). | In Accordance with section 6.2 of the Project Technical Spec. Scala no less than 18 blows/300mm (CBR = 15). | Contractor's site diary | Contractor | Clean Pumice Fill to be used
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 400 Rip Rap
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 400 - Rip Rap |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
400 | Setout, Materials and Preparation
400.1 | Mark out and approve | Set out and mark up of scour protection area | H | All locations scour protection is required | Visual Inspection | Engineer to confirm | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep.
400.2 | Confirm filter material | Contractor to provide manufacturers specificationfor proposed filter material | H | 1 per material type | N/A | Engineer to review and approve proposed material in accordance with Technical Specifications ( Section 7.1) | NTC / Site instruction | Contractor
400.3 | Confirm rip rap material | Confirm the supply of grading results for proposed rip rap material | M | 1 per material type | N/A | Engineer to review and approve proposed material in accordance with Project Technical Specification (Section 7.2) | Laboratory Test Results | Contractor | Laboratory test may be substitues for a visual inspection (if instructured by the Engineer)
Construction and Finshing
Void Fill Rip-Rap Placement @ Stormwater Line 1 : SHEET 2126 (300mmx 14.5m)
400.4 | Base Soil | Prepared slope or channel bottom | W | All locations scour protection is required | Visual Inspection | No significant visual deformation | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.5 | Rip Rap Placement | Location - Excavation depth - assembly - Installed length | H | 1 check per structure | Visual Inspection | Conform to Specification | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.6 | Visual Structural Inspection | Visual inspection of Void Filled rip rap structutre | W | 1 per structure | Visual Inspection | Conform to Approved Drawings & Specification | Contractor's site diary/Photo's | Contractor
400.7 | Final Inspection | Engineer to inspect the final works | H | All locations scour protection is required | Visual Inspection | The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
Void Fill Rip-Rap Placement @ Stormwater Line 2 : SHEET 2128, 2129 and 2127
400.4 | Base Soil | Prepared slope or channel bottom | W | All locations scour protection is required | Visual Inspection | No significant visual deformation | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.4 | Rip Rap Placement | Location - Excavation depth - assembly - Installed length | H | 1 check per structure | Visual Inspection | Conform to Specification | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.7 | Visual Structural Inspection | Visual inspection of Void Filled rip rap structutre | W | 1 per structure | Visual Inspection | Conform to Approved Drawings & Specification | Contractor's site diary/Photo's | Contractor
400.4 | Final Inspection | Engineer to inspect the final works | H | All locations scour protection is required | Visual Inspection | The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
Void Fill Rip-Rap Placement @ Stormwater Line 3 : SHEET 2129
400.4 | Base Soil | Prepared slope or channel bottom | W | All locations scour protection is required | Visual Inspection | No significant visual deformation | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.4 | Rip Rap Placement | Location - Excavation depth - assembly - Installed length | H | 1 check per structure | Visual Inspection | Conform to Specification | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.7 | Visual Structural Inspection | Visual inspection of Void Filled rip rap structutre | W | 1 per structure | Visual Inspection | Conform to Approved Drawings & Specification | Contractor's site diary/Photo's | Contractor
400.4 | Final Inspection | Engineer to inspect the final works | H | All locations scour protection is required | Visual Inspection | The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
Void Fill Rip-Rap Placement @ Stormwater Line 4 : SW Forebay : SHEET 2131
400.4 | Base Soil | Prepared slope or channel bottom | W | All locations scour protection is required | Visual Inspection | No significant visual deformation | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.4 | Rip Rap Placement | Location - Excavation depth - assembly - Installed length | H | 1 check per structure | Visual Inspection | Conform to Specification | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.7 | Visual Structural Inspection | Visual inspection of Void Filled rip rap structutre | W | 1 per structure | Visual Inspection | Conform to Approved Drawings & Specification | Contractor's site diary/Photo's | Contractor
400.4 | Final Inspection | Engineer to inspect the final works | H | All locations scour protection is required | Visual Inspection | The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
Void Fill Rip-Rap Placement @ Stormwater Line 5 : Swale 1: SHEET 2129
400.4 | Base Soil | Prepared slope or channel bottom | W | All locations scour protection is required | Visual Inspection | No significant visual deformation | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.4 | Rip Rap Placement | Location - Excavation depth - assembly - Installed length | H | 1 check per structure | Visual Inspection | Conform to Specification | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
400.7 | Visual Structural Inspection | Visual inspection of Void Filled rip rap structutre | W | 1 per structure | Visual Inspection | Conform to Approved Drawings & Specification | Contractor's site diary/Photo's | Contractor
400.4 | Final Inspection | Engineer to inspect the final works | H | All locations scour protection is required | Visual Inspection | The final surface shall be thoroughly wetted for good compaction and smoothed and compacted by vibrating equipment | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 500 Granular pavement
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 500 - Granular Pavement |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
500 | Setout, Materials and Preparation
500.1 | Determine Embankment / Subgrade Strength (Shoulder Top-up) | Proof Roll the excavated area | W | All areas of shoulder top-up. 1 Lot < 300m long. | NZS 4402.6.5.2 | No significant visual deformation under the wheel load CBR>10 | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
500.2 | Determine Embankment / Subgrade Strength (Pavement Widening) | Determine bearing strength of subgrade | W | 1 Scala per 20m of shoulder or | NZS 4402.6.5.2 | CBR >10 For design input | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
500.4 | Confirm SIL Material | SIL Aggregate | M | Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3 | Crushing Resistance MDD OMC CBR | Project Spec 2.2.10 | IANZ Report | Contractor | By IANZ accredited lab
500.4 | Confirm Subbase Material | Subbase Aggregate | M | Source properties: 1 test per source 4 weeks prior to use, repeat every 10,000m3 Production properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3 | PSD, SE, CI, PI, Broken Faces Crushing Resistance Weathering Resistance MDD OMC CBR | NZTA WHAP 65/ Project Spec 8.1.2 | IANZ Report | Contractor | By IANZ accredited lab
500.5 | Confirm Basecourse Material | Basecourse Aggregates | M | Source properties: 2 tests per source 4 weeks prior to use, repeat every 10,000m3 Produiction properties in stockpile: 0-1500m3 - 3 tests 1500-4000m3 - 4 tests >4000m3 1 test for every 1000m3 | PSD, SE, CI, PI, Broken Faces Crushing Resistance Weathering Resistance MDD OMC CBR | NZTA M4 / Project Spec | IANZ Report | Contractor | By IANZ accredited lab
Construction and Finshing
500.10. | SIL Layer Depth/Thickness | Scala/Infered CBR of Subgrade | H | All Subgrade Areas | Scala @3 points across carriageway @ 20m spacings | CBR<10 then SIL Layer = 600mm CBR <2 seek advice from engineer | Scala Recording Sheet | Contractor
500.9 | Pavement - (SIL Construction) | Maximum Dry Density | M | 5 per Lot (1,000 m2) | NZS 4402.4.1.3 | For analysis of DoC | IANZ Report | Contractor | By Contractor with random Verification by IANZ accredited lab
500.9 |  | Degree of Compaction | H | 5 per Lot (1,000 m2) | NZS 4407.4.2.1 | NZTA B02: DoC ≥ 95% with all >92% | IANZ Report | Contractor | By Contractor with random Verification by IANZ accredited lab
500.9 | Pavement - (Subbase Construction) | Maximum Dry Density | M | 5 per Lot (1,000 m2) | NZS 4402.4.1.3 | For analysis of DoC | IANZ Report | Contractor | By IANZ accredited lab
500.9 |  | Degree of Compaction | H | 5 per Lot (1,000 m2) | NZS 4407.4.2.1 | NZTA B02: DoC ≥ 95% | IANZ Report | Contractor | By IANZ accredited lab
500.9 | Pavement - (Basecourse Construction) | Maximum Dry Density | M | 5 per Lot (1,000 m2) | NZS 4402.4.1.3 | For analysis of DoC | IANZ Report | Contractor | By IANZ accredited lab
500.9 |  | Degree of Compaction | H | 5 per Lot (1,000 m2) | NZS 4407.4.2.1 | NZTA B02: DoC ≥ 98% | IANZ Report | Contractor | By IANZ accredited lab
500.10. | Surface Finishing Subbase | Check geometry of the placed fill is in accordance with the design. | H | All Subbase Areas | Suvey, Stringline dips @5 points across carriageway @ 20m spacings | Geometry is in accordance with design drawings . | Stringline Report | Contractor | Joint walkover between Contractor and Engineers Representative. All points to be within -25mm +5mm
500.10. | Surface Finishing Basecoarse | Check geometry of the placed fill is in accordance with the design. | H | All Basecoarse Areas | Suvey, Stringline dips @5 points across carriageway @ 20m spacings | Geometry is in accordance with design drawings . | Stringline Report | Contractor | Joint walkover between Contractor and Engineers Representative. All points to be within -5mm +15mm
500.10. | Surface Finishing | Roughness Requirements | M | Finished Sealed Surface | NAASRA Counts | Surface shape complies with Section 2 of NZTA TM7003. | IANZ Report | Contractor | Maximum NAASRA count of 70/100m with a target of 60/100m.
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 600 Seal Coat
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 600 - Seal Coat |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
600 | Setout, Materials and Preparation
600.1 | Seal Design | Seal design outling all design assumptions | H | 1 per seal application type | Review | New Zealand Chip Sealing Handbook | Seal design in contractor's site folder | Contractor
600.2 | Check raw materials | Sealing Aggregates | M | 1 per source stockpile | Source Properties | NZTA M06 / RNZ 9805:2009 | Certificate in contractor's site folder | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
600.3 |  | Sealing Aggregates | M | 1 per source stockpile | Production Properties | NZTA M06 / RNZ 9805:2009 | Certificate in contractor's site folder | Contractor
600.4 |  | Adhesion Agents | M | Prior to use |  | NZTA M06 / NZTA M13 | Certificate in contractor's site folder | Contractor
600.5 |  | Audit Samples | M | 20 kg per stockpile | TNZ M/20; TNZ M/7; TNZ M/24 | Stored in a sealed plastic bag in a covered environment | ITP | Contractor | Retain for testing if required
600.6 | Confirm sealing material | Visual inspection of surface to be sealed | W | per sealing schedule. 1 Lot = 1 day's production and < 1500m2 | TNZ M/20; TNZ M/7; TNZ M/24 | NZTA B02 | Contractor's site diary | Beca's Rep. | The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
600.7 |  | Dry back Moisture Content | H | 9 per Lot | NZS 4407.4.2.1 | DOS ≤ 80% preferably ≤ 70% | IANZ Report | Contractor | DOS required for all pavement before surface is sealed.
Construction and Finshing
600.8 | Sealing | Bitumen for Chip Sealing | M | 2 samples per distributor | Penetration grade testing | NZTA M01 - Tables 1, 2, 3 and 5 | Certificate in contractor's site folder | Contractor | Sampling as per ASTM D140 or equivalent
600.9 |  |  | M |  | Durability | NZTA M01 - Table 5 | Certificate in contractor's site folder | Contractor | Refer notes in clause 5 of NZTA M01
600.10 |  | Spraying Temperature | W | Ongoing with non-going heat sensing gauge | Non-contact heat sensing gun | NZTA P03 - Table 2 | ITP | Contractor
600.11 |  | Bitumen Application Rate | W | Per Sprayer, per Site, per run | E/2 Certificate. Spray Sheets | Current E/2 Certificate per Spray Run of Seal Design | E/2 Certificate. Spray Sheets | Contractor | Forms part of Quality Assurance requirements
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 700 Safety Barriers
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 700 - Safety Barriers |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
700 | Setout, Materials and Preparation
700.1 | Seal Design | Seal design outling all design assumptions | H | 1 per seal application type | Review | New Zealand Chip Sealing Handbook | Seal design in contractor's site folder | Contractor
700.1
700.2 | Leading and trailing treatments | Start and End locations marked out and agreed with Engineer's rep. | H | All barrier lengths | Visual Inspection | Positions in agreed marked out location | Check sheet | Contractor
700.3 |  | Correct type | H | All barrier lengths | Visual Inspection | Types as specified on drawings | Check sheet | Contractor | Engineer Rep to be aware of point where LON starts for terminal being used and account for it if possible.
Construction and Finshing (W-Section Barriers)
700.4 | Ground conditions testing | Bearing strength of foundation depth | H | 1 Scala every 20m - All leading and terminal ends Or as directed by the Engineer | NZS 4402.6.5.2 | For design input | Scalar test sheet / previous layer testing | Contractor | Test results provided to Eng.Rep. for analysis. BBo provides foundation size details
700.5 | Pile position | Pile position | M | All piles | Visual Inspection | Sufficient supporting slope outside the line of the posts in relation to pile size | Check sheet | Contractor
700.6 |  | Pile spacing | M | All piles | Visual Inspection | Post spacing's as per the Construction Drawings or NTCs | Check sheet | Contractor
700.7 |  | Post orientation | M | All piles | Visual Inspection | Slot orientation consistent for the entire length of the barrier | Check sheet | Contractor
700.8 | Installed WSB system | Barrier section at correct position as per manufacturer's installation manual | M | All posts | Visual Inspection | Barrier is at correct height and secured correctly | Check sheet | Contractor
700.9 |  | All cables are tensioned correctly | M | All barrier lengths | Visual Inspection | As per manufacturer's installation manual | Check sheet | Contractor
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 800 Road Lighting
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 800 - Road Lighting |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
800 | Setout, Materials and Preparation
800.1 | Mark out works | Set out fencing alignment and extents on site | H | All lighting columns and associated cabling | Visual Inspection | N/A | Contractor's site diary | Contractor
800.2 | Underground services | Identify and positively locate services | H | All lighting columns and associated cabling | Hydoexcavation | N/A | Drawings | Contractor
800.3 | Lighting Column Waranty Certificates | Contractor to provide design and warranty information for nominated lighting columns and luminares | H | Prior to commencing works | N/A | Engineer to review and approve proposed lighting columns and luminaries | NTC / Site instruction | Contractor
Construction and Finshing (W-Section Barriers)
800.4 | Electrical Certificates | Contractor to provide electrical certification information for all electrical works installed | H | All lighting columns and associated cabling | TNZ M/20; TNZ M/7; TNZ M/24 | Engineer to review and approve electrical certificates | NTC / Site instruction | Contractor
800.5 | Completed road lights | Visual inspection of completed road lighting installations | H | All lighting columns and associated cabling | TNZ M/20; TNZ M/7; TNZ M/24 | Compliance with project specifications | NTC / Site instruction | Contractor
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.

## 900 Fencing
|  |  |  | INSPECTION AND TEST PLAN |  |  |  |  | ITP No: Project # - dd mm yyyy
|  |  |  | Project: xxxx - |  |  |  |  | Date submitted: dd/mm/yyyy
|  |  |  | Construction Process: General Contract |  |  |  |  | Prepared By: Inframax Construction
Client: NZTA |  | Head Contractor Subcontractor |  | Specification: 900 - Fencing |  |  |  |  | Approved By:
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by
|  | Detail of Activity | Action (Hold, Monitor, Witness) | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) | Inspection / Test method |  |  |  |  | Engineer | Contractor | Date
900 | Setout, Materials and Preparation
900.1 | Mark out works | Set out fencing alignment and extents on site | H | All proposed fences | Visual Inspection | N/A | Contractor's site diary | Contractor
900.2 | Underground services | Identify and positively locate services | H | All proposed fences | Hydro excavation | N/A | Drawings | Contractor
900.3 | Confirm fencing Details | Contractor to confirm fencing details and nominated Supplier. Also confirm fencing meets the landowner agreement | H | Prior to commencing works | N/A | Engineer to review and approve proposed culvert supplier and methodology | NTC / Site instruction | Contractor | This requirement confirms the Contractors fencing methodology and supply is in accordfance with the performance specification and TNZ F4:1975
Construction and Finshing (W-Section Barriers)
900.4 | Post and Wire Fence | Constructing new or relocating boundary fences | H | All proposed fences |  | TNZ F4: 1975 | NTC / Site instruction | Contractor | As per the design drawings and specifications.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
BBO Engineers Rep Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.