## res_ITP-01-012 - Hot Mix Asphal
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 1 Soil Nails, Tecco Mesh | itp |  |  |  |  | ITP 1 Soil Nails, Tecco Mesh
section | A. Preliminary
checkpoint | A1
label | Description - Ensure design is complete and "Issued For Construction" (IFC) drawings are accurate, complete, and approved by GSI Engineer & GSI Management
label | Frequency - Before issue to site
label | Specification Reference - Job pack
label | Responsible Person - GSI Project Manager
label | Record Required - Job Pack
label | Notes - Hard copies on site
checkpoint | A2
label | Description - Confirm all material intended for use in the works comply with design specification, have been ordered, and will be available on site when required
label | Frequency - Before site establishment
label | Specification Reference - Job pack
label | Responsible Person - GSI Construction Manager / Site Engineer
label | Record Required - Job pack
checkpoint | A3
label | Description - Load test schedule, test locations and test sheets are reviewed and approved by GSI Engineer and Engineer to contract
label | Frequency - Prior to start on site
label | Specification Reference - NZTA 2226 TS
label | Responsible Person - GSI Project Engineer
label | Record Required - Engineer to contract agreement in writing
label | Notes - Hard copy of standard held on site
checkpoint | A4
label | Description - Ensure load testing equipment is calibrated and calibration certificates supplied to Engineer to contract for review
label | Frequency - Prior to start on site
label | Specification Reference - NZTA 2226 TS
label | Responsible Person - GSI Project Engineer
label | Record Required - Engineer to contract receipt
label | Notes - Hard copy of standard held on site
checkpoint | A5
label | Description - Slope assessment completed and reviewed by GSI Project Manager
label | Frequency - Prior to start on site
label | Specification Reference - N/A
label | Responsible Person - GSI Project Engineer
label | Record Required - Slope assessment checksheet
label | Notes - Hard copy on site
checkpoint | A6
label | Description - Confirm site extents agreed with Engineer and aligns with general intent of the design
label | Frequency - Prior to start on site
label | Specification Reference - N/A
label | Responsible Person - GSI Project Engineer
label | Record Required - Written confirmation to design team
checkpoint | A7
label | Description - Sacrificial test nail number and locations agreed and approved by GSI PDE/BBO/Earthtec
label | Frequency - Prior to start on site
label | Specification Reference - N/A
label | Responsible Person - GSI Project Manager
label | Record Required - Engineer to contract agreement in writing
checkpoint | A8
label | Description - Pre-construction sign off - Subcontract agreement signed, TMP approved, all staff and subcontractors inducted, CMP reveiwed and in place
label | Frequency - Prior to start on site
label | Specification Reference - N/A
label | Responsible Person - GSI General Manager
label | Record Required - Job pack signed
label | Notes - Document reviewed and signed off by site staff and required management .
checkpoint | A9
label | Description - Permit to Work/Excavate - Confirm location and extent of works, notify service authorities, locate underground services where applicable, notify Worksafe of notifiable works
label | Frequency - Before commencing work
label | Specification Reference - N/A
label | Responsible Person - GSI Project Manager
label | Record Required - Job pack signed
checkpoint | A10
label | Description - Plant - Ensure plant suitable for use on site and calibration up to date. Rig capable of reaching all anchor locations, sufficient wire rope and rig anchoring equipment
label | Frequency - Before commencing work
label | Specification Reference - N/A
label | Responsible Person - Site supervisor
label | Record Required - Job pack signed
checkpoint | A11 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
holdpoint | HOLD POINT
section | B. Site Establishment
checkpoint | B1
label | Description - Check Erosion & Sediment Controls are in place and adequate
label | Frequency - Before commencing work
label | Specification Reference - Job pack
label | Responsible Person - Site supervisor
label | Record Required - Photos / drawings
label | Notes - Visual inspection
checkpoint | B2
label | Description - Establish lay down area and suitable protection of property (ply wood, tarps etc) and bunding around grout unit/refuelling areas as required
label | Frequency - At time of establishment
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Photos. Note on Pre-Start form
label | Notes - Consider delivery of materials
checkpoint | B3
label | Description - Check slope stability, area is safe to work in for slope remediation crews (WAH permit in place)
label | Frequency - Daily prior to accessing lower levels
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Photos. Note on Pre-Start form
label | Notes - Install offset pegs
checkpoint | B4
label | Description - Notify tenants / land users below work site of intended work and likely duration
label | Frequency - At time of establishment
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Note on Pre-Start form
label | Notes - Door knock and face to face discussion required.
checkpoint | B5
label | Description - Completed installation of approved rope access anchor points as required
label | Frequency - At time of establishment
label | Specification Reference - N/A
label | Responsible Person - Site supervisor
label | Record Required - Photos. Note on Pre-Start form
checkpoint | B6
label | Description - Before You Dig completed. Identify and mark location of any existing services including probing, potholing and survey as required
label | Frequency - At time of establishment
label | Specification Reference - N/A
label | Responsible Person - Project Engineer and Site supervisor
label | Record Required - Written confirmation to client
label | Notes - Install offset pegs, mark on drawings
checkpoint | B7
label | Description - Site markout - GSI Engineer, GSI PDE and Engineer to contract to agree on nail and test nail set out plan
label | Frequency - Before commencing work
label | Specification Reference - N/A
label | Responsible Person - GSI Project Engineer & GSI PDE
label | Record Required - Engineer to contract agreement in writing
label | Notes - Install offset pegs, mark on drawings
checkpoint | B8 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | Frequency - Before commencing work
holdpoint | HOLD POINT
section | C. Excavations/Slope trimming
checkpoint | C1
label | Description - Valid Permit to Dig/SWMS
label | Frequency - Daily
label | Specification Reference - N/A
label | Responsible Person - Project Engineer
label | Record Required - Permit signed and valid
checkpoint | C2
label | Description - Pre-start check on equipment
label | Frequency - Daily
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Daily Equipment Pre-start form completed by operator
checkpoint | C3
label | Description - Safety audit completed when trimming/scaling slope - not to impact people or property below slope
label | Frequency - Daily
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Aduit results sent to PM
checkpoint | C4
label | Description - Levels and extents of devegatation and slope trimming marked and checked
label | Frequency - Prior to excavating
label | Specification Reference - Drawings
label | Responsible Person - Project engineer and site supervisor
label | Record Required - Photo
checkpoint | C5
label | Description - GSI Engineer / GSI PM to sign off on completed vegatation and slope trimming
label | Frequency - At completion of earthworks
label | Specification Reference - N/A
label | Responsible Person - GSI PDE and GSI PM
label | Record Required - Confirm with client
checkpoint | C6 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | Description -
label | Frequency - Before commencing work
holdpoint | HOLD POINT
section | D. Soil Nails and Grouting
checkpoint | D1
label | Description - Pre-start check on equipment
label | Frequency - Daily
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Daily Equipment Pre-start form completed by operator
checkpoint | D2
label | Description - Valid Permit to Dig/SWMS
label | Frequency - Daily
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Permit signed by operator and Site Superivisor and valid
checkpoint | D3
label | Description - Confirm cement/water mix ratio including number bags cement needed versus water capacity of mixer
label | Frequency - Prior to drilling
label | Specification Reference - Confirm ratio / IFC drawings / Specification
label | Responsible Person - Site Supervisor
label | Record Required - Grout log
label | Notes - Engineer to contract to confirm in writing
checkpoint | D4
label | Description - Drill methodology approved by GSI PDE/GSI Engineer and Engineer to contract confirmed following review of proof test results
label | Frequency - Prior to production nail installation
label | Specification Reference - Engineer to contract
label | Responsible Person - Project Engineer
label | Record Required - Written confirmation designer
label | Notes - Engineer to contract to confirm in writing
checkpoint | D5 - HOLD POINT - Ensure soil nail setout is in accordance with the drawings and approved by BBO/Earthtec
label | Description -
label | Frequency - Prior to drilling
label | Specification Reference - Drawings
label | Responsible Person - Project Manager / GSI PDE
label | Record Required - Written confirmation to client
holdpoint | HOLD POINT
checkpoint | D6
label | Description - Confirm drill depth, angle and orientation of soil nails - per IFC drawings
label | Frequency - Each nail
label | Specification Reference - Drawings
label | Responsible Person - Site Supervisor
label | Record Required - Drill log
label | Notes - Mark on as-built drawings
checkpoint | D7
label | Description - Ensure grout sample cubes or cylinders are available and ready for use (4 per day of grouting)
label | Frequency - Prior to drilling
label | Specification Reference - GSI grout sampling procedure
label | Responsible Person - Site Supervisor
label | Record Required - Grout log
label | Notes - All GSI staff to review updated Grout Samplign SOP prior to start of works
checkpoint | D8
label | Description -
label | • Install sacrifical anchors: 1 x 9m anchor and 1 x 6m anchor with Grouted Bond Length of 4m ONLY.
label | • Anchors to be installed with 16mm tremmie line, with centralizers every 1.5m. Locations to be confirmed by GSI Engineer and Engineer to contract (per B7).
label | Frequency - During drilling
label | Specification Reference - NZTA 2226 TS (181220)
label | Responsible Person - Project Engineer
label | Record Required - Photo, Test result sheet
label | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint | D9
label | Description -
label | • Drill logs (fully) complete, including hole ID, diameter and length of hole drilled - as well as geology i.e. colour, type (rock/soil), moisture (i.e. dry, slightly moist, wet).
label | • Ensure to stipulate which holes are to be used for test anchors - based on B7.
label | Frequency - During drilling
label | Specification Reference - NZTA 2226 TS (181220)
label | Responsible Person - Project Engineer
label | Record Required - Photo, Test result sheet
label | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint | D10
label | Description -
label | • Anchor testing to follow NZTA 2226 TS test schedule at min 7 days after install. For both 6m and 9m anchors.
label | • Pullout Creep test per NZTA 2226 TS test schedule i.e. 60 min creep test at 110kN. If pullout has not occurred at 150kN, proceed to next load. Do not exceed 250kN.
label | Frequency - During drilling
label | Specification Reference - NZTA 2226 TS (181220)
label | Responsible Person - Project Engineer
label | Record Required - Photo, Test result sheet
label | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint | D11 - HOLD POINT - NO WORK TO COMMENCE UNTIL SACRIFICAL TEST RESULTS REVIEWED BY ENGINEER
label | Frequency - Before commencing work
holdpoint | HOLD POINT
checkpoint | D12
label | Description -
label | • Install 78 no Anchors, in a top down methodology, 18 x 9m RB32 (top row) Anchors, 58 x 6m RB32 anchors. Anchors to be installed with 16mm tremmie line, with centralizers every 1.5m.
label | • Suitability testing on 5% of installed nails to 150% design working load. 2 x 9m and 3 x 6m suitability anchors to have 1m temporary debonded length for suitability testing. Locations to be confirmed by GSI Engineer and Engineer to contract (per B7).
label | Frequency - During drilling
label | Specification Reference - Drawings/NZTA 2226 TS
label | Responsible Person - Project Engineer
label | Record Required - Photo, Test result sheet
label | Notes - Results to be reviewed by GSI Engineer and Engineer to contract
checkpoint | D13 - HOLD POINT - NO WORK TO COMMENCE UNTIL SUITABILITY TEST RESULTS REVIEWED BY ENGINEER
label | Frequency - Before commencing work
holdpoint | HOLD POINT
checkpoint | D14
label | Description - Acceptance testing on 25% of installed nails to 100% design working load
label | Frequency - After Drilling
label | Specification Reference - NZTA 2226 TS (181220)
label | Responsible Person - Project Engineer
label | Record Required - Photo, Test result sheet
label | Notes - Results to be reviewed by Engineer to the contract and GSI Engineer
checkpoint | D15
label | Description -
label | • Grout sampling to follow relevant SOP i.e. tamping down in 1/3 lifts, and stored in supplied chilly bin after initial 12 hours of curing.
label | • Temperature in chilly bin is to remain as constant as practicable (avoid uneccesarily opening lid).
label | Frequency - During drilling
label | Specification Reference - GSI grout sampling procedures
label | Responsible Person - Site Supervisor
label | Record Required - Grout log
checkpoint | D16
label | Description - Grout samples to be delivered to the lab within 2 days of sampling, where practicable, or as soon as possible thereafter.
label | Frequency - During drilling
label | Specification Reference - GSI grout sampling procedures
label | Responsible Person - Site Supervisor
label | Record Required - Grout log
checkpoint | D17
label | Description - Grout mud balance testing - per relevant SOP
label | Frequency - Per hour during grouting session
label | Specification Reference - GSI grout sampling procedures
label | Responsible Person - Site Supervisor
label | Record Required - Grout log
checkpoint | D18
label | Description -
label | • Grout logs i.e. number of grout bags per hole and total.
label | • Volumes to be recorded for each sol nail anchor.
label | • Ensure nails are appropriately numbered with relevant ID.
label | Frequency - Each grout session
label | Specification Reference - N/A
label | Responsible Person - Batching Operator and Project Engineer
label | Record Required - Grout log
checkpoint | D19
label | Description -
label | • Grout top-up complete.
label | • Where necessary, dry pack grout behind plates where grout not in contact with plate. Ensure temporary debonded sections of acceptance test nails are topped up.
label | • Update grout logs with those test nails that have been topped up.
label | Frequency - Each grout session
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Photo
checkpoint | D20
label | Description - Soil nail sacrifical, suitability and acceptance tests complete (as above) - per IFC drawings/NZTA 2226 specification
label | Frequency - 2 nails, 5% of nails (or min. 5), and 25% of nails
label | Specification Reference - Drawings
label | Responsible Person - Project Engineer
label | Record Required - Test result sheets
checkpoint | D21 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | Frequency - Before commencing work
holdpoint | HOLD POINT
section | E. TECCO Mesh, Spider Plate and Bio Coir
checkpoint | E1
label | Description - Confirm extents of mesh to be installed
label | Frequency - Prior to commencement
label | Specification Reference - Drawing
label | Responsible Person - GSI Project Engineer and Site Supervisor
label | Record Required - Email to PM
checkpoint | E2
label | Description - Confirm that depressions for spike plates have been SUITABLY excavated around nail collars.
label | Frequency - Daily
label | Specification Reference - Manufacturers Guidelines
label | Responsible Person - Site Supervisor
label | Record Required - Photo
checkpoint | E3
label | Description - TECCO mesh installed as per manufacturers guidelines. Ensure wire ropes are installed on top and bottom edges of mesh and tensioned appropriately.
label | Frequency - Daily
label | Specification Reference - Manufacturers Guidelines
label | Responsible Person - Site Supervisor
label | Record Required - Photo
checkpoint | E4
label | Description - Cirtex Bio-Core installed as per manufacturers guidelines.
label | Frequency - Daily
label | Specification Reference - Manufacturers Guidelines
label | Responsible Person - Site Supervisor
label | Record Required - Photo
checkpoint | E5 - HOLD POINT - NO WORK TO COMMENCE UNLESS THESE ARE COMPLETE
label | Frequency - Before commencing work
holdpoint | HOLD POINT
section | G. Sign-Off and QA deliverables
checkpoint | G1
label | Description - Drill and Grout logs
label | Frequency - Daily
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor
label | Record Required - Drill and grout logs
checkpoint | G2
label | Description - Sacrificial, Suitability and Acceptance test nails
label | Frequency - Per IFC drawings/NZTA 2226 TS
label | Specification Reference - NZTA 2226 TS
label | Responsible Person - Project Engineer
label | Record Required - Test log sheets
checkpoint | G3
label | Description - Grout crushing test
label | Frequency - 7, 14 and 28 day results
label | Specification Reference - 30MPa at 28 days
label | Responsible Person - Project Engineer
label | Record Required - Test reults
label | Notes - 7 and 14 day results are indicative only
checkpoint | G4
label | Description - Photo records
label | Frequency - Daily
label | Specification Reference - N/A
label | Responsible Person - Site Supervisor and Project Engineer
label | Record Required - Photos
checkpoint | G5
label | Description - As-Built Drawings
label | Frequency - Project Completion
label | Specification Reference - N/A
label | Responsible Person - Project Engineer
label | Record Required - Updated Drawings
checkpoint | Close out - Sign and Date When Action Complete
textbox | Project Engineer:
textbox | Project Manager:
textbox | Client:
textbox | Supervisor:
textbox | Construction Manager:
signoff | Add Signature