## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | b9bf7f79-d9a0-4e10-834d-455feecd8e7b |  | checklist | Fan Rough In |  |  |  |  | Yes | Fan Rough In | 1842c81a-4da7-4bf6-9cff-1a8f7d451792
checkpoint-status | a9735240-c924-4f6a-9a3d-f7ddb4e20940 |  | checkpoint | Fan Model Number matches shop drawings & tech data
checkpoint-status | 4f07377e-a28e-49fb-bd42-8e7eb5b8bbcf |  | checkpoint | Fan installed Level & Seismic installed
checkpoint-status | 56bdbdfb-d4fc-435f-8358-c5ad18d32ef5 |  | checkpoint | Backdraught damper fitted
checkpoint-status | 389084d2-4e49-474f-8293-ed146fafe22b |  | checkpoint | Unit labelled with designation
checkpoint-status | 4f8a427e-0e95-4d28-9b5a-43becc2ce56a |  | checkpoint | Filters Fitted if applicable
checklist-flat | 77a3e8e0-d2bf-4f46-98be-e2b89988f6e4 |  | checklist | Fan Commissioning |  |  |  |  | Yes | Fan Commissioning | 444abcf4-c6e5-4360-9ee0-baab409eae5c
checkpoint-status | e95d765b-5d54-4dcc-b516-cbc2465ff57b |  | checkpoint | Electrical/Controls Operational
checkpoint-status | bd259d5f-bacd-40b6-a868-ac81d69c921a |  | checkpoint | Check For Vibration And Noise
checklist-flat | 52c426bc-2879-4b79-ab9b-d9be525aed89 |  | checklist | Project Details |  |  |  |  | Yes | Project Details | 497165a3-4ca0-4112-a110-2708365604c3
checkpoint-status | a3f212d1-74f7-43f9-8645-2fa6c6235751 |  | checkpoint | Project Details: 341 George St Fitzroy
label | 7ca8fc28-cf04-5e4d-9528-9840744bf402 |  | note | Project Number: 852
label | fbd2b8c0-4eda-5b38-ab0d-aa2506d5fe10 |  | note | Builder: Amber Property Group
label | f3919a09-77bb-5641-a444-447ac7c40f20 |  | note | Project Manager: Leroy Thomas
checklist-flat | a6e6ebd0-9176-492d-aefc-401bff07d058 |  | checklist | Split Commissioning |  |  |  |  | Yes | Split Commissioning | 68cc2f29-c3f2-462e-bfc8-dd231b559df9
checkpoint-status | 3a8f2bdb-0173-423c-9d2f-e404a93a567e |  | checkpoint | Drain checked
checkpoint-status | ac61cc09-280a-4123-ac86-e439fb540321 |  | checkpoint | Electrical/Controls Operational
checkpoint-status | e3f5b06c-4d9a-4858-b1aa-ab7c7d9614a5 |  | checkpoint | Unit Operating Heat/Cool Fan Operation
checkpoint-status | 9c95c3c2-10fe-4c94-ba63-006541224f1d |  | checkpoint | Check For Noise And Vibration
checkpoint-status | a013e6a3-a1d9-4e35-ad38-b0cbd0cc8ce1 |  | checkpoint | Unit Model Number matches shop drawings & tech data
checkpoint-status | f37e0d0e-56fd-4dd0-9ad3-95fa63690556 |  | checkpoint | Unit installed Level
checkpoint-status | 0daa5e15-e07c-4a0f-93eb-8550c5768580 |  | checkpoint | Check Pressure Test @ 400psi
checkpoint-status | 088341cd-0b09-47b6-be1c-7dc934e9cc0e |  | checkpoint | Unit labelled with designation
checkpoint-status | c31b2928-627a-4f26-a8e7-efb837109796 |  | checkpoint | Vac tested including drop test
checkpoint-status | 4b0e5fbf-58bf-4483-989c-6495d51809bc |  | checkpoint | Refrigerant added & recorded
checklist-flat | e0f1a413-c653-4906-a5b8-6d75ae36040c |  | checklist | Ducted Commissioning |  |  |  |  | Yes | Ducted Commissioning | 743b8a73-bd59-4365-ab90-2d39b9bcbe2d
checkpoint-status | c734707d-0127-4b31-a48b-ba75bc2acd71 |  | checkpoint | Drain checked
checkpoint-status | d8f2e0e2-f1db-487f-b94c-d40ce5131aab |  | checkpoint | Electrical/Controls Operational
checkpoint-status | 85291407-d4c0-4bc0-9ed4-8ea9cf7c9b4b |  | checkpoint | Unit Operating Heat/Cool Fan Operation
checkpoint-status | 78aea788-7f23-4ff8-a5c4-e0783f4ea5fa |  | checkpoint | Check For Noise And Vibration
checklist-flat | 247d2292-5837-4303-97c5-e77e65c991e1 |  | checklist | Fan Fit Off |  |  |  |  | Yes | Fan Fit Off | 9a3fc7d1-b02c-455f-9855-51df381d84cb
checkpoint-status | 97370081-1f99-4c0b-b90b-dbaab0c3a8b1 |  | checkpoint | Registers Fitted square / aligned
checkpoint-status | ad77e69d-b9f7-4b85-a635-91367f1b97ba |  | checkpoint | Registers cleaned as required
checkpoint-status | 2c929d34-1e3d-40dd-b87f-8f5a700e83b6 |  | checkpoint | External Louvres Sealed
checklist-flat | 80183bba-a20c-4f4b-b17f-440bcfa7c6b4 |  | checklist | Ducted Rough In |  |  |  |  | Yes | Ducted Rough In | 9b794965-dc9d-488a-8b1f-ebe8939d364c
checkpoint-status | 9bd4285d-c435-435f-b3f5-385be3a0997e |  | checkpoint | Unit Model Number matches shop drawings & tech data
checkpoint-status | 4f1846a4-9f87-45d3-a1c9-a3ac5cb70e13 |  | checkpoint | Unit installed Level & Seismic Installed
checkpoint-status | 084fe416-0b44-4359-9713-4f65e961f012 |  | checkpoint | Supply & return transitions installed
checkpoint-status | c3f3a199-bca2-4b76-858b-f258b251485c |  | checkpoint | Supply & return Flex installed
checkpoint-status | 527d15ba-cc75-4430-a52f-69cd84a983d4 |  | checkpoint | Cushion heads installed & marked out
checkpoint-status | da9160b4-4437-4d1f-bad0-47743b9d048d |  | checkpoint | Condensate Drain Run On Grade To T/D
checkpoint-status | 5ff01938-7340-480f-82a4-471d5775d990 |  | checkpoint | Hose Clamps installed on unit drain connection
checkpoint-status | f42ac0af-fc9a-4723-907d-1ce3f659b733 |  | checkpoint | Pipework insulation socks installed
checkpoint-status | db967541-f3e9-4117-8636-58f36355f9a7 |  | checkpoint | Filters Fitted
checkpoint-status | 740b8a62-f88f-436c-8bdd-76626c433d06 |  | checkpoint | Electrical Wiring & Isolator by Site Electrician installed
checkpoint-status | c1d1b478-1b5e-40e1-b4c9-27e4e9af455e |  | checkpoint | Electrical connection from isolator to indoor fitted off
checkpoint-status | 9303ebcb-605e-43ce-816c-c1c445e320bb |  | checkpoint | Control Cabling roughed in
checkpoint-status | 886bbcd1-68c0-47cc-a9ba-eb2ee7f257ba |  | checkpoint | Access Panels For Future Servicing marked on drwgs
checkpoint-status | ea469ca0-3c75-44c3-8b88-ec8a7119d523 |  | checkpoint | Unit addressing completed by Mech Elec
checklist-flat | 281174b9-ccc2-45fa-93e7-499caf871ce6 |  | checklist | Penetration |  |  |  |  | Yes | Penetration | a2e62476-f031-4299-9a34-fea150f47acf
checkpoint-status | c440946b-51b6-4e40-a462-02cd6c3444d0 |  | checkpoint | Please take photo of label
checklist-flat | 145f0bb8-6d15-4d51-9081-7c753c6c30ff |  | checklist | Condenser Unit |  |  |  |  | Yes | Condenser Unit | a4dd10d5-d106-4ad8-87d6-de5fffaa9bed
checkpoint-status | 0b2dd77e-be30-4905-b8de-ccb29581b64a |  | checkpoint | Unit Model Number matches shop drawings & tech data
checkpoint-status | 88e28884-8c90-4296-bf34-5901be6d916e |  | checkpoint | Unit installed Level & Seismic Installed
checkpoint-status | 26a45ac9-96a6-4cb0-95cc-5322a9c869f6 |  | checkpoint | Install Pipework At Condensers As Per Schematic
checkpoint-status | 4aefd1e8-e014-4721-b6ba-c4e0edd6d213 |  | checkpoint | Pipework Pressure Tested @400 psi
checkpoint-status | 8fbc0f99-5bf3-4cfc-8ab6-b84ab42fbba7 |  | checkpoint | External pipework capped/protected
checkpoint-status | 4d1897d2-6036-406e-a0dd-54651314fa48 |  | checkpoint | Drain tray fitted under condenser or drain kit connected
checkpoint-status | 70e2a5d0-4098-46a6-add2-dd41e43a77dc |  | checkpoint | Drain to point of discharge installed on grade
checkpoint-status | e3add01a-47de-47ce-8919-e5550f4fbc08 |  | checkpoint | Unit labelled with designation
checklist-flat |  |  | checklist | New Checklist: |  |  |  |  | Yes | Add New Checklist | b085cd2c-7d4c-4f2c-ae44-e408cf18d7d7
checkpoint-status |  |  | checkpoint | Attach photos, files and comments as required - pass once complete
checklist-flat | 30f6e8b5-23a2-4f16-b52e-90a3cdfeae9a |  | checklist | Split Fit Off |  |  |  |  | Yes | Split Fit Off | b63da830-9adb-450a-8f24-ef8af9adb809
checkpoint-status | b90c01e7-f6a0-4542-a210-02fc85ee7aad |  | checkpoint | Unit Model Number matches shop drawings & tech data
checkpoint-status | 4a5e14c3-69e4-47a2-bafd-f3a3396e720b |  | checkpoint | Unit installed Level
checkpoint-status | 260860a2-1b8a-42e8-9a85-c06cec4578ae |  | checkpoint | Drain & or pump check
checkpoint-status | 207b541c-17e1-4728-a5fb-f78410b53ac8 |  | checkpoint | Controller fitted to wall &/or Wall controller installed
checklist-flat | f2344256-b639-4952-b563-bff0947c5d90 |  | checklist | Split Rough In |  |  |  |  | Yes | Split Rough In | dd3745c0-d911-4620-97aa-473e81bb9f82
checkpoint-status | a68ce135-75b5-4d49-afd8-c8814a846352 |  | checkpoint | Drain roughed in to correct indoor unit location
checkpoint-status | aa042b36-cef0-4ade-ac14-881949747f8c |  | checkpoint | Condensate Drain run On Grade To T/D
checkpoint-status | a6dc651c-fe5f-40ed-9000-e806ba7091e6 |  | checkpoint | Condensate Pump Roughed In If Required including tubing
checkpoint-status | f2daf70d-29f8-4105-934f-56a859075f64 |  | checkpoint | Pipework roughed in to correct location
checklist-flat | 2712c541-88bc-422e-acc9-ce47a6c16f92 |  | checklist | Fire Treatment |  |  |  |  | Yes | Fire Treatment | dd6d3eab-0396-406d-b8d7-a9618651df2c
checkpoint-status | 68eb7490-6d26-49b2-bc80-942710aefce5 |  | checkpoint | All Fire Penetrations sealed with Approved Method
checkpoint-status | 7fb8fbe5-c89b-4f15-86f4-08e6751f2bd3 |  | checkpoint | All Fire Damper Access Panels Clear Of Obstruction
checkpoint-status | 706dce38-8bca-41fc-b8e4-2a79d46c33f6 |  | checkpoint | Ductwork fire treatment completed
checkpoint-status | 68324902-edf4-4729-a793-2fc465b72470 |  | checkpoint | Fire Penetrations labelling completed
checkpoint-status | 61f4f11d-1723-4793-a56d-5b8225ffb380 |  | checkpoint | Detailed on shop drwgs & referenced with photo in CONQA
text | eb5db61e-7580-5326-8a1c-8a4b074c115f |  | textbox | Penetration No.
checklist-flat | b0184510-1980-4898-91d6-10232c7f0095 |  | checklist | Ducted Fit Off |  |  |  |  | Yes | Ducted Fit Off | f7153450-f86f-41b4-941a-de6fade6c555
checkpoint-status | 0097979e-a9c8-4381-8e5b-eb378ef69068 |  | checkpoint | Registers Fitted square / aligned
checkpoint-status | 562f9f81-8ab5-4aaf-8527-83e2e3242bc1 |  | checkpoint | Registers cleaned as required
checkpoint-status | 2f623d9b-ac5c-451d-92ca-79376c987ca6 |  | checkpoint | Electrical wiring fitted off
checkpoint-status | 5a049934-b919-45e2-ab4f-205a8d8f05cc |  | checkpoint | Wall controller fitted off
checkpoint-status | 888965de-9700-4010-bcf5-f01c23f198a4 |  | checkpoint | Check tundish is complete
checkpoint-status | fc7abc28-1985-4b3d-9e62-df004c54e8c1 |  | checkpoint | Unit labelled with designation